## NABARD
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding: NABARD | [8 empty] | Month : May 2023
Sl. no | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the Month |  | Overall cumulative achievement |  | Remarks
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
1 | Const.of BUSG Composite Bridges over R.Chepte on Bilkhawthlar to Saiphai Road | 508.45 | Kolasib Division | 24.6.19 | 31.03.22 | 41% | 128.5 | - | - | 41% | 128.5 | The cost column is being merged as revised quantity calculation for supplimentary agreement is being done due to the increase in span of the bridge
2 | Const.of BUSG Composite Bridges over R.Sesih on Bilkhawthlar to Saiphai Road | 281.12 | Kolasib Division | 24.6.19 | 31.03.22 | 41% | 90.94 | - | - | 41% | 90.94 | Formwork of Abutment Cap being prepared
3 | Design & Construction of T-Beam Bridge Package-II at Bulung River (CH:10.20 KMP) | 996 | Kolasib Division | 24.12.21 | 24.06.23 | - | - | - | - | - | - | Site preparation for Bridge Abutment completed. However, detail report, design, sub soil investigation etc.not yet submitted by the contractor
4 | Design & Construction of T-Beam Bridge Package-II at Damdiai River (CH:23.50 KMP) | 996 | Kolasib Division | 24.12.21 | 24.06.23 | - | - | - | - | - | - | Location of Bridge Abutment finalised in principle
5 | Design & Construction of T-Beam Bridge Package-I at Chhimluangte River (CH:0.450 KMP) | 969 | Kolasib Division | 18.12.21 | 18.06.23 | 12% | 28.56 | - | - | 12% | 28.56 | Demolision of inferior abutment completed and the contractor is instructed to resume the work immediately
6 | Design & Construction of T-Beam Bridge Package-I at Dumkhel River (CH:5.50 KMP) | 969 | Kolasib Division | 18.12.21 | 18.06.23 | 6% | - | - | - | 6% | -
7 | Const.of Meidum to Hortoki Road Phase -II (Km 9.100 to Km 26.000) SH: Earthworks and Permanent works from Km 9.100-Km 13.325) Package -I | 1087.32 | Kolasib Division | 24.12.21 | 24.06.23 | 81% | 839.99 | - |  | 81% | 839.99 | Work in progress
8 | Const.of Meidum to Hortoki Road Phase -II (Km 13.325 to Km 17.500 SH: Earthworks and Permanent works from Km 13.325 to Km 17.500) Package -II | 1171 | Kolasib Division | 25.12.21 | 25.06.23 | 65% | 562.23 |  |  | 65% | 562.23 | Work in progress
9 | Const.of Meidum to Hortoki Road Phase -II (Km 17.500 to Km 21.725 SH: Earthworks and Permanent works from Km 15.690 to Km 19.005) Package -III | 1422 | Kolasib Division | 18.12.21 | 18.06.23 | 76% | 1054.73 | - |  | 76% | 1054.73 | Work in progress
10 | Const.of Meidum to Hortoki Road Phase -II (Km 21.725 to Km 26.000 SH: Earthworks and Permanent works from Km 19.005 to Km 22.360) Package -IV | 959 | Kolasib Division | 24.11.21 | 08.06.23 | 80% | 726.91 |  |  | 80% | 726.91 | Work in progress
11 | Construction of Meidum to Hortoki Road Phase - II (Km 9.100 to 26.000)Package I | 2390.08 | Kolasib Division | 03.08.22 | 03.08.23 | 0.14% | 440.93 | - | - | 0.14% | 440.93 | Work in progress
12 | Construction of Meidum to Hortoki Road Phase - II (Km 9.100 to 26.000) Package II | 2390.08 | Kolasib Division | 03.05.22 | 03.05.23 | 0.14% | 390.1 | - |  | 0.14% | 390.1 | Work in progress
13 | Construction of link Road from NH-306 (PHE pump House) to R.Aitlang Lui Basin Crop Land : Length = 9.22 Kms | 465.66 | Kolasib Division | 12.08.22 | 12.08.23 | 60% | 266.358 | - |  | 60% | 266.358 | In Progress
14 | Construction of link Road from NH-306 (Vairengte) to Sabual Mual Arable Crop Land = 3.720 Kms | 418.89 | Kolasib Division | 13.08.22 | 13.08.23 | 55% | 136.81 | - |  | 55% | 136.81 | In Progress
15 | Construction of Agriculture Link Road from NH-306 A to Buarchep Arable Crop Land : Length = 1.720 Kms | 175.03 | Kolasib Division | 27.08.22 | 27.08.23 | 68% | 101.65 | - |  | 68% | 101.65 | In Progress
16 | Re-Construction of double storied PHC Building at Bungzung | 268.99 | Project Division-III | 3.12.21 | 3.6.23 | 100% | 228.91 |  | - | 100% | 228.91 | Work completed
17 | Re-Construction of double storied PHC Building at Ngentiang | 266.51 | Project Division-III | 3.12.21 | 13.6.23 | 90% | 228.71 | 8% | 1.44 | 98% | 230.15 | Work in progress
18 | Improvement & Strengthening of Nalkawn - Chamdur Valley | 3400 | Lawngtlai Division | 09.02.22 | 19.11.23 | 52.36% | 1582.47 | 3.06% | - | 55.42% | 1582.47 | Work in progress
19 | Const.of double lane built up Steel Girden Bridge over R.Teirei (Span -102m) at Ch.7.00 Kmp on Bairabi Zamuang Road | 2322.42 | Kawrthah Division | 5.8.17 | 5.8.19 | 52.5% | 781.21 |  |  | 52.5% | 781.21 | Work in progress
20 | Const.of double lane built up Steel Girden Bridge (Span-81m) over R.Langkaih on Mizoram-Tripura Border at Kanhmun | 2231.91 | Kawrthah Division | 6.4.18 | 6.4.20 | 41% | 677.44 |  |  | 41% | 677.44 | Work in progress
21 | Construction of Agriculture Link Road in Nothern Mizoram (Sh: Construction of Link Road from Saikhawthlir to R.Hnanglui Arable crop land, Length = 3.50 kms) | 362.02 | Kawrthah Division | 20.08.22 | 20.08.23 | 32.82% | 215.41 |  |  | 32.82% | 215.41 | Work in progress
22 | Construction of Agriculture Link Road in Nothern Mizoram (Sh: Construction of Link Road from Chuhvel to R.Hnanglui Arable crop land, Length = 2.35 kms) | 284.76 | Kawrthah Division | 18.08.22 | 18.08.23 | 35.65% | 169.45 |  |  | 35.65% | 169.45 | Work in progress
23 | Construction of Agriculture Link Road in Nothern Mizoram (Sh: Construction of Link Road from from Thinghlun to Hriphaw through permanent crop length=9.570 kmp) | 385.61 | Kawrthah Division | 20.08.22 | 20.08.23 | 51.55% | 229.44 | 1.64% |  | 53.19% | 229.44 | Work in progress
24 | Upgradation of Meidum to Hortoki Phase-I | 4445 | NHD-III |  |  | 54.82% | 1731 | 3.65% | - | 58.47% | 1731
25 | Construction of River Training Works for Protection of Tlawng River Bank at Bairabi Phase-I F.Lalthlamuana | 1111 | NHD-III |  |  | 42.81% | 78 | 27.29% | - | 70.1% | 78
| Phase-II F.Lalliansanga |  |  |  |  | 32.04% | 72 | 6.28% |  | 38.32% | 72
| Phase-III Babie Cons.& Consultancy Services |  |  |  |  | 82.08% | 148 | 17.92% | - | 100% | 148
| Phase-IV Zothantluanga |  |  |  |  | 83.82% | 136 | 16.18% | - | 100% | 136
26 | Const.of Road from Khamrang - Selesih Ph-I | [10 empty] | Work in progress. Initial cutting taken up, hence no progress/achievement (completed length) can be shown
| a) (11 Km Group A) | 705.48 | Project Division-IV | 8.2.21 | 8.2.23 | 1.7% | 314.25 | - | - | 1.7% | 314.25
| b) 11 Km Group B | 705.32 | Project Division-IV | 8.2.21 | 8.2.23 | 2.4% | 434.62 | - | - | 2.4% | 434.62
| c) 11 Km Group C | 703.89 | Project Division-IV | 8.2.21 | 8.2.23 | 2.4% | 299.52 | - | - | 2.4% | 299.52
27 | Construction of road from Khamrang to Selesih Phase-I (Sh: Construction of rigid pavement from 7/00 Kmp to 11/00 Kmp = 4.00 kms) | 1463.41 | Project Division-IV | N.A | 16.02.24 | - | - | - | - | - | - | Work not yet started
28 | Const.of Road from Khamrang - Selesih Ph-II a) (11 Km Group 1) | 2537 | Project Division-IV | 8.11.21 | 8.5.23 | 3.35% | 547.46 | - | - | 3.35% | 547.46 | Work in progress. However, due to encountering rocky portion, progress is considerably affected. Initial cutting taken up, hence no progress/achievement (completed length) can be shown
| b) 11 Km Group 2 | 435.74 | Project Division-IV | 22.11.21 | 22.11.22 | 2.2% | 166.81 | - | - | 2.2% | 166.81
| c) 25 Km Group 3 | 611.93 | Project Division-IV | 11.11.21 | 11.11.22 | 0.5% | 45.02 | - | - | 0.5% | 45.02
29 | 1) Construction of MDR Road from Sirvakawn-11 kmp to Selesih-28 kmp (Phase-II of 28 kms Dilsei-Selesih By-pass road NH-54) 2) Construction of Village road for connecting Village Mualkhang with Dilsei-Selesih by pass road at 8 kmp | 14529.27 | Project Division-IV | 8.11.21 | 8.05.23 | 39.06% | 801.42 | 0.65% | - | 39.71% | 801.42
30 | Construction of MDR from Khamrang-Dilsei to Selesih (Phase-I) | 6583.18 | Project Division-IV | 8.02.21 | 8.02.23 | 59.09% | 1095.3 | 0.91% | - | 60% | 1095.3
31 | Const.of Double Storied PHC at Tawipui South | 267.15 | Lunglei Building Project Division | 1.2.22 | 1.2.24 | 100% | 267.15 | - | - | 100% | 267.15 | Completed and hand over to the Client Dept.on dt.30.5.23
32 | Const.of Double Storied PHC at Lungsen | 267.15 | Lunglei Building Project Division | 10.2.22 | 10.2.24 | 78% | 149.32 | 4% |  | 82% | 149.32 | Work in progress
33 | Const.of Infrastructure Support fro School of Agricultural Science at Hnahthial: Phase-II | 685 | Lunglei Building Project Division | 08.04.23 | 08.04.25 | [6 empty] | Work not yet started due to dispute on the exact location of the buildings from the Client Dept.
34 | Re-Construction of Primary Health Centre at Bukpui | 215.43 | Project Division-II | 06.01.22 | 06.07.23 | 85% | 172.19 | 2% |  | 87% | 172.19 | Work in progress
35 | Re-Construction of Primary Health Centre at Marpara | 227.72 | Project Division-II | 25.03.22 | 25.09.23 | 70% | 201.38 | 10% |  | 80% | 201.38 | Work in progress

## NEC
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding: NEC | [8 empty] | Month : May 2023
Sl. no | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the Month |  | Overall cumulative achievement |  | Remarks
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
1 | Construction of Lunglei Market and Trade Centre at Electric/Chanmari Veng, Lunglei (NEC) | 1403.4 | Lunglei Building Project Division | 25.08.22 | 25.08.24 | 5% | 284.86 | - | - | 5% | 284.86 | Secured advanced released. Laying of column in progress
2 | Construction of Mara Handloom & Weaving Centre at Council Vaih, Saiha | 458.61 | Lunglei Building Project Division | 13.04.22 | 13.04.24 | 20% | 60.58 | 2% |  | 22% | 60.58 | Work in progress
3 | Proposal of Identified Village for providing key identified Service at Marpara S Village of W Bunghmun Block of Lunglei District | 141.3 | Lunglei Building Project Division | 6.4.23 | 6.4.24 | [6 empty] | Work not yet started
4 | Proposal of Identified Village for providing key identified Service at Bungtlang S Village of Lawngtlai District, Mizoram | 186.89 | Lunglei Building Project Division | 6.4.23 | [7 empty] | Work not yet started
5 | Proposal of Identified Village for providing key identified Service at Bungtlang RD Block of Lawngtlai District, Mizoram | 423.92 | Lunglei Building Project Division | 6.4.23 | 6.4.24 | [6 empty] | Work not yet started
6 | Proposal of Identified Village for providing key identified Service at Chawngte RD Block of Lawngtlai District, Mizoram | 379.65 | Lunglei Building Project Division | 6.4.23 | 6.4.24 | [6 empty] | Work not yet started
7 | Proposal of Identified Village for providing key identified Service at Bunghmun Block of Lunglei District, Mizoram | 391.94 | Lunglei Building Project Division | 6.4.23 | 6.4.24 | [6 empty] | Work not yet started
8 | Improvement & Upgradation of KDZKP Road (0.00 - 88.400Kmp) | 18327.42 | Kawrthah Division | 27.4.15 | 31.3.21 | 100% | 17963 | - | - | 100% | 17963 | Work Phy.Completed on 31.12.21 B.A is demanded
9 | Const.of Patient Lodging at Mawdiangdiang near NEIGHRIMS, Shillong | 419.67 | Project Division-I | 9.9.21 | 9.9.23 | 15% | - | - | - | 15% | - | Contractor stopped the coinstruction work from 3rd April and Dismantling of sub standard work from 5th April, the matter has been already reported
10 | Construction of 60 Bedded Intern Hostel at ZMC, Falkawn | 679 | Project Division-II | 01.09.22 | 01.05.24 | 15% | 10 | 5% | - | 20% | 10 | Work in progress
11 | Etablishment of Sinlung Hills Council Administrative Complex (Const.of Sinlung Hills Administrative Building at Sakawrdai) | 381.99 | Project Division-III | 8.11.21 | 8.11.23 | 48% | 78.06 | 0.5% | - | 48.5% | 78.06 | Work in progress
12 | Construction of passion fruit processing unit at IIDC Zote, Champhai | 750 | Project Division-III | 23.09.22 | 24.03.24 | - | - | - | - | - | - | 1. Approval for new DPR submitted to NEC due to change of site from IIDC Champhai to SDO (Cvil Complex at New Champhai is awaited 2. Approval for change of Implementing Agency from DC Champhai to PWD is awaited
13 | Construction of Zomi cultural Centre and preservation of historical sites at Champhai | 478.69 | Project Division-III | 26.09.22 | 26.09.24 | 5% | - | - | - | 5% | - | 1. Fund not yet released by NEC 2. Approval for change of Implementation Agency from DC Champhai to PWD is awaited
14 | Construction of AYUSH Development Centre at MINECO Aizawl | 264.16 | Project Division-IV | 7.12.22 | 17.8.24 | 7.33% | 10 | 0.76% |  | 8.09% | 10 | Work in progress
15 | Upgradation of Serkhan - Bagha Road | 17328 | NHD-III | 24.9.11 | - | 100% | 17239.22 | - | - | 100% | 17239.22 | Completed
16 | Periodical Renewal of NH-54 in the state of Mizoram under ARP for the year 2019-2020 between Km 118/00-133/00 Km (15.00Km) | 1477 | NHD-III | - | - | 100% | 1106 |  | - | 100% | 1106
17 | Strengthening of Km 10.00 to Km 33.00 (Length 23.00 Km) on NH-306A including Strengthening & Construction of Retaining Walls and Culverts and Strenthening of 3 Nos.of Bailey Bridges in the State of Mizoram | 6523 | NHD-III | - | - | 79.34% | 2614 | 11.1% |  | 90.44% | 2614

## Deposit
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : Deposit | [9 empty] | Month : May 2023
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummutive Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
1 | Construction of New Ward Building (Renovation & Upgradation of Central Jail) at Aizawl, Mizoram | 100 | Project Division-I | 28.8.22 | 23.3.24 | - | - | 5% | - | 5% | -

## PMGSY
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding: PMGSY | [8 empty] | Month : May 2023
Sl. no | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the Month |  | Overall cumulative achievement |  | Remarks
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
1 | Diblibagh to Chengkawllui Road (0.000-19.520)Kmp | 2798.82 | Tlabung Division | 17.6.19 | 31.03.23 | 80.45% | 429.71 |  | 1079.47 | 80.45% | 1509.18 | Work in progress
2 | Diblibagh to Sugarbasora Road (0.000-2.000)Kmp | 305.81 | Tlabung Division | 28.9.18 | 31.03.23 | 69.81% | 88.3 | - | - | 69.81% | 88.3 | Pending Forest Clearance
3 | Diblibagh to Sugarbasora Road Group B (2.000-4.760)Kmp | 373.19 | Tlabung Division | 22.9.18 | 31.03.23 | 92.2% | 123.6 | - | - | 92.2% | 123.6 | Pending Forest Clearance
4 | Const & Maintenance of Tlabung-Nunsury Road (0.000-8.000) Kmp | 579.77 | Tlabung Division | 17.6.19 | 31.03.23 | 47.8% | 145.96 | 3.6% | - | 51.4% | 145.96 | Work in progress
5 | Const.of Serhuan-Lamthai Road | 1378.12 | Tlabung Division | 21.12.17 | 31.03.23 | 91.48% | 969.08 |  | - | 91.48% | 969.08 | Work in progress
6 | Mauzam-Puankhai Road | 831.91 | Tlabung Division | 21.12.13 | 05.02.22 | 100% | 664.9 | - | - | 100% | 664.9 | Completed physical works
7 | Chhotapansuri-Tungasora Road (0.000-2.000)Kmp | 303.43 | Tlabung Division | 22.9.18 | 11.12.22 | 55.24% | 100.06 | 7.36% | - | 62.6% | 100.06 | Work in progress
8 | Chhotapansuri-Tupasora Road (2.000-3.500)Kmp | 199.69 | Tlabung Division | 5.10.18 | 30.11.22 | 83.33% | 118.43 | 10% | - | 93.33% | 118.43 | Work in progress
9 | Ngharum to Rajmandal Road | 929.42 | Tlabung Division | 17.06.19 | 04.03.22 | 88% | 596.25 | 10.55% | - | 98.55% | 596.25 | Work in progress
10 | Mandiasora-Ajasora Road (0.000 - 8.500) Kmp | 734.93 | Tlabung Division | 17.6.19 | 31.12.22 | 88.64% | 213.21 | 3.96% | 359.82 | 92.6% | 573.03 | Work in progress
11 | Construction & Maintenance of Sairang - Leng-Nghalchawm | 842.17 | NHD-I | 19.12.20 | 19.12.22 | 93% | 476.06 |  | - | 93% | 476.06 | Work in progress
12 | Construction of Mualpheng to Maite Road (Sh:-Construction of Road using flexible pavement) | 1868.8 | Saitual Division | 13.11.17 | 13.11.19 | 100% | 1276.33 | - | 592.12 | 100% | 1868.45 | Work in progress
13 | Construction of Dilkhan to Tualbung Road (Sh:-Construction of Road using flexible pavement) | 567.6 | Saitual Division | 27.10.17 | 27.4.19 | 100% | 499.05 | - | - | 100% | 499.05 | Physically completed
14 | Construction and Maintenance of Dilkhan to N Lungpher Road (Sh: Construction of road using Plastic Cell filled concrete (Panelled concrete) | 802.98 | Saitual Division | 27.10.17 | 27.10.19 | 100% | 730.87 | - | - | 100% | 730.87 | Physically completed
15 | Construction and Maintenance of Lungpher to Buhban Road (Sh: Construction of road using flexible pavement) | 490.11 | Saitual Division | 13.11.17 | 13.5.19 | 100% | 478.12 | - | - | 100% | 478.12 | Actual length 6.500Kms Physically completed
16 | Construction and Maintenance of Phullen to Zawngin Road (Sh: Construction of Road using flexible pavement) | 937.8 | Saitual Division | 27.10.17 | 27.10.19 | 100% | 720.24 | - | - | 100% | 720.24 | Physically completed
17 | Construction of NE Tlangnuam to Daido Road (Sh:- Construction of Road using flexible pavement) | 627.04 | Saitual Division | 31.12.17 | 31.12.18 | 100% | 472.57 | - | - | 100% | 472.57 | Physically completed
18 | Construction and Maintenance of Ruallung-Lenchim Phullen to Zawngin Road (Sh: Construction of Road using flexible pavement) | 1283.24 | Saitual Division | 17.9.18 | 10.9.19 | 100% | 907.31 | - | 48.35 | 100% | 955.66 | Physically completed
19 | Construction and Maintenance of Phullen to Luangpawn Road (Sh: FC, Culvert & R/Wall and Construction of road using flexible pavement) | 993.46 | Saitual Division | 17.09.18 | 17.09.19 | 100% | 969.75 | - | - | 100% | 969.75 | Physically completed
20 | Construction and Maintenance of E.Phaileng-Suangpuilawn Road (0.000-6.000Kmp) (Sh: Widening, Culverts & R/Wall and Contstruction of road using flexible pavement) | 831.6 | Saitual Division | 19.12.20 | 19.12.22 | 81% | 142.92 | - | - | 81% | 142.92 | Work in progress
21 | Construction and Maintenance of E.Phaileng-Suangpuilawn Road (6.000-11.000Kmp) (Sh: Widening, Culverts & R/Wall and Construction of Road using flexible pavement) | 906.47 | Saitual Division | 19.12.20 | 19.12.22 | 72% | 116.25 | - | - | 72% | 116.25 | Work in progress
22 | Construction and Maintenance of E.Phaileng-Suangpuilawn Road (11.000-16.000Kmp) (Sh: Widening, Culverts & R/Wall and Construction of Road using flexible pavement) | 807.84 | Saitual Division | 15.8.20 | 15.8.22 | 100% | 327.43 | - | 350.47 | 100% | 677.9 | Physically completed
29
23 | Construction and Maintenance of E.Phaileng-Suangpuilawn Road (16.000-22.000Kmp) (Sh: Widening, Culverts & R/Wall and Construction of Road using flexible pavement) | 826.35 | Saitual Division | 01.01.21 | 01.01.23 | 77% | 305.65 | - | - | 77% | 305.65 | Work in progress
24 | Construction and Maintenance of E.Phaileng-Suangpuilawn Road (22.000-28.000Kmp) (Sh: Widening, Culverts & R/Wall and Construction of Road using flexible pavement) | 811.17 | Saitual Division | 01.01.20 | 01.01.22 | 100% | 632.27 | - | - | 100% | 632.27 | Work in progress
25 | Construction and Maintenance of E.Phaileng-Suangpuilawn Road (28.000-34.000Kmp) (Sh: Widening, Culverts & R/Wall and Construction of Road using flexible pavement) | 1133.6 | Saitual Division | 10.02.20 | 10.02.22 | 100% | 531.51 | - | - | 100% | 531.51 | Work in progress
26 | Construction and Maintenance of E.Phaileng-Suangpuilawn Road 34.000-40.000Kmp) (Sh: Widening, Culverts & R/Wall and Construction of Road using flexible pavement) | 1055.65 | Saitual Division | 6.01.20 | 6.01.22 | 76% | 164.3 | - | - | 76% | 164.3 | Work in progress
27 | Construction and Maintenance of E.Phaileng-Suangpuilawn Road 40.000-46.000Kmp) (Sh: Widening, Culverts & R/Wall and Construction of Road using flexible pavement) | 1000.02 | Saitual Division | 6.01.20 | 24 months | 77% | 163.62 | - | - | 77% | 163.62 | Work in progress
28 | Construction and Maintenance of Bunghmun-W.Mualthuam Road (Sh: Cell filled Concrete Road) (0.00-13.500 Kmp) | 955.77 | Kawrthah Division | 27.11.17 | 23.03.21 | 100% | 918.23 | - | - | 100% | 918.23
29 | Construction and Maintenance of Bunghmun to Thaidawr Road (0.00 Kmp-8.90 Kmp) | 745.77 | Kawrthah Division | 17.6.19 | 31.3.22 | 100% | 720.23 | - | - | 100% | 720.72 | Work completed physically
30 | Construction of Darlak-Sihthiang Road (0.00-35.610 Kmp) | 5369.98 | Kawrthah Division | 17.6.19 | 19.6.20 | 10% | 488.49 | - | - | 10% | 488.49 | Physical progress put hold due to Forest Clearance issue. Hence, no target for the next month
31 | Construction & Maintenance of Khawzawl to Biate Road (0.00 kmp-6.00Km) Group-A | 780.49 | Project Division-IV | 31.12.20 | 31.03.23 | 80.52% | 381.64 |  | - | 80.52% | 381.64
32 | Construction & Maintenance of Khawzawl to Biate Road (6.00 kmp-12.00Km) Group-B | 760.98 | Project Division-IV | 31.12.20 | 31.03.23 | 77.16% | 386.23 | - |  | 77.16% | 386.23
33 | Construction & Maintenance of Khawzawl to Biate Road (12.00 kmp-18.00Km) Group-C | 817.47 | Project Division-IV | 2.1.21 | 31.03.23 | 61.24% | 283.024 | 1.35% | - | 62.59% | 283.024 | In progress
34 | Construction & Maintenance of Khawzawl to Biate Road (18.00 kmp-24.00Km) Group-D | 750.94 | Project Division-IV | 10.6.20 | 31.03.23 | 62.54% | 258.56 | 0.05% | - | 62.59% | 258.56 | In progress
35 | Construction & Maintenance of Khawzawl to Biate Road (24.00 kmp-30.00Km) Group-E | 766.62 | Project Division-IV | 29.4.21 | 31.03.23 | 54.6% | 216.99 | - | - | 54.6% | 216.99 | In progress
36 | Construction & Maintenance of Khawzawl to Biate Road (30.00 kmp-36.00Km) Group-F | 1148.93 | Project Division-IV | 7.2.20 | 31.03.23 | 85.54% | 612.96 | - | - | 85.54% | 612.96 | In progress
37 | Construction & Maintenance of Khawzawl to Biate Road (36.00 kmp-42.00Km) Group-G | 818.99 | Project Division-IV | 1.1.21 | 31.03.23 | 90.26% | 601.74 |  | - | 90.26% | 601.74 | In progress
38 | Construction & Maintenance of Khawzawl to Biate Road (42.00 kmp-48.00Km) Group-H | 1430.26 | Project Division-IV | 6.1.20 | 31.03.23 | 78.78% | 930.61 |  | - | 78.78% | 930.61 | In progress
39 | Construction & Maintenance of Khawzawl to Biate Road (48.00 kmp-54.00Km) Group-I | 1108.01 | Project Division-IV | 24.3.21 | 31.03.23 | 67.25% | 407.28 | - | - | 67.25% | 407.28 | In progress
40 | Construction & Maintenance of Khawzawl to Biate Road (54.00 kmp-60.00Km) Group-J | 937.99 | Project Division-IV | 4.1.21 | 31.03.23 | 64.31% | 434.12 | - | - | 64.31% | 434.12 | in progress
41 | Construction of Niawhtlang - Chakhang Road (0.00 - 44.05) Kmp | 1615.335 | Siaha Division | 20.10.20 | 20.06.22 | 35.15% | 184.027 | - | - | 35.15% | 184.027 | Contractor expired
42 | Construction of Phura - Vahai Road (0.00 - 17.000) Kmp | 1563.92 | Siaha Division | 13.11.17 | 17.4.22 | 100% | 1409.46 | - | - | 100% | 1409.46 | Materials collection
43 | Construction of Tawngkolong - Lawngmasu Road (0.00 - 22.700) Kmp | 1289.738 | Siaha Division | 14.02.22 | 30.09.22 | 37.14% | 258.42 | - | - | 37.14% | 258.42 | Work in progress
44 | Construction & Maintenance of Khawzawl-Ngaizawl Road | 817.57 | Khawzawl Division | 13.11.17 | 13.11.19 | 93% | 486.84 | - | - | 93% | 486.84 | Work in progress
45 | Construction & Maintenance of Khawhai - Tlangpuilian Road | 962.79 | Khawzawl Division | 13.11.17 | 13.11.19 | 93% | 604.81 | 7% | - | 100% | 604.81 | Work in progress
46 | Construction & Maintenance of Khawzawl - Vankal Road | 1997.33 | Khawzawl Division | 13.12.18 | 13.12.19 | 93% | 1442.35 | - | 62.37 | 93% | 1504.72 | 100m Panelled Concrete is set aside for Bridge Site
47 | Construction & Maintenance of Khawzawl - Hmuncheng Road | 1595.69 | Khawzawl Division | 05.10.18 | 23.05.22 | 77% | 1089.5 | - | - | 77% | 1089.5 | Work in progress
48 | Construction & Maintenance of Khawzawl - Hmuncheng Road | 1595.69 | Khawzawl Division | 05.10.18 | 05.10.19 | 75% | 959.03 | - | - | 75% | 959.03
49 | Construction & Maintenance of Khawzawl - Hmuncheng Road | 636.68 | Khawzawl Division | 23.05.22 | 23.09.22 | 48% | 130.47 | - | - | 48% | 130.47
50 | Construction & Maintenance of Rengtekawn to Builum Road | 2082.73 | Kolasib Division | 17.09.18 | 31.03.22 | 100% | 1862.1 | - | - | 100% | 1862.1 | Work completed
51 | Construction & Maintenance of Rengtekawn to Builum Road G-A | 400.6 | Kolasib Division | 17.09.18 | 31.03.22 | 100% | 291.12 | - | - | 100% | 291.12 | Work completed
52 | Construction & Maintenance of Rengtekawn to Builum Road G-B | 482.26 | Kolasib Division | 17.09.18 | 31.03.22 | 100% | 445.17 | - | - | 100% | 445.17 | Work completed
53 | Construction & Maintenance of Rengtekawn to Builum Road G-C | 393.35 | Kolasib Division | 26.09.18 | 31.03.22 | 100% | 319.37 | - | - | 100% | 319.37 | Work completed
54 | Construction & Maintenance of Rengtekawn to Builum Road G-D | 806.52 | Kolasib Division | 22.09.18 | 31.01.22 | 100% | 806.44 | - | - | 100% | 806.44 | Work completed
55 | Construction & Maintenance of Bilkhawthlir to N.Chawnpui Road Builum Road | 2421.5 | Kolasib Division | 12.12.18 | 31.03.22 | 100% | 2286.96 | - | - | 100% | 2286.96 | Work completed
56 | Construction & Maintenance of Phuldungsei to Parvatui Road (0.00 Kmp - 17.30 Kmp) | 3743.71 | Mamit Division | 13.12.18 | 05.09.22 | 76% | 2888.4 | - | - | 76% | 2888.4 | Work in progress
57 | Construction & Maintenance of Tuipuibari to Andermanik Road (0.00 Kmp - 2.760 km) | 430.18 | Mamit Division | 17.9.18 | 12.02.22 | 95% | 297.93 | - | - | 95% | 297.93 | Work in progress
58 | Construction & Maintenance of Andermanik to N.Belkhai Road (0.00 Kmp - 6.00 km) | 1016.7 | Mamit Division | 10.6.19 | 10.6.20 | 36% | 156.41 | - | - | 36% | 156.41 | Work in progress
59 | Thuampui - Lungchem Road (23.000 - 27.000 KMP) | 447.49 | Lunglei Road Division-I | 27.10.19 | 27.10.18 | 100% | 447.49 | - | - | 100% | 447.49 | Deviation already approved due to Some items are changed as mentioned in EE letter No.D-13024/5/2019(DV)/S&I/LD/PWD/Pt/10 Dt.18.02.21 Completed
60 | Thuampui - Lungchem Road (27.000 -32.000 KMP) | 395.75 | Lunglei Road Division-I | 27.10.17 | 27.10.18 | 100% | 378.64 | - | - | 100% | 378.64
61 | Thuampui - Lungchem Road (32.000 -37.000 KMP) | 372.33 | Lunglei Road Division-I | 27.11.17 | 27.11.18 | 100% | 268.97 | - | - | 100% | 268.97 | Completed
62 | Thuampui - Lungchem Road (37.000 - 40.900 KMP) | 307.24 | Lunglei Road Division-I | 27.10.17 | 27.10.18 | 100% | 336.09 | - | - | 100% | 336.09 | Completed
63 | Construction and Maintenance of Sachan to Sumasumi Road (0.00 - 24.09 Kmp) | 4005.26 | Lunglei Road Division-I | 10.06.19 | 31.08.22 | 45% | 1516.3 | 5% |  | 50% | 1516.3 | Work in progress
64 | Construction and Maintenance of Sumasumi - Tuikawi Road (0.00 - 19.22 Kmp) | 2882.21 | Lunglei Road Division-I | 14.06.19 | 26.12.21 | 31% | 697.5 | 2% | - | 33% | 697.5 | Work in progress
65 | Thuampui - Lungchem Road (0.000 - 4.000 KMP) | 85.83 | Lunglei Road Division-I | 01.04.21 | 31.03.22 | 100% | 85.83 | - | - | 100% | 85.53 | Completed
66 | Thuampui - Lungchem Road (4.000 - 7.000 KMP) | 268.21 | Lunglei Road Division-I | 27.10.17 | 27.10.18 | 100% | 268.19 | - | - | 100% | 268.19 | Completed
67 | Thuampui - Lungchem Road (7.000 - 10.000 KMP) | 306.59 | Lunglei Road Division-I | 27.10.17 | 1.04.20 | 100% | 306.56 | - | - | 100% | 306.56 | Completed
68 | Thuampui - Lungchem Road (10.000 - 14.000 KMP) | 387.7 | Lunglei Road Division-I | 27.10.17 | 27.10.18 | 100% | 387.68 | - | - | 100% | 387.68 | Completed
69 | Thuampui - Lungchem Road (14.000 - 18.000 KMP) | 394.46 | Lunglei Road Division-I | 13.11.17 | 13.11.18 | 100% | 257.8 | - | - | 100% | 257.8 | Work in progress
70 | Thuampui - Lungchem Road (18.000 - 21.000 KMP) | 418.83 | Lunglei Road Division-I | 27.10.17 | 27.10.18 | 100% | 195.53 | - | - | 100% | 195.53 | Some items are changes due to Deviation approval vide EE letter no.D-13024/5/2019(DV)/S&I/LDIPWD/28 dt.9.03.22 completed
71 | Thuampui - Lungchem Road (21.000 - 23.000 KMP) | 370.75 | Lunglei Road Division-I | 13.11.17 | 13.11.18 | 100% | 280.41 | - | - | 100% | 280.41 | Completed
72 | Const. & Maint.of Bunghmun to Sachan Road (0.00-9.07Kmp) | 1325.06 | Lunglei Road Division-I | 13.12.18 | 31.07.22 | 51% | 654.39 | 5% |  | 56% | 654.39
73 | Const. & Maint.of Cherhlun to Ngharchhip Road (0.00-7.64 Kmp) | 554.08 | Lunglei Road Division-II | 13.12.18 | 12.12.19 | 100% | 399.01 | - | - | 100% | 399.01 | Work phy.completed
74 | Const. & Maint.of Khawhri to Chawngtui Road (0.00-17.81 Kmp) | 1280.59 | Lunglei Road Division-II | 8.10.18 | 10.04.21 | 86% | 741.73 | - |  | 86% | 741.73 | Work in progress
75 | Const. & Maint.of Luangmual to Vaisam Road (0.00-26.700 Kmp) | 4518.74 | Lunglei Road Division-II | 10.06.19 | 31.03.22 | 60% | 2170.44 | - |  | 60% | 2170.44 | Work in progress
76 | Const. & Maint.of Haulawng to Dawn Road (0.00-6.00 Kmp) | 742.02 | Lunglei Road Division-II | 10.06.20 | 10.06.22 | 72% | 515.06 | 11% | - | 83% | 515.06 | Work in progress
77 | Const. & Maint.of Haulawng to Dawn Road (6.00-12.000 Kmp) | 605.77 | Lunglei Road Division-II | 01.01.21 | 01.01.23 | 61% | 239.43 | - | - | 61% | 239.43 | Work in progress
78 | Const. & Maint.of Haulawng to Dawn Road (12.00-18.000 Kmp) | 607.56 | Lunglei Road Division-II | 01.01.21 | 01.01.23 | 64% | 235.06 | 7% | 264.88 | 71% | 499.94 | Work in progress
79 | Const. & Maint.of Haulawng to Dawn Road (18.00-24.000 Kmp) | 743.95 | Lunglei Road Division-II | 01.01.21 | 01.01.23 | 68% | 203.38 | - | - | 68% | 203.38 | Work in progress
80 | Const. & Maint.of Haulawng to Dawn Road (24.00-30.500 Kmp) | 840.58 | Lunglei Road Division-II | 01.01.21 | 01.01.23 | 56% | 226.9 | 9% | - | 65% | 226.9 | Work in progress
81 | Construction of Nghalimlui to Bolisora (0.00-3.00)Kmp (Sh: FC, Culvert, R.Wall) | 158.34 | Lawngtlai Division | 27.10.17 | 30.04.20 | 100% | 158.33 | - | - | 100% | 158.33 | Completed
82 | Construction of Nghalimlui to Bolisora (3.00-5.00)Kmp (Sh: FC, Culvert, R.Wall) | 249.3 | Lawngtlai Division | 27.10.17 | 23.03.20 | 100% | 247.3 | - | - | 100% | 247.3 | Completed
83 | Construction of Nghalimlui to Bolisora (5.00-8.00)Kmp (Sh: FC, Culvert, R.Wall) | 226.89 | Lawngtlai Division | 27.10.17 | 10.08.20 | 100% | 206.24 | - | - | 100% | 206.24 | Completed
84 | Construction of Nghalimlui to Bolisora (8.00-12.65)Kmp (Sh: FC, Culvert, R.Wall) | 266.55 | Lawngtlai Division | 27.10.17 | 16.08.20 | 100% | 246.66 | - | - | 100% | 246.66 | Completed
85 | Construction of Karlui to Damlui (0.00-2.00)Kmp (Sh: FC, Culvert, R.Wall) | 185.86 | Lawngtlai Division | 27.10.17 | 28.2.20 | 100% | 207.66 | - | - | 100% | 207.66 | Completed
86 | Construction of Karlui to Damlui (2.00-6.00)Kmp (Sh: FC, Culvert, R.Wall) | 227.54 | Lawngtlai Division | 27.10.17 | 30.10.19 | 100% | 216.35 | - | - | 100% | 216.35 | Work Physically Completed
87 | Construction of Karlui to Damlui (6.00-8.800)Kmp (Sh: FC, Culvert, R.Wall) | 147.71 | Lawngtlai Division | 13.11.17 | 25.10.19 | 100% | 147.69 | - | - | 100% | 147.69 | Completed
88 | Construction of Bolisora to Chamdurtlang (0.00 - 2.00) Kmp (Sh: FC, Culvert. R.Wall) | 155.49 | Lawngtlai Division | 27.10.17 | 20.05.20 | 100% | 155.49 | - | - | 100% | 155.49 | Completed
89 | Construction of Bolisora to Chamdurtlang(2.00-5.00)Kmp (Sh: FC, Culvert, R.Wall) | 229.32 | Lawngtlai Division | 27.10.17 | 16.03.20 | 100% | 229.32 | - | - | 100% | 229.32 | Completed
90 | Construction of Bolisora to Chamdurtlang(5.00-9.00)Kmp (Sh: FC, Culvert, R.Wall) | 359.96 | Lawngtlai Division | 01.04.19 | 29.09.21 | 100% | 359.95 | - | - | 100% | 359.95 | Work Physically Completed
91 | Construction of Bolisora to Chamdurtlang(9.00-11.650)Kmp (Sh: FC, Culvert, R.Wall) | 251.92 | Lawngtlai Division | 27.10.17 | 16.03.20 | 100% | 251.9 | - | - | 100% | 251.9 | Completed
92 | Construction of Ajasora to Longpuighat (0.00-10.900)Kmp (Sh: Const.of road using Flexible Pavement Technology) | 934 | Lawngtlai Division | 13.11.17 | 19.12.21 | 100% | 857.32 | - | - | 100% | 857.32 | Work Physically Completed
93 | Construction of Jognasury - Karlui Road (0.000-12.100)Kmp (Sh: Formation Cutting, Culvert & R.Walls & Const.of of Road Using Flexible Pavement) | 888.27 | Lawngtlai Division | 13.12.18 | 30.09.22 | 100% | 760.65 |  | - | 100% | 760.65 | Work in progress
94 | Construction of Maniababsora-I to Maniababsora-II Road (0.000-1.520)Kmp (Sh: FC, Culvert & R.Wall & Const.of road using Panelled Concrete Technology) | 212.57 | Lawngtlai Division | 27.12.18 | 22.11.20 | 100% | 212.32 | - | - | 100% | 212.32 | Completed
95 | Construction of Boroituli to Jaruldubasora Road (0.000-2.100)Kmp (Sh: FC, Culvert & R.Wall & Const.of road using Panelled Concrete Technology) | 257.02 | Lawngtlai Division | 17.09.18 | 10.02.22 | 100% | 257 | - | - | 100% | 257 | Completed
96 | Construction of Boroituli to Jaruldubasora Road (2.000-3.700)Kmp (Sh: FC, Culvert & R.Wall & Const.of road using Panelled Concrete Technology) | 269.85 | Lawngtlai Division | 28.09.18 | 30.09.22 | 100% | 258.28 | - | 10.26 | 100% | 268.54 | Work in progress
97 | Construction of Vaseitlang to Lokhisury Road(0.00-9.560)Kmp (Sh: FC, Culvert, R.Wall & Const.of road using Panelled Concrete Technology) | 1366.7 | Lawngtlai Division | 28.09.18 | 30.09.22 | 65.85% | 663.44 | 2% | 158.72 | 67.85% | 822.16 | Work in progress
98 | Construction of Vathuampui to Tuisentlang Road(0.000-9.600)Kmp (Sh: FC, Culvert, R.Wall & Const.of Road Using panelled Concrete) | 1320.64 | Lawngtlai Division | 03.01.18 | 30.09.22 | 72.58% | 910.99 | - | - | 72.58% | 910.99 | Proposed for cancellation of the project
99 | Construction of Vathuampui to Chamdur P-I Road(0.000-1.720)Kmp (Sh: FC, Culvert, R.Wall & Const.of Road Using panelled Concrete) | 241.02 | Lawngtlai Division | 15.10.18 | 30.09.22 | 100% | 262.91 | - | - | 100% | 262.91 | Work Physically Completed
100 | Construction of Vathuampui to Chamdurtlang (0.000-1.720)Kmp (Sh: FC, Culvert, R.Wall & Const.of Road Using panelled Concrete) | 249.37 | Lawngtlai Division | 13.12.18 | 28.02.23 | 71.15% | 180.75 |  | - | 71.15% | 180.75 | Work in progress
101 | Construction of Vathuampui to Chamdurtlang (2.000-3.800)Kmp (Sh: FC, Culvert, R.Wall & Const.of Road Using panelled Concrete) | 362.32 | Lawngtlai Division | 22.09.18 | 30.09.22 | 100% | 318.22 |  | - | 100% | 318.22 | Work in progress
102 | Construction of Chamdurtlang to Mualtlang Road(0.000-7.970)Kmp (Sh: FC, Culvert, R.Wall & Const.of Road Using panelled Concrete) | 863.89 | Lawngtlai Division | 13.12.18 | 28.02.23 | 95.29% | 1089.09 | 4.71% |  | 100% | 1089.09 | Work in progress
103 | Construction of Parva II to Zochachhuah Road(0.000-29.720)Kmp (Sh: FC, Culvert, R.Wall & Const.of Road Using panelled Concrete) | 5212.3 | Lawngtlai Division | 05.04.20 | 31.03.23 | 100% | 4048.61 |  | - | 100% | 4048.61 | Technology changed from Cell-Filled Concrete to panelled Cement Concrete vide letter No.B.15028/254/2019/PMGSY/EC/PWD/61 of 1.06.20
104 | Construction of Parva II to Bondukbanga Road(0.000-2.000)Kmp (Sh: FC, Culvert, R.Wall & Const.of Road Using Flexible Pavement) | 269.72 | Lawngtlai Division | 13.12.19 | 31.12.22 | 100% | 269.14 | - | - | 100% | 269.14 | Completed
105 | Construction of Parva II to Bondukbanga Road(2.000-4.120)Kmp (Sh: FC, Culvert, R.Wall & Const.of Road Using Flexible Pavement) | 285.87 | Lawngtlai Division | 13.12.19 | 31.12.22 | 96.98% | 259.1 | 3.02% | - | 100% | 259.1 | Work in progress
106 | Construction &Maintenance of Parva-II - Kamtuli Road (0.000-25.550)Kmp (Sh: FC, Culvert, R.Wall & Const.of Road Using panelled Concrete) | 3620.34 | Lawngtlai Division | 17.06.20 | 31.03.23 | 79.52% | 964.52 | 4.77% | 892.77 | 84.29% | 1857.29 | Technology changed from Flexible Pavement to Panelled Cement Concrete vide letter No.B.15028/254/2019/PMGSY/EC/PWD/61 of 1.06.20
107 | Construction & Maintenance of Vaseitlang to Maniababsora Road (0.000-13.500)Kmp (Sh: FC, Culvert, R.Wall & Const.of Road Using panelled Concrete) | 2356.86 | Lawngtlai Division | 14.06.19 | 30.09.22 | 100% | 2358.27 | - | - | 100% | 2358.27 | Technology changed from Cell-Filled Concrete to Panelled Cement Concrete vide letter No.B.15028/254/2019/PMGSY/EC/PWD/61 of 1.06.21
108 | Construction & Maintenance of Sedailui to Tuikhurlui Road (0.000-1.720)Kmp (Sh: FC, Culvert, R.Wall & Const.of Road Using panelled Concrete Techonology) | 204.33 | Lawngtlai Division | 17.06.20 | 31.12.22 | 92.06% | 159.96 | - | - | 92.06% | 159.96 | Work in progress
109 | Construction &Maintenance of M.Kawnpui to Vathuampui Road (0.000-20.000)Kmp (Sh: FC, Culvert, R.Wall & Const.of Road Using panelled Concrete Technology) | 2088.74 | Lawngtlai Division | 14.06.19 | 31.03.23 | 58.98% | 662.69 | 0.35% | 72.96 | 59.33% | 735.65 | Technology changed from Flexible Pavement to Panelled Cement Concrete vide letter No.B.15028/254/2019/PMGSY/EC/PWD/61 of 1.06.20
110 | Construction &Maintenance of Sumsului Road to Jognasury (0.000-15.44)Kmp (Sh: Const.of Road Using panelled Concrete Technology) | 1278.38 | Lawngtlai Division | 14.06.20 | 28.02.23 | 81.98% | 760.63 | 2.1% | 225.11 | 84.08% | 985.74 | Technology changed from Flexible Pavement to Panelled Cement Concrete vide letter No.B.15028/254/2019/PMGSY/EC/PWD/74 of 24.09.20
111 | Construction &Maintenance of Chawngte 'P' to Sumsului Road (0.000-4.570)Kmp (Sh: FC, Culvert, R.Wall & Const.of Road Using panelled Concrete Technology) | 313.29 | Lawngtlai Division | 17.06.20 | 31.03.23 | 95.83% | 175.44 | 1.76% | 111.07 | 97.59% | 286.51 | Technology changed from Flexible Pavement to Panelled Cement Concrete vide letter No.B.15028/254/2019/PMGSY/EC/PWD/61 of 1.06.20
112 | Const.& Maintenance of Chhingchhip-Thentlang Road | 716.15 | Serchhip Division | 21.12.13 | 14.11.19 | 100% | 716.15 | - | - | 100% | 716.15 | Completed
113 | Const.& Maintenance of Hmuntha-Khawbel Road | 1191.86 | Serchhip Division | 21.12.13 | 18.03.20 | 100% | 1191.84 | - | - | 100% | 1191.84 | Completed
114 | Const.& Maintenance of Chhingchhip-Hmuntha Road | 1443.48 | Serchhip Division | 21.12.13 | 25.11.19 | 100% | 1429.95 | - | - | 100% | 1429.95 | Completed
115 | Const.& Maintenance of Serchhhip-Hriangtlang Road (7.000-9.000 Kmp) | 341.073 | Serchhip Division | 27.10.17 | 31.3.22 | 100% | 330.64 | - | - | 100% | 330.64 | Completed
116 | Const.& Maintenance of Serchhhip-Hriangtlang Road (9.000-11.000 Kmp) | 284.78 | Serchhip Division | 30.12.17 | 30.12.18 | 100% | 284.78 | - | - | 100% | 284.78 | Physically completed
117 | Construction of Serchhip to Hriangtlang Road (11.000-13.000 Kmp) | 193.22 | Serchhip Division | 27.10.17 | 18.6.20 | 100% | 193.22 | - | - | 100% | 193.22 | Completed
118 | Construction of Serchhip to Hriangtlang Road (13.000-15.000 Kmp) | 199.16 | Serchhip Division | 27.10.17 | 21.3.20 | 100% | 199.16 | - | - | 100% | 199.16 | Completed
119 | Construction of Serchhip to Hriangtlang Road (15.000-18.000 Kmp) | 210.65 | Serchhip Division | 27.10.17 | 31.8.19 | 100% | 210.25 | - | - | 100% | 210.25 | Completed
120 | Const.& Maintenance of Serchhhip-Hriangtlang Road (18.000-20.260 Kmp) | 154.9 | Serchhip Division | 27.10.17 | 28.8.19 | 100% | 154.88 | - | - | 100% | 154.88 | Completed
121 | Const.& Maintenance of Khawlailung-Piler Road (0.000-4.160 Kmp) | 675.44 | Serchhip Division | 17.9.18 | 01.07.21 | 100% | 665.15 | - | - | 100% | 665.15 | Completed
122 | Const.& Maintenance of Chekawn-Sialsir Road (0.000-6.240 Kmp) | 882.58 | Serchhip Division | 13.12.18 | 01.09.21 | 100% | 881.1 | - | - | 100% | 881.1 | Completed
123 | Const.& Maintenance of Thentlang-Sialhau Road (0.000-19.54 Kmp) | 1367.2 | Serchhip Division | 28.9.18 | 28.9.19 | 100% | 1355.66 | - |  | 100% | 1355.66 | Physically completed
124 | Const.& Maintenance of Mualcheng-N.Vanlaiphai Road Group 'A' (0.000-8.000 Kmp) | 535.67 | Serchhip Division |  | 31.12.22 | 100% | 303.31 | - | - | 100% | 303.13 | Physically completed
125 | Const.& Maintenance of Mualcheng-N.Vanlaiphai Road Group 'B' (8.000-16.000 Kmp) | 606.37 | Serchhip Division | 31.12.20 | 31.12.22 | 100% | 393.51 | - | - | 100% | 393.51 | Physically completed
126 | Const.& Maintenance of E.Lungdar - Sailulak Road | 1243.47 | Serchhip Division | 21.12.13 | 31.03.19 | 100% | 1241.01 | - | - | 100% | 1241.01 | Completed
127 | Const.& Maintenance of Chekawn - Lungchhuan Road (0.000 - 4.000 Kmp) | 255.85 | Serchhip Division | 17.11.17 | 8.11.19 | 100% | 255.82 | - | - | 100% | 255.82 | Completed
128 | Construction of Serchhip to Hriangtlang Road (0.000-4.000 Kmp) | 286.62 | Serchhip Division | 27.10.17 | 20.12.19 | 100% | 286.61 | - | - | 100% | 286.61 | Completed
129 | Construction of Serchhip to Hriangtlang Road (4.000-7.000 Kmp) | 271.4 | Serchhip Division | 27.10.17 | 20.12.19 | 100% | 271.38 | - | - | 100% | 271.38 | Completed
130 | Construction of Tuithumhnar to Lunghauka (0.00 - 5.00) Kmp (Sh: FC, Culvert, R.Wall) | 189.03 | Multi Modal Project Division | 27.10.17 | 31.07.19 | 100% | 189.03 | - | - | 100% | 189.03 | Completed on 05/07/2019
131 | Construction of Tuithumhnar to Lunghauka (5.00 - 7.00) Kmp (Sh: FC, Culvert, R.Wall) | 196.98 | Multi Modal Project Division | 13.11.18 | 31.03.21 | 100% | 193.28 | - | - | 100% | 193.28 | Completed on 30/03/2021
132 | Construction of Tuithumhnar to Lunghauka (7.00 - 10.00) Kmp (Sh: FC, Culvert, R.Wall) | 247.04 | Multi Modal Project Division | 27.10.17 | 16.07.20 | 100% | 247.04 | - | - | 100% | 247.04 | Completed on 20/07/2020
133 | Construction of Tuithumhnar to Lunghauka (10.00 - 13.00) Kmp (Sh: FC, Culvert, R.Wall) | 184.6 | Multi Modal Project Division | 27.10.17 | 29.06.20 | 100% | 184.6 | - | - | 100% | 184.6 | Completed on 29/06/2020
134 | Construction of Tuithumhnar to Lunghauka (13.00 - 15.480) Kmp (Sh: FC, Culvert, R.Wall) | 198.08 | Multi Modal Project Division | 27.10.17 | 16.07.20 | 100% | 198.08 | - | - | 100% | 198.08 | Completed on 26/06/2020
135 | Construction & Maintenance of Ngenpuitlng to Darnamtlang (0.00 - 4.00) Kmp (Sh: FC, Culvert, R.Wall) | 233.08 | Multi Modal Project Division | 27.10.17 | 31.01.20 | 100% | 193.78 | - | - | 100% | 193.78 | Physically completed on 01/05/2020
136 | Construction & Maintenance of Ngenpuitlng to Darnamtlang (4.00 - 6.20) Kmp (Sh: FC, Culvert, R.Wall) | 161.44 | Multi Modal Project Division | 27.10.17 | 31.08.21 | 100% | 224.73 | - | - | 100% | 224.73 | Completed on 30/08/2021
137 | Construction & Maintenance of Tuithumhnar to Hmawngbu (0.00 - 6.720) Kmp (Sh: Construction of road using Grove Concrete Pavement) | 459.3 | Multi Modal Project Division | 12.11.17 | 1.10.21 | 100% | 459.29 | - | - | 100% | 459.29 | Completed on 16/06/2021
138 | Construction of Sabualtlang to Hmawngbuchhuah Road (0.00 - 1.760) Kmp (Sh:Formation Cutting, Culvert & Retaining Walls & Construction of Road Using Flexible Pavement) | 244.22 | Multi Modal Project Division | 17.12.18 | 24.10.21 | 100% | 196.96 | - | - | 100% | 196.96 | Completed on 23/10/2021
139 | Construction & Maintenance of Nalkawn to Rulkual Road (0.000-16.000) Kmp Group A (Sh: Const.of Road using Cold Mix Technology | 1078.79 | Multi Modal Project Division | 04.01.21 | 04.01.23 | 100% | 1194.51 | - | - | 100% | 1194.51 | Completed on 29.9.22
140 | Construction & Maintenance of Nalkawn to Rulkual Road (16.000-32.000) Kmp Group B (Sh: Const.of Road using Cold Mix Technology | 1315.37 | Multi Modal Project Division | 10.02.20 | 30.09.22 | 17.51% | 476.65 | - | - | 17.51% | 467.63 | The contractor is expired and balance work is being prepared for NIT.
141 | Construction & Maintenance of Rawmibawk to Phalrang Road (0.000-10.200) Kmp (Sh: Const.of Road usinggroove concrete Technology | 759.92 | Multi Modal Project Division | 13.12.18 | 30.09.22 | 100% | 674.31 | - | - | 100% | 674.31 | Completed on 29.9.22
142 | Construction & Maintenance of Saiha to Rawmibawk Road (0.000-22.30) Kmp (Sh: Const.of Road using groove concrete Technology | 1941.19 | Multi Modal Project Division | 17.06.19 | 30.09.22 | 60.81% | 1642.89 | 39.19% | - | 100% | 1642.89 | Phy.Completed on 29.03.23

## SEDP
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding: SEDP | [8 empty] | Month : May 2023
Sl. no | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the Month |  | Overall cumulative achievement |  | Remarks
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
1 | Junction Improvement of Bawngkawn to ITI Road below Pu Sangnova (L) House (at Zirtiri College Junction) | 53.36 | Aizawl Road North Division |  |  | - | - | - | - | - | - | Land acquisition problem
2 | Const. of Approach Road to Aizawl College at Mualpui | 415 | Aizawl Road South Division | 26.07.21 | 26.04.22 | 73% | 300 | - | - | 73% | 300 | Work in progress
3 | Re-Construction of Concrete Pavement on Approach Road to Mission Vengthlang Cemetry, L=150M | 8.51 | Aizawl Road South Division | [8 empty] | Works not yet started
3 | Construction of High Court Parking Building at MINECO | 1960 | Project Division-I | 2.7.20 | 30.10.23 | 71% | 917.4 | 1% | - | 72% | 917.4
4 | Construction of Govt.Staff Quarter (Block-A) at DIET Complex | 439.2 | Project Division-I | 23.4.22 | 22.4.24 | 80% | 275.94 | 5% | - | 85% | 275.94
5 | Construction of Govt.Staff Quarter (Block-B) at DIET Complex | 386.6 | Project Division-I | 28.8.22 | 28.8.24 | 14% | 0.25 | 1% | - | 15% | 0.25
6 | Construction of Rest House & Chowkider Quarter at PWD Complex Bilkhawthlir | 348.5 | Project Division-II | 15.12.20 | 28.02.23 | 100% | 308.57 | - | - | 100% | 308.57 | Work physically Completed
7 | Establishment of Company Headquarters at Vairengte | 200.53 | Project Division-II | 10.06.22 | 10.12.23 | 95% | 96.1 | 3% | 66.47 | 98% | 162.57 | Work in progress
8 | Const.of MBSE New Building and renovation of existing main Building | 1000 | Project Division-III | 22.2.21 | 18.2.23 | 69% | 449.13 | 1% |  | 70% | 449.13 | Pandemic crisis delayed work progress. Now work iis in progress
9 | Construction of Link Drain on Vaivakawn lui & Hunthar Biak In lui (Sh: Construction of Gabion Wall on Biak In Kawr & Vaivakawn kawr at Hunthar sinking) | 436.89 | Project Division-IV | 25.10.21 | 25.04.22 | 100% | 436.89 | - | - | 100% | 436.89 | Completed
11 | Improvement of Khanpui - Tualbung Road Phase-II | 2935.99 | Saitual Division | 25.03.18 | 15.6.22 | 83% | 2020.31 | - | - | 83% | 2030.31
25 | Resurfacing of YMA Park to Centinary Road at Bilkhawthlir | 24.68 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 24.68 | - | - | 100% | 24.68 | Completed
26 | Resurfacing of Thirhruibankawn to Hmarveng Via Fire Station, Kolasib | 38 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 38 | - |  | 100% | 38 | Completed
27 | Resurfacing of Banglakawn to karkawn Via Primary School V at Tumpui | 15 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 15 | - | - | 100% | 15 | Completed
28 | Resurfacing of Ramenga's House to Helipad at Tumpui | 6 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 6 | - | - | 100% | 6 | Completed
29 | Resurfacing of NH-54 to CP road via Presbyterian Church, Ne Diakkawn | 4 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 4 | - | - | 100% | 4 | Completed
30 | Resurfacing Community Hall Zonunmawia's House at Tumpui | 3.22 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 3.22 | - | - | 100% | 3.22 | Completed
31 | Presbyterian Church to PHE Tlang Via Old BRTF Camp | 10.09 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 10.09 | - | - | 100% | 10.09 | Completed
32 | Construction of Cement Pavement on Kawnpui to Hortoki | 11.66 | Kolasib Division | 2023-03-23 | 2023-03-24 | 80% | 11.66 | 20% | - | 100% | 11.66 | Completed
33 | Resurfacing of Approach Road to Middle School-II (Kualmawi Middle School-II), Bilkhawthlir (0.00 Kmp to 0.260 Kmp) | 7.78 | Kolasib Division | 2023-03-23 | 2023-03-24 | 80% | 7.78 | 20% | - | 100% | 7.78 | On going
34 | Resurfacing of Saprema's House to Pu Lalrinenga's House at Bilkhawthlir | 5.31 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 5.31 | - | - | 100% | 5.31 | Completed
35 | Resurfacing of CP Road to Fundamental Baptist Church, Dikkawn, Kolasib | 3 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 3 |  | - | 100% | 3 | Completed
36 | Resurfacing of Pi Lalmuani's House to Pu Ralchhuana's House at Bilkhawthlir | 3 | Kolasib Division | 2023-03-23 | 2023-03-24 | - | 3 | 0.14% | - | 0.14% | 3 | On going
37 | Resurfacing of College Veng Presbyterian Church to MHIP Building College Veng, Kolasib | 15 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 15 | - | - | 100% | 15 | Completed
38 | Resurfacing od Kawnpui to Hortoki Road Balance Stretch Ch:14.140 Kmp to 14.760 Kmp | 15.43 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 15.43 | - | - | 100% | 15.43 | Completed
39 | Resurfacing of Approach Road Road from Zachhunga's House to Pianruala's House (Balance stretch) at Kawnpui Chhimveng | 13.19 | Kolasib Division | 2023-03-23 | 2023-03-24 | 40% | 13.19 | 60% | - | 100% | 13.19 | Completed
40 | Resurfacing of YMA Hall to Green Hills at Kawnpui Chhimveng | 11.58 | Kolasib Division | 2023-03-23 | 2023-03-24 | 80% | 11.58 | 20% | - | 100% | 11.58 | Completed
41 | Re-construction of Retaining Wall on Rengtekawn to NH-154 (zero point) At Ch: 0+800 Kmp | 5 | Kolasib Division | 2023-03-23 | 2023-03-24 | 20% | 5 | 40% | - | 60% | 5 | On-Going
| At Ch: 3+200 Kmp | 6 | Kolasib Division | 2023-03-23 | 2023-03-24 | 90% | 6 | 10% | - | 100% | 6 | Completed
42 | Patch Repair of Serkhan to Bagha Road (N.Hlimen to Saipum) | 25 | Kolasib Division | 2023-03-23 | 2023-03-24 | 50% | 25 | - | - | 50% | 25 | On-Going
43 | Urgent Work for Reconstruction of RCC Slab Culvert on College Veng to Saihatlangkawn Road at Chainage 0.700 km | 44.11 | Siaha Division | - | 31.12.23 | 100% | 44.11 |  |  | 100% | 44.11 | Work completed
44 | Pot Hole Patching and Resurfacing on Er.VL Khuma Residence to Council Veng road from Chainage 0.000 Km to 0.750 Km | 27.27 | Siaha Division | - | - | 100% | 27.27 |  |  | 100% | 27.27 | Work completed
45 | Repair of Slab Culvert on Meisatla Forest Forest Chackgate to NH54 (NH54 to Tawngtaina) part-2 road at chainage 0.78 | 5.42 | Siaha Division | - | 28.2.23 | 100% | 5.42 |  |  | 100% | 5.42 | Work completed
46 | Pot Hole Patching and Resurfacing on Tourist Lodge junction to Helipad road from Chainage 0.000 km to 0.610 Km | 5.8 | Siaha Division | - | 28.2.23 | 100% | 5.8 |  |  | 100% | 5.8 | Work completed
47 | Strengthening of pavement on approach road to college vaih cemetery from Vaih-I (Govt.Saiha Collge Main Gate - V.John House )road from chainage 0.000 km to 0.260 km | 12.37 | Siaha Division | - | 28.2.23 | 100% | 12.37 |  |  | 100% | 12.37 | Work completed
48 | Strengthening of Strengthening of Kawlchaw to Serkawr road from chainage 8.000 km to 9.100 km | 33.92 | Siaha Division | - | 30.4.23 | 44.88% | - | 24.42% | - | 69.3% | - | Work in progress
49 | Reconstruction of collapsed HP Culvert at chainage 2.400 km on serkawr-Tuipang 'L' Road | 21.1 | Siaha Division | - | 30.4.23 | 100% | 21.1 |  |  | 100% | 21.1 | Work Completed
50 | Patching of Pot Holes and Resurfacing on Suakkunga Road to Prayer Hall at Bualpui 'NG' (Bethlehem junction to Sedailui) from chainage 0.000 to 1.019 km | 9.44 | Siaha Division | - | 30.4.23 | 33.33% | - | 66.67% | - | 100% | - | Work physically completed on 12.05.2023
51 | Patching of Pot Holes and Resurfacing on Lalthlan to Quarry road at Chhuarlung from chainage 0.000 to 0.550 km | 27.03 | Siaha Division | - | 30.4.24 | 100% | 27.03 |  |  | 100% | 27.03 | Work physically Completed on 10.04.2023
52 | Patching of Pot Holes and Resurfacing on Khurtelui to C.Khawthiaua House road at Bualpui 'NG' from chainage 0.000 to 0.272 km | 13.53 | Siaha Division | - | 30.4.25 | 100% | 13.53 |  |  | 100% | 13.53 | Work physically Completed on 30.04.2023
53 | Curve Improvement on ATL Road at Chainage 20.100 Kmp | 10 | Hmuifang Division | 18.02.23 | 31.03.23 | 100% | 10 |  |  | 100% | 10 | Completed
54 | Resurfacing of PWD Staff Lodge Approach Road at Aibawk | 10 | Hmuifang Division | 18.02.23 | 31.03.23 | 100% | 10 |  |  | 100% | 10 | Completed
55 | Resurfacing of Aizawl-Thenzawl-Lunglei Road (30.00 Kmp - 51.00 Kmp) | 1271.17 | Hmuifang Division | 18.12.23 | 31.03.23 | 52% | 210.61 | 19% | - | 71% | 210.61 | Work in progress
56 | Bad patch repair of Aizawl-Thenzawl-Lunglei Road (83.00 Kmp-100.00 Kmp) | 50 | Hmuifang Division | 18.12.23 | 31.03.23 | 100% | 50 |  |  | 100% | 50 | Completed
57 | Re-Construction of Hume pipe wing wall culvert at Ch.20.650 Kmp on Damdiai - Sialsuk Road (Location:20.650 Kmp) | 4.45 | Hmuifang Division | 18.12.23 | 31.03.23 | 100% | 4.45 |  |  | 100% | 4.45 | Completed
58 | Re-Construction of Hume pipe wing wall culvert at Ch.5.350 Kmp on Lungsei Road (Location:5.350 Kmp) | 6.5 | Hmuifang Division | 18.12.23 | 31.03.23 | 100% | 6.5 |  |  | 100% | 6.5 | Completed
59 | Patch Repair of Main Road at Thenzawl | 25 | Hmuifang Division | 18.02.23 | 31.03.23 | 100% | 25 |  |  | 100% | 25 | Completed
60 | Patch repair of Dinthar Veng Internal road at Thenzawl | 7.5 | Hmuifang Division | 18.12.23 | 31.03.23 | 100% | 7.5 |  |  | 100% | 7.5 | Completed
61 | Patch repair of Horticulture College approach road at Thenzawl | 10 | Hmuifang Division | 18.12.23 | 31.03.23 | 100% | 10 |  |  | 100% | 10 | Completed
62 | Patch repair of Rawpuichhip-Buarpui Road 81.000-88.000 Kmp (Section : S.Khawlek to New Khawlek) | 30 | Hmuifang Division | 18.12.23 | 31.03.23 | 100% | 30 |  |  | 100% | 30 | Completed
63 | Curve Improvement on ATL Road at Chaiage 17.700 Kmp | 10 | Hmuifang Division | 18.12.23 | 31.03.23 | 100% | 10 |  |  | 100% | 10 | Completed
64 | Resurfacing of Doctor's Quarter Approach Road at Sialsuk | 9 | Hmuifang Division | 18.12.23 | 31.03.23 | 100% | 9 |  |  | 100% | 9 | Completed
65 | Patch repair and resurfacing of Hualngohmun Internal Roads | 20 | Hmuifang Division | 18.12.23 | 31.03.23 | 100% | 20 |  |  | 100% | 20 | Completed
66 | Patch repair of Kelsih Internal Roads | 10 | Hmuifang Division | 18.12.23 | 31.03.23 | 100% | 10 |  |  | 100% | 10 | Completed
67 | Patch repair of Approach Road to Tachhip | 10 | Hmuifang Division | 18.12.23 | 31.03.23 | 100% | 10 |  |  | 100% | 10 | Completed
68 | Patch repair of Muallungthu to Khumtung Road | 20 | Hmuifang Division | 18.12.23 | 31.03.23 | 100% | 20 |  |  | 100% | 20 | Completed
69 | Patch repair of Aizawl-Thenzawl-Lunglei Road (63.00-71.00 Kmp) | 35 | Hmuifang Division | 18.12.23 | 31.03.23 | 100% | 35 |  |  | 100% | 35 | Completed

## SEDP 4 (hidden)
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding: SEDP | [8 empty] | Month : May 2022
Sl. no | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the Month |  | Overall cumulative achievement |  | Remarks
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
25 | Widening of Road infront of CE, PWD Building at Tuikhuahtlang | 46.5 | Aizawl Road South Division |  |  | 100% | 46.5
26 | Const. of Approach Road to Aizawl College at Mualpui | 415 | Aizawl Road South Division |  |  | 35% | 120.12
27 | Const. of Approach Road to T.Romana College from ITI to Mualpui Road | 464.9 | Aizawl Road South Division |  |  | 49% | 171.33
28 | Wideing of Curve near Zokhuma's House on Bethlehem Vengthlang to College Road | 38.5 | Aizawl Road South Division |  |  | 100% | 38.5
29 | Const.of Approach Road to Zopar Vaipuanpho | 50 |  |  |  | 100% | 50
30 | Improvement at 0.50 Kmp on Hridaikawn to Power Sub Station at Tlangnuam | 12.3 | Aizawl Road South Division |  |  | 100% | 12.3
31 | Concrete pavement from Kohhran Thianghlim Biak In to PHE Pump House road within Maubawk | 30.5 | Aizawl Road South Division |  |  | 100% | 30.5
32 | Const.of Composite Retaining Wall at Kawilun Republic Veng | 7 | Aizawl Road South Division |  |  | 100% | 7
33 | Re-Construcrion of Retaining Wall near T.Lalhmuntiama's house on Nursery to Mission Veng Road via Kawltheihuan | 2.19 | Aizawl Road South Division |  |  | 100% | 2.19
34 | Const.of Bridge on Chhinga Vengthar to Tuithiang Road | 586.36 | Aizawl Road South Division |  |  | 59% | 60
35 | Widening of Approach road with rigid pavement from Thlanmual to Dam veng at Tlangnuam | 55 | Aizawl Road South Division |  |  | 100% | -

## CSS
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding: CSS | [8 empty] | Month : May 2023
Sl. no | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the Month |  | Overall cumulative achievement |  | Remarks
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
1 | Construction of Polytechnic at Lawngtlai (Const.of Administrative cum Academic Block) | 800 | Lunglei Building Project Division | 18.3.13 | 1.05.19 | 100% | 624.62 | - | - | 100% | 624.62 | Civil Work Completed & IE fund transferred to EE (EL) LLi for execution
2 | Construction of Judicial Quarter at Lawngtlai Grade-I Qtr. | 110.58 | Lunglei Building Project Division | 8.6.20 | 31.3.23 | 73% | 32.19 | 3% | 32.56 | 76% | 64.75 | Work in progress. EOT in process
3 | Construction of Judicial Quarter at Lawngtlai Type-I & II Qtr. | 138.67 | Lunglei Building Project Division | 22.6.20 | 26.05.23 | 53% | 34.73 | 7% | - | 60% | 34.73 | Work in progress. EOT in process
4 | Const.of Administrative cum Academic Block for Polytechnic Thingsen Saiha | 501.08 | Lunglei Building Project Division | 15.03.16 | 30.6.19 | 60% | 103.76 | - | - | 60% | 103.76 | The contractor has stopped work due to no funds
5 | Const.of Hostel building for Polytechnic at Thingsen saiha | 191.83 | Lunglei Building Project Division | 15.3.16 | 30.6.19 | 80% | 80.41 | - | - | 80% | 80.41 | The contractor has stopped work due to no funds
6 | Construction of Staff Qtr Type I, II & III for Polytechnic at Thingsen Saiha | 77.1 | Lunglei Building Project Division | 06.10.15 | 30.6.19 | 87.5% | 61.04 | 12.5% | - | 100% | 61.04 | Civil work completed I/E not yet started. The contractor has stopped work due to no funds
7 | Const.of Type-IV Qtr for Polytechnic at Thingsen Saiha | 29.99 | Lunglei Building Project Division | 15.03.16 | 30.6.19 | 76.5% | 24.79 | - | - | 76.5% | 24.79 | The contractor has stopped work due to no funds
8 | Construction of District Court Building at Saiha. | 1803.39 | Lunglei Building Project Division | 10.9.18 | 28.04.23 | 98% | 1776.1 | 1% |  | 99% | 1776.1 | Civil work & I/E works completed and service connection awaited
9 | Construction of fast truck Court at Kolasib | 1375.74 | Project Division II | 20.09.22 | 20.09.24 | 15% | 237.47 | 5% | - | 20% | 237.47 | Work in progress
10 | Construction of Grade-I Judicial Quarters at Project Veng Kolasib | 215.58 | Project Division-II | 15.03.22 | 15.03.23 | 97% | 220.23 | 3% |  | 100% | 220.23 | Work Phy.completed
11 | Const.of Tourist Logde at Champhai | 270 | Project Division-III | 09.12.10 | 30.11.20 | 100% | 300 | - | - | 100% | 300 | Taken over by the Deeptt.on Dt.3.8.2021 LOC amounting to Rs.30.00 lakh submitted for clearing liability.Hene, release of LOC awaited for financial closure.
12 | Const.of Polytechnic at Chhiahtlang i) Approach Road | 800 | Project Division-III | 3.3.16 | 2.8.16 | 100% | 103.67 | - | - | 100% | 103.67 | Estimate based on SOR 2019 submitted as per written instruction of the client department. Waiting for approval.
ii) Administrative & Academic Block iii) Hostel Block iv) Staff Quarters
13 | Construction of General Nursing Midwifery Hostel at Champhai | 250 | Project Division-III | 13.07.22 | 13.07.24 | 67.5% | 127.89 | 0.4% | - | 67.9% | 127.89 | Work in progress

## MRF
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : Mizoram Road Fund Board (MRF) | [9 empty] | Month : March 2023
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummutive Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13

## MAP
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding: Maintenance Action Plan | [8 empty] | Month :April 2023
Sl. no | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the Month |  | Overall cumulative achievement |  | Remarks
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13

## LLBPR
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
IMPROVEMENT OF LUNGLEI TOWN ROAD 2022-2023 (ILTR ) | [8 empty] | Month : February 2023
Sl. no | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the Month |  | Overall cumulative achievement |  | Remarks
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
1 | Approach Road to Kendrya School at Ramthar Veng (Nursing School Approach Road Kendrya School Ramthar Veng) | 38.98 | Lunglei Road Division I |  |  | - | - | - | - | - | - | Not Yet Started
2 | Strengthening of Paveement from Kikawn to AOC at Selected Stretches | 50.68 | Lunglei Road Division I |  |  | - | - | - | - | - | - | Not Yet Started
3 | JB Press to Sobji Bazar (0.00-0.307) | 6.17 | Lunglei Road Division I |  |  | - | - | 50% | - | 50% | - | Work in Progress
4 | Parallel Road from Pu Lalpara's House to Presbyterian church ( Part I ) | 15.22 | Lunglei Road Division I |  |  | - | - | - | - | - | - | Not Yet Started
5 | AOC to District Road ( AOC Ramthar District Road ) | 6.78 | Lunglei Road Division I |  |  | - | - | - | - | - | - | Not Yet Started
6 | MAP Complex Internal Road ( Commanding Bungalow to Thangte Peng | 22.37 | Lunglei Road Division I |  |  | - | - | - | - | - | - | Not Yet Started
7 | Z.Rosanga Road at Lunglawn ( NH 54A Z. Rosanga;s House ) | 3.37 | Lunglei Road Division I |  |  | - | - | - | - | - | - | Not Yet Started
8 | NH 54A to Lunglawn Hmunhlui Tlang via Pu H.Lalzarliana;s House (NH 54A Main Road PC Thlamuana's House ) | 2.41 | Lunglei Road Division I |  |  | - | - | 45% | - | 45% | - | Work in Progress
9 | JH Lalduhawma's House to Venghlun Cemetry Venghlun | 19.12 | Lunglei Road Division I |  |  | - | - | - | - | - | - | Not Yet Started
10 | Sserkawn Hospital to DIET, Melte, Lunglei. ( 0.00-1.350kmp ) | 28.18 | Lunglei Road Division I |  |  | - | - | - | - | - | - | Not Yet Started
11 | Patch repair & Re-surfacing of VCP Hall Serkawn to Chawngbawla Point Zotlang ( 0.00-1.590 kmp ) | 31.65 | Lunglei Road Division I |  |  | - | - | - | - | - | - | Not Yet Started
12 | Patch repair & Re-surfacing of Zohnuai Approach Road ( 0.00-0.50 kmp ) | 12.55 | Lunglei Road Division I |  |  | - | - | - | - | - | - | Not Yet Started
13 | Centenary Road Serkawn ( Serkawn Christian Hospital, Serkawn Pastor Quarters (0.00-0.540 ) | 10.93 | Lunglei Road Division I |  |  | - | - | - | - | - | - | Not Yet Started
14 | Approach Road to LDSC Ground No.II from District Road (District Road LDSC Ground No II | 5.03 | Lunglei Road Division I |  |  | - | - | - | - | - | - | Not Yet Started
15 | Salem Internal Road ( NH 54A to District Road ) | 11.63 | Lunglei Road Division I |  |  | - | - | 60% | - | 60% | - | Work in Progress
16 | Falkawn to District Road (Falkawn District Road) | 10.56 | Lunglei Road Division I |  |  | - | - | - | - | - | - | Not Yet Started
17 | Ramthar Veng Baptist Church Ring Road (AOC Ramthar Mazaras Spare Parts) | 4.97 | Lunglei Road Division I |  |  | - | - | - | - | - | - | Not Yet Started
18 | Resurfacing of MRB Junction to Mini Sport Complex Bunghmun | 6.76 | Lunglei Road Division I |  |  | - | - | - | - | - | - | Not Yet Started
19 | Resurfacing of MRB Junction to Falkawn Bunghmun | 13.53 | Lunglei Road Division I |  |  | - | - | - | - | - | - | Not Yet Started
20 | Resurfacing of District Road | 87.87 | Lunglei Road Division I |  |  | - | - | - | - | - | - | Not Yet Started
21 | esurfacing of Rahsi Veng to Tlabung Road via Sazaikawn (Forest Check Gate Tlabung Kawng) | 105.02 | Lunglei Road Division I |  |  | - | - | - | - | - | - | Not Yet Started
22 | Ressurfacing of LP Thangzika Shop to Forest Check Gate (LP Thangzika Shop to Forest Check Gate) | 37.2 | Lunglei Road Division I |  |  | - | - | - | - | - | - | Not Yet Started
23 | Resurfacing of Parallel Road from Pu Lalpara's House to Presbyterian Chucrh (Part 2) | 111.56 | Lunglei Road Division I |  |  | - | - | - | - | - | - | Not Yet Started
24 | Approach Road DC's Office From MST Bus Station (MST Bus Station DC Office) | 1.94 | Lunglei Road Division I |  |  | - | - | - | - | - | - | Not Yet Started
25 | Mizoram Rural Bank to DC Office via LAD Office (Mizoram Rurak Bank DC Office) | 4.88 | Lunglei Road Division I |  |  | - | - | - | - | - | - | Not Yet Started
26 | SE PWD Residence Approach Road (DCs Office SE Office) | 2.39 | Lunglei Road Division I |  |  | - | - | - | - | - | - | Not Yet Started
27 | DC Residence From SE PWD Qtr.Approach Road (SE PWD Qts DC Residence) | 0.73 | Lunglei Road Division I |  |  | - | - | - | - | - | - | Not Yet Started
28 | Damkawng Theiriat Road (C.Thangkimas House to Lalfakkimas House) | 3.47 | Lunglei Road Division I |  |  | - | - | - | - | - | - | Not Yet Started
29 | AOC to Kikawn Road | 49.31 | Lunglei Road Division I |  |  | - | - | - | - | - | - | Not Yet Started
30 | Construction of Retaining Wall on ATL Road to Kawmzawl Helipad Road Pukpui (At Ch=400.00m) | 3.51 | Lunglei Road Division I |  |  | - | - | - | - | - | - | Not Yet Started
31 | Construction of Breast Wall at 0.120 Kmp on Approach Road to Kendria School, Lunglei | 30.5 | Lunglei Road Division I |  |  | - | - | - | - | - | - | Not Yet Started
32 | Construction of Retaining Wall at 0.600 Kmp on Tlabung Peng to Colony PWD Road (Boundary of Venghlun and Rahsiveng) | 8.29 | Lunglei Road Division I |  |  | - | - | 30% | - | 30% | - | Work in Progress
33 | Construction of Retaining Wall at 1.100Kmp on 2nd Parallel Road, Bazar Veng, Lunglei | 6.86 | Lunglei Road Division I |  |  | - | - | 45% | - | 45% | - | Work in Progress
34 | Construction of Retaining Wall at 1.48 Kmp on Sangchem Road | 17.66 | Lunglei Road Division I |  |  | - | - | 50% | - | 50% | - | Work in Progress
35 | Retaining Wall of PWD Complex Bunghmun | 8.46 | Lunglei Road Division I |  |  | - | - | 100% | 8.46 | 100% | 8.46 | Completed
36 | Construction of Retaining Wall at Ch:31.500 Kmp on Lunglei to Buarpui Road | 29.64 | Lunglei Road Division I |  |  | - | - | 66% | 19.64 | 66% | 19.64 | Work in Progress
37 | Improvement of drainage system from Kikawn to AOC (Culverts & Cross drainage) | 34.53 | Lunglei Road Division I |  |  | - | - | - | - | - | - | Not Yet Started
38 | Construction of Retaining Wall at Ch:18.450 Kmp on Lunglei to Buarpui Road | 7.98 | Lunglei Road Division I |  |  | - | - | 68% | 5.41 | 68% | 5.41 | Work in Progress
39 | Construction of Retaining Wall at 18.500Kmp on Lunglei to Buarpui Road | 4.9 | Lunglei Road Division I |  |  | - | - | 67% | 3.31 | 67% | 3.31 | Work in Progress

## SASCI
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
| Source of funding : SASCI 2022-23 | [8 empty] | Month : May, 2023
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
1 | Construction of District Research Officers Quarters & Office Building at Hnahthial | 43 | Lunglei Building Project Division | 15.09.22 | 15.09.23 | 100% | 43 |  |  | 100% | 43 | Civil Works completed and Fund fro I/E transfer to Electrical Division
2 | Construction of Circuit House at Hnahthial | 304 | Lunglei Building Project Division | 13.04.23 | 13.10.24 |  |  | 10% |  | 10% |  | Layout has been done and work not yet started
3 | Strengthening of Infrastrucrture in 3 (three) new Districts in Mizoram (Sh: Const.of DC Office Building at Hnahthial | 1000 | Lunglei Building Project Division | 27.08.21 | 27.08.24 | 86% | 713.78 | 3% | 125.95 | 89% | 839.73 | Work in progress
4 | Construction of Sangau SDO© Office building at Sangau | 77 | Lunglei Building Project Division | 20.03.23 | 20.03.2024 |  |  | 5% |  | 5% |  | Work in progress
5 | Construction of SDO© Quarter at Sangau | 80 | Lunglei Building Project Division | 20.03.23 | 20.03.24 |  |  | 5% |  | 5% |  | Work in progress
6 | Construction of Staff Quarter(2 Units) at Sangau | 50.45 | Lunglei Building Project Division | 20.03.23 | 20.03.24 |  |  | 5% |  | 5% |  | Work in progress
7 | Construction of Volleyball Court at Gulsil Chawngte 'L' | 20 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 90% |  |  |  | 90% |  | Work in progress
8 | Construction of Meisatla Futsal Ground at Siaha | 34.78 | Lunglei Building Project Division | 20.03.23 | 20.09.23 | [6 empty] | Not yet started
9 | Construction of Futsal Playground at Gov't Higher secondary School at Siaha | 34.78 | Lunglei Building Project Division | 20.03.23 | 20.09.23 | [6 empty] | Not yet started
10 | Construction of New Football ground at Ramlaitui | 20 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | [6 empty] | Not yet started
11 | Construction of New Football Ground at Haulawng | 20 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | [6 empty] | Not yet started
12 | Construction of New Football Ground at Mualthuam 'N' | 20 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% |  |  |  | 100% |  | Phy.Completed
13 | Construction of New Football Ground at Mualthuam 'N' (on going) | 10 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% |  |  |  | 100% |  | Phy.Completed
14 | Construction of New Football Ground at Haulawng ( on going ) | 10 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | [6 empty] | Not yet started
15 | Construction of New Football Ground at Rawpui | 15 | Lunglei Building Project Division | 20.03.23 | 20.06.23 |  |  | 10% |  | 10% |  | Work in progress
16 | Construction of Community Hall at Pukpui | 80 | Lunglei Building Project Division | 20.03.23 | 20.03.24 |  |  | 5% |  | 5% |  | Work in progress
17 | Construction of New Badminton Hall at Chhipphir | 20 | Lunglei Building Project Division | 20.03.23 | 20.09.23 | [6 empty] | Not yet started
18 | Renovation of Community Hall at Farm Veng | 10 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% |  |  |  | 100% |  | Phy.Completed
19 | Renovation of Community Hall at Zobawk 'S' | 10 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 85% |  |  |  | 85% |  | Work in progress
20 | Renovation of Sport recreation House ( TT Hall) at Zobawk 'N' at Zobawk Bazar | 10 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 80% |  |  |  | 80% |  | Work in progress
21 | Painting & Electrification of Zobawk 'N' Hall | 12 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | [6 empty] | Not yet started
22 | Land development & Earthwork for Community Hall at Ralvawng | 10 | Lunglei Building Project Division | 20.03.23 | 20.06.23 |  |  | 30% |  | 30% |  | Work in progress
23 | Renovation of Community Hall at Leite | 5 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 90% |  |  |  | 90% |  | Work in progress
24 | Renovation of Public NGO's House at Leite | 5 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 70% |  |  |  | 70% |  | Work in progress
25 | Renovation of Community Hall at Rotlang 'E' | 5 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% |  |  |  | 100% |  | Phy.Completed
26 | Completion of Community Hall at Dawn | 8 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 95% |  |  |  | 95% |  | Work in progress
27 | Construction of Community Hall at Zehtet | 30 | Lunglei Building Project Division | 20.03.23 | 20.09.23 | 95% |  |  |  | 95% |  | Work in progress
28 | Construction of Community Hall at Lungrang 'S' | 40 | Lunglei Building Project Division | 20.03.23 | 20.03.24 | [6 empty] | Not yet started
29 | Construction of Community Hall | 12 | Lunglei Building Project Division | 20.03.23 | 20.09.23 |  |  | 60% |  | 60% |  | Work in progress
30 | Construction of Community Hall at Chhumkhum | 27.47 | Lunglei Building Project Division | 20.03.23 | 20.09.23 | 20% |  |  |  | 20% |  | Work in progress
31 | Construction of Community Hall at New Sachan | 27.47 | Lunglei Building Project Division | 20.03.23 | 20.09.23 | 100% |  |  |  | 100% |  | Phy.Completed
32 | Construction of Public Recreation House at Chanmari, Lunglei | 10 | Lunglei Building Project Division | 20.03.23 | 20.06.23 |  |  | 35% |  | 35% |  | Work in progress
33 | Construction of Old Aged Home cum Library House at Community Hall at Ramthar, Lunglei | 15 | Lunglei Building Project Division | 20.03.23 | 20.06.23 |  |  | 20% |  | 20% |  | Work in progress
34 | Construction of Women Recreation House or Cemetary House at Electric veng Lunglei (Women recreation house) | 10 | Lunglei Building Project Division | 20.03.23 | 20.06.23 |  |  | 20% |  | 20% |  | Work in progress
35 | Construction of NGO's House cum Library Room at Zobawk 'S' Vengthar | 10 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 50% |  |  |  | 50% |  | Work in progress
36 | Completion of NGO's Recreation House at Lungpuizawl | 5 | Lunglei Building Project Division | 20.03.23 | 20.06.23 |  |  | 70% |  | 70% |  | Work in progress
37 | Renovation of Women Recreation House at Lower Ramthar, Lunglei | 5 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 90% |  |  |  | 90% |  | Work in progress
38 | Construction of Waiting Shed & Godown of Animal Feed Building at dawn | 5 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% |  |  |  | 100% |  | Phy.Completed
39 | Construction of Women Recreation House at Upper Ramthar, Lunglei | 15 | Lunglei Building Project Division | 20.03.23 | 20.06.23 |  |  | 60% |  | 60% |  | Work in progress
40 | Construction of NGO's Recreation house at Farm Veng, lunglei | 10 | Lunglei Building Project Division | 20.03.23 | 20.06.23 |  |  | 85% |  | 85% |  | Work in progress
41 | Construction of Clinic Center Building at Bungtlang W | 5 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | [6 empty] | Not yet started
42 | Rahsiveng Market Shed | 52 | Lunglei Building Project Division | 20.03.23 | 20.09.23 | [6 empty] | Not yet started
Construction of Public Toilet, Cemetary House, Waiting Shed, Water Supply & Footpath at Lunglei and Bunghmun
43 | Constructuion of Toilet and Water Pint at Kawmzawl Helipad, aizawl to lunglei Helicopter service Station | 15 | Lunglei Building Project Division | 20.03.23 | 20.09.23 | [6 empty] | Not yet started
44 | Construction of Cemetary House at Chanmari, Lunglei | 15 | Lunglei Building Project Division | 20.03.23 | 20.06.23 |  |  | 35% |  | 35% |  | Work in progress
45 | Construction of Fencing & Cement Flooring at YMA hall courtyard at Electric Veng, Lunglei | 15 | Lunglei Building Project Division | 20.03.23 | 20.06.23 |  |  | 0.8 |  | 80% |  | Work in progress
46 | Construction of Public Store house and Urinal Shed at Electric Veng, Lunglei | 15 | Lunglei Building Project Division | 20.03.23 | 20.06.23 |  |  | 0.2 |  | 20% |  | Work in progress
47 | Construction of Waiting Shed near PWD Turning Point | 10 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | [6 empty] | Not yet started
48 | Estimate for Construction of Cemetary House at College Veng, lunglei | 5 | Lunglei Building Project Division | 20.03.23 | 20.06.23 |  |  | 60% |  | 60% |  | Work in progress
49 | Construction of Cemetary House at Bazar Veng Thlanmual No. 3 | 5 | Lunglei Building Project Division | 20.03.23 | 20.06.23 |  |  | 10% |  | 10% |  | Work in progress
50 | Construction of Boat Waiting shed at New Sachan | 0.69 | Lunglei Building Project Division | 20.03.23 | 20.05.23 |  |  | 100% |  | 100% |  | Phy.Completed
51 | Construction of Waiting near border Fencing inside India at Terabonia | 10.8 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% |  |  |  | 100% |  | Phy.Completed
52 | Construction of Boat Waiting Shed at Tuikawi | 0.69 | Lunglei Building Project Division | 20.03.23 | 20.05.23 |  |  | 100% |  | 100% |  | Phy.Completed
53 | Construction of Boat Waiting Shed at Sumasuri | 0.69 | Lunglei Building Project Division | 20.03.23 | 20.05.23 |  |  | 100% |  | 100% |  | Phy.Completed
54 | Construction of Boat waiting Shed at Old Sachan | 0.69 | Lunglei Building Project Division | 20.03.23 | 20.05.23 |  |  | 100% |  | 100% |  | Phy.Completed
55 | Construction of Waiting shed at Bungkawn, Lungchem | 0.69 | Lunglei Building Project Division | 20.03.23 | 20.05.23 |  |  | 100% |  | 100% |  | Phy.Completed
56 | Construction of Public Urinal near Vanlalhriara's House at Changpui | 0.73 | Lunglei Building Project Division | 20.03.23 | 20.06.23 |  |  | 100% |  | 100% |  | Phy.Completed
57 | Construction of Public Urinal near Hrangthuama's House at Changpui | 0.73 | Lunglei Building Project Division | 20.03.23 | 20.06.23 |  |  | 100% |  | 100% |  | Phy.Completed
58 | Construction of Urinal near Vanlalpianga's House at Dengsur | 0.73 | Lunglei Building Project Division | 20.03.23 | 20.06.23 |  |  | 100% |  | 100% |  | Phy.Completed
59 | Construction of Urinal near Thanthianga's House at Dengsur | 0.73 | Lunglei Building Project Division | 20.03.23 | 20.06.23 |  |  | 100% |  | 100% |  | Phy.Completed
60 | Construction of Urinal near Community Hall at Dengsur | 0.73 | Lunglei Building Project Division | 20.03.23 | 20.06.23 |  |  | 100% |  | 100% |  | Phy.Completed
61 | construction of Waiting Shed at Mangkhan Kawn, Dengsur | 10.8 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% |  |  |  | 100% |  | Phy.Completed
62 | Construction of Waiting shed at sabual & Dengsur Boundary. | 10.8 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% |  |  |  | 100% |  | Phy.Completed
63 | Construction of Waiting Shed near K.Vanlalruata's House at S.Khawlek | 1.08 | Lunglei Building Project Division | 20.03.23 | 20.06.23 |  |  | 100% |  | 100% |  | Phy.Completed
64 | Construction of Public Urinal near Information Centre Building at S.Khawlek | 0.73 | Lunglei Building Project Division | 20.03.23 | 20.06.23 |  |  | 100% |  | 100% |  | Phy.Completed
65 | Construction of Waiting shed at Dampui | 1.08 | Lunglei Building Project Division | 20.03.23 | 20.06.23 |  |  | 100% |  | 100% |  | Phy.Completed
66 | Construction of Cemetary House at Thenhlum | 0.76 | Lunglei Building Project Division | 20.03.23 | 20.06.23 |  |  | 100% |  | 100% |  | Phy.Completed
67 | Construction of Waiting Shed at Tawngtaina Hmun Zawlpui | 1.08 | Lunglei Building Project Division | 20.03.23 | 20.06.23 |  |  | 100% |  | 100% |  | Phy.Completed
68 | Construction of Bus Waiting Shed near Thantluanga's House at Belthei | 0.88 | Lunglei Building Project Division | 20.03.23 | 20.06.23 |  |  | 100% |  | 100% |  | Phy.Completed
69 | Construction of Waiting Shed at Tuisenchhuah | 10.8 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% |  |  |  | 100% |  | Phy.Completed
70 | Construction of Cemetary House at Rangte | 0.76 | Lunglei Building Project Division | 20.03.23 | 20.06.23 |  |  | 100% |  | 100% |  | Phy.Completed
71 | Stainless Steel Railling with Checker Tiles | 6 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 70% |  |  |  | 70% |  | Work in progress
72 | River view & Resting shed. ( Tlabung) | 9.5 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 90% |  |  |  | 90% |  | Work in progress
73 | Urinal Building with Side Drain Cover (Tlabung) | 5 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% |  |  |  | 100% |  | Phy.Completed
74 | Lowering of Siahatla field at Siaha | 35.97 | Lunglei Building Project Division | 20.03.23 | 20.03.24 | 95% |  |  |  | 95% |  | Work in progress
75 | Construction of Bazar Shed at Tuichawng | 5 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% |  |  |  | 100% |  | Phy.Completed
76 | Construction of MHIP Building at Bunghmun | 17.71 | Lunglei Building Project Division | 20.03.23 | 20.09.23 | 95% |  |  |  | 95% |  | Work in progress
77 | Construction of Anganwadi Centre at Zodin | 4.5 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% |  |  |  | 100% |  | Phy.Completed
78 | Construction of Playground at Chawngte 'L' | 40 | Lunglei Building Project Division | 20.03.23 | 20.09.23 | 85% |  |  |  | 85% |  | Work in progress
SUB DIVISION-I
1. CONSTRUCTION AND UPGRADATION OF ROAD FROM BAWNGKAWN TO RAMHLUN NORTH, AIZAWL
RAMHLUN NORTH
79 | Extension of Slab Culvert Side drain with cover Near Pi Duhawmi House at Ramhlun North | 0.81 | Aizawl Road North Division | - | - | 100% | - |  | 0.41 | 100% | 0.41 | Phy.Completed
80 | Construction of RCC Balcony Vety Qtr to Pu Lalrinsanga House Ramhlun North Basic Mual at Ramhlun North | 29.55 | Aizawl Road North Division | - | - | 30% |  | 50% | 14.77 | 80% | 14.77 | Work in progress
81 | Construction of PCC Pavement on AMC road Ramhlun North | 4.52 | Aizawl Road North Division | - | - | 100% |  |  | 2.26 | 100% | 2.26 | Phy.Completed
82 | Construction of Breast Wall near Pi Lalthlamuani at Ramhlun North | 2.49 | Aizawl Road North Division | - | - | 100% |  |  | 1.25 | 100% | 1.25 | Phy.Completed
83 | Construction of Retaining wall near Pi Duhawmi at Ramhlun North | 3.57 | Aizawl Road North Division | - | - | 100% |  |  | 1.79 | 100% | 1.79 | Phy.Completed
84 | Construction of Retaining Wall near Pi Thangluri at Ramhlun North | 7.66 | Aizawl Road North Division | - | - | 100% |  |  | 3.83 | 100% | 3.83 | Phy.Completed
| RAMHLUN SOUTH |  |  | - | -
85 | Cons.of Side drain with cover steel on Centenary Tuikhur to rev.Vanlalbuaia House On Carmel road at Ramhlun South | 19.26 | Aizawl Road North Division | - | - | 100% |  |  | 9.63 | 100% | 9.63 | Phy.Completed
86 | Const.of RCC Rectangular Side drain with cover on Bawngkawn to ITI road at Ramhlun South | 30.88 | Aizawl Road North Division |  | - | 100% |  |  | 15.44 | 100% | 15.44 | Phy.Completed
87 | Const.of RCC Rectanggular Side drain with cover on Thlanmual to Darnam Lui at Ramhlun South | 10.05 | Aizawl Road North Division |  | - | 100% |  |  | 5.03 | 100% | 5.03 | Phy.Completed
88 | Const.of Retaining wall near Pu Rohnuna Varte house at Ramhlun South | 8.22 | Aizawl Road North Division |  | - | 100% |  |  | 4.11 | 100% | 4.11 | Phy.Completed
89 | Construction of RCC Retaining wall near Ralhnehthanga House at Ramhlun South | 5.22 | Aizawl Road North Division |  |  | 100% |  |  | 2.61 | 100% | 2.61 | Phy.Completed
RAMHLUN VENGLAI
90 | Const.of RCC Rectangular side drain with cover on Approach Road to NHC office near Lalnghakliani to Pi Vanhnuaithangi House at Ramhlun Venglai | 2.68 | Aizawl Road North Division |  |  | 100% |  |  | 1.34 | 100% | 1.34 | Phy.Completed
91 | Const.of RCC Rectangular side drain with cover Near Pu mabiaka House at Ramhlun Venglai | 6.12 | Aizawl Road North Division |  |  | 80% |  | 20% | 3.06 | 100% | 3.06 | Work in progress
92 | Const.of RCC Rectangular side drain with cover on Ramhlun Venglai PCI to PC.Vanlalena House at Ramhlun Venglai | 7.05 | Aizawl Road North Division |  |  | 100% |  |  | 3.52 | 100% | 3.52 | Phy.Completed
93 | Const.of RCC Rectangular side drain with cover near H.Lalbiakmawia House at Ramhlun Venglai | 3.02 | Aizawl Road North Division |  |  | 100% |  |  | 1.51 | 100% | 1.51 | Phy.Completed
94 | Const.of Steel cross drain near H.lalbiakmawia House (Lower) at Ramhlun Venglai | 0.75 | Aizawl Road North Division |  |  | 100% |  |  | 0.37 | 100% | 0.37 | Phy.Completed
95 | Const.of Widening & Breast Wall on Approach Road to NHC Office near Pi Lalnghakliani House to Pi Vanhnuaithangi House at Ramhlun Venglai | 15.88 | Aizawl Road North Division |  |  | 100% |  |  | 7.94 | 100% | 7.94 | Phy.Completed
96 | Const.of Breast Wall Extension with Side Drain on DIC Office at Ramhlun Venglai at Ramhlun Venglai | 13.1 | Aizawl Road North Division |  |  | 60% |  | 40% | 6.55 | 100% | 6.55 | Phy.Completed
RAMHLUN VENGTHAR
97 | Const.of RCC Rectangular side drain with cover near Ramhlun Vengthar taxi stand at Ramhlun Vengthar | 6.53 | Aizawl Road North Division |  |  | 100% |  |  | 3.27 | 100% | 3.27 | Phy.Completed
98 | Const.of RCC Rectangular side drain with cover on Tluangpui road (Pu lalthawmliana to Cosma Mantluanga House) at Ramhlun Vengthar | 4.71 | Aizawl Road North Division |  |  | 100% |  |  | 2.35 | 100% | 2.35 | Phy.Completed
99 | Const.of RCC Rectangular side drain with cover on Zohmasawna House to bangla Lui at ramhlun Vengthar | 6.63 | Aizawl Road North Division |  |  | 100% |  |  | 3.32 | 100% | 3.32 | Phy.Completed
100 | Const.of RCC Rectangular side drain with cover on Sihpui to Ramhlun Vengthar Bus turning point at Ramhlun Vengthar | 11.25 | Aizawl Road North Division |  |  | 100% |  |  | 5.62 | 100% | 5.62 | Phy.Completed
101 | Const.of RCC Rectangular Cross drain with cover near Waiting Shed at Ramhlun Vengthar | 0.75 | Aizawl Road North Division |  |  | 100% |  |  | 0.37 | 100% | 0.37 | Phy.Completed
102 | Const.of Link drain near V.Lalvela House at Ramhlun Vengthar | 1.68 | Aizawl Road North Division |  |  | 100% |  |  | 0.84 | 100% | 0.84 | Phy.Completed
RAMHLUN SPORT COMPLEX
103 | Const.of RCC Rectangular Cross drain with cover near B.Lalthlamuana (L) House at Ramhlun Sport Complex | 0.73 | Aizawl Road North Division |  |  | 100% |  |  | 0.37 | 100% | 0.37 | Phy.Completed
104 | Const.of RCC Rectangular Side drain with cover near B.Lalthlamuana (L) House at Ramhlun Sport Complex | 2.52 | Aizawl Road North Division |  |  | 100% |  |  | 1.26 | 100% | 1.26 | Phy.Completed
105 | Const.of Link drain near B.Lalthlamuana (L) House at Ramhlun Sport Complex | 1.61 | Aizawl Road North Division |  |  | 100% |  |  | 0.81 | 100% | 0.81 | Phy.Completed
106 | Const.of steel cross drain near Laldinliana House at Ramhlun Sport Complex | 0.55 | Aizawl Road North Division |  |  | 100% |  |  | 0.27 | 100% | 0.27 | Phy.Completed
107 | Const.of RCC Rectangular Side drain with cover near Laldinliana House at Ramhlun Sport Complex | 0.7 | Aizawl Road North Division |  |  | 100% |  |  | 0.35 | 100% | 0.35 | Phy.Completed
108 | Const.of PCC Pavement near ICI road at Ramhlun Sport Complex | 1.4 | Aizawl Road North Division |  |  | 100% |  |  | 0.7 | 100% | 0.7 | Phy.Completed
109 | Const.of Retaining Wall on ICI road at Ramhlun Sport Complex | 5.83 | Aizawl Road North Division |  |  | 100% |  |  | 2.91 | 100% | 2.91 | Phy.Completed
110 | Const.of PCC Pavement on Pu Hrekima House to Zohmingsanga House at Ramhlun Sport Complex | 2.53 | Aizawl Road North Division |  |  | 100% |  |  | 1.26 | 100% | 1.26 | Phy.Completed
111 | Const.of PCC Pavement near Laldinliana House at Ramhlun Sport Complex | 1.69 | Aizawl Road North Division |  |  | 100% |  |  | 0.84 | 100% | 0.84 | Phy.Completed
112 | Const.of Breast wall near Laldinliana House at Ramhlun Sport Complex | 2.22 | Aizawl Road North Division |  |  | 100% |  |  | 1.11 | 100% | 1.11 | Phy.Completed
113 | Const.of Retaining wall near Pu Hrekima House at Ramhlun Sport Complex | 2.25 | Aizawl Road North Division |  |  | 100% |  |  | 1.12 | 100% | 1.12 | Phy.Completed
114 | Const.of Retaining wall on LC Road to Lalfakawmi House at Ramhlun Sport Complex | 1.44 | Aizawl Road North Division |  |  | 100% |  |  | 0.72 | 100% | 0.72 | Phy.Completed
115 | Const.of Retaining wall near Pu Lingngoa at Ramhlun Sport Complex | 1.54 | Aizawl Road North Division |  |  | 100% |  |  | 0.77 | 100% | 0.77 | Phy.Completed
116 | Const.of Retaining wall near Kiamlova House at Ramhlun Sport Complex | 7.52 | Aizawl Road North Division |  |  | 100% |  |  | 3.76 | 100% | 3.76 | Phy.Completed
117 | Const.of Retaining wall block-I on LC road Lianhnuna House to Buchhawna ME School at Ramhlun Sport Complex | 3.69 | Aizawl Road North Division |  |  | 100% |  |  | 1.84 | 100% | 1.84 | Phy.Completed
118 | Const.of Retaining wall block-II on LC road Lianhnuna House to Buchhawna ME School at Ramhlun Sport Complex | 5.26 | Aizawl Road North Division |  |  | 100% |  |  | 2.63 | 100% | 2.63 | Phy.Completed
119 | Const.of Retaining wall block-III on LC road Lianhnuna House to Buchhawna ME School at Ramhlun Sport Complex | 7.56 | Aizawl Road North Division |  |  | 10% |  | 90% | 3.78 | 100% | 3.78 | Work in progress
120 | Const.of Retaining wall block-IV on LC road Lianhnuna House to Buchhawna ME School at Ramhlun Sport Complex | 7.03 | Aizawl Road North Division |  |  | 100% |  |  | 3.52 | 100% | 3.52 | Phy.Completed
121 | Const.of Retaining wall Near YMA ram at Ramhlun Sport Complex | 7.17 | Aizawl Road North Division |  |  | 100% |  |  | 3.59 | 100% | 3.59 | Phy.Completed
122 | Const.of Retaining wall Near Bangla Lui at Ramhlun Sport Complex | 13.45 | Aizawl Road North Division |  |  | 90% |  | 10% | 6.73 | 100% | 6.73 | Work in progress
123 | Const.of Retaining wall Near Bangla Lui Counterford at Ramhlun Sport Complex | 8.84 | Aizawl Road North Division |  |  | 100% |  |  | 4.42 | 100% | 4.42 | Phy.Completed
124 | Const.of PCC Pavement on Presbyterian Biak In road at Ramhlun Sport Complex Vengthlang | 3.89 | Aizawl Road North Division |  |  | 100% |  |  | 1.94 | 100% | 1.94 | Phy.Completed
125 | Const.of PCC Pavement on Ramhlun Vengthar road at Ramhlun Sport Complex Vengthlang | 4.11 | Aizawl Road North Division |  |  | 95% |  | 5% | 2.05 | 100% | 2.05 | Work in progress
126 | Const.of PCC Pavement on Ringzova road to Pu Lalbiakliana House at Ramhlun Sport Complex Vengthlang | 3.89 | Aizawl Road North Division |  |  | 100% |  |  | 1.94 | 100% | 1.94 | Phy.Completed
BAWNGKAWN SOUTH
127 | Const.of Link drain between Ou Darringaia's House to Pu Lalensanga's House at Bawngkawn 'S' | 9.55 | Aizawl Road North Division |  |  | 100% |  |  | 4.77 | 100% | 4.77 | Phy.Completed
128 | Const.of Hand Railing for Public Step near Pi Mangkungi House Bawngkawn 'S' | 3.11 | Aizawl Road North Division |  |  | 100% |  |  | 1.56 | 100% | 1.56 | Phy.Completed
129 | Const.of Hand Railing for Public Step near YMA Hall, Bawngkawn 'S' | 0.81 | Aizawl Road North Division |  |  | 100% |  |  | 0.41 | 100% | 0.41 | Phy.Completed
130 | Const.of Hand Railing for Public Step near Pu Tlangdingliana House Bawngkawn 'S' | 2.11 | Aizawl Road North Division |  |  | 100% |  |  | 1.06 | 100% | 1.06 | Phy.Completed
131 | Const.of Hand Railing for Public footpath near YMA Hall, Bawngkawn 'S' | 1.81 | Aizawl Road North Division |  |  | 100% |  |  | 0.91 | 100% | 0.91 | Phy.Completed
132 | Const.of Retaining wall near YMA Hall, Bawngkawn 'S' | 1.41 | Aizawl Road North Division |  |  | 100% | - |  | 0.7 | 100% | 0.7 | Phy.Completed
133 | Const.of Retaining wall near transformer on Pu Liansailova road at Bawngkawn 'S' | 1.66 | Aizawl Road North Division |  |  | 100% | - |  | 0.83 | 100% | 0.83 | Phy.Completed
134 | Construction of PCC Pavement on Pu Liansailova Road at Bawngkawn South | 3.36 | Aizawl Road North Division |  |  | 100% | - |  | 1.68 | 100% | 1.68 | Phy.Completed
135 | Repair of Side drain near Pu Tlangdingliana House | 0.36 | Aizawl Road North Division |  |  | 100% | - |  | 0.18 | 100% | 0.18 | Phy.Completed
2. CONSTRUCTION AND UPGRADATION OF ROAD FROM BAWNGKAWN TO RAMHLUN NORTH, AIZAWL
ZARKAWT
136 | Construction of RCC Rectangular Side drain with cover on P.Lalvuana to R.Lalhmachhuana House at Aizawl Venglai | 77.98 | Aizawl Road North Division | [5 empty] | 11.7 |  | 11.7
| Widening=150Rm |  |  |  |  | 15% |  |  |  | 15% |  | Work in progress
| Breast Wall - 3 nos-75Rm |  |  |  |  | 0% |  |  |  | 0% |  | Not yet started
| V-Shape - 150Rm |  |  |  |  | 0% |  |  |  | 0% |  | Not yet started
| Concrete Pavement - 150Rm |  |  |  |  | 0% |  |  |  | 0% |  | Not yet started
AIZAWL VENGLAI
137 | Construction of of RCC Rectangular Side drain with cover on P.Lalvuana to R.Lalhmachhuana house at Aizawl Venglai | 3.36 | Aizawl Road North Division |  |  | 100% |  |  | 1.68 | 100% | 1.68 | Phy.Completed
138 | Construction of RCC Rectangular Side drain with cover on Taitea Tuikhur to YMA Hall at Aizawl Venglai | 7.01 | Aizawl Road North Division |  |  | 100% |  |  | 3.5 | 100% | 3.5 | Phy.Completed
139 | Construction of RCC Rectangular Side drain with cover on Pu Lalhluna House to Pu Nghinglova House at Aizawl Venglai | 1.26 | Aizawl Road North Division |  |  | 100% |  |  | 0.63 | 100% | 0.63 | Phy.Completed
140 | Construction of RCC Rectangular Side drain with cover on Pu Zosiama Garrage to Pi Lalbiaki House at Aizawl Venglai | 3.36 | Aizawl Road North Division |  |  | 100% |  |  | 1.68 | 100% | 1.68 | Phy.Completed
141 | Construction of Link drain on Chuangkimi to Benben step at Aizawl Venglai | 1.89 | Aizawl Road North Division |  |  | 100% |  |  | 0.95 | 100% | 0.95 | Phy.Completed
142 | Construction of Link drain on Pi Rosiami to Pi Lalmuanpuii House at Aizawl Venglai | 2.79 | Aizawl Road North Division |  |  | 100% |  |  | 1.4 | 100% | 1.4 | Phy.Completed
143 | Construction of Link drain near Pi Chuangkimi House at Aizawl Venglai | 2.7 | Aizawl Road North Division |  |  | 100% |  |  | 1.35 | 100% | 1.35 | Phy.Completed
144 | Construction of Link drain on Mini market to VDP House at Aizawl Venglai | 3.08 | Aizawl Road North Division |  |  | 100% |  |  | 1.54 | 100% | 1.54 | Phy.Completed
145 | Construction of V-Shape side drain on Zirtiri College to Pu Saptawnliana House at Aizawl Venglai | 2.68 | Aizawl Road North Division |  |  | 100% |  |  | 1.34 | 100% | 1.34 | Phy.Completed
146 | Construction of V-Shape side on Pu Sapliantawna to khurpui at Aizawl Venglai | 0.76 | Aizawl Road North Division |  |  | 100% |  |  | 0.38 | 100% | 0.38 | Phy.Completed
147 | Construction of V-Shape side on Lalnghinglova House to Chuangkimi House at Aizawl Venglai | 1.65 | Aizawl Road North Division |  |  | 100% |  |  | 0.82 | 100% | 0.82 | Phy.Completed
148 | Construction of V-Shape side drain on K.Zaneiha Garrage to Kawrhpui (Rozami House) at Aizawl Venglai | 2.16 | Aizawl Road North Division |  |  | 70% |  | 10% | 1.08 | 80% | 1.08 | Work in progress
149 | Construction of of Steel cross drain on near Pu J.Laltanpuia at Aizawl Venglai | 0.75 | Aizawl Road North Division |  |  | 100% |  |  | 0.37 | 100% | 0.37 | Phy.Completed
150 | Construction of of Steel cross drain on near Pi Chuangkimi House at Aizawl Venglai | 0.58 | Aizawl Road North Division |  |  | 100% |  |  | 0.29 | 100% | 0.29 | Phy.Completed
151 | Construction of Chequerred tile near MHIP House at Aizawl Venglai | 1.88 | Aizawl Road North Division |  |  | 100% |  |  | 0.94 | 100% | 0.94 | Phy.Completed
152 | Construction of Link drain cover near Pi Lalchawngpuii House at Aizawl Venglai | 1.88 | Aizawl Road North Division |  |  | 100% |  |  | 0.94 | 100% | 0.94 | Phy.Completed
153 | Construction of PCC Pavement on Middle School to Biakthuama House at Aizawl Venglai | 0.42 | Aizawl Road North Division |  |  | 100% |  |  | 0.21 | 100% | 0.21 | Phy.Completed
154 | Construction of Retaining Wall near VDP House at Aizawl Venglai | 0.58 | Aizawl Road North Division |  |  | 100% |  |  | 0.29 | 100% | 0.29 | Phy.Completed
155 | Construction of Link drain on Pi lalmuanpuii House to Pu KC.Vanlalruata House at Aizawl Venglai | 1.45 | Aizawl Road North Division |  |  | 100% |  |  | 0.72 | 100% | 0.72 | Phy.Completed
156 | Construction of Lowering & RCC Pavement near Pu Sangmawia (L) House at Aizawl Venglai | 1.25 | Aizawl Road North Division |  |  | 100% |  |  | 0.62 | 100% | 0.62 | Phy.Completed
157 | Construction of Chequrred tile near near Basketball Court at Aizawl Venglai | 1.49 | Aizawl Road North Division |  |  | 100% |  |  | 0.74 | 100% | 0.74 | Phy.Completed
RAMTHAR
158 | Construction of RCC Rectangular side drain with cover on Sihpui Taxi stand to Electric Vengthlang PCI at Ramthar | 9.6 | Aizawl Road North Division |  |  | 100% |  |  | 4.8 | 100% | 4.8 | Phy.Completed
159 | Construction of RCC Rectangular Cross drain with cover near David Malsawma House at Ramthar | 1.66 | Aizawl Road North Division |  |  | 100% |  |  | 0.83 | 100% | 0.83 | Phy.Completed
160 | Construction of Breast wall Below Pu K.Lalchawimawia House at Ramthar | 1.37 | Aizawl Road North Division |  |  | 100% |  |  | 0.68 | 100% | 0.68 | Phy.Completed
161 | Construction of PCC Pavement on Tetea Road | 2.81 | Aizawl Road North Division |  |  | 100% |  |  | 1.4 | 100% | 1.4 | Phy.Completed
162 | Construction of Retaining Wall near Pu Biakzaua House at Ramthar | 4.24 | Aizawl Road North Division |  |  | 100% |  |  | 2.12 | 100% | 2.12 | Phy.Completed
163 | Construction of Breast Wall Near C.Zothantluanga House at Ramthar | 1.53 | Aizawl Road North Division |  |  | 100% |  |  | 0.76 | 100% |  | Phy.Completed
164 | Construction of Chequrred tile and Hand railing near UPC (NEI) Church at Ramthar | 3.78 | Aizawl Road North Division |  |  | 100% |  |  | 1.89 | 100% |  | Phy.Completed
165 | Construction of Breast Wall on Pu Zothansanga Near UPC (MZ) Church Upper Galilie at Ramthar Veng at Ramthar | 3.52 | Aizawl Road North Division |  |  | 100% |  |  | 1.76 | 100% | 1.76 | Phy.Completed
166 | Construction of Retaining Wall Near Pu Lalhmunsiama House at Ramthar | 4.99 | Aizawl Road North Division |  |  | 100% |  |  | 2.49 | 100% | 2.49 | Phy.Completed
167 | Construction of Breast Wall Near SH.Lalkhama House at Ramthar | 4.51 | Aizawl Road North Division |  |  | 100% |  |  | 0.76 | 100% | 0.76 | Phy.Completed
168 | Construction of Retaining Wall Near Cfootpath Sihpui to upper Galilie at Ramthar | 2.63 | Aizawl Road North Division |  |  | 100% |  |  | 1.31 | 100% | 1.31 | Phy.Completed
169 | Construction of Retaining Wall Near Pu Laltlankima House at Ramthar | 2.93 | Aizawl Road North Division |  |  | 100% |  |  | 1.46 | 100% | 1.46 | Phy.Completed
170 | Construction of Step, Hand Railing and Widening near Tlangveng Taxi Stand at Ramthar | 2.44 | Aizawl Road North Division |  |  | 100% |  |  | 1.22 | 100% | 1.22 | Phy.Completed
171 | Construction of Widening and Breast Wall below Bishop House at Ramthar | 7.61 | Aizawl Road North Division |  |  | 100% |  |  | 3.81 | 100% | 3.81 | Phy.Completed
172 | Construction of Widening and Breast Wall Near Pu Lalbuanga House at Ramthar | 5.45 | Aizawl Road North Division |  |  | 100% |  |  | 2.73 | 100% | 2.73 | Phy.Completed
173 | Construction of RCC Pavement on Pu Thianghlima House to Pu B.Lalmalsawma House at Ramthar | 4.64 | Aizawl Road North Division |  |  | 100% |  |  | 2.32 | 100% | 2.32 | Phy.Completed
174 | Construction of Breast Wall Near Republic High School at Ramthar | 1.47 | Aizawl Road North Division |  |  | 100% |  |  | 0.73 | 100% | 0.73 | Phy.Completed
175 | Construction of Retaining Wall at Chainage 0.100 Kmp on Ramthar Cemetrey to Sihpui via Upper Galilie | 23.17 | Aizawl Road North Division |  |  | 100% |  |  | 11.59 | 100% | 11.59 | Phy.Completed
176 | Construction of Retaining Wall at Chainage 0.060 Kmp on Ramthar Cemetry to Sihpui via Upper Galilie Pu Lalbuanga House at Ramthar | 14.1 | Aizawl Road North Division |  |  | 100% |  |  | 7.05 | 100% | 7.05 | Phy.Completed
RAMTHAR NORTH
177 | Construction of RCC Rectangular side drain with cover on Electric Cemetry to Ruali Tuikhur at Ramthar North | 0.87 | Aizawl Road North Division |  |  | 100% |  |  | 0.44 | 100% | 0.44 | Phy.Completed
178 | Construction of Breast Wall on Tetea Road at Ramthar North | 1.43 | Aizawl Road North Division |  |  | 100% |  |  | 0.72 | 100% | 0.72 | Phy.Completed
179 | Construction of RCC Balcony near Ruali Tuikhur at Ramthar North | 4.71 | Aizawl Road North Division |  |  | 100% |  |  | 2.35 | 100% | 2.35 | Phy.Completed
180 | Construction of RCC Balcony on Tetea Road at Ramthar North | 5.4 | Aizawl Road North Division |  |  | 100% |  |  | 2.7 | 100% | 2.7 | Phy.Completed
181 | Construction of Retaining Wall on Tetea Road at Ramthar North | 11.42 | Aizawl Road North Division |  |  | 100% |  |  | 5.71 | 100% | 5.71 | Phy.Completed
182 | Construction of Retaining Wall on Near Electric Cemetry at Ramthar North | 7.77 | Aizawl Road North Division |  |  | 100% |  |  | 3.88 | 100% | 3.88 | Phy.Completed
SARON VENG
183 | Construction of RCC Link Drain with Cover at Saron Veng | 50 | Aizawl Road North Division
| Link Drain - 72Rm |  |  |  |  | 100% |  |  | 25 | 100% | 25 | Phy.Completed
| RCC Foot Step - 60Rm |  |  |  |  | 20% |  | 50% |  | 70% |  | Work in progress
| Pavement - 42.5Rm |  |  |  |  | 100% |  |  |  | 100% |  | Phy.Completed
| RCC Side Drain - 44.17Rm |  |  |  |  | 20% |  | 80% |  | 100% |  | Work in progress
3. CONSTRUCTION AND UPGRADATION OF ROAD FROM TUITHIANG - CHHINGA VENG - ARMED VENG - CHITE, AIZAWL
184 | Construction of PCC Pavement on District Jail to Lower Armed Veng Road (Service Road) | 68 | Aizawl Road North Division |  |  | 100% |  |  | 34 | 100% | 34 | Phy.Completed
185 | Construction of Concrete Pavement on Dawrpui Cemetery Internal Road betweenn Pu Thangdanga's House to Lalkima Sailo Site Junction | 16 | Aizawl Road North Division |  |  | 100% |  |  | 8 | 100% | 8 | Phy.Completed
186 | Construction of Concrete Pavement on District Jail to CRPF Road | 16 | Aizawl Road North Division |  |  | 100% |  |  | 8 | 100% | 8 | Phy.Completed
187 | Construction of New Road from Pu Lalhmingliana Sailo House to Pu Siamphunga Lei at Tuithiang Veng | 50 | Aizawl Road North Division | [5 empty] | 25 |  | 25
| RCC Balcony - 24Rm |  |  |  |  | 10% |  | 40% |  | 50% |  | Work in progress
| Retaining Wall - 3nos-50.70Rm |  |  |  |  | 100% |  |  |  | 100% |  | Phy.Completed
| Breast Wall - 27.00 Rm |  |  |  |  | 100% |  |  |  | 100% |  | Phy.Completed
| Concrete Pavement - 90.00Rm | [10 empty] | Not yet started
| Formation cutting - 86.00Rm |  |  |  |  | 100% |  |  |  | 100% |  | Work completed
188 | Consrtuction of Concrete Pavement on C.P Road chite Veng | 50 | Aizawl Road North Division | [5 empty] | 25 |  | 25
| Concrete Pavement - 380.00Rm |  |  |  |  | 30% |  | 70% |  | 100% |  | Work in progress
| Lowering & Widening -30Rm |  |  |  |  | 100% |  |  |  | 100% |  | Phy.Completed
| Slab Culvert - 1no |  |  |  |  | 100% |  |  |  | 100% |  | Phy.Completed
| Retaining Wall-12Rm |  |  |  |  | 100% |  |  |  | 100% |  | Phy.Completed
189 | Construction of RCC Balcony on Bethany Road at Chhinga Veng | 50 | Aizawl Road North Division |  |  | 40% |  | 10% | 25 | 50% | 25 | Work in progress
190 | Construction of Retaining Wall at Armed Veng near Pu lalkima House | 22 | Aizawl Road North Division | [5 empty] | 11 |  | 11
| Retaining Wall - 2nos-24.10Rm |  |  |  |  | 100% |  |  |  | 100% |  | Phy.Completed
| Breast Wall -15.00Rm |  |  |  |  | 100% |  |  |  | 100% |  | Phy.Completed
| Side Drain-55.00Rm |  |  |  |  | 100% |  |  |  | 100% |  | Phy.Completed
4. CONSTRUCTION CHECK DAM AT THEIHAI LUI, ARMED VENG
191 | Counterfort Retaining Wall at Armed Veng | 41.22 | Aizawl Road North Division | [8 empty] | Not yet started
192 | Toe Walls at Armed Veng side | 31.44 | Aizawl Road North Division | [8 empty] | Not yet started
193 | Retaining Wall at Ramthar side | 30.21 | Aizawl Road North Division | [8 empty] | Not yet started
194 | Counterfort Retaining Wall at Canara Bank | 43.62 | Aizawl Road North Division |  |  | 10% |  |  | 21.8 | 10% | 21.8 | Work in progress
195 | Retaining Wall at Canara Bank Bridge | 23.06 | Aizawl Road North Division | [8 empty] | Not yet started
196 | Const.of Breast Wall on Bazar Bungkawn to Chite Road near 1st Battalion MAP One Gate Armed Veng | 4.93 | Aizawl Road North Division | [8 empty] | Not yet started
197 | Construction of RCC Link Drain near Pu Phirthanga's House | 24.79 | Aizawl Road North Division | [8 empty] | Not yet started
198 | Const.of RCC Link Drain between Pu Lalrinsanga Hmar House to Pu Lalhuliana's House | 12.09 | Aizawl Road North Division | [8 empty] | Not yet started
199 | Const.of RCC Link Drain between Pu Ralkapa's House to Pu Darchhunga's House | 11.65 | Aizawl Road North Division | [8 empty] | Not yet started
200 | Const.of RCC Link Drain Pu Lalhmingthanga's House | 12.48 | Aizawl Road North Division | [8 empty] | Not yet started
201 | Const.of RCC Link Drain Pu Lalhmingthanga's House | 13.87 | Aizawl Road North Division | [8 empty] | Not yet started
202 | Const.of RCC Link Drain near Pu Rallianzuala's Land | 50.65 | Aizawl Road North Division | [8 empty] | Not yet started
SUB-DIVISION-II
203 | Construction of Link Drain from Lalzarliana at High School Veng at Zemabawk | 6.4 | Aizawl Road North Division |  |  | 100% |  |  | 3.2 | 100% | 3.2 | Phy.Completed
204 | Construction of Masonry Step from Pi Zahmingthangi to Dr.Robert Khawlhring Residence at Zemabawk | 7.51 | Aizawl Road North Division |  |  | 100% |  |  | 3.75 | 100% | 3.75 | Phy.Completed
205 | Const.of Link Drain at Mellimual 2 Tuikhur at Zemabawk | 6.4 | Aizawl Road North Division |  |  | 100% |  |  | 3.2 | 100% | 3.2 | Phy.Completed
206 | Construction of Slab Culvert Near Vety Dispensary at Zemabawk | 8.42 | Aizawl Road North Division |  |  | 100% | - |  | 4.21 | 100% | 4.21 | Phy.Completed
207 | Construction of Link drain Near Lalrinmawia Residence at Zemabawk | 4.06 | Aizawl Road North Division |  |  | 100% |  |  | 2.03 | 100% | 2.03 | Phy.Completed
208 | Construction of Side Drain with Cover at Approach Road to Cancer Hospital, Zemabawk | 3.71 | Aizawl Road North Division |  |  | 100% |  |  | 1.85 | 100% | 1.85 | Phy.Completed
209 | Construction of Slab Culvert Including Cross Drainage Dinthar Veng at Zemabawk | 2.03 | Aizawl Road North Division |  |  | 100% |  |  | 1.01 | 100% | 1.01 | Phy.Completed
210 | Construction of U-Shape Side Drain with Cover near Zemabawk North Biak In | 4.24 | Aizawl Road North Division |  |  | 100% |  |  | 2.12 | 100% | 2.12 | Phy.Completed
211 | Construction of Slab Culvert (2 Nos) at Berawlui to Thlanmual to Berawlui School | 12.18 | Aizawl Road North Division |  |  | 100% |  |  | 6.09 | 100% | 6.09 | Phy.Completed
212 | Construction of Slab Culvert including Link Drain at Middle School Veng, Zemabawk | 27 | Aizawl Road North Division |  |  | 100% |  |  | 13.5 | 100% | 13.5 | Phy.Completed
213 | Strengthening of Bethel Veng to High School Veng at Zemabawk | 36.7 | Aizawl Road North Division |  |  | 100% |  |  | 18.35 | 100% | 18.35 | Phy.Completed
214 | Construction of of RCC Frame Retaining Wall Including Concrete Pavement on Approach Road to Zemabawk Thlanmual No.1 | 12 | Aizawl Road North Division |  |  | 100% |  |  | 6 | 100% | 6 | Phy.Completed
215 | Construction of Rertaining Wall on Zemabawk Borth Field | 2.8 | Aizawl Road North Division |  |  | 100% |  |  | 1.4 | 100% | 1.4 | Phy.Completed
216 | Construction of RCC Frame Retaining Wall Beneath Zemabawk Thlanmual | 9.9 | Aizawl Road North Division |  |  | 100% |  |  | 4.95 | 100% | 4.95 | Phy.Completed
217 | Patch repiar & Seal Coating of approach road road to cancer Hospital at Zemabawk | 11.63 | Aizawl Road North Division |  |  | 5% |  |  | 5.82 | 5% | 5.82 | On going work
218 | Widening & Improvement of Approach Road to Cancer Hospital at Zemabawk | 136.46 | Aizawl Road North Division |  |  | 100% |  |  | 68.23 | 100% | 68.23 | Phy.Completed
219 | Widening and Construction of Retaining Wall at landslide prone area on Old Lunglei Road | 11.16 | Aizawl Road North Division |  |  | 100% |  |  | 5.58 | 100% | 5.58 | Phy.Completed
220 | Construction of Retaining Wall near Urban Hospital at Zemabawk | 7.81 | Aizawl Road North Division |  |  | 100% |  |  | 3.9 | 100% | 3.9 | Phy.Completed
221 | Concrete pavement of ANM to CMO at Zemabawk Vengthar Road | 19.72 | Aizawl Road North Division |  |  | 100% |  |  | 9.86 | 100% | 9.86 | Phy.Completed
222 | Construction of Cross drain & PCC Vshape side drain on approach Zemabawk road | 3.6 | Aizawl Road North Division | [8 empty] | Not yet started
223 | Construction of Retaining Wall Beneath Urban hospital at Zemabawk | 7.81 | Aizawl Road North Division |  |  | 100% |  |  | 3.9 | 100% | 3.9 | Phy.Completed
224 | Construction of Galili Veng to Vailui road upon Falkland | 7.1 | Aizawl Road North Division | [8 empty] | Not yet started
225 | Construction of Footpath and Retaining Wall on NH-54 near CRPF Camp at Zembawk | 46.57 | Aizawl Road North Division |  |  | 100% |  |  | 23.29 | 100% | 23.29 | Phy.Completed
226 | Construction of Retaining Wall at below R.D Godown at Zemabawk | 10.6 | Aizawl Road North Division |  |  | 100% |  |  | 5.3 | 100% | 5.3 | Phy.Completed
227 | Additional requirement for Construction Retaining Wall at the on-going construction of RCC Balcony Berawtlang approach road due to slide from uphill side | 21.2 | Aizawl Road North Division |  |  | 100% |  |  | 10.6 | 100% | 10.6 | Phy.Completed
228 | Construction of RCC frame R/wall on approach road to seventh Day Adventist Church at Zemabawk | 12.72 | Aizawl Road North Division |  |  | 5% |  | 55% | 6.36 | 60% | 6.36 | On going work
229 | Widening and Lowering of Sericulture to Thlanmual including conrete pavement & retaining Wall at Zemabawk North | 34.88 | Aizawl Road North Division |  |  | 100% |  |  | 17.44 | 100% | 17.44 | Phy.Completed
230 | Concrete pavement of Kailiana road (balance Portion) | 32.93 | Aizawl Road North Division |  |  | 100% |  |  | 16.47 | 100% | 16.47 | Phy.Completed
231 | Construction of Retaining Wall near Primary School at Zemabawk North | 2.09 | Aizawl Road North Division |  |  | 100% | - |  | 1.04 | 100% | 1.04 | Phy. Completed
232 | Concrete pavement of Dinthar to Muthi Lui kawng including Masonry U-Shape Side Drain at Zemabawk North | 29.87 | Aizawl Road North Division |  |  | 100% | - |  | 14.94 | 100% | 14.94 | Phy. Completed
233 | Construction of RCC Frame retaining wall including temporary side drain at Zemabawk North, Dinthar Veng | 21.2 | Aizawl Road North Division |  |  | 100% | - |  | 10.6 | 100% | 10.6 | Phy. Completed
234 | Widening at portion and construction of Retaining Wall at Zemabawk North Dinthar Veng | 6.36 | Aizawl Road North Division |  |  |  | - |  | 3.18 |  | 3.18 | Not Yet Started
235 | Concrete pavement of Bungbangla approach road | 10.05 | Aizawl Road North Division |  |  | 100% | - |  | 5.03 | 100% | 5.03 | Phy. Completed
236 | Formation cutting only Berawlui Thlanmual to School at Berawlui | 0.53 | Aizawl Road North Division |  |  | 100% | - |  | 0.26 | 100% | 0.26 | Phy. Completed
237 | Construction of Retaining Wall at Lungbial Zemabawk | 10.6 | Aizawl Road North Division |  |  | 5% | - | 55% | 5.3 | 60% | 5.3 | On going work
238 | Contsruction of Protection work on Lungbial Tuikhur to lalram farm (Landslide areas) (3.Nos.) | 20.99 | Aizawl Road North Division |  |  |  | - | 50% | 10.5 | 50% | 10.5 | On going work
239 | Construction of RCC Balcony at Lungbial | 30.18 | Aizawl Road North Division |  |  | 100% | - |  | 15.09 | 100% | 15.09 | Phy. Completed
240 | Construction of RCC Frame Retaining Wall Including Concrete Pavement on Approach Road to Zemabawk thlanmual No.1 | 12 | Aizawl Road North Division |  |  | 100% | - |  | 6 | 100% | 6 | Phy. Completed
241 | Construction of Link Drain, Culvert near primary School including PCC Concrete Pavement at Tuirial | 15.77 | Aizawl Road North Division |  |  | 100% | - |  | 7.88 | 100% | 7.88 | Phy. Completed
242 | Concrete pavement of NH 54 to Tlangveng Kawng at Tuirial (Balalnce portion) | 9.5 | Aizawl Road North Division |  |  | 100% | - |  | 4.75 | 100% | 4.75 | Phy. Completed
243 | Construction of RCC Concrete pavement of approach road to tuirial Lui | 14.6 | Aizawl Road North Division |  |  | 100% | - |  | 7.3 | 100% | 7.3 | Phy. Completed
244 | Concrete pavement of approach road to Tuirial Airfield from NH-54 | 110 | Aizawl Road North Division |  |  | 100% | - |  | 55 | 100% | 55 | Phy. Completed
245 | Profile Correction of Kutcha Road to Tuirial Airfield Mual thlang | 0.11 | Aizawl Road North Division |  |  | 100% | - |  | 0.05 | 100% | 0.05 | Phy. Completed
246 | Construction of PCC V shape Side drain on Muthi peng to Muthi Kawn | 10.93 | Aizawl Road North Division |  |  | 100% | - |  | 5.46 | 100% | 5.46 | Phy. Completed
247 | Construction of concrete pavement, retaining wall, PCC V shape drain & U shape drain at Muthi | 5.3 | Aizawl Road North Division |  |  | 100% | - |  | 2.65 | 100% | 2.65 | Phy. Completed
248 | Construction of PCC pavement of Chawngdailova House Hmingthansanga house, Muthi Vengthlang | 5.94 | Aizawl Road North Division |  |  | 100% | - |  | 2.97 | 100% | 2.97 | Phy. Completed
249 | Construction of Retaining wall near Lamhnai Tuikhur, Muthi | 11.93 | Aizawl Road North Division |  |  | 100% | - |  | 5.96 | 100% | 5.96 | Phy. Completed
250 | Construction of RCC Frame Retaining wall near Biakmawii residence at Muthi | 6.29 | Aizawl Road North Division |  |  | 100% | - |  | 3.14 | 100% | 3.14 | Phy. Completed
251 | Construction of PCC pavement of Sangnghinglove house to Engzami house, Muthi | 4.16 | Aizawl Road North Division |  |  | 100% | - |  | 2.08 | 100% | 2.08 | Phy. Completed
252 | Construction of Retaining wall on approach road to Muthi (1.800 kmp) | 7.5 | Aizawl Road North Division |  |  |  | - | 40% | 3.75 | 40% | 3.75 | On going work
253 | Strengthening of Approach road to LED Complex Muanna Veng including drainage work (Balance portion) Bituminous pavement | 54.7 | Aizawl Road North Division |  |  | 100% | - | 100% | 27.35 | 100% | 27.35 | Phy.Completed
254 | PCC U shape side drain | 0 | Aizawl Road North Division |  |  | 100% | - |  | - | 100% | - | Phy. Completed
255 | Concrete pavement of approach road to Muanna Veng Cemetary | 20.29 | Aizawl Road North Division |  |  | 20% | - |  | 10.14 | 100% | 10.14 | Phy.Completed
256 | Concrete pavement of approach road to YMA House at Muanna Veng | 8.12 | Aizawl Road North Division |  |  | 15% | - |  | 4.06 | 100% | 4.06 | Phy.Completed
257 | Junction improvement & strengthening of Zeda approach road including side drain, retaining walls at Zuangtui Resurfacing | 0.00 84.27 | Aizawl Road North Division |  |  | 100% | - |  | 42.14 | 100% | 42.14 | Phy.Completed
| Concrete pavement | 0 |  |  |  | 100% | - |  | - | 100% | - | Phy. Completed
258 | Concrete Pevement of Swan Industry to RK Lianzuala House at Zuangtui | 27.18 | Aizawl Road North Division |  |  | 100% | - |  | 13.59 | 100% | 13.59 | Phy. Completed
259 | Concrete Pavementof Zuangtui Vengthar road at Zuangtui | 39.82 | Aizawl Road North Division |  |  | 100% | - |  | 19.91 | 100% | 19.91 | Phy. Completed
260 | Construction of Retaining Wall at Zuangtui Industry Mual | 9.64 | Aizawl Road North Division |  |  | 100% | - |  | 4.82 | 100% | 4.82 | Phy. Completed
261 | Construction of Retaining Wall on approach road to Chhim Veng near Pi Ronghaki's House at Zuangtui | 8.48 | Aizawl Road North Division |  |  | 100% | - |  | 4.24 | 100% | 4.24 | Phy. Completed
262 | Earth work cutting, Construction of Retaining Wall, & Concrete flooring of Futsal Ground at Zuangtui Industry Mual | 63.02 | Aizawl Road North Division |  |  | 100% | - |  | 31.51 | 100% | 31.51 | Phy. Completed
263 | Concrete flooring of Futsal Ground at zuangtui | 22.94 | Aizawl Road North Division |  |  | 100% | - |  | 11.47 | 100% | 11.47 | Phy. Completed
264 | Construction of PCC Pavement on Zuangtui Vengthar (Balance Portion) | 31 | Aizawl Road North Division |  |  | - | - |  | - |  | - | Not Yet Started
265 | Construction of PCC V-Shape side drain on Zuangtui road to Thuampui Primary School | 3.5 | Aizawl Road North Division |  |  | - | - |  | - |  | - | Not Yet Started
266 | Construction of PCC V-shaped side drain near Pu Kama House, Laipuitlang | 0.37 | Aizawl Road North Division |  |  | 100% | - |  | 0.18 | 100% | 0.18 | Phy. Completed
267 | Construction of PCC V-shaped Side Drain near Pu Zakamlova House, Laipuitlang | 0.53 | Aizawl Road North Division |  |  | 100% | - |  | 0.26 | 100% | 0.26 | Phy. Completed
268 | Construction of PCC V-shaped Side Drain near Pu Lalengmawia House, Laipuitlang | 0.63 | Aizawl Road North Division |  |  | 100% | - |  | 0.32 | 100% | 0.32 | Phy. Completed
269 | Construction of PCC V-shaped Side Drain near Pu Marka House, Laipuitlang | 0.46 | Aizawl Road North Division |  |  | 100% | - |  | 0.23 | 100% | 0.23 | Phy. Completed
270 | Construction of Side Drain near Nazareth Hospital to DIET Junction at Chaltlang | 8.05 | Aizawl Road North Division |  |  | 100% | - |  | 4.02 | 100% | 4.02 | Phy. Completed
271 | Construction of of Side Drain with Cover between H.Hiato House to high School, Chaltlang | 8 | Aizawl Road North Division |  |  | 100% | - |  | 4 | 100% | 4 | Phy. Completed
272 | Construction of Retaining Wall at Chaltlang mear Pu Rophira's House | 4 | Aizawl Road North Division |  |  |  | - | 100% | 2 | 100% | 2 | Not Yet Started
273 | DIET Junction improvement | 57.03 | Aizawl Road North Division |  |  | 100% | - |  | 28.51 | 100% | 28.51 | Phy. Completed
274 | Construction of concrete Pavement of Chanmari Thlanmual Courtyard including junction Improvement (Sh: Seal Coating) | 2.35 | Aizawl Road North Division |  |  | - | - |  | - |  | - | Not Yet Started
| (Sh: RCC Frame Retaining Wall) | 3.25 |  |  |  | 100% | - |  | 1.63 | 100% | 1.63 | Phy Completed
| (Sh: Concrete Pavement) | 12.42 |  |  |  |  | - | 100% | 6.21 | 100% | 6.21 | Not Yet Started
275 | Construction of Protection Work for P&E Transformer at DIET Junction Chaltlang | 9.54 | Aizawl Road North Division |  |  | 100% | - |  | 4.77 | 100% | 4.77 | Phy Completed
276 | Construction of Concrete Pavement Chaltlang Lily Veng Cemetrery Road | 7.26 | Aizawl Road North Division |  |  | 100% | - |  | 3.63 | 100% | 3.63 | Phy Completed
277 | Construction of Retaing Wall at Chaltlang Lily Veng Cemetrery Road | 4.82 | Aizawl Road North Division |  |  | 100% | - |  | 2.41 | 100% | 2.41 | Phy Completed
278 | Construction of Railing wih chequered tiles at Chaltlang Dawrkawn | 8 | Aizawl Road North Division |  |  | 100% | - |  | 4 | 100% | 4 | Phy Completed
279 | Construction of Retaining Wall and Footpath at Chaltlang Veng Cemetery | 10 | Aizawl Road North Division |  |  | 100% | - |  | 5 | 100% | 5 | Phy Completed
280 | Improvement of Chaltlang Lily Veng to Chaltlang Link step near R.Lalropuia House | 5 | Aizawl Road North Division |  |  | 100% | - |  | 2.5 | 100% | 2.5 | Phy Completed
281 | Construction of approach road PCC & Side Drain from Chaltlang Dingdi Veng Turning Point to H.Lalluaia (L) House at Chaltlang Venglai | 16 | Aizawl Road North Division |  |  | 100% | - |  | 8 | 100% | 8 | Phy Completed
282 | Reconstruction of Chaltlang Lily Veng to Chaltlang Link Road near Lalthuthlungliana House | 8 | Aizawl Road North Division |  |  |  | - | 100% | 4 | 100% | 4 | Not Yet Started
283 | Construction of Retaining Wall near Pu Ralkapa House, Laipuitlang | 1.71 | Aizawl Road North Division |  |  | 100% | - |  | 0.85 | 100% | 0.85 | Phy Completed
284 | Construction of Retaining Wall near Pu Kama House, Laipuitlang | 1.19 | Aizawl Road North Division |  |  | 100% | - |  | 0.6 | 100% | 0.6 | Phy Completed
285 | Construction of Masonry Step including Hand Railing near Pu Kama House, Laipuitlang | 1.47 | Aizawl Road North Division |  |  | 100% | - |  | 0.73 | 100% | 0.73 | Phy Completed
286 | Construction of Retaining Wall near Pu Duhzuala House, Laipuitlang | 2.61 | Aizawl Road North Division |  |  | 100% | - |  | 1.31 | 100% | 1.31 | Phy Completed
287 | Construction of Step in concrete over Link Drain including Railing near Community Hall, Laipuitlang | 4.05 | Aizawl Road North Division |  |  | 100% | - |  | 2.03 | 100% | 2.03 | Phy Completed
288 | Construction of Retaining Wall including hand Railing near Pu Rama House, Laipuitlang | 1.86 | Aizawl Road North Division |  |  | 100% | - |  | 0.93 | 100% | 0.93 | Phy Completed
289 | Construction of Retaining Wall including hand Railing near Pi Dawli House, Laipuitlang | 3.37 | Aizawl Road North Division |  |  | 100% | - |  | 1.69 | 100% | 1.69 | Phy Completed
290 | Construction of Retaining Wall near Jubilee Hall Laipuitlang | 1.56 | Aizawl Road North Division |  |  | 100% | - |  | 0.78 | 100% | 0.78 | Phy Completed
291 | Construction of Hand Railing near C.Zonunmawia House, Laipuitlang | 0.63 | Aizawl Road North Division |  |  | 100% | - |  | 0.32 | 100% | 0.32 | Phy Completed
292 | Construction of Retaining Wall at Chaltlang near T.Thangchungnunga (L) | 4 | Aizawl Road North Division |  |  | 100% | - |  | 2 | 100% | 2 | Phy Completed
293 | Construction of PCC U-Shape Side Drain near Pu Thanseia House, Bawngkawn | 0.3 | Aizawl Road North Division |  |  | 100% | - |  | 0.15 | 100% | 0.15 | Phy Completed
294 | Construction of PCC U-Shape Side Drain including Steel Railing near Pu Lalduhkima House, Bawngkawn | 5.52 | Aizawl Road North Division |  |  | 100% | - |  | 2.76 | 100% | 2.76 | Phy Completed
295 | Construction of step over Link Drain including Railing near K.Lalhlunchhungi residence at Bawngkawn | 18.42 | Aizawl Road North Division |  |  | 100% | - |  | 9.21 | 100% | 9.21 | Phy Completed
296 | Construction of Link Drain Cover near Pu R.Romawia House at Bawngkawn | 4 | Aizawl Road North Division |  |  | 100% | - |  | 2 | 100% | 2 | Phy Completed
297 | Construction of Side Drain near Pu ElBethela House at Bawngkawn | 0.4 | Aizawl Road North Division |  |  | 100% | - |  | 0.2 | 100% | 0.2 | Phy Completed
298 | Construction of Side Drain near Pu Salemthara House at Bawngkawn | 1.3 | Aizawl Road North Division |  |  | 100% | - |  | 0.65 | 100% | 0.65 | Phy Completed
299 | Construction of Concrete Pavement of Brigade Slaughter House Road Bawngkawn | 58.3 | Aizawl Road North Division |  |  | 100% | - |  | 29.15 | 100% | 29.15 | Phy. Completed
300 | Construction of Brigade Internal Road at Bawngkawn | 14.84 | Aizawl Road North Division |  |  | 100% | - |  | 7.42 | 100% | 7.42 | Phy. Completed
301 | Construction of Steel Railing near Pu Rintluanga House, Bawngkawn | 2.18 | Aizawl Road North Division |  |  | 100% | - |  | 1.09 | 100% | 1.09 | Phy. Completed
302 | Construction of Step at Zotui Kawng at Bawngkawn | 2 | Aizawl Road North Division |  |  | 100% | - |  | 1 | 100% | 1 | Phy. Completed
303 | Construction of Step near PC Mawia House, Bawngkawn | 11 | Aizawl Road North Division |  |  | 100% | - |  | 5.5 | 100% | 5.5 | Phy. Completed
304 | Construction of Step and Hand railing at Shalom Veng | 8 | Aizawl Road North Division |  |  | 100% | - |  | 4 | 100% | 4 | Phy. Completed
305 | Construction RCC Balcony at YMA Zampuimanga | 5 | Aizawl Road North Division |  |  | 100% | - |  | 2.5 | 100% | 2.5 | Phy. Completed
306 | Construction of Step near Ramdinthara Tuikhur | 2 | Aizawl Road North Division |  |  | 100% | - |  | 1 | 100% | 1 | Phy. Completed
307 | Construction of Approach Road to Helipad from Bawngkawn Shalom Veng | 16 | Aizawl Road North Division |  |  | 100% | - |  | 8 | 100% | 8 | Phy. Completed
308 | PCC Flooring near Upa Chaldailova House, Bawngkawn | 3 | Aizawl Road North Division |  |  | 100% | - |  | 1.5 | 100% | 1.5 | Phy. Completed
309 | Construction of Step on Zotui Kawng | 2 | Aizawl Road North Division |  |  | 100% | - |  | 1 | 100% | 1 | Phy. Completed
310 | Construction of Approach Road from JK Manga House to Thlanmual Kawng | 10 | Aizawl Road North Division |  |  | 100% | - |  | 5 | 100% | 5 | Phy. Completed
311 | Construction of RCC Balcony on Approach Road to Bawngkawn Cemetry | 41.59 | Aizawl Road North Division |  |  | 100% | - |  | 20.79 | 100% | 20.79 | Phy. Completed
312 | Construction of Masonry U-Shape Side Drain at Thuampui Internal Road | 4.24 | Aizawl Road North Division |  |  | 100% | - |  | 2.12 | 100% | 2.12 | Phy. Completed
313 | Construction of Side Drain with cover at Zemabawk North Presbyterian Church Courtyard | 3.71 | Aizawl Road North Division |  |  | 100% | - |  | 1.86 | 100% | 1.86 | Phy. Completed
314 | Construction of Culvert Side Drain & RCC Frame Retaining Wall on Approach Road to Thuampui Cemetry | 11.34 | Aizawl Road North Division |  |  | 100% | - |  | 5.67 | 100% | 5.67 | Phy. Completed
315 | Concrete Pavement & Drainage works on Thuampui PRIMARY School to Zuangtui Vengthar (Balance Portion ) | 53.57 | Aizawl Road North Division |  |  | 100% | - |  | 26.78 | 100% | 26.78 | Phy. Completed
316 | Construction of Retaining Wall at 8.040Kmp on Thuampui - selesih Road | 9.95 | Aizawl Road North Division |  |  | 100% | - |  | 4.97 | 100% | 4.97 | Phy. Completed
317 | Construction of Concrete Pavement Approach Road to PB Vanlalauva Camping Center at Thuampui Selesih Road (Gospel Thunder Team) | 21.2 | Aizawl Road North Division |  |  | 100% | - |  | 10.6 | 100% | 10.6 | Phy. Completed
318 | Pavement of Thuampui Helipad | 24 | Aizawl Road North Division |  |  | 100% | - |  | 12 | 100% | 12 | Phy. Completed
319 | Construction of RCC Balcony on Durtlang Leitan to Thuampui Selesih Road at Ch:1.840 Kmp | 100.59 | Aizawl Road North Division |  |  |  | - |  | - |  | - | Not Yet Started
320 | Construction of Retaining Wall on Thuampui to Selesih Road at Ch:4.350 Kmp | 4 | Aizawl Road North Division |  |  | 60% | - | 40% | 2 | 100% | 2 | On going work
321 | Clearing of Landslip under Aizawl Road North Division | 9.2 | Aizawl Road North Division |  |  | 100% | - |  | 4.6 | 100% | 4.6 | Phy. Completed
322 | Seal Coating of Thuampui Cemetry Road | 29.83 | Aizawl Road North Division |  |  | 30% | - |  | 14.91 | 30% | 14.91 | On going work
323 | Construction of Retaining Wall at Salvation Army Turning Point, Thuampui | 3.94 | Aizawl Road North Division |  |  | 100% | - |  | 1.97 | 100% | 1.97 | Phy. Completed
324 | Concrete Pavement of Govt. Welfare Road at Thuampui | 37.94 | Aizawl Road North Division |  |  | 100% | - |  | 18.97 | 100% | 18.97 | Phy. Completed
325 | Earthwork Cutting, Construction of Retaining Wall & PCC Flooring of Futsal Ground at Thuampui | 51 | Aizawl Road North Division |  |  | 20% | - | 80% | 25.5 | 100% | 25.5 | Phy. Completed
326 | Construction of Approach Road to Thuampui Vengthar at Thuampui | 18.61 | Aizawl Road North Division |  |  | 15% | - | 85% | 9.3 | 100% | 9.3 | Phy. Completed
327 | Construction of Road below Thuampui Presbyterian Church | 15.9 | Aizawl Road North Division |  |  | 40% | - | 60% | 7.95 | 100% | 7.95 | Phy. Completed
328 | Concrete Pavement of liansailova Road, Thuampui | 26.97 | Aizawl Road North Division |  |  | 100% | - |  | 13.48 | 100% | 13.48 | Phy. Completed
329 | Construction of Gallery including Side Drain at Falkland | 6.9 | Aizawl Road North Division |  |  | 100% | - |  | 3.45 | 100% | 3.45 | Phy. Completed
330 | Construction of Masonry Link Drain near Mizoram UPC Chuech at Falkland | 5.32 | Aizawl Road North Division |  |  | 100% | - |  | 2.66 | 100% | 2.66 | Phy. Completed
331 | Seal Coating of Hebrai Veng at Falkland | 23.74 | Aizawl Road North Division |  |  | 100 | - |  | 11.87 | 100% | 11.87 | Phy Completed
332 | Construction of Retaining Wall on Tuikhur thlang at Falkland East including Masonry Cross Drain | 11.32 | Aizawl Road North Division |  |  | 100% | - |  | 5.66 | 100% | 5.66 | Phy. Completed
334 | Concrete Pavement at Falkland Veng | 15.27 | Aizawl Road North Division |  |  | 100% | - |  | 7.63 | 100% | 7.63 | Phy. Completed
335 | Construction of Step at Falkland Cemetry | 4.77 | Aizawl Road North Division |  |  | 100% | - |  | 2.38 | 100% | 2.38 | Phy. Completed
336 | Construction of Thlanmual No. 1 Shed at Falkland | 5.3 | Aizawl Road North Division |  |  | 100% | - |  | 2.65 | 100% | 2.65 | Phy. Completed
337 | Concrete Pavement of Peniel Road at Falkland | 13 | Aizawl Road North Division |  |  |  | - | 100% | 6.5 | 100% | 6.5 | Phy. Completed
338 | Bituminous pavement of Falkland East internal Road | 15 | Aizawl Road North Division |  |  | 50% | - | 50% | 7.5 | 100% | 7.5 | Phy. Completed
339 | Patch repair and Seal Coating of Middle School | 19.88 | Aizawl Road North Division |  |  | - | - | 100% | 9.94 | 100% | 9.94 | Phy. Completed
340 | Improvement of Approach Road to Falkland East Junction (Sh:Construction of RCC Framed Structure Retaining Wall) | 4.72 | Aizawl Road North Division |  |  | 100% | - |  | 2.36 | 100% | 2.36 | Phy Completed
341 | Improvement of Approach Road to Falkland East Junction (Sh:Pavement) | 2.79 | Aizawl Road North Division |  |  | 100% | - |  | 1.39 | 100% | 1.39 | Phy Completed
342 | Construction of Link Drain Near Pu Lalngamliana House to Sihphir Venglai | 6.96 | Aizawl Road North Division |  |  | 100% | - |  | 3.48 | 100% | 3.48 | Phy. Completed
343 | Construction of Concrete Pavement Link road from Sihphir Kawnveng to Khamrang Road (i/c Seal Coating of Sihphir Bypass Road via Selesih | 42.4 | Aizawl Road North Division |  |  | 100% | - |  | 21.2 | 100% | 21.2 | Phy Completed
344 | Construction of PCC V-Shape Side Drain on Sihphir Lower Lane, Sihphir Venghlun | 1 | Aizawl Road North Division |  |  | 100% | - |  | 0.5 | 100% | 0.5 | Phy. Completed
345 | Construction of Link Drain including extention of Culvert Near Pu Lalruatvela House, Sihphir Venghlun | 2.98 | Aizawl Road North Division |  |  | 100% | - |  | 1.49 | 100% | 1.49 | Phy. Completed
346 | Construction of Link Drain near Pu Lalngamliana House to Sihphir Venglai Biak In, Sihphir (Balance) | 5.3 | Aizawl Road North Division |  |  | 100% | - |  | 2.65 | 100% | 2.65 | Phy. Completed
347 | Construction of Cross Drainage, Passing place on Approach Road to Nausel | 5.89 | Aizawl Road North Division |  |  | 100% | - |  | 2.94 | 100% | 2.94 | Phy. Completed
348 | Construction of PCC V-Shape Side Drain on Nausel Road | 10.6 | Aizawl Road North Division |  |  | 100% | - |  | 5.3 | 100% | 5.3 | Phy. Completed
349 | Construction of Retaining Wall Sihphir Bypass Road | 15.03 | Aizawl Road North Division |  |  | 100% | - |  | 7.52 | 100% | 7.52 | Phy. Completed
350 | Concrete Pavement of Approach Road to Lalbiaki Residence to YMA Park at Sihphir Hmar Veng | 19.89 | Aizawl Road North Division |  |  | 100% | - |  | 9.95 | 100% | 9.95 | Phy. Completed
351 | Widening of Approach Road to SBI from Sihphir Lower lane Beneath Salvation Army Church | 7.89 | Aizawl Road North Division |  |  | 100% | - |  | 3.94 | 100% | 3.94 | Phy. Completed
352 | Construction of PCC Pavement High Atitude panna kawng | 16.23 | Aizawl Road North Division |  |  | 100% | - |  | 8.11 | 100% | 8.11 | Phy. Completed
353 | Constriction of Retaining Wall including Link Drain near K.Lalengzauva house at Sihphir Venghlun | 11.32 | Aizawl Road North Division |  |  | 100% | - |  | 5.66 | 100% | 5.66 | Phy. Completed
354 | Construction of Retaining Wall near Pi Remthangi Residence on Nausel Road, Sihphir Venghlun | 14.79 | Aizawl Road North Division |  |  | 100% | - |  | 7.4 | 100% | 7.4 | Phy. Completed
355 | Concrete Pavement of Approach Road to Sihphir Venghlun Cemetry | 10.06 | Aizawl Road North Division |  |  | 100% | - |  | 5.03 | 100% | 5.03 | Phy. Completed
356 | Concrete Pavement of Sihphir Venghlun Khawhnuai to Multipurpose Hall | 54.59 | Aizawl Road North Division |  |  | 100% | - |  | 27.3 | 100% | 27.3 | Phy Completed
357 | Concrete Pavement of Nausel Field Thlang | 12.23 | Aizawl Road North Division |  |  | 100% | - |  | 6.11 | 100% | 6.11 | Phy. Completed
358 | Construction of Slab Culvert from Sihphir to Khamrang Road | 21.2 | Aizawl Road North Division |  |  | 100% | - |  | 10.6 | 100% | 10.6 | Phy. Completed
359 | Construction of RCC V-Shape Side Drain on Durtlang Leitan | 3.17 | Aizawl Road North Division |  |  | 100% | - |  | 1.58 | 100% | 1.58 | Phy Completed
360 | Construction of Masonry Cross Drain with Cover near Leitan 'S' Presbyterian Church | 2.61 | Aizawl Road North Division |  |  | 100% | - |  | 1.3 | 100% | 1.3 | Phy Completed
361 | Construction of U-Shape Side Drain on BSNL Junction near Pu Rinawma House, Durtlang North | 4 | Aizawl Road North Division |  |  | 100% | - |  | 2 | 100% | 2 | Phy Completed
362 | Extension of RCC Slab Culvert at Arbai Veng, Durtlang | 1.5 | Aizawl Road North Division |  |  | 100% | - |  | 0.75 | 100% | 0.75 | Phy Completed
363 | Construction of RCC Slab Culvert between Pi Saii and Pi Purni House, Durtlang Leitan | 5.25 | Aizawl Road North Division |  |  | 100% | - |  | 2.62 | 100% | 2.62 | Phy Completed
364 | Concrete Flooring, Drain with Cover & RCC Balcony from Zuangtui road to Pu Lalhmachhuana's House at Durtlang Venglai | 22.36 | Aizawl Road North Division |  |  | - | - |  | - |  | - | Not Yet Started
365 | Construction of Step with Cheqered Tile including Railing near Pi Ngurmawii, Durtlang Leitan | 8 | Aizawl Road North Division |  |  | 100% | - |  | 4 | 100% | 4 | Phy Completed
366 | Constrution of Retaining Wall near Prsbyterian Church, Dutlang North | 15 | Aizawl Road North Division |  |  | 100% | - |  | 7.5 | 100% | 7.5 | Phy Completed
367 | Constrution of Retaining Wall No.1 at Arbai Peng, Durtlang | 2.83 | Aizawl Road North Division |  |  | 100% | - |  | 1.41 | 100% | 1.41 | Phy Completed
368 | Constrution of Retaining Wall No.2 at Arbai Peng, Durtlang | 5.67 | Aizawl Road North Division |  |  | 100% | - |  | 2.83 | 100% | 2.83 | Phy Completed
369 | Widening near Leitan's Presbyterian Church, Durtlang | 2.73 | Aizawl Road North Division |  |  | 100% | - |  | 1.37 | 100% | 1.37 | Phy Completed
370 | PCC Pavement near Zakianglova House, Durtlang North | 4 | Aizawl Road North Division |  |  | 100% | - |  | 2 | 100% | 2 | Phy Completed
371 | Constrution of Retaining Wall Unit-I, Durtlang Leitan | 3.6 | Aizawl Road North Division |  |  | 100% | - |  | 1.8 | 100% | 1.8 | Phy Completed
372 | Constrution of Retaining Wall Unit-I, Durtlang Leitan | 0.82 | Aizawl Road North Division |  |  | 100% | - |  | 0.41 | 100% | 0.41 | Phy Completed
373 | Constrution of Retaining Wall Unit-I, Durtlang Leitan | 2.69 | Aizawl Road North Division |  |  | 100% | - |  | 1.34 | 100% | 1.34 | Phy Completed
374 | Constrution of Retaining Wall Unit-I, Durtlang Leitan | 2.8 | Aizawl Road North Division |  |  | 100% | - |  | 1.4 | 100% | 1.4 | Phy Completed
375 | PCC Pavement Zion Veng to Suaka Veng at Durtlang | 3 | Aizawl Road North Division |  |  | 100% | - |  | 1.5 | 100% | 1.5 | Phy Completed
376 | PCC Pavement Upper SL Road at Durtlang | 2.5 | Aizawl Road North Division |  |  | 100% | - |  | 1.25 | 100% | 1.25 | Phy Completed
377 | PCC Pavement Upper SL Road at Durtlang | 2.5 | Aizawl Road North Division |  |  | 100% | - |  | 1.25 | 100% | 1.25 | Phy Completed
378 | PCC Pavement on Local Council Road, Durtlang | 8 | Aizawl Road North Division |  |  | 100% | - |  | 4 | 100% | 4 | Phy Completed
379 | PCC Pavement on Chhingtei Road, Durtlang | 8 | Aizawl Road North Division |  |  | 100% | - |  | 4 | 100% | 4 | Phy Completed
380 | Construction of Kawmzawl to Centenary Road at durtlang including RCC pavement | 8 | Aizawl Road North Division |  |  | 100% | - |  | 4 | 100% | 4 | Phy Completed
381 | RCC Pavement at Lanu Road, Mizoram UPC to Presbyterian Chucrh at Suaka Veng, Durtlang | 8 | Aizawl Road North Division |  |  | 100% | - |  | 4 | 100% | 4 | Phy Completed
382 | RCC pavement at Selesih | 8 | Aizawl Road North Division |  |  | 100% | - |  | 4 | 100% | 4 | Phy Completed
383 | Construction of Slab Culvert near Pu Thawmtea's house | 7 | Aizawl Road North Division |  |  | - | - | 100% | 3.5 | 100% | 3.5 | Phy.Completed
384 | Improvement of Y-Road Junction | 5.44 | Aizawl Road North Division |  |  | 100% | - |  | 2.72 | 100% | 2.72 | Phy. Completed
385 | Improvement of Y-Road near Pu Sajjal Residence | 0.96 | Aizawl Road North Division |  |  | 100% | - |  | 0.48 | 100% | 0.48 | Phy. Completed
386 | Pavement of Sihphir By-pass Road | 4.41 | Aizawl Road North Division |  |  | - | - | 100% | 2.21 | 100% | 2.21 | Phy.Completed
387 | Imrpvement of Road Profile and PCC Pavement at Falkland | 2.42 | Aizawl Road North Division |  |  | - | - | 100% | 1.21 | 100% | 1.21 | Phy.Completed
388 | Construction of PCC V Shape side drain near Pu BM-a House | 0.3 | Aizawl Road North Division |  |  | 100% | - |  | 0.15 | 100% | 0.15 | Phy Completed
389 | Construction of Hand Railing near Papuia House | 0.72 | Aizawl Road North Division |  |  | 100% | - |  | 0.36 | 100% | 0.36 | Phy Completed
390 | Construction of Hand Railing near Chhunglawmi House at Durtlang Leitan | 3.7 | Aizawl Road North Division |  |  | 100% | - |  | 1.85 | 100% | 1.85 | Phy Completed
391 | Construction of Hand Railing Pu Malsawma House to Upa Zairemmawia House at Zotui Veng Durtlang | 2.65 | Aizawl Road North Division |  |  | 100% | - |  | 1.33 | 100% | 1.33 | Phy Completed
392 | Imrprovement of Bethel veng road at zemabawk, Aizawl in Mizoram for the the year 2022-2023 | 318 | Aizawl Road North Division |  |  | 100% | - |  | 159 | 100% | 159 | Phy Completed
393 | Imrprovement of Thuampui-Selesih road (uoto 5.120 Km)Aiawl in Mizoram for the the year 2022-2024 | 370 | Aizawl Road North Division |  |  | 100% | - |  | 185 | 100% | 185 | Phy. Completed
394 | Construction of Side Drain with cover at zemabawk North Presbyterian kawt | 12 | Aizawl Road North Division |  |  | 100% | - |  | 6 | 100% | 6 | Phy. Completed
SUB DIVISION-III
Construction and Upgradation of connectivity from Kangthelhkawn - Ainawn - Luangmual by creating a new alternative road
395 | Repair of culvert wing wall near Mimi's House on Chhangurkawn to Govt.Complex | 1.27 | Aizawl Road North Division |  |  | 50% | - | 50% | 0.64 | 100% | 0.64 | Phy.Completed
396 | Improvement and Widening of approach road to MPRO Quarter (Sh: Construction of Pavement) | 75.88 | Aizawl Road North Division |  |  | 50% |  |  | 37.94 | 50% | 37.94 | Work in progress
397 | Improvement and Widening of approach road to MPRO Quarter (Sh: 1. Construction of Slab Culvert @ ch.0.050 Kmp | 3.51 | Aizawl Road North Division |  |  | 100% |  |  | 1.76 | 100% | 1.76 | Phy.Completed
398 | 2. Construction of Slab Culvert @ ch.0.510 Kmp | 3.5 | Aizawl Road North Division |  |  | 100% |  |  | 1.75 | 100% | 1.75 | Phy.Completed
399 | 3. Construction of Slab Culvert @ ch.0.650 Kmp | 3.52 | Aizawl Road North Division |  |  | 100% |  |  | 1.76 | 100% | 1.76 | Phy.Completed
400 | 4. Construction of Breast Wall @ ch.0.550 Kmp | 5.51 | Aizawl Road North Division |  |  | 100% |  |  | 2.76 | 100% | 2.76 | Phy.Completed
401 | 5. Construction of Breast Wall @ ch.0.410 Kmp | 8.06 | Aizawl Road North Division |  |  | 100% |  |  | 4.03 | 100% | 4.03 | Phy.Completed
402 | 6. Construction of Link Drain | 8.4 | Aizawl Road North Division |  |  | 100% |  |  | 4.2 | 100% | 4.2 | Phy.Completed
403 | 7. Construction of V-Shape side drain | 2.01 | Aizawl Road North Division |  |  | 100% |  |  | 1.01 | 100% | 1.01 | Phy.Completed
404 | Construction of RCC Frame struction Retaining Wall & Hume pipe Culvert with link drain on Approach Road to Govt.Housing Complex, at Luangmual at Ch 0.100Kmp Sh: 1. Retaining Wall | 14.03 | Aizawl Road North Division | [8 empty] | Not Yet Started
405 | 2. Humne Pipe Culvert | 3.62 | Aizawl Road North Division |  |  |  |  | 50% | 1.81 | 100% | 1.81 | Phy.Completed
406 | 3. Linked Drain | 4.77 | Aizawl Road North Division | [8 empty] | Not Yet Started
407 | Construction of Breast Wall near Pu Lalrinawma House at Luangmual | 5.08 | Aizawl Road North Division |  |  | 10% |  | 40% | 2.54 | 50% | 2.54 | Work in progress
408 | Construction of Road at Ainawn Veng, Aizawl Sh: 1. Earth Work Formation cutting | 41.17 | Aizawl Road North Division |  |  | 100% |  |  | 20.59 | 100% | 20.59 | Phy.Completed
409 | 2. Construction of RCC Slab Culvert Type-I | 13.58 | Aizawl Road North Division |  |  | 100% |  |  | 6.79 | 100% | 6.79 | Phy.Completed
410 | 3. Slab-Culvert-II | 16.79 | Aizawl Road North Division |  |  | 60% |  | 40% | 8.4 | 100% | 8.4 | Phy.Completed
411 | Construction of road at Chawnpui, Aizawl Sh: 1. Earth Work Formation cutting | 38.02 | Aizawl Road North Division |  |  | 100% |  |  | 19.01 | 100% | 19.01 | Phy.Completed
412 | 2. Construction og RCC Slab Vulvert Type-I | 13.57 | Aizawl Road North Division | [8 empty] | Not Yet Started
413 | 3. Construction of TCC Slab Culvert Type-II | 8.4 | Aizawl Road North Division | [8 empty] | Not Yet Started
414 | Resurfaccing of Kangthlehkawn to High Court (0.000 to 1.830 Kmp) | 59.29 | Aizawl Road North Division |  |  | 100% |  |  | 29.65 | 100% | 29.65 | Phy.Completed
415 | Construction of Approach Road (RCC Pavement) to Chhimveng Presbyterian Church at Ainawn Veng | 31.76 | Aizawl Road North Division |  |  | 100% |  |  | 15.88 | 100% | 15.88 | Phy.Completed
Construction of Upgradation of Road from Dawrpui Vengthar - Vaivakawn - Zotlang - MZU
416 | Construction of Link Drain near P/S at Vaivakawn | 13.92 | Aizawl Road North Division |  |  | 50% |  | 50% | 6.96 | 100% | 6.96 | Phy. Completed
417 | RCC Link Drain with Cover Step K.Buanga's House approach to NH-06, Vaivakawn | 25.42 | Aizawl Road North Division | [5 empty] | 12.71 | 50% | 12.71 | Work in progress
418 | Rectangular Side Drain with cover near Salvation Army Church at k.Zamawia's House to MZU Road including Cross Drain cover, Vaivakawn | 11.55 | Aizawl Road North Division |  |  | 70% |  | 30% | 5.77 | 100% | 5.77 | Phy.Completed
419 | Construction of RCC Mini Bridge near Pi Malsawma's House (Dam veng) | 14.82 | Aizawl Road North Division |  |  |  |  | 60% | 7.41 | 60% | 7.41 | Work in progress
420 | Construction of RCC Foot path near Presbyterian Pastor Quarter to Zarkawt approach road at Dawrpui Vengthar | 15.96 | Aizawl Road North Division |  |  | 50% |  | 45% | 7.98 | 95% | 7.98 | Work in progress
421 | RCC approach road to Vanlalzuiliana's House Sh: 1. Construction of Rigid Pavement | 9.21 | Aizawl Road North Division |  |  |  |  | 50% | 4.61 | 50% | 4.61 | Work in progress
| 2. Construction of V-Shaped Side Drain | 2.22 | Aizawl Road North Division |  |  |  |  | 50% | 1.11 | 50% | 1.11 | Work in progress
422 | Improvement of road Zotlang, Aizawl Sh: 1.Earth Work Widening of existing road | 9 | Aizawl Road North Division |  |  | 100% |  |  | 4.5 | 100% | 4.5 | Phy.Completed
| 2. Construction of Retaining Wall | 28.52 | Aizawl Road North Division |  |  | 100% |  |  | 14.26 | 100% | 14.26 | Phy.Completed
| 3. Rigid Pavement | 5.58 | Aizawl Road North Division |  |  | 100% |  |  | 2.79 | 100% | 2.79 | Phy.Completed
423 | Road Widening and R/Wall at Pu Rosanga House to Neitumi House, Zohnuai Vaivakawn Sh: Earthwork | 5.41 | Aizawl Road North Division |  |  | 10% |  | 20% | 2.71 | 30% | 2.71 | Work in progress
| 2. Construction of Slab Culvert @ ch.0.115 Kmp | 3.5 | Aizawl Road North Division |  |  |  |  | 30% | 1.75 | 30% | 1.75 | Work in progress
| 3. Construction of Breast wall | 24.97 | Aizawl Road North Division |  |  |  |  | 30% | 12.49 | 30% | 12.49 | Work in progress
424 | Construction og Retaining Wall on Electric Veng Cemetery Road Sh: 1. Construction og Retaining Wall Section - 1 | 9.95 | Aizawl Road North Division |  |  | 100% |  |  | 4.98 | 100% | 4.98 | Phy.Completed
| 2. Construction og Retaining Wall Section - 2 | 4.76 | Aizawl Road North Division |  |  | 100% |  |  | 2.38 | 100% | 2.38 | Phy.Completed
| 3. Construction og Retaining Wall Section - 3 | 9.32 | Aizawl Road North Division |  |  | 100% |  |  | 4.66 | 100% | 4.66 | Phy.Completed
425 | Construction of Step near Seventh Day Church to Dosangvunga (L) House at Electrict Veng Sh: Construction of Step | 13.9 | Aizawl Road North Division |  |  | 90% |  | 10% | 6.95 | 100% | 6.95 | Phy.Completed
426 | Construction of Step in concrete over Link Drain including Railing near Presbyterian Jubilee Hall, Laipuitlang | 6.63 | Aizawl Road North Division |  |  | 90% |  | 10% | 3.32 | 100% | 3.32 | Phy.Completed
Construction and Upgradation of croad from Chanmari West - Hunthar - Edenthar - Rangvamual
427 | Pot Hole Repair & Resurfacing and Seal Coating of Chanmari West to NH-54 | 11.01 | Aizawl Road North Division |  |  | 100% |  |  | 5.51 | 100% | 5.51 | Phy.Completed
428 | Pot Hole Repair & Resurfacing and Seal Coating of Chanmari West to Vaivakawn Road (0.000 - 0.550Kms) | 16.93 | Aizawl Road North Division |  |  | 100% |  |  | 8.47 | 100% | 8.47 | Phy. Completed
429 | Hole Repair & Resurfacing and Seal Coating of edenthar internal (0.000-1.175 Kms) | 15.25 | Aizawl Road North Division |  |  |  |  | 100% | 7.63 | 100% | 7.63 | Phy.Completed
430 | Pot Hole Repair & Resurfacing and Seal Coating of Bt Bakery to turning Point via Middle School at Hunthar (0.000 - 0.175Kms) | 10.16 | Aizawl Road North Division |  |  |  |  | 100% | 5.08 | 100% | 5.08 | Phy.Completed
431 | Pot Hole Repair & Resurfacing and Seal Coating of Edenthar Internal (0.000-1.175 Kms) | 17.46 | Aizawl Road North Division |  |  |  |  | 100% | 8.73 | 100% | 8.73 | Phy.Completed
432 | Construction of Edenthar BPL raod at Edenthar Sh: 1. Estimate for Earthwork | 3.24 | Aizawl Road North Division | [8 empty] | Not Yet Started
433 | 2. Construction of RCC Balcony at Ch. 0.275 Kmp | 11.04 | Aizawl Road North Division | [8 empty] | Not Yet Started
434 | 3. Construction of retaining Wall at Ch.0.190 Kmp | 3.23 | Aizawl Road North Division | [8 empty] | Not Yet Started
435 | 4. Consreruction of Slab Culvert @ch.0.160Kmp | 5.51 | Aizawl Road North Division | [8 empty] | Not Yet Started
436 | 5. Construction of Slab Culvert @ ch.0.200 Kmp | 2.37 | Aizawl Road North Division | [8 empty] | Not Yet Started
438 | Construction of RCC Pavement Edenthar to Chanmari West Road Sh: 1. Construction of RCC Pavement | 78 | Aizawl Road North Division |  |  | 50% |  | 50% | 39 | 100% | 39 | Phy.Completed
439 | 2. Construction of Hume Pipe Culvert at Ch.0.037 Kmp | 6.77 | Aizawl Road North Division |  |  | 50% |  | 50% | 3.39 | 100% | 3.39 | Phy.Completed
440 | Construction of Ram,lai Road at Edenthar Sh: Earth work for Widening of existing road) | 16.95 | Aizawl Road North Division |  |  |  |  | 20% | 8.48 | 20% | 8.48 | Work in progress
441 | Construction of Lunghlu Road at Chanmari West Sh: 1. Earth Work for Formation cutting | 17.52 | Aizawl Road North Division | [8 empty] | Not yet started
442 | 2. Construction of RCC Slab Culvert Type-I | 8.03 | Aizawl Road North Division |  |  |  |  | 10% | 4.02 | 10% | 4.02 | Work in progress
443 | 3. Slab Culvert-II | 33.76 | Aizawl Road North Division | [8 empty] | Not Yet Started
444 | Construction of Retaining Wall near Middle School, Hunthar | 25.41 | Aizawl Road North Division | [8 empty] | Not yet started
445 | Construction of road at Rangvamual, Aizawl Sh: 1. Earth Work for Formation Cutting | 107.52 | Aizawl Road North Division |  |  | 85% |  |  | 53.76 | 85% | 53.76 | Work in progress
446 | 2. Construction of RCC Slab Culvert Type-I | 26.62 | Aizawl Road North Division | [8 empty] | Not yet started
447 | 3. Slab Culvert-II | 24.71 | Aizawl Road North Division | [8 empty] | Not yet started
Construction and Upgradation of connectivity by creating a New Alternative Route, Tanhril - Sakawrtuichhun
448 | Patch repairs of Sakawrtuichhun to PTC Road due to vice President visit | 7.18 | Aizawl Road North Division |  |  | 100% |  |  | 3.59 | 100% | 3.59 | Phy.Completed
449 | Construction of Retaining Wall near Lallawmzuala's House at sakawrtuichhun | 5.66 | Aizawl Road North Division |  |  | 100% |  |  | 2.83 | 100% | 2.83 | Phy. Completed
450 | Construction of Dumping Ground at Industrial Areas at Sakawrtuichhun Sh: 1. Earth Work for Formation Cutting of Internal Road | 10.53 | Aizawl Road North Division |  |  | 100% |  |  | 5.27 | 100% | 5.27 | Phy.Completed
451 | 2. Hume Pipe NP4 | 27.27 | Aizawl Road North Division |  |  | 100% |  |  | 13.64 | 100% | 13.64 | Phy.Completed
452 | Construction of Road at Tanhril, Aizawl Sh: 1. Earth Work for Formation Cutting | 80.48 | Aizawl Road North Division |  |  | 100% |  |  | 40.24 | 100% | 40.24 | Phy.Completed
453 | 2. Construction of RCC Slab Culvert Type-I | 27.15 | Aizawl Road North Division |  |  | 100% |  |  | 13.58 | 100% | 13.58 | Phy.Completed
454 | 3. Construction of RCC Slab Culvert Type-II | 16.79 | Aizawl Road North Division |  |  | 100% |  |  | 8.4 | 100% | 8.4 | Phy.Completed
455 | Construcytion of Road at Sakawrtuichhun, Aizawl Sh: 1. Earth Work for Widening of existing Road | 19.53 | Aizawl Road North Division |  |  | 80% |  | 20% | 9.77 | 100% | 9.77 | Phy.Completed
456 | 2. Construction of Flexible Pavement NBCC Road I & II | 24.82 | Aizawl Road North Division |  |  | 100% |  |  | 12.41 | 100% | 12.41 | Phy. Completed
457 | 3. Construction of RCC Slab Culvert Type-I | 17.84 | Aizawl Road North Division |  |  | 60% |  |  | 8.92 | 60% | 8.92 | Work in Progress
Improvement of Ramrikawn to NH-54 via Sakawrtuichhun
458 | Improvement of Ramrikawn to NH-54 via Sakawrtuichhun Roads in Mizoram for the year 2022-2023 Sh: 1. Pavement of ramrikawn to NH-54 | 254.15 | Aizawl Road North Division |  |  |  |  | 10% | 127.08 | 10% | 127.08 | Work in progress
459 | 2. Const.of R/Wall at Ch 5.950 Kmp at Sakawrtuichhun | 0.95 | Aizawl Road North Division |  |  | 100% |  |  | 0.48 | 100% | 0.48 | Phy. Completed
460 | 3. Const.of R/W near Zoo Gate, Lungverh | 16.01 | Aizawl Road North Division |  |  | 100% |  |  | 8.01 | 100% | 8.01 | Phy. Completed
461 | 4. Const.of Hume Pipe Culvert at 0.270 Kmp at Sakawrtuichhun | 7.31 | Aizawl Road North Division |  |  | 100% |  |  | 3.66 | 100% | 3.66 | Phy. Completed
462 | 5. Const.of Hume Pipe Culvert at 1.580 Kmp at Sakawrtuichhun | 6.34 | Aizawl Road North Division |  |  | 100% |  |  | 3.17 | 100% | 3.17 | Phy. Completed
463 | Patch Repair from Thirhruibankawn to hmar veng Via Fire Station | 9.92 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | - |  | 9.92 | 100% | 9.92 | Phy.Completed
464 | Formation cutting of Serlui Zau at Kawnpui | 46 | Kolasib Division | 2023-03-23 | 2023-03-24 | 70% | - | 30% | - | 100% | - | Phy.Completed
465 | Formation cutting of Panhnah kawn at N.Chaltlang | 28 | Kolasib Division | 2023-03-23 | 2023-03-24 | 70% | - | 30% | - | 100% | - | Phy.Completed
466 | Formation cutting of Kawnpui zau at Bukpui | 28 | Kolasib Division | 2023-03-23 | 2023-03-24 | 70% | - | 30% | - | 100% | - | Phy.Completed
467 | Formation cutting of Tuirial Road at Lungmuat | 28 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | - |  | - | 100% | - | Phy.Completed
468 | Improvement and Upgradation of Road from Mizo Hotelpui (Diakkawn Bazaar) to NH-306 via KVK (SW: Resurfacing of Mizo Hotelpui to NH-306 via ICAR1(a) | 57.028 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% |  |  | 57.02 | 100% | 57.02 | Phy.Completed
469 | Improvement and Upgradation of Road from Mizo Hotelpui (Diakkawn Bazaar) to NH-306 via KVK (SW: Hume Pipe Culvert near SIRD Quarter, Vengthar 1(b) | 3.78 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% |  |  |  | 100% |  | Phy.Completed
470 | Improvement and Upgradation of Road from Mizo Hotelpui (Diakkawn Bazaar) to NH-306 via KVK (SW: Hume Pipe Culvert near Pu Sawma's House 1(c) | 7.64 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% |  |  |  | 100% |  | Phy.Completed
471 | Improvement and Upgradation of Road from Mizo Hotelpui (Diakkawn Bazaar) to NH-306 via KVK (SW: Hume Pipe Culvert near S.Kaigina Ventgthar 1(d) | 1.941 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% |  |  |  | 100% |  | Phy.Completed
472 | Improvement and Upgradation of Road from Mizo Hotelpui (Diakkawn Bazaar) to NH-306 via KVK (SW: Const.of V-Shaped SD at Essential Places on Mizo Hotelpui-NH 306 via ICAR 1€ | 8.675 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% |  |  |  | 100% |  | Phy.Completed
473 | Improvement and Upgradation of Road from Mizo Hotelpui (Diakkawn Bazaar) to NH-306 via KVK (Embankment in front of Pu Laltanpuia's House, Vengthar 1(f) | 0.787 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% |  |  |  | 100% |  | Phy.completed
474 | Improvement and Upgradation of Road from Mizo Hotelpui (Diakkawn Bazaar) to NH-306 via KVK (Road Widening below Remsiami's House, Vengthar 1(g) | 0.109 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% |  |  |  | 100% |  | Phy.Completed
475 | Improvement and Upgradation of Road from Mizo Hotelpui (Diakkawn Bazaar) to NH-306 via KVK (SW: Road widening near Leitan, Vengthar 1(h) | 0.787 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% |  |  |  | 100% |  | Phy.Completed
476 | Improvement and Upgradation of Road from Mizo Hotelpui (Diakkawn Bazaar) to NH-306 via KVK (Upgradation of CP Road, New Diakkawn Kolasib (Resurfacing of CP Road) 2(a) | 22.88 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% |  |  |  | 100% |  | Phy.Completed
477 | Improvement and Upgradation of Road from Mizo Hotelpui (Diakkawn Bazaar) to NH-306 via KVK (Upgradation of CP Road, New Diakkawn Kolasib (Const.of LSD at CP Road) 2(b) | 8.049 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% |  |  |  | 100% |  | Phy.Completed
478 | Improvement and Upgradation of Road from Mizo Hotelpui (Diakkawn Bazaar) to NH-306 via KVK (SW: Improvement and Upgradation of Soil Peng to KVK (Kawnglaiphei) Resurfacing of Soil Dept.peng to KVK) 3(a) | 46.78 | Kolasib Division | 2023-03-23 | 2023-03-24 | [6 empty] | Work not started
479 | Improvement and Upgradation of Road from Mizo Hotelpui (Diakkawn Bazaar) to NH-306 via KVK SW:Improvement and Upgradation of Soil Peng to KVK (Kawnglaiphei) Hume Pipe Culvert at Middle of the Road) 3 (b) | 3.098 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% |  |  |  | 100% |  | Phy.Completed
480 | Improvement and Upgradation of Road from Mizo Hotelpui (Diakkawn Bazaar) to NH-306 via KVK (Improvement and Upgradation of Soil Peng to KVK (Kawnglaiphei) (Extension of Downstream Hume Pipe Culvert near Pu Lalchhuanawma's House, Vengthar) 3(c) | 2.31 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% |  |  |  | 100% |  | Phy.Completed
481 | Improvement and Upgradation of Road from Mizo Hotelpui (Diakkawn Bazaar) to NH-306 via KVK (Improvement and Upgradation of Soil Peng to KVK (Kawnglaiphei) (Extension of Hume Pipe Culvert near Pu Lalthana House, Vengthar) 3(d) | 6.52 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% |  |  |  | 100% |  | Phy.Completed
482 | Improvement and Upgradation of Road from Mizo Hotelpui (Diakkawn Bazaar) to NH-306 via KVK (Improvement and Upgradation of Soil Peng to KVK (Kawnglaiphei) (Const.of LSD at Essential Places of Soil Dept.peng to KVK 3(e) | 9.45 | Kolasib Division | 2023-03-23 | 2023-03-24 |  |  | 100% |  | 100% |  | Phy.Completed
483 | Improvement and Upgradation of Road from Mizo Hotelpui (Diakkawn Bazaar) to NH-306 via KVK (Improvement and Upgradation of Soil Peng to KVK (Kawnglaiphei) (Road Widening near Saichhungi House, Vengthar 3(f) | 0.416 | Kolasib Division | 2023-03-23 | 2023-03-24 | 50% |  |  |  | 50% |  | Work in progress
484 | Improvement and Upgradation of Road from Mizo Hotelpui (Diakkawn Bazaar) to NH-306 via KVK (Improvement and Upgradation of Soil Peng to KVK (Kawnglaiphei) (Road Widening near Masanga House to Pu Tanpuia House, Vengthar 3(g) | 0.566 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% |  |  |  | 100% |  | Phy.Completed
485 | Improvement and Upgradation of Road from Mizo Hotelpui (Diakkawn Bazaar) to NH-306 via KVK (Improvement and Upgradation of Soil Peng to Rammawia's House 4(a) | 11.01 | Kolasib Division | 2023-03-23 | 2023-03-24 | [6 empty] | Not Yet Started
486 | Improvement and Upgradation of Road from Mizo Hotelpui (Diakkawn Bazaar) to NH-306 via KVK (Improvement and Upgradation of Soil Peng to Rammawia's House 4(b) | 4.25 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% |  |  |  | 100% |  | Phy.Completed
487 | Improvement and Upgradation of Road from Mizo Hotelpui (Diakkawn Bazaar) to NH-306 via KVK (Improvement and Upgradation of Soil Peng to Rammawia's House 4(c) | 14.55 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% |  |  |  | 100% |  | Phy.Completed
488 | Improvement and Upgradation of Road from Mizo Hotelpui (Diakkawn Bazaar) to NH-306 via KVK Improvement and Upgradation of ICAR to Dinthar Road 5 | 19.73 | Kolasib Division | 2023-03-23 | 2023-03-24 | [6 empty] | Not yet started
489 | Improvement and Upgradation of Road from Mizo Hotelpui (Diakkawn Bazaar) to NH-306 via KVK Improvement and Upgradation of ICAR to Dinthar Road 5 (a) | 6.08 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% |  |  |  | 100% |  | Phy.Completed
490 | Improvement and Upgradation of Road from Mizo Hotelpui (Diakkawn Bazaar) to NH-306 via KVK Improvement and Upgradation of Road from Hmarveng Tuikhur to NH-306 near Sericulture Complex 6(a) | 0.65 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% |  |  |  | 100% |  | Phy.Completed
491 | Improvement and Upgradation of Road from Mizo Hotelpui (Diakkawn Bazaar) to NH-306 via KVK Improvement and Upgradation of Road from Hmarveng Tuikhur to NH-306 near Sericulture Complex 6(b(i)) | 6 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% |  |  |  | 100% |  | Phy.Completed
492 | Improvement and Upgradation of Road from Mizo Hotelpui (Diakkawn Bazaar) to NH-306 via KVK Improvement and Upgradation of Road from Hmarveng Tuikhur to NH-306 near Sericulture Complex 6(b(ii)) | 5 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% |  |  |  | 100% |  | Phy.Completed
493 | Improvement and Upgradation of Road from Mizo Hotelpui (Diakkawn Bazaar) to NH-306 via KVK Improvement and Upgradation of Road from Hmarveng Tuikhur to NH-306 near Sericulture Complex 6(b(iii)) | 5 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% |  |  |  | 100% |  | Phy.Completed
494 | Improvement and Upgradation of Road from Mizo Hotelpui (Diakkawn Bazaar) to NH-306 via KVK Improvement and Upgradation of Road from Hmarveng Tuikhur to NH-306 near Sericulture Complex 6(c) | 64.65 | Kolasib Division | 2023-03-23 | 2023-03-24 | 65% |  |  |  | 65% |  | Work in progress
495 | Improvement and Upgradation of Road from Mizo Hotelpui (Diakkawn Bazaar) to NH-306 via KVK Improvement and Upgradation of Road from Hmarveng to Saidan Field via KL Siama's House 7(a) | 20.75 | Kolasib Division | 2023-03-23 | 2023-03-24 | [6 empty] | Not yet started
496 | Improvement and Upgradation of Road from Mizo Hotelpui (Diakkawn Bazaar) to NH-306 via KVK Improvement and Upgradation of Road from Hmarveng to Saidan Field via KL Siama's House 7(b) | 3.21 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% |  |  |  | 100% |  | Phy.Completed
497 | Improvement and Upgradation of Road from Mizo Hotelpui (Diakkawn Bazaar) to NH-306 via KVK Improvement and Upgradation of Road from Hmarveng to Saidan Field via KL Siama's House 7(c) | 5.2 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% |  |  |  | 100% |  | Phy.Completed
498 | Improvement and Upgradation of Road from Mizo Hotelpui (Diakkawn Bazaar) to NH-306 via KVK Widening, Upgradation & Resurfacing of Helipad to Lungsumlui Road 8(a) | 17.64 | Kolasib Division | 2023-03-23 | 2023-03-24 | [6 empty] | Not Yet Started
499 | Improvement and Upgradation of Road from Mizo Hotelpui (Diakkawn Bazaar) to NH-306 via KVK Widening, Upgradation & Resurfacing of Helipad to Lungsumlui Road 8(b) | 1.5 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% |  |  |  | 100% |  | Phy.Completed
500 | Improvement and Upgradation of Road from Mizo Hotelpui (Diakkawn Bazaar) to NH-306 via KVK Widening, Upgradation & Resurfacing of Helipad to Lungsumlui Road 8(c) | 19.92 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% |  |  |  | 100% |  | Phy.Completed
501 | Improvement and Upgradation of Road from Mizo Hotelpui (Improvement & Upgradation of Diakkawn NH-306 to Challui Veng via Galili Veng 9(a) | 18.13 | Kolasib Division | 2023-03-23 | 2023-03-24 | 5% |  |  |  | 5% |  | Work in progress
502 | Improvement and Upgradation of Road from Mizo Hotelpui (Improvement & Upgradation of Diakkawn NH-306 to Challui Veng via Galili Veng 9(b) | 13.19 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% |  |  |  | 100% |  | Phy.Completed
503 | Improvement and Upgradation of Road from Mizo Hotelpui (Improvement & Upgradation of Diakkawn NH-306 to Challui Veng via Galili Veng 9(c) | 3.18 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% |  |  |  | 100% |  | Phy.Completed
504 | Improvement and Upgradation of Road from Mizo Hotelpui (Improvement & Upgradation of Diakkawn NH-306 to Challui Veng via Galili Veng 9(d) | 2.6 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% |  |  |  | 100% |  | Phy.Completed
505 | Improvement and Upgradation of Road from Mizo Hotelpui (Improvement & Upgradation of Diakkawn NH-306 to Challui Veng via Galili Veng 9(e) | 0.98 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% |  |  |  | 100% |  | Phy.Completed
506 | Improvement and Upgradation of Road from Mizo Hotelpui (Diakkawn Bazaar) to NH-306 via KVK (SW: PCC Flooring from NH-6 Rengtekawn Kualmawi to Hebron Veng 10 | 25.42 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% |  |  |  | 100% |  | Phy.Completed
507 | Improvement and Upgradation of Road from Mizo Hotelpui (Diakkawn Bazaar) to NH-306 via KVK (SW: PCC Flooring from PWD Town road near KVK Compound to Dinthar Vengthar 11 | 25.42 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% |  |  |  | 100% |  | Phy.Completed
508 | Resurfacing of approach road to Electric veng from Banglakawn, Kolasib | 14.72 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% |  |  | 14.72 | 100% | 14.72 | Phy.Completed
509 | Improvement and Black topping of approach road to Pavillion at Football Playground at Bilkhawthlir | 15.32 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% |  |  | 15.32 | 100% | 15.32 | Phy.Completed
510 | Construction of Retaining wall at Kawnpui Hmarveng Graveland | 5.23 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% |  |  | 5.23 | 100% | 5.23 | Phy.Completed
511 | Resurfacing of Mualvum approach road from Chainage 1.150 Kmp to 2.800 Kmp9 Balance Stretch) | 29.45 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% |  |  | 29.45 | 100% | 29.45 | Phy.Completed
512 | Construction of Masonry Link drain with RCC Slab Cover at PWD Complex, Kawnpui | 4.8 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% |  |  | 4.8 | 100% | 4.8 | Phy.Completed
513 | Restoration of Shoulder subsidence at Ch: 7.35Kmp on Buhchang to Phaisen: a)Repairing of Rigid pavement from km 7/340 to km 7/370 (Length = 30 m) on Buhchang to Phaisen road in the State of Mizoram | 7.8 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% |  |  | 7.8 | 100% | 7.8 | Phy.Completed
514 | b) Construction of Gabion wall at the side shoulder. | 17.55 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% |  |  | 17.55 | 100% | 17.55 | Phy.Completed
515 | c) Construction of Gabion wall at the Toe of the Slip. | 7.35 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% |  |  | 7.35 | 100% | 7.35 | Phy.Completed
516 | d) Construction of Line Side Drain | 5.9 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% |  |  | 5.9 | 100% | 5.9 | Phy.Completed
Construction of PCC Pavement on Phainuam to Saihapui V (Muddy Portion)
517 | a) Repair of Damage Stretch on approach road to Saihapui V | 18 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% |  |  | 18 | 100% | 18 | Phy.Completed
518 | b) Construction of Police Camp approach road at Saihapui V | 7 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% |  |  | 7 | 100% | 7 | Phy.Completed
519 | Extension of Community Hall at Upper Republic | 53 | Project Division-I | 15.3.23 |  | 40% | - | 5% | - | 45% | - | Work in progress
520 | Construction of RCC slab Dam veng YMA Hall | 4.83 | Project Division-I | 15.3.23 |  | 80% | - | 5% | - | 85% | - | Work in progress
521 | Construction of Cequered tiles Near Local Council House Bungkawn Vengthar | 1.45 | Project Division-I | 15.3.23 |  | 90% | - | 10% | - | 100% | - | Phy.Completed
522 | Construction of Saizahawla Tuikhur near R.Lalrinchhana Field Road | 7.72 | Project Division-I | 15.3.23 |  | 80% | - | 20% | - | 100% | - | Phy.completed
523 | Construction of RCC Structure at Electric Sub-Station, Khatla, Tlawng Road | 4.8 | Project Division-I | 15.3.23 |  | 80% | - | 10% | - | 90% | - | Work in progress
524 | Laying of Chequered Tiles Between Zonghaka and Sk Thanga's House at Nursery | 2.12 | Project Division-I | 15.3.23 |  | 90% | - | 10% | - | 100% | - | Phy.Completed
525 | Laying of Chequered Tiles tetween UPC (Mizoram) and RC Vanlalsawma (L) House at Nursery | 2.69 | Project Division-I | 15.3.23 |  | 95% |  | 5% | - | 100% | - | Phy.Completed
526 | Construction of Chequered tiles near Khatla South Presbyterian | 1.43 | Project Division-I | 15.3.23 |  | 90% |  | 10% | - | 100% | - | Phy.Completed
527 | Constrcution of Chequered tiles between J.Zangena House and Rinsanga Colney (L) near Khatla's Presbyterian Church | 0.98 | Project Division-I | 15.3.23 |  | 95% |  | 5% | - | 100% | - | Phy.Completed
528 | Construction of Step Chequered tiles with Hand Railing near Khatla Pastor Quarter to J.Lianhlira House | 2.84 | Project Division-I | 15.3.23 |  | 95% |  | 5% | - | 100% | - | Phy.Completed
529 | Renovation and linement of new Cemetary at Maubawk | 1.24 | Project Division-I | 15.3.23 |  | 50% |  | 5% | - | 55% | - | Work in progress
530 | Renovation of Kanan Multipurpose Community Hall | 14.42 | Project Division-I | 15.3.23 |  | 98% | - |  | - | 98% | - | Work in progress
531 | Renovation & Repair of Khatla Bazar Building | 3.86 | Project Division-I | 15.3.23 |  | 100% | - |  | - | 100% | - | Phy.Completed
532 | Renovation of Mission Veng Health Clinic at Mission | 1.93 | Project Division-I | 15.3.23 |  | 100% | - |  | - | 100% | - | Phy.Completed
533 | Construction of Anganwadi Centre-II, Aizawl | 4.79 | Project Division-I | 15.3.23 |  | 100% | - |  | - | 100% | - | Phy.Completed
534 | Construction of Basketball Court at Dinthar | 52.99 | Project Division-I | 15.3.23 |  | 10% | - | 5% | - | 15% | - | Work in progress
535 | Construction of Basketball Court at Dinthar | 43.36 | Project Division-I | 15.3.23 |  | 5% | - | 15% | - | 20% | - | Work in progress
536 | Construction of Basketball Court at Dinthar | 4.82 | Project Division-I | 15.3.23 |  | 80% | - | 20% | - | 100% | - | Phy.Completed
537 | Improvement & Strengthening of Aibawk-Darlung Road for 4.000-14.000 Kmp in Mizoram for the year 2022-2023 | 547 | Hmuifang Division | 20.12.23 | 31.03.23 | 65% | 86.26 | 13.45% | 177.77 | 78.45% | 264.03 | Work in progress
538 | Construction of Agriculture Link Road for Thingzam Zau, Tuirial Lui | 269.6 | Hmuifang Division | 15.02.23 | 14.05.23 | 100% |  |  | 125.87 | 100% | 125.87 | Phy.Completed
539 | Contsruction of Upgradation of Aizawl-Thenzawl-Lunglei Road 5.00 kmp-100.00 Kmp | 206 | Hmuifang Division | 15.02.23 | 14.05.23 | 91% |  | 9% | 103 | 100% | 103 | Phy.Completed
540 | Strengthening of approach road to IR Headquarter of Khawzawl in Mizoram for the year 2022-2023 under SASCI | 401 | Khawzawl Division | 15.02.23 | 30.06.23 | 38% |  |  | 136.34 | 38% | 136.34 | Work in progress
541 | Improvement of Farmual road at Khawzawl in Mizoram for the year 2022-2023 under SASCI | 343.5 | Khawzawl Division | 16.02.23 | 30.06.23 | 50% |  |  | 19.04 | 50% | 19.04 | Work in progress
542 | Contsruction /Upgradation of Road from NE Khawdungsei-Tuivai-Mimbung in Mizoram for the year 2022-2023 under SASCI | 377 | Khawzawl Division | 15.02.23 | 31.03.23 | 72% | - |  | 75.37 | 72% | 75.37 | Work in progress
543 | Construction of Kawlkulh Bypass Road | 805 | Khawzawl Division | 01.02.23 | 30.06.23 | 15% | - | 3% | 145.95 | 18% | 145.95 | Work in progress
544 | Construction of road from Hliappui-Aiduzawl-Neihdawn in Mizoram for the year 2022-2023 under SASCI | 340 | Khawzawl Division | 15.02.23 | 30.06.23 | 64% | - |  | - | 64% | - | Work in progress
545 | Improvement and Strengthening of Saitual - Phullen Road |  | Saitual Division | 13.2.23 | 31.3.24 | 100% | 92.11 | - | - | 100%
| A.Section-I 1) Strengthening of Saitual-Phullen Road (28.30) Tuivawl-Phullen | 139.71 | [8 empty] | 92.11 | Phy.Completed
546 | B.Section-II 1) Construction of concrete pavement between PWB IB to Thlanmual at Suangpuilawn & Improvement of Internal Roads | 28.98 | Saitual Division | 13.2.2023 | 31.3.24 | 100% | - | - | 14.49 | 100% | 14.49 | Phy.Completed
547 | 2) Construction of concrete pavement between Pu Zodinmawia's House to Lalsangbera's House at Vangbawng & Improvement of Internal Roads & Playground | 24.15 | Saitual Division | 13.2.23 | 31.3.24 | 100% | - | - | 12.07 | 100% | 12.07 | Phy.Completed
548 | 3) Construction of concrete pavement between RMSA school to Main road at Lamherh | 14.49 | Saitual Division | 13.2.23 | 31.3.24 | 100% | - | - | 7.24 | 100% | 7.24 | Phy.Completed
549 | 4) Construction and widening of road between N.Khawlek to Tuivawl Kai at N.Khawlek & Improvement of Internal Roads | 52.17 | Saitual Division | 13.2.23 | 31.3.24 | 100% | - | - | 26.08 | 100% | 26.08 | Phy.Completed
550 | 5) Construction of concrete pavement between Dawrkawn to High school at Khawlian & Improvement of Internal Roads | 35.75 | Saitual Division | 13.2.23 | 31.3.24 | 100% | - | - | 17.87 | 100% | 17.87 | Phy.Completed
551 | 6) Construction of concrete pavement between Anganwadi Centre I to YMA road at Phaibuang & Improvement of Internal Roads | 33.81 | Saitual Division | 13.2.23 | 31.3.24 | 100% | - |  | 16.9 | 100% | 16.9 | Phy.Completed
552 | 7) Construction of Approach Road to CC Puk at Luangpawn | 16.42 | Saitual Division | 13.2.23 | 31.3.24 | 100% | - |  | 8.21 | 100% | 8.21 | Phy.Completed
553 | 8) Construction of Community Hall at Phullen (Formation cutting and Retaining Wall) & Improvement of Internal Roads | 33.81 | Saitual Division | 13.2.23 | 31.3.24 | 100% | - |  | 16.9 | 100% | 16.9 | Phy.Completed
554 | 9) Widening of Mualkhang Road, Sihfa & Improvement of Internal Roads | 38.65 | Saitual Division | 13.2.23 | 31.3.24 | 100% | - | - | 19.32 | 100% | 19.32 | Phy.Completed
555 | 10) Improvement of High School Road, Daido | 9.66 | Saitual Division | 12.2.23 | 31.3.23 | 100% | - | - | 4.83 | 100% | 4.83 | Phy.Completed
556 | 11) PCC Flooring of Public Field Approach Road, Lailak & Improvement of Internal Roads | 19.32 | Saitual Division | 12.3.23 | 31.3.24 | 100% | - | - | 9.66 | 100% | 9.66 | Phy.Completed
| Improvement of Mualpheng to Maite Road |  | Saitual Division | 13.2.23 | 31.3.23 | 100% | - |  | 4.83 | 100%
557 | A.Section-I 1) Construction of Retaining Wall between main Road to Village extension peng at NE Tlangnuam | 9.66 | [8 empty] | 4.83 | Phy.Completed
558 | 2) Widening cum PCC Flooring of Thlanmual Kawng. Thanglailung & Improvement of Internal Roads | 23.21 | Saitual Division | 13.2.23 | 31.3.23 | 100% | - | - | 11.6 | 100% | 11.6 | Phy.Completed
559 | 3) Formation cutting from Buhban to Tuivawl Road, Buhban | 28.98 | Saitual Division | 13.2.23 | 31.3.23 | 100% | - | - | 14.49 | 100% | 14.49 | Phy.Completed
560 | 4) PCC Flooring from Catholic Church to Presbyterian Church, Dilkhan & Improvement of Internal Roads | 14.49 | Saitual Division | 13.2.23 | 31.3.23 | 100% | - | - | 7.24 | 100% | 7.24 | Phy.Completed
561 | 5) PCC Flooring from Main Road to High School Road, N.Lungpher & Improvement of Internal Roads | 20.29 | Saitual Division | 13.2.23 | 31.3.23 | 100% | - | - | 10.14 | 100% | 10.14 | Phy.Completed
562 | 6) Construction of concrete pavement between Hmundo to Tuivawl at Zawngin & Improvement of Internal Roads | 19.32 | Saitual Division | 13.2.23 | 31.3.23 | 100% | - |  | 9.66 | 100% | 9.66 | Phy.Completed
563 | 7) Formation cutting of Khanpui road to Tlanghmawr Approach Road, Tualbung & Improvement of Internal Roads | 19.32 | Saitual Division | 13.2.23 | 31.3.23 | 100% | - | - | 9.66 | 100% | 9.66 | Phy.Completed
564 | B.Section-II 1) Resurfacing of Rulchawm to Ruallung | 85.64 | Saitual Division | 13.2.23 | 31.3.23 | 50% | - |  | 42.82 | 50% | 42.82 | Work in progress
565 | 2) Construction of Retaining Wall at 2.300 Km on Rulchawm - Mualpheng Road | 1.71 | Saitual Division | 13.2.23 | 31.3.23 | 100% | - | - | 0.85 | 100% | 0.85 | Phy.Completed
566 | 3) Construction of Retaining Wall at 2.50 Km on Rulchawm - Mualpheng Road | 5.32 | Saitual Division | 13.2.23 | 31.3.23 | 100% | - | - | 2.66 | 100% | 2.66 | Phy.Completed
567 | 4) Construction of Retaining Wall at 4.70 Km on Rulchawm - Mualpheng Road | 3.55 | Saitual Division | 13.2.23 | 31.3.23 | 100% | - | - | 1.77 | 100% | 1.77 | Phy.Completed
568 | 5) Construction of Retaining Wall at 18.800 Km on Mualpheng - Maite Road | 3.34 | Saitual Division | 13.2.23 | 31.3.23 | 100% | - | - | 1.67 | 100% | 1.67 | Phy.Completed
569 | 6) Resurfacing of Ruallung - Maite Road up to Mualpheng | 211.69 | Saitual Division | 13.2.23 | 31.3.23 | 35% | - | 15% | 105.84 | 50% | 105.84 | Work in progress
570 | 7) Construction of RCC Side Drain between 0.400Km and 1.000 Km on Helipad Road, Saitual | 19.24 | Saitual Division | 13.2.23 | 31.3.23 | 100% | - | - | 9.62 | 100% | 9.62 | Phy.completed
571 | 8) Construction of V Shape RCC Side Drain between 1.000 Km and 2.000 Km on Helipad Road, Saitual | 50.62 | Saitual Division | 13.2.23 | 31.3.23 | 100% | - | - | 3.2 | 100% | 3.2 | Phy.completed
572 | 9) Construction of Retaining Wall at 18.900 Km on Mualpheng - Maite Road | 3.34 | Saitual Division | 13.2.23 | 31.3.23 | 100% | - | - | 1.67 | 100% | 1.67 | Phy.completed
573 | 10) Construction of Retaining Wall at 0.70Km on Helipad Road, Saitual | 2.17 | Saitual Division | 13.2.23 | 31.3.23 | 100% | - | - | 1.08 | 100% | 1.08 | Phy.completed
574 | 11) Construction of Retaining Wall at 0.90 Km on Helipad Road, Saitual | 2.22 | Saitual Division | 13.2.23 | 31.3.23 | 100% |  | - | 1.11 | 100% | 1.11 | Phy.completed
575 | 12) Construction of Retaining Wall at 15.350 Km on Mualpheng - Maite Road | 4.28 | Saitual Division | 13.2.23 | 31.3.23 | 100% | - | - | 2.14 | 100% | 2.14 | Phy.completed
576 | 13) Construction of RCC Covered Cross Drain at 1.250 Km on Helipad Road, Saitual | 2.67 | Saitual Division | 13.2.23 | 31.3.23 | 100% | - | - | 1.33 | 100% | 1.33 | Phy.completed
577 | 14) Construction of Rigid Pavement of DC Complex Road, Saitual | 183.86 | Saitual Division | 13.2.23 | 31.3.23 | 17.61% | - | 0.23% | 91.93 | 17.84% | 91.93 | Work in progress
| Strengthening of Phairuang - Thenhlum Road Group-A | 5.81 | Tlabung Division | 2023-03-01 | March-2024 | 100% | - |  | 2.65 | 100% | 2.65 | Completed Phy.Works
578 | 1. Excavation for Structure (Earth work in excavation of foundation of structures as per drawing and technical specification, including setting out I. Ordinary soil (upto 3m depth)
579 | 2. Plain/Reinforced cement concrete in sub-structure complete as per drawing and technical specifications, A.PCC Grade Grade M15 Nominal mix 1:3:6 (hand mixing) | 4.35 | Tlabung Division | 2023-03-23 | March-2024 | 100% | - |  | 2.02 | 100% | 2.02 | Completed Phy.Works
580 | 3. Stone Masonry work in cement mortar for substructure complete as per drawing and Technical Specifications II. Course rublle masonry (1st sort) iii) in cement mortar 1:3 | 15.75 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | 7.45 | 100% | 7.45 | Completed Phy.Works
581 | 4. Providing and laying filter media with granular crush aggregates as per specification to a tickness of not less than 600mm | 4.34 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | 2.02 | 100% | 2.02 | Completed Phy.Works
582 | 5. Restoration of Rain Cuts (Restoration of rain cuts with soil, moorum, gravel or a mixture of these, clearing the loose soil, benching for 300mm width | 0.82 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | 0.38 | 100% | 0.38 | Completed Phy.Works
583 | 6. Cement Concrete Pavement with a provision of edge stone (Construction of un-reinforced, dowel jointed, plain cement concrete pavement over a prepared sub base with 43 grade cement | 18.19 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | 6 | 100% | 6 | Completed Phy.Works
584 | 7. PCC 1:3:6 in Foundation (Plain cement concrete 1:3:6 nominal mix in foundation with crushed stone aggregate 40mm nominal size mechanically mixed, placed in foundation and compacted by vibration including curing 14 dyas) | 18.97 | Tlabung Division | March 2023 | March-2025 | 100% | - |  | 8.35 | 100% | 8.35 | Completed Phy.Works
585 | 8. Plain/Reinforced cement concrete in open foundation complete as per drawing and techincal specifications A.PCC Grade M15 | 8.55 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | 3.98 | 100% | 3.98 | Completed Phy.Works
586 | 9. Earthwork in exvacation in foundation trenches etc.not exceeding 2 meters depth including dressing of bottom and sides of trenches Hard soil (Pick work) | 0.84 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | 0.39 | 100% | 0.39 | Completed Phy.Works
587 | 10. Filling available excavated earth (excluding rock) in trenches, plinth, sides of foundations etc.in layers not exceeding 20cm in depth | 0.01 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | 0.004 | 100% | 0.004 | Completed Phy.Works
588 | 11. Providing and laying cement concrete in retaining wall, return walls, walls (any thickness) including pilasters, 1:3:6 (1 cement: 3 course sand: 6 stone aggregate 40mm) | 0.52 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | 0.24 | 100% | 0.24 | Completed Phy.Works
589 | 12. Steel reinforcement for RCC work including straighthening, cutting, bending, placing in position and binding all complete. Mild steel and medium Tensile steel bars | 2.33 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | 1.08 | 100% | 1.08 | Completed Phy.Works
590 | 13. Providing, fitting and placing GI pipe 100mm dia | 5.07 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | 2.36 | 100% | 2.36 | Completed Phy.Works
591 | 14 Excavation in soil by Manual Means (Excavation for roadway in soil using manual means including loading in truck for carrying of cut earth to embankment site with all lifts and lead upto 1000 meters | 0.45 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | 0.21 | 100% | 0.21 | Completed Phy.Works
592 | 15. Stone Masonry work in cement mortar in foundation complete as per drawing and technical specifications clauses 702, 704, 1202 & 1203. II. Coursed rubble masonry ii) In 1:4 cement mortar | 10.45 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | 6.72 | 100% | 6.72 | Completed Phy.Works
593 | 16. Providing and laying in position cement concrete of specified grade excluding cost of centering and shuttering-All work upto plinth level: 1:2:4 (Cement:2 course sand: 4 stone aggregate 20mm nominal size) | 2.21 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | 1.03 | 100% | 1.03 | Completed Phy.Works
594 | 17. Providing and laying in position reinforced cement concrete excluding cost of centering and shuttering, finishing and reinforcement in- 1:2:4 (1 cement: 2 coarse sand:4 graded stone aggregate 20mm nominal size) | 0.47 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | 0.22 | 100% | 0.22 | Completed Phy.Works
595 | 18. First class brickwork in foundation and plinth in: (b) in cement mortar 1:4 | 4.46 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | 2.07 | 100% | 2.07 | Completed Phy.Works
596 | 19. Providing 1st class local wood in trusses etc.including purlin, hoisting fixingf in position supplying necessary fittings such as spikes bolts and nuts, nails etc and applying wood preservative for unexposed surface etc.complete | 0.7 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | 0.33 | 100% | 0.33 | Completed Phy.Works
597 | 20. Providing corrugated G.S sheet roofing fixed with polymer coated J or L hooks, bolts and nuts 8mm diameter with nitumen and G.I limpet washers or with G.I limpet washers filled with white lead and including a coat of approved steel primer 0.80mm thick with zinc coating not less than 275gm/m2 | 0.65 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | 0.33 | 100% | 0.33 | Completed Phy.Works
598 | 21. Providing and fixing 1st class teak wood panelled and glazed shutters using 4mm thick plate sneet glass for doors and windows etc.including M.S butt hinges with necessary screws etc. complete | 1.2 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | 0.52 | 100% | 0.52 | Completed Phy.Works
599 | 22. Painting with synthetic enamel paint of approved brand and manufacture in all shades on new work. (two or more coats) | 0.22 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | 0.14 | 100% | 0.14 | Completed Phy.Works
600 | 23. Supplying, fitting and placing HTSD bar reinforcement in sub-structure complete as per drawing and technical specifications | 19.1 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | 9.05 | 100% | 9.05 | Completed Phy.Works
601 | 24. Providing and laying reinforce cement concrete in super structure as per drawing and technical specifications clause 800, 1205.4 and 1205.5 II. RCC M25 grade | 2.1 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | 1.12 | 100% | 1.12 | Completed Phy.Works
602 | 25. Backfilling in abutment, wing wall and return wall complete as per drawing and technical specification clause 1204.3.8 I. Granular material | 1.46 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | 0.68 | 100% | 0.68 | Completed Phy.Works
603 | 26. Stone masonry in cement mortar 1:3 for parapet complete as per drawing and technical specifications Clasues 700 and 1208.4 A.Random rubble masonry | 0.36 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | 0.17 | 100% | 0.17 | Completed Phy.Works
604 | 27. Plastering with cement mortar (1:4) 15mm thick on Brick/Stone works as per drawing and technical specification clauses 613.4 and 1204 | 0.85 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | 0.4 | 100% | 0.4 | Completed Phy.Works
605 | 28. Providing 1st class local wood work dressed in frames of sill, upright, batten, post, beams etc. as structural members fixed in position complete | 0.94 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | 0.44 | 100% | 0.44 | Completed Phy.Works
606 | 29. Providing 2nd class local wood work dressed in frames of chaukut for doors, windows, clerestory windows fixed in postion | 0.2 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | 0.09 | 100% | 0.09 | Completed Phy.Works
607 | 30. Providing and fixing 25mm thick and 2nd class local wood plank walling (both sides planned) tongue and groove joints including necessary nails, screws, etc.complete | 0.84 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | 0.39 | 100% | 0.39 | Completed Phy.Works
608 | 31. Providing and fixing MS handles with necessary screws etc (a) 150mm | 0.01 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | 0.002 | 100% | 0.002 | Completed Phy.Works
609 | 32. Providing and fixing MS hooks and eyes (a) 200mm | 0 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | 0.0002 | 100% | 0.0002 | Completed Phy.Works
610 | 33. Providing and fixing MS tower bolts (socket bolts) bright finished with necessary screws etc. (a) 200mm | 0.03 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | 0.1 | 100% | 0.1 | Completed Phy.Works
611 | (b) 150mm | 0 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | 0.0001 | 100% | 0.0001 | Completed Phy.Works
612 | 34. Earthwork in excavation for foundation of structures upto 3m depth as per drawing and technical specification | 0.8 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | 0.35 | 100% | 0.35 | Completed Phy.Works
613 | 35. Providing cement concrete M10 (1:3:6) in levelling cpurse below open foundation of head wall as per drawing and technical specification clause 1109. I. PCC grade M10 Mominal mix 1:3:6 (hand mixing) | 1.2 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | 0.56 | 100% | 0.56 | Completed Phy.Works
614 | 36. Stone Masonry Work in cement mortar in foundation of head walls complete as per drawing and technical specification Clause 1109 (A) in 1:4 cement Mortar | 5.64 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | 3.45 | 100% | 3.45 | Completed Phy.Works
615 | 37. Type-B (First class) bedding: Lating (first class) bedding of well compacted sand, moorum or approved granular materials as per clause 1105 (ii) | 0.14 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | 0.07 | 100% | 0.07 | Completed Phy.Works
616 | 38. Providng and laying RCC Pipe NP3 for Culvert on first class bedding of granular material | 4.74 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | 2.25 | 100% | 2.25 | Completed Phy.Works
617 | 39. Backfilling in abutment, wing wall and return wall complete as drawing and technical specification clause 1204.3.8 I. Granular material | 0.85 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | 0.42 | 100% | 0.42 | Completed Phy.Works
618 | 40. Backfilling in Foundation Trenches as per drawing and techniical specification Clause 1108 II. Earth filling | 0.05 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | 0.02 | 100% | 0.02 | Completed Phy.Works
619 | 41. Stone masonry in cement mortar 1:3 for parapet complete I. Random rubble masonry | 0.25 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | 0.12 | 100% | 0.12 | Completed Phy.Works
620 | 42. Plastering with cement mortar (1:4) 15mm thick on Brick/Stone works | 0.08 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | 0.04 | 100% | 0.04 | Completed Phy.Works
621 | 43. Providing PCC M20 architectural coping on the top of retaining wall complete between parapet walls | 0.13 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | 0.06 | 100% | 0.06 | Completed Phy.Works
| Sttrengthening of Phairuangkai-Thenhlum Road Group-B | 1.79 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | 0.83 | 100% | - | Completed Phy.Works
622 | 1. Clearing and Grubbing Road Land. (Clearing and gribbing road land including uprooting rank vegetation, grass, bushes, shribs, sapling and tress girth up to 300 mm, removal of stumps of tree cut earlier By Manual Means:- In area of thorny jungle
2. Cutting of Tress, including cutting of Trunks, Branches and Removal (Cutting of tress, including cutting of trunks, branches and removal of stumps, roots, stacking
623 | Girth from 300mm to 600mm | 0.09 | Tlabung Division | Mar'23 | Mar'24 | 100% |  |  | 0.04 | 100% | 0.04 | Phy.completed
624 | Girth from 600mm to 900mm | 0.07 | Tlabung Division | Mar'23 | Mar'24 | 100% |  |  | 0.03 | 100% | 0.03 | Phy.completed
625 | Girth from 900mm to 1800 | 0.12 | Tlabung Division | Mar'23 | Mar'24 | 100% |  |  | 0.06 | 100% | 0.06 | Phy.completed
626 | 3. Excavation in Soil by Mechanical means (Excavation for road way in soil by mechanical means including cutting | 12.88 | Tlabung Division | Mar'23 | Mar'24 | 100% |  |  | 5.99 | 100% | 5.99 | Phy.completed
627 | 4. Excavation in Ordinary Roak by Mechanical means (Excavation for roadway in ordinary rock by mechanical menas including cutting and pushing the earth | 9.46 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | 4.4 | 100% | 4.4 | Completed Phy.Works
628 | 5. Restoration of Rain Cuts (Restoration of rain cuts with soil, moorum, gravel or a mixture of these, clearing the loose soil | 0.69 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | 0.32 | 100% | 0.32 | Completed Phy.Works
629 | 6. Cement Concrete Pavement with a provision of edge stone (Construction of un-reinforced, dowel jointed, plain cement concrete pavement over a prepared sub base with 43 grade cement @400 kg per cum | 38.16 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | 17.74 | 100% | 17.74 | Completed Phy.Works
630 | 7. Excavation of structures (Earth work in excavtion of foundation of structures as per drawing and technical specification, including setting out, construction of shoring and bracing, removal of stumps and other deleterious matter, dressing of sides and bottom and backfilling with approved material) I. Orinary soil (upto 3m depth) | 11.16 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | 5.23 | 100% | 5.23 | Completed Phy.Works
631 | 8. Earthwork in excavation in foundation trenches etc, not exceeding 2 meters depth including dressing of bottom and sides of trenches Hard soil (pick work) | 0.66 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | 0.31 | 100% | 0.31 | Completed Phy.Works
632 | 9. Excavation in Soil by Manual Means (Excavation for roadway in soil using manual means including loading in truck for carrying of cut earth to embankment site with all lifts and lead upto 1000 metres) | 0.5 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | 0.23 | 100% | 0.23 | Completed Phy.Works
633 | 10. PCC 1:3:6 in Foundation (Plain cement concrete 1:3:6 nominal mix in foundation with crushed stone aggregate 40mm nominal size mechanical mixed, placed in foundation and compacted by vibration including curing for 14 days) | 20.18 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | 9.38 | 100% | 9.38 | Completed Phy.Works
634 | 11. Plain/Reinforced cement concrete in sub-structure complete as per drawing and technical specifications A. PCC Grade M15 Nominal mix 1:3:6 (hand mixing) | 10.94 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | 5.09 | 100% | 5.09 | Completed Phy.Works
635 | 12. Providing and laying in position reinforced cement concrete exluding cost of centering and shuttering, finishing and reinforcement in - 1:2:4 (1 cement:2 coarse sand: 4 graded stone aggregate) | 0.79 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | 0.37 | 100% | 0.37 | Completed Phy.Works
636 | 13. Plain/Reinforced cement concrete in open foundation complete as per drawing and technical specifications A. PCC Grade M15 | 17.22 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | 8.02 | 100% | 8.02 | Completed Phy.Works
637 | 14. Providing and laying in position cement concrete of specified grade excluding cost of centering and shuttering - All work upto plinth level: 1:2:4 (1 cement:2 coarse sand: 4 graded stone aggregate 20mm nominal size) | 1.23 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | 0.57 | 100% | 0.57 | Completed Phy.Works
638 | 15. Stone Masonry work in cement mortar for substructure complete as per drawing and Technical specifications II. Course rubble masonry (1st sort) (iii) in cement mortar 1:3 | 47.05 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | 21.98 | 100% | 21.98 | Completed Phy.Works
639 | 16. Complete as per drawing and technical specifications claises 702, 704, 1202 & 1203 II. Coursed rubble masonry (ii) In 1:4 cement mortar | 11.35 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | 5.29 | 100% | 5.29 | Completed Phy.Works
640 | 17. Stone Masonry in cement mortar 1:3 for parapet complete as per drawing and technical specifications A.Random rubble masonry | 0.07 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | 0.04 | 100% | 0.04 | Completed Phy.Works
641 | 18. Providing and laying filter media with granular crush aggregates as per specification to a thickness of not less than 600mm | 7.29 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | 3.39 | 100% | 3.39 | Completed Phy.Works
642 | 19. Backfilling in abutment, wing wall and return wall complete as per drawing and technical specification I. Granular material | 0.46 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | 0.21 | 100% | 0.21 | Completed Phy.Works
643 | 20. Filling available excavated earth (excluding rock) in trenches, plinth, sides of foundation etc. in layers not exceeding 20cm in depth, consolidating each deposited layer by ramming and watering, lead up to 50m and lift upto 15m | 1.01 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | 0.004 | 100% | 0.004 | Completed Phy.Works
644 | 21. Providing and laying cement concrete in retaining wall, return walls, walls (any thickness) including pilasters, piers, columns, abutments, pillars, posts, 1:3:6 (1 cement : 3 course sand : 6 stone aggregate 40mm) | 0.62 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | 0.29 | 100% | 0.29 | Completed Phy.Works
645 | 22. Plastering with cement mortar (1:4) 15mm thick on Brick/Stone works as per drawing and technical specification clauses 613.4 and 1204 | 0.58 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | 0.27 | 100% | 0.27 | Completed Phy.Works
646 | 23. Providing and laying reinforced cement concrete 1:2:4 (b) Column, etc | 0.13 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | 0.06 | 100% | 0.06 | Completed Phy.Works
647 | 24. Providing and laying reinforce cement concrete in super structure as per drawing and technical specifications clause 800, 1205.4 and 1205.5 II. RCC M25 grade | 0.79 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | 0.47 | 100% | 0.47 | Completed Phy.Works
648 | 25. Steel reinforcement for RCC work including straighthening cutting, bending, placing in position and binding all complete Mild steel and Medium Tensile steel bars | 3.82 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | 1.78 | 100% | 1.78 | Completed Phy.Works
649 | 26. Supplying, fitting and placing HYSD bar reinforcement in sub-structure complete as per drawing and technical specifications | 1.6 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | 0.75 | 100% | 0.75 | Completed Phy.Works
650 | 27. Providing, fitting and placing GI pipe 100mm dia | 6.14 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | 2.87 | 100% | 2.87 | Completed Phy.Works
651 | 28. Providing and fixing G.I Union in existing G.I pipeline, cutting and threading the pipe and making long screws including excavation refilling the earth or cutting of wall and making good the same complete wherever required. (f) 50mm nominal size | 0.01 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | 0.01 | 100% | 0.01 | Completed Phy.Works
652 | 29. First class brickwork in foundation and plinth in: (b) in cement mortar 1:4 | 3.19 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | 1.48 | 100% | 1.48 | Completed Phy.Works
653 | 30. Providing 1st class local wood in trusses etc.including purlin, hosting fixing in position supplying necessary fittings such as spikes bolts and nuts, nails etc and applying wood preservative for unexposed surface etc. complete | 1.49 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | 0.69 | 100% | 0.69 | Completed Phy.Works
654 | 31. Providing and fixing 1st class teak wood pannelled and glazed shutters using 4mm thick plate sneet glass for doors and windows etc.including M.S butt hinges with necessary screws etc. comoplete | 0.34 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | 0.16 | 100% | 0.16 | Completed Phy.Works
655 | 32. Providing corrugated G.S sheet roofing fixed with polymer coated J or L hooks, bolts and nuts 8mm diameter with bitumenn and G.I limpet washers 0.80 mm thick with zinc coating not less than 275gm/m2 | 0.77 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | 0.36 | 100% | 0.36 | Completed Phy.Works
656 | 33. Painting with synthetic enamel paint of approved brand and manufacture in all shades on new work (two or more coats) | 0.12 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | 0.06 | 100% | 0.06 | Completed Phy.Works
657 | Strenthening of Phairungkai-Thenhlum Road Group C | 1.71 | Tlabung Division | March 2023 | March-2024 | 100% | - |  |  | 100% | - | Completed Phy.Works
658 | 1. Construction of Subgrade and Earthen Shoulders (Construction of subgrade and eartheh shoulders with approved material obtained from borrow pits with all lifts & leads
659 | 2. Water Bound Macadam (Providng, laying, spreading and compactinf stone aggregates of specific sizes to water bound macadan specification including spreading in uniform thickness, A. By Manual Means (ii) Grading - 2 (53 mm to 22.4mm) (a) Using Screeining Crushable type such as Moorum of Gravel | 11.24 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | - | 100% | - | Completed Phy.Works
660 | 3. Cement Concrete Pavement (Construction of unreinforced, dowel jointed, plain cement concrete pavement over a prepared sub base with 43 grade cement | 56.07 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | - | 100% | - | Completed Phy.Works
661 | 4. Excavation for Structures (Earth work in excavation of foundation of structures as per drawing and technical specification. I. Ordinary soil (upto 3m depth) | 0.91 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | - | 100% | - | Completed Phy.Works
662 | 5. Stone masonry work in cement mortar for substructure complete as per drawing and Technical Specifications II. Course rubble masonry (1st sort) (iii) in cement mortar 1:3 | 21.28 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | - | 100% | - | Completed Phy.Works
663 | 6. Excavation for structure (Earth work in excavation for foundation of structures as per drawing and technical specification, (i) Ordinary soil A Manual Mean (Depth upto 3m) | 0.32 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | - | 100% | - | Completed Phy.Works
664 | 7. PCC 1:3:6 Foundation (Plain cement concrete 1:3:6 in foundation including for 14 days) | 0.914 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | - | 100% | - | Completed Phy.Works
665 | 8. Back filling behind abutment, wing wall and return wall complete as per drawing and Technical specification | 1.49 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | - | 100% | - | Completed Phy.Works
666 | 9. Plastering with cement mortar (1:3) in sub-structure as per Technical Specifications | 0.13 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | - | 100% | - | Completed Phy.Works
667 | 10. Excavation in Hilly areas in soil by Manual Means | 6.81 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | - | 100% | - | Completed Phy.Works
668 | 11. Excavation in Hilly areas in ordinary Rock by Manual Means | 2.37 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | - | 100% | - | Completed Phy.Works
669 | 12. Removal of unsuitable soil including excavtion, loading and disposals with a lead of 1000m | 0.95 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | - | 100% | - | Completed Phy.Works
670 | 13. Reinforced cement concrete approach slab including reinforcement and formwork complete as per drawing and Technical specification | 0.41 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | - | 100% | - | Completed Phy.Works
671 | 14. 12mm cement plaster 1:3 (1 cement : 3 fine sand) | 0.1 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | - | 100% | - | Completed Phy.Works
672 | 15. Providng and fixing G.I pipe complete with G.I fitting including trenching and refilling etc. (external work) | 2.28 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | - | 100% | - | Completed Phy.Works
673 | 16. Water Bound Macadam (Providing, layinf, spreading and compacting stone aggregates of specific sizes to water bound madacam specification (ii) Grading II (53mm - 22.4mm) (b) Using Screening type-B | 14.08 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | - | 100% | - | Completed Phy.Works
674 | 17. Prime coat (Providing and applying primer coat with bitument emulsion on prepared surface of granular base including 1) Low Porosity | 1.55 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | - | 100% | - | Completed Phy.Works
675 | 18. Tack Coat (Providing and applying tack coat with bitumen emulsion using emulsion pressure distributor (ii) Granular surface treated with primer | 0.93 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | - | 100% | - | Completed Phy.Works
676 | 19. Open-Graded Premix Surfacing (Providng laying and rolling of open graded premix surfacing of 20mm thickness | 8.57 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | - | 100% | - | Completed Phy.Works
677 | 20. Seal Coat (Providing and laying seal coat sealing the voids in a bituminous surface laid to the specified levels, grade and cross fall using Type A and B seal coat A using Bitumen 60/70 grade (i) Case - I : Type A | 2.96 | Tlabung Division | March 2023 | March-2024 | 100% | - |  | - | 100% | - | Completed Phy.Works
678 | Construction of Public Playground at Thenzawl (Sh: Const.of Public Playgound Galley of length 120 metre (6 block of 20 metre each including 3 (three) steps for sitting at Thenzawl | 24.32 | Project Division-II | 26.02.23 | 26.08.23 | 50% | - | 40% | - | 90% | - | Completed Phy.Works
679 | Construction of Community Hall at Chawilung (Sh: Construcytion of Steel Truss with dyna roofing) | 5.84 | Project Division-II | 24.02.23 | 24.04.23 | 90% | - | 10% | - | 100% | - | Completed Phy.Works
680 | Construction of Community Hall at Hualngohmun (Sh: Construction of Steel Truss with dyna roofing) | 7.78 | Project Division-II | 24.02.23 | 24.04.23 | 80% | - | 20% | - | 100% | - | Completed Phy.Works
681 | Construction of MUP House at Zamuang, Mamit District | 14.43 | Project Division-II | 26.02.23 | 26.06.23 | 95% | - | 5% | - | 100% | - | Completed Phy.Works
682 | Construction of Urinal Sheds (sh: Near Rambeiseia In, BBEC Pastor Qtrs, Pu Lalzama House, Lalaithai's House, C.Laltanpuia House, Darlak Peng at Tuidam, Urinal Sheds at Vengthar, W.Bunghmun, H/S Veng at Bunghmun, Near Baptist Church at New Eden, near Presbyterian Church at New Eden) | 4.85 | Project Division-II | 24.02.23 | 24.04.23 | 100% | - |  | - | 100% | - | Completed Phy.Works
683 | Construction of waiting Sheds (Sh: Const.of Waiting shed at Dilpeng, Kawrtethawveng 2. Repair of Waiting Shed at New Kawnpui Village 3. Construction of Buhfai Semna/Dahna Teireikam at Kananthar). | 7.3 | Project Division-II | 24.02.23 | 24.04.23 | 95% | - | 5% | - | 100% | - | Completed Phy.Works
684 | Construction of Pavement of Chequered Tiles (Sh: Near Pi Duhkungi House to Kawnghnuai at Tuidam 2. Ramrikawn to Pi Rinngaii In Kawng at Kawrtethawveng 3. Mualzawl (Hmarveng) to Arm Veng 4. KDZKT Road to Internal Road near Pi Nuntluangi In at Kawrtethawveng 5. Chequered Tile phah, step Repair approach to Tuikhuah tuikhur panna at Kawrtethawveng) | 9.24 | Project Division-II | 24.02.23 | 24.04.23 | 100% | - |  | - | 100% | - | Work phy.completed
685 | Construction of Tourist Lodge at Kawnpui | 48.78 | Project Division-II | 26.02.23 | 26.10.23 | - | - | - | - | - | - | Work not started
686 | Construction of Futsal Ground at Kawnpui Chhimveng | 24.65 | Project Division-II | 25.02.23 | 25.06.23 | 10% | - | 10% | - | 20% | - | Work in progress
687 | Continuation of Public Playground at Serkhan | 14.6 | Project Division-II | 25.03.23 | 25.05.23 | 70% | - | 5% | - | 75% | - | Work in progress
688 | Construction of Community Hall at Hortoki | 68.25 | Project Division-II | 26.02.23 | 26.10.23 | 80% | - | 10% | - | 90% | - | Work in progress
689 | Continuation of Public Playground at Zanlawn | 14.6 | Project Division-II | 25.02.23 | 25.05.23 | 5% | - | 25% | - | 30% | - | Work in progress
690 | Continuation of Public Playground at Bualpui | 14.6 | Project Division-II | 25.02.23 | 25.05.23 | - | - | 20% | - | 20% | - | Work being started
691 | Construction of Bazar Shed at Nisapui | 14.6 | Project Division-II | 25.02.23 | 25.05.23 | - | - | - | - | - | - | Work not started
692 | Continuation of Futsal Ground at Lungdai | 24.29 | Project Division-II | 25.02.23 | 25.06.23 | 20% | - | 10% | - | 30% | - | Work in progress
693 | Construction of Govt.Serchhip College (Sh: Adninistrative Block) | 650 | Project Division-III | 27.02.23 | 27.02.25 | 3 | - | 10% | - | 13% | - | work in progress
Improvement of Tlabung Road - Thuamluaia Mual - College Veng - Rahsi Veng at Lunglei District in Mizoram for the year 2022-2023 under SASCI, Length = 11.500 kms
694 | Strengthening & Re-Surfacing of Aizawl-Thenzawl-Lunglei Road from 160.00-164.00 Kmp (Kikawn, AOC Veng, Lunglei. | 590.07 | Lunglei Road Division I | 18.6.22 | 18.12.22 | 100% | 427 | - | - | 100% | 427 | Phy.Completed
695 | Improvement of Tlabung road to Thuamluaia Mual Junction (a) Dismantling of Flexible Pavement, Earthwork for Lowering, Pavement Works | 44.77 | Lunglei Road Division-I |  |  | 50% | - | 40% | - | 90% | - | Work in progress
696 | (b) Construction of Retaining Wall (2 Nos) | 6.14 | Lunglei Road Division-I |  |  | 5% | - | 95% | - | 100% | - | Phy.Completed
697 | (c) Construction of RCC Hume pipe Culvert (1 No) | 10.8 | Lunglei Road Division-I |  |  | 100% | - |  | - | 100% | - | Phy.Completed
698 | (d) Construction of RCC Line Side Drain (75.00 Rm) | 2.03 | Lunglei Road Division-I |  |  | 10% | - | 80% | - | 90% | - | Work in progress
699 | (e) Construction of RCC Public Step (7.00 Rm) Drain (75.00 Rm) | 1.06 | Lunglei Road Division-I |  |  | - | - | 50% | - | 50% | - | Work in progress
700 | (f) Utility Shifting of Electric Pole, Water Pipe Lines, telephone line etc (Lumpsum) | 3 | Lunglei Road Division-I |  |  | - | - | 100% | - | 100% | - | Phy.Completed
701 | Construction of PCC Pavement between Tarmita road, Kikawn and College Veng | 84.75 | Lunglei Road Division-I |  |  | 99% | - |  | - | 99% | - | Work in progress
702 | Construction of Bluemount Farmers Society approach road from Thehlep Road | 25.42 | Lunglei Road Division-I |  |  | 99% | - |  | - | 99% | - | Work in progress
703 | Construction of approach road from Post Office, Lunglei to BCM Church Road (a) Dismentling, Excavation/Lowering and Pavement | 7.99 | Lunglei Road Division-I |  |  | 95% | - |  | - | 95% | - | Work in progress
704 | (b) Construction of Retaining Wall | 16.43 | Lunglei Road Division-I |  |  | 95% | - |  | - | 95% | - | Work in progress
705 | (c) Utility Shifting of Electric Pole, Water Pipe lines, Telephone lines etc (lumpsum) | 1 | Lunglei Road Division-I |  |  | 95% | - |  | - | 95% | - | Work in progress
706 | Construction of Slab Culvert at Lamhla Tuikhur, Tarmita Road Bazar Veng Kikawn | 16.95 | Lunglei Road Division-I |  |  | 40% | - | 60% | - | 100% | - | Phy.Completed
707 | Construction of Retaining wall near Kailiana's House Rahsiveng Veng, Lunglei | 8.47 | Lunglei Road Division-I |  |  | 50% | - | 50% | - | 100% | - | Phy.Completed
708 | Construction of Slab Culvert at Kawngkan Lui | 12.71 | Lunglei Road Division-I |  |  | - | - | 50% | - | 50% | - | Work in progress
709 | Construction of PCC Pavement from Bazar Veng Thlanmual No.2 BNGRSK Building to Pu Tawnga Garden | 25.42 | Lunglei Road Division-I |  |  | 50% | - | 50% | - | 100% | - | Phy.Completed
710 | Construction of PCC Pavement approach road to Lunglei Venghlun Cemetary | 25.42 | Lunglei Road Division-I |  |  | 85% | - | 15% | - | 100% | - | Phy.Completed
711 | Construction of PCC Pavement from Ngaihlova's House to Mini Sport Complex | 25.42 | Lunglei Road Division-I |  |  | 70% | - | 20% | - | 90% | - | Work in progress
Improvement of Chanmari -Electric Veng-Ramthar Veng at Lunglei District in Mizoram for the year 2022-2023 under SASCI, Length = 9.000 kms
712 | Construction of Slab Culvert at Ramthar & Salem boundary at Ramthar | 16.95 | Lunglei Road Division-I |  |  | 50% | - | 15% | - | 65% | - | Work in progress
713 | Construction of Line side Drain from Nghaksangi House to Venhimi House at Ramthar veng | 2.97 | Lunglei Road Division-I |  |  | - | - | - | - | - | - | Not Yet Started
714 | Construction of PCC Pavement from Highway to BCM Galili Church at Ramthar Veng | 4.24 | Lunglei Road Division-I |  |  | 100% | - |  | - | 100% | - | Phy.Completed
715 | Construction of Retaining wall from Zairemmawia House to F.Muanawma House at Ramthar veng | 4.24 | Lunglei Road Division-I |  |  | - | - | 100% |  | 100% |  | Phy.Completed
716 | Construction of Retaining wall at Sapdawla Land & Pu J.Lianngura Land at Ramthar veng | 3.39 | Lunglei Road Division-I |  |  | - | - | - | - | - | - | Not Yet Started
717 | Renovation of step from Saidingliana House to Hmuzuala House at Ramthar | 3.39 | Lunglei Road Division-I |  |  | - | - | - | - | - | - | Not Yet Started
718 | Construction of Retaining wall from V.Muankima House to Thangte Veng Tuikhur at Ramthar Veng | 4.24 | Lunglei Road Division-I |  |  | - | - | - | - | - | - | Not Yet Started
719 | Construction of PCC Pavement from Thathleia's House to T.Lalthianghlima House at Ramthar veng | 1.7 | Lunglei Road Division-I |  |  | - | - | - | - | - | - | Not Yet Started
720 | Construction of PCC Pavement from Zaii House to Lallawzuali House at Ramthar veng | 1.27 | Lunglei Road Division-I |  |  | - | - | - | - | - | - | Not Yet Started
721 | Laying of Chequerred Tiles from V.Muankima House to Tuikhur Kawng at Ramthar | 5.08 | Lunglei Road Division-I |  |  | - | - | - | - | - | - | Not Yet Started
722 | Construction of PCC Pavement from YMA Run to Lianzathanga's House via Thanpuii's House at Electric Veng | 7.63 | Lunglei Road Division-I |  |  | - | - | - | - | - | - | Not Yet Started
723 | Construction of Retaining wall at Pu Zalawma Punte land at Electric veng | 6.78 | Lunglei Road Division-I |  |  | - | - | - | - | - | - | Not Yet Started
724 | Construction of PCC Pavement from Pu Hmangaiha House to UPC NE Church at Electric Veng | 3.39 | Lunglei Road Division-I |  |  | - | - | - | - | - | - | Not Yet Started
725 | Construction of PCC Pavement from Main road to R.Rozika House near BCM Church at Electric Veng | 2.54 | Lunglei Road Division-I |  |  | - | - | - | - | - | - | Not Yet Started
726 | Construction of PCC Pavement from Muanzova to F.Lalsangliana House at Electric Veng | 5.09 | Lunglei Road Division-I |  |  | - | - | - | - | - | - | Not Yet Started
727 | Curve improvement of opposite of Pu Bawka Point at Farm Veng | 7.63 | Lunglei Road Division-I |  |  | 95 | - | 5% | - | 100% | - | Phy.Completed
728 | Construction of Retaining wall between Sericulture Gate to Lalremruata House at Farm Veng | 7.63 | Lunglei Road Division-I |  |  | 70% | - | 25% | - | 95% | - | Work in Progress
729 | Construction of Footpath between C.Lalthianghlima House to Vety Gate at Farm Veng | 6.78 | Lunglei Road Division-I |  |  | 50% | - | 50% | - | 100% | - | Phy.Completed
730 | Construction of HP Culvert near H.Saihmingthanga House at Farm Veng | 3.39 | Lunglei Road Division-I |  |  | 95% | - |  | - | 95% | - | Work in progress
731 | Construction of Line side drain between Rev.Killuaia House to Pu Lalrinpuia House at Chanmari | 5.93 | Lunglei Road Division-I |  |  | 100% | - |  | - | 100% | - | Phy.Completed
732 | Construction of PCC Pavement to Chanmari field at Chanmari | 11.86 | Lunglei Road Division-I |  |  | - | - | - | - | - | - | Not Yet Started
733 | Construction of Retaining at GHSS Lunglei Chanmari | 5.08 | Lunglei Road Division-I |  |  | - | - | 85% | - | 85% | - | Work in progress
734 | Construction of Retaining at Pu V.Lalnuntluanga House to Pu Rohmingthanga House at District Road Chanmari | 4.24 | Lunglei Road Division-I |  |  | - | - | 100% | - | 100% | - | Phy.Completed
735 | Construction of Retaining Wall at Leitlangpui HSS Chanmari | 6.78 | Lunglei Road Division-I |  |  | 40% | - | 60% | - | 100% | - | Phy.Completed
736 | Formation Cutting of Agricultural Link Road at Mausen | 8.47 | Lunglei Road Division-I |  |  | - | - | 70% | - | 70% | - | Work in progress
737 | Construction of New Internal Road in remembrance of the Golden Jubilee of Pukpui Village to be named Jubilee Road | 16.95 | Lunglei Road Division-I |  |  | 40% | - | 35% | - | 75% | - | Work in progress
738 | Formation Cutting of Mausep Agricultural Link Road at Sekhum | 16.95 | Lunglei Road Division-I |  |  | - | - | - | - | - | - | Not Yet Started
739 | Construction of Pavement on approach Road to Pialthleng at Lunglei District | 724 | Lunglei Road Division -I |  |  |  |  | 15% |  | 15% |  | Work in progress
740 | Construction of Retaining Wall at 4 places between Market Shed to Entrance of Pukpui along ATL Road | 50 | Lunglei Road Division -I | [8 empty] | Not Yet Started
741 | Construction of PCC Pavement from Santosh Mot's House to Duresh Chandra's House at Mauzam | 4.23 | Lunglei Road Division -I | [8 empty] | Not Yet Started
742 | Construction of PCC Pavement from main Road to Community Hall at Salmur | 2.82 | Lunglei Road Division -I |  |  |  |  | 14% |  | 14% |  | Work in progress
743 | Construction of PCC Pavement from Lalremruata's House to Lalnunzira's house at New Sachan | 4.51 | Lunglei Road Division -I |  |  |  |  | 97% |  | 97% |  | Work in progress
744 | Construction of approach road with PCC Pavement from PMGSY road to Phainuam | 10.15 | Lunglei Road Division -I |  |  |  |  | 23% |  | 23% |  | Work in progress
745 | Construction of Foot Step from Niachan's house to Lawngkai at Tuikawi | 3.07 | Lunglei Road Division -I |  |  |  |  | 13% |  | 13% |  | Work in progress
746 | Construction of RCC Foot Bridge from Rody Ranjan's house to Jugothi's House at Tuikawi | 3.54 | Lunglei Road Division -I |  |  |  |  | 100% |  | 100% |  | Phy.Completed
747 | Construction of Retaining Wall near Mandhir at Sumasumi | 9.18 | Lunglei Road Division -I |  |  |  |  | 100% |  | 100% |  | Phy.Completed
748 | Construction of PCC Pavement from Shanti's Pryo's House to Football Field at Sumasumi | 0.56 | Lunglei Road Division -I | [8 empty] | Not Yet Started
749 | Construction of PCC Pavement at Bazar line Old Sachan | 3.38 | Lunglei Road Division -I |  |  |  |  | 33% |  | 33% |  | Work in progress
750 | Construction of PCC Pavement from Gov't Primary School to Saimawia'a House at Laisawral | 3.38 | Lunglei Road Division -I |  |  |  |  | 95% |  | 95% |  | Work in progress
751 | Construction of PCC Pavement from Lalchhandama's House to Lalvulrenga's House at Laisawral | 1.69 | Lunglei Road Division -I |  |  |  |  | 100% |  | 100% |  | Phy.Completed
752 | Construction of PCC Pavement from internal road to Primary School at Laisawral | 0.34 | Lunglei Road Division -I |  |  |  |  | 100% |  | 100% |  | Phy.Completed
753 | Construction of PCC Pavement from internal road to P.Thanglura's house at Laisawral | 1.35 | Lunglei Road Division -I |  |  |  |  | 49% |  | 49% |  | Work in progress
754 | Construction of Foot Step from Saimawia's House to Baptist Church at Laisawral | 1.23 | Lunglei Road Division -I |  |  |  |  | 41% |  | 41% |  | Work in progress
755 | Construction of PCC Pavement from Primary School to Thlanmual Road at Tleu | 2.26 | Lunglei Road Division -I |  |  |  |  | 66% |  | 66% |  | Work in progress
756 | Construction of PCC Pavement from Saichhunga's House to Vengthar UPC Church at Sesawm | 5.64 | Lunglei Road Division -I |  |  |  |  | 36% |  | 36% |  | Work in progress
757 | Construction of PCC Pavement from Lalrindika's House to Sahlam Tree at Lungchem | 4.23 | Lunglei Road Division -I |  |  |  |  | 100% |  | 100% |  | Phy.Completed
758 | Construction of PCC Pavement from Sahlam Tree to C.Kairuma's House at Lungchem | 4.23 | Lunglei Road Division -I |  |  |  |  | 79% |  | 79% |  | Work in progress
759 | Construction of PCC Pavement from Lalnunpuia's House to Sub-Centre at Lungchem | 0.42 | Lunglei Road Division -I |  |  |  |  | 93% |  | 93% |  | Work in progress
760 | Consruction of Footstep from NERGS House Main road at Lungchem | 1.23 | Lunglei Road Division -I |  |  |  |  | 37% |  | 37% |  | Work in progress
761 | Construction of PCC Pavement from Bharat Chandra's House to Priya Ranjan's House at Marpara 'S' | 6.77 | Lunglei Road Division -I |  |  |  |  | 40% |  | 40% |  | Work in progress
762 | Construction of PCC Pavement from Priya Ranjan's House to Sneha Kumar's House at Marpara 'S" | 6.77 | Lunglei Road Division -I |  |  |  |  | 64% |  | 64% |  | Work in progress
763 | Construction of PCC Pavement from Baptist School to Bazar line at Marpara 'S' | 6.77 | Lunglei Road Division -I |  |  |  |  | 35% |  | 35% |  | Work in Progress
764 | Construction of PCC Pavement from Monu Ranjan's house to Kanchha's House at Bunghmun | 7.05 | Lunglei Road Division -I |  |  |  |  | 61% |  | 61% |  | Work in Progress
765 | Construction of PCC Pavement from Lalnunkima's Housw to Lalnunpuii's House at Bunghmun | 3.38 | Lunglei Road Division -I |  |  |  |  | 75% |  | 75% |  | Work in Progress
766 | Construction of Foot step from B. tlanghmingthanga's House to UPC Church at Bunghmun | 2.45 | Lunglei Road Division -I |  |  |  |  | 32% |  | 32% |  | Work in Progress
767 | Construction of PCC Pavement from Lalhmingthangi's House to Rochungnunga's House at Bunghmun | 5.08 | Lunglei Road Division -I |  |  |  |  | 80% |  | 80% |  | Work in Progress
768 | Construction of PCC Pavement from P/S - II to High School at Bunghmun | 3.38 | Lunglei Road Division -I |  |  |  |  | 98% |  | 98% |  | Work in Progress
769 | Construction of Newly Agricultural Link Road from Hnawla Dil to Chulpui Lui | 17.22 | Lunglei Road Division -I |  |  |  |  | 100% |  | 100% |  | Phy.Completed
770 | Construction of Newly Agricultural Link Road from Chulpui Lui to Sangkawi | 23.87 | Lunglei Road Division -I |  |  |  |  | 25% |  | 25% |  | Work in Progress
771 | Construction of PCC Pavement from Lalramhluna's House to Main Road at Changpui | 1.69 | Lunglei Road Division -I |  |  |  |  | 64% |  | 64% |  | Work in Progress
772 | Construction of Pavement from Changpui to Lunghar chho (Lungchem road) at Changpui | 1.69 | Lunglei Road Division -I |  |  |  |  | 72% |  | 72% |  | Work in Progress
773 | Construction of PCC Pavement from Health Worker's Quarter to Lalchawimawia's House at Dengsur | 2.82 | Lunglei Road Division -I |  |  |  |  | 98% |  | 98% |  | Work in Progress
774 | Construction of PCC Pavement from KV Thanmawia's House to High School at Dengsur | 2.82 | Lunglei Road Division -I |  |  |  |  | 100% |  | 100% |  | Phy.Completed
775 | Construction of PCC Pavement from Zoramthanga's House to PWD road at S.Khawlek | 0.51 | Lunglei Road Division -I |  |  |  |  | 100% |  | 100% |  | Phy.Completed
776 | Construction of PCC Pavement near BCM Church to P/S at S.Khawlek | 0.56 | Lunglei Road Division -I | [8 empty] | Not Yet Started
777 | Construction of Foot step near Liantluanga's House to Tuikhur at New Khawlek | 2.04 | Lunglei Road Division -I |  |  |  |  | 18% |  | 18% |  | Work in Progress
778 | Construction of Foot step near Suakthuama's House to Public Play Ground Road near New Khawlek | 3.07 | Lunglei Road Division -I |  |  |  |  | 41% |  | 41% |  | Work in Progress
779 | Construction of PCC Pavement from BCM Church to Lalsangzuala's House at New Khawlek | 1.13 | Lunglei Road Division -I |  |  |  |  | 100% |  | 100% |  | Phy.Completed
780 | Construction of slab Culvert near Ngurthangluaia's House at Thenhlum | 5.24 | Lunglei Road Division -I |  |  |  |  | 100% |  | 100% |  | Phy.Completed
781 | Construction of Slab Culvert near Thenhlum Playground - I | 7.5 | Lunglei Road Division -I |  |  |  |  | 100% |  | 100% |  | Phy.Completed
782 | Construction of PCC Pavement from main road to Football Playground at Thenhlum | 0.47 | Lunglei Road Division -I |  |  |  |  | 32% |  | 32% |  | Work in progress
783 | Construction of Foot step from Main Road to Middle School | 1.53 | Lunglei Road Division -I |  |  |  |  | 14% |  | 14% |  | Work in progress
Improvement & Upgradation of Roads from Hnahthial to Thingsai
784 | (a) Improvement and upgradation of Hnahthial - Thingsai Road | 48.37 | Lunglei Road Division-II |  |  | 20% | - | 60% | 24.18 | 80% | 24.18 | Work in progress
785 | (b) Construction of Darzo (Kawipui) Saibuchhuah Road | 96.61 | Lunglei Road Division-II |  |  | 100% | - |  | 48.3 | 100% | 48.3 | Phy.Completed
786 | (c) Improvement of Internal Road within Thingsai Village | 48.31 | Lunglei Road Division-II |  |  | - | - | 30% | 24.15 | 30% | 24.15 | Work in progress
787 | (d) Improvement of Hnahthial Town Road | 96.61 | Lunglei Road Division-II |  |  | 100% | - |  | 48.3 | 100% | 48.3 | Phy.Completed
788 | (e) PCC Flooring of Tarpho to Aithur Road | 173.92 | Lunglei Road Division-II |  |  | - | - | 20% | 86.96 | 20% | 86.96 | Work in progress
789 | (f) PDD Pavement from MTR (Road) Tuipui D to Nghafuan (R.Tuipui) Road | 67.63 | Lunglei Road Division-II |  |  | 30% | - | 20% | 33.81 | 50% | 33.81 | Work in progress
790 | (g) Improvement of road from Hnahthial Town to Takam tlaw | 48.3 | Lunglei Road Division-II |  |  | 10 | - | 80% | 24.15 | 90% | 24.15 | Work in progress
Construction and Upgradation of Road from Bualpui V to River Mat via Lungmawi
791 | (a) Strengthening/Widening of Road between Bualpui V to River Mat via Lungmawi | 96.61 | Lunglei Road Division-II |  |  | 30% | - | 30% | 48.3 | 60% | 48.3 | Work in progress
792 | (b) Const./FC of Road between Pangzawl to Tuichang | 28.98 | Lunglei Road Division-II |  |  | 80% | - |  | 14.49 | 80% | 14.49 | Work in progress
793 | (c) Improvement of Internal Road between main Pangzawl Village to upper Pangzawl | 28.98 | Lunglei Road Division-II |  |  | 100% | - |  | 14.49 | 100% | 14.49 | Phy.Completed
794 | (d) Const./FC of Agriculture Link Road at Thiltlang | 14.49 | Lunglei Road Division-II |  |  | - | - | 80% | 7.24 | 80% | 7.24 | Work in progress
795 | (e) Const./FC of Agriculture Link Road at Rawpui | 9.66 | Lunglei Road Division-II |  |  | - | - | 100% | 4.83 | 100% | 4.83 | Phy.Completed
796 | (f) Const./FC within Agriculture Link Road at Phaileng S | 9.66 | Lunglei Road Division-II |  |  | 80% | - | 20% | 4.83 | 100% | 4.83 | Phy.Completed
797 | (g) Const of PCC Pavement from Haulawng to Community Hall | 7.73 | Lunglei Road Division-II |  |  | 100% | - |  | 3.86 | 100% | 3.86 | Phy.Completed
Construction and Upgradation of Retaining Wall at Zobawk Ringroad
798 | (1) Re-Construction of permanent works at Tawipui N Mualcheng S at chainage 1.00 kmp, 2.500 kmp, 3.700 kmp, 3.720 kmp & 5.500 kmp | 37.1 | Lunglei Road Division-II |  |  | 100% | - | - | 18.55 | 100% | 18.55 | Phy.Completed
799 | (2) Construction of link road Silaitlak (Balu lakna) Road at Rotlang 'E | 4.83 | Lunglei Road Division-II |  |  | 100% | - |  | 2.41 | 100% | 2.41 | Phy.Completed
800 | (3) Construction of PCC Pavement at High school road at Rotlang East | 5.8 | Lunglei Road Division-II |  |  | 100% | - |  | 2.9 | 100% | 2.9 | Phy.Completed
801 | (4) Construction of PCC Pavement near F.Malsawmthanga House at Rotlang East | 1.93 | Lunglei Road Division-II |  |  | 100% | - |  | 0.96 | 100% | 0.96 | Phy.Completed
802 | (5) Construction of Retaining wall at Middle School at Rotlang E | 1.93 | Lunglei Road Division-II |  |  | 100% | - |  | 0.96 | 100% | 0.96 | Phy.Completed
803 | (6) Construction of Waiting Shed at Chinrang Kawn & Ramri Kawn at Ralvawng | 2.9 | Lunglei Road Division-II |  |  | 100% | - |  | 1.45 | 100% | 1.45 | Phy.Completed
804 | (7) Construction of link road at New Ralvawng to Old Ralvawng | 4.83 | Lunglei Road Division-II |  |  | 100% | - |  | 2.41 | 100% | 2.41 | Phy.Completed
805 | (8) Construction of PCC Pavement Vanlalhmuaki House to Middle Const.of PCC Pavement Vanlalhmuaki House to Middle School road at Lungpuizawl | 3.87 | Lunglei Road Division-II |  |  | 100% | - |  | 1.9 | 100% | 1.9 | Phy.Completed
806 | (9) Construction of PCC Pavement Hmingthana House to HS.Lalhmunmawia House at Lungpuizawl | 2.9 | Lunglei Road Division-II |  |  | 100% | - |  | 1.45 | 100% | 1.45 | Phy.Completed
807 | (10) Construction of PCC Pavement PCI Biak In to Public Playground at Lungpuizawl | 2.9 | Lunglei Road Division-II |  |  | 100% | - |  | 1.45 | 100% | 1.45 | Phy.Completed
808 | (11) Const.of Retaining Wall at NEI UPC Zobawk Local at Zobawk 'S' | 8.7 | Lunglei Road Division-II |  |  | - | - | 50% | 4.35 | 50% | 4.35 | Work in progress
809 | (12) Const.of R/W at Zobawk Venglai near Community Hall at Zobawk Venglai | 4.83 | Lunglei Road Division-II |  |  | 100% | - |  | 2.41 | 100% | 2.41 | Phy.Completed
810 | (13) Const.of Internal Road with Widening from Pu Kawlramtawna House to Tuitai Kawi at Zobawk Venglai | 9.18 | Lunglei Road Division-II |  |  | - | - | 100% | 4.54 | 100% | 4.54 | Phy.Completed
811 | (14) Const.of PCC Pavement Public Playground to Transformer at Zobawk Vengthar | 4.35 | Lunglei Road Division-II |  |  | - | - | 100% | 2.17 | 100% | 2.17 | Phy.Completed
812 | (15) Const.of PCC Pavement Zabuanga House to Zailawma House at Zobawk Vengthar | 5.8 | Lunglei Road Division-II |  |  | - | - | 100% | 2.9 | 100% | 2.9 | Phy.Completed
813 | (16) Const.of R/W near Govt HS Road (Hmawng hnuai) at Zobawk Vengthar | 5.8 | Lunglei Road Division-II |  |  | - | - | 50% | 2.9 | 50% | 2.9 | Work in progress
814 | (17) Const.of R/W B.Laltanpuii House at Zobawk Venghlun | 4.84 | Lunglei Road Division-II |  |  | 100% | - |  | 2.42 | 100% | 2.42 | Phy.Completed
815 | (18) Const.of PCC Pavement between C.Vanlalhmuaka House to P.Lalromawia House at Zobawk Bazar | 9.67 | Lunglei Road Division-II |  |  | - | - | 100% | 4.83 | 100% | 4.83 | Phy.Completed
816 | (19) Const.of PCC Pavement between Ralvawng mual Volleyball Court at Zobawk Bazar | 5.31 | Lunglei Road Division-II |  |  | 100% | - |  | 2.65 | 100% | 2.65 | Phy.Completed
817 | (20) Const.of PCC Pavement between Pu Lallawma to Pu V.Zoramthanga House at Zobawk Venghlun | 5.8 | Lunglei Road Division-II |  |  | - | - | 100% | 2.9 | 100% | 2.9 | Phy.Completed
818 | (21) Const.of RCC Steps C.Lalchungnunga House to Lallianpuii House at Zobawk Venghlun | 4.35 | Lunglei Road Division-II |  |  | - | - | 50% | 2.17 | 50% | 2.17 | Work in progress
819 | (22) Const.of PCC Pavement from Ramthim Dawr to Govt. Primary School at Leite | 2.9 | Lunglei Road Division-II |  |  | 100% | - |  | 1.45 | 100% | 1.45 | Phy.Completed
820 | (23) Const.of PCC Step with Railing and Side Drain between NH-54 to K.Vanramenga House at Leite | 6.77 | Lunglei Road Division-II |  |  | 100% | - |  | 3.38 | 100% | 3.38 | Phy.Completed
821 | (24) Reapairing & Widening of Roads Sairep to Hlumte Road | 11.6 | Lunglei Road Division-II |  |  | - | - | 100% | 5.8 | 100% | 5.8 | Phy.Completed
822 | (25) Const.of R/W near BCM Biak In & Lalramlawma House between Lalnunhlua House at Hlumte | 3.87 | Lunglei Road Division-II |  |  | - | - | 50% | 1.93 | 50% | 1.93 | Work in progress
823 | (26) Const.of Bawkzau (Sairep Village potential area) Link from Sairep Viallage | 38.64 | Lunglei Road Division-II |  |  | 25% | - | 50% | 19.32 | 75% | 19.32 | Work in progress
IMPROVEMENT OF HNAHTHIAL TOWN ROAD
824 | SMBT of approach Road to HDFA Playground | 63.6 | Lunglei Road Division-II |  |  |  |  | 100% | 31.8 | 100% | 31.8 | Phy.Completed
825 | Resurfacing within Hnahthial Town | 31.51 | Lunglei Road Division-II |  |  |  |  | 100% | 15.75 | 100% | 15.75 | Phy.Completed
826 | RCC Drain on approach Road to DC Office | 3 | Lunglei Road Division-II |  |  |  |  | 100% | 1.5 | 100% | 1.5 | Phy.Completed
827 | Retaining wall at Ch: 0.4 Km on approach Road to Zosangliana House to Lalduhawma House | 1.89 | Lunglei Road Division-II |  |  |  |  | 100% | 0.94 | 100% | 0.94 | Phy.Completed
828 | Retaining wall on H-T at Ch: 3.750 Kmp | 5.18 | Lunglei Road Division-II |  |  |  |  | 100% | 2.59 | 100% | 2.59 | Phy.Completed
829 | Retaining wall on H-T at Ch: 5.450 Kmp | 6.62 | Lunglei Road Division-II |  |  |  |  | 100% | 3.31 | 100% | 3.31 | Phy.Completed
830 | Retaining Wall on H-T at Ch: 9.450Kmp | 5.55 | Lunglei Road Division-II |  |  |  |  | 100% | 2.77 | 100% | 2.77 | Phy.Completed
831 | Retaining Wall on H-T at Ch: 43.300 Kmp | 2 | Lunglei Road Division-II |  |  |  |  | 100% | 1 | 100% | 1 | Phy.Completed
832 | Construction of Link Road Silaitlak (Balu lakna) Road at Rotlang 'E' | 4.83 | Lunglei Road Division-II |  |  |  |  | 100% | 2.41 | 100% | 2.41 | Phy.Completed
833 | Construction of PCC Pavement at High School Road at Rotlang 'E' | 5.8 | Lunglei Road Division-II |  |  |  |  | 100% | 2.9 | 100% | 2.9 | Phy.Completed
834 | Construction of PCC Pavement near F.Malsawmthanga House at Rotlang 'E' | 1.93 | Lunglei Road Division-II |  |  |  |  | 100% | 0.96 | 100% | 0.96 | Phy.Completed
835 | Construction of Retaining Wall at Middle School Rotlang 'E' | 1.93 | Lunglei Road Division-II |  |  |  |  | 100% | 0.96 | 100% | 0.96 | Phy.Completed
Construction of Pavement at Tawipui S - Tawipui N
836 | (i) Const.of PCC Pavement Tawipui S approach road | 28.98 | Lunglei Road Division-II |  |  | 100% | - |  | 14.49 | 100% | 14.49 | Phy.Completed
837 | (ii) Construction of PCC Pavement Tawipui N-II HS approach road | 38.65 | Lunglei Road Division-II |  |  | 100% | - |  | 19.32 | 100% | 19.32 | Phy.Completed
838 | (iii) Const.of PCC Pavement Road from Tawipui S Bazar (NH 54) to Hermon Veng | 43.48 | Lunglei Road Division-II |  |  | 100% | - |  | 21.74 | 100% | 21.74 | Phy.Completed
839 | (iv) Const.of PCC Pavement Road from NH 54 to Thualthu Bazar to Upper Thaulthu | 43.48 | Lunglei Road Division-II |  |  | 100% | - |  | 21.74 | 100% | 21.74 | Phy.Completed
840 | (v) Const.of Thangpui and Thangte Village Road from Vaisam PMGSY Road (at Thangpui Khawhnuai Chainage) | 38.64 | Lunglei Road Division-II |  |  | 50% | - | 50% | 19.32 | 100% | 19.32 | Phy.Completed
841 | (vi) Cons.of Ngengpui Zau Link road from Thlisam Road | 24.15 | Lunglei Road Division-II |  |  | 50% | - |  | 12.07 | 50% | 12.07 | Work in progress
842 | (vii) Const.of Mat Zau Link road from Tawipui N-II | 48.31 | Lunglei Road Division-II |  |  | 30% | - | 70% | 24.15 | 100% | 24.15 | Phy.Completed
843 | (viii) Const.of Ruangte river zau Link road from Vaisam PMGSY Road | 19.32 | Lunglei Road Division-II |  |  | 100% | - | - | 9.66 | 100% | 9.66 | Phy.Completed
844 | Strengthening and Improvement of Kawlchaw to Serkawr Road | 310.34 | Siaha Division | 21.03.23 | 21.03.24 | [6 empty] | Work in progress. Material Collection stage
845 | Improvement and Upgradation of Siaha to Thingsen Road upto NH 54B Junction (7.00km) | 759.67 | Siaha Division | 21.03.23 | 21.03.24 | 0.67% |  | 1.67% |  | 2.34% |  | Work in progress.
846 | Construction of RCC Slab Culvert on I&PRO Office to Upper Council Vaih Road at 0.200kmp | 38.29 | Siaha Division | 06.03.23 | 30.04.23 | 100% |  |  |  | 100% |  | Phy. completed
847 | Re-construction of Slab Culvert on Chheihlu to Chakhang Road at 9.100kmp | 9.4 | Siaha Division | 21.03.23 | 21.03.24 | 100% |  |  |  | 100% |  | Work Phy. completed
848 | Construction of Retaining Wall near EE, PWD Qtrs at Ch:0.020Km | 8.74 | Siaha Division | 21.23.23 | 30.04.23 | 100% |  |  |  | 100% |  | Work Phy. completed
849 | Wifening Road at Cheural - Lungzarhtum - Vartekkai - Sangau (11.50Km) in Mizoram for the year 2022-23 under SASCI Group-1. Widening of Road from BCM Church to BRTF Road via Middle School at Cheural Town Extension (L=1.800km) | 41.66 | Siaha Division | 09.04.23 | 08.07.23 |  |  | 9.43% |  | 9.43% |  | Work in progress
850 | Wifening Road at Cheural - Lungzarhtum - Vartekkai - Sangau (11.50Km) in Mizoram for the year 2022-23 under SASCI Group-2. Widening of Road from LIKBK Pastor Qtr to Pu H.Lalhranga House at Lungzarhtum (L=1.500km) | 43.03 | Siaha Division | 09.04.23 | 08.07.23 | 24.77% |  | 10.66% |  | 35.43% |  | Work in progress.
851 | Wifening Road at Cheural - Lungzarhtum - Vartekkai - Sangau (11.50Km) in Mizoram for the year 2022-23 under SASCI Group-3 Widening of Road from NEC road Junction to Vartekkai with construction of minor bridge (L=7.000km) | 200.25 | Siaha Division | 09.04.23 | 08.04.24 | 23.42% |  | 7.81% |  | 31.23% |  | Work in progress.
852 | Wifening Road at Cheural - Lungzarhtum - Vartekkai - Sangau (11.50Km) in Mizoram for the year 2022-23 under SASCI Group-4 Widening of Road from Tourist Lodge to Vengthar Field via SDO (C) Complex at Sangau (L=0.860km) | 19.39 | Siaha Division | 09.04.23 | 08.07.23 | 31.45% |  | 6.29% |  | 37.74% |  | Work in progress.
853 | Formation Cutting of Road to Sand Quarry at Bualpui 'NG' -Archhuang-Sangau-Lungpher (15.46Km) in Mizoram for the year 2022-23 under SASCI | 59.75 | Siaha Division | 09.04.23 | 08.07.23 | 27.96% |  | 5.59% |  | 33.55% |  | Work in progress.
854 | Formation Cutting of Road to Sand Quarry at Bualpui 'NG' -Archhuang-Sangau-Lungpher (15.46Km) in Mizoram for the year 2022-23 under SASCI | 47.95 | Siaha Division | 09.04.23 | 08.07.23 | 10.36% |  | 24.17% |  | 34.53% |  | Work in progress.
855 | Formation Cutting of Road to Sand Quarry at Bualpui 'NG' -Archhuang-Sangau-Lungpher (15.46Km) in Mizoram for the year 2022-23 under SASCI | 37.59 | Siaha Division | 09.04.26 | 08.07.26 | 42.37% |  | 10.6% |  | 52.97% |  | Work in progress.
856 | Formation Cutting of Road to Sand Quarry at Bualpui 'NG' -Archhuang-Sangau-Lungpher (15.46Km) in Mizoram for the year 2022-23 under SASCI | 122.32 | Siaha Division | 09.04.23 | 08.04.23 | 22.3% |  | 22.31% |  | 44.61% |  | Work in progress.
857 | Construction & Upgradation of Bairabi-Zamuang Road (0.00-4.00Kmp) in Mizoram under SASCI | 3.3 | Kawrthah Division | 22.2.23 | 22.5.23 | 100% |  |  | 49.32 | 100% | 49.32 | Phy.Completed
858 | Construction of Mamit Ring Road (5.66) | 600 | Mamit Division | 22.2.24 | 22.5.24 | - |  | - |  | - |  | Work being started
859 | Pavement of Rawpuichhip to Buarpui Road (47.27-58.00Km) | 511 | Mamit Division | 22.2.25 | 22.5.25 | 58% |  | 35% | 255 | 93% | 255 | Work in progress
860 | Construction of Pavement, retaining wal, culverts and Balcony at Serchhip Internal Road | 269 | Serchhip Division | 27.2.23 | 27.2.24 | 100% |  |  | 134.46 | 100% | 134.46 | Phy.Completed
861 | Construction of Economic Road at Tuikum in Mizoram for the year 2022-2023 | 250 | Serchhip Division | 27.2.23 | 27.2.24 | 100% |  |  | 125 | 100% | 125 | Phy.Completed
862 | Improvement of Existing Road Artahkawn-Biate-Tuipui road within Srchhip District (Sh: Strengthening of Chekawn to Artahkawn Road 0.00-80.00Km) pothole filling and path repair of Biate-Tuipui Road 0.00-18.00Kmp) | 739 | Serchhip Division | 27.2.23 | 27.2.24 | 83.33% |  | 6.67% | 369.5% | 90% | 369.49 | Work in progress
863 | Construction of DS.Chawngtui-N.Vanlaiphai Road (0.00-14.800Kmp) Phase-II (Parmanent Works) | 295 | Serchhip Division | 15.2.23 | 27.10.24 | 30% |  |  |  | 30% |  | Work in progress
864 | Construction of Strengthening of double lane BUGS Bridge Over R.Tuichang at 6.00Kmp on Keitum-Artahkawn Road (40R-70R) | 343 | Serchhip Division | 15.2.23 | 31.3.23 | 100% |  |  |  | 100% |  | Completed
Improvement of Thlengang to river Chhimtuipui Road :
865 | Construction of RCC Dock along with approach Slab | 23.31 | Lawngtlai Division | 11.05.23 | 10.4.24 |  |  | 50% |  | 50% |  | Work in progress
866 | Widening of Lawngtlai to Sahriluichhuah (Kalodyne River) Balu Road | 94.8 | Lawngtlai Division | 11.05.23 | 10.4.24 |  |  | 80% |  | 80% |  | Work in progress
867 | Improvement of Bethel veng to Chengkawllui road at College veng, Lawngtlai | 90.84 | Lawngtlai Division | 11.05.23 | 10.4.24 | [6 empty] | Not yet started
Improvement of Thlengang to river Chhimtuipui Road :
868 | Formation cutting of Vathuampui to Mautlang Road | 70.47 | Lawngtlai Division | 11.05.23 | 10.4.24 |  |  | 100% |  | 100% |  | Phy.Completed
869 | Widening of Bungtlang 'S' to Saikhawthlir Road | 56.15 | Lawngtlai Division | 11.05.23 | 10.4.24 |  |  | 100% |  | 100% |  | Phy.Completed
870 | Widening of Hmawngbu to Kakichhuah Road | 61.99 | Lawngtlai Division | 11.05.23 | 10.4.24 |  |  | 100% |  | 100% |  | Phy.Completed
IMPROVEMENT OF DILTLANG TO CHAWNGTELUI ROAD
871 | Construction of Retaining Wall at Certain Location | 25.07 | Lawngtlai Division | 11.05.23 | 10.4.24 |  |  | 90% |  | 90% |  | Work in progress
872 | Resurfacing of NH-54 to DTO Office (including courtyard) at Chanmari, Lawngtlai | 6.99 | Lawngtlai Division | 11.05.23 | 10.4.24 | [6 empty] | Not yet started
873 | Construction of Minor Bridge between Khawmawi Bazar Veng to Khawmawi Vengthar | 34.48 | Lawngtlai Division | 11.05.23 | 10.4.24 |  |  | 100% |  | 100% |  | Phy.Completed
874 | Black topping of internal road at Lawngpuighat | 81.65 | Lawngtlai Division | 11.05.23 | 10.4.24 | [6 empty] | Not yet started
875 | Construction of Playground approach road at Thingfal Mamte Veng | 19.49 | Lawngtlai Division | 11.05.23 | 10.4.24 |  |  | 100% |  | 100% |  | Phy.Completed
876 | Consultancy fee for Roads | 66.55 | Lawngtlai Division | 11.05.23 | 10.4.24 |  |  | 15% |  | 15% |  | Work in progress
877 | Consultancy Fee for Bridges | 106.39 | Lawngtlai Division | 11.05.23 | 10.4.24 |  |  | 70% |  | 70% |  | Work in progress