## NLCPR
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : NLCPR | [9 empty] | Month : June 2023
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
1 | Construction of Community Hall at Various place in Mizoram | 206.49 | Project Division-III | 22.2.12 | 30.11.19 | 100% | 186.01 | - | - | 100% | 186.01 | Completed and balance fund of Rs.20.48 (rs.16.35 lakhs NLCPR + Rs.4.13 lakhs SMS) a waited for clearing liabilities

## NEDP
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : NEDP | [9 empty] | Month: June 2023
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 4 | 8 | 9 | 10 | 11 | 12 | 13
1 | Construction of Market Shed at Rahsi Veng Lunglei | 182.22 | Lunglei Building Project Division | 16.12.19 | 04.06.21 | 100% | 130 | - | - | 100% | 130 | Civil & I/E Works completed, Final Bill is pending and fund released being awaited
2 | Construction of Officers & Staff Quarter Type-IV, 2 Units and Type-III 4 Units for Taxation Department Lunglei | 330 | Lunglei Building Project Division | 3.7.20 | 07.08.23 | 82% | 161.35 | 2% |  | 82% | 161.35 | Work in progress
3 | Construction of DC Bangalow Type-VI at Saiha | 110.9 | Lunglei Building Division | 26.11.08 | 23.04.24 | 79.6% | 92.01 | 0.1% | - | 79.7% | 92.01 | Work in progress
4 | Construction of DC Office Building at Saiha | 610.11 | Lunglei Building Division | 31.10.18 | 28.11.23 | 83% | 414.49 | 2% |  | 85% | 414.49 | Work in progress
5 | Improvement of Buarpui - Bunghmun - via Thenhlum Road (65.000-79.00) Kmp during 2016-2017 | 1000 | Lunglei Road Division-I | 17.5.17 | 31.3.23 | 74% | 870.29 | - | - | 74% | 870.29 | Contract work is terminated and joint inspection with contractors will be done on balance work
6 | Resurfacing of MRB Junction to Mini Sport Complex | 6.76 | Lunglei Road Division-I |  |  | 100% | 6.76 |  |  | 100% | 6.76 | Completed
7 | Resurfacing of MRB Junction to Falkawn Bunghmun | 13.53 | Lunglei Road Division-I |  |  | 100% | 13.53 |  |  | 100% | 13.53 | Completed
8 | Retaining Wall of PWD Complex Bunghmun | 8.45 | Lunglei Road Division-I |  |  | 100% | 8.45 |  |  | 100% | 8.45 | Completed
9 | Strengthening of Pavement from Kikawn to AOC at Selected stretches | 50.68 | Lunglei Road Division-I |  |  | 100% | 51.99 |  |  | 100% | 51.99 | Completed
10 | Serkawn Hospital to DIET, Melte (Christian Hospital Serkawn to DIET, Lunglei (0.00 - 1.590Kmp) | 28.18 | Lunglei Road Division-I |  |  | 100% | 17.6 |  |  | 100% | 17.6 | Completed
11 | Patch Repair & Resurfacinf of YPC Hall Serkawn to Chawngbawla Point Zotlang (0.00-1.590Kmp) | 31.65 | Lunglei Road Division-I |  |  | 100% | 19.93 |  |  | 100% | 19.93 | Completed
12 | Patch Repair & Resurfacinf of Zohnuai approach road (0.00-0.50Kmp) | 12.55 | Lunglei Road Division-I |  |  | 100% | 8.05 |  |  | 100% | 8.05 | Completed
13 | Centenary Road Serkawn (Serkawn Christian Hospital, Serkawn Pastor Quarters (0.00-0.540) | 10.93 | Lunglei Road Division-I |  |  |  | 4.58 | 50% |  | 50% | 4.58 | Not yet completed
14 | AOC to Kikawn | 49.31 | Lunglei Road Division-I |  |  | 100% | 43.25 |  |  | 100% | 43.25 | Completed
15 | Construction of Retaining Wall on ATL Road to Kawmzawl Helipad Road Pukpui (At Ch=400.00m) | 3.51 | Lunglei Road Division-I |  |  | 100% | 0.6 |  |  | 100% | 0.6 | Completed
16 | Improvement of Drainage System from Kikawn to AOC (Culverts & Cross drainage) | 34.53 | Lunglei Road Division-I |  |  | 100% | 30.92 |  |  | 100% | 30.92 | Completed
17 | Approach Road to Kendriya School at Ramthar Veng (Nursing School Approach Road Kendriya School Ramthar Veng) | 38.99 | Lunglei Road Division-I | [6 empty] | 17.51% |  | Only widening completed
18 | JB Press to Sobji Bazar (0.000-0.307 Kmp) | 6.17 | Lunglei Road Division-I |  |  | 100% | 6.17 |  |  | 100% | 6.17 | Completed
19 | AOC to District Road (AOC Ramthar District Road) | 6.78 | Lunglei Road Division-I |  |  | 100% |  |  |  | 100% |  | Completed
20 | MAO Complex Internal Road (Caommandant Bungalow to Thangte Peng) | 22.37 | Lunglei Road Division-I |  |  | 100% |  |  |  | 100% |  | Only Physical Completed
21 | R.Zosanga Road at Lunglawn (NH-54A Z.Rosanga's House) | 3.37 | Lunglei Road Division-I |  |  | 100% | 3.37 |  |  | 100% | 3.37 | Completed
22 | NH 54A to Lunglawn Hmunhlui Tlang via Pu H.Lalzarliana's House (NG 54A Main Road PC Thlanmual's House) | 2.4 | Lunglei Road Division-I |  |  | 100% | 2.4 |  |  | 100% | 2.4 | Completed
23 | Parallel Road from Pu Lalpara's House to Prebyterian Church (Part 1) | 15.22 | Lunglei Road Division-I |  |  | 100% | 15.21 |  |  | 100% | 15.21 | Completed
24 | Approach Road to LDSC Ground No II from District Road (District Road LDSC Ground No II) | 5.02 | Lunglei Road Division-I |  |  |  | 5.02 |  |  |  | 5.02 | Completed
25 | Salem Internal Road (NH 54A to District Road) | 11.62 | Lunglei Road Division-I |  |  | 100% | 11.62 |  |  | 100% | 11.62 | Completed
26 | Falkawn to District Road (Falkawn District Road) | 10.56 | Lunglei Road Division-I |  |  |  | 10.55 | 100% |  | 100% | 10.55 | Only Pothole repair Completed
27 | Ramthar Veng Baptist Church Ring Road (AOC Ramthar Mazara's Spare Parts) | 4.97 | Lunglei Road Division-I |  |  | 100% | 4.97 |  |  | 100% | 4.97 | Completed
28 | Resurfacing of Approach Road DCs Office from MST Bus Station (MST Bus Station DC Office) | 14.18 | Lunglei Road Division-I |  |  | 100% | 1.93 |  |  | 100% | 1.93 | Completed
29 | Reusrfacing of Mizoram Rural Bank to DC Office via LAD Office (Mizoram Rural Bank DC Office) | 15.52 | Lunglei Road Division-I |  |  | 100% | 4.88 |  |  | 100% | 4.88 | Completed
30 | Resurfacing of District Road | 126.66 | Lunglei Road Division-I |  |  | 100% | 105.64 |  |  | 100% | 105.65 | Completed
31 | Resurfacing of LP Thangzika's Shop to Forest Check Gate) | 60.64 | Lunglei Road Division-I | [8 empty] | Only Pothole repair completed
32 | Resuirfacing of Parallel Road from Pu Lalpara's House to BCM Kikawn Biak In (Part 2) | 111.56 | Lunglei Road Division-I |  |  | 100% | 88.95 |  |  | 100% | 88.95 | Completed
33 | Resurfacing of Rahsi Veng to Tlabung Road via Sazaikawn (Forest Check Gate to Tlabung Kawng) | 14.63 | Lunglei Road Division-I |  |  | 100% |  |  |  | 100% |  | Completed
34 | Resurfacing of Rahsi Veng to Tlabung Road via Sazaikawn (Forest Check Gate to Tlabung Kawng) | 25.16 | Lunglei Road Division-I | [8 empty] | Only Pothole repair Completed
35 | SE PWD Residence Approach Road (DC's Office SE Office) | 2.4 | Lunglei Road Division-I |  |  | 100% | 2.4 |  |  | 100% | 2.4 | Completed
36 | DC Residence from SE PWD Qtr Approach road (SE PWD Qtr DC Residence) | 0.72 | Lunglei Road Division-I |  |  | 100% | 0.72 |  |  | 100% | 0.72 | Completed
37 | Construction of Breast Wall at 0.120Kmp on approach road to Kendryia School Lunglei | 30.5 | Lunglei Road Division-I |  |  | 100% | 30.5 |  |  | 100% | 30.5 | Completed
38 | Construction of Retaining Wall at 0.600 Kmp on Tlabung Peng to Colony PWD Road (Boundary of Venghlun and Rahsi veng) | 8.29 | Lunglei Road Division-I |  |  | 100% | 8.29 |  |  | 100% | 8.29 | Completed
39 | Construction of Retaining Wall at 1.100Kmp on 2nd Parallel Road, Bazar Veng, Lunglei | 6.86 | Lunglei Road Division-I |  |  | 100% | 6.94 |  |  | 100% | 6.94 | Completed
40 | Construction of Retaining Wall at 1.48 Kmp on Sangchem Road | 17.66 | Lunglei Road Division-I |  |  | 100% | 17.66 |  |  | 100% | 17.66 | Completed
41 | Construction of Retaining Wall at Ch:18.450Kmp on Lunglei to Buarpui Road | 29.64 | Lunglei Road Division-I |  |  | 100% | 29.64 |  |  | 100% | 29.64 | Completed
42 | Construction of Retaining Wall at Ch: 18.450Kmp on Lunglei to Buarpui Road | 7.97 | Lunglei Road Division-I |  |  | 100% | 7.97 |  |  | 100% | 7.97 | Completed
43 | Construction of Retaining Wall at 18.500Kmp on Lunglei to Buarpui Road | 4.9 | Lunglei Road Division-I |  |  | 100% |  |  |  | 100% | 4.9 | Completed
44 | Construction of Multi Level Parking cum Basketball Court beside the main Building | 541.8 | Project Division-I | 5.12.19 | 31.1.23 | 99% | 532.48 | 1% | - | 100% | 532.48
45 | Const.of Bridge on Chhinga Vengthar to Tuithiang Road | 586.36 | Aizawl Road South Division | 19.04.21 | 31.10.22 | 100% | 200 | - |  | 100% | 200 | Phy.Work completed

## STATE
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : STATE | [9 empty] | Month : June 2023
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
1 | Construction of Laboratory Building at Civil Hospital Lunglei Ground Floor | 192.98 | Lunglei Building Project Division | 28.10.21 | 28.04.24 | 100% | 192.98 | - |  | 100% | 192.98 | Completed
2 | Construction of Laboratory Building at Civil Hospital Lunglei (1st & 2nd Floor) Supplementary Works | 396 | Lunglei Building Project Division | 28.10.21 | 28.4.24 | 48% | 162.6 | 10% | 0.39 | 48% | 162.99 | Work in progress

## SPA
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : SPA | [9 empty] | Month: June 2023
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
1 | Construction of District Transport Office at Lawngtlai | 228 | Lunglei Building Project Division | 27.9.16 | 31.01.20 | 100% | 186.8 | - | 2.89 | 100% | 189.69 | Completed and handed over to the client dept. Liabilities yet to be cleared as amount shown in column 11
2 | Construction of DC of State Tax Office & Staff Quarters at Saiha | 408.37 | Lunglei Building Project Division | 25.10.19 | 20.01.23 | 100% | 408.28 | - |  | 100% | 408.28 | Civil work completed and I/E not yet started.

## SPP
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : SPP | [9 empty] | Month : June 2023
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
1 | Construction of Office Building for IF & SL at Tuikhuahtlang | 401.18 | Project Division-III | 13.7.20 | 11.06.23 | 93.5% | 264.62 | 0.5% |  | 94% | 264.62 | Work in progress
2 | Construction of Circuit House at Serchhip | 358.18 | Project Division-III |  |  | - | - | - | - | - | - | Estimate amounting to Rs.3.58 Cr submitted as per new drawing. Waiting for approval for tender.
3 | Construction of Truckable Road between Tlangpui and Lungva | 480 | Khawzawl Division | 5.7.18 | 7.10.20 | 63% | 327.23 | - | - | 63% | 327.23

## DONER
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : One Time Special Assistance under Ministry of DONER | [9 empty] | Month : June 2023
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
1 | Re-Construction of safe House at Tlabung | 114.9 | Lunglei Building Project Division | 18.11.21 | 28.02.23 | 100% | 70.38 | - |  | 100% | 70.38 | Civil Works completed. IE not yet done. Allocation of Rs.44.52 lalkhs being awaited
2 | Re-Construction of safe shelter at Sairang | 96.58 | Project Division-II | 13.11.21 | 13.11.22 | 100% | 79.7 | - | - | 100% | 79.7 | Work physically completed

## NERSDS
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : NERSDS | [9 empty] | Month : June 2023
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
1 | Upgradation of Saiha-Lungbun-Tluangram-Haka Road in the State of Mizoram | 4307.95 | Saiha Division | 29.10.21 |  | 40.95% | 1055 | 7.26% |  | 48.21% | 1055 | Work in progress.
2 | Upgradation of Hnahlan-Hmunhlui-Tuimang-Singngei Road (Length = 12.000 Kms) | 3845.19 | Champhai Division | 29.11.21 | 28.4.23 | 48.2% | 1572.39 | 1.36% |  | 49.56% | 1572.39 | In progress
3 | Upgradation of Zote-Fartlang-Buanli-Tuipui-Tawnzang Road in the state of Mizoram under NERSDS (Length = 8.00 Kms) | 2547.32 | Champhai Division | 12.12.21 | 11.5.23 | 60.87% | 1169.98 | 3.18% |  | 64.05% | 1169.98 | In progress

## ISC Scheme
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : ISC Scheme | [9 empty] | Month : June 2023
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
1 | Improvement of Tuipuibari - W.Kawnpui Road and ISC (0.00-9.00 Kmp) | 4870 | Mamit Division | 20.3.20 | 20.3.22 | 68% | 3246.44 | 2% |  | 70% | 3246.44 | Work in progress

## MPR 3054 (R&B)
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : 3054 (R&B) | [9 empty] | Month : June 2023
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
1 | Improvement of Approach Road to MPRO Quarter at Luangmual | 180 | Aizawl Road North Division | 1.5.21 | 2.11.21 | 100% | 50 | - | - | 100% | 50 | Work stopped due to non availability of fund
2 | Construction of Pavement for the approach road to Gan Sabra at Luangmual | 63.82 | Aizawl Road North Division | - | - | 59% | 30 | - | - | 59% | 30 | Work stopped due to non availability of fund
3 | Ordinary Repair (DPP) for short term maintenance from Km 0.00 to Km 42.80 and from Km 60.30 to km 130.00 on NH-150 in the state of Mizoram | 418 | NHD-II | - | - | 100% | 327.67 | - | - | 100% | 327.67 | Phy.Completed
4 | Land acquisition for 2-laning on NH-150 from Km 34/500 to 62/800 in the State of Mizoram | 786 | NHD-II | - | - | 77% | 600.92 | - | - | 77% | 600.92
5 | Special Repair to Bailey Bridge at Km 135/80 (River Luaklui) & 136850 (River Luakzal) of NH-150 in the State of Mizoram (job No. TA/150/MZ/20165-16/84) | 27.3 | NHD-II | - | - | 100% | 14.2 | - | - | 100% | 14.2 | Completed
6 | Construction of 2 laning with paved shoulder flexible pavement from Km 42.80 to Km 60.30 of NH-150 road during 2016-17 within Mizoram State under NH(O) Scheme. (Job No. & Dtae of Sac Original/Revised : 150/MZ/2016-17/107) | 20594.82 | NHD-II | - | - | 100% | 13681.44 | - | - | 100% | 13681.44 | Phy.Completed
7 | Reconstruction of single pavement from Km 130.00 to Km 140.00 on NH-150 in the State of Mizoram on EPC Mode (Job No.150/MZ/2019-20.119) | 3440.95 | NHD-II | - | - | 100% | 2441.16 | - | - | 100% | 2441.16 | Physically completed
8 | Consultancy Services for Project Management including prparation of Feasibility Study/Detailed {roject report fro laning with Paved Shoulders of stretches from Km 0/00 to Km 42/80 and from Km 60/00 to Km 140/00 on NH-150 NH (O) Package No. DPR/MZ/NER/2015/13 | 166.04 | NHD-II | - | - | 10% | 16.6 | - | - | 10% | 16.6

## CRF
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : CRF | [9 empty] | Month : June 2023
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
1 | Construction of Two Lane from Sihhmui-Ramrikawn Road (Stage-I) | 8000 | Aizawl Road North Division | 1.10.18 | 03.05.22 | 77% | 2994 | - | - | 77% | 2994 | In progress
2 | Construction of BUG Bridge over Tlawng on Aizawl-Reiek-W.Lungdar Road at 14.800 Kmp | 757.56 | Aizawl Road South Division | 1.10.18 | 31.3.22 | 74.4% | 400.56 | 7.2% | 88 | 81.6% | 488.56 | Work in progress
3 | Construction of Muallungthu-Lungphun Road | 5996 | Hmuifang Division | 23.11.17 | 5.8.21 | 33.39% | 1940.67 | - | - | 33.39% | 1940.67
4 | Widening to single lane with geometric imprivement & Upgradation of Chhiahtlang-Lamchhip Road | 6668.18 | Hmuifang Division | 23.6.17 | Feb.2022 | 100% | 4426.6 | - | - | 100% | 4426.6 | Physically completed and current Liabilities against the contractor is Rs.1857.15 lakh
5 | Construction of double lane BUSC Girder Bridge over R.Tuichang on Keitum-Artahkawn Road | 754.75 | Serchhip Division | 1.12.16 | 31.3.22 | 100% | 564.95 |  | - | 100% | 564.95 | Completed
6 | Construction of Chakkhei to Siasi Road (Permanent Work) (0.00-20.00 Kmp) | 1216.88 | Saiha Division | 8.7.19 | 07.05.23 | 97.03% | 450.43 |  | - | 97.03% | 450.43 | Work in progress
7 | Construction of Chakkhei to Siasi Road (FC&Pavement Work) (0.00-20.00 Kmp) | 3505.54 | Saiha Division | 8.7.19 | 16.03.23 | 98.55% | 2277.26 |  | - | 98.55% | 2277.26 | Work in progress

## NESIDS
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : NESIDS | [9 empty] | Month : June 2023
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
1 | Construction of 2 Residential Hostel at ZMC (Boys) | 1000 | Project Division-II | 14.10.21 | 29.10.23 | 85% | 539.52 | 3% | 364.53 | 88% | 904.05 | Work in progress
2 | Construction of 2 Residential Hotel at ZMC (Girls) | 1000 | Project Division-II | 14.10.21 | 27.10.23 | 68% | 260.48 | 2% | 297.36 | 70% | 557.84 | Work in progress
3 | Construction of 100 Bedded Distict Hospital at Kolasib | 1859.87 | Project Division-II | 23.09.22 | 23.09.24 | 14% | 10 | 3% | 233.9 | 17% | 243.9 | Work in progress
4 | Construction of State Resource Centre for HIV/AIDS at Aizawl | 360.51 | Project Division-II | 22.09.22 | 22.09.24 | 13% | - | 2% | - | 15% | - | Work in progress
5 | Improvement /Upgradation of Operational/Non-operational facilities of Lengpui Aiport (elevated Road with connected components of Terminal Building) | 1959 | Project Division-III | 30.9.21 | 30.3.23 | 80% | 1167.61 | 5% | 149.7 | 85% | 1317.31 | Pandemic crisis delayed work progress. Now work is in progress
6 | Improvement & Upgradation of Lawngtlai-Tuipui ferry Road under NESIDS | 2897.8 | Lawngtlai Division | 08.08.19 | 31.03.23 | 96.48% | 2666.69 | 0.37% |  | 96.85% | 2666.69 | Work in progress

## SCA
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : S.C.A | [9 empty] | Month : June 2023
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummutive Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
1 | Improvement of MPSC Office Building at MINECO | 394 | Project Division-I | 29.10.22 | 29.10.24 | 45% | 115.57 | 3% |  | 48% | 115.57
2 | Construction of DIG (NR) Office Building at PHQ Complex, Aizawl | 320 | Project Division-I | 21.7.22 | 21.1.24 | 35% | 2.48 | 10% | - | 45% | 2.48
3 | Strenthening of Infrastructure in 3 newly created Districts (Const.of DC Office Khawzawl) | 1000 | Project Division-III | 25.02.21 | 21.04.24 | 95% | 722.21 | 1% | 1.2 | 96% | 723.41 | Pandemic crisis delayed work progress. Now Work is in progress
4 | Strenthening of Infrastructure in 3 newly created Districts (Const.of DC Office Saitual) | 1000 | Project Division-III | 25.02.21 | 20.04.24 | 84% | 650.75 | 2% | 2.61 | 86% | 653.36 | Pandemic crisis delayed work progress. Now Work is in progress
5 | Construction of District Research Officers Office at Khawzawl (Sh: C/o DRO Office Ground Floor & C/O Quarters 1st Floor) | 43 | Project Division-III | 18.08.22 | 12.05.23 | 95% | 14.61 | 5% | - | 100% | 14.61 | Work in progress
6 | Construction of District Research Officers Quarters and Staff Cum Chowkider Quarters at Keifang, Saitual District | 70 | Project Division-III | 22.03.22 | 09.07.23 | 20.1% | - | 2% | - | 22.1% | - | Work in progress
7 | Improvement & Upgradation of Operational/Non Operational facilities of Lengpui (Sh: Renovation of Terminal building) | 2124 | Project Division-III | 16.03.21 | 21.10.23 | 91.3% | 1254.05 | 1% | - | 92.3% | 1254.05 | Pandemic crisis delayed work progress. Now Work is in progress
8 | Construction of Solid Waste Management Centre at Hualngohmun, Mizoram (Phase-I) | 1664 | Project Division-III | 07.04.23 | 07.04.25 | - | - | - | 83.2 | - | 83.2 | 1. Environmental Impact Assessment (EIA) is being done by consultant. 2. Work in progress 3. Work transferred to Project Division IV, PWD, on Dt.21.06.23
9 | Strengthening of Aizawl-Thenzawl-Lunglei Road from (17.000-30.000 & 51.000-63.00 Kmp) | 1332 | Hmuifang Division | 12.10.20 | 31.03.22 | 100% | 1289.94 | - | - | 100% | 1289.94 | Completed
10 | Rehabilitation of Landslide Area within Hualngohmun Village at Chainage 9.400 | 162 | Hmuifang Division | 28.03.22 | 28.03.23 | 86% | 90.98 |  | - | 86% | 90.98 | Fund received amounting to Rs.71,02,000 is kept under D-III

## NLUP
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : NLUP | [9 empty] | Month : June 2023
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
1 | Re-Construction of District Transport Office at Champhai | 262 | Project Division-III | 11.7.22 | 11.01.24 | 88% | 123.19 | 2% | 0.23 | 90% | 123.42 | Work in good progress

## SARDP
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : SARDP-NE | [9 empty] | Month : June 2023
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
1 | Widening to two laning/Re-alignment and geometric improvement from km.11+000 to 114+618 of NH-44 'A' in the state of Mizoram | 1,10,988.00 | NHD-I |  |  | 96.03% | 97146.5 | 0.01% | 4999.5 | 96.04% | 102146
2 | Construction of Steel Arch (Semi Through) Bridge with concrete Deck 90m Arch Span over River Tlawng at Km 5.200 on NH-44A In the State of Mizoram of EPC Mode | 4244 | NHD-I |  |  | 66.4% | 1317 |  | 106 | 66.4% | 1423 | Percentage was revised as per the direction given by RO (MoRTH)
3 | Construction of a new 2-lane Highway from km 0/00kmp to 38/00 in Mizoram to support Kaladan Multi Modal Transit Transport project in Phase-'A of SARDP-NE package-I | 43465 | Multi Modal Project Division |  |  | 98.24% | 42058 | 1.76% |  | 100% | 42058 | 1. Financial progress is upto RA 145 2. Work completed on 22.6.2023
4 | Construction of a new 2-lane Highway from km 38.00 to km 71.00 in Mizoram to support Kaladan Multi Modal Transit Transport project in Phase-'A of SARDP-NE package-II | 32224 | Multi Modal Project Division |  |  | 99.56% | 30977 | 0.44% | - | 100% | 30977 | 1. Financial progress is based on bill submitted by the Contractor after verifying at the spot by the Department. 2. Work completed on 30.04.22
5 | Construction of a new 2-lane Highway from km 71.00 to km 99.83 in Mizoram to support Kaladan Multi Modal Transit Transport project in Phase-'A of SARDP-NE package-III | 37459 | Multi Modal Project Division |  |  | 98% | 36432 | 2% | - | 100% | 36432 | 1. Financial progress is based on bill submitted by the Contractor after verifying at the spot by the Department. 2. Work completed on 26.06.23

## Major
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : Major & Minor Works and Deposit woks 8443-108, D-III | [9 empty] | Month : June 2023
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
1 | I/E to Additional Court Room with Chamber at Kolasib | 4.26 | Electrical Division Aizawl |  |  | 100% | 4.26 | - | - | 100% | 4.26 | I/E Completed, S/C being process
2 | I/E to Arrival & Departure Passenger Lobby at Lengpui Airport | 25.27 | Electrical Division Aizawl |  |  | 90% | 25.27 | - | - | 90% | 25.27 | Panel Board not yet installed
3 | SITC 13 Passenger Lift-2 nos, 2-opening, 900mm centre opening Stainless Steel cable with Automatic Rescue Device (ARD) for Hydraulic Lift with Minor Civil Works at Lengpui Airport Mizoram | 77.91 | Electrical Division Aizawl |  |  | 25% | - | - | - | 25% | - | On going works
4 | I/E to Chowkider Qtrs at PWD Complex, Bilkhawthlir | 3.6 | Electrical Division Aizawl |  |  | 100% | 3.6 | - | - | 100% | 3.6 | Completed
5 | I/E to Rest House at PWD Complex, Bilkhawthlir | 30.91 | Electrical Division Aizawl |  |  | 100% | 25.37 | - | - | 100% | 25.37 | Phy. Completed
6 | I/E to Re-construction of Safe House at Sairang | 5.2 | Electrical Division Aizawl |  |  | 100% | 5.2 | - | - | 100% | 5.2 | Completed
7 | I/E to Paying Cabin for ZMC at Falkawn | 99.32 | Electrical Division Aizawl |  |  | 100% | 99.32 | - | - | 100% | 99.32 | Completed
8 | SITC with fire fighting system for paying cabin ZMC at Falkawn | 34.57 | Electrical Division Aizawl |  |  | 100% | 13.82 | - | 20.75 | 100% | 34.57 | Completed
9 | SITC of 15 passenger G+4MRL Hospital Lift with 900mm Central Opening with Automatic Resue Device (ARD) est (OTISmake) at Paying | 50 | Electrical Division Aizawl |  |  | 100% | 49.78 | - | 0.22 | 100% | 50 | Completed
10 | I/E to Fast Track Court (Judical Gr-I qtr) at Kolasib | 11.43 | Electrical Division Aizawl |  |  | 100% | 11.43 | - | - | 100% | 11.43 | Completed
11 | Street Light Parking light at Lengpui Airport | 37.32 | Electrical Division Aizawl |  |  | 50% | 37.31 | 35% | - | 85% | 37.31 | On going works
12 | Laying of XLPE Cable from Power House to Glide Path control at Lengpui Airport, Mizoram | 39.53 | Electrical Division Aizawl |  |  | 60% | - | 30% | - | 90% | - | On going works
13 | Estimate for I/E of Energy Meter for Terminal Building at Lengpui Airport | 7.99 | Electrical Division Aizawl |  |  | 40% | 7.99 | - | - | 40% | 7.99 | On going works
14 | I/E for Const.of Grade I Officers Qtr at Project veng Kolasib | 5.13 | Electrical Division Aizawl |  |  | 100% | 5.13 | - | - | 100% | 5.13 | Completed
15 | I/E & Fire fighting to Car Parking at Dist.Court MINECO | 32.48 | Electrical Division Aizawl |  |  | 60% | 16.99 | - | - | 60% | 16.99 | On going works
16 | SITC of Fire Fighting System of Dist.Court, MINECO | 125.4 | Electrical Division Aizawl |  |  | 100% | 124.83 | - | - | 100% | 124.83 | Completed
17 | Addl.Estimate for SITC of MRV/VRF Centralizes Air Conditioner Airport Fist Floor Departure Hall, Mizoram | 247.74 | Electrical Division Aizawl |  |  | 60% | 220.1 | - | - | 60% | 220.1 | On going works
18 | SITC of EPABX System for Lengpui Airport Terminal Building | 24.64 | Electrical Division Aizawl |  |  | 50% | 9.86 | - | - | 50% | 9.86 | On going works
19 | SITC of PA System at Lengpui Airport Terminal Building | 36.36 | Electrical Division Aizawl |  |  | 50% | 14.54 | - | - | 50% | 14.54 | On going works
20 | Supply & Installation of Integrated Fire Hydrant System (Wise Riser) & SiTC of Alarm System for Lengpui Airport Terminal building | 119.96 | Electrical Division Aizawl |  |  | 50% | 47.99 | - | - | 50% | 47.99 | On going works
21 | SITC of AVTRON IP Surveillance System for Lengpui Airport Terminal Building | 94.76 | Electrical Division Aizawl |  |  | 50% | 37.9 | - | - | 50% | 37.9 | On going works
22 | SITC of LANE SETUP at Lengpui Airport Terminal Building | 20.05 | Electrical Division Aizawl |  |  | 50% | 8.02 | - | - | 50% | 8.02 | On going works
23 | Estimate for XLPE Cable for Lengpui Airport | 27.23 | Electrical Division Aizawl |  |  | 50% | 27.23 | - | - | 50% | 27.23 | On going works
24 | Additional Estimate fo SITC of Air Conditioner Departer Pssenger Lobby at Lengpui Airport | 24.67 | Electrical Division Aizawl |  |  | 100% | 24.67 | - | - | 100% | 24.67 | Completed
25 | I/E works for Const. of MBSE Office | 57.37 | Electrical Division Aizawl |  |  | 25% | 48.85 | - | 5.28 | 25% | 54.13 | On going works
26 | I/E for DC Office at Saitual | 70 | Electrical Division Aizawl |  |  | 100% | 70 | - | - | 100% | 70 | I/E completed, S/C left due to non installation of required transformer
27 | I/E for Const. of IF &SL Office building at Tuikhuahtlang | 23.33 | Electrical Division Aizawl |  |  | 70% | 20.01 | - | 3.32 | 70% | 23.33 | On going works
28 | I/E to High Court Parking at MINECO | 109.5 | Electrical Division Aizawl |  |  | 40% | 65.73 | - | - | 40% | 65.73 | On going works
29 | I/E to Staff qtrr Block A for DIET, Chaltlang | 40.11 | Electrical Division Aizawl |  |  | 85% | 39 | 5% | - | 90% | 39 | Works in progress
30 | I/E to PHC at Bungzung | 18.18 | Electrical Division Aizawl |  |  | 90% | 18.18 | 10% | - | 100% | 18.18 | I/E Completed, S/C left due to non installation of required transformer
31 | I/E to PHC at Ngentiang | 15.72 | Electrical Division Aizawl |  |  | 100% | 15.55 | - | 0.17 | 100% | 15.72 | Completed
32 | Const.of DIG(NR) Office at Aizawl under SCA during 2022-23 (Sh:I/E) | 43.84 | Electrical Division Aizawl |  |  | 40% | 17.29 | - | - | 40% | 17.29 | On going works
33 | I/E to Mizoram Public Service Commission (MPSC) Building, Aizawl | 24.66 | Electrical Division Aizawl |  |  | 45% | 13.9 | 10% | - | 55% | 13.9 | On going works
34 | Construction of DC Office at Khawzawl (Sh: Lift & I/E) | 90 | Electrical Division Aizawl |  |  |  | 33.44 |  |  |  | 33.44 | On going works
35 | I/W Multi Level Parking Cum Basketball Court | 11.4 | Electrical Division Aizawl |  |  | 60% | 7.36 | 30% | 4.04 | 90% | 11.4 | On going works
36 | Reconstruction of PHC Building at Marpara, Mamit District | 16.18 | Electrical Division Aizawl |  |  | 60% |  |  | 16.18 | 60% | 16.18 | On going works
37 | Reconstruction of PHC Building at Bukpui | 14.59 | Electrical Division Aizawl |  |  | 60% |  | 40% | 14.59 | 100% | 14.59 | Completed
38 | Type-III Qtr at Vairengte | 1.6 | Electrical Division Aizawl |  |  | 60% |  | 40% | 1.6 | 100% | 1.6 | Completed
39 | JCO/NCO & Jawan Mess at Vairengte | 1.1 | Electrical Division Aizawl |  |  | 90% |  | 10% | 1.1 | 100% | 1.1 | Completed
40 | JCO Qtr Barrack cum Hote Company Hqrs at Vairengte | 3.6 | Electrical Division Aizawl |  |  | 90% |  | 10% | 3.6 | 100% | 3.6 | Completed
41 | Barrack I at Vairengte | 2.2 | Electrical Division Aizawl |  |  | 90% |  | 10% | 2.2 | 90% | 2.2 | Completed
42 | Barrack II at Vairengte | 2.2 | Electrical Division Aizawl |  |  | 90% |  | 10% | 2.2 | 100% | 2.2 | Completed
43 | Barrack III at Vairengte | 2.2 | Electrical Division Aizawl |  |  | 90% |  | 10% | 2.2 | 100% | 2.2 | Completed
44 | Reconstruction of DTO Office at Champhai | 17 | Electrical Division Aizawl |  |  |  |  | 40% | 17 | 40% | 17 | On going works

## SASCE
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : SASCE | [9 empty] | Month : June 2023
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummutive Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
1 | Construction of RCC Minor Bridge between I.R approach road and NH-154 along Ch.Chhunga's paddy filed, Bairabi | 64.9 | Kolasib Division | 05.05.20 | 25.03.21 | 35% | 54.9 | - | - | 35% | 54.9 | As reported to the undersigned by the on.Dt.30.10.21, DC Kolasib District/Magistrate Kolasib District Kolasib instructed the Contractor in verbal to stop the work and to remove all the materials stocked at the site for construction of this bridge due to border conflict between Mizoram and Assam. Rs.10.00 lakhs kept under D-III
2 | Construction of Multi Utility Centre at Zemabawk, Aizawl, Mizoram. | 636.07 | Project Division-IV | 19.12.22 | 16.8.25 | 12.14% | 145.35 | 0.71% | - | 12.85% | 145.34 | Work in progress

## SPF
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : State Plan Fund | [9 empty] | Month : June 2023
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummutive Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
1 | 4202 Co-On Education etc. a) I/E to boys & girls Hostel for Govt.Saiha College bldg at Siaha | 2 | Electrical Division, Lunglei |  |  | 40% | - | - | - | 40% | - | Materials received, building not yet ready
2 | 8443-108-PWD Deposit-III a) I/E to DC Bungalow (Type-IV) at Siaha | 8.2 | Electrical Division, Lunglei |  |  | 40% | - |  | - | 40% | - | Materials received, building not yet ready
| b) I/E to Primary Health Centre (PHC) at Tawipui 'S' | 20 | Electrical Division, Lunglei |  |  | 10% |  | 80% |  | 90% |  | I/E Completed S/C left
| c) I/E to DRO Quarter & DRO Office at Hnahthial | 2.7 | Electrical Division, Lunglei |  |  | 10% |  |  |  | 10% |  | Estimate Submitted
| d) I/E to DC Office Building at Hnahthial | 68.43 | Electrical Division, Lunglei |  |  |  |  | 20% |  | 20% |  | Materials not yet receive
3 | 4059-Co on Public works (Plan) a) I/E to District Court Building at Siaha | 139 | Electrical Division, Lunglei |  |  | 95% | - | - | - | 95% | - | I/E Completed S/C left
4 | 4047-Co on other Fiscal Sevice
| a) I/E to deputy Commissioner of State Tax, Siaha zone (Office( at Siaha | 17 | Electrical Division, Lunglei |  |  |  |  | 80% |  | 80% |  | On going works
| b) I/E to Staff Quarter for Deputy Commissioner of State Tax, Siaha Zone (Type-I & Type-III) at Siaha | 13 | Electrical Division, Lunglei |  |  |  |  | 80% |  | 80% |  | On going works
| c) I/E to Staff Quarter for Deputy Commissioner of State Tax, Siaha Zone (Type-IV) at Siaha | 5 | Electrical Division, Lunglei |  |  |  |  | 80% |  | 80% |  | On going works