## NABARD
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding: NABARD | [9 empty] | Month : September 2023
Sl. no | Name of Work/Project | Unit | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[7 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Const.of BUSG Composite Bridges over R.Chepte on Bilkhawthlar to Saiphai Road |  | 508.45 | Kolasib Division | 24.6.19 | 31.03.22 | 42% | 128.5 |  | - | 42% | 128.5
2 | Const.of BUSG Composite Bridges over R.Sesih on Bilkhawthlar to Saiphai Road |  | 281.12 | Kolasib Division | 24.6.19 | 31.03.22 | 49% | 90.94 |  | - | 49% | 90.94
3 | Design & Construction of T-Beam Bridge Package-II at Bulung River (CH:10.20 KMP) |  | 996 | Kolasib Division | 24.12.21 | 24.06.23 | - | - | - | - | - | -
4 | Design & Construction of T-Beam Bridge Package-II at Damdiai River (CH:23.50 KMP) |  | 996 | Kolasib Division | 24.12.21 | 24.06.23 | - | - | - | - | - | - | Location of Bridge Abutment finalised in principle
5 | Design & Construction of T-Beam Bridge Package-I at Chhimluangte River (CH:0.450 KMP) |  | 969 | Kolasib Division | 18.12.21 | 18.06.23 | 12% | 28.56 | - | - | 12% | 28.56
6 | Design & Construction of T-Beam Bridge Package-I at Dumkhel River (CH:5.50 KMP) |  | 969 | Kolasib Division | 18.12.21 | 18.06.23 | 11% | - | 1% | - | 12% | -
7 | Const.of Meidum to Hortoki Road Phase -II (Km 9.100 to Km 26.000) SH: Earthworks and Permanent works from Km 9.100-Km 13.325) Package -I |  | 1087.32 | Kolasib Division | 24.12.21 | 24.06.23 | 81% | 839.99 | - |  | 81% | 839.99
8 | Const.of Meidum to Hortoki Road Phase -II (Km 13.325 to Km 17.500 SH: Earthworks and Permanent works from Km 13.325 to Km 17.500) Package -II |  | 1171 | Kolasib Division | 25.12.21 | 25.06.23 | 65% | 562.23 |  |  | 65% | 562.23
9 | Const.of Meidum to Hortoki Road Phase -II (Km 17.500 to Km 21.725 SH: Earthworks and Permanent works from Km 15.690 to Km 19.005) Package -III |  | 1422 | Kolasib Division | 18.12.21 | 18.06.23 | 76% | 1054.73 | - |  | 76% | 1054.73
10 | Const.of Meidum to Hortoki Road Phase -II (Km 21.725 to Km 26.000 SH: Earthworks and Permanent works from Km 19.005 to Km 22.360) Package -IV |  | 959 | Kolasib Division | 08.12.21 | 8.06.23 | 80% | 726.91 |  |  | 80% | 726.91
11 | Construction of Meidum to Hortoki Road Phase - II (Km 9.100 to 26.000)Package I |  | 2390.08 | Kolasib Division | 03.08.22 | 03.08.23 | 0.14% | 440.93 | - | - | 0.14% | 440.93
12 | Construction of Meidum to Hortoki Road Phase - II (Km 9.100 to 26.000) Package II |  | 2390.08 | Kolasib Division | 24.12.21 | 24.06.23 | 0.14% | 390.1 | - |  | 0.14% | 390.1
13 | Construction of link Road from NH-306 (PHE pump House) to R.Aitlang Lui Basin Crop Land : Length = 9.22 Kms |  | 465.66 | Kolasib Division | 12.08.22 | 12.08.23 | 60% | 266.358 | - |  | 60% | 266.358 | In Progress
14 | Construction of link Road from NH-306 (Vairengte) to Sabual Mual Arable Crop Land = 3.720 Kms |  | 418.89 | Kolasib Division | 13.08.22 | 13.08.23 | 55% | 136.81 | - |  | 55% | 136.81 | In Progress
15 | Construction of Agriculture Link Road from NH-306 A to Buarchep Arable Crop Land : Length = 1.720 Kms |  | 175.03 | Kolasib Division | 27.08.22 | 27.08.23 | 68% | 101.65 | - |  | 68% | 101.65 | In Progress
16 | Construction of 24 Warehouse with associated Infrastructure in 23 locations in Mizoram under NABARD (Group-II Zuangtui/Sairang |  | 1300 | Project Division-I | 4.8.23 | 14.8.25 | [7 empty] | EPC
17 | Establishment of Central Medical Warehouse at Aizawl, Mizoram |  | 1300 | Project Division-I | 4.8.23 | 14.8.25 | [7 empty] | EPC
18 | Re-Construction of Primary Health Centre at Bukpui | % | 215.43 | Project Division-II | 06.01.22 | 06.07.23 | 100% | 245.06 |  | 14.28 | 100% | 259.34 | Work phy. Completed & Handed over to Client Dept
19 | Re-Construction of Primary Health Centre at Marpara | % | 227.72 | Project Division-II | 25.03.22 | 25.09.23 | 95% | 228.25 | 2% | 0.6 | 97% | 228.85 | Work in progress EOT being process
20 | Re-Construction of double storied PHC Building at Bungzung | % | 268.99 | Project Division-III | 3.12.21 | 3.6.23 | 100% | 268.99 |  |  | 100% | 268.99 | Work completed & Handed over to H&FW Deptt. | PWD Form-8
21 | Re-Construction of double storied PHC Building at Ngentiang | % | 266.51 | Project Division-III | 3.12.21 | 13.6.23 | 100% | 266.46 |  |  | 100% | 266.46 | Work completed & Handed over to H&FW Deptt. | PWD Form-8
22 | Const.of 24 Warehouses with associated infrastructure in 23 locations in Mizoram under NABARD (Group VII: Teikhang, Rabung & Dungtlang) | % | 336.53 | Project Division-III | 17.7.23 | 31.3.25 | [6 empty] | Dismantling of existing building required | PWD Form-8
23 | Construction of 24 warehouse with associated infrastructure in 23 locations in Mizoram under NABARD (Group V: Zohmun) | % | 170.99 | Project Division-IV | 17.07.23 | 31.03.25 | [6 empty] | Mobilisation in progress | Item Rate
24 | Improvement & Strengthening of Nalkawn - Chamdur Valley |  | 3400 | Lawngtlai Division | 09.08.22 | 09.02.22 | 55.42% | 1582.47 |  | - | 55.42% | 1582.47 | EOT Granted upto 19.11.2023
25 | Const.of double lane built up Steel Girden Bridge over R.Teirei (Span -102m) at Ch.7.00 Kmp on Bairabi Zamuang Road |  | 2322.42 | Kawrthah Division | 5.8.17 | 5.8.19 | 54.6% | 1181.36 |  | 35.97 | 54.6% | 1217.33 | Work in progress | Contract after call of Restricted Tender
26 | Const.of double lane built up Steel Girden Bridge (Span-81m) over R.Langkaih on Mizoram-Tripura Border at Kanhmun |  | 2231.91 | Kawrthah Division | 6.4.18 | 6.4.20 | 41.1% | 679.03 |  | 500 | 41.1% | 1179.03 | Work in progress | Contract after call of Restricted Tender
27 | Construction of Agriculture Link Road in Nothern Mizoram (Sh: Construction of Link Road from Saikhawthlir to R.Hnanglui Arable crop land, Length = 3.50 kms) |  | 362.02 | Kawrthah Division | 20.08.22 | 20.08.23 | 41.73% | 215.41 |  | 61.22 | 41.73% | 276.63 | Work in progress | Contract after call of Restricted Tender
28 | Construction of Agriculture Link Road in Nothern Mizoram (Sh: Construction of Link Road from Chuhvel to R.Hnanglui Arable crop land, Length = 2.35 kms) |  | 284.76 | Kawrthah Division | 18.08.22 | 18.08.23 | 47.9% | 169.45 |  | 36.02 | 47.9% | 205.47 | Work in progress | Contract after call of Restricted Tender
29 | Construction of Agriculture Link Road in Nothern Mizoram (Sh: Construction of Link Road from from Thinghlun to Hriphaw through permanent crop length=9.570 kmp) |  | 385.61 | Kawrthah Division | 20.08.22 | 20.08.23 | 70.22% | 229.44 |  |  | 70.22% | 229.44 | Work in progress | Contract after call of Restricted Tender
30 | Upgradation of Meidum to Hortoki Phase-I (0.0-9.10) |  | 4445 | NHD-III | 26.5.20 | 26.11.21 1st EOT=211 days (21.11.21-20.6.22) 2nd EOT=375 days (21.6.22-30.6.23) 3rd EOT =243 days (30.6.23-28.2.24) | 59.71.% | 1731 | 18.5% | - | 78.21% | 1731 |  | Item Rate
31 | Construction of River Training Works for Protection of Tlawng River Bank at Bairabi Phase-I F.Lalthlamuana |  | 1111 | NHD-III | 17.10.22 | 17.10.23 | 70.1% | 78 |  | 120.7 | 70.1% | 198.7 |  | Item Rate
| Phase-II F.Lalliansanga |  |  |  | 17.10.22 | 17.10.23 | 38.32% | 72 |  |  | 38.32% | 72 |  | Item Rate
| Phase-III Babie Cons.& Consultancy Services |  |  |  | 17.10.22 | 17.10.23 | 100% | 148 |  | 68.65 | 100% | 216.65 |  | Item Rate
| Phase-IV Zothantluanga |  |  |  | 17.10.22 | 17.10.23 | 100% | 136 |  | 110.7 | 100% | 246.7 |  | Item Rate
32 | Construction of Road from Khamrang to Selesih Phase-II Group-1 (11/00 to 22/00Km) | Km | 14529.27 | NHD-III | 8.11.21 | 8.5.23 1st EOT=210 days (wef 09.05.23- 04.12.23 | 23.12% | 547.46 |  | - | 23.12% | 547.46 |  | Item Rate
33 | Construction of Road from Khamrang to Selesih Phase-II Group-2 (22/00 to 25/00Km) | Km |  | NHD-III | 22.11.21 | 22.11.22 1st EOT=90days (upto -20.02.23) 2nd EOT=90 dyas (wef 21.2.23-21.5.23) 3rd EOT = 90 days(22.5.23-19.8.23) | 26.78% | 166.82 | 3.21% | 52.99 | 29.99% | 219.81 |  | Item Rate
34 | Construction of Road from Khamrang to Selesih Phase-II Group-3 (25/00 to 28/00Km) | Km |  | NHD-III | 11.11.21 | 11.11.22 1st EOT=104 days (upto -24.02.23) 2nd EOT=90 dyas (wef 10.2.23-11.5.23) 3rd EOT = 90 days(wef 12.5.23-9.8.23) | 12.66% | 45.02 |  | 162.26 | 12.66% | 207.28 |  | Item Rate
35 | Construction of Road from Khamrang to Selesih Phase-II (Sh: Construction of Rigid Pavement from 11/00 to 19/00 Kmp=8.00 Kms) Group A | Km |  | NHD-III | 26.8.23 | 26.8.25 | [7 empty] | Item Rate
36 | Construction of Road from Khamrang to Selesih Phase-II (Sh: Construction of Rigid Pavement from 19/00 to 28/00 Kmp=9.00Kms) Group B | Km |  | NHD-III | 26.8.23 | 26.8.25 | [7 empty] | Item Rate
37 | Construction of MDR from Khamrang-Dilsei to Selesih (Phase-I) (Length = 11.00 Kms) Group-A (0/00 to 3/600Km) | Km | 6583.18 | NHD-III | 8.02.21 | 8.8.22 1st EOT=184 days (upto 08.02.23, 2nd EOT=150 days (upto 08.07.23) | 42.89% | 314.25 | 4.19% | - | 42.89% | 314.25 |  | Item Rate
38 | Construction of road from Khamrang to Selesih Phase-I (Length = 11.00 Kms) Group-B (3/60 to 7/200Km) | Km |  | NHD-III | 8.02.21 | 8.8.22 1st EOT=184 days (upto 08.02.23, 2nd EOT=150 days (wef 09.02.23-08.07.23) | 44.34% | 434.62 | 9.02% |  | 53.36% | 434.62 |  | Item Rate
39 | Construction of road from Khamrang to Selesih Phase-I (Length = 11.00 Kms) Group-C (7/200 to 11/00Km) | Km |  | NHD-III | 8.02.21 | 8.8.22 1st EOT=184 days (upto 08.02.23, 2nd EOT=150 days (wef 09.02.23-08.07.23) | 42.04% | 177.27 | 5.24% |  | 47.28% | 177.27 |  | Item Rate
40 | Construction of road from Khamrang to Selesih Phase-I (Sh: Construction of Rigid Pavement from 7/00 to 11/00 Kmp = 4.00 Kms) | Km |  | NHD-III | 16.8.22 | 16.02.24 | [7 empty] | Item Rate
41 | Construction of MDR from Khamrang (Dilsei) to Selesih (Sh: Construction of approach road to Mualkhang Village) | Km |  | NHD-III | 8.2.21 | 08.08.22 | 100% | 122.25 |  |  | 100% | 122.25 |  | Item Rate
42 | Const.of Double Storied PHC at Tawipui South |  | 267.15 | Lunglei Building Project Division | 1.2.22 | 0.02.24 | 100% | 267.15 | - | - | 100% | 267.15 | Completed and hand over to the Client Dept.on dt.30.5.23 UCs & Project Completion Report already submitted | Restricted Tender
43 | Const.of Double Storied PHC at Lungsen |  | 267.15 | Lunglei Building Project Division | 10.2.22 | 10.2.24 | 95% | 196.81 | 1% |  | 96% | 196.81 | Civil Works in completion stage and fund for I/E already transferred | Restricted Tender
44 | Const.of Infrastructure Support fro School of Agricultural Science at Hnahthial: Phase-II |  | 685 | Lunglei Building Project Division | 08.04.23 | 08.04.25 | 11% |  | 2% |  | 13% |  | Works in progress | Restricted Tender
45 | Construction of Security Wall at District Jail Siaha |  | 100 | Lunglei Building Project Division | 10.3.23 | 10.9.23 | 60% | 40.05 | 1% |  | 60% | 40.05 | Work in progress and EOT in progress | Restricted Tender
46 | Construction of 24 Warehouses with associated Infrastructure in 23 localities in Mizoram under NABARD (Gr-III: Siaha, Chapui, Bungtlang South |  | 4543.15 | Lunglei Building Project Division | 17.07.23 | 13.10.24 |  |  | 5% |  | 5% |  | Works not yet started. Approval for dismantling and survey report being awaited from the government | Restricted Tender
47 | Construction of 24 Warehouses with associated Infrastructure in 23 localities in Mizoram under NABARD (Gr-IV: Lungpher) |  | 4543.15 | Lunglei Building Project Division | 17.07.23 | 13.10.24 |  |  | 5% |  | 5%
48 | Construction of 24 Warehouses with associated Infrastructure in 23 localities in Mizoram under NABARD (Gr-VI: South Vanlaiphai and Vawmbuk) |  | 4543.15 | Lunglei Building Project Division | 17.07.23 | 13.10.24 |  |  | 5% |  | 5%
49 | Construction of 24 Warehouses with associated Infrastructure in 23 localities in Mizoram under NABARD (Gr-VII: Hnahthial, Thingsai. Cherhlun and Siata) |  | 4543.15 | Lunglei Building Project Division | 17.07.23 | 13.10.24 |  |  | 5% |  | 5%
50 | Construction of 24 Warehouses with associated Infrastructure in 23 localities in Mizoram under NABARD (Gr-X: Vaseikai and Tlabung) |  | 4543.15 | Lunglei Building Project Division | 17.07.23 | 13.10.24 |  |  | 5% |  | 5%
51 | Strenthening & Improvement of W.Phaileng to Marpara Road (00.00-80.00Kmp) Package-I&II |  | 6633.38 | Mamit Division | 15.03.23 | 15.03.25 | 1% |  |  |  | 1% |  | Work in progress | Item rate
52 | Improvement of Chawngte - Borapansuri Road (0.00-30.00 Kmp) |  | 3987 | Tlabung Division | 15.3.23 | 15.3.25 | [6 empty] | Work cannot be progress due to Monsoon season | Item rate

## NEC
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding: NEC | [9 empty] | Month : September 2023
Sl. no | Name of Work/Project | Unit | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the Month |  | Overall cumulative achievement |  | Remarks | Mode of Contract
[7 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Construction of Lunglei Market and Trade Centre at Electric/Chanmari Veng, Lunglei (NEC) |  | 1403.4 | Lunglei Building Project Division | 25.08.22 | 25.08.24 | 20% | 298.74 | 2% |  | 22% | 298.74 | Work in progress | Restricted Tender
2 | Construction of Mara Handloom & Weaving Centre at Council Vaih, Saiha |  | 458.61 | Lunglei Building Project Division | 13.04.22 | 13.04.24 | 47% | 131.01 | 2% |  | 49% | 131.01 | Work in progress | Restricted Tender
3 | Proposal of Identified Village for providing key identified Service at Marpara S Village of W Bunghmun Block of Lunglei District |  | 141.3 | Lunglei Building Project Division | 6.4.23 | 6.4.24 | 16.87% |  | 8.75% |  | 25.62% |  |  | Work allotted to Vanlalsanga, Aizawl through Restricted Tender
4 | Proposal of Identified Village for providing key identified Service at Bungtlang S Village of Lawngtlai District, Mizoram |  | 186.89 | Lunglei Building Project Division | 6.4.23 | 6.4.24 | 62.72% |  |  | 82.05 | 62.72% | 82.05 |  | Work allotted to Vanlalsanga, Aizawl through Restricted Tender
5 | Proposal of Identified Village for providing key identified Service at Bungtlang RD Block of Lawngtlai District, Mizoram |  | 423.92 | Lunglei Building Project Division | 6.4.23 | 6.4.24 | 45.81% |  |  | 107.89 | 45.81% | 107.89
6 | Proposal of Identified Village for providing key identified Service at Chawngte RD Block of Lawngtlai District, Mizoram |  | 379.65 | Lunglei Building Project Division | 6.4.23 | 6.4.24 | 13.82% |  |  |  | 13.82% | 50.37
7 | Proposal of Identified Village for providing key identified Service at Bunghmun Block of Lunglei District, Mizoram |  | 391.94 | Lunglei Building Project Division | 6.4.23 | 6.4.24 | 11.25% |  |  |  | 11.25% |  |  | Work allotted to Lalnunmawia Bungkawn a, Aizawl through Restricted Tender
8 | Improvement & Upgradation of KDZKT Road (0.00 - 88.400Kmp) |  | 18327.42 | Kawrthah Division | 27.4.15 | 4.6.18 D.O.C = 31.12.21 | 100% | 18290 | - |  | 100% | 18290 | Work Phy.Completed on 31.12.21 SMS of R.Revised estimate is being awaited for financial closure | Open Tender
9 | Const.of Patient Lodging at Mawdiangdiang near NEIGHRIMS, Shillong |  | 419.67 | Project Division-I | 9.9.21 | 9.9.23 | 15% | - | - | 167.87 | 15% | 167.87 |  | EPC
10 | Infrastructure Development of Biotechnology Cell in Mizoram (C/O Building at MINECO) |  | 386.6 | Project Division-I | 1.7.23 | 1.5.25 | [6 empty] | Work in progress | EPC
11 | Establishment of Central Medical Warehouse at Aizawl, Mizoram |  | 1490 | Project Division-I | 4.8.23 | 14.8.25 | [6 empty] | Work being started
12 | Construction of Aizawl Institute of Arts & Music for the NER, Tuivamit Tlang, Aizawl |  | 590.23 | Project Division-I | 4.9.23 | 4.9.25 |  |  |  |  | 1% |  |  | EPC
13 | Construction of 60 Bedded Intern Hostel at ZMC, Falkawn | % | 679 | Project Division-II | 01.09.22 | 01.05.24 | 32% | 271.6 | 5% |  | 37% | 271.6 | Work in progress
14 | Construction of Market Building at West Phaileng, Mamit District | % | 278.242 | Project Division-II | 22.08.23 | 22.08.25 | [6 empty] | Work just started
15 | Creation of Passion fruit Processing unit at Cold Storage, New Champhai Mizoram | % | 185.36 | Project Division-III | 23.09.22 | 24.03.24 | 10% | - | 5% | - | 15% | - | As per revised sanction by NEC, only civil construction work is under PWD Work in progress | PWD Form-8
16 | Construction of Zomi cultural Centre and preservation of historical sites at Champhai | % | 478.69 | Project Division-III | 26.09.22 | 26.09.24 | 10% | - |  | - | 10% | - | 1. Fund not yet released by NEC 2. Approval for change of Implementation Agency from DC Champhai to PWD is awaited | PWD Form-8
17 | Construction of Biate Tea Tourism Circuit & Nature Camp in Mizoram | % | 369.62 | Project Division-III | 9.10.23 | 9.10.25 | [5 empty] | - | Work order issued | PWD Form-8
18 | Forstering Industry, Innovation, Infrastructure and Livelihood Oppurtunities (SDG 9) at Lunglen-1 and Sialhawk, Mizoram and strengthening of Food Testing Laboratory (Sh: Construction of Pineapple precessing plant building at Sialhawk) | % | 65.7 | Project Division-III | 12.10.23 | 12.10.25 | [6 empty] | Work order issued | PWD Form-8
19 | Construction of AYUSH Development Centre at MINECO Aizawl | % | 264.16 | Project Division-IV | 7.12.22 | 17.8.24 | 16% | 10 | 5.15% |  | 21.15% | 10 | Work in progress | Item Rate
20 | Etablishment of Sinlung Hills Council Administrative Complex (Const.of Sinlung Hills Administrative Building at Sakawrdai) | % | 381.99 | Project Division-IV | 8.11.21 | 8.11.23 | 49.5% | 115.08 | 3.5% | 37.9 | 53% | 152.98 | Work in progress | Item Rate
21 | Upgradation of Serkhan - Bagha Road |  | 17328 | NHD-III | 4.10.11 | 10.01.20 | 100% | 17239.22 | - | - | 100% | 17239.22 | Completed | Item Rate

## Deposit
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : Deposit | [10 empty] | Month : September 2023
Sl. No | Name of Work/Project | Unit | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummutive Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[7 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Construction of New Ward Building (Renovation & Upgradation of Central Jail) at Aizawl, Mizoram |  | 100 | Project Division-I | 28.8.22 | 23.3.24 | 20% | - | 5% | - | 25% | - |  | EPC

## PMGSY
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding: PMGSY | [9 empty] | Month : September 2023
Sl. no | Name of Work/Project | Unit | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[7 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Diblibagh to Chengkawllui Road (0.000-19.520)Kmp |  | 2798.82 | Tlabung Division | 17.6.19 | 17.6.20 | 80.45% | 1509.18 |  |  | 80.45% | 1509.18 | Extension granted upto Dt.31.3.23 | Item Rate
2 | Diblibagh to Sugarbasora Road (0.000-2.000)Kmp |  | 305.81 | Tlabung Division | 28.9.18 | 28.9.19 | 69.81% | 211.07 | - |  | 69.81% | 211.07 | Extension granted upto Dt.31.3.23 | Item Rate
3 | Diblibagh to Sugarbasora Road Group B (2.000-4.760)Kmp |  | 373.19 | Tlabung Division | 22.9.18 | 22.9.19 | 92.2% | 123.6 | - | - | 92.2% | 123.6 | Extension granted upto Dt.31.3.23 | Item Rate
4 | Const & Maintenance of Tlabung-Nunsury Road (0.000-8.000) Kmp |  | 579.77 | Tlabung Division | 17.6.19 | 17.6.20 | 51.4% | 145.96 |  | - | 51.4% | 145.96 | Extension granted upto Dt.31.3.23 | Item Rate
5 | Const.of Serhuan-Lamthai Road |  | 1378.12 | Tlabung Division | 21.12.17 | 27.11.19 | 91.48% | 969.08 |  | - | 91.48% | 969.08 | Extension granted upto Dt.13.8.23 | Item Rate
6 | Chhotapansuri-Tungasora Road (0.000-2.000)Kmp |  | 303.43 | Tlabung Division | 22.9.18 | 22.9.19 | 64.23% | 100.06 |  | - | 64.23% | 100.06 | Extension granted upto Dt.09.2.23 | Item Rate
7 | Chhotapansuri-Tungasora Road (2.000-3.500)Kmp |  | 209.66 | Tlabung Division | 5.10.18 | 5.10.19 | 93.33% | 175.89 |  |  | 93.33% | 175.89 | Extension granted upto Dt.08.2.23 | Item Rate
8 | Ngharum to Rajmandal Road |  | 929.42 | Tlabung Division | 17.06.19 | 04.03.22 | 100% | 596.25 |  | - | 100% | 596.25
9 | Mandiasora-Ajasora Road (0.000 - 8.500) Kmp |  | 734.93 | Tlabung Division | 17.6.19 | 17.6.20 | 92.6% | 635.71 |  |  | 92.6% | 635.71 | Extension granted upto Dt.30.6.23 | Item Rate
10 | Construction & Maintenance of Sairang - Lengte-Nghalchawm |  | 842.17 | NHD-I | 19.12.20 | 29.08.23 | 95% | 476.06 | 0.2% | 225.28 | 95.2% | 701.34 | 4th EOT til 15.12.23 being applied | Item rate contract
11 | Construction of Dilkhan to Tualbung Road (Sh:-Construction of Road using flexible pavement) |  | 567.6 | Saitual Division | 27.10.17 | 27.10.19 | 100% | 499.05 | - | - | 100% | 499.05 | EoT Dt.31.7.2022
12 | Construction and Maintenance of Lungpher to Buhban Road (Sh: Construction of road using flexible pavement) |  | 490.11 | Saitual Division | 13.11.17 | 13.5.19 | 100% | 478.12 | - | - | 100% | 478.12 | EoT Dt.31.11.19
13 | Construction and Maintenance of Phullen to Luangpawn Road (Sh: FC, Culvert & R/Wall and Construction of road using flexible pavement) |  | 993.46 | Saitual Division | 17.09.18 | 17.09.19 | 100% | 969.75 | - | - | 100% | 969.75 | EoT Dt.31.7.22
14 | Construction and Maintenance of E.Phaileng-Suangpuilawn Road (0.000-6.000Kmp) (Sh: Widening, Culverts & R/Wall and Contstruction of road using flexible pavement) |  | 831.6 | Saitual Division | 19.12.20 | 19.12.22 | 81% | 142.92 | 9% | - | 90% | 142.92 | EoT Dt.15.10.23
15 | Construction and Maintenance of E.Phaileng-Suangpuilawn Road (6.000-11.000Kmp) (Sh: Widening, Culverts & R/Wall and Construction of Road using flexible pavement) |  | 906.47 | Saitual Division | 19.12.20 | 19.12.22 | 72% | 116.25 | 5% | - | 77% | 116.25 | EoT Dt.15.10.23
16 | Construction and Maintenance of E.Phaileng-Suangpuilawn Road (11.000-16.000Kmp) (Sh: Widening, Culverts & R/Wall and Construction of Road using flexible pavement) |  | 807.84 | Saitual Division | 15.8.20 | 15.8.22 | 100% | 678.98 | - |  | 100% | 678.98 | EoT Dt.24.03.23
29 | [12 empty] | EoT Dt.24.13.24
17 | Construction and Maintenance of E.Phaileng-Suangpuilawn Road (16.000-22.000Kmp) (Sh: Widening, Culverts & R/Wall and Construction of Road using flexible pavement) |  | 826.35 | Saitual Division | 01.01.21 | 01.01.23 | 71% | 305.65 | 6% |  | 77% | 305.65 | EoT Dt.28.10.23
18 | Construction and Maintenance of E.Phaileng-Suangpuilawn Road (22.000-28.000Kmp) (Sh: Widening, Culverts & R/Wall and Construction of Road using flexible pavement) |  | 811.17 | Saitual Division | 01.01.20 | 01.01.22 | 100% | 632.27 | - | - | 100% | 632.27 | EoT Dt.28.10.23
19 | Construction and Maintenance of E.Phaileng-Suangpuilawn Road (28.000-34.000Kmp) (Sh: Widening, Culverts & R/Wall and Construction of Road using flexible pavement) |  | 1133.6 | Saitual Division | 10.02.20 | 10.02.22 | 100% | 531.51 | - | - | 100% | 531.51
20 | Construction and Maintenance of E.Phaileng-Suangpuilawn Road 34.000-40.000Kmp) (Sh: Widening, Culverts & R/Wall and Construction of Road using flexible pavement) |  | 1055.65 | Saitual Division | 6.01.20 | 6.01.22 | 76% | 342.95 | - |  | 76% | 342.95 | EoT Dt.29.11.22
21 | Construction and Maintenance of E.Phaileng-Suangpuilawn Road 40.000-46.000Kmp) (Sh: Widening, Culverts & R/Wall and Construction of Road using flexible pavement) |  | 1000.02 | Saitual Division | 6.01.20 | 6.01.22 | 77% | 342.05 | - |  | 77% | 342.05 | EoT Dt.29.11.22
22 | Construction and Maintenance of Bunghmun-W.Mualthuam Road (Sh: Cell filled Concrete Road) (0.00-13.500 Kmp) |  | 955.77 | Kawrthah Division | 27.11.17 | 16.09.22 | 100% | 918.23 | - | - | 100% | 918.23 | Works under maintenance from 16.9.22 | Open Tender
23 | Construction and Maintenance of Bunghmun to Thaidawr Road (0.00 Kmp-8.90 Kmp) |  | 745.77 | Kawrthah Division | 17.6.19 | 16.09.23 | 100% | 720.72 | - | - | 100% | 720.72 | Works under maintenance from 16.9.22 | Open Tender
24 | Construction of Darlak-Sihthiang Road (0.00-35.610 Kmp) |  | 5369.98 | Kawrthah Division | 17.6.19 | 19.6.20 | 10% | 488.49 | - | - | 10% | 488.49 | Foreclosed due to Forest clearance vide letter No.B.13016/2/2022-PWD(T)/Pt Dt.20.9.23 | Open Tender
25 | Construction & Maintenance of Khawzawl to Biate Road (0.00 kmp-6.00Km) Group-A |  | 780.49 | Khawzawl Division | 31.12.20 | 31.12.22 | 80.52% | 381.64 |  | 103.55 | 80.52% | 485.19 | EOT granted upto 31.12.23 | Item Rate Contract
26 | Construction & Maintenance of Khawzawl to Biate Road (6.00 kmp-12.00Km) Group-B |  | 760.98 | Khawzawl Division | 31.12.20 | 31.12.22 | 77.16% | 386.23 | - | 43.57 | 77.16% | 429.8 | EOT granted upto 31.12.23 | Item Rate Contract
27 | Construction & Maintenance of Khawzawl to Biate Road (12.00 kmp-18.00Km) Group-C |  | 817.47 | Khawzawl Division | 2.1.21 | 2.1.23 | 69% | 372.56 |  |  | 69% | 372.56 | EOT granted upto 29.10.23 | Item Rate Contract
28 | Construction & Maintenance of Khawzawl to Biate Road (18.00 kmp-24.00Km) Group-D |  | 750.94 | Khawzawl Division | 10.6.20 | 10.6.23 | 62.59% | 258.56 |  | - | 62.59% | 258.56 | EOT Not yet granted | Item rate contract
29 | Construction & Maintenance of Khawzawl to Biate Road (24.00 kmp-30.00Km) Group-E |  | 766.62 | Khawzawl Division | 29.4.21 | 29.4.22 | 54.6% | 291.76 | - |  | 54.6% | 291.76 | EOT granted upto 1.04.23 | Item Rate Contract
30 | Construction & Maintenance of Khawzawl to Biate Road (30.00 kmp-36.00Km) Group-F |  | 1148.93 | Khawzawl Division | 7.2.20 | 7.2.22 | 85.54% | 664.74 | - |  | 85.54% | 664.74 | EOT granted upto 31.12.22 | Item Rate Contract
31 | Construction & Maintenance of Khawzawl to Biate Road (36.00 kmp-42.00Km) Group-G |  | 818.99 | Khawzawl Division | 1.1.21 | 1.1.23 | 90.26% | 680.48 |  |  | 90.26% | 680.48 | EOT granted upto 31.12.23 | Item Rate Contract
32 | Construction & Maintenance of Khawzawl to Biate Road (42.00 kmp-48.00Km) Group-H |  | 1430.26 | Khawzawl Division | 6.1.20 | 6.1.22 | 78.78% | 930.61 |  | - | 78.78% | 930.61 | EOT Not yet granted | Item rate contract
33 | Construction & Maintenance of Khawzawl to Biate Road (48.00 kmp-54.00Km) Group-I |  | 1108.01 | Khawzawl Division | 24.3.21 | 24.3.23 | 67.25% | 407.28 | - | - | 67.25% | 407.28 | EOT granted upto 31.12.23 | Item Rate Contract
34 | Construction & Maintenance of Khawzawl to Biate Road (54.00 kmp-60.00Km) Group-J |  | 937.99 | Khawzawl Division | 4.1.21 | 4.1.23 | 64.31% | 442.83 | - |  | 64.31% | 442.83 | EOT granted upto 31.12.23 | Item Rate Contract
35 | Construction & Maintenance of Khawzawl-Ngaizawl Road |  | 817.57 | Khawzawl Division | 13.11.17 | 13.11.19 | 93% | 486.84 | - | - | 93% | 486.84 | EOT granted upto 14.04.22 | Item Rate Contract
36 | Construction & Maintenance of Khawhai - Tlangpuilian Road |  | 962.79 | Khawzawl Division | 13.11.17 | 31.12.19 | 100% | 855.19 |  |  | 100% | 855.19 | EOT granted upto 30.09.2022 | Item Rate Contract
37 | Construction & Maintenance of Khawzawl - Vankal Road |  | 1997.33 | Khawzawl Division | 13.12.18 | 13.12.19 | 93% | 1625.3 | - |  | 93% | 1625.3 | EOT granted upto 31.11.21 | Item rate contract
38 | Construction & Maintenance of Khawzawl - Hmuncheng Road |  | 1595.69 | Khawzawl Division | 23.05.22 | 23.05.23 | 78% | 1163.72 | 1% |  | 79% | 1163.72 | Work in progress
39 | Construction & Maintenance of Khawzawl - Hmuncheng Road |  | 1595.69 | Khawzawl Division | 05.10.18 | 05.10.19 | 75% | 959.03 | - | - | 75% | 959.03
40 | Construction & Maintenance of Khawzawl - Hmuncheng Road |  | 636.68 | Khawzawl Division | 23.05.22 | 30.09.22 | 48% | 204.69 | - |  | 48% | 204.69 | EOT Not yet granted | Item rate contract
41 | Construction & Maintenance of Phuldungsei to Parvatui Road (0.00 Kmp - 17.30 Kmp) |  | 3743.71 | Mamit Division | 13.12.18 | 13.12.19 | 76% | 2888.4 | 1% | - | 77% | 2888.4 | Revised Target date of completion=5.9.22 Supplementary Estimate=36,95,51,610.56 | Item rate
42 | Construction & Maintenance of Tuipuibari to Andermanik Road (0.00 Kmp - 2.760 km) |  | 430.18 | Mamit Division | 17.9.18 | 17.9.19 | 95% | 297.93 | - | - | 95% | 297.93 | Revised Target date of completion= 12.2.2022 | Item rate
43 | Construction & Maintenance of Andermanik to N.Belkhai Road (0.00 Kmp - 6.00 km) |  | 1016.7 | Mamit Division | 10.6.19 | 10.6.20 | 40% | 156.41 |  | - | 40% | 156.41 | Revised Target date of completion= 31.01.2023 | Item rate
44 | Thuampui - Lungchem Road (23.000 - 27.000 KMP) |  | 447.49 | Lunglei Road Division-I | 27.10.17 | 21.07.21 | 100% | 447.49 | - | - | 100% | 447.49 | Deviation already approved due to Some items are changed as mentioned in EE letter No.D-13024/5/2019(DV)/S&I/LD/PWD/Pt/10 Dt.18.02.21 Completed
45 | Thuampui - Lungchem Road (27.000 -32.000 KMP) |  | 395.75 | Lunglei Road Division-I | 27.10.17 | 24.09.21 | 100% | 378.64 | - | - | 100% | 378.64
46 | Thuampui - Lungchem Road (32.000 -37.000 KMP) |  | 372.33 | Lunglei Road Division-I | 27.11.17 | 30.09.22 | 100% | 372.31 | - |  | 100% | 372.31 | Completed
47 | Thuampui - Lungchem Road (37.000 - 40.900 KMP) |  | 307.24 | Lunglei Road Division-I | 27.10.17 | 13.08.21 | 100% | 336.09 | - | - | 100% | 336.09 | Completed
48 | Construction and Maintenance of Sachan to Sumasumi Road (0.00 - 24.09 Kmp) |  | 4005.26 | Lunglei Road Division-I | 10.06.19 | 31.08.22 | 50% | 1831.54 |  |  | 50% | 1831.54 | Work in progress
49 | Construction and Maintenance of Sumasumi - Tuikawi Road (0.00 - 19.22 Kmp) |  | 2882.21 | Lunglei Road Division-I | 14.06.19 | 26.12.21 | 33% | 697.5 |  | - | 33% | 697.5 | Work in progress
50 | Thuampui - Lungchem Road (0.000 - 4.000 KMP) |  | 85.83 | Lunglei Road Division-I | 01.04.21 | 31.03.22 | 100% | 85.83 | - | - | 100% | 85.53 | Completed
51 | Thuampui - Lungchem Road (4.000 - 7.000 KMP) |  | 268.21 | Lunglei Road Division-I | 27.10.17 | 14.07.21 | 100% | 268.19 | - | - | 100% | 268.19 | Completed
52 | Thuampui - Lungchem Road (7.000 - 10.000 KMP) |  | 306.59 | Lunglei Road Division-I | 27.10.17 | 15.08.21 | 100% | 306.56 | - | - | 100% | 306.56 | Completed
53 | Thuampui - Lungchem Road (10.000 - 14.000 KMP) |  | 387.7 | Lunglei Road Division-I | 27.10.17 | 04.07.21 | 100% | 387.68 | - | - | 100% | 387.68 | Completed
54 | Thuampui - Lungchem Road (14.000 - 18.000 KMP) |  | 394.46 | Lunglei Road Division-I | 13.11.17 | 31.12.22 | 100% | 257.8 | - | - | 100% | 257.8
55 | Thuampui - Lungchem Road (18.000 - 21.000 KMP) |  | 418.83 | Lunglei Road Division-I | 27.10.17 | 07.11.21 | 100% | 195.53 | - | 223.35 | 100% | 418.88 | Some items are changes due to Deviation approval vide EE letter no.D-13024/5/2019(DV)/S&I/LDIPWD/28 dt.9.03.22 completed
56 | Thuampui - Lungchem Road (21.000 - 23.000 KMP) |  | 370.75 | Lunglei Road Division-I | 13.11.17 | 31.07.22 | 100% | 280.41 | - | 90.33 | 100% | 370.74 | Completed
57 | Const. & Maint.of Bunghmun to Sachan Road (0.00-9.07Kmp) |  | 1325.06 | Lunglei Road Division-I | 13.12.18 | 31.07.22 | 56% | 654.39 |  |  | 56% | 654.39
58 | Const. & Maint.of Cherhlun to Ngharchhip Road (0.00-7.64 Kmp) |  | 554.08 | Hnahthial Division | 13.12.18 | 31.3.23 | 100% | 399.01 | - | - | 100% | 399.01 |  | Open Tender
59 | Const. & Maint.of Khawhri to Chawngtui Road (0.00-17.81 Kmp) |  | 1280.59 | Hnahthial Division | 8.10.18 | 31.3.24 | 81% | 741.73 |  | - | 81% | 741.73 | Collection of Material is in progress | Open Tender
60 | Const. & Maint.of Luangmual to Vaisam Road (0.00-26.700 Kmp) |  | 4518.74 | Hnahthial Division | 10.06.19 | 31.3.24 | 63% | 2439.75 |  |  | 63% | 2439.75 | Collection of Material is in progress | Open Tender
61 | Const. & Maint.of Haulawng to Dawn Road (0.00-6.00 Kmp) |  | 742.02 | Hnahthial Division | 10.06.20 | 31.3.24 | 94% | 623.89 |  |  | 94% | 623.89 | Collection of Material is in progress | Open Tender
62 | Const. & Maint.of Haulawng to Dawn Road (6.00-12.000 Kmp) |  | 605.77 | Hnahthial Division | 01.01.21 | 31.3.24 | 82% | 239.43 |  | - | 82% | 239.43 | Financial Progress stated in the previous MPR was incorrect as it is not alignment with the OMMAS. I have provided correct Financial Progress in this MPR | Open Tender
63 | Const. & Maint.of Haulawng to Dawn Road (12.00-18.000 Kmp) |  | 607.56 | Hnahthial Division | 01.01.21 | 31.3.24 | 79% | 480.18 |  |  | 79% | 480.18 | Collection of Material is in progress | Open Tender
64 | Const. & Maint.of Haulawng to Dawn Road (18.00-24.000 Kmp) |  | 743.95 | Hnahthial Division | 01.01.21 | 31.3.24 | 85% | 203.38 |  | 182.33 | 85% | 385.71 | Financial Progress stated in the previous MPR was incorrect as it is not alignment with the OMMAS. I have provided correct Financial Progress in this MPR | Open Tender
65 | Const. & Maint.of Haulawng to Dawn Road (24.00-30.500 Kmp) |  | 840.58 | Hnahthial Division | 01.01.21 | 31.3.24 | 92% | 401.68 |  |  | 92% | 401.68 | Financial Progress stated in the previous MPR was incorrect as it is not alignment with the OMMAS. I have provided correct Financial Progress in this MPR | Open Tender
66 | Construction of Nghalimlui to Bolisora (0.00-3.00)Kmp (Sh: FC, Culvert, R.Wall) | 3 | 158.34 | Lawngtlai Division | 27.10.17 | 30.04.20 | 100% | 158.33 | - | - | 100% | 158.33 | Completed | NIT
67 | Construction of Nghalimlui to Bolisora (3.00-5.00)Kmp (Sh: FC, Culvert, R.Wall) | 2 | 249.3 | Lawngtlai Division | 27.10.17 | 23.03.20 | 100% | 247.3 | - | - | 100% | 247.3 | Completed | NIT
68 | Construction of Nghalimlui to Bolisora (5.00-8.00)Kmp (Sh: FC, Culvert, R.Wall) | 3 | 206.24 | Lawngtlai Division | 27.10.17 | 10.08.20 | 100% | 206.24 | - | - | 100% | 206.24 | Completed | NIT
69 | Construction of Nghalimlui to Bolisora (8.00-12.65)Kmp (Sh: FC, Culvert, R.Wall) | 4.65 | 266.55 | Lawngtlai Division | 27.10.17 | 16.08.20 | 100% | 246.66 | - | - | 100% | 246.66 | Completed | NIT
70 | Construction of Karlui to Damlui (0.00-2.00)Kmp (Sh: FC, Culvert, R.Wall) | 2 | 207.84 | Lawngtlai Division | 27.10.17 | 28.2.20 | 100% | 207.66 | - | - | 100% | 207.66 | Completed | NIT
71 | Construction of Karlui to Damlui (2.00-6.00)Kmp (Sh: FC, Culvert, R.Wall) | 4 | 227.54 | Lawngtlai Division | 27.10.17 | 30.10.19 | 100% | 216.35 | - | - | 100% | 216.35 | Completed | NIT
72 | Construction of Karlui to Damlui (6.00-8.800)Kmp (Sh: FC, Culvert, R.Wall) | 2.8 | 147.71 | Lawngtlai Division | 13.11.17 | 25.10.19 | 100% | 147.69 | - | - | 100% | 147.69 | Completed | NIT
73 | Construction of Bolisora to Chamdurtlang (0.00 - 2.00) Kmp (Sh: FC, Culvert. R.Wall) | 2 | 155.49 | Lawngtlai Division | 27.10.17 | 20.05.20 | 100% | 155.49 | - | - | 100% | 155.49 | Completed | NIT
74 | Construction of Bolisora to Chamdurtlang(2.00-5.00)Kmp (Sh: FC, Culvert, R.Wall) | 3 | 229.32 | Lawngtlai Division | 27.10.17 | 16.03.20 | 100% | 229.32 | - | - | 100% | 229.32 | Completed | NIT
75 | Construction of Bolisora to Chamdurtlang(5.00-9.00)Kmp (Sh: FC, Culvert, R.Wall) | 4 | 359.96 | Lawngtlai Division | 01.04.19 | 29.09.21 | 100% | 359.95 | - | - | 100% | 359.95 | Completed | NIT
76 | Construction of Bolisora to Chamdurtlang(9.00-11.650)Kmp (Sh: FC, Culvert, R.Wall) | 2.65 | 251.92 | Lawngtlai Division | 27.10.17 | 16.03.20 | 100% | 251.9 | - | - | 100% | 251.9 | Completed | NIT
77 | Construction of Ajasora to Longpuighat (0.00-10.900)Kmp (Sh: Const.of road using Flexible Pavement Technology) | 10.9 | 934 | Lawngtlai Division | 13.11.17 | 19.12.21 | 100% | 857.32 | - | - | 100% | 857.32 | Ongoing | NIT
78 | Construction of Jognasury - Karlui Road (0.000-12.100)Kmp (Sh: Formation Cutting, Culvert & R.Walls & Const.of of Road Using Flexible Pavement) | 12.1 | 888.27 | Lawngtlai Division | 13.12.18 | 30.09.22 | 100% | 760.65 |  | - | 100% | 760.65 | Completed | NIT
79 | Construction of Maniababsora-I to Maniababsora-II Road (0.000-1.520)Kmp (Sh: FC, Culvert & R.Wall & Const.of road using Panelled Concrete Technology) | 1.52 | 212.32 | Lawngtlai Division | 27.12.18 | 22.11.20 | 100% | 212.32 | - | - | 100% | 212.32 | Completed | NIT
80 | Construction of Boroituli to Jaruldubasora Road (0.000-2.100)Kmp (Sh: FC, Culvert & R.Wall & Const.of road using Panelled Concrete Technology) | 2.1 | 257.02 | Lawngtlai Division | 17.09.18 | 10.02.22 | 100% | 257 | - | - | 100% | 257 | Completed | NIT
81 | Construction of Boroituli to Jaruldubasora Road (2.000-3.700)Kmp (Sh: FC, Culvert & R.Wall & Const.of road using Panelled Concrete Technology) | 1.7 | 269.85 | Lawngtlai Division | 28.09.18 | 30.09.22 | 100% | 268.54 | - | - | 100% | 268.54 | Completed | NIT
82 | Construction of Vaseitlang to Lokhisury Road(0.00-9.560)Kmp (Sh: FC, Culvert, R.Wall & Const.of road using Panelled Concrete Technology) | 9.56 | 1366.7 | Lawngtlai Division | 28.09.18 | 30.09.22 | 67.85% | 822.15 | - | - | 67.85% | 822.15 | Ongoing | NIT
83 | Construction of Vathuampui to Tuisentlang Road(0.000-9.600)Kmp (Sh: FC, Culvert, R.Wall & Const.of Road Using panelled Concrete) | 9.6 | 910.99 | Lawngtlai Division | 03.01.18 | 30.09.22 | 72.58% | 910.99 | 0.42% | - | 73% | 910.99 | Ongoing | NIT
84 | Construction of Vathuampui to Chamdur P-I Road(0.000-1.720)Kmp (Sh: FC, Culvert, R.Wall & Const.of Road Using panelled Concrete) | 1.72 | 263.08 | Lawngtlai Division | 15.10.18 | 30.09.22 | 100% | 261.11 | - | - | 100% | 261.11 | Completed | NIT
85 | Construction of Vathuampui to Chamdurtlang (0.000-1.720)Kmp (Sh: FC, Culvert, R.Wall & Const.of Road Using panelled Concrete) | 2 | 274.17 | Lawngtlai Division | 13.12.18 | 30.09.22 | 71.15% | 180.75 | - | - | 71.15% | 180.75 | Ongoing | NIT
86 | Construction of Vathuampui to Chamdurtlang (2.000-3.800)Kmp (Sh: FC, Culvert, R.Wall & Const.of Road Using panelled Concrete) | 1.8 | 360.89 | Lawngtlai Division | 22.09.18 | 30.09.22 | 100% | 356.27 | - |  | 100% | 356.27 | Completed | NIT
87 | Construction of Chamdurtlang to Mualtlang Road(0.000-7.970)Kmp (Sh: FC, Culvert, R.Wall & Const.of Road Using panelled Concrete) | 7.97 | 1152.2 | Lawngtlai Division | 13.12.18 | 30.09.22 | 100% | 1089.09 | - | - | 100% | 1089.09 | Completed | NIT
88 | Construction of Parva II to Zochachhuah Road(0.000-29.720)Kmp (Sh: FC, Culvert, R.Wall & Const.of Road Using panelled Concrete) | 29.72 | 5432.38 | Lawngtlai Division | 05.04.20 | 30.09.23 | 100% | 4745.79 | - |  | 100% | 4745.79 | Ongoing | NIT
89 | Construction of Parva II to Bondukbanga Road(0.000-2.000)Kmp (Sh: FC, Culvert, R.Wall & Const.of Road Using Flexible Pavement) | 2 | 269.72 | Lawngtlai Division | 28.09.18 | 12.01.22 | 100% | 269.14 | - | - | 100% | 269.14 | Completed | NIT
90 | Construction of Parva II to Bondukbanga Road(2.000-4.120)Kmp (Sh: FC, Culvert, R.Wall & Const.of Road Using Flexible Pavement) | 2.12 | 294.1 | Lawngtlai Division | 13.12.18 | 31.12.22 | 100% | 259.1 |  | - | 100% | 259.1 | Ongoing | NIT
91 | Construction &Maintenance of Parva-II - Kamtuli Road (0.000-25.550)Kmp (Sh: FC, Culvert, R.Wall & Const.of Road Using panelled Concrete) | 25.55 | 4139.88 | Lawngtlai Division | 17.06.20 | 30.09.22 | 85.12% | 2148.95 |  |  | 85.12% | 2148.95 | Ongoing | NIT
92 | Construction & Maintenance of Vaseitlang to Maniababsora Road (0.000-13.500)Kmp (Sh: FC, Culvert, R.Wall & Const.of Road Using panelled Concrete) | 13.5 | 2361.15 | Lawngtlai Division | 14.06.19 | 30.04.22 | 100% | 2358.27 | - | - | 100% | 2358.27 | Completed | NIT
93 | Construction & Maintenance of Sedailui to Tuikhurlui Road (0.000-1.720)Kmp (Sh: FC, Culvert, R.Wall & Const.of Road Using panelled Concrete Techonology) | 1.72 | 204.33 | Lawngtlai Division | 17.06.19 | 08.05.22 | 92.06% | 159.96 | - | - | 92.06% | 159.96 | Ongoing | NIT
94 | Construction &Maintenance of M.Kawnpui to Vathuampui Road (0.000-20.000)Kmp (Sh: FC, Culvert, R.Wall & Const.of Road Using panelled Concrete Technology) | 20 | 1976.47 | Lawngtlai Division | 14.06.19 | 30.09.22 | 59.33% | 735.65 | - | - | 59.33% | 735.65 | Ongoing | NIT
95 | Construction &Maintenance of Sumsului Road to Jognasury (0.000-15.44)Kmp (Sh: Const.of Road Using panelled Concrete Technology) | 13.7 | 1278.38 | Lawngtlai Division | 14.06.20 | 30.09.22 | 84.08% | 1065.69 | - |  | 84.08% | 1065.69 | Ongoing | NIT
96 | Construction &Maintenance of Chawngte 'P' to Sumsului Road (0.000-4.570)Kmp (Sh: FC, Culvert, R.Wall & Const.of Road Using panelled Concrete Technology) | 4.57 | 313.29 | Lawngtlai Division | 01.07.19 | 31.03.22 | 100% | 286.51 |  | - | 100% | 286.51 | Completed | NIT
97 | Construction of Niawhtlang - Chakhang Road (0.00 - 44.05) Kmp |  | 1615.335 | Siaha Division | 20.10.20 | 31.03.23 | 35.15% | 184.027 | - | - | 35.15% | 184.027 | 1. Contractor expired 2. Closure of contract and retending of balance work under process | Item rate contract
98 | Construction of Phura - Vahai Road (0.00 - 17.000) Kmp |  | 1563.92 | Siaha Division | 13.11.17 | 31.11.19 | 100% | 1409.46 | - | - | 100% | 1409.46 | 4th EOT has being applied upto March 2024 | Item rate contract
99 | Construction of Tawngkolong - Lawngmasu Road (0.00 - 22.700) Kmp |  | 1289.738 | Siaha Division | 14.02.22 | 30.09.22 | 35.15% | 660.23 | 8.42% |  | 43.57% | 660.23 | 1st EOT has being applied upto March 2024 | Item rate contract
100 | Const.& Maintenance of Chhingchhip-Thentlang Road |  | 716.15 | Serchhip Division | 21.12.13 | 14.11.19 | 100% | 716.15 | - | - | 100% | 716.15 | Completed
101 | Const.& Maintenance of Hmuntha-Khawbel Road |  | 1191.86 | Serchhip Division | 21.12.13 | 18.03.20 | 100% | 1191.84 | - | - | 100% | 1191.84 | Completed
102 | Const.& Maintenance of Chhingchhip-Hmuntha Road |  | 1443.48 | Serchhip Division | 21.12.13 | 25.11.19 | 100% | 1429.95 | - | - | 100% | 1429.95 | Completed
103 | Const.& Maintenance of Khawlailung-Piler Road (0.000-4.160 Kmp) |  | 675.44 | Serchhip Division | 17.9.18 | 01.07.21 | 100% | 665.15 | - | - | 100% | 665.15 | Completed
104 | Const.& Maintenance of Chekawn-Sialsir Road (0.000-6.240 Kmp) |  | 882.58 | Serchhip Division | 13.12.18 | 01.09.21 | 100% | 881.1 | - | - | 100% | 881.1 | Completed
105 | Const.& Maintenance of Thentlang-Sialhau Road (0.000-19.54 Kmp) |  | 1367.2 | Serchhip Division | 28.9.18 | 28.9.19 | 100% | 1355.66 | - |  | 100% | 1355.66 | Physically completed
106 | Const.& Maintenance of Mualcheng-N.Vanlaiphai Road Group 'A' (0.000-8.000 Kmp) |  | 535.67 | Serchhip Division | 31.12.20 | 31.12.22 | 100% | 303.31 | - | - | 100% | 303.13 | Physically completed | Item rate contract
107 | Const.& Maintenance of Mualcheng-N.Vanlaiphai Road Group 'B' (8.000-16.000 Kmp) |  | 606.37 | Serchhip Division | 31.12.20 | 31.12.22 | 100% | 393.51 | - | - | 100% | 393.51 | Physically completed | Item rate contract
108 | Const.& Maintenance of E.Lungdar - Sailulak Road |  | 1243.47 | Serchhip Division | 21.12.13 | 31.03.19 | 100% | 1241.01 | - | - | 100% | 1241.01 | Completed
109 | Const.& Maintenance of Chekawn - Lungchhuan Road (0.000 - 4.000 Kmp) |  | 255.85 | Serchhip Division | 17.11.17 | 8.11.19 | 100% | 255.82 | - | - | 100% | 255.82 | Completed
110 | Construction of Tuithumhnar to Lunghauka (0.00 - 5.00) Kmp (Sh: FC, Culvert, R.Wall) |  | 189.03 | Multi Modal Project Division | 27.10.17 | 31.07.19 | 100% | 189.03 | - | - | 100% | 189.03 | Completed on 05/07/2019
111 | Construction of Tuithumhnar to Lunghauka (5.00 - 7.00) Kmp (Sh: FC, Culvert, R.Wall) |  | 196.98 | Multi Modal Project Division | 13.11.18 | 31.03.21 | 100% | 193.28 | - | - | 100% | 193.28 | Completed on 30/03/2021
112 | Construction of Tuithumhnar to Lunghauka (7.00 - 10.00) Kmp (Sh: FC, Culvert, R.Wall) |  | 247.04 | Multi Modal Project Division | 27.10.17 | 16.07.20 | 100% | 247.04 | - | - | 100% | 247.04 | Completed on 20/07/2020
113 | Construction of Tuithumhnar to Lunghauka (10.00 - 13.00) Kmp (Sh: FC, Culvert, R.Wall) |  | 184.6 | Multi Modal Project Division | 27.10.17 | 29.06.20 | 100% | 184.6 | - | - | 100% | 184.6 | Completed on 29/06/2020
114 | Construction of Tuithumhnar to Lunghauka (13.00 - 15.480) Kmp (Sh: FC, Culvert, R.Wall) |  | 198.08 | Multi Modal Project Division | 27.10.17 | 16.07.20 | 100% | 198.08 | - | - | 100% | 198.08 | Completed on 26/06/2020
115 | Construction & Maintenance of Ngenpuitlng to Darnamtlang (0.00 - 4.00) Kmp (Sh: FC, Culvert, R.Wall) |  | 233.08 | Multi Modal Project Division | 27.10.17 | 31.01.20 | 100% | 193.78 | - | - | 100% | 193.78 | Physically completed on 01/05/2020
116 | Construction & Maintenance of Ngenpuitlng to Darnamtlang (4.00 - 6.20) Kmp (Sh: FC, Culvert, R.Wall) |  | 161.44 | Multi Modal Project Division | 27.10.17 | 31.08.21 | 100% | 224.73 | - | - | 100% | 224.73 | Completed on 30/08/2021
117 | Construction & Maintenance of Tuithumhnar to Hmawngbu (0.00 - 6.720) Kmp (Sh: Construction of road using Grove Concrete Pavement) |  | 442.51 | Multi Modal Project Division | 12.11.17 | 1.10.21 | 100% | 441.76 | - |  | 100% | 441.76
118 | Construction of Sabualtlang to Hmawngbuchhuah Road (0.00 - 1.760) Kmp (Sh:Formation Cutting, Culvert & Retaining Walls & Construction of Road Using Flexible Pavement) |  | 244.22 | Multi Modal Project Division | 17.12.18 | 24.10.21 | 100% | 196.96 | - | 47.26 | 100% | 244.22 | Completed on 23/10/2021
119 | Construction & Maintenance of Nalkawn to Rulkual Road (0.000-16.000) Kmp Group A (Sh: Const.of Road using Cold Mix Technology |  | 1078.79 | Multi Modal Project Division | 04.01.21 | 04.01.23 | 100% | 1194.51 | - | - | 100% | 1194.51 | Completed on 29.9.22
120 | Construction & Maintenance of Nalkawn to Rulkual Road (16.000-32.000) Kmp Group B (Sh: Const.of Road using Cold Mix Technology |  | 1315.37 | Multi Modal Project Division | 10.02.20 | 30.09.22 | 17.51% | 476.65 | - | - | 17.51% | 476.63 | The contractor is expired and balance work is being prepared for NIT.
121 | Construction & Maintenance of Rawmibawk to Phalrang Road (0.000-10.200) Kmp (Sh: Const.of Road usinggroove concrete Technology |  | 759.92 | Multi Modal Project Division | 13.12.18 | 30.09.22 | 100% | 674.31 | - | 83.69 | 100% | 758 | Completed on 29.9.22
122 | Construction & Maintenance of Saiha to Rawmibawk Road (0.000-22.30) Kmp (Sh: Const.of Road using groove concrete Technology |  | 1941.19 | Multi Modal Project Division | 17.06.19 | 30.09.22 | 100% | 1914.2 |  |  | 100% | 1914.2 | Phy.Completed on 29.03.23

## SEDP
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding: SEDP | [9 empty] | Month : September 2023
Sl. no | Name of Work/Project | Unit | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[7 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Junction Improvement of Bawngkawn to ITI Road below Pu Sangnova (L) House (at Zirtiri College Junction) |  | 53.36 | Aizawl Road North Division |  |  | - | - | - | - | - | - | Land acquisition problem
2 | Const. of Approach Road to Aizawl College at Mualpui | Rm | 415 | Aizawl Road South Division | 26.07.21 | 26.04.22 | 73% | 300 | - | - | 73% | 300 | Work in progress | Item Rate Contract
3 | Re-Construction of Concrete Pavement on Approach Road to Mission Vengthlang Cemetry, L=150M | Rm | 8.51 | Aizawl Road South Division | [8 empty] | Works not yet started
4 | Construction of High Court Parking Building at MINECO | 1 | 1960 | Project Division-I | 2.7.20 | 30.10.23 | 73% | 994.63 | 1% | 4.09 | 74% | 998.72 |  | EPC
5 | Construction of Govt.Staff Quarter (Block-A) at DIET Complex | 1 | 439.2 | Project Division-I | 23.4.22 | 22.4.24 | 99% | 365.38 | 1% | 4.4 | 99% | 369.78 |  | EPC
6 | Construction of Rest House & Chowkider Quarter at PWD Complex Bilkhawthlir | % | 348.5 | Project Division-II | 15.12.20 | 28.02.23 | 100% | 392.69 | - | 1.3 | 100% | 393.99 | Work physically Completed
7 | Establishment of Company Headquarters at Vairengte |  | 200.53 | Project Division-II | 10.06.22 | 10.12.23 | 100% | 221.01 |  | 2.7 | 100% | 223.71 | Work completed
8 | Const.of MBSE New Building and renovation of existing main Building | % | 1000 | Project Division-III | 22.2.21 | 31.12.23 | 73% | 449.13 | 2% |  | 75% | 449.13 | Pandemic crisis delayed work progress. Now work is in progress | PWD Form-8
9 | Construction of Link Drain on Vaivakawn lui & Hunthar Biak In lui (Sh: Construction of Gabion Wall on Biak In Kawr & Vaivakawn kawr at Hunthar sinking) |  | 436.89 | Project Division-IV | 25.10.21 | 25.04.22 | 100% | 436.89 | - | - | 100% | 436.89 | Completed
10 | Improvement of Khanpui - Tualbung Road Phase-II |  | 2935.99 | Saitual Division | 25.03.18 | 15.6.22 | 83% | 2030.31 | - | 3 | 83% | 2033.31
11 | Strengthening of Saitual - Phullen Road (28.300 Km) (Tuivawl - Phullen) (28.700-57.000) |  | 1120 | Saitual Division | 18.12.19 | 18.04.21 | 100% | 800.01 |  |  | 100% | 800.01 | Phy. Completed
12 | Curve Improvement on ATL Road at Chainage 20.100 Kmp | Km | 10 | Hmuifang Division | 18.02.23 | 31.03.23 | 100% | 10 |  |  | 100% | 10 | Completed
13 | Resurfacing of PWD Staff Lodge Approach Road at Aibawk | Km | 10 | Hmuifang Division | 18.02.23 | 31.03.23 | 100% | 10 |  |  | 100% | 10 | Completed
14 | Resurfacing of Aizawl-Thenzawl-Lunglei Road (30.00 Kmp - 51.00 Kmp) | Km | 1271.17 | Hmuifang Division | 18.02.23 | 31.03.23 | 88% | 210.21 | 12% | 53.57 | 100% | 263.78 | Phy. Completed
15 | Bad patch repair of Aizawl-Thenzawl-Lunglei Road (83.00 Kmp-100.00 Kmp) | Km | 50 | Hmuifang Division | 18.12.23 | 31.03.23 | 100% | 50 |  |  | 100% | 50 | Completed
16 | Re-Construction of Hume pipe wing wall culvert at Ch.20.650 Kmp on Damdiai - Sialsuk Road (Location:20.650 Kmp) | No | 4.45 | Hmuifang Division | 18.12.23 | 31.03.23 | 100% | 4.45 |  |  | 100% | 4.45 | Completed
17 | Re-Construction of Hume pipe wing wall culvert at Ch.5.350 Kmp on Lungsei Road (Location:5.350 Kmp) | No | 6.5 | Hmuifang Division | 18.12.23 | 31.03.23 | 100% | 6.5 |  |  | 100% | 6.5 | Completed
18 | Patch Repair of Main Road at Thenzawl | Km | 25 | Hmuifang Division | 18.02.23 | 31.03.23 | 100% | 25 |  |  | 100% | 25 | Completed
19 | Patch repair of Dinthar Veng Internal road at Thenzawl | Km | 7.5 | Hmuifang Division | 18.02.23 | 31.03.23 | 100% | 7.5 |  |  | 100% | 7.5 | Completed
20 | Patch repair of Horticulture College approach road at Thenzawl | Km | 10 | Hmuifang Division | 18.02.23 | 31.03.23 | 100% | 10 |  |  | 100% | 10 | Completed
21 | Patch repair of Rawpuichhip-Buarpui Road 81.000-88.000 Kmp (Section : S.Khawlek to New Khawlek) | Km | 30 | Hmuifang Division | 18.02.23 | 31.03.23 | 100% | 30 |  |  | 100% | 30 | Completed
22 | Curve Improvement on ATL Road at Chaiage 17.700 Kmp | Km | 10 | Hmuifang Division | 18.02.23 | 31.03.23 | 100% | 10 |  |  | 100% | 10 | Completed
23 | Resurfacing of Doctor's Quarter Approach Road at Sialsuk | Km | 9 | Hmuifang Division | 18.02.23 | 31.03.23 | 100% | 9 |  |  | 100% | 9 | Completed
24 | Patch repair and resurfacing of Hualngohmun Internal Roads | Km | 20 | Hmuifang Division | 18.02.23 | 31.03.23 | 100% | 20 |  |  | 100% | 20 | Completed
25 | Patch repair of Kelsih Internal Roads | Km | 10 | Hmuifang Division | 18.02.23 | 31.03.23 | 100% | 10 |  |  | 100% | 10 | Completed
26 | Patch repair of Approach Road to Tachhip | Km | 10 | Hmuifang Division | 18.02.23 | 31.03.23 | 100% | 10 |  |  | 100% | 10 | Completed
27 | Patch repair of Muallungthu to Khumtung Road | Km | 20 | Hmuifang Division | 18.02.23 | 31.03.23 | 100% | 20 |  |  | 100% | 20 | Completed
28 | Patch repair of Aizawl-Thenzawl-Lunglei Road (63.00-71.00 Kmp) | Km | 35 | Hmuifang Division | 18.02.23 | 31.03.23 | 100% | 35 |  |  | 100% | 35 | Completed

## SEDP 4 (hidden)
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding: SEDP | [8 empty] | Month : May 2022
Sl. no | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the Month |  | Overall cumulative achievement |  | Remarks
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
25 | Widening of Road infront of CE, PWD Building at Tuikhuahtlang | 46.5 | Aizawl Road South Division |  |  | 100% | 46.5
26 | Const. of Approach Road to Aizawl College at Mualpui | 415 | Aizawl Road South Division |  |  | 35% | 120.12
27 | Const. of Approach Road to T.Romana College from ITI to Mualpui Road | 464.9 | Aizawl Road South Division |  |  | 49% | 171.33
28 | Wideing of Curve near Zokhuma's House on Bethlehem Vengthlang to College Road | 38.5 | Aizawl Road South Division |  |  | 100% | 38.5
29 | Const.of Approach Road to Zopar Vaipuanpho | 50 |  |  |  | 100% | 50
30 | Improvement at 0.50 Kmp on Hridaikawn to Power Sub Station at Tlangnuam | 12.3 | Aizawl Road South Division |  |  | 100% | 12.3
31 | Concrete pavement from Kohhran Thianghlim Biak In to PHE Pump House road within Maubawk | 30.5 | Aizawl Road South Division |  |  | 100% | 30.5
32 | Const.of Composite Retaining Wall at Kawilun Republic Veng | 7 | Aizawl Road South Division |  |  | 100% | 7
33 | Re-Construcrion of Retaining Wall near T.Lalhmuntiama's house on Nursery to Mission Veng Road via Kawltheihuan | 2.19 | Aizawl Road South Division |  |  | 100% | 2.19
34 | Const.of Bridge on Chhinga Vengthar to Tuithiang Road | 586.36 | Aizawl Road South Division |  |  | 59% | 60
35 | Widening of Approach road with rigid pavement from Thlanmual to Dam veng at Tlangnuam | 55 | Aizawl Road South Division |  |  | 100% | -

## CSS
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding: CSS | [9 empty] | Month : September 2023
Sl. no | Name of Work/Project | Unit | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[7 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Construction of Polytechnic at Lawngtlai (Const.of Administrative cum Academic Block) |  | 800 | Lunglei Building Project Division | 18.3.13 | 14.10.15 | 100% | 624.62 | - | - | 100% | 624.62 | Civil Work Completed & IE fund transferred to EE (EL) LLi for execution of I/E Works | Restricted
2 | Construction of Judicial Quarter at Lawngtlai Grade-I Qtr. |  | 110.58 | Lunglei Building Project Division | 8.6.20 | 7.12.21 | 86% | 64.75 | 9% | 2.49 | 95% | 67.24 | Work due to be completed during Oct/2023. I/E not yet transferred and EOT resubmitted for approval | Restricted Tender
3 | Construction of Judicial Quarter at Lawngtlai Type-I & II Qtr. |  | 138.67 | Lunglei Building Project Division | 22.6.20 | 21.11.21 | 95% | 34.73 | 5% | 1.52 | 100% | 36.25 | Work completed & IE not yet transferred and EOT resubmitted approval | Restricted Tender
4 | Const.of Administrative cum Academic Block for Polytechnic Thingsen Saiha |  | 501.08 | Lunglei Building Project Division | 15.03.16 | 11.7.17 | 60% | 103.76 | - | - | 60% | 103.76 | The contractor has stopped work due to no fund | Restricted Tender
5 | Const.of Hostel building for Polytechnic at Thingsen saiha |  | 191.83 | Lunglei Building Project Division | 15.3.16 | 11.04.17 | 80% | 80.41 | - | - | 80% | 80.41 | The contractor has stopped work due to no fund | Restricted Tender
6 | Construction of Staff Qtr Type I, II & III for Polytechnic at Thingsen Saiha |  | 77.1 | Lunglei Building Project Division | 06.10.15 | 20.4.17 | 100% | 61.04 |  | - | 100% | 61.04 | Civil work completed I/E not yet started. The contractor has stopped work due to no fund | Restricted Tender
7 | Const.of Type-IV Qtr for Polytechnic at Thingsen Saiha |  | 29.99 | Lunglei Building Project Division | 15.03.16 | 11.01.17 | 76.5% | 24.79 | - | - | 76.5% | 24.79 | The contractor has stopped work due to no fund | Restricted
8 | Construction of District Court Building at Saiha. |  | 1803.39 | Lunglei Building Project Division | 10.9.18 | 21.03.21 | 100% | 1803.395 |  |  | 100% | 1803.395 | Works completed on dt.28.4.23 and and handover paper already submitted to Client Dept. | Restricted Tender
9 | Construction of DC Office Building at Saiha |  | 610.11 | Lunglei Building Division | 31.10.18 | 28.11.23 | 86.5% | 414.49 | 0.2% |  | 87.2% | 414.49 | Works near to completion. Allocation of Balanced Fund of Rs.205.99 lakh is being awaited for completion of the whole projects i.e DC Office, DC Bungalow ETC. Revised estimate resubmitted for approval | Restricted Tender
10 | Construction of fast truck Court at Kolasib |  | 1375.74 | Project Division II | 20.09.22 | 20.09.24 | 35% | 237.47 | 2% | - | 37% | 237.47 | Work in progress
11 | Construction of Grade-I Judicial Quarters at Project Veng Kolasib | % | 215.58 | Project Division-II | 15.03.22 | 15.05.23 | 100% | 248.27 |  | 4.22 | 100% | 252.49 | Work Phy.completed
12 | Const.of Tourist Logde at Champhai | % | 270 | Project Division-III | 09.12.10 | 30.11.20 | 100% | 300 | - | - | 100% | 300 | Taken over by the Deptt.on Dt.3.8.2021 LOC amounting to Rs.30.00 lakh submitted for clearing liability.Hene, release of LOC awaited for financial closure.
13 | Const.of Polytechnic at Chhiahtlang i) Approach Road | % | 800 | Project Division-III | 3.3.16 | 2.8.16 | 100% | 103.67 | - | - | 100% | 103.67 | Estimate based on SOR 2019 submitted as per written instruction of the client department. Waiting for approval.
ii) Administrative & Academic Block iii) Hostel Block iv) Staff Quarters
14 | Construction of General Nursing Midwifery Hostel at Champhai | % | 250 | Project Division-III | 13.07.22 | 13.07.24 | 72% | 127.89 | 3% | 10.4 | 75% | 138.29 | Work in progress | PWD Form-8
15 | Construction of Hostel for S.T Girls at Champhai | % | 4652.75 | Project Division-III | 18.9.23 | 28.9.25 |  |  | 1% |  | 1% |  | Work in progress | PWD Form-8

## NH(o)
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : NH(O) - MoRTH | [10 empty] | Month : September 2023
Sl. No | Name of Work/Project | Unit | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummutive Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[7 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 78 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Construction of Steel Arch (Semi Through) Bridge with concrete Deck 90m Arch Span over River Tlawng at Km 5.200 on NH-44A In the State of Mizoram of EPC Mode (NHO) | Phy in % Fin in lakh | 4244 | NHD-I | 30.01.21 | 21.10.23 | 66.4% | 1423 |  | 452.57 | 66.4% | 1875.57 |  | EPC Mode
2 | Ordinary Repair (DPP) for short term maintenance from Km 0.00 to Km 42.80 and from Km 60.30 to km 130.00 on NH-150 in the state of Mizoram |  | 418 | NHD-II | 05.11.21 | 02.02.22 | 100% | 327.67 | - | - | 100% | 327.67 |  | Item Rate
3 | Land acquisition for 2-laning on NH-150 from Km 34/500 to 62/800 in the State of Mizoram | Km | 786 | NHD-II | April.2009 | March.2011 | 77% | 600.92 | - | - | 77% | 600.92 |  | N.A
4 | Special Repair to Bailey Bridge at Km 135/80 (River Luaklui) & 136850 (River Luakzal) of NH-150 in the State of Mizoram (job No. TA/150/MZ/20165-16/84) | m/ft | 27.3 | NHD-II | 25.11.19 | 25.11.19 | 100% | 14.2 | - | - | 100% | 14.2 |  | Depart mental
5 | Construction of 2 laning with paved shoulder flexible pavement from Km 42.80 to Km 60.30 of NH-150 road during 2016-17 within Mizoram State under NH(O) Scheme. (Job No. & Dtae of Sac Original/Revised : 150/MZ/2016-17/107) |  | 20594.82 | NHD-II | 29.11.17 | 22.05.21 | 100% | 13681.44 | - | - | 100% | 13681.44 | Phy. Completed | EPC Mode
6 | Reconstruction of single pavement from Km 130.00 to Km 140.00 on NH-150 in the State of Mizoram on EPC Mode (Job No.150/MZ/2019-20.119) |  | 3440.95 | NHD-II | 23.11.20 | 26.05.23 | 100% | 2441.16 | - | - | 100% | 2441.16 | Work under Defect Liability period | EPC Mode
7 | Consultancy Services for Project Management including prparation of Feasibility Study/Detailed {roject report fro laning with Paved Shoulders of stretches from Km 0/00 to Km 42/80 and from Km 60/00 to Km 140/00 on NH-150 NH (O) Package No. DPR/MZ/NER/2015/13 |  | 166.04 | NHD-II | 24.06.17 | 20.05.18 | 10% | 16.6 | - | - | 10% | 16.6 |  | MoRTH
8 | Periodical Renewal of NH-54 in the state of Mizoram under ARP for the year 2019-2020 between Km 118/00-133/00 Km (15.00Km) |  | 1477 | NHD-III | 20.04.21 | 20.04.22 1st Extension of Time = 96 dyas (19.4.22=14.6.22) | 100% | 1106 |  | 4.48 | 100% | 1110.48 | Completed | EPC
9 | Strengthening of Km 10.00 to Km 33.00 (Length 23.00 Km) on NH-306A including Strengthening & Construction of Retaining Walls and Culverts and Strenthening of 3 Nos.of Bailey Bridges in the State of Mizoram |  | 6523 | NHD-III | 07.02.22 | 07.08.23 | 100% | 2614 |  | 113.53 | 100% | 2727.53 | Completed | EPC

## Article 275
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : Article 275(1) of the Constitution | [10 empty] | Month : September 2023
Sl. No | Name of Work/Project | Unit | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummutive Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[7 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Construction of Tribal Hostel at Suangpuilawn, Mizoram | % | 320 | Project Division-IV | 12.08.23 | 12.08.25 | [6 empty] | Mobilisation in progress | Item Rate
2 | Construction of Multipurpose Community Hall at Darlawn, Mizoram | % | 720 | Project Division-IV | 12.08.23 | 12.08.25 | 0.06% |  | 2.24% |  | 2.3% |  | Work in progress | Item Rate

## ECRP-II
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : ECRP-II (Emergency Covid Response Package-II) | [10 empty] | Month : August 2023
Sl. No | Name of Work/Project | Unit | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummutive Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[7 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Construction of 50 Bedded critical care block at Champhai District Hospital Mizoram | % | 1346.4 | Project Division-III | 4.8.23 | 4.2.26 | 3% |  | 1% |  | 1% |  | Work in progress | PWD Form-8

## MAP
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding: Maintenance Action Plan | [9 empty] | Month : September 2023
Sl. no | Name of Work/Project | Unit | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the Month |  | Overall cumulative achievement |  | Remarks | Mode of Contract
[7 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Patch Repair and Full Resurfacing on Southern Gate of Raj Bhavan to E-in-C Office, Tuikhuahtlang | Rm | 38 | Aizawl Road South Division | - | - | [6 empty] | Works not yet started as LOC not yet received
2 | Patch Repair and Seal Coat on Kulikawn to Mission Veng Bazar | Rm | 10 | Aizawl Road South Division | 04.07.23 | 31.07.23 | 100% | 10 |  |  | 100% | 10 | Completed | Dept
3 | Junction Improvement with seal coat of road from YMA Hall to Liamduak at ITI Veng | Rm | 3 | Aizawl Road South Division | 04.07.23 | 20.07.23 | 100% | 3 |  |  | 100% | 3 | Completed | Dept
4 | Patch Repair and Resurfacing of Road from Pi Lalchawii (L) House to K.Lalramhmachhuana House at Bethlehem Vengthlang | Rm | 7 | Aizawl Road South Division | - | - | [6 empty] | Works not started due to Monsoon Season
5 | Patch Repair of Upper Republic Junction to Governor Gate | Rm | 1.5 | Aizawl Road South Division | 03.07.23 | 14.07.23 | 100% | 1.5 |  |  | 100% | 1.5 | Completed | Dept
6 | Seal Coating of Approach Road & Courtyard of MLA Hostel at Tuikhuahtlang | Rm | 1.76 | Aizawl Road South Division | 10.5.23 | 16.5.23 | 100% | 1.76 |  |  | 100% | 1.76 | Completed | Dept
7 | Estimate for Patch Repair of Approach Road to Reiek Tourist Resort | Rm | 5 | Aizawl Road South Division | - | - | [6 empty] | Works not started as LOC not yet received
8 | Patch Repair and Seal Coating of Aizawl-Reiek-W.Lungdar Road 0.000-6.000 Kmp | Rm | 18 | Aizawl Road South Division | [8 empty] | Works not started as LOC not yet received
9 | Patch Repair and Seal Coating of MHNL Section-III | Rm | 5 | Aizawl Road South Division | [8 empty] | Works not started as LOC not yet received
10 | Patch Repair and Seal Coating of Sikulpuikawn to City Hospital Road | Rm | 4 | Aizawl Road South Division | [8 empty] | Works not started as LOC not yet received
11 | Patch Repair and Seal Coating of Bungkawn YMA Road | Rm | 3 | Aizawl Road South Division | [8 empty] | Works not started as LOC not yet received
12 | Patch Repair and Seal Coating of T.Sangkuna Road at Dinthar Tlang Veng | Rm | 6 | Aizawl Road South Division | [8 empty] | Works not started as LOC not yet received
13 | Patch Repair and Seal Coating of Sub-way below Vanapa Hall | Rm | 2 | Aizawl Road South Division | 10.4.23 | 20.4.23 | 100% | 2 |  |  | 100% | 2 | Completed | Dept
14 | Patch Repair and Seal Coating of Lower Dinthar to Tuikual (Aichhinga Road) | Rm | 5 | Aizawl Road South Division | [8 empty] | Works not started as LOC not yet received
15 | Extension and repair of Hume Pipe Culvert on Tlangnuam CP Road near Tlangnuam Vengthar Presbyterian Church | Rm | 6 | Aizawl Road South Division | 13.7.23 | Connot specify due to Monsoon season | 30% |  |  |  | 30% |  | Works started in advance due to necessity. However, LOC not yet received
16 | Patch Repair and Resurfacing of Pika Road at Kulikawn | Rm | 5 | Aizawl Road South Division | 03.08.23 | 17.08.23 | 100% | 5 |  |  | 100% | 5 | Completed | Dept
17 | Patch Repair and Resurfacing of Kulikawn to Saikhamakawn via Hridaikawn (CP Road) Road (Section: 1.000-1.874 Km) | Rm | 6 | Aizawl Road South Division | [8 empty] | Works not started as LOC not yet received
18 | Reconstruction of Culvert at CP Road, Tlangnuam | Rm | 5.6 | Aizawl Road South Division | 3.7.23 | Connot specify due to Monsoon season | 40% |  |  |  | 40% |  | Works started in advance due to necessity. However, LOC not yet received | Dept
19 | Resurfacing of approach road to Zobawm at Kulikawn | Rm | 5 | Aizawl Road South Division | [8 empty] | Works not started as LOC not yet received
20 | Resurfacing of Hridaikawn to Power Sub-Station Road at Tlangnuam | Rm | 15 | Aizawl Road South Division | 25.4.23 | 6.6.23 | 100% | 15 |  |  | 100% | 15 | Completed | Dept
21 | Construction of CD works with cover between Pu Ngura Sailo and Pu Remruata's House on Saikhamakawn - Tlangnuam Road | Rm | 3.5 | Aizawl Road South Division | [8 empty] | Works not started as LOC not yet received
22 | SUB DIVISION-II Re-surfacing of DC Workshop to NH-54 via Chaltlang Lily Veng | Km | 20 | Aizawl Road North Division | 29.5.23 | 31.5.23 | 100% | 20 |  |  | 100% | 20 | Completed | Depart mental
23 | Patch Repair of Leitan -Agape (Lower & Upper) Ring Road | Km | 7 | Aizawl Road North Division | 17.7.23 | 19.7.23 | 100% | 3.1 |  |  | 100% | 3.1 | Phy. Completed | Depart mental
24 | Patch Repair & Seal Coating of Pema Road at Ramhlun North | Km | 1.5 | Aizawl Road North Division | 17.7.23 | 18.7.23 | 100% | 0.73 |  |  | 100% | 0.73 | Phy. Completed | Depart mental
25 | Approach Road to Durtlang Cemetery | Km | 12 | Aizawl Road North Division | 5.6.23 | 8.6.23 | 100% | 12 |  |  | 100% | 12 | Phy. Completed | Depart mental
26 | SUB DIVISION-III Re-surfacing of Lower Kanan to Dawrpui Vengthar | Rm | 11.43 | Aizawl Road North Division | 17.7.23 | 15.8.23 | 100% | 10.95 |  |  | 100% | 10.95 | Phy. Completed | Depart mental
27 | Re-surfacing of Balance portion of 7th Day Hospital to Ebenezer | Rm | 10.72 | Aizawl Road North Division | 24.7.23 | 22.8.23 | 100% | 10.56 |  |  | 100% | 10.56 | Phy. Completed | Depart mental
28 | Re-surfacing of Approach Road to AICS Shekina Hills Tanhril | Rm | 15.2 | Aizawl Road North Division | 17.3.23 | 15.8.23 | 100% | 10.6 |  |  | 100% | 10.6 | Phy. Completed | Depart mental
29 | Resurfacing of road from Pu Rfa's Kawn to Primary School including Construction of Rigid Pavement (PCC) at Tanhril | Rm | 25.05 | Aizawl Road North Division | 17.3.23 | 16.8.23 | 100% | 17.4 |  |  | 100% | 17.4 | Phy. Completed | Depart mental
30 | Patch repair of Chhangurkawn to High Court road | Rm | 40 | Aizawl Road North Division | 17.3.23 | 16.8.23 | 100% | 38.3 |  |  | 100% | 38.3 | Phy. Completed | Depart mental
31 | Re-Surfacing of Zonuam Police Outpost to Ainawn | Rm | 15 | Aizawl Road North Division | 17.3.23 | 16.8.23 | 100% | 14.36 |  |  | 100% | 14.36 | Phy. Completed | Depart mental
32 | Strengthening & Resurfacing of Zobawk Dispensary Approach Road (NH 54A Zobawk - PHC Zobawk) (Balance Portion) | Km | 5.02 | Hnahthial Division
33 | Re-Surfacing of Approach Road to Laveng, Haulawng (0.00-1.400Kmp) | Km | 12.92 | Hnahthial Division
34 | Extension of Wing Wall on Haulawng Bualpui 'V' upto Chhipphir Road (Chainage : 10.000 & 10.600 Kmp) | Km | 7.81 | Hnahthial Division |  |  |  |  | 100% |  | 100%
35 | Re-Surfacing of Approach Road from BRTF canteen to Helipad upto ICDS Office at Hnahthial | Km | 8.31 | Hnahthial Division
36 | SMBT of Approach Road from Pu Sangkunga House to Pu Lalsiama House Peniel Veng Hnahthial | Km | 13.89 | Hnahthial Division
37 | Resurfacing of Approach Road from Pu Sangkunga House to Pu Lalsiama House Peniel Veng Hnahthial | Km | 6.25 | Hnahthial Division
38 | Repair of Thingsai Shortcut Road | Rm | 5.61 | Hnahthial Division |  |  |  |  | 100% |  | 100%
39 | Re-Surfacing of Approach Road from Pu F.Zosangliana House to Pu F.Lalduhawma House via Model Veng, Hnahthial | Km | 17.88 | Hnahthial Division
40 | PWD SDO Quarter Approach Road at Hnahthial (IB Main Road to PWD SDO Qtr) | Km | 3.31 | Hnahthial Division

## LLBPR
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
IMPROVEMENT OF LUNGLEI TOWN ROAD 2022-2023 (ILTR ) | [8 empty] | Month : February 2023
Sl. no | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the Month |  | Overall cumulative achievement |  | Remarks
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
1 | Approach Road to Kendrya School at Ramthar Veng (Nursing School Approach Road Kendrya School Ramthar Veng) | 38.98 | Lunglei Road Division I |  |  | - | - | - | - | - | - | Not Yet Started
2 | Strengthening of Paveement from Kikawn to AOC at Selected Stretches | 50.68 | Lunglei Road Division I |  |  | - | - | - | - | - | - | Not Yet Started
3 | JB Press to Sobji Bazar (0.00-0.307) | 6.17 | Lunglei Road Division I |  |  | - | - | 50% | - | 50% | - | Work in Progress
4 | Parallel Road from Pu Lalpara's House to Presbyterian church ( Part I ) | 15.22 | Lunglei Road Division I |  |  | - | - | - | - | - | - | Not Yet Started
5 | AOC to District Road ( AOC Ramthar District Road ) | 6.78 | Lunglei Road Division I |  |  | - | - | - | - | - | - | Not Yet Started
6 | MAP Complex Internal Road ( Commanding Bungalow to Thangte Peng | 22.37 | Lunglei Road Division I |  |  | - | - | - | - | - | - | Not Yet Started
7 | Z.Rosanga Road at Lunglawn ( NH 54A Z. Rosanga;s House ) | 3.37 | Lunglei Road Division I |  |  | - | - | - | - | - | - | Not Yet Started
8 | NH 54A to Lunglawn Hmunhlui Tlang via Pu H.Lalzarliana;s House (NH 54A Main Road PC Thlamuana's House ) | 2.41 | Lunglei Road Division I |  |  | - | - | 45% | - | 45% | - | Work in Progress
9 | JH Lalduhawma's House to Venghlun Cemetry Venghlun | 19.12 | Lunglei Road Division I |  |  | - | - | - | - | - | - | Not Yet Started
10 | Sserkawn Hospital to DIET, Melte, Lunglei. ( 0.00-1.350kmp ) | 28.18 | Lunglei Road Division I |  |  | - | - | - | - | - | - | Not Yet Started
11 | Patch repair & Re-surfacing of VCP Hall Serkawn to Chawngbawla Point Zotlang ( 0.00-1.590 kmp ) | 31.65 | Lunglei Road Division I |  |  | - | - | - | - | - | - | Not Yet Started
12 | Patch repair & Re-surfacing of Zohnuai Approach Road ( 0.00-0.50 kmp ) | 12.55 | Lunglei Road Division I |  |  | - | - | - | - | - | - | Not Yet Started
13 | Centenary Road Serkawn ( Serkawn Christian Hospital, Serkawn Pastor Quarters (0.00-0.540 ) | 10.93 | Lunglei Road Division I |  |  | - | - | - | - | - | - | Not Yet Started
14 | Approach Road to LDSC Ground No.II from District Road (District Road LDSC Ground No II | 5.03 | Lunglei Road Division I |  |  | - | - | - | - | - | - | Not Yet Started
15 | Salem Internal Road ( NH 54A to District Road ) | 11.63 | Lunglei Road Division I |  |  | - | - | 60% | - | 60% | - | Work in Progress
16 | Falkawn to District Road (Falkawn District Road) | 10.56 | Lunglei Road Division I |  |  | - | - | - | - | - | - | Not Yet Started
17 | Ramthar Veng Baptist Church Ring Road (AOC Ramthar Mazaras Spare Parts) | 4.97 | Lunglei Road Division I |  |  | - | - | - | - | - | - | Not Yet Started
18 | Resurfacing of MRB Junction to Mini Sport Complex Bunghmun | 6.76 | Lunglei Road Division I |  |  | - | - | - | - | - | - | Not Yet Started
19 | Resurfacing of MRB Junction to Falkawn Bunghmun | 13.53 | Lunglei Road Division I |  |  | - | - | - | - | - | - | Not Yet Started
20 | Resurfacing of District Road | 87.87 | Lunglei Road Division I |  |  | - | - | - | - | - | - | Not Yet Started
21 | esurfacing of Rahsi Veng to Tlabung Road via Sazaikawn (Forest Check Gate Tlabung Kawng) | 105.02 | Lunglei Road Division I |  |  | - | - | - | - | - | - | Not Yet Started
22 | Ressurfacing of LP Thangzika Shop to Forest Check Gate (LP Thangzika Shop to Forest Check Gate) | 37.2 | Lunglei Road Division I |  |  | - | - | - | - | - | - | Not Yet Started
23 | Resurfacing of Parallel Road from Pu Lalpara's House to Presbyterian Chucrh (Part 2) | 111.56 | Lunglei Road Division I |  |  | - | - | - | - | - | - | Not Yet Started
24 | Approach Road DC's Office From MST Bus Station (MST Bus Station DC Office) | 1.94 | Lunglei Road Division I |  |  | - | - | - | - | - | - | Not Yet Started
25 | Mizoram Rural Bank to DC Office via LAD Office (Mizoram Rurak Bank DC Office) | 4.88 | Lunglei Road Division I |  |  | - | - | - | - | - | - | Not Yet Started
26 | SE PWD Residence Approach Road (DCs Office SE Office) | 2.39 | Lunglei Road Division I |  |  | - | - | - | - | - | - | Not Yet Started
27 | DC Residence From SE PWD Qtr.Approach Road (SE PWD Qts DC Residence) | 0.73 | Lunglei Road Division I |  |  | - | - | - | - | - | - | Not Yet Started
28 | Damkawng Theiriat Road (C.Thangkimas House to Lalfakkimas House) | 3.47 | Lunglei Road Division I |  |  | - | - | - | - | - | - | Not Yet Started
29 | AOC to Kikawn Road | 49.31 | Lunglei Road Division I |  |  | - | - | - | - | - | - | Not Yet Started
30 | Construction of Retaining Wall on ATL Road to Kawmzawl Helipad Road Pukpui (At Ch=400.00m) | 3.51 | Lunglei Road Division I |  |  | - | - | - | - | - | - | Not Yet Started
31 | Construction of Breast Wall at 0.120 Kmp on Approach Road to Kendria School, Lunglei | 30.5 | Lunglei Road Division I |  |  | - | - | - | - | - | - | Not Yet Started
32 | Construction of Retaining Wall at 0.600 Kmp on Tlabung Peng to Colony PWD Road (Boundary of Venghlun and Rahsiveng) | 8.29 | Lunglei Road Division I |  |  | - | - | 30% | - | 30% | - | Work in Progress
33 | Construction of Retaining Wall at 1.100Kmp on 2nd Parallel Road, Bazar Veng, Lunglei | 6.86 | Lunglei Road Division I |  |  | - | - | 45% | - | 45% | - | Work in Progress
34 | Construction of Retaining Wall at 1.48 Kmp on Sangchem Road | 17.66 | Lunglei Road Division I |  |  | - | - | 50% | - | 50% | - | Work in Progress
35 | Retaining Wall of PWD Complex Bunghmun | 8.46 | Lunglei Road Division I |  |  | - | - | 100% | 8.46 | 100% | 8.46 | Completed
36 | Construction of Retaining Wall at Ch:31.500 Kmp on Lunglei to Buarpui Road | 29.64 | Lunglei Road Division I |  |  | - | - | 66% | 19.64 | 66% | 19.64 | Work in Progress
37 | Improvement of drainage system from Kikawn to AOC (Culverts & Cross drainage) | 34.53 | Lunglei Road Division I |  |  | - | - | - | - | - | - | Not Yet Started
38 | Construction of Retaining Wall at Ch:18.450 Kmp on Lunglei to Buarpui Road | 7.98 | Lunglei Road Division I |  |  | - | - | 68% | 5.41 | 68% | 5.41 | Work in Progress
39 | Construction of Retaining Wall at 18.500Kmp on Lunglei to Buarpui Road | 4.9 | Lunglei Road Division I |  |  | - | - | 67% | 3.31 | 67% | 3.31 | Work in Progress

## PM DeVINE
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : PM-DeVINE | [10 empty] | Month : September 2023
Sl. No | Name of Work/Project | Unit | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummutive Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of Contract
[7 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Construction of Bamboo Link Road from Lengpui to Saiphal Bamboo Plantation (41 Km) under PM-DeVINE | Phy in % Fin in lakh | 4941 | NHD-I | 21.07.23 | 19.01.25 | [6 empty] | Mobilisation in progress | EPC Mode

## DIPHR
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : DIPHR (ICMR) | [10 empty] | Month : September 2023
Sl. No | Name of Work/Project | Unit | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummutive Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of Contract
[7 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Construction of Model Rural Health Research Units at Lungtian Ram, Aibawk | % | 169.89 | Project Division-II | 21.09.23 | 21.03.25 | [6 empty] | Work just started

## Ministry
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : Ministry of Tribal Affairs | [10 empty] | Month : September 2023
Sl. No | Name of Work/Project | Unit | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummutive Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of Contract
[7 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Construction of Auditorium at Pukpui Lunglei |  | 523 | Lunglei Building Project Division | 16.9.23 | 16.01.25 |  |  | 5% |  | 5% |  | Work started | Retsricted Tender

## Interstate
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : Interstate Connectivity | [10 empty] | Month : September 2023
Sl. No | Name of Work/Project | Unit | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummutive Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of Contract
[7 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Road construction of Mizoram-Assam Interstate Border (Sh: Hlimen to Serlui Tuikhuah) Group-I
| 1) Excavation in soil by Mechanical means | Cum | 68.43 | Kolasib Division | 10.08.23 | 31.01.24 | 80% |  | 20% | 68.43 | 100% | 68.43
| 2) Excavation in Ordinary Rock by Mechanical means | Cum | 50.29 | Kolasib Division | 10.08.23 | 31.01.24 | 80% |  | 20% | 50.2 | 100% | 50.2
2 | Road construction of Mizoram-Assam Interstate Border (Sh: New Builum to Chemtlang Zau) Grou-2 (Phse-I & III)
| 1) Excavation of soil by Mechanical means | Cum | 54.59 | Kolasib Division | 10.08.23 | 31.01.24 | 60% |  | 40% | 54.59 | 100% | 54.59
| 5) Excavation in Ordinary Rock by Mechanical means | Cum | 62.36 | Kolasib Division | 10.08.23 | 31.01.24 | 60% |  | 40% | 45.69 | 100% | 45.69

## NLCPR
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : NLCPR | [10 empty] | Month : September 2023
Sl. No | Name of Work/Project | Unit | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[7 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Construction of Community Hall at Various place in Mizoram | % | 206.49 | Project Division-III | 22.2.12 | 30.11.19 | 100% | 186.01 | - | - | 100% | 186.01 | Completed and balance fund of Rs.20.48 (Rs.16.35 lakhs NLCPR + Rs.4.13 lakhs SMS) a waited for clearing liabilities

## NEDP
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : NEDP | [10 empty] | Month: September 2023
Sl. No | Name of Work/Project | Unit | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[7 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Construction of Market Shed at Rahsi Veng Lunglei |  | 182.22 | Lunglei Building Project Division | 16.12.19 | 15.12.20 | 100% | 130 | - | - | 100% | 130 | Work handed over to the client Dept.and Liabilities of amount Rs.52.0 lakhs has been cleared from SASCI from 2022-2023 | Restricted Tender
2 | Construction of Officers & Staff Quarter Type-IV, 2 Units and Type-III 4 Units for Taxation Department Lunglei |  | 330 | Lunglei Building Project Division | 3.7.20 | 3.6.22 | 88% | 161.35 | 2% |  | 90% | 161.35 | Work almost completed. I/E Fund not yet transferred and will be transferred as soon as D-III permission is received from Finance Dept. EOT received and extended upto Dt.31.10.23 | Restricted Tender
3 | Construction of DC Bangalow Type-VI at Saiha |  | 110.9 | Lunglei Building Division | 26.11.08 | 26.11.19 | 80.5% | 92.01 | 0.2% | - | 80.7% | 92.01 | Works near to completion. Allocation of Fund for remaining balanced work is being awaited from the government. EOT under process | Restricted Tender
4 | Improvement of Buarpui - Bunghmun - via Thenhlum Road (65.000-79.00) Kmp during 2016-2017 | Km | 1000 | Lunglei Road Division-I | 17.5.17 | 31.3.23 | 74% | 870.29 | - | - | 74% | 870.29 | Contract work is terminated and joint inspection with contractors will be done on balance work
5 | Resurfacing of MRB Junction to Mini Sport Complex | Km | 5.93 | Lunglei Road Division-I |  |  | 100% | 5.93 |  |  | 100% | 5.93 | Completed
6 | Resurfacing of MRB Junction to Falkawn Bunghmun | Km | 11.87 | Lunglei Road Division-I |  |  | 100% | 11.87 |  |  | 100% | 11.87 | Completed
7 | Retaining Wall of PWD Complex Bunghmun | Km | 7.42 | Lunglei Road Division-I |  |  | 100% | 7.42 |  |  | 100% | 7.42 | Completed
8 | Strengthening of Pavement from Kikawn to AOC at Selected stretches | Km | 44.46 | Lunglei Road Division-I |  |  | 100% | 44.46 |  |  | 100% | 44.46 | Completed
9 | Serkawn Hospital to DIET, Melte (Christian Hospital Serkawn to DIET, Lunglei (0.00 - 1.590Kmp) | Km | 24.72 | Lunglei Road Division-I |  |  | 100% | 24.72 |  |  | 100% | 24.72 | Completed
10 | Patch Repair & Resurfacinf of YPC Hall Serkawn to Chawngbawla Point Zotlang (0.00-1.590Kmp) | Km | 27.76 | Lunglei Road Division-I |  |  | 100% | 27.76 |  |  | 100% | 27.76 | Completed
11 | Patch Repair & Resurfacinf of Zohnuai approach road (0.00-0.50Kmp) | Km | 11.01 | Lunglei Road Division-I |  |  | 100% | 11.01 |  |  | 100% | 11.01 | Completed
12 | Centenary Road Serkawn (Serkawn Christian Hospital, Serkawn Pastor Quarters (0.00-0.540) | Km | 9.59 | Lunglei Road Division-I |  | 2023-11-01 | 50% | 9.59 |  |  | 50% | 9.59 | Not yet completed
13 | AOC to Kikawn | Km | 43.25 | Lunglei Road Division-I |  |  | 100% | 43.25 |  |  | 100% | 43.25 | Completed
14 | Construction of Retaining Wall on ATL Road to Kawmzawl Helipad Road Pukpui (At Ch=400.00m) | Km | 3.08 | Lunglei Road Division-I |  |  | 100% | 3.08 |  |  | 100% | 3.08 | Completed
15 | Improvement of Drainage System from Kikawn to AOC (Culverts & Cross drainage) | Km | 30.29 | Lunglei Road Division-I |  |  | 100% | 30.92 |  |  | 100% | 30.92 | Completed
16 | Approach Road to Kendriya School at Ramthar Veng (Nursing School Approach Road Kendriya School Ramthar Veng) | Km | 34.21 | Lunglei Road Division-I |  | 2024-03-01 | 17.51% |  |  |  | 17.51% |  | Only widening completed
17 | JB Press to Sobji Bazar (0.000-0.307 Kmp) | Km | 5.41 | Lunglei Road Division-I |  |  | 100% | 5.41 |  |  | 100% | 5.41 | Completed
18 | AOC to District Road (AOC Ramthar District Road) | Km | 5.95 | Lunglei Road Division-I |  |  | 100% |  |  | 5.95 | 100% | 5.95 | Completed
19 | MAO Complex Internal Road (Caommandant Bungalow to Thangte Peng) | Km | 19.62 | Lunglei Road Division-I |  |  | 100% |  |  | 19.62 | 100% | 19.62 | Completed
20 | R.Zosanga Road at Lunglawn (NH-54A Z.Rosanga's House) | Km | 2.96 | Lunglei Road Division-I |  |  | 100% | 2.96 |  |  | 100% | 2.96 | Completed
21 | NH 54A to Lunglawn Hmunhlui Tlang via Pu H.Lalzarliana's House (NG 54A Main Road PC Thlanmual's House) | Km | 2.11 | Lunglei Road Division-I |  |  | 100% | 2.11 |  |  | 100% | 2.11 | Completed
22 | Parallel Road from Pu Lalpara's House to Prebyterian Church (Part 1) | Km | 13.35 | Lunglei Road Division-I |  |  | 100% | 13.35 |  |  | 100% | 13.35 | Completed
23 | Approach Road to LDSC Ground No II from District Road (District Road LDSC Ground No II) | Km | 4.41 | Lunglei Road Division-I |  |  | 100% | 4.41 |  |  | 100% | 4.41 | Completed
24 | Salem Internal Road (NH 54A to District Road) | Km | 10.2 | Lunglei Road Division-I |  |  | 100% | 10.2 |  |  | 100% | 10.2 | Completed
25 | Falkawn to District Road (Falkawn District Road) | Km | 9.26 | Lunglei Road Division-I |  |  | 100% | 9.26 |  |  | 100% | 9.26 | Only Pothole repair Completed
26 | Ramthar Veng Baptist Church Ring Road (AOC Ramthar Mazara's Spare Parts) | Km | 4.36 | Lunglei Road Division-I |  |  | 100% | 4.36 |  |  | 100% | 4.36 | Completed
27 | Resurfacing of Approach Road DCs Office from MST Bus Station (MST Bus Station DC Office) | Km | 12.44 | Lunglei Road Division-I |  |  | 100% | 12.44 |  |  | 100% | 12.44 | Completed
28 | Reusrfacing of Mizoram Rural Bank to DC Office via LAD Office (Mizoram Rural Bank DC Office) | Km | 13.35 | Lunglei Road Division-I |  |  | 100% | 13.35 |  |  | 100% | 13.35 | Completed
29 | Resurfacing of District Road | Km | 113.74 | Lunglei Road Division-I |  |  | 100% | 113.74 |  |  | 100% | 113.74 | Completed
30 | Resurfacing of LP Thangzika's Shop to Forest Check Gate) | Km | 53.19 | Lunglei Road Division-I | [8 empty] | Only Pothole repair completed
31 | Resuirfacing of Parallel Road from Pu Lalpara's House to BCM Kikawn Biak In (Part 2) | Km | 97.86 | Lunglei Road Division-I |  |  | 100% | 97.86 |  |  | 100% | 97.86 | Completed
32 | Resurfacing of Rahsi Veng to Tlabung Road via Sazaikawn (Forest Check Gate to Tlabung Kawng) | Km | 12.83 | Lunglei Road Division-I |  |  | 100% | 12.83 |  |  | 100% | 12.83 | Completed
33 | Resurfacing of Rahsi Veng to Tlabung Road via Sazaikawn (Forest Check Gate to Tlabung Kawng) | Km | 22.07 | Lunglei Road Division-I | [8 empty] | Only Pothole repair Completed
34 | SE PWD Residence Approach Road (DC's Office SE Office) | Km | 2.1 | Lunglei Road Division-I |  |  | 100% | 2.1 |  |  | 100% | 2.1 | Completed
35 | DC Residence from SE PWD Qtr Approach road (SE PWD Qtr DC Residence) | Km | 0.64 | Lunglei Road Division-I |  |  | 100% | 0.64 |  |  | 100% | 0.64 | Completed
36 | Construction of Breast Wall at 0.120Kmp on approach road to Kendryia School Lunglei | Km | 26.75 | Lunglei Road Division-I |  |  | 100% | 26.75 |  |  | 100% | 26.75 | Completed
37 | Construction of Retaining Wall at 0.600 Kmp on Tlabung Peng to Colony PWD Road (Boundary of Venghlun and Rahsi veng) | Km | 7.27 | Lunglei Road Division-I |  |  | 100% | 7.27 |  |  | 100% | 2.27 | Completed
38 | Construction of Retaining Wall at 1.100Kmp on 2nd Parallel Road, Bazar Veng, Lunglei | Km | 6.02 | Lunglei Road Division-I |  |  | 100% | 6.02 |  |  | 100% | 6.02 | Completed
39 | Construction of Retaining Wall at 1.48 Kmp on Sangchem Road | Km | 15.49 | Lunglei Road Division-I |  |  | 100% | 15.49 |  |  | 100% | 15.49 | Completed
40 | Construction of Retaining Wall at Ch:18.450Kmp on Lunglei to Buarpui Road | Km | 26 | Lunglei Road Division-I |  |  | 100% | 26 |  |  | 100% | 26 | Completed
41 | Construction of Retaining Wall at Ch: 18.450Kmp on Lunglei to Buarpui Road | Km | 7 | Lunglei Road Division-I |  |  | 100% | 7 |  |  | 100% | 7 | Completed
42 | Construction of Retaining Wall at 18.500Kmp on Lunglei to Buarpui Road | Km | 4.3 | Lunglei Road Division-I |  |  | 100% | 4.3 |  |  | 100% | 4.3 | Completed
43 | Construction of Multi Level Parking cum Basketball Court beside the main Building | 1 | 541.8 | Project Division-I | 5.12.19 | 31.1.23 | 100% | 541.8 |  |  | 100% | 541.8 | Completed | EPC
44 | Const.of Bridge on Chhinga Vengthar to Tuithiang Road | Rm | 586.36 | Aizawl Road South Division | 19.04.21 | 31.10.22 | 100% | 200 | - |  | 100% | 200 | Phy.Work completed | Item Rate Contract

## STATE
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : STATE | [10 empty] | Month : September 2023
Sl. No | Name of Work/Project | Unit | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[7 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Construction of Laboratory Building at Civil Hospital Lunglei Ground Floor |  | 192.98 | Lunglei Building Project Division | 28.10.21 | 28.10.22 | 100% | 192.98 | - |  | 100% | 192.98 | Completed | Restricted Tender
2 | Construction of Laboratory Building at Civil Hospital Lunglei (1st & 2nd Floor) Supplementary Works |  | 396 | Lunglei Building Project Division | 28.10.22 | 28.4.24 | 60% | 163.63 | 3% |  | 63% | 163.63 | Work in progress. Allocation of Balanced Fund of Rs.198.00 lakh awaited from the government | Restricted Tender

## SPA
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : SPA | [10 empty] | Month: September 2023
Sl. No | Name of Work/Project | Unit | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[7 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Construction of District Transport Office at Lawngtlai |  | 228 | Lunglei Building Project Division | 27.9.16 | 27.9.17 | 100% | 189.69 | - | 30.01 | 100% | 219.7 | Completed on Dt.31.01.20 Allocxation of Balanced Fund of Rs.38.31 lakh received and liabilities being cleared from division office | Restricted Tender
2 | Construction of DC of State Tax Office & Staff Quarters at Saiha |  | 408.37 | Lunglei Building Project Division | 25.10.19 | 15.11.23 | 100% | 408.28 | - |  | 100% | 408.28 | Works completed and handed over to the client department on 7/7/23 and inaugurated on 20/7/2023

## SPP
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : SPP | [10 empty] | Month : September 2023
Sl. No | Name of Work/Project | Unit | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[7 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Construction of Office Building for IF & SL at Tuikhuahtlang | % | 401.18 | Project Division-III | 13.7.20 | 11.06.23 | 95% | 323.94 | 0.5% |  | 95.5% | 323.94 | Work in progress | PWD Form-8 EOT under processed
2 | Construction of Circuit House at Serchhip | % | 358.18 | Project Division-III |  |  | - | - | - | - | - | - | Estimate amounting to Rs.3.58 Cr submitted as per new drawing. Waiting for approval for tender.
3 | Construction of Truckable Road between Tlangpui and Lungva |  | 480 | Khawzawl Division | 5.7.18 | 5.7.19 | 63% | 327.23 | - | - | 63% | 327.23 | EOT granted upto 7.10.2020 | Item rate contract

## DONER
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : One Time Special Assistance under Ministry of DONER | [10 empty] | Month : September 2023
Sl. No | Name of Work/Project | Unit | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[7 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Re-Construction of safe House at Tlabung |  | 114.9 | Lunglei Building Project Division | 18.11.21 | 18.11.22 | 100% | 106.83 | - | 0.83 | 100% | 107.66 | Civil Works completed. Fund for IE has been transferred Handover in process | Restricted Tender
2 | Re-Construction of safe shelter at Sairang | % | 96.58 | Project Division-II | 13.11.21 | 13.11.22 | 100% | 79.7 | - | - | 100% | 79.7 | Work physically completed

## NERSDS
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : NERSDS | [10 empty] | Month : September 2023
Sl. No | Name of Work/Project | Unit | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[7 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Upgradation of Saiha-Lungbun-Tluangram-Haka Road in the State of Mizoram |  | 4307.95 | Saiha Division | 8.7.19 | 16.3.23 | 55.02% | 1947 | 0.23% |  | 55.25% | 1947 | 1.Work in progress. 2. Incessant rainfall has disrupted progress of work
2 | Upgradation of Hnahlan-Hmunhlui-Tuimang-Singngei Road (Length = 12.000 Kms) |  | 3845.19 | Champhai Division | 29.11.21 | 28.4.23 | 62.15% | 1713.13 | 1.61% | 483.62 | 63.76% | 2196.75 | In progress
3 | Upgradation of Zote-Fartlang-Buanli-Tuipui-Tawnzang Road in the state of Mizoram under NERSDS (Length = 8.00 Kms) |  | 2547.32 | Champhai Division | 12.12.21 | 11.5.23 | 70% | 1465.42 | 0.05% |  | 70.05% | 1465.42 | In progress

## ISC Scheme
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : ISC Scheme & EI | [10 empty] | Month : September 2023
Sl. No | Name of Work/Project | Unit | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of Contract
[7 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Improvement of Tuipuibari - W.Kawnpui Road and ISC (0.00-9.00 Kmp) |  | 4870 | Mamit Division | 20.3.20 | 20.3.22 | 72% | 3246.44 | 2% | 731.86 | 74% | 3978.3 | Work in progress | EPC

## CRF
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : CRF | [10 empty] | Month : September 2023
Sl. No | Name of Work/Project | Unit | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[7 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Construction of Two Lane from Sihhmui-Ramrikawn Road (Stage-I) |  | 8000 | Aizawl Road North Division | 1.10.18 | 1.10.20 | 92.28% | 4620.81 |  |  | 92.28% | 4620.81 | In progress
2 | Construction of BUG Bridge over Tlawng on Aizawl-Reiek-W.Lungdar Road at 14.800 Kmp | Rm | 757.56 | Aizawl Road South Division | 1.10.18 | 31.3.22 | 85% | 488.56 | 0.2% |  | 85.2% | 488.56 | Work in progress | EPC Mode
3 | Construction of Muallungthu-Lungphun Road |  | 5996 | Hmuifang Division | 23.11.17 | 23.11.19 | 33.39% | 1940.67 | - | - | 33.39% | 1940.67 | Work in progress
4 | Widening to single lane with geometric imprivement & Upgradation of Chhiahtlang-Lamchhip Road |  | 6668.18 | Hmuifang Division | 23.6.17 | 23.06.19 | 100% | 6283.78 | - |  | 100% | 6283.78 | Completed
5 | Construction of double lane BUSC Girder Bridge over R.Tuichang on Keitum-Artahkawn Road |  | 754.75 | Serchhip Division | 1.12.16 | 31.3.23 | 100% | 698.67 |  | 55.28 | 100% | 753.95 | Completed | Item rate
6 | Construction of Chakkhei to Siasi Road (Permanent Work) (0.00-20.00 Kmp) |  | 1216.88 | Saiha Division | 8.7.19 | 30.9.23 | 97.03% | 450.43 |  | 405.95 | 97.03% | 856.38 | Work in progress | Item rate contract
7 | Construction of Chakkhei to Siasi Road (FC&Pavement Work) (0.00-20.00 Kmp) |  | 3505.54 | Saiha Division | 8.7.19 | 11.11.23 | 98.55% | 2277.26 |  | - | 98.55% | 2277.26 | Work in progress | Item rate contract

## NESIDS
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : NESIDS | [10 empty] | Month : September 2023
Sl. No | Name of Work/Project | Unit | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[7 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Construction of 2 Residential Hostel at ZMC (Boys) | % | 1000 | Project Division-II | 14.10.21 | 29.10.23 | 92% | 904.05 | 3% |  | 95% | 904.05 | Work in progress
2 | Construction of 2 Residential Hotel at ZMC (Girls) | % | 1000 | Project Division-II | 14.10.21 | 27.10.23 | 76% | 557.84 | 4% |  | 80% | 557.84 | Work in progress
3 | Construction of 100 Bedded Distict Hospital at Kolasib | % | 1859.87 | Project Division-II | 23.09.22 | 23.09.24 | 23% | 458.26 | 2% |  | 25% | 458.26 | Work in progress
4 | Construction of State Resource Centre for HIV/AIDS at Aizawl | % | 360.51 | Project Division-II | 22.09.22 | 22.09.24 | 20% | 96.8 | 3% |  | 23% | 96.8 | Work in progress
5 | Improvement /Upgradation of Operational/Non-operational facilities of Lengpui Aiport (elevated Road with connected components of Terminal Building) | % | 1959 | Project Division-III | 30.9.21 | 4.12.23 | 88% | 1317.31 | 1% |  | 89% | 1317.31 | Pandemic crisis delayed work progress. Now work is in progress | PWD Form-8
6 | Improvement & Upgradation of Lawngtlai-Tuipui ferry Road under NESIDS |  | 2897.8 | Lawngtlai Division | 08.08.19 | 08.02.21 | 100% | 2666.69 |  |  | 100% | 2666.69 | Phy. Completed | Item rate

## SCA
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : S.C.A | [10 empty] | Month : September 2023
Sl. No | Name of Work/Project | Unit | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummutive Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of Contract
[7 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Improvement of MPSC Office Building at MINECO |  | 394 | Project Division-I | 29.10.22 | 29.10.24 | 65% | 170.57 | 5% |  | 70% | 170.57 |  | EPC
2 | Construction of DIG (NR) Office Building at PHQ Complex, Aizawl |  | 320 | Project Division-I | 21.7.22 | 21.1.24 | 55% | 95.22 | 5% |  | 60% | 95.22 |  | EPC
3 | Construction of Govt.Staff Qtrs.(Block-B) at DIET Complex |  | 386.6 | Project Division-I | 28.8.22 | 28.8.24 | 35% | 0.25 | 3% | 93.58 | 38% | 93.83 |  | EPC
4 | Strenthening of Infrastructure in 3 newly created Districts (Const.of DC Office Khawzawl) |  | 1000 | Project Division-III | 21.04.21 | 21.04.24 | 97.5% | 861.17 | 1.2% |  | 98.7% | 861.17 | Work in progress
5 | Strenthening of Infrastructure in 3 newly created Districts (Const.of DC Office Saitual) |  | 1000 | Project Division-III | 20.01.21 | 20.04.24 | 90% | 776.28 | 3% | 128.44 | 93% | 904.72 | Pandemic crisis delayed work progress. Now Work is in progress
6 | Construction of District Research Officers Office at Khawzawl (Sh: C/o DRO Office Ground Floor & C/O Quarters 1st Floor) |  | 43 | Project Division-III | 12.09.22 | 12.05.23 | 100% | 26.65 |  | 16.35 | 100% | 43 | Completed
7 | Construction of District Research Officers Quarters and Staff Cum Chowkider Quarters at Keifang, Saitual District |  | 70 | Project Division-III | 09.09.22 | 09.07.23 | 28% | - | 10% | - | 38% | - | Work in progress
8 | Improvement & Upgradation of Operational/Non Operational facilities of Lengpui (Sh: Renovation of Terminal building) |  | 2124 | Project Division-III | 16.03.21 | 21.10.23 | 93.7% | 1254.05 | 1% | - | 94.7% | 1254.05 | Pandemic crisis delayed work progress. Now Work is in progress
9 | Strengthening of Aizawl-Thenzawl-Lunglei Road from (17.000-30.000 & 51.000-63.00 Kmp) |  | 1332 | Hmuifang Division | 12.10.20 | 31.03.22 | 100% | 1289.94 | - |  | 100% | 1289.94 | Completed
10 | Rehabilitation of Landslide Area within Hualngohmun Village at Chainage 9.400 |  | 162 | Hmuifang Division | 28.03.22 | 28.03.23 | 86% | 90.98 |  | 13.5 | 86% | 104.48 | Work in progress
11 | Const.of Road from IR Camp to Ramri Lui, Zophai, Bairabi (Sh: Group A-Formation Cutting, Permanent works and side drain) | Km | 498 | NHD-III | 27.07.23 | 27.01.24 | 91.48% |  | 8.52% |  | 100% |  |  | Item Rate

## NLUP
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : NLUP | [10 empty] | Month : September2023
Sl. No | Name of Work/Project | Unit | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[7 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Re-Construction of District Transport Office at Champhai | % | 262 | Project Division-III | 11.7.22 | 11.01.24 | 96% | 186.43 | 2% |  | 98% | 186.43 | Work in progress | PWD Form-8

## SARDP
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : SARDP-NE | [10 empty] | Month : September 2023
Sl. No | Name of Work/Project | Unit | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[7 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Widening to two laning/Re-alignment and geometric improvement from km.11+000 to 114+618 of NH-44 'A' in the state of Mizoram | Phy in % Fin in lakh | 1,10,988.00 | NHD-I | 17.3.11 | 31.12.22 | 96.04% | 102146 |  |  | 96.04% | 102146 | Contract was terminated on 24.08.2023 Tender being floated for selection of new contractor | Item rate contract
2 | Construction of a new 2-lane Highway from km 0/00kmp to 38/00 in Mizoram to support Kaladan Multi Modal Transit Transport project in Phase-'A of SARDP-NE package-I |  | 43465 | Multi Modal Project Division |  |  | 100% | 42058 |  |  | 100% | 42058 | 1. Financial progress is upto RA 145 2. Work completed on 22.6.2023
3 | Construction of a new 2-lane Highway from km 38.00 to km 71.00 in Mizoram to support Kaladan Multi Modal Transit Transport project in Phase-'A of SARDP-NE package-II |  | 32224 | Multi Modal Project Division |  |  | 100% | 30977 |  | - | 100% | 30977 | 1. Financial progress is based on bill submitted by the Contractor after verifying at the spot by the Department. 2. Work completed on 30.04.22
4 | Construction of a new 2-lane Highway from km 71.00 to km 99.83 in Mizoram to support Kaladan Multi Modal Transit Transport project in Phase-'A of SARDP-NE package-III |  | 37459 | Multi Modal Project Division |  |  | 100% | 36432 |  | - | 100% | 36432 | 1. Financial progress is based on bill submitted by the Contractor after verifying at the spot by the Department. 2. Work completed on 23.06.23

## MAJOR
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : Major & Minor Works and Deposit woks 8443-108, D-III | [10 empty] | Month : September 2023
Sl. No | Name of Work/Project | Unit | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[7 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | I/E to Additional Court Room with Chamber at Kolasib | % | 4.26 | Electrical Division Aizawl |  |  | 100% | 4.26 | - | - | 100% | 4.26 | I/E Completed, S/C being process
2 | I/E to Arrival & Departure Passenger Lobby at Lengpui Airport | % | 25.27 | Electrical Division Aizawl |  |  | 90% | 25.27 | - | - | 90% | 25.27 | Panel Board not yet installed
3 | SITC 13 Passenger Lift-2 nos, 2-opening, 900mm centre opening Stainless Steel cable with Automatic Rescue Device (ARD) for Hydraulic Lift with Minor Civil Works at Lengpui Airport Mizoram | % | 77.91 | Electrical Division Aizawl |  |  | 25% | - | - | - | 25% | - | On going works
4 | I/E to Chowkider Qtrs at PWD Complex, Bilkhawthlir | % | 3.6 | Electrical Division Aizawl |  |  | 100% | 3.6 | - | - | 100% | 3.6 | Completed
5 | I/E to Rest House at PWD Complex, Bilkhawthlir | % | 30.91 | Electrical Division Aizawl |  |  | 100% | 25.37 | - | - | 100% | 25.37 | Completed
6 | I/E to Re-construction of Safe House at Sairang | % | 5.2 | Electrical Division Aizawl |  |  | 100% | 5.2 | - | - | 100% | 5.2 | Completed
7 | I/E to Paying Cabin for ZMC at Falkawn | % | 99.32 | Electrical Division Aizawl |  |  | 100% | 99.32 | - | - | 100% | 99.32 | Completed
8 | SITC with fire fighting system for paying cabin ZMC at Falkawn | % | 34.57 | Electrical Division Aizawl |  |  | 100% | 34.57 | - |  | 100% | 34.57 | Completed
9 | SITC of 15 passenger G+4MRL Hospital Lift with 900mm Central Opening with Automatic Resue Device (ARD) est (OTISmake) at Paying | % | 50 | Electrical Division Aizawl |  |  | 100% | 50 | - |  | 100% | 50 | Completed
10 | I/E to Fast Track Court (Judical Gr-I qtr) at Kolasib | % | 11.43 | Electrical Division Aizawl |  |  | 100% | 11.43 | - | - | 100% | 11.43 | Completed
11 | Street Light Parking light at Lengpui Airport | % | 37.32 | Electrical Division Aizawl |  |  | 90% | 37.31 |  | - | 90% | 37.31 | On going works
12 | Laying of XLPE Cable from Power House to Glide Path control at Lengpui Airport, Mizoram | % | 39.53 | Electrical Division Aizawl |  |  | 95% | - | 5% | 39.52 | 100% | 39.52 | Works completed
13 | Estimate for I/E of Energy Meter for Terminal Building at Lengpui Airport | % | 7.99 | Electrical Division Aizawl |  |  | 40% | 7.99 | - | - | 40% | 7.99 | On going works
14 | I/E for Const.of Grade I Officers Qtr at Project veng Kolasib | % | 5.13 | Electrical Division Aizawl |  |  | 100% | 5.13 | - | - | 100% | 5.13 | Completed
15 | I/E & Fire fighting to Car Parking at Dist.Court MINECO | % | 32.48 | Electrical Division Aizawl |  |  | 60% | 16.99 | - | - | 60% | 16.99 | On going works
16 | SITC of Fire Fighting System of Dist.Court, MINECO | % | 125.4 | Electrical Division Aizawl |  |  | 100% | 124.83 | - | - | 100% | 124.83 | Completed
17 | Addl.Estimate for SITC of MRV/VRF Centralizes Air Conditioner Airport Fist Floor Departure Hall, Mizoram | % | 247.74 | Electrical Division Aizawl |  |  | 70% | 220.1 |  | - | 70% | 220.1 | On going works
18 | SITC of EPABX System for Lengpui Airport Terminal Building | % | 24.64 | Electrical Division Aizawl |  |  | 50% | 9.86 | - | - | 50% | 9.86 | On going works
19 | SITC of PA System at Lengpui Airport Terminal Building | % | 36.36 | Electrical Division Aizawl |  |  | 50% | 14.54 | - | - | 50% | 14.54 | On going works
20 | Supply & Installation of Integrated Fire Hydrant System (Wise Riser) & SiTC of Alarm System for Lengpui Airport Terminal building | % | 119.96 | Electrical Division Aizawl |  |  | 50% | 47.99 | - | - | 50% | 47.99 | On going works
21 | SITC of AVTRON IP Surveillance System for Lengpui Airport Terminal Building | % | 94.76 | Electrical Division Aizawl |  |  | 50% | 37.9 | - | - | 50% | 37.9 | On going works
22 | SITC of LANE SETUP at Lengpui Airport Terminal Building | % | 20.05 | Electrical Division Aizawl |  |  | 50% | 8.02 | - | - | 50% | 8.02 | On going works
23 | Estimate for XLPE Cable for Lengpui Airport | % | 27.23 | Electrical Division Aizawl |  |  | 50% | 27.23 | 30% | - | 80% | 27.23 | On going works
24 | Additional Estimate fo SITC of Air Conditioner Departer Pssenger Lobby at Lengpui Airport | % | 24.67 | Electrical Division Aizawl |  |  | 100% | 24.67 | - | - | 100% | 24.67 | Completed
25 | I/E works for Const. of MBSE Office | % | 57.37 | Electrical Division Aizawl |  |  | 25% | 57.37 | - |  | 25% | 57.37 | On going works
26 | I/E for DC Office at Saitual | % | 70 | Electrical Division Aizawl |  |  | 100% | 70 | - | - | 100% | 70 | I/E completed, S/C left due to non installation of required transformer
27 | I/E for Const. of IF &SL Office building at Tuikhuahtlang | % | 23.33 | Electrical Division Aizawl |  |  | 70% | 23.33 | - |  | 70% | 23.33 | On going works
28 | I/E to High Court Parking at MINECO | % | 109.5 | Electrical Division Aizawl |  |  | 40% | 65.73 | - | - | 40% | 65.73 | On going works
29 | I/E to Staff qtrr Block A for DIET, Chaltlang | % | 40.11 | Electrical Division Aizawl |  |  | 90% | 38.99 | 10% | - | 100% | 38.99 | Completed
30 | I/E to PHC at Bungzung | % | 18.18 | Electrical Division Aizawl |  |  | 100% | 18.18 |  | - | 100% | 18.18 | I/E Completed, S/C left due to non installation of required transformer
31 | I/E to PHC at Ngentiang | % | 15.72 | Electrical Division Aizawl |  |  | 100% | 15.72 | - |  | 100% | 15.72 | Completed
32 | Const.of DIG(NR) Office at Aizawl under SCA during 2022-23 (Sh:I/E) | % | 43.84 | Electrical Division Aizawl |  |  | 40% | 17.29 | - | - | 40% | 17.29 | On going works
33 | I/E to Mizoram Public Service Commission (MPSC) Building, Aizawl | % | 24.66 | Electrical Division Aizawl |  |  | 70% | 13.9 | 5% | - | 75% | 13.9 | On going works
34 | Construction of DC Office at Khawzawl (Sh: Lift & I/E) | % | 90 | Electrical Division Aizawl |  |  | 50% | 55.73 | 50% |  | 100% | 55.73 | I/E Works completed, Serrvices connection Left
35 | I/W Multi Level Parking Cum Basketball Court | % | 11.4 | Electrical Division Aizawl |  |  | 100% | 11.4 |  |  | 100% | 11.4 | Completed
36 | Reconstruction of PHC Building at Marpara, Mamit District | % | 16.18 | Electrical Division Aizawl |  |  | 60% | 16.18 |  |  | 60% | 16.18 | On going works
37 | Reconstruction of PHC Building at Bukpui | % | 14.59 | Electrical Division Aizawl |  |  | 100% | 14.59 |  |  | 100% | 14.59 | Completed
38 | Type-III Qtr at Vairengte | % | 1.6 | Electrical Division Aizawl |  |  | 100% | 1.6 |  |  | 100% | 1.6 | Completed
39 | JCO/NCO & Jawan Mess at Vairengte | % | 1.1 | Electrical Division Aizawl |  |  | 100% | 1.1 |  |  | 100% | 1.1 | Completed
40 | JCO Qtr Barrack cum Hote Company Hqrs at Vairengte | % | 3.6 | Electrical Division Aizawl |  |  | 100% | 3.6 |  |  | 100% | 3.6 | Completed
41 | Barrack I at Vairengte | % | 2.2 | Electrical Division Aizawl |  |  | 100% | 2.2 |  |  | 100% | 2.2 | Completed
42 | Barrack II at Vairengte | % | 2.2 | Electrical Division Aizawl |  |  | 100% | 2.2 |  |  | 100% | 2.2 | Completed
43 | Barrack III at Vairengte | % | 2.2 | Electrical Division Aizawl |  |  | 100% | 2.2 |  |  | 100% | 2.2 | Completed
44 | Reconstruction of DTO Office at Champhai | % | 17 | Electrical Division Aizawl |  |  | 100% | 17 |  |  | 100% | 17 | Completed
45 | I/E to DRO Office at Khawzawl | % | 2.84 | Electrical Division Aizawl |  |  | 100% | 2.84 |  |  | 100% | 2.84 | Completed
46 | Impvt/Revamping of Lengpui Airport runway Lighting -Isolation Bay-DGCA Observation Reg. | % | 347.05 | Electrical Division Aizawl |  |  | 10% | 188.46 | 50% | 30.48 | 60% | 218.94 | On-going works
47 | Impvt/Revamping of Lengpui Airport runway Lighting -Isolation Bay-DGCA Observation Reg. | % | 10.91 | Electrical Division Aizawl |  |  | 10% |  | 50% |  | 60% |  | On-going works
48 | Impvt/Revamping of Lengpui Airport runway Lighting -Isolation Bay-DGCA Observation Reg. | % | 14.6 | Electrical Division Aizawl |  |  | 10% |  | 50% |  | 60% |  | On-going works
49 | Impvt of Mizoram House at Silchar-repair of Dak Bangla Ground Floor, DRC Office & DRC Qtr T-IV | % | 5.19 | Electrical Division Aizawl |  |  | 100% |  |  | 5.19 | 100% | 5.19 | Completed

## SASCE
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : SASCE | [10 empty] | Month : September 2023
Sl. No | Name of Work/Project | Unit | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummutive Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[7 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Construction of RCC Minor Bridge between I.R approach road and NH-154 along Ch.Chhunga's paddy filed, Bairabi |  | 64.9 | Kolasib Division | 05.05.20 | 25.03.21 | 35% | 54.9 | - | - | 35% | 54.9 | As reported to the undersigned by the on.Dt.30.10.21, DC Kolasib District/Magistrate Kolasib District Kolasib instructed the Contractor in verbal to stop the work and to remove all the materials stocked at the site for construction of this bridge due to border conflict between Mizoram and Assam. Rs.10.00 lakhs kept under D-III
2 | Construction of Multi Utility Centre at Zemabawk, Aizawl, Mizoram. |  | 636.07 | Project Division-IV | 19.12.22 | 16.8.25 | 20.81% | 145.35 | 1.89% | - | 22.7% | 145.34 | Work in progress | Item Rate
3 | Construction of Solid Waste Management Centre at Hualngohmun, Mizoram (Phase-I) | % | 1664 | Project Division-IV | 07.04.23 | 07.04.25 | 5% | 9.14 |  |  | 5% | 9.14 | New architectural drawing/plan is awaited from Architect Cell, MPWD | Item Rate
4 | Strengthening of Saitual-Phullen Road (28.300 Km) (Tuivawl - Phullen) (28.700-57.000 Kmp) |  | 320 | Saitual Division | 08.02.21 |  | 100% | 319.99 |  | - | 100% | 319.99

## SPF
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : State Plan Fund | [10 empty] | Month : September 2023
Sl. No | Name of Work/Project | Unit | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummutive Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of Contract
[7 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | 4202 Co-On Education etc. a) I/E to boys & girls Hostel for Govt.Saiha College bldg at Siaha |  | 2 | Electrical Division, Lunglei |  |  | 40% | - | - | - | 40% | - | Materials received, building not yet ready
2 | 8443-108-PWD Deposit-III a) I/E to DC Bungalow (Type-IV) at Siaha |  | 8.2 | Electrical Division, Lunglei |  |  | 40% | - |  | - | 40% | - | Materials received, building not yet ready
| b) I/E to Primary Health Centre (PHC) at Tawipui 'S' |  | 20 | Electrical Division, Lunglei | 1.6.23 | 13.7.23 | 100% |  |  |  | 100% |  | Completed | Electrical Licensed Contractor
| c) I/E to DRO Quarter & DRO Office at Hnahthial |  | 2.71 | Electrical Division, Lunglei |  |  | 10% |  |  |  | 10% |  | TS accorded
| d) I/E to DC Office Building at Hnahthial |  | 68.43 | Electrical Division, Lunglei |  |  | 100% |  |  |  | 100% |  | Completed | Depart mental
| e) I/E to Safe House at Tlabung |  | 8 | Electrical Division, Lunglei | [8 empty] | TS accorded
3 | 4059-Co on Public works (Plan) a) I/E to District Court Building at Siaha |  | 139 | Electrical Division, Lunglei |  |  | 95% | - | 5% | - | 100% | - | Completed | Depart mental
4 | 4047-Co on other Fiscal Sevice
| a) I/E to deputy Commissioner of State Tax, Siaha zone (Office( at Siaha |  | 17 | Electrical Division, Lunglei |  |  | 100% |  |  |  | 100% |  | Completed | Depart mental
| b) I/E to Staff Quarter for Deputy Commissioner of State Tax, Siaha Zone (Type-I & Type-III) at Siaha |  | 13 | Electrical Division, Lunglei |  |  | 100% |  |  |  | 100% |  | Completed | Depart mental
| c) I/E to Staff Quarter for Deputy Commissioner of State Tax, Siaha Zone (Type-IV) at Siaha |  | 5 | Electrical Division, Lunglei |  |  | 100% |  |  |  | 100% |  | Completed | Depart mental

## SASCI
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
| Source of funding : SASCI 2022-23 | [8 empty] | Month : September, 2023
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
LUNGLEI BUILDING PROJECT DIVISION :
1 | Construction of District Research Officers Quarters & Office Building at Hnahthial | 43 | Lunglei Building Project Division | 15.09.22 | 15.09.23 | 100% | 43 |  |  | 100% | 43 | Completed
2 | Construction of Circuit House at Hnahthial | 304 | Lunglei Building Project Division | 13.04.23 | 13.10.24 | 10% |  |  |  | 10% |  | Layout has been done and work not yet started
3 | Strengthening of Infrastrucrture in 3 (three) new Districts in Mizoram (Sh: Const.of DC Office Building at Hnahthial | 1000 | Lunglei Building Project Division | 27.08.21 | 27.08.24 | 100% | 839.73 |  | 4.63 | 100% | 844.36 | Phy.Completed
4 | Construction of Sangau SDO© Office building at Sangau | 77 | Lunglei Building Project Division | 20.03.23 | 20.03.2024 | 80% | 36.91 | 3% |  | 83% | 36.91 | Work in progress
5 | Construction of SDO© Quarter at Sangau | 80 | Lunglei Building Project Division | 20.03.23 | 20.03.24 | 80% | 40 | 3% |  | 83% | 40 | Work in progress
6 | Construction of Staff Quarter(2 Units) at Sangau | 50.45 | Lunglei Building Project Division | 20.03.23 | 20.03.24 | 80% | 25 | 3% |  | 83% | 25 | Work in progress
7 | Construction of Volleyball Court at Gulsil Chawngte 'L' | 20 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% |  |  |  | 100% |  | Phy.Completed
8 | Construction of Meisatla Futsal Ground at Siaha | 34.78 | Lunglei Building Project Division | 20.03.23 | 20.09.23 | 31% |  |  |  | 31% |  | Work in progress
9 | Construction of Futsal Playground at Gov't Higher secondary School at Siaha | 34.78 | Lunglei Building Project Division | 20.03.23 | 20.09.23 | [6 empty] | Not yet started
10 | Construction of New Football ground at Ramlaitui | 20 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 90% |  | 3% |  | 93% |  | Work in progress
11 | Construction of New Football Ground at Haulawng | 20 | Lunglei Building Project Division | 20.03.23 | 20.06.23 |  |  | 10% |  | 10% |  | Work in progress
12 | Construction of New Football Ground at Mualthuam 'N' | 20 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% |  |  |  | 100% |  | Phy.Completed
13 | Construction of New Football Ground at Mualthuam 'N' (on going) | 10 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% |  |  |  | 100% |  | Phy.Completed
14 | Construction of New Football Ground at Haulawng ( on going ) | 10 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 50% |  | 30% |  | 80% |  | Work in progress
15 | Construction of New Football Ground at Rawpui | 15 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 90% |  | 3% |  | 93% |  | Work in progress
16 | Construction of Community Hall at Pukpui | 80 | Lunglei Building Project Division | 20.03.23 | 20.03.24 | 25% |  | 10% | 0.2 | 35% | 0.2 | Work in progress
17 | Construction of New Badminton Hall at Chhipphir | 20 | Lunglei Building Project Division | 20.03.23 | 20.09.23 | 20% |  | 50% |  | 70% |  | Work in progress
18 | Renovation of Community Hall at Farm Veng | 10 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% |  |  | 5 | 100% | 5 | Phy.Completed
19 | Renovation of Community Hall at Zobawk 'S' | 10 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% |  |  |  | 100% |  | Phy.Completed
20 | Renovation of Sport recreation House ( TT Hall) at Zobawk 'N' at Zobawk Bazar | 10 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% |  |  |  | 100% |  | Phy.Completed
21 | Painting & Electrification of Zobawk 'N' Hall | 12 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 75% |  | 10% |  | 85% |  | Work in progress
22 | Land development & Earthwork for Community Hall at Ralvawng | 10 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 80% |  | 20% | 5 | 100% | 5 | Phy.Completed
23 | Renovation of Community Hall at Leite | 5 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% |  |  |  | 100% |  | Phy.Completed
24 | Renovation of Public NGO's House at Leite | 5 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 80% |  | 20% |  | 100% |  | Phy Completed
25 | Renovation of Community Hall at Rotlang 'E' | 5 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% |  |  |  | 100% |  | Phy.Completed
26 | Completion of Community Hall at Dawn | 8 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 95% |  |  |  | 95% |  | Work in progress
27 | Construction of Community Hall at Zehtet | 30 | Lunglei Building Project Division | 20.03.23 | 20.09.23 | 100% |  |  |  | 100% |  | Phy.Completed
28 | Construction of Community Hall at Lungrang 'S' | 40 | Lunglei Building Project Division | 20.03.23 | 20.03.24 | [6 empty] | Not yet started
29 | Construction of Community Hall | 12 | Lunglei Building Project Division | 20.03.23 | 20.09.23 | 100% |  |  | 6 | 100% | 6 | Phy.Completed
30 | Construction of Community Hall at Chhumkhum | 27.47 | Lunglei Building Project Division | 20.03.23 | 20.09.23 | 20% |  |  | 13.75 | 20% | 13.75 | Work in progress
31 | Construction of Community Hall at New Sachan | 27.47 | Lunglei Building Project Division | 20.03.23 | 20.09.23 | 100% |  |  | 13.75 | 100% | 13.75 | Phy.Completed
32 | Construction of Public Recreation House at Chanmari, Lunglei | 10 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 95% |  | 5% | 5 | 100% | 5 | Phy.Completed
33 | Construction of Old Aged Home cum Library House at Community Hall at Ramthar, Lunglei | 15 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 50% |  | 30% |  | 80% |  | Work in progress
34 | Construction of Women Recreation House or Cemetary House at Electric veng Lunglei (Women recreation house) | 10 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 60% |  | 40% | 4.9 | 100% | 4.9 | Phy.Completed
35 | Construction of NGO's House cum Library Room at Zobawk 'S' Vengthar | 10 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 60% |  | 40% | 5 | 100% | 5 | Phy.Completed
36 | Completion of NGO's Recreation House at Lungpuizawl | 5 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% |  |  |  | 100% |  | Phy.Completed
37 | Renovation of Women Recreation House at Lower Ramthar, Lunglei | 5 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% |  |  |  | 100% |  | Phy.Completed
38 | Construction of Waiting Shed & Godown of Animal Feed Building at dawn | 5 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% |  |  |  | 100% |  | Phy.Completed
39 | Construction of Women Recreation House at Upper Ramthar, Lunglei | 15 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 70% |  | 10% |  | 80% |  | Work in progress
40 | Construction of NGO's Recreation house at Farm Veng, lunglei | 10 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 85% |  | 3% |  | 88% |  | Work in progress
41 | Construction of Clinic Center Building at Bungtlang W | 5 | Lunglei Building Project Division | 20.03.23 | 20.06.23 |  |  | 100% | 2.5 | 100% | 2.5 | Phy.Completed
42 | Rahsiveng Market Shed | 52 | Lunglei Building Project Division | 20.03.23 | 20.09.23 | 100% |  |  | 26 | 100% | 26 | Phy Completed
Construction of Public Toilet, Cemetary House, Waiting Shed, Water Supply & Footpath at Lunglei and Bunghmun
43 | Constructuion of Toilet and Water Pint at Kawmzawl Helipad, aizawl to lunglei Helicopter service Station | 15 | Lunglei Building Project Division | 20.03.23 | 20.09.23 | 70% |  |  |  | 70% |  | Work in progress
44 | Construction of Cemetary House at Chanmari, Lunglei | 15 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 80% |  | 20% | 7.5 | 100% | 7.5 | Phy.Completed
45 | Construction of Fencing & Cement Flooring at YMA hall courtyard at Electric Veng, Lunglei | 15 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% |  |  | 0.2 | 100% | 0.2 | Phy.Completed
46 | Construction of Public Store house and Urinal Shed at Electric Veng, Lunglei | 15 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 85% |  |  | 0.2 | 85% | 0.2 | Work in progress
47 | Construction of Waiting Shed near PWD Turning Point | 10 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 90% |  | 10% | 5 | 100% | 5 | Phy.Completed
48 | Estimate for Construction of Cemetary House at College Veng, lunglei | 5 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 90% |  | 10% | 2.5 | 100% | 2.5 | Phy.Completed
49 | Construction of Cemetary House at Bazar Veng Thlanmual No. 3 | 5 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% |  |  | 2.5 | 100% | 2.5 | Phy.Completed
50 | Construction of Boat Waiting shed at New Sachan | 0.69 | Lunglei Building Project Division | 20.03.23 | 20.05.23 | 100% | 0.35 |  |  | 100% | 0.35 | Phy.Completed
51 | Construction of Waiting near border Fencing inside India at Terabonia | 10.8 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 0.53 |  |  | 100% | 0.53 | Phy.Completed
52 | Construction of Boat Waiting Shed at Tuikawi | 0.69 | Lunglei Building Project Division | 20.03.23 | 20.05.23 | 100% | 0.35 |  |  | 100% | 0.35 | Phy.Completed
53 | Construction of Boat Waiting Shed at Sumasuri | 0.69 | Lunglei Building Project Division | 20.03.23 | 20.05.23 | 100% | 0.35 |  |  | 100% | 0.35 | Phy.Completed
54 | Construction of Boat waiting Shed at Old Sachan | 0.69 | Lunglei Building Project Division | 20.03.23 | 20.05.23 | 100% | 0.35 |  |  | 100% | 0.35 | Phy.Completed
55 | Construction of Waiting shed at Bungkawn, Lungchem | 0.69 | Lunglei Building Project Division | 20.03.23 | 20.05.23 | 100% | 0.35 |  |  | 100% | 0.35 | Phy.Completed
56 | Construction of Public Urinal near Vanlalhriara's House at Changpui | 0.73 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 0.37 |  |  | 100% | 0.37 | Phy.Completed
57 | Construction of Public Urinal near Hrangthuama's House at Changpui | 0.73 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 0.37 |  |  | 100% | 0.37 | Phy.Completed
58 | Construction of Urinal near Vanlalpianga's House at Dengsur | 0.73 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 0.37 |  |  | 100% | 0.37 | Phy.Completed
59 | Construction of Urinal near Thanthianga's House at Dengsur | 0.73 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 0.37 |  |  | 100% | 0.37 | Phy.Completed
60 | Construction of Urinal near Community Hall at Dengsur | 0.73 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 0.37 |  |  | 100% | 0.37 | Phy.Completed
61 | construction of Waiting Shed at Mangkhan Kawn, Dengsur | 10.8 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 0.53 |  |  | 100% | 0.53 | Phy.Completed
62 | Construction of Waiting shed at sabual & Dengsur Boundary. | 10.8 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 0.53 |  |  | 100% | 0.53 | Phy.Completed
63 | Construction of Waiting Shed near K.Vanlalruata's House at S.Khawlek | 1.08 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 0.53 |  |  | 100% | 0.53 | Phy.Completed
64 | Construction of Public Urinal near Information Centre Building at S.Khawlek | 0.73 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 0.37 |  |  | 100% | 0.37 | Phy.Completed
65 | Construction of Waiting shed at Dampui | 1.08 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 0.53 |  |  | 100% | 0.53 | Phy.Completed
66 | Construction of Cemetary House at Thenhlum | 0.76 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 0.38 |  |  | 100% | 0.38 | Phy.Completed
67 | Construction of Waiting Shed at Tawngtaina Hmun Zawlpui | 1.08 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 0.53 |  |  | 100% | 0.53 | Phy.Completed
68 | Construction of Public Urinal at Tawngtaina hmun at Zawlpui | 0.73 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% |  |  |  | 100% |  | Phy.Completed
69 | Construction of Bus Waiting Shed near Thantluanga's House at Belthei | 0.88 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 0.44 |  |  | 100% | 0.44 | Phy.Completed
70 | Construction of Waiting Shed at Tuisenchhuah | 10.8 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 0.53 |  |  | 100% | 0.53 | Phy.Completed
71 | Construction of Cemetary House at Rangte | 0.76 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 0.38 |  |  | 100% | 0.38 | Phy.Completed
72 | Stainless Steel Railling with Checker Tiles | 6 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 90% |  | 10% |  | 100% |  | Phy.Completed
73 | River view & Resting shed. ( Tlabung) | 9.5 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% |  |  |  | 100% |  | Phy.Completed
74 | Urinal Building with Side Drain Cover (Tlabung) | 5 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% |  |  |  | 100% |  | Phy.Completed
75 | Lowering of Siahatla field at Siaha | 35.97 | Lunglei Building Project Division | 20.03.23 | 20.03.24 | 100% | 18 |  |  | 100% | 18 | Phy.Completed
76 | Construction of Bazar Shed at Tuichawng | 5 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% |  |  |  | 100% |  | Phy.Completed
77 | Construction of MHIP Building at Bunghmun | 17.71 | Lunglei Building Project Division | 20.03.23 | 20.09.23 | 100% |  |  | 8.8 | 100% | 8.8 | Phy.Completed
78 | Construction of Anganwadi Centre at Zodin | 4.5 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% |  |  |  | 100% |  | Phy.Completed
79 | Construction of Playground at Chawngte 'L' | 40 | Lunglei Building Project Division | 20.03.23 | 20.09.23 | 100% |  |  |  | 100% |  | Phy.Completed
80 | Construction of Anganwadi Centre at Mauzam | 4.02 | Lunglei Building Project Division | 20.03.23 | 20.09.23 | 90% | 2 |  |  | 90% | 2 | Work in progress
81 | Construction of Anganwadi Centre at Tuisenchhuah | 9 | Lunglei Building Project Division | 20.03.23 | 20.09.23 | 90% |  |  | 4.5 | 90% | 4.5 | Work in progress
82 | Construction of MUP Building at Thenhlum | 9 | Lunglei Building Project Division | 20.03.23 | 20.09.23 | 100% |  |  | 4.5 | 100% | 4.5 | Phy.Completed
SUB DIVISION-I AIZAWL ROAD NORTH DIVISION :
1. CONSTRUCTION AND UPGRADATION OF ROAD FROM BAWNGKAWN TO RAMHLUN NORTH, AIZAWL
RAMHLUN NORTH
83 | Extension of Slab Culvert Side drain with cover Near Pi Duhawmi House at Ramhlun North | 0.81 | Aizawl Road North Division | - | - | 100% | 0.41 |  |  | 100% | 0.41 | Phy.Completed
84 | Construction of RCC Balcony Vety Qtr to Pu Lalrinsanga House Ramhlun North Basic Mual at Ramhlun North | 29.55 | Aizawl Road North Division | - | - | 100% | 14.77 |  |  | 100% | 14.77 | Phy.Completed
85 | Construction of PCC Pavement on AMC road Ramhlun North | 4.52 | Aizawl Road North Division | - | - | 100% | 2.26 |  |  | 100% | 2.26 | Phy.Completed
86 | Construction of Breast Wall near Pi Lalthlamuani at Ramhlun North | 2.49 | Aizawl Road North Division | - | - | 100% | 1.25 |  |  | 100% | 1.25 | Phy.Completed
87 | Construction of Retaining wall near Pi Duhawmi at Ramhlun North | 3.57 | Aizawl Road North Division | - | - | 100% | 1.79 |  |  | 100% | 1.79 | Phy.Completed
88 | Construction of Retaining Wall near Pi Thangluri at Ramhlun North | 7.66 | Aizawl Road North Division | - | - | 100% | 3.83 |  |  | 100% | 3.83 | Phy.Completed
| RAMHLUN SOUTH |  |  | - | -
89 | Cons.of Side drain with cover steel on Centenary Tuikhur to rev.Vanlalbuaia House On Carmel road at Ramhlun South | 19.26 | Aizawl Road North Division | - | - | 100% | 9.63 |  |  | 100% | 9.63 | Phy.Completed
90 | Const.of RCC Rectangular Side drain with cover on Bawngkawn to ITI road at Ramhlun South | 30.88 | Aizawl Road North Division |  | - | 100% | 15.44 |  |  | 100% | 15.44 | Phy.Completed
91 | Const.of RCC Rectanggular Side drain with cover on Thlanmual to Darnam Lui at Ramhlun South | 10.05 | Aizawl Road North Division |  | - | 100% | 5.03 |  |  | 100% | 5.03 | Phy.Completed
92 | Const.of Retaining wall near Pu Rohnuna Varte house at Ramhlun South | 8.22 | Aizawl Road North Division |  | - | 100% | 4.11 |  |  | 100% | 4.11 | Phy.Completed
93 | Construction of RCC Retaining wall near Ralhnehthanga House at Ramhlun South | 5.22 | Aizawl Road North Division |  |  | 100% | 2.61 |  |  | 100% | 2.61 | Phy.Completed
RAMHLUN VENGLAI
94 | Const.of RCC Rectangular side drain with cover on Approach Road to NHC office near Lalnghakliani to Pi Vanhnuaithangi House at Ramhlun Venglai | 2.68 | Aizawl Road North Division |  |  | 100% | 1.34 |  |  | 100% | 1.34 | Phy.Completed
95 | Const.of RCC Rectangular side drain with cover Near Pu mabiaka House at Ramhlun Venglai | 6.12 | Aizawl Road North Division |  |  | 100% | 3.06 |  |  | 100% | 3.06 | Phy.Completed
96 | Const.of RCC Rectangular side drain with cover on Ramhlun Venglai PCI to PC.Vanlalena House at Ramhlun Venglai | 7.05 | Aizawl Road North Division |  |  | 100% | 3.52 |  |  | 100% | 3.52 | Phy.Completed
97 | Const.of RCC Rectangular side drain with cover near H.Lalbiakmawia House at Ramhlun Venglai | 3.02 | Aizawl Road North Division |  |  | 100% | 1.51 |  |  | 100% | 1.51 | Phy.Completed
98 | Const.of Steel cross drain near H.lalbiakmawia House (Lower) at Ramhlun Venglai | 0.75 | Aizawl Road North Division |  |  | 100% | 0.37 |  |  | 100% | 0.37 | Phy.Completed
99 | Const.of Widening & Breast Wall on Approach Road to NHC Office near Pi Lalnghakliani House to Pi Vanhnuaithangi House at Ramhlun Venglai | 15.88 | Aizawl Road North Division |  |  | 100% | 7.94 |  |  | 100% | 7.94 | Phy.Completed
100 | Const.of Breast Wall Extension with Side Drain on DIC Office at Ramhlun Venglai at Ramhlun Venglai | 13.1 | Aizawl Road North Division |  |  | 100% | 6.55 |  |  | 100% | 6.55 | Phy.Completed
RAMHLUN VENGTHAR
101 | Const.of RCC Rectangular side drain with cover near Ramhlun Vengthar taxi stand at Ramhlun Vengthar | 6.53 | Aizawl Road North Division |  |  | 100% | 3.27 |  |  | 100% | 3.27 | Phy.Completed
102 | Const.of RCC Rectangular side drain with cover on Tluangpui road (Pu lalthawmliana to Cosma Mantluanga House) at Ramhlun Vengthar | 4.71 | Aizawl Road North Division |  |  | 100% | 2.35 |  |  | 100% | 2.35 | Phy.Completed
103 | Const.of RCC Rectangular side drain with cover on Zohmasawna House to bangla Lui at ramhlun Vengthar | 6.63 | Aizawl Road North Division |  |  | 100% | 3.32 |  |  | 100% | 3.32 | Phy.Completed
104 | Const.of RCC Rectangular side drain with cover on Sihpui to Ramhlun Vengthar Bus turning point at Ramhlun Vengthar | 11.25 | Aizawl Road North Division |  |  | 100% | 5.62 |  |  | 100% | 5.62 | Phy.Completed
105 | Const.of RCC Rectangular Cross drain with cover near Waiting Shed at Ramhlun Vengthar | 0.75 | Aizawl Road North Division |  |  | 100% | 0.37 |  |  | 100% | 0.37 | Phy.Completed
106 | Const.of Link drain near V.Lalvela House at Ramhlun Vengthar | 1.68 | Aizawl Road North Division |  |  | 100% | 0.84 |  |  | 100% | 0.84 | Phy.Completed
RAMHLUN SPORT COMPLEX
107 | Const.of RCC Rectangular Cross drain with cover near B.Lalthlamuana (L) House at Ramhlun Sport Complex | 0.73 | Aizawl Road North Division |  |  | 100% | 0.37 |  |  | 100% | 0.37 | Phy.Completed
108 | Const.of RCC Rectangular Side drain with cover near B.Lalthlamuana (L) House at Ramhlun Sport Complex | 2.52 | Aizawl Road North Division |  |  | 100% | 1.26 |  |  | 100% | 1.26 | Phy.Completed
109 | Const.of Link drain near B.Lalthlamuana (L) House at Ramhlun Sport Complex | 1.61 | Aizawl Road North Division |  |  | 100% | 0.81 |  |  | 100% | 0.81 | Phy.Completed
110 | Const.of steel cross drain near Laldinliana House at Ramhlun Sport Complex | 0.55 | Aizawl Road North Division |  |  | 100% | 0.27 |  |  | 100% | 0.27 | Phy.Completed
111 | Const.of RCC Rectangular Side drain with cover near Laldinliana House at Ramhlun Sport Complex | 0.7 | Aizawl Road North Division |  |  | 100% | 0.35 |  |  | 100% | 0.35 | Phy.Completed
112 | Const.of PCC Pavement near ICI road at Ramhlun Sport Complex | 1.4 | Aizawl Road North Division |  |  | 100% | 0.7 |  |  | 100% | 0.7 | Phy.Completed
113 | Const.of Retaining Wall on ICI road at Ramhlun Sport Complex | 5.83 | Aizawl Road North Division |  |  | 100% | 2.91 |  |  | 100% | 2.91 | Phy.Completed
114 | Const.of PCC Pavement on Pu Hrekima House to Zohmingsanga House at Ramhlun Sport Complex | 2.53 | Aizawl Road North Division |  |  | 100% | 1.26 |  |  | 100% | 1.26 | Phy.Completed
115 | Const.of PCC Pavement near Laldinliana House at Ramhlun Sport Complex | 1.69 | Aizawl Road North Division |  |  | 100% | 0.84 |  |  | 100% | 0.84 | Phy.Completed
116 | Const.of Breast wall near Laldinliana House at Ramhlun Sport Complex | 2.22 | Aizawl Road North Division |  |  | 100% | 1.11 |  |  | 100% | 1.11 | Phy.Completed
117 | Const.of Retaining wall near Pu Hrekima House at Ramhlun Sport Complex | 2.25 | Aizawl Road North Division |  |  | 100% | 1.12 |  |  | 100% | 1.12 | Phy.Completed
118 | Const.of Retaining wall on LC Road to Lalfakawmi House at Ramhlun Sport Complex | 1.44 | Aizawl Road North Division |  |  | 100% | 0.72 |  |  | 100% | 0.72 | Phy.Completed
119 | Const.of Retaining wall near Pu Lingngoa at Ramhlun Sport Complex | 1.54 | Aizawl Road North Division |  |  | 100% | 0.77 |  |  | 100% | 0.77 | Phy.Completed
120 | Const.of Retaining wall near Kiamlova House at Ramhlun Sport Complex | 7.52 | Aizawl Road North Division |  |  | 100% | 3.76 |  |  | 100% | 3.76 | Phy.Completed
121 | Const.of Retaining wall block-I on LC road Lianhnuna House to Buchhawna ME School at Ramhlun Sport Complex | 3.69 | Aizawl Road North Division |  |  | 100% | 1.84 |  |  | 100% | 1.84 | Phy.Completed
122 | Const.of Retaining wall block-II on LC road Lianhnuna House to Buchhawna ME School at Ramhlun Sport Complex | 5.26 | Aizawl Road North Division |  |  | 100% | 2.63 |  |  | 100% | 2.63 | Phy.Completed
123 | Const.of Retaining wall block-III on LC road Lianhnuna House to Buchhawna ME School at Ramhlun Sport Complex | 7.56 | Aizawl Road North Division |  |  | 100% | 3.78 |  |  | 100% | 3.78 | Phy.Completed
124 | Const.of Retaining wall block-IV on LC road Lianhnuna House to Buchhawna ME School at Ramhlun Sport Complex | 7.03 | Aizawl Road North Division |  |  | 100% | 3.52 |  |  | 100% | 3.52 | Phy.Completed
125 | Const.of Retaining wall Near YMA ram at Ramhlun Sport Complex | 7.17 | Aizawl Road North Division |  |  | 100% | 3.59 |  |  | 100% | 3.59 | Phy.Completed
126 | Const.of Retaining wall Near Bangla Lui at Ramhlun Sport Complex | 13.45 | Aizawl Road North Division |  |  | 100% | 6.73 |  |  | 100% | 6.73 | Phy.Completed
127 | Const.of Retaining wall Near Bangla Lui Counterford at Ramhlun Sport Complex | 8.84 | Aizawl Road North Division |  |  | 100% | 4.42 |  |  | 100% | 4.42 | Phy.Completed
128 | Const.of PCC Pavement on Presbyterian Biak In road at Ramhlun Sport Complex Vengthlang | 3.89 | Aizawl Road North Division |  |  | 100% | 1.94 |  |  | 100% | 1.94 | Phy.Completed
129 | Const.of PCC Pavement on Ramhlun Vengthar road at Ramhlun Sport Complex Vengthlang | 4.11 | Aizawl Road North Division |  |  | 100% | 2.05 |  |  | 100% | 2.05 | Phy.Completed
130 | Const.of PCC Pavement on Ringzova road to Pu Lalbiakliana House at Ramhlun Sport Complex Vengthlang | 3.89 | Aizawl Road North Division |  |  | 100% | 1.94 |  |  | 100% | 1.94 | Phy.Completed
BAWNGKAWN SOUTH
131 | Const.of Link drain between Ou Darringaia's House to Pu Lalensanga's House at Bawngkawn 'S' | 9.55 | Aizawl Road North Division |  |  | 100% | 4.77 |  |  | 100% | 4.77 | Phy.Completed
132 | Const.of Hand Railing for Public Step near Pi Mangkungi House Bawngkawn 'S' | 3.11 | Aizawl Road North Division |  |  | 100% | 1.56 |  |  | 100% | 1.56 | Phy.Completed
133 | Const.of Hand Railing for Public Step near YMA Hall, Bawngkawn 'S' | 0.81 | Aizawl Road North Division |  |  | 100% | 0.41 |  |  | 100% | 0.41 | Phy.Completed
134 | Const.of Hand Railing for Public Step near Pu Tlangdingliana House Bawngkawn 'S' | 2.11 | Aizawl Road North Division |  |  | 100% | 1.06 |  |  | 100% | 1.06 | Phy.Completed
135 | Const.of Hand Railing for Public footpath near YMA Hall, Bawngkawn 'S' | 1.81 | Aizawl Road North Division |  |  | 100% | 0.91 |  |  | 100% | 0.91 | Phy.Completed
136 | Const.of Retaining wall near YMA Hall, Bawngkawn 'S' | 1.41 | Aizawl Road North Division |  |  | 100% | 0.7 |  |  | 100% | 0.7 | Phy.Completed
137 | Const.of Retaining wall near transformer on Pu Liansailova road at Bawngkawn 'S' | 1.66 | Aizawl Road North Division |  |  | 100% | 0.83 |  |  | 100% | 0.83 | Phy.Completed
138 | Construction of PCC Pavement on Pu Liansailova Road at Bawngkawn South | 3.36 | Aizawl Road North Division |  |  | 100% | 1.68 |  |  | 100% | 1.68 | Phy.Completed
139 | Repair of Side drain near Pu Tlangdingliana House | 0.36 | Aizawl Road North Division |  |  | 100% | 0.18 |  |  | 100% | 0.18 | Phy.Completed
2. CONSTRUCTION AND UPGRADATION OF ROAD FROM BAWNGKAWN TO RAMHLUN NORTH, AIZAWL
ZARKAWT
140 | Construction of RCC Rectangular Side drain with cover on P.Lalvuana to R.Lalhmachhuana House at Aizawl Venglai | 77.98 | Aizawl Road North Division | [7 empty] | 35.79
| Widening=150Rm |  |  |  |  | 40% |  | 3% |  | 43% |  | Work progress
| Breast Wall - 3 nos-75Rm |  |  |  |  | 0% | 11.7 |  | 24.09 | 0% |  | Not yet started
| V-Shape - 150Rm |  |  |  |  | 0% |  |  |  | 0% |  | Not yet started
| Concrete Pavement - 150Rm |  |  |  |  | 0% |  |  |  | 0% |  | Not yet started
AIZAWL VENGLAI
141 | Construction of of RCC Rectangular Side drain with cover on P.Lalvuana to R.Lalhmachhuana house at Aizawl Venglai | 3.36 | Aizawl Road North Division |  |  | 100% | 1.68 |  |  | 100% | 1.68 | Phy.Completed
142 | Construction of RCC Rectangular Side drain with cover on Taitea Tuikhur to YMA Hall at Aizawl Venglai | 7.01 | Aizawl Road North Division |  |  | 100% | 3.5 |  |  | 100% | 3.5 | Phy.Completed
143 | Construction of RCC Rectangular Side drain with cover on Pu Lalhluna House to Pu Nghinglova House at Aizawl Venglai | 1.26 | Aizawl Road North Division |  |  | 100% | 0.63 |  |  | 100% | 0.63 | Phy.Completed
144 | Construction of RCC Rectangular Side drain with cover on Pu Zosiama Garrage to Pi Lalbiaki House at Aizawl Venglai | 3.36 | Aizawl Road North Division |  |  | 100% | 1.68 |  |  | 100% | 1.68 | Phy.Completed
145 | Construction of Link drain on Chuangkimi to Benben step at Aizawl Venglai | 1.89 | Aizawl Road North Division |  |  | 100% | 0.95 |  |  | 100% | 0.95 | Phy.Completed
146 | Construction of Link drain on Pi Rosiami to Pi Lalmuanpuii House at Aizawl Venglai | 2.79 | Aizawl Road North Division |  |  | 100% | 1.4 |  |  | 100% | 1.4 | Phy.Completed
147 | Construction of Link drain near Pi Chuangkimi House at Aizawl Venglai | 2.7 | Aizawl Road North Division |  |  | 100% | 1.35 |  |  | 100% | 1.35 | Phy.Completed
148 | Construction of Link drain on Mini market to VDP House at Aizawl Venglai | 3.08 | Aizawl Road North Division |  |  | 100% | 1.54 |  |  | 100% | 1.54 | Phy.Completed
149 | Construction of V-Shape side drain on Zirtiri College to Pu Saptawnliana House at Aizawl Venglai | 2.68 | Aizawl Road North Division |  |  | 100% | 1.34 |  |  | 100% | 1.34 | Phy.Completed
150 | Construction of V-Shape side on Pu Sapliantawna to khurpui at Aizawl Venglai | 0.76 | Aizawl Road North Division |  |  | 100% | 0.38 |  |  | 100% | 0.38 | Phy.Completed
151 | Construction of V-Shape side on Lalnghinglova House to Chuangkimi House at Aizawl Venglai | 1.65 | Aizawl Road North Division |  |  | 100% | 0.82 |  |  | 100% | 0.82 | Phy.Completed
152 | Construction of V-Shape side drain on K.Zaneiha Garrage to Kawrhpui (Rozami House) at Aizawl Venglai | 2.16 | Aizawl Road North Division |  |  | 100% | 1.08 |  |  | 100% | 1.08 | Phy.Completed
153 | Construction of of Steel cross drain on near Pu J.Laltanpuia at Aizawl Venglai | 0.75 | Aizawl Road North Division |  |  | 100% | 0.37 |  |  | 100% | 0.37 | Phy.Completed
154 | Construction of of Steel cross drain on near Pi Chuangkimi House at Aizawl Venglai | 0.58 | Aizawl Road North Division |  |  | 100% | 0.29 |  |  | 100% | 0.29 | Phy.Completed
155 | Construction of Chequerred tile near MHIP House at Aizawl Venglai | 1.88 | Aizawl Road North Division |  |  | 100% | 0.94 |  |  | 100% | 0.94 | Phy.Completed
156 | Construction of Link drain cover near Pi Lalchawngpuii House at Aizawl Venglai | 1.88 | Aizawl Road North Division |  |  | 100% | 0.94 |  |  | 100% | 0.94 | Phy.Completed
157 | Construction of PCC Pavement on Middle School to Biakthuama House at Aizawl Venglai | 0.42 | Aizawl Road North Division |  |  | 100% | 0.21 |  |  | 100% | 0.21 | Phy.Completed
158 | Construction of Retaining Wall near VDP House at Aizawl Venglai | 0.58 | Aizawl Road North Division |  |  | 100% | 0.29 |  |  | 100% | 0.29 | Phy.Completed
159 | Construction of Link drain on Pi lalmuanpuii House to Pu KC.Vanlalruata House at Aizawl Venglai | 1.45 | Aizawl Road North Division |  |  | 100% | 0.72 |  |  | 100% | 0.72 | Phy.Completed
160 | Construction of Lowering & RCC Pavement near Pu Sangmawia (L) House at Aizawl Venglai | 1.25 | Aizawl Road North Division |  |  | 100% | 0.62 |  |  | 100% | 0.62 | Phy.Completed
161 | Construction of Chequrred tile near near Basketball Court at Aizawl Venglai | 1.49 | Aizawl Road North Division |  |  | 100% | 0.74 |  |  | 100% | 0.74 | Phy.Completed
RAMTHAR
162 | Construction of RCC Rectangular side drain with cover on Sihpui Taxi stand to Electric Vengthlang PCI at Ramthar | 9.6 | Aizawl Road North Division |  |  | 100% | 4.8 |  |  | 100% | 4.8 | Phy.Completed
163 | Construction of RCC Rectangular Cross drain with cover near David Malsawma House at Ramthar | 1.66 | Aizawl Road North Division |  |  | 100% | 0.83 |  |  | 100% | 0.83 | Phy.Completed
164 | Construction of Breast wall Below Pu K.Lalchawimawia House at Ramthar | 1.37 | Aizawl Road North Division |  |  | 100% | 0.68 |  |  | 100% | 0.68 | Phy.Completed
165 | Construction of PCC Pavement on Tetea Road | 2.81 | Aizawl Road North Division |  |  | 100% | 1.4 |  |  | 100% | 1.4 | Phy.Completed
166 | Construction of Retaining Wall near Pu Biakzaua House at Ramthar | 4.24 | Aizawl Road North Division |  |  | 100% | 2.12 |  |  | 100% | 2.12 | Phy.Completed
167 | Construction of Breast Wall Near C.Zothantluanga House at Ramthar | 1.53 | Aizawl Road North Division |  |  | 100% | 0.76 |  |  | 100% | 0.76 | Phy.Completed
168 | Construction of Chequrred tile and Hand railing near UPC (NEI) Church at Ramthar | 3.78 | Aizawl Road North Division |  |  | 100% | 1.89 |  |  | 100% | 1.89 | Phy.Completed
169 | Construction of Breast Wall on Pu Zothansanga Near UPC (MZ) Church Upper Galilie at Ramthar Veng at Ramthar | 3.52 | Aizawl Road North Division |  |  | 100% | 1.76 |  |  | 100% | 1.76 | Phy.Completed
170 | Construction of Retaining Wall Near Pu Lalhmunsiama House at Ramthar | 4.99 | Aizawl Road North Division |  |  | 100% | 2.49 |  |  | 100% | 2.49 | Phy.Completed
171 | Construction of Breast Wall Near SH.Lalkhama House at Ramthar | 1.51 | Aizawl Road North Division |  |  | 100% | 0.76 |  |  | 100% | 0.76 | Phy.Completed
172 | Construction of Retaining Wall Near Cfootpath Sihpui to upper Galilie at Ramthar | 2.63 | Aizawl Road North Division |  |  | 100% | 1.31 |  |  | 100% | 1.31 | Phy.Completed
173 | Construction of Retaining Wall Near Pu Laltlankima House at Ramthar | 2.93 | Aizawl Road North Division |  |  | 100% | 1.46 |  |  | 100% | 1.46 | Phy.Completed
174 | Construction of Step, Hand Railing and Widening near Tlangveng Taxi Stand at Ramthar | 2.44 | Aizawl Road North Division |  |  | 100% | 1.22 |  |  | 100% | 1.22 | Phy.Completed
175 | Construction of Widening and Breast Wall below Bishop House at Ramthar | 7.61 | Aizawl Road North Division |  |  | 100% | 3.81 |  |  | 100% | 3.81 | Phy.Completed
176 | Construction of Widening and Breast Wall Near Pu Lalbuanga House at Ramthar | 5.45 | Aizawl Road North Division |  |  | 100% | 2.73 |  |  | 100% | 2.73 | Phy.Completed
177 | Construction of RCC Pavement on Pu Thianghlima House to Pu B.Lalmalsawma House at Ramthar | 4.64 | Aizawl Road North Division |  |  | 100% | 2.32 |  |  | 100% | 2.32 | Phy.Completed
178 | Construction of Breast Wall Near Republic High School at Ramthar | 1.47 | Aizawl Road North Division |  |  | 100% | 0.73 |  |  | 100% | 0.73 | Phy.Completed
179 | Construction of Retaining Wall at Chainage 0.100 Kmp on Ramthar Cemetrey to Sihpui via Upper Galilie | 23.17 | Aizawl Road North Division |  |  | 100% | 11.59 |  |  | 100% | 11.59 | Phy.Completed
180 | Construction of Retaining Wall at Chainage 0.060 Kmp on Ramthar Cemetry to Sihpui via Upper Galilie Pu Lalbuanga House at Ramthar | 14.1 | Aizawl Road North Division |  |  | 100% | 7.05 |  |  | 100% | 7.05 | Phy.Completed
RAMTHAR NORTH
181 | Construction of RCC Rectangular side drain with cover on Electric Cemetry to Ruali Tuikhur at Ramthar North | 0.87 | Aizawl Road North Division |  |  | 100% | 0.44 |  |  | 100% | 0.44 | Phy.Completed
182 | Construction of Breast Wall on Tetea Road at Ramthar North | 1.43 | Aizawl Road North Division |  |  | 100% | 0.72 |  |  | 100% | 0.72 | Phy.Completed
183 | Construction of RCC Balcony near Ruali Tuikhur at Ramthar North | 4.71 | Aizawl Road North Division |  |  | 100% | 2.35 |  |  | 100% | 2.35 | Phy.Completed
184 | Construction of RCC Balcony on Tetea Road at Ramthar North | 5.4 | Aizawl Road North Division |  |  | 100% | 2.7 |  |  | 100% | 2.7 | Phy.Completed
185 | Construction of Retaining Wall on Tetea Road at Ramthar North | 11.42 | Aizawl Road North Division |  |  | 100% | 5.71 |  |  | 100% | 5.71 | Phy.Completed
186 | Construction of Retaining Wall on Near Electric Cemetry at Ramthar North | 7.77 | Aizawl Road North Division |  |  | 100% | 3.88 |  |  | 100% | 3.88 | Phy.Completed
SARON VENG
187 | Construction of RCC Link Drain with Cover at Saron Veng | 50 | Aizawl Road North Division
| Link Drain - 72Rm |  |  |  |  | 100% |  |  |  | 100% | 25 | Phy.Completed
| RCC Foot Step - 60Rm |  |  |  |  | 100% | 25 |  |  | 100% |  | Phy.Completed
| Pavement - 42.5Rm |  |  |  |  | 100% |  |  |  | 100% |  | Phy.Completed
| RCC Side Drain - 44.17Rm |  |  |  |  | 100% |  |  |  | 100% |  | Phy.Completed
3. CONSTRUCTION AND UPGRADATION OF ROAD FROM TUITHIANG - CHHINGA VENG - ARMED VENG - CHITE, AIZAWL
188 | Construction of PCC Pavement on District Jail to Lower Armed Veng Road (Service Road) | 68 | Aizawl Road North Division |  |  | 100% | 34 |  |  | 100% | 34 | Phy.Completed
189 | Construction of Concrete Pavement on Dawrpui Cemetery Internal Road betweenn Pu Thangdanga's House to Lalkima Sailo Site Junction | 16 | Aizawl Road North Division |  |  | 100% | 8 |  |  | 100% | 8 | Phy.Completed
190 | Construction of Concrete Pavement on District Jail to CRPF Road | 16 | Aizawl Road North Division |  |  | 100% | 8 |  |  | 100% | 8 | Phy.Completed
191 | Construction of New Road from Pu Lalhmingliana Sailo House to Pu Siamphunga Lei at Tuithiang Veng | 50 | Aizawl Road North Division | [7 empty] | 25
| RCC Balcony - 24Rm |  |  |  |  | 100% |  |  |  | 100% |  | Phy Completed
| Retaining Wall - 3nos-50.70Rm |  |  |  |  | 100% | 25 |  |  | 100% |  | Phy.Completed
| Breast Wall - 27.00 Rm |  |  |  |  | 100% |  |  |  | 100% |  | Phy.Completed
| Concrete Pavement - 90.00Rm |  |  |  |  | 100% |  |  |  | 100% |  | Work in progress
| Formation cutting - 86.00Rm |  |  |  |  | 100% |  |  |  | 100% |  | Phy completed
192 | Consrtuction of Concrete Pavement on C.P Road chite Veng | 50 | Aizawl Road North Division | [7 empty] | 25
| Concrete Pavement - 380.00Rm |  |  |  |  | 100% |  |  |  | 100% |  | Phy Completed
| Lowering & Widening -30Rm |  |  |  |  | 100% | 25 |  |  | 100% |  | Phy.Completed
| Slab Culvert - 1no |  |  |  |  | 100% |  |  |  | 100% |  | Phy.Completed
| Retaining Wall-12Rm |  |  |  |  | 100% |  |  |  | 100% |  | Phy.Completed
193 | Construction of RCC Balcony on Bethany Road at Chhinga Veng | 50 | Aizawl Road North Division |  |  | 100% | 25 |  |  | 100% | 25 | Phy Completed
194 | Construction of Retaining Wall at Armed Veng near Pu lalkima House | 22 | Aizawl Road North Division
| Retaining Wall - 2nos-24.10Rm |  |  |  |  | 100% | 11 |  |  | 100% |  | Phy.Completed
| Breast Wall -15.00Rm |  |  |  |  | 100% |  |  |  | 100% |  | Phy.Completed
| Side Drain-55.00Rm |  |  |  |  | 100% |  |  |  | 100% |  | Phy.Completed
4. CONSTRUCTION CHECK DAM AT THEIHAI LUI, ARMED VENG
195 | Counterfort Retaining Wall at Armed Veng | 41.22 | Aizawl Road North Division | [8 empty] | Not yet started
196 | Toe Walls at Armed Veng side | 31.44 | Aizawl Road North Division | [8 empty] | Not yet started
197 | Retaining Wall at Ramthar side | 30.21 | Aizawl Road North Division | [8 empty] | Not yet started
198 | Counterfort Retaining Wall at Canara Bank | 43.62 | Aizawl Road North Division |  |  | 20% | 21.8 | 40% |  | 60% | 21.81 | Work in progress
199 | Retaining Wall at Canara Bank Bridge | 23.06 | Aizawl Road North Division | [8 empty] | Not yet started
200 | Const.of Breast Wall on Bazar Bungkawn to Chite Road near 1st Battalion MAP One Gate Armed Veng | 4.93 | Aizawl Road North Division |  |  | 100 |  |  |  | 100% |  | Phy Completed
201 | Construction of RCC Link Drain near Pu Phirthanga's House | 24.79 | Aizawl Road North Division | [8 empty] | Not yet started
202 | Const.of RCC Link Drain between Pu Lalrinsanga Hmar House to Pu Lalhuliana's House | 12.09 | Aizawl Road North Division |  |  | 10% |  |  |  | 10% |  | Work in progress
203 | Const.of RCC Link Drain between Pu Ralkapa's House to Pu Darchhunga's House | 11.65 | Aizawl Road North Division | [8 empty] | Not yet started
204 | Const.of RCC Link Drain Pu Lalhmingthanga's House | 12.48 | Aizawl Road North Division |  |  |  |  | 100% |  | 100% |  | Phy Completed
205 | Const.of RCC Link Drain Pu Lalhmingthanga's House | 13.87 | Aizawl Road North Division |  |  |  |  | 35% |  | 35% |  | Work in progress
206 | Const.of RCC Link Drain near Pu Rallianzuala's Land | 50.65 | Aizawl Road North Division | [8 empty] | Not yet started
SUB-DIVISION-II
207 | Construction of Link Drain from Lalzarliana at High School Veng at Zemabawk | 6.4 | Aizawl Road North Division |  |  | 100% | 3.2 |  |  | 100% | 3.2 | Phy.Completed
208 | Construction of Masonry Step from Pi Zahmingthangi to Dr.Robert Khawlhring Residence at Zemabawk | 7.51 | Aizawl Road North Division |  |  | 100% | 3.75 |  |  | 100% | 3.75 | Phy.Completed
209 | Const.of Link Drain at Mellimual 2 Tuikhur at Zemabawk | 6.4 | Aizawl Road North Division |  |  | 100% | 3.2 |  |  | 100% | 3.2 | Phy.Completed
210 | Construction of Slab Culvert Near Vety Dispensary at Zemabawk | 8.42 | Aizawl Road North Division |  |  | 100% | 4.21 |  |  | 100% | 4.21 | Phy.Completed
211 | Construction of Link drain Near Lalrinmawia Residence at Zemabawk | 4.06 | Aizawl Road North Division |  |  | 100% | 2.03 |  |  | 100% | 2.03 | Phy.Completed
212 | Construction of Side Drain with Cover at Approach Road to Cancer Hospital, Zemabawk | 3.71 | Aizawl Road North Division |  |  | 100% | 1.85 |  |  | 100% | 1.85 | Phy.Completed
213 | Construction of Slab Culvert Including Cross Drainage Dinthar Veng at Zemabawk | 2.03 | Aizawl Road North Division |  |  | 100% | 1.01 |  |  | 100% | 1.01 | Phy.Completed
214 | Construction of U-Shape Side Drain with Cover near Zemabawk North Biak In | 4.24 | Aizawl Road North Division |  |  | 100% | 2.12 |  |  | 100% | 2.12 | Phy.Completed
215 | Construction of Slab Culvert (2 Nos) at Berawlui to Thlanmual to Berawlui School | 12.18 | Aizawl Road North Division |  |  | 100% | 6.09 |  |  | 100% | 6.09 | Phy.Completed
216 | Construction of Slab Culvert including Link Drain at Middle School Veng, Zemabawk | 27 | Aizawl Road North Division |  |  | 100% | 13.5 |  |  | 100% | 13.5 | Phy.Completed
217 | Strengthening of Bethel Veng to High School Veng at Zemabawk | 36.7 | Aizawl Road North Division |  |  | 100% | 18.35 |  |  | 100% | 18.35 | Phy.Completed
218 | Construction of of RCC Frame Retaining Wall Including Concrete Pavement on Approach Road to Zemabawk Thlanmual No.1 | 12 | Aizawl Road North Division |  |  | 100% | 6 |  |  | 100% | 6 | Phy.Completed
219 | Construction of Rertaining Wall on Zemabawk Borth Field | 2.8 | Aizawl Road North Division |  |  | 100% | 1.4 |  |  | 100% | 1.4 | Phy.Completed
220 | Construction of RCC Frame Retaining Wall Beneath Zemabawk Thlanmual | 9.9 | Aizawl Road North Division |  |  | 100% | 4.95 |  |  | 100% | 4.95 | Phy.Completed
221 | Patch repiar & Seal Coating of approach road to cancer Hospital at Zemabawk North | 11.63 | Aizawl Road North Division |  |  | 100% | 5.82 |  |  | 100% | 5.82 | Phy Completed
222 | Widening & Improvement of Approach Road to Cancer Hospital at Zemabawk | 136.46 | Aizawl Road North Division |  |  | 100% | 68.23 |  |  | 100% | 68.23 | Phy.Completed
223 | Widening and Construction of Retaining Wall at landslide prone area on Old Lunglei Road | 11.16 | Aizawl Road North Division |  |  | 100% | 5.58 |  |  | 100% | 5.58 | Phy.Completed
224 | Construction of Retaining Wall near Urban Hospital at Zemabawk | 7.81 | Aizawl Road North Division |  |  | 100% | 3.9 |  |  | 100% | 3.9 | Phy.Completed
225 | Concrete pavement of ANM to CMO at Zemabawk Vengthar Road | 19.72 | Aizawl Road North Division |  |  | 100% | 9.86 |  |  | 100% | 9.86 | Phy.Completed
226 | Construction of Cross drain & PCC Vshape side drain on approach Zemabawk road | 3.6 | Aizawl Road North Division |  |  | 100% |  |  |  | 100% |  | Phy.Completed
227 | Construction of Retaining Wall Beneath Urban hospital at Zemabawk | 7.81 | Aizawl Road North Division |  |  | 100% | 3.9 |  |  | 100% | 3.9 | Phy.Completed
228 | Construction of Galili Veng to Vailui road upon Falkland | 7.1 | Aizawl Road North Division |  |  | 100% |  |  |  | 100% |  | Phy Completed
229 | Construction of Footpath and Retaining Wall on NH-54 near CRPF Camp at Zembawk | 46.57 | Aizawl Road North Division |  |  | 100% | 23.29 |  |  | 100% | 23.29 | Phy.Completed
230 | Construction of Retaining Wall at below R.D Godown at Zemabawk | 10.6 | Aizawl Road North Division |  |  | 100% | 5.3 |  |  | 100% | 5.3 | Phy.Completed
231 | Additional requirement for Construction Retaining Wall at the on-going construction of RCC Balcony Berawtlang approach road due to slide from uphill side | 21.2 | Aizawl Road North Division |  |  | 100% | 10.6 |  |  | 100% | 10.6 | Phy.Completed
232 | Construction of RCC frame R/wall on approach road to seventh Day Adventist Church at Zemabawk | 12.72 | Aizawl Road North Division |  |  | 100% | 6.36 |  |  | 100% | 6.36 | Phy Completed
233 | Widening and Lowering of Sericulture to Thlanmual including conrete pavement & retaining Wall at Zemabawk North | 34.88 | Aizawl Road North Division |  |  | 100% | 17.44 |  |  | 100% | 17.44 | Phy.Completed
234 | Concrete pavement of Kailiana road (balance Portion) | 32.93 | Aizawl Road North Division |  |  | 100% | 16.47 |  |  | 100% | 16.47 | Phy.Completed
235 | Construction of Retaining Wall near Primary School at Zemabawk North | 2.09 | Aizawl Road North Division |  |  | 100% | 1.04 |  |  | 100% | 1.04 | Phy. Completed
236 | Concrete pavement of Dinthar to Muthi Lui kawng including Masonry U-Shape Side Drain at Zemabawk North | 29.87 | Aizawl Road North Division |  |  | 100% | 14.94 |  |  | 100% | 14.94 | Phy. Completed
237 | Construction of RCC Frame retaining wall including temporary side drain at Zemabawk North, Dinthar Veng | 21.2 | Aizawl Road North Division |  |  | 100% | 10.6 |  |  | 100% | 10.6 | Phy. Completed
238 | Widening at portion and construction of Retaining Wall at Zemabawk North Dinthar Veng | 6.36 | Aizawl Road North Division |  |  |  | 3.18 | 100% |  | 100% | 3.18 | Phy Completed
239 | Concrete pavement of Bungbangla approach road | 10.05 | Aizawl Road North Division |  |  | 100% | 5.03 |  |  | 100% | 5.03 | Phy. Completed
240 | Formation cutting only Berawlui Thlanmual to School at Berawlui | 0.53 | Aizawl Road North Division |  |  | 100% | 0.26 |  |  | 100% | 0.26 | Phy. Completed
241 | Construction of Retaining Wall at Lungbial Zemabawk | 10.6 | Aizawl Road North Division |  |  | 100% | 5.3 |  |  | 100% | 5.3 | Phy Completed
242 | Contsruction of Protection work on Lungbial Tuikhur to lalram farm (Landslide areas) (3.Nos.) | 20.99 | Aizawl Road North Division |  |  | 100% | 10.5 |  |  | 100% | 10.5 | Phy Completed
243 | Construction of RCC Balcony at Lungbial | 30.18 | Aizawl Road North Division |  |  | 100% | 15.09 |  |  | 100% | 15.09 | Phy. Completed
244 | Construction of RCC Frame Retaining Wall Including Concrete Pavement on Approach Road to Zemabawk thlanmual No.1 | 12 | Aizawl Road North Division |  |  | 100% | 6 |  |  | 100% | 6 | Phy. Completed
245 | Construction of Link Drain, Culvert near primary School including PCC Concrete Pavement at Tuirial | 15.77 | Aizawl Road North Division |  |  | 100% | 7.88 |  |  | 100% | 7.88 | Phy. Completed
246 | Concrete pavement of NH 54 to Tlangveng Kawng at Tuirial (Balalnce portion) | 9.5 | Aizawl Road North Division |  |  | 100% | 4.75 |  |  | 100% | 4.75 | Phy. Completed
247 | Construction of RCC Concrete pavement of approach road to tuirial Lui | 14.6 | Aizawl Road North Division |  |  | 100% | 7.3 |  |  | 100% | 7.3 | Phy. Completed
248 | Concrete pavement of approach road to Tuirial Airfield from NH-54 | 110 | Aizawl Road North Division |  |  | 100% | 55 |  |  | 100% | 55 | Phy. Completed
249 | Profile Correction of Kutcha Road to Tuirial Airfield Mual thlang | 0.11 | Aizawl Road North Division |  |  | 100% | 0.05 |  |  | 100% | 0.05 | Phy. Completed
250 | Construction of PCC V shape Side drain on Muthi peng to Muthi Kawn | 10.93 | Aizawl Road North Division |  |  | 100% | 5.46 |  |  | 100% | 5.46 | Phy. Completed
251 | Construction of concrete pavement, retaining wall, PCC V shape drain & U shape drain at Muthi | 5.3 | Aizawl Road North Division |  |  | 100% | 2.65 |  |  | 100% | 2.65 | Phy. Completed
252 | Construction of PCC pavement of Chawngdailova House Hmingthansanga house, Muthi Vengthlang | 5.94 | Aizawl Road North Division |  |  | 100% | 2.97 |  |  | 100% | 2.97 | Phy. Completed
253 | Construction of Retaining wall near Lamhnai Tuikhur, Muthi | 11.93 | Aizawl Road North Division |  |  | 100% | 5.96 |  |  | 100% | 5.96 | Phy. Completed
254 | Construction of RCC Frame Retaining wall near Biakmawii residence at Muthi | 6.29 | Aizawl Road North Division |  |  | 100% | 3.14 |  |  | 100% | 3.14 | Phy. Completed
255 | Construction of PCC pavement of Sangnghinglove house to Engzami house, Muthi | 4.16 | Aizawl Road North Division |  |  | 100% | 2.08 |  |  | 100% | 2.08 | Phy. Completed
256 | Construction of Retaining wall on approach road to Muthi (1.800 kmp) | 7.5 | Aizawl Road North Division |  |  | 100% | 3.75 |  |  | 100% | 3.75 | Phy Completed
257 | Strengthening of Approach road to LED Complex Muanna Veng including drainage work (Balance portion) Bituminous pavement | 54.7 | Aizawl Road North Division |  |  | 100% | 27.35 |  |  | 100% | 27.35 | Phy.Completed
258 | PCC U shape side drain | 0 | Aizawl Road North Division |  |  | 100% | - |  |  | 100% |  | Phy Completed
259 | Concrete pavement of approach road to Muanna Veng Cemetary | 20.29 | Aizawl Road North Division |  |  | 100% | 10.14 |  |  | 100% | 10.14 | Phy.Completed
260 | Concrete pavement of approach road to YMA House at Muanna Veng | 8.12 | Aizawl Road North Division |  |  | 100% | 4.06 |  |  | 100% | 4.06 | Phy.Completed
261 | Junction improvement & strengthening of Zeda approach road including side drain, retaining walls at Zuangtui Resurfacing | 84.27 | Aizawl Road North Division |  |  | 100% | 42.14 |  |  | 100% | 42.14 | Phy.Completed
| Concrete pavement | 0 |  |  |  | 100% | - |  |  | 100% | - | Phy. Completed
262 | Concrete Pevement of Swan Industry to RK Lianzuala House at Zuangtui | 27.18 | Aizawl Road North Division |  |  | 100% | 13.59 |  |  | 100% | 13.59 | Phy. Completed
263 | Concrete Pavementof Zuangtui Vengthar road at Zuangtui | 39.82 | Aizawl Road North Division |  |  | 100% | 19.91 |  |  | 100% | 19.91 | Phy. Completed
264 | Construction of Retaining Wall at Zuangtui Industry Mual | 9.64 | Aizawl Road North Division |  |  | 100% | 4.82 |  |  | 100% | 4.82 | Phy. Completed
265 | Construction of Retaining Wall on approach road to Chhim Veng near Pi Ronghaki's House at Zuangtui | 8.48 | Aizawl Road North Division |  |  | 100% | 4.24 |  |  | 100% | 4.24 | Phy. Completed
266 | Earth work cutting, Construction of Retaining Wall, & Concrete flooring of Futsal Ground at Zuangtui Industry Mual | 63.02 | Aizawl Road North Division |  |  | 100% | 31.51 |  |  | 100% | 31.51 | Phy. Completed
267 | Concrete flooring of Futsal Ground at zuangtui | 22.94 | Aizawl Road North Division |  |  | 100% | 11.47 |  |  | 100% | 11.47 | Phy. Completed
268 | Construction of PCC Pavement on Zuangtui Vengthar (Balance Portion) | 31 | Aizawl Road North Division |  |  | 100% | - |  | - | 100% | - | Phy Completed
269 | Construction of PCC V-Shape side drain on Zuangtui road to Thuampui Primary School | 3.5 | Aizawl Road North Division |  |  | 100% | - |  | - | 100% | - | Phy Completed
270 | Construction of PCC V-shaped side drain near Pu Kama House, Laipuitlang | 0.37 | Aizawl Road North Division |  |  | 100% | 0.18 |  |  | 100% | 0.18 | Phy. Completed
271 | Construction of PCC V-shaped Side Drain near Pu Zakamlova House, Laipuitlang | 0.53 | Aizawl Road North Division |  |  | 100% | 0.26 |  |  | 100% | 0.26 | Phy. Completed
272 | Construction of PCC V-shaped Side Drain near Pu Lalengmawia House, Laipuitlang | 0.63 | Aizawl Road North Division |  |  | 100% | 0.32 |  |  | 100% | 0.32 | Phy. Completed
273 | Construction of PCC V-shaped Side Drain near Pu Marka House, Laipuitlang | 0.46 | Aizawl Road North Division |  |  | 100% | 0.23 |  |  | 100% | 0.23 | Phy. Completed
274 | Construction of Side Drain near Nazareth Hospital to DIET Junction at Chaltlang | 8.05 | Aizawl Road North Division |  |  | 100% | 4.02 |  |  | 100% | 4.02 | Phy. Completed
275 | Construction of of Side Drain with Cover between H.Hiato House to high School, Chaltlang | 8 | Aizawl Road North Division |  |  | 100% | 4 |  |  | 100% | 4 | Phy. Completed
276 | Construction of Retaining Wall at Chaltlang mear Pu Rophira's House | 4 | Aizawl Road North Division |  |  | 100% | 2 |  |  | 100% | 2 | Phy Completed
277 | DIET Junction improvement | 57.03 | Aizawl Road North Division |  |  | 100% | 28.51 |  |  | 100% | 28.51 | Phy. Completed
278 | Construction of concrete Pavement of Chanmari Thlanmual Courtyard including junction Improvement (Sh: Seal Coating) | 2.35 | Aizawl Road North Division |  |  | 100% | - |  | - | 100% | - | Phy Completed
| (Sh: RCC Frame Retaining Wall) | 3.25 |  |  |  | 100% | 1.63 |  |  | 100% | 1.63 | Phy Completed
| (Sh: Concrete Pavement) | 12.42 |  |  |  | 100% | 6.21 |  |  | 100% | 6.21 | Phy Completed
279 | Construction of Protection Work for P&E Transformer at DIET Junction Chaltlang | 9.54 | Aizawl Road North Division |  |  | 100% | 4.77 |  |  | 100% | 4.77 | Phy Completed
280 | Construction of Concrete Pavement Chaltlang Lily Veng Cemetrery Road | 7.26 | Aizawl Road North Division |  |  | 100% | 3.63 |  |  | 100% | 3.63 | Phy Completed
281 | Construction of Retaing Wall at Chaltlang Lily Veng Cemetrery Road | 4.82 | Aizawl Road North Division |  |  | 100% | 2.41 |  |  | 100% | 2.41 | Phy Completed
282 | Construction of Railing wih chequered tiles at Chaltlang Dawrkawn | 8 | Aizawl Road North Division |  |  | 100% | 4 |  |  | 100% | 4 | Phy Completed
283 | Construction of Retaining Wall and Footpath at Chaltlang Veng Cemetery | 10 | Aizawl Road North Division |  |  | 100% | 5 |  |  | 100% | 5 | Phy Completed
284 | Improvement of Chaltlang Lily Veng to Chaltlang Link step near R.Lalropuia House | 5 | Aizawl Road North Division |  |  | 100% | 2.5 |  |  | 100% | 2.5 | Phy Completed
285 | Construction of approach road PCC & Side Drain from Chaltlang Dingdi Veng Turning Point to H.Lalluaia (L) House at Chaltlang Venglai | 16 | Aizawl Road North Division |  |  | 100% | 8 |  |  | 100% | 8 | Phy Completed
286 | Reconstruction of Chaltlang Lily Veng to Chaltlang Link Road near Lalthuthlungliana House | 8 | Aizawl Road North Division |  |  | 100% | 4 |  |  | 100% | 4 | Phy Completed
287 | Construction of Retaining Wall near Pu Ralkapa House, Laipuitlang | 1.71 | Aizawl Road North Division |  |  | 100% | 0.85 |  |  | 100% | 0.85 | Phy Completed
288 | Construction of Retaining Wall near Pu Kama House, Laipuitlang | 1.19 | Aizawl Road North Division |  |  | 100% | 0.6 |  |  | 100% | 0.6 | Phy Completed
289 | Construction of Masonry Step including Hand Railing near Pu Kama House, Laipuitlang | 1.47 | Aizawl Road North Division |  |  | 100% | 0.73 |  |  | 100% | 0.73 | Phy Completed
290 | Construction of Retaining Wall near Pu Duhzuala House, Laipuitlang | 2.61 | Aizawl Road North Division |  |  | 100% | 1.31 |  |  | 100% | 1.31 | Phy Completed
291 | Construction of Step in concrete over Link Drain including Railing near Community Hall, Laipuitlang | 4.05 | Aizawl Road North Division |  |  | 100% | 2.03 |  |  | 100% | 2.03 | Phy Completed
292 | Construction of Retaining Wall including hand Railing near Pu Rama House, Laipuitlang | 1.86 | Aizawl Road North Division |  |  | 100% | 0.93 |  |  | 100% | 0.93 | Phy Completed
293 | Construction of Retaining Wall including hand Railing near Pi Dawli House, Laipuitlang | 3.37 | Aizawl Road North Division |  |  | 100% | 1.69 |  |  | 100% | 1.69 | Phy Completed
294 | Construction of Retaining Wall near Jubilee Hall Laipuitlang | 1.56 | Aizawl Road North Division |  |  | 100% | 0.78 |  |  | 100% | 0.78 | Phy Completed
295 | Construction of Hand Railing near C.Zonunmawia House, Laipuitlang | 0.63 | Aizawl Road North Division |  |  | 100% | 0.32 |  |  | 100% | 0.32 | Phy Completed
296 | Construction of Retaining Wall at Chaltlang near T.Thangchungnunga (L) | 4 | Aizawl Road North Division |  |  | 100% | 2 |  |  | 100% | 2 | Phy Completed
297 | Construction of PCC U-Shape Side Drain near Pu Thanseia House, Bawngkawn | 0.3 | Aizawl Road North Division |  |  | 100% | 0.15 |  |  | 100% | 0.15 | Phy Completed
298 | Construction of PCC U-Shape Side Drain including Steel Railing near Pu Lalduhkima House, Bawngkawn | 5.52 | Aizawl Road North Division |  |  | 100% | 2.76 |  |  | 100% | 2.76 | Phy Completed
299 | Construction of step over Link Drain including Railing near K.Lalhlunchhungi residence at Bawngkawn | 18.42 | Aizawl Road North Division |  |  | 100% | 9.21 |  |  | 100% | 9.21 | Phy Completed
300 | Construction of Link Drain Cover near Pu R.Romawia House at Bawngkawn | 4 | Aizawl Road North Division |  |  | 100% | 2 |  |  | 100% | 2 | Phy Completed
301 | Construction of Side Drain near Pu ElBethela House at Bawngkawn | 0.4 | Aizawl Road North Division |  |  | 100% | 0.2 |  |  | 100% | 0.2 | Phy Completed
302 | Construction of Side Drain near Pu Salemthara House at Bawngkawn | 1.3 | Aizawl Road North Division |  |  | 100% | 0.65 |  |  | 100% | 0.65 | Phy Completed
303 | Construction of Concrete Pavement of Brigade Slaughter House Road Bawngkawn | 58.3 | Aizawl Road North Division |  |  | 100% | 29.15 |  |  | 100% | 29.15 | Phy. Completed
304 | Construction of Brigade Internal Road at Bawngkawn | 14.84 | Aizawl Road North Division |  |  | 100% | 7.42 |  |  | 100% | 7.42 | Phy. Completed
305 | Construction of Steel Railing near Pu Rintluanga House, Bawngkawn | 2.18 | Aizawl Road North Division |  |  | 100% | 1.09 |  |  | 100% | 1.09 | Phy. Completed
306 | Construction of Step at Zotui Kawng at Bawngkawn | 2 | Aizawl Road North Division |  |  | 100% | 1 |  |  | 100% | 1 | Phy. Completed
307 | Construction of Step near PC Mawia House, Bawngkawn | 11 | Aizawl Road North Division |  |  | 100% | 5.5 |  |  | 100% | 5.5 | Phy. Completed
308 | Construction of Step and Hand railing at Shalom Veng | 8 | Aizawl Road North Division |  |  | 100% | 4 |  |  | 100% | 4 | Phy. Completed
309 | Construction RCC Balcony at YMA Zampuimanga | 5 | Aizawl Road North Division |  |  | 100% | 2.5 |  |  | 100% | 2.5 | Phy. Completed
310 | Construction of Step near Ramdinthara Tuikhur | 2 | Aizawl Road North Division |  |  | 100% | 1 |  |  | 100% | 1 | Phy. Completed
311 | Construction of Approach Road to Helipad from Bawngkawn Shalom Veng | 16 | Aizawl Road North Division |  |  | 100% | 8 |  |  | 100% | 8 | Phy. Completed
312 | PCC Flooring near Upa Chaldailova House, Bawngkawn | 3 | Aizawl Road North Division |  |  | 100% | 1.5 |  |  | 100% | 1.5 | Phy. Completed
313 | Construction of Step on Zotui Kawng | 2 | Aizawl Road North Division |  |  | 100% | 1 |  |  | 100% | 1 | Phy. Completed
314 | Construction of Approach Road from JK Manga House to Thlanmual Kawng | 10 | Aizawl Road North Division |  |  | 100% | 5 |  |  | 100% | 5 | Phy. Completed
315 | Construction of RCC Balcony on Approach Road to Bawngkawn Cemetry | 41.59 | Aizawl Road North Division |  |  | 100% | 20.79 |  |  | 100% | 20.79 | Phy. Completed
316 | Construction of Masonry U-Shape Side Drain at Thuampui Internal Road | 4.24 | Aizawl Road North Division |  |  | 100% | 2.12 |  |  | 100% | 2.12 | Phy. Completed
317 | Construction of Side Drain with cover at Zemabawk North Presbyterian Church Courtyard | 3.71 | Aizawl Road North Division |  |  | 100% | 1.86 |  |  | 100% | 1.86 | Phy. Completed
318 | Construction of Culvert Side Drain & RCC Frame Retaining Wall on Approach Road to Thuampui Cemetry | 11.34 | Aizawl Road North Division |  |  | 100% | 5.67 |  |  | 100% | 5.67 | Phy. Completed
319 | Concrete Pavement & Drainage works on Thuampui PRIMARY School to Zuangtui Vengthar (Balance Portion ) | 53.57 | Aizawl Road North Division |  |  | 100% | 26.78 |  |  | 100% | 26.78 | Phy. Completed
320 | Construction of Retaining Wall at 8.040Kmp on Thuampui - selesih Road | 9.95 | Aizawl Road North Division |  |  | 100% | 4.97 |  |  | 100% | 4.97 | Phy. Completed
321 | Construction of Concrete Pavement Approach Road to PB Vanlalauva Camping Center at Thuampui Selesih Road (Gospel Thunder Team) | 21.2 | Aizawl Road North Division |  |  | 100% | 10.6 |  |  | 100% | 10.6 | Phy. Completed
322 | Pavement of Thuampui Helipad | 24 | Aizawl Road North Division |  |  | 100% | 12 |  |  | 100% | 12 | Phy. Completed
323 | Construction of RCC Balcony on Durtlang Leitan to Thuampui Selesih Road at Ch:1.840 Kmp | 100.59 | Aizawl Road North Division |  |  | 60% | - |  | - | 60% | - | Work in Progress
324 | Construction of Retaining Wall on Thuampui to Selesih Road at Ch:4.350 Kmp | 4 | Aizawl Road North Division |  |  | 100% | 2 |  |  | 100% | 2 | Phy Completed
325 | Clearing of Landslip under Aizawl Road North Division | 9.2 | Aizawl Road North Division |  |  | 100% | 4.6 |  |  | 100% | 4.6 | Phy. Completed
326 | Seal Coating of Thuampui Cemetry Road | 29.83 | Aizawl Road North Division |  |  | 100% | 14.91 |  |  | 100% | 14.91 | Phy Completed
327 | Construction of Retaining Wall at Salvation Army Turning Point, Thuampui | 3.94 | Aizawl Road North Division |  |  | 100% | 1.97 |  |  | 100% | 1.97 | Phy. Completed
328 | Concrete Pavement of Govt. Welfare Road at Thuampui | 37.94 | Aizawl Road North Division |  |  | 100% | 18.97 |  |  | 100% | 18.97 | Phy. Completed
329 | Earthwork Cutting, Construction of Retaining Wall & PCC Flooring of Futsal Ground at Thuampui | 51 | Aizawl Road North Division |  |  | 100% | 25.5 |  |  | 100% | 25.5 | Phy. Completed
330 | Construction of Approach Road to Thuampui Vengthar at Thuampui | 18.61 | Aizawl Road North Division |  |  | 100% | 9.3 |  |  | 100% | 9.3 | Phy. Completed
331 | Construction of Road below Thuampui Presbyterian Church | 15.9 | Aizawl Road North Division |  |  | 100% | 7.95 |  |  | 100% | 7.95 | Phy. Completed
332 | Concrete Pavement of liansailova Road, Thuampui | 26.97 | Aizawl Road North Division |  |  | 100% | 13.48 |  |  | 100% | 13.48 | Phy. Completed
333 | Construction of Gallery including Side Drain at Falkland | 6.9 | Aizawl Road North Division |  |  | 100% | 3.45 |  |  | 100% | 3.45 | Phy. Completed
334 | Construction of Masonry Link Drain near Mizoram UPC Chuech at Falkland | 5.32 | Aizawl Road North Division |  |  | 100% | 2.66 |  |  | 100% | 2.66 | Phy. Completed
335 | Seal Coating of Hebrai Veng at Falkland | 23.74 | Aizawl Road North Division |  |  | 100% | 11.87 |  |  | 100% | 11.87 | Phy Completed
336 | Construction of Retaining Wall on Tuikhur thlang at Falkland East including Masonry Cross Drain | 11.32 | Aizawl Road North Division |  |  | 100% | 5.66 |  |  | 100% | 5.66 | Phy. Completed
337 | Concrete Pavement at Falkland Veng | 15.27 | Aizawl Road North Division |  |  | 100% | 7.63 |  |  | 100% | 7.63 | Phy. Completed
338 | Construction of Step at Falkland Cemetry | 4.77 | Aizawl Road North Division |  |  | 100% | 2.38 |  |  | 100% | 2.38 | Phy. Completed
339 | Construction of Thlanmual No. 1 Shed at Falkland | 5.3 | Aizawl Road North Division |  |  | 100% | 2.65 |  |  | 100% | 2.65 | Phy. Completed
340 | Concrete Pavement of Peniel Road at Falkland | 13 | Aizawl Road North Division |  |  | 100% | 6.5 |  |  | 100% | 6.5 | Phy. Completed
341 | Bituminous pavement of Falkland East internal Road | 15 | Aizawl Road North Division |  |  | 100% | 7.5 |  |  | 100% | 7.5 | Phy. Completed
342 | Patch repair and Seal Coating of Middle School | 19.88 | Aizawl Road North Division |  |  | 100% | 9.94 |  |  | 100% | 9.94 | Phy. Completed
343 | Improvement of Approach Road to Falkland East Junction (Sh:Construction of RCC Framed Structure Retaining Wall) | 4.72 | Aizawl Road North Division |  |  | 100% | 2.36 |  |  | 100% | 2.36 | Phy Completed
344 | Improvement of Approach Road to Falkland East Junction (Sh:Pavement) | 2.79 | Aizawl Road North Division |  |  | 100% | 1.39 |  |  | 100% | 1.39 | Phy Completed
345 | Construction of Link Drain Near Pu Lalngamliana House to Sihphir Venglai | 6.96 | Aizawl Road North Division |  |  | 100% | 3.48 |  |  | 100% | 3.48 | Phy. Completed
346 | Construction of Concrete Pavement Link road from Sihphir Kawnveng to Khamrang Road (i/c Seal Coating of Sihphir Bypass Road via Selesih | 42.4 | Aizawl Road North Division |  |  | 100% | 21.2 |  |  | 100% | 21.2 | Phy Completed
347 | Construction of PCC V-Shape Side Drain on Sihphir Lower Lane, Sihphir Venghlun | 1 | Aizawl Road North Division |  |  | 100% | 0.5 |  |  | 100% | 0.5 | Phy. Completed
348 | Construction of Link Drain including extention of Culvert Near Pu Lalruatvela House, Sihphir Venghlun | 2.98 | Aizawl Road North Division |  |  | 100% | 1.49 |  |  | 100% | 1.49 | Phy. Completed
349 | Construction of Link Drain near Pu Lalngamliana House to Sihphir Venglai Biak In, Sihphir (Balance) | 5.3 | Aizawl Road North Division |  |  | 100% | 2.65 |  |  | 100% | 2.65 | Phy. Completed
350 | Construction of Cross Drainage, Passing place on Approach Road to Nausel | 5.89 | Aizawl Road North Division |  |  | 100% | 2.94 |  |  | 100% | 2.94 | Phy. Completed
351 | Construction of PCC V-Shape Side Drain on Nausel Road | 10.6 | Aizawl Road North Division |  |  | 100% | 5.3 |  |  | 100% | 5.3 | Phy. Completed
352 | Construction of Retaining Wall Sihphir Bypass Road | 15.03 | Aizawl Road North Division |  |  | 100% | 7.52 |  |  | 100% | 7.52 | Phy. Completed
353 | Concrete Pavement of Approach Road to Lalbiaki Residence to YMA Park at Sihphir Hmar Veng | 19.89 | Aizawl Road North Division |  |  | 100% | 9.95 |  |  | 100% | 9.95 | Phy. Completed
354 | Widening of Approach Road to SBI from Sihphir Lower lane Beneath Salvation Army Church | 7.89 | Aizawl Road North Division |  |  | 100% | 3.94 |  |  | 100% | 3.94 | Phy. Completed
355 | Construction of PCC Pavement High Atitude panna kawng | 16.23 | Aizawl Road North Division |  |  | 100% | 8.11 |  |  | 100% | 8.11 | Phy. Completed
356 | Constriction of Retaining Wall including Link Drain near K.Lalengzauva house at Sihphir Venghlun | 11.32 | Aizawl Road North Division |  |  | 100% | 5.66 |  |  | 100% | 5.66 | Phy. Completed
357 | Construction of Retaining Wall near Pi Remthangi Residence on Nausel Road, Sihphir Venghlun | 14.79 | Aizawl Road North Division |  |  | 100% | 7.4 |  |  | 100% | 7.4 | Phy. Completed
358 | Concrete Pavement of Approach Road to Sihphir Venghlun Cemetry | 10.06 | Aizawl Road North Division |  |  | 100% | 5.03 |  |  | 100% | 5.03 | Phy. Completed
359 | Concrete Pavement of Sihphir Venghlun Khawhnuai to Multipurpose Hall | 54.59 | Aizawl Road North Division |  |  | 100% | 27.3 |  |  | 100% | 27.3 | Phy Completed
360 | Concrete Pavement of Nausel Field Thlang | 12.23 | Aizawl Road North Division |  |  | 100% | 6.11 |  |  | 100% | 6.11 | Phy. Completed
361 | Construction of Slab Culvert from Sihphir to Khamrang Road | 21.2 | Aizawl Road North Division |  |  | 100% | 10.6 |  |  | 100% | 10.6 | Phy. Completed
362 | Construction of RCC V-Shape Side Drain on Durtlang Leitan | 3.17 | Aizawl Road North Division |  |  | 100% | 1.58 |  |  | 100% | 1.58 | Phy Completed
363 | Construction of Masonry Cross Drain with Cover near Leitan 'S' Presbyterian Church | 2.61 | Aizawl Road North Division |  |  | 100% | 1.3 |  |  | 100% | 1.3 | Phy Completed
364 | Construction of U-Shape Side Drain on BSNL Junction near Pu Rinawma House, Durtlang North | 4 | Aizawl Road North Division |  |  | 100% | 2 |  |  | 100% | 2 | Phy Completed
365 | Extension of RCC Slab Culvert at Arbai Veng, Durtlang | 1.5 | Aizawl Road North Division |  |  | 100% | 0.75 |  |  | 100% | 0.75 | Phy Completed
366 | Construction of RCC Slab Culvert between Pi Saii and Pi Purni House, Durtlang Leitan | 5.25 | Aizawl Road North Division |  |  | 100% | 2.62 |  |  | 100% | 2.62 | Phy Completed
367 | Concrete Flooring, Drain with Cover & RCC Balcony from Zuangtui road to Pu Lalhmachhuana's House at Durtlang Venglai | 22.36 | Aizawl Road North Division |  |  | 80% | - |  | - | 80% | - | Work in Progress
368 | Construction of Step with Cheqered Tile including Railing near Pi Ngurmawii, Durtlang Leitan | 8 | Aizawl Road North Division |  |  | 100% | 4 |  |  | 100% | 4 | Phy Completed
369 | Constrution of Retaining Wall near Prsbyterian Church, Dutlang North | 15 | Aizawl Road North Division |  |  | 100% | 7.5 |  |  | 100% | 7.5 | Phy Completed
370 | Constrution of Retaining Wall No.1 at Arbai Peng, Durtlang | 2.83 | Aizawl Road North Division |  |  | 100% | 1.41 |  |  | 100% | 1.41 | Phy Completed
371 | Constrution of Retaining Wall No.2 at Arbai Peng, Durtlang | 5.67 | Aizawl Road North Division |  |  | 100% | 2.83 |  |  | 100% | 2.83 | Phy Completed
372 | Widening near Leitan's Presbyterian Church, Durtlang | 2.73 | Aizawl Road North Division |  |  | 100% | 1.37 |  |  | 100% | 1.37 | Phy Completed
373 | PCC Pavement near Zakianglova House, Durtlang North | 4 | Aizawl Road North Division |  |  | 100% | 2 |  |  | 100% | 2 | Phy Completed
374 | Constrution of Retaining Wall Unit-I, Durtlang Leitan | 3.6 | Aizawl Road North Division |  |  | 100% | 1.8 |  |  | 100% | 1.8 | Phy Completed
375 | Constrution of Retaining Wall Unit-I, Durtlang Leitan | 0.82 | Aizawl Road North Division |  |  | 100% | 0.41 |  |  | 100% | 0.41 | Phy Completed
376 | Constrution of Retaining Wall Unit-I, Durtlang Leitan | 2.69 | Aizawl Road North Division |  |  | 100% | 1.34 |  |  | 100% | 1.34 | Phy Completed
377 | Constrution of Retaining Wall Unit-I, Durtlang Leitan | 2.8 | Aizawl Road North Division |  |  | 100% | 1.4 |  |  | 100% | 1.4 | Phy Completed
378 | PCC Pavement Zion Veng to Suaka Veng at Durtlang | 3 | Aizawl Road North Division |  |  | 100% | 1.5 |  |  | 100% | 1.5 | Phy Completed
379 | PCC Pavement Upper SL Road at Durtlang | 2.5 | Aizawl Road North Division |  |  | 100% | 1.25 |  |  | 100% | 1.25 | Phy Completed
380 | PCC Pavement Upper SL Road at Durtlang | 2.5 | Aizawl Road North Division |  |  | 100% | 1.25 |  |  | 100% | 1.25 | Phy Completed
381 | PCC Pavement on Local Council Road, Durtlang | 8 | Aizawl Road North Division |  |  | 100% | 4 |  |  | 100% | 4 | Phy Completed
382 | PCC Pavement on Chhingtei Road, Durtlang | 8 | Aizawl Road North Division |  |  | 100% | 4 |  |  | 100% | 4 | Phy Completed
383 | Construction of Kawmzawl to Centenary Road at durtlang including RCC pavement | 8 | Aizawl Road North Division |  |  | 100% | 4 |  |  | 100% | 4 | Phy Completed
384 | RCC Pavement at Lanu Road, Mizoram UPC to Presbyterian Chucrh at Suaka Veng, Durtlang | 8 | Aizawl Road North Division |  |  | 100% | 4 |  |  | 100% | 4 | Phy Completed
385 | RCC pavement at Selesih | 8 | Aizawl Road North Division |  |  | 100% | 4 |  |  | 100% | 4 | Phy Completed
386 | Construction of Slab Culvert near Pu Thawmtea's house | 7 | Aizawl Road North Division |  |  | 100% | 3.5 |  |  | 100% | 3.5 | Phy.Completed
387 | Improvement of Y-Road Junction | 5.44 | Aizawl Road North Division |  |  | 100% | 2.72 |  |  | 100% | 2.72 | Phy. Completed
388 | Improvement of Y-Road near Pu Sajjal Residence | 0.96 | Aizawl Road North Division |  |  | 100% | 0.48 |  |  | 100% | 0.48 | Phy. Completed
389 | Pavement of Sihphir By-pass Road | 4.41 | Aizawl Road North Division |  |  | 100% | 2.21 |  |  | 100% | 2.21 | Phy.Completed
390 | Imrpvement of Road Profile and PCC Pavement at Falkland | 2.42 | Aizawl Road North Division |  |  | 100% | 1.21 |  |  | 100% | 1.21 | Phy.Completed
391 | Construction of PCC V Shape side drain near Pu BM-a House | 0.3 | Aizawl Road North Division |  |  | 100% | 0.15 |  |  | 100% | 0.15 | Phy Completed
392 | Construction of Hand Railing near Papuia House | 0.72 | Aizawl Road North Division |  |  | 100% | 0.36 |  |  | 100% | 0.36 | Phy Completed
393 | Construction of Hand Railing near Chhunglawmi House at Durtlang Leitan | 3.7 | Aizawl Road North Division |  |  | 100% | 1.85 |  |  | 100% | 1.85 | Phy Completed
394 | Construction of Hand Railing Pu Malsawma House to Upa Zairemmawia House at Zotui Veng Durtlang | 2.65 | Aizawl Road North Division |  |  | 100% | 1.33 |  |  | 100% | 1.33 | Phy Completed
395 | Imrprovement of Bethel veng road at zemabawk, Aizawl in Mizoram for the the year 2022-2023 | 318 | Aizawl Road North Division |  |  | 100% | 159 |  |  | 100% | 159 | Phy Completed
396 | Imrprovement of Thuampui-Selesih road (uoto 5.120 Km)Aiawl in Mizoram for the the year 2022-2024 | 370 | Aizawl Road North Division |  |  | 100% | 185 |  |  | 100% | 185 | Phy. Completed
397 | Construction of Side Drain with cover at zemabawk North Presbyterian kawt | 12 | Aizawl Road North Division |  |  | 100% | 6 |  |  | 100% | 6 | Phy. Completed
SUB DIVISION-III
Construction and Upgradation of connectivity from Kangthelhkawn - Ainawn - Luangmual by creating a new alternative road
398 | Repair of culvert wing wall near Mimi's House on Chhangurkawn to Govt.Complex | 1.27 | Aizawl Road North Division |  |  | 100% | 0.64 |  |  | 100% | 0.64 | Phy.Completed
399 | Improvement and Widening of approach road to MPRO Quarter (Sh: Construction of Pavement) | 75.88 | Aizawl Road North Division |  |  | 70% | 37.94 | 10% |  | 80% | 37.94 | Work in progress
400 | Improvement and Widening of approach road to MPRO Quarter (Sh: 1. Construction of Slab Culvert @ ch.0.050 Kmp | 3.51 | Aizawl Road North Division |  |  | 100% | 1.76 |  |  | 100% | 1.76 | Phy.Completed
401 | 2. Construction of Slab Culvert @ ch.0.510 Kmp | 3.5 | Aizawl Road North Division |  |  | 100% | 1.75 |  |  | 100% | 1.75 | Phy.Completed
402 | 3. Construction of Slab Culvert @ ch.0.650 Kmp | 3.52 | Aizawl Road North Division |  |  | 100% | 1.76 |  |  | 100% | 1.76 | Phy.Completed
403 | 4. Construction of Breast Wall @ ch.0.550 Kmp | 5.51 | Aizawl Road North Division |  |  | 100% | 2.76 |  |  | 100% | 2.76 | Phy.Completed
404 | 5. Construction of Breast Wall @ ch.0.410 Kmp | 8.06 | Aizawl Road North Division |  |  | 100% | 4.03 |  |  | 100% | 4.03 | Phy.Completed
405 | 6. Construction of Link Drain | 8.4 | Aizawl Road North Division |  |  | 100% | 4.2 |  |  | 100% | 4.2 | Phy.Completed
406 | 7. Construction of V-Shape side drain | 2.01 | Aizawl Road North Division |  |  | 100% | 1.01 |  |  | 100% | 1.01 | Phy.Completed
407 | Construction of RCC Frame struction Retaining Wall & Hume pipe Culvert with link drain on Approach Road to Govt.Housing Complex, at Luangmual at Ch 0.100Kmp Sh: 1. Retaining Wall | 14.03 | Aizawl Road North Division | [8 empty] | Not Yet Started
408 | 2. Humne Pipe Culvert | 3.62 | Aizawl Road North Division |  |  | 80% | 1.81 | 20% |  | 100% | 1.81 | Phy.Completed
409 | 3. Linked Drain | 4.77 | Aizawl Road North Division | [8 empty] | Not Yet Started
410 | Construction of Breast Wall near Pu Lalrinawma House at Luangmual | 5.08 | Aizawl Road North Division |  |  | 100% | 2.54 |  |  | 100% | 2.54 | Phy Completed
411 | Construction of Road at Ainawn Veng, Aizawl Sh: 1. Earth Work Formation cutting | 41.17 | Aizawl Road North Division |  |  | 100% | 20.59 |  |  | 100% | 20.59 | Phy.Completed
412 | 2. Construction of RCC Slab Culvert Type-I | 13.58 | Aizawl Road North Division |  |  | 100% | 6.79 |  |  | 100% | 6.79 | Phy.Completed
413 | 3. Slab-Culvert-II | 16.79 | Aizawl Road North Division |  |  | 100% | 8.4 |  |  | 100% | 8.4 | Phy.Completed
414 | Construction of road at Chawnpui, Aizawl Sh: 1. Earth Work Formation cutting | 38.02 | Aizawl Road North Division |  |  | 100% | 19.01 |  |  | 100% | 19.01 | Phy.Completed
415 | 2. Construction og RCC Slab Vulvert Type-I | 13.57 | Aizawl Road North Division |  |  | 100% |  |  |  | 100% |  | Phy Completed
416 | 3. Construction of TCC Slab Culvert Type-II | 8.4 | Aizawl Road North Division |  |  | 90% |  | 10% |  | 100% |  | Phy Completed
417 | Resurfaccing of Kangthlehkawn to High Court (0.000 to 1.830 Kmp) | 59.29 | Aizawl Road North Division |  |  | 100% | 29.65 |  |  | 100% | 29.65 | Phy.Completed
418 | Construction of Approach Road (RCC Pavement) to Chhimveng Presbyterian Church at Ainawn Veng | 31.76 | Aizawl Road North Division |  |  | 100% | 15.88 |  |  | 100% | 15.88 | Phy.Completed
Construction of Upgradation of Road from Dawrpui Vengthar - Vaivakawn - Zotlang - MZU
419 | Construction of Link Drain near P/S at Vaivakawn | 13.92 | Aizawl Road North Division |  |  | 100% |  |  |  | 100% |  | Phy. Completed
420 | RCC Link Drain with Cover Step K.Buanga's House approach to NH-06, Vaivakawn | 25.42 | Aizawl Road North Division |  |  | 100% |  |  |  | 100% |  | Phy Completed
421 | Rectangular Side Drain with cover near Salvation Army Church at k.Zamawia's House to MZU Road including Cross Drain cover, Vaivakawn | 11.55 | Aizawl Road North Division |  |  | 100% |  |  |  | 100% |  | Phy.Completed
422 | Construction of RCC Mini Bridge near Pi Malsawma's House (Dam veng) | 14.82 | Aizawl Road North Division |  |  | 100% |  |  |  | 100% |  | Phy Completed
423 | Construction of RCC Foot path near Presbyterian Pastor Quarter to Zarkawt approach road at Dawrpui Vengthar | 15.96 | Aizawl Road North Division |  |  | 100% |  |  |  | 100% |  | Phy Completed
424 | RCC approach road to Vanlalzuiliana's House Sh: 1. Construction of Rigid Pavement | 9.21 | Aizawl Road North Division |  |  | 100% | 4.61 |  |  | 100% | 4.61 | Phy Completed
| 2. Construction of V-Shaped Side Drain | 2.22 | Aizawl Road North Division |  |  | 100% | 1.11 |  |  | 100% | 1.11 | Phy Completed
425 | Improvement of road Zotlang, Aizawl Sh: 1.Earth Work Widening of existing road | 9 | Aizawl Road North Division |  |  | 100% | 4.5 |  |  | 100% | 4.5 | Phy.Completed
| 2. Construction of Retaining Wall | 28.52 | Aizawl Road North Division |  |  | 100% | 14.26 |  |  | 100% | 14.26 | Phy.Completed
| 3. Rigid Pavement | 5.58 | Aizawl Road North Division |  |  | 100% | 2.79 |  |  | 100% | 2.79 | Phy.Completed
426 | Road Widening and R/Wall at Pu Rosanga House to Neitumi House, Zohnuai Vaivakawn Sh: Earthwork | 5.41 | Aizawl Road North Division |  |  | 50% | 2.71 |  |  | 50% | 2.71 | Work in progress
| 2. Construction of Slab Culvert @ ch.0.115 Kmp | 3.5 | Aizawl Road North Division |  |  | 50% | 1.75 |  |  | 50% | 1.75 | Work in progress
| 3. Construction of Breast wall | 24.97 | Aizawl Road North Division |  |  | 50% | 12.49 |  |  | 50% | 12.49 | Work in progress
427 | Construction og Retaining Wall on Electric Veng Cemetery Road Sh: 1. Construction og Retaining Wall Section - 1 | 9.95 | Aizawl Road North Division |  |  | 100% | 4.98 |  |  | 100% | 4.98 | Phy.Completed
| 2. Construction og Retaining Wall Section - 2 | 4.76 | Aizawl Road North Division |  |  | 100% | 2.38 |  |  | 100% | 2.38 | Phy.Completed
| 3. Construction og Retaining Wall Section - 3 | 9.32 | Aizawl Road North Division |  |  | 100% | 4.66 |  |  | 100% | 4.66 | Phy.Completed
428 | Construction of Step near Seventh Day Church to Dosangvunga (L) House at Electrict Veng Sh: Construction of Step | 13.9 | Aizawl Road North Division |  |  | 100% | 6.95 |  |  | 100% | 6.95 | Phy.Completed
429 | Construction of Step in concrete over Link Drain including Railing near Presbyterian Jubilee Hall, Laipuitlang | 6.63 | Aizawl Road North Division |  |  | 100% | 3.32 |  |  | 100% | 3.32 | Phy.Completed
Construction and Upgradation of croad from Chanmari West - Hunthar - Edenthar - Rangvamual
430 | Pot Hole Repair & Resurfacing and Seal Coating of Chanmari West to NH-54 | 11.01 | Aizawl Road North Division |  |  | 100% | 5.51 |  |  | 100% | 5.51 | Phy.Completed
431 | Pot Hole Repair & Resurfacing and Seal Coating of Chanmari West to Vaivakawn Road (0.000 - 0.550Kms) | 16.93 | Aizawl Road North Division |  |  | 100% | 8.47 |  |  | 100% | 8.47 | Phy. Completed
432 | Hole Repair & Resurfacing and Seal Coating of edenthar internal (0.000-1.175 Kms) | 15.25 | Aizawl Road North Division |  |  | 100% | 7.63 |  |  | 100% | 7.63 | Phy.Completed
433 | Pot Hole Repair & Resurfacing and Seal Coating of Bt Bakery to turning Point via Middle School at Hunthar (0.000 - 0.175Kms) | 10.16 | Aizawl Road North Division |  |  | 100% | 5.08 |  |  | 100% | 5.08 | Phy.Completed
434 | Pot Hole Repair & Resurfacing and Seal Coating of Edenthar Internal (0.000-1.175 Kms) | 17.46 | Aizawl Road North Division |  |  | 100% | 8.73 |  |  | 100% | 8.73 | Phy.Completed
435 | Construction of Edenthar BPL raod at Edenthar Sh: 1. Estimate for Earthwork | 3.24 | Aizawl Road North Division | [8 empty] | Not Yet Started
436 | 2. Construction of RCC Balcony at Ch. 0.275 Kmp | 11.04 | Aizawl Road North Division | [8 empty] | Not Yet Started
437 | 3. Construction of retaining Wall at Ch.0.190 Kmp | 3.23 | Aizawl Road North Division | [8 empty] | Not Yet Started
438 | 4. Consreruction of Slab Culvert @ch.0.160Kmp | 5.51 | Aizawl Road North Division | [8 empty] | Not Yet Started
439 | 5. Construction of Slab Culvert @ ch.0.200 Kmp | 2.37 | Aizawl Road North Division | [8 empty] | Not Yet Started
440 | Construction of RCC Pavement Edenthar to Chanmari West Road Sh: 1. Construction of RCC Pavement | 78 | Aizawl Road North Division |  |  | 100% | 53.48 |  |  | 100% | 53.48 | Phy.Completed
441 | 2. Construction of Hume Pipe Culvert at Ch.0.037 Kmp | 6.77 | Aizawl Road North Division |  |  | 100% | 3.39 |  |  | 100% | 3.39 | Phy.Completed
442 | Construction of Ram,lai Road at Edenthar Sh: Earth work for Widening of existing road) | 16.95 | Aizawl Road North Division |  |  | 30% | 8.48 |  |  | 30% | 8.48 | Work in progress
443 | Construction of Lunghlu Road at Chanmari West Sh: 1. Earth Work for Formation cutting | 17.52 | Aizawl Road North Division |  |  | 20% |  |  |  | 20% |  | Work stop due to rainy season
444 | 2. Construction of RCC Slab Culvert Type-I | 8.03 | Aizawl Road North Division |  |  | 10% | 4.02 |  |  | 10% | 4.02 | Work in progress
445 | 3. Slab Culvert-II | 33.76 | Aizawl Road North Division | [8 empty] | Not Yet Started
446 | Construction of Retaining Wall near Middle School, Hunthar | 25.41 | Aizawl Road North Division | [8 empty] | Not yet started
447 | Construction of road at Rangvamual, Aizawl Sh: 1. Earth Work for Formation Cutting | 107.52 | Aizawl Road North Division |  |  | 98% | 53.76 | 2% |  | 100% | 53.76 | Phy Completed
448 | 2. Construction of RCC Slab Culvert Type-I | 26.62 | Aizawl Road North Division | [8 empty] | Not yet started
449 | 3. Slab Culvert-II | 24.71 | Aizawl Road North Division | [8 empty] | Not yet started
450 | Patch repairs of Sakawrtuichhun to PTC Road due to vice President visit | 7.18 | Aizawl Road North Division |  |  | 100% | 3.59 |  |  | 100% | 3.59 | Phy.Completed
451 | Construction of Retaining Wall near Lallawmzuala's House at sakawrtuichhun | 5.66 | Aizawl Road North Division |  |  | 100% | 2.83 |  |  | 100% | 2.83 | Phy. Completed
452 | Construction of Dumping Ground at Industrial Areas at Sakawrtuichhun Sh: 1. Earth Work for Formation Cutting of Internal Road | 10.53 | Aizawl Road North Division |  |  | 100% | 5.27 |  |  | 100% | 5.27 | Phy.Completed
453 | 2. Hume Pipe NP4 | 27.27 | Aizawl Road North Division |  |  | 100% | 13.64 |  |  | 100% | 13.64 | Phy.Completed
454 | Construction of Road at Tanhril, Aizawl Sh: 1. Earth Work for Formation Cutting | 80.48 | Aizawl Road North Division |  |  | 100% | 40.24 |  |  | 100% | 40.24 | Phy.Completed
455 | 2. Construction of RCC Slab Culvert Type-I | 27.15 | Aizawl Road North Division |  |  | 100% | 13.58 |  |  | 100% | 13.58 | Phy.Completed
456 | 3. Construction of RCC Slab Culvert Type-II | 16.79 | Aizawl Road North Division |  |  | 100% | 8.4 |  |  | 100% | 8.4 | Phy.Completed
457 | Construcytion of Road at Sakawrtuichhun, Aizawl Sh: 1. Earth Work for Widening of existing Road | 19.53 | Aizawl Road North Division |  |  | 100% | 9.77 |  |  | 100% | 9.77 | Phy.Completed
458 | 2. Construction of Flexible Pavement NBCC Road I & II | 24.82 | Aizawl Road North Division |  |  | 100% | 12.41 |  |  | 100% | 12.41 | Phy. Completed
459 | 3. Construction of RCC Slab Culvert Type-I | 17.84 | Aizawl Road North Division |  |  | 100% | 8.92 |  |  | 100% | 8.92 | Phy Completed
IMPROVEMENT OF RAMRIKAWN TO NH-54 via SAKAWRTUICHHUN
460 | Improvement of Ramrikawn to NH-54 via Sakawrtuichhun Roads in Mizoram for the year 2022-2023 Sh: 1. Pavement of ramrikawn to NH-54 |  | Aizawl Road North Division |  |  | 30% |  | 30% |  | 60% |  | Work progress
461 | 2. Const.of R/Wall at Ch 5.950 Kmp at Sakawrtuichhun | 336 | Aizawl Road North Division |  |  | 100% | 168 |  |  | 100% | 168 | Phy. Completed
462 | 3. Const.of R/W near Zoo Gate, Lungverh |  | Aizawl Road North Division |  |  | 100% |  |  |  | 100% |  | Phy. Completed
463 | 4. Const.of Hume Pipe Culvert at 0.270 Kmp at Sakawrtuichhun |  | Aizawl Road North Division |  |  | 100% |  |  |  | 100% |  | Phy. Completed
464 | 5. Const.of Hume Pipe Culvert at 1.580 Kmp at Sakawrtuichhun |  | Aizawl Road North Division |  |  | 100% |  |  |  | 100% |  | Phy. Completed
KOLASIB DIVISION :
465 | Formation cutting of Serlui Zau at Kawnpui | 46 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 27.52 |  |  | 100% | 27.52 | Phy.Completed
466 | Formation cutting of Panhnah kawn at N.Chaltlang | 28 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 18.71 |  |  | 100% | 18.71 | Phy.Completed
467 | Formation cutting of Kawnpui zau at Bukpui | 28 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 14.06 |  |  | 100% | 14.06 | Phy.Completed
468 | Formation cutting of Tuirial Road at Lungmuat | 28 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 9.4 |  |  | 100% | 9.4 | Phy.Completed
469 | Improvement and Upgradation of Road from Mizo Hotelpui (Diakkawn Bazaar) to NH-306 via KVK (SW: Resurfacing of Mizo Hotelpui to NH-306 via ICAR1(a) | 57.028 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 57.02 |  |  | 100% | 57.02 | Phy.Completed
470 | Improvement and Upgradation of Road from Mizo Hotelpui (Diakkawn Bazaar) to NH-306 via KVK (SW: Hume Pipe Culvert near SIRD Quarter, Vengthar 1(b) | 3.85 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 1.92 |  |  | 100% | 1.92 | Phy.Completed
471 | Improvement and Upgradation of Road from Mizo Hotelpui (Diakkawn Bazaar) to NH-306 via KVK (SW: Hume Pipe Culvert near Pu Sawma's House 1(c) | 8.72 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 4.35 |  |  | 100% | 4.35 | Phy.Completed
472 | Improvement and Upgradation of Road from Mizo Hotelpui (Diakkawn Bazaar) to NH-306 via KVK (SW: Hume Pipe Culvert near S.Kaigina Ventgthar 1(d) | 2.21 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 1.11 |  |  | 100% | 1.11 | Phy.Completed
473 | Improvement and Upgradation of Road from Mizo Hotelpui (Diakkawn Bazaar) to NH-306 via KVK (SW: Const.of V-Shaped SD at Essential Places on Mizo Hotelpui-NH 306 via ICAR 1€ | 9.89 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 4.94 |  |  | 100% | 4.94 | Phy.Completed
474 | Improvement and Upgradation of Road from Mizo Hotelpui (Diakkawn Bazaar) to NH-306 via KVK (Embankment in front of Pu Laltanpuia's House, Vengthar 1(f) | 0.89 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 0.44 |  |  | 100% | 0.44 | Phy.completed
475 | Improvement and Upgradation of Road from Mizo Hotelpui (Diakkawn Bazaar) to NH-306 via KVK (Road Widening below Remsiami's House, Vengthar 1(g) | 0.125 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 0.06 |  |  | 100% | 0.06 | Phy.Completed
476 | Improvement and Upgradation of Road from Mizo Hotelpui (Diakkawn Bazaar) to NH-306 via KVK (SW: Road widening near Leitan, Vengthar 1(h) | 0.89 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 0.44 |  |  | 100% | 0.44 | Phy.Completed
477 | Improvement and Upgradation of Road from Mizo Hotelpui (Diakkawn Bazaar) to NH-306 via KVK (Upgradation of CP Road, New Diakkawn Kolasib (Resurfacing of CP Road) 2(a) | 22.88 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 22.88 |  |  | 100% | 22.88 | Completed
478 | Improvement and Upgradation of Road from Mizo Hotelpui (Diakkawn Bazaar) to NH-306 via KVK (Upgradation of CP Road, New Diakkawn Kolasib (Const.of LSD at CP Road) 2(b) | 9.17 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 4.58 |  |  | 100% | 4.58 | Phy.Completed
479 | Improvement and Upgradation of Road from Mizo Hotelpui (Diakkawn Bazaar) to NH-306 via KVK (SW: Improvement and Upgradation of Soil Peng to KVK (Kawnglaiphei) Resurfacing of Soil Dept.peng to KVK) 3(a) | 46.78 | Kolasib Division | 2023-03-23 | 2023-03-24 | 98% |  |  |  | 98% |  | Work progress
480 | Improvement and Upgradation of Road from Mizo Hotelpui (Diakkawn Bazaar) to NH-306 via KVK SW:Improvement and Upgradation of Soil Peng to KVK (Kawnglaiphei) Hume Pipe Culvert at Middle of the Road) 3 (b) | 3.209 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 1.6 |  |  | 100% | 1.6 | Phy.Completed
481 | Improvement and Upgradation of Road from Mizo Hotelpui (Diakkawn Bazaar) to NH-306 via KVK (Improvement and Upgradation of Soil Peng to KVK (Kawnglaiphei) (Extension of Downstream Hume Pipe Culvert near Pu Lalchhuanawma's House, Vengthar) 3(c) | 2.636 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 1.318 |  |  | 100% | 1.318 | Phy.Completed
482 | Improvement and Upgradation of Road from Mizo Hotelpui (Diakkawn Bazaar) to NH-306 via KVK (Improvement and Upgradation of Soil Peng to KVK (Kawnglaiphei) (Extension of Hume Pipe Culvert near Pu Lalthana House, Vengthar) 3(d) | 7.43 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 3.71 |  |  | 100% | 3.71 | Phy.Completed
483 | Improvement and Upgradation of Road from Mizo Hotelpui (Diakkawn Bazaar) to NH-306 via KVK (Improvement and Upgradation of Soil Peng to KVK (Kawnglaiphei) (Const.of LSD at Essential Places of Soil Dept.peng to KVK 3(e) | 10.78 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 5.39 |  |  | 100% | 5.39 | Phy.Completed
484 | Improvement and Upgradation of Road from Mizo Hotelpui (Diakkawn Bazaar) to NH-306 via KVK (Improvement and Upgradation of Soil Peng to KVK (Kawnglaiphei) (Road Widening near Saichhungi House, Vengthar 3(f) | 0.47 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 0.23 |  |  | 100% | 0.23 | Phy Completed
485 | Improvement and Upgradation of Road from Mizo Hotelpui (Diakkawn Bazaar) to NH-306 via KVK (Improvement and Upgradation of Soil Peng to KVK (Kawnglaiphei) (Road Widening near Masanga House to Pu Tanpuia House, Vengthar 3(g) | 0.645 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 0.32 |  |  | 100% | 0.32 | Phy.Completed
486 | Improvement and Upgradation of Road from Mizo Hotelpui (Diakkawn Bazaar) to NH-306 via KVK (Improvement and Upgradation of Soil Peng to Rammawia's House 4(a) | 11.01 | Kolasib Division | 2023-03-23 | 2023-03-24 | [6 empty] | Not Yet Started
487 | Improvement and Upgradation of Road from Mizo Hotelpui (Diakkawn Bazaar) to NH-306 via KVK (Improvement and Upgradation of Soil Peng to Rammawia's House 4(b) | 4.85 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 2.42 |  |  | 100% | 2.42 | Phy.Completed
488 | Improvement and Upgradation of Road from Mizo Hotelpui (Diakkawn Bazaar) to NH-306 via KVK (Improvement and Upgradation of Soil Peng to Rammawia's House 4(c) | 16.59 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 8.29 |  |  | 100% | 8.29 | Phy.Completed
489 | Improvement and Upgradation of Road from Mizo Hotelpui (Diakkawn Bazaar) to NH-306 via KVK Improvement and Upgradation of ICAR to Dinthar Road 5 | 19.73 | Kolasib Division | 2023-03-23 | 2023-03-24 | [6 empty] | Not yet started
490 | Improvement and Upgradation of Road from Mizo Hotelpui (Diakkawn Bazaar) to NH-306 via KVK Improvement and Upgradation of ICAR to Dinthar Road 5 (a) | 6.93 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 3.46 |  |  | 100% | 3.46 | Phy.Completed
491 | Improvement and Upgradation of Road from Mizo Hotelpui (Diakkawn Bazaar) to NH-306 via KVK Improvement and Upgradation of Road from Hmarveng Tuikhur to NH-306 near Sericulture Complex 6(a) | 0.74 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 0.37 |  |  | 100% | 0.37 | Phy.Completed
492 | Improvement and Upgradation of Road from Mizo Hotelpui (Diakkawn Bazaar) to NH-306 via KVK Improvement and Upgradation of Road from Hmarveng Tuikhur to NH-306 near Sericulture Complex 6(b(i)) | 6.95 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 3.47 |  |  | 100% | 3.47 | Phy.Completed
493 | Improvement and Upgradation of Road from Mizo Hotelpui (Diakkawn Bazaar) to NH-306 via KVK Improvement and Upgradation of Road from Hmarveng Tuikhur to NH-306 near Sericulture Complex 6(b(ii)) | 5.7 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 2.85 |  |  | 100% | 2.85 | Phy.Completed
494 | Improvement and Upgradation of Road from Mizo Hotelpui (Diakkawn Bazaar) to NH-306 via KVK Improvement and Upgradation of Road from Hmarveng Tuikhur to NH-306 near Sericulture Complex 6(b(iii)) | 5.7 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 2.85 |  |  | 100% | 2.85 | Phy.Completed
495 | Improvement and Upgradation of Road from Mizo Hotelpui (Diakkawn Bazaar) to NH-306 via KVK Improvement and Upgradation of Road from Hmarveng Tuikhur to NH-306 near Sericulture Complex 6(c) | 73.7 | Kolasib Division | 2023-03-23 | 2023-03-24 | 65% | 36.85 |  |  | 65% | 36.85 | Work progress
496 | Improvement and Upgradation of Road from Mizo Hotelpui (Diakkawn Bazaar) to NH-306 via KVK Improvement and Upgradation of Road from Hmarveng to Saidan Field via KL Siama's House 7(a) | 20.75 | Kolasib Division | 2023-03-23 | 2023-03-24 | [6 empty] | Not yet started
497 | Improvement and Upgradation of Road from Mizo Hotelpui (Diakkawn Bazaar) to NH-306 via KVK Improvement and Upgradation of Road from Hmarveng to Saidan Field via KL Siama's House 7(b) | 3.66 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 1.83 |  |  | 100% | 1.83 | Phy.Completed
498 | Improvement and Upgradation of Road from Mizo Hotelpui (Diakkawn Bazaar) to NH-306 via KVK Improvement and Upgradation of Road from Hmarveng to Saidan Field via KL Siama's House 7(c) | 5.92 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 2.96 |  |  | 100% | 2.96 | Phy.Completed
499 | Improvement and Upgradation of Road from Mizo Hotelpui (Diakkawn Bazaar) to NH-306 via KVK Widening, Upgradation & Resurfacing of Helipad to Lungsumlui Road 8(a) | 17.64 | Kolasib Division | 2023-03-23 | 2023-03-24 | [6 empty] | Not Yet Started
500 | Improvement and Upgradation of Road from Mizo Hotelpui (Diakkawn Bazaar) to NH-306 via KVK Widening, Upgradation & Resurfacing of Helipad to Lungsumlui Road 8(b) | 1.5 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 0.75 |  |  | 100% | 0.75 | Phy.Completed
501 | Improvement and Upgradation of Road from Mizo Hotelpui (Diakkawn Bazaar) to NH-306 via KVK Widening, Upgradation & Resurfacing of Helipad to Lungsumlui Road 8(c) | 22.71 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 11.35 |  |  | 100% | 11.35 | Phy.Completed
502 | Improvement and Upgradation of Road from Mizo Hotelpui (Improvement & Upgradation of Diakkawn NH-306 to Challui Veng via Galili Veng 9(a) | 18.13 | Kolasib Division | 2023-03-23 | 2023-03-24 | 5% |  |  |  | 5% |  | Work progress
503 | Improvement and Upgradation of Road from Mizo Hotelpui (Improvement & Upgradation of Diakkawn NH-306 to Challui Veng via Galili Veng 9(b) | 15.03 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 7.52 |  |  | 100% | 7.52 | Phy.Completed
504 | Improvement and Upgradation of Road from Mizo Hotelpui (Improvement & Upgradation of Diakkawn NH-306 to Challui Veng via Galili Veng 9(c) | 3.62 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 1.81 |  |  | 100% | 1.81 | Phy.Completed
505 | Improvement and Upgradation of Road from Mizo Hotelpui (Improvement & Upgradation of Diakkawn NH-306 to Challui Veng via Galili Veng 9(d) | 2.97 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 1.48 |  |  | 100% | 1.48 | Phy.Completed
506 | Improvement and Upgradation of Road from Mizo Hotelpui (Improvement & Upgradation of Diakkawn NH-306 to Challui Veng via Galili Veng 9(e) | 1.12 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 0.56 |  |  | 100% | 0.56 | Phy.Completed
507 | Improvement and Upgradation of Road from Mizo Hotelpui (Diakkawn Bazaar) to NH-306 via KVK (SW: PCC Flooring from NH-6 Rengtekawn Kualmawi to Hebron Veng 10 | 28.97 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 14.48 |  |  | 100% | 14.48 | Phy.Completed
508 | Improvement and Upgradation of Road from Mizo Hotelpui (Diakkawn Bazaar) to NH-306 via KVK (SW: PCC Flooring from PWD Town road near KVK Compound to Dinthar Vengthar 11 | 28.98 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 14.49 |  |  | 100% | 14.49 | Phy.Completed
509 | Resurfacing of approach road to Electric veng from Banglakawn, Kolasib | 14.72 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 14.72 |  |  | 100% | 14.72 | Completed
510 | Improvement and Black topping of approach road to Pavillion at Football Playground at Bilkhawthlir | 15.32 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 15.32 |  |  | 100% | 15.32 | Completed
511 | Construction of Retaining wall at Kawnpui Hmarveng Graveland | 5.23 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 5.23 |  |  | 100% | 5.23 | Completed
512 | Resurfacing of Mualvum approach road from Chainage 1.150 Kmp to 2.800 Kmp9 Balance Stretch) | 29.45 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 29.45 |  |  | 100% | 29.45 | Completed
513 | Construction of Masonry Link drain with RCC Slab Cover at PWD Complex, Kawnpui | 4.8 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 4.8 |  |  | 100% | 4.8 | Completed
514 | Restoration of Shoulder subsidence at Ch: 7.35Kmp on Buhchang to Phaisen: a)Repairing of Rigid pavement from km 7/340 to km 7/370 (Length = 30 m) on Buhchang to Phaisen road in the State of Mizoram | 7.8 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 7.8 |  |  | 100% | 7.8 | Completed
515 | b) Construction of Gabion wall at the side shoulder. | 17.55 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 17.55 |  |  | 100% | 17.55 | Completed
516 | c) Construction of Gabion wall at the Toe of the Slip. | 7.35 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 7.35 |  |  | 100% | 7.35 | Completed
517 | d) Construction of Line Side Drain | 5.9 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 5.9 |  |  | 100% | 5.9 | Completed
Construction of PCC Pavement on Phainuam to Saihapui V (Muddy Portion)
518 | a) Repair of Damage Stretch on approach road to Saihapui V | 18 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 18 |  |  | 100% | 18 | Completed
519 | b) Construction of Police Camp approach road at Saihapui V | 7 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 7 |  |  | 100% | 7 | Completed
520 | Patch repair from Thirhruibankawn to Hmarveng via Fire Station | 9.92 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 9.92 |  |  | 100% | 9.92 | Completed
PROJECT DIVISION - I
521 | Extension of Community Hall at Upper Republic | 53 | Project Division-I | 15.3.23 | 15.2.24 | 70% | 24.48 | 5% |  | 75% | 24.48 | Work progress
522 | Construction of RCC slab Dam veng YMA Hall | 4.83 | Project Division-I | 15.3.23 |  | 100% | 2.42 |  |  | 100% | 2.42 | Phy.completed
523 | Construction of Cequered tiles Near Local Council House Bungkawn Vengthar | 1.45 | Project Division-I | 15.3.23 |  | 100% | 0.73 |  |  | 100% | 0.73 | Phy.Completed
524 | Construction of Saizahawla Tuikhur near R.Lalrinchhana Field Road | 7.72 | Project Division-I | 15.3.23 |  | 100% | 3.86 |  |  | 100% | 3.86 | Phy.completed
525 | Construction of RCC Structure at Electric Sub-Station, Khatla, Tlawng Road | 4.8 | Project Division-I | 15.3.23 |  | 100% | 2.4 |  |  | 100% | 2.4 | Phy.Completed
526 | Laying of Chequered Tiles Between Zonghaka and Sk Thanga's House at Nursery | 2.12 | Project Division-I | 15.3.23 |  | 100% | 1.06 |  |  | 100% | 1.06 | Phy.Completed
527 | Laying of Chequered Tiles tetween UPC (Mizoram) and RC Vanlalsawma (L) House at Nursery | 2.69 | Project Division-I | 15.3.23 |  | 100% | 1.35 |  |  | 100% | 1.35 | Phy.Completed
528 | Construction of Chequered tiles near Khatla South Presbyterian | 1.43 | Project Division-I | 15.3.23 |  | 100% | 0.72 |  |  | 100% | 0.72 | Phy.Completed
529 | Constrcution of Chequered tiles between J.Zangena House and Rinsanga Colney (L) near Khatla's Presbyterian Church | 0.98 | Project Division-I | 15.3.23 |  | 100% | 0.49 |  |  | 100% | 0.49 | Phy.Completed
530 | Construction of Step Chequered tiles with Hand Railing near Khatla Pastor Quarter to J.Lianhlira House | 2.84 | Project Division-I | 15.3.23 |  | 100% | 1.42 |  |  | 100% | 1.42 | Phy.Completed
531 | Renovation and linement of new Cemetary at Maubawk | 1.24 | Project Division-I | 15.3.23 |  | 100% | 0.62 |  |  | 100% | 0.62 | Phy.Completed
532 | Renovation of Kanan Multipurpose Community Hall | 14.42 | Project Division-I | 15.3.23 |  | 98% | 7.21 |  |  | 98% | 7.21 | Work in progress
533 | Renovation & Repair of Khatla Bazar Building | 3.86 | Project Division-I | 15.3.23 |  | 100% | 1.93 |  |  | 100% | 1.93 | Phy.Completed
534 | Renovation of Mission Veng Health Clinic at Mission | 1.93 | Project Division-I | 15.3.23 |  | 100% | 0.97 |  |  | 100% | 0.97 | Phy.Completed
535 | Construction of Anganwadi Centre-II, Aizawl | 4.79 | Project Division-I | 15.3.23 |  | 100% | 2.39 |  |  | 100% | 2.39 | Phy.Completed
536 | Construction of Basketball Court at Dinthar | 52.99 | Project Division-I | 15.3.23 |  | 15% | 5.81 |  |  | 15% | 5.81 | Work progress
537 | Construction of Basketball Court at Dinthar | 43.36 | Project Division-I | 15.3.23 |  | 95% | 18.61 | 5% |  | 100% | 18.61 | Phy.Completed
538 | Construction of Basketball Court at Dinthar | 4.82 | Project Division-I | 15.3.23 |  | 100% | 2.41 |  |  | 100% | 2.41 | Phy.Completed
539 | Upgradation of Chief Minister Staff Quarter ( 5 nos of Quarters Phase -I | 193 | Project Division-I | 15.3.23 |  | 100% | 81.46 |  |  | 100% | 81.46 | Phy.Completed
540 | Upgradation of Chief Minister Staff Quarter ( 5 nos of Quarters Phase -II | 95 | Project Division-I | 15.3.23 |  | 100% |  |  |  | 100% |  | Phy.Completed
541 | Constructuction of Government Staff Quarters ( Block-C) at DIET Complex. | 544 | Project Division - I | 10.05.2023 | 10.05.2025 | 30% | 21.63 | 5% |  | 35% | 21.63 | Work in progress
542 | C/O Food Civil Supplies & Consumer Affairs 1500MTGodown at Sairang | 921.07 | Project Division - I | 20.4.23 | 20.4.26 | [6 empty] | Work not started
HMUIFANG DIVISION :
543 | Improvement & Strengthening of Aibawk-Darlung Road for 4.000-14.000 Kmp in Mizoram for the year 2022-2023 | 547 | Hmuifang Division | 20.12.23 | 31.03.23 | 78.45% | 268.96 |  |  | 78.45% | 268.96 | Work in progress
544 | Construction of Agriculture Link Road for Thingzam Zau, Tuirial Lui | 269.6 | Hmuifang Division | 15.02.23 | 14.05.23 | 100% | 127.25 |  |  | 100% | 127.25 | Phy.Completed
545 | Contsruction of Upgradation of Aizawl-Thenzawl-Lunglei Road 5.00 kmp-100.00 Kmp | 206 | Hmuifang Division | 15.02.23 | 14.05.23 | 100% | 103.2 |  |  | 100% | 103.2 | Phy.Completed
KHAWZAWL DIVISION
546 | Strengthening of approach road to IR Headquarter of Khawzawl in Mizoram for the year 2022-2023 under SASCI | 401 | Khawzawl Division | 15.02.23 | 30.06.23 | 60% | 173.44 | 5% | 22.68 | 65% | 196.12 | Work in progress
547 | Improvement of Farmual road at Khawzawl in Mizoram for the year 2022-2023 under SASCI | 343.5 | Khawzawl Division | 16.02.23 | 30.06.23 | 65% | 142.94 |  |  | 65% | 142.94 | Work in progress
548 | Contsruction /Upgradation of Road from NE Khawdungsei-Tuivai-Mimbung in Mizoram for the year 2022-2023 under SASCI | 377 | Khawzawl Division | 15.02.23 | 31.03.23 | 100% | 123.99 |  | 8.35 | 100% | 132.34 | Phy.Completed
549 | Construction of Kawlkulh Bypass Road | 805 | Khawzawl Division | 01.02.23 | 30.06.23 | 21% | 167.44 |  |  | 21% | 167.44 | Work in progress
550 | Construction of road from Hliappui-Aiduzawl-Neihdawn in Mizoram for the year 2022-2023 under SASCI | 340 | Khawzawl Division | 15.02.23 | 30.06.23 | 100% | 231.91 |  |  | 100% | 231.91 | Phy.Completed
SAITUAL DIVISION :
551 | A.Section-I 1) Strengthening of Saitual-Phullen Road (28.30) Tuivawl-Phullen | 139.71 | Saitual Division | 13.2.2023 | 31.3.24 | 100% | 70 |  |  | 100% | 70 | Phy.Completed
552 | B.Section-II 1) Construction of concrete pavement between PWB IB to Thlanmual at Suangpuilawn & Improvement of Internal Roads | 28.98 | Saitual Division | 13.2.2023 | 31.3.24 | 100% | 14.49 |  |  | 100% | 14.49 | Phy.Completed
553 | 2) Construction of concrete pavement between Pu Zodinmawia's House to Lalsangbera's House at Vangbawng & Improvement of Internal Roads & Playground | 24.15 | Saitual Division | 13.2.23 | 31.3.24 | 100% | 12.07 | - |  | 100% | 12.07 | Phy.Completed
554 | 3) Construction of concrete pavement between RMSA school to Main road at Lamherh | 14.49 | Saitual Division | 13.2.23 | 31.3.24 | 100% | 7.24 | - |  | 100% | 7.24 | Phy.Completed
555 | 4) Construction and widening of road between N.Khawlek to Tuivawl Kai at N.Khawlek & Improvement of Internal Roads | 52.17 | Saitual Division | 13.2.23 | 31.3.24 | 100% | 26.08 | - |  | 100% | 26.08 | Phy.Completed
556 | 5) Construction of concrete pavement between Dawrkawn to High school at Khawlian & Improvement of Internal Roads | 35.75 | Saitual Division | 13.2.23 | 31.3.24 | 100% | 17.87 | - |  | 100% | 17.87 | Phy.Completed
557 | 6) Construction of concrete pavement between Anganwadi Centre I to YMA road at Phaibuang & Improvement of Internal Roads | 33.81 | Saitual Division | 13.2.23 | 31.3.24 | 100% | 16.9 |  |  | 100% | 16.9 | Phy.Completed
558 | 7) Construction of Approach Road to CC Puk at Luangpawn | 16.42 | Saitual Division | 13.2.23 | 31.3.24 | 100% | 8.21 |  |  | 100% | 8.21 | Phy.Completed
559 | 8) Construction of Community Hall at Phullen (Formation cutting and Retaining Wall) & Improvement of Internal Roads | 33.81 | Saitual Division | 13.2.23 | 31.3.24 | 100% | 16.9 |  |  | 100% | 16.9 | Phy.Completed
560 | 9) Widening of Mualkhang Road, Sihfa & Improvement of Internal Roads | 38.65 | Saitual Division | 13.2.23 | 31.3.24 | 100% | 19.32 | - |  | 100% | 19.32 | Phy.Completed
561 | 10) Improvement of High School Road, Daido | 9.66 | Saitual Division | 12.2.23 | 31.3.23 | 100% | 4.83 | - |  | 100% | 4.83 | Phy.Completed
562 | 11) PCC Flooring of Public Field Approach Road, Lailak & Improvement of Internal Roads | 19.32 | Saitual Division | 12.3.23 | 31.3.24 | 100% | 9.66 | - |  | 100% | 9.66 | Phy.Completed
563 | Improvement of Mualpheng to Maite Road |  | Saitual Division | 13.2.23 | 31.3.23 | 100% |  |  |  | 100%
564 | A.Section-I 1) Construction of Retaining Wall between main Road to Village extension peng at NE Tlangnuam | 9.66 |  |  |  |  | 4.83 |  |  |  | 4.83 | Phy.Completed
565 | 2) Widening cum PCC Flooring of Thlanmual Kawng. Thanglailung & Improvement of Internal Roads | 23.21 | Saitual Division | 13.2.23 | 31.3.23 | 100% | 11.6 | - |  | 100% | 11.6 | Phy.Completed
566 | 3) Formation cutting from Buhban to Tuivawl Road, Buhban | 28.98 | Saitual Division | 13.2.23 | 31.3.23 | 100% | 14.49 | - |  | 100% | 14.49 | Phy.Completed
567 | 4) PCC Flooring from Catholic Church to Presbyterian Church, Dilkhan & Improvement of Internal Roads | 14.49 | Saitual Division | 13.2.23 | 31.3.23 | 100% | 7.24 | - |  | 100% | 7.24 | Phy.Completed
568 | 5) PCC Flooring from Main Road to High School Road, N.Lungpher & Improvement of Internal Roads | 20.29 | Saitual Division | 13.2.23 | 31.3.23 | 100% | 10.14 | - |  | 100% | 10.14 | Phy.Completed
569 | 6) Construction of concrete pavement between Hmundo to Tuivawl at Zawngin & Improvement of Internal Roads | 19.32 | Saitual Division | 13.2.23 | 31.3.23 | 100% | 9.66 |  |  | 100% | 9.66 | Phy.Completed
570 | 7) Formation cutting of Khanpui road to Tlanghmawr Approach Road, Tualbung & Improvement of Internal Roads | 19.32 | Saitual Division | 13.2.23 | 31.3.23 | 100% | 9.66 | - |  | 100% | 9.66 | Phy.Completed
571 | B.Section-II 1) Resurfacing of Rulchawm to Ruallung | 85.64 | Saitual Division | 13.2.23 | 31.3.23 | 50% | 42.82 |  |  | 50% | 42.82 | Work in progress
572 | 2) Construction of Retaining Wall at 2.300 Km on Rulchawm - Mualpheng Road | 1.71 | Saitual Division | 13.2.23 | 31.3.23 | 100% | 0.85 | - |  | 100% | 0.85 | Phy.Completed
573 | 3) Construction of Retaining Wall at 2.50 Km on Rulchawm - Mualpheng Road | 5.32 | Saitual Division | 13.2.23 | 31.3.23 | 100% | 2.66 | - |  | 100% | 2.66 | Phy.Completed
574 | 4) Construction of Retaining Wall at 4.70 Km on Rulchawm - Mualpheng Road | 3.55 | Saitual Division | 13.2.23 | 31.3.23 | 100% | 1.77 |  |  | 100% | 1.77 | Phy.Completed
575 | 5) Construction of Retaining Wall at 18.800 Km on Mualpheng - Maite Road | 3.34 | Saitual Division | 13.2.23 | 31.3.23 | 100% | 1.67 |  |  | 100% | 1.67 | Phy.Completed
576 | 6) Resurfacing of Ruallung - Maite Road up to Mualpheng | 211.69 | Saitual Division | 13.2.23 | 31.3.23 | 50% | 105.84 |  |  | 50% | 105.84 | Work in progress
577 | 7) Construction of RCC Side Drain between 0.400Km and 1.000 Km on Helipad Road, Saitual | 19.24 | Saitual Division | 13.2.23 | 31.3.23 | 100% | 9.62 |  |  | 100% | 9.62 | Phy.completed
578 | 8) Construction of V Shape RCC Side Drain between 1.000 Km and 2.000 Km on Helipad Road, Saitual | 50.62 | Saitual Division | 13.2.23 | 31.3.23 | 100% | 25.31 |  |  | 100% | 25.31 | Phy.completed
579 | 9) Construction of Retaining Wall at 18.900 Km on Mualpheng - Maite Road | 3.34 | Saitual Division | 13.2.23 | 31.3.23 | 100% | 1.67 |  |  | 100% | 1.67 | Phy.completed
580 | 10) Construction of Retaining Wall at 0.70Km on Helipad Road, Saitual | 2.17 | Saitual Division | 13.2.23 | 31.3.23 | 100% | 1.08 |  |  | 100% | 1.08 | Phy.completed
581 | 11) Construction of Retaining Wall at 0.90 Km on Helipad Road, Saitual | 2.22 | Saitual Division | 13.2.23 | 31.3.23 | 100% | 1.11 |  |  | 100% | 1.11 | Phy.completed
582 | 12) Construction of Retaining Wall at 15.350 Km on Mualpheng - Maite Road | 4.28 | Saitual Division | 13.2.23 | 31.3.23 | 100% | 2.14 |  |  | 100% | 2.14 | Phy.completed
583 | 13) Construction of RCC Covered Cross Drain at 1.250 Km on Helipad Road, Saitual | 2.67 | Saitual Division | 13.2.23 | 31.3.23 | 100% | 1.33 |  |  | 100% | 1.33 | Phy.completed
584 | 14) Construction of Rigid Pavement of DC Complex Road, Saitual | 183.86 | Saitual Division | 13.2.23 | 31.3.23 | 17.84% | 91.93 |  |  | 17.84% | 91.93 | Work in progress
TLABUNG DIVISION :
| Strengthening of Phairuang - Thenhlum Road Group-A | 5.81 | Tlabung Division | 2023-03-01 | March-2024 | 100% | 2.65 |  |  | 100% | 2.65 | Completed Phy.Works
585 | 1. Excavation for Structure (Earth work in excavation of foundation of structures as per drawing and technical specification, including setting out I. Ordinary soil (upto 3m depth)
586 | 2. Plain/Reinforced cement concrete in sub-structure complete as per drawing and technical specifications, A.PCC Grade Grade M15 Nominal mix 1:3:6 (hand mixing) | 4.35 | Tlabung Division | 2023-03-23 | March-2024 | 100% | 2.02 |  |  | 100% | 2.02 | Completed Phy.Works
587 | 3. Stone Masonry work in cement mortar for substructure complete as per drawing and Technical Specifications II. Course rublle masonry (1st sort) iii) in cement mortar 1:3 | 15.75 | Tlabung Division | March 2023 | March-2024 | 100% | 7.45 |  |  | 100% | 7.45 | Completed Phy.Works
588 | 4. Providing and laying filter media with granular crush aggregates as per specification to a tickness of not less than 600mm | 4.34 | Tlabung Division | March 2023 | March-2024 | 100% | 2.02 |  |  | 100% | 2.02 | Completed Phy.Works
589 | 5. Restoration of Rain Cuts (Restoration of rain cuts with soil, moorum, gravel or a mixture of these, clearing the loose soil, benching for 300mm width | 0.82 | Tlabung Division | March 2023 | March-2024 | 100% | 0.38 |  |  | 100% | 0.38 | Completed Phy.Works
590 | 6. Cement Concrete Pavement with a provision of edge stone (Construction of un-reinforced, dowel jointed, plain cement concrete pavement over a prepared sub base with 43 grade cement | 18.19 | Tlabung Division | March 2023 | March-2024 | 100% | 6 |  |  | 100% | 6 | Completed Phy.Works
591 | 7. PCC 1:3:6 in Foundation (Plain cement concrete 1:3:6 nominal mix in foundation with crushed stone aggregate 40mm nominal size mechanically mixed, placed in foundation and compacted by vibration including curing 14 dyas) | 18.97 | Tlabung Division | March 2023 | March-2025 | 100% | 8.35 |  |  | 100% | 8.35 | Completed Phy.Works
592 | 8. Plain/Reinforced cement concrete in open foundation complete as per drawing and techincal specifications A.PCC Grade M15 | 8.55 | Tlabung Division | March 2023 | March-2024 | 100% | 3.98 |  |  | 100% | 3.98 | Completed Phy.Works
593 | 9. Earthwork in exvacation in foundation trenches etc.not exceeding 2 meters depth including dressing of bottom and sides of trenches Hard soil (Pick work) | 0.84 | Tlabung Division | March 2023 | March-2024 | 100% | 0.39 |  |  | 100% | 0.39 | Completed Phy.Works
594 | 10. Filling available excavated earth (excluding rock) in trenches, plinth, sides of foundations etc.in layers not exceeding 20cm in depth | 0.01 | Tlabung Division | March 2023 | March-2024 | 100% | 0.004 |  |  | 100% | 0.004 | Completed Phy.Works
595 | 11. Providing and laying cement concrete in retaining wall, return walls, walls (any thickness) including pilasters, 1:3:6 (1 cement: 3 course sand: 6 stone aggregate 40mm) | 0.52 | Tlabung Division | March 2023 | March-2024 | 100% | 0.24 |  |  | 100% | 0.24 | Completed Phy.Works
596 | 12. Steel reinforcement for RCC work including straighthening, cutting, bending, placing in position and binding all complete. Mild steel and medium Tensile steel bars | 2.33 | Tlabung Division | March 2023 | March-2024 | 100% | 1.08 |  |  | 100% | 1.08 | Completed Phy.Works
597 | 13. Providing, fitting and placing GI pipe 100mm dia | 5.07 | Tlabung Division | March 2023 | March-2024 | 100% | 2.36 |  |  | 100% | 2.36 | Completed Phy.Works
598 | 14 Excavation in soil by Manual Means (Excavation for roadway in soil using manual means including loading in truck for carrying of cut earth to embankment site with all lifts and lead upto 1000 meters | 0.45 | Tlabung Division | March 2023 | March-2024 | 100% | 0.21 |  |  | 100% | 0.21 | Completed Phy.Works
599 | 15. Stone Masonry work in cement mortar in foundation complete as per drawing and technical specifications clauses 702, 704, 1202 & 1203. II. Coursed rubble masonry ii) In 1:4 cement mortar | 10.45 | Tlabung Division | March 2023 | March-2024 | 100% | 6.72 |  |  | 100% | 6.72 | Completed Phy.Works
600 | 16. Providing and laying in position cement concrete of specified grade excluding cost of centering and shuttering-All work upto plinth level: 1:2:4 (Cement:2 course sand: 4 stone aggregate 20mm nominal size) | 2.21 | Tlabung Division | March 2023 | March-2024 | 100% | 1.03 |  |  | 100% | 1.03 | Completed Phy.Works
601 | 17. Providing and laying in position reinforced cement concrete excluding cost of centering and shuttering, finishing and reinforcement in- 1:2:4 (1 cement: 2 coarse sand:4 graded stone aggregate 20mm nominal size) | 0.47 | Tlabung Division | March 2023 | March-2024 | 100% | 0.22 |  |  | 100% | 0.22 | Completed Phy.Works
602 | 18. First class brickwork in foundation and plinth in: (b) in cement mortar 1:4 | 4.46 | Tlabung Division | March 2023 | March-2024 | 100% | 2.07 |  |  | 100% | 2.07 | Completed Phy.Works
603 | 19. Providing 1st class local wood in trusses etc.including purlin, hoisting fixingf in position supplying necessary fittings such as spikes bolts and nuts, nails etc and applying wood preservative for unexposed surface etc.complete | 0.7 | Tlabung Division | March 2023 | March-2024 | 100% | 0.33 |  |  | 100% | 0.33 | Completed Phy.Works
604 | 20. Providing corrugated G.S sheet roofing fixed with polymer coated J or L hooks, bolts and nuts 8mm diameter with nitumen and G.I limpet washers or with G.I limpet washers filled with white lead and including a coat of approved steel primer 0.80mm thick with zinc coating not less than 275gm/m2 | 0.65 | Tlabung Division | March 2023 | March-2024 | 100% | 0.33 |  |  | 100% | 0.33 | Completed Phy.Works
605 | 21. Providing and fixing 1st class teak wood panelled and glazed shutters using 4mm thick plate sneet glass for doors and windows etc.including M.S butt hinges with necessary screws etc. complete | 1.2 | Tlabung Division | March 2023 | March-2024 | 100% | 0.52 |  |  | 100% | 0.52 | Completed Phy.Works
606 | 22. Painting with synthetic enamel paint of approved brand and manufacture in all shades on new work. (two or more coats) | 0.22 | Tlabung Division | March 2023 | March-2024 | 100% | 0.14 |  |  | 100% | 0.14 | Completed Phy.Works
607 | 23. Supplying, fitting and placing HTSD bar reinforcement in sub-structure complete as per drawing and technical specifications | 19.1 | Tlabung Division | March 2023 | March-2024 | 100% | 9.05 |  |  | 100% | 9.05 | Completed Phy.Works
608 | 24. Providing and laying reinforce cement concrete in super structure as per drawing and technical specifications clause 800, 1205.4 and 1205.5 II. RCC M25 grade | 2.1 | Tlabung Division | March 2023 | March-2024 | 100% | 1.12 |  |  | 100% | 1.12 | Completed Phy.Works
609 | 25. Backfilling in abutment, wing wall and return wall complete as per drawing and technical specification clause 1204.3.8 I. Granular material | 1.46 | Tlabung Division | March 2023 | March-2024 | 100% | 0.68 |  |  | 100% | 0.68 | Completed Phy.Works
610 | 26. Stone masonry in cement mortar 1:3 for parapet complete as per drawing and technical specifications Clasues 700 and 1208.4 A.Random rubble masonry | 0.36 | Tlabung Division | March 2023 | March-2024 | 100% | 0.17 |  |  | 100% | 0.17 | Completed Phy.Works
611 | 27. Plastering with cement mortar (1:4) 15mm thick on Brick/Stone works as per drawing and technical specification clauses 613.4 and 1204 | 0.85 | Tlabung Division | March 2023 | March-2024 | 100% | 0.4 |  |  | 100% | 0.4 | Completed Phy.Works
612 | 28. Providing 1st class local wood work dressed in frames of sill, upright, batten, post, beams etc. as structural members fixed in position complete | 0.94 | Tlabung Division | March 2023 | March-2024 | 100% | 0.44 |  |  | 100% | 0.44 | Completed Phy.Works
613 | 29. Providing 2nd class local wood work dressed in frames of chaukut for doors, windows, clerestory windows fixed in postion | 0.2 | Tlabung Division | March 2023 | March-2024 | 100% | 0.09 |  |  | 100% | 0.09 | Completed Phy.Works
614 | 30. Providing and fixing 25mm thick and 2nd class local wood plank walling (both sides planned) tongue and groove joints including necessary nails, screws, etc.complete | 0.84 | Tlabung Division | March 2023 | March-2024 | 100% | 0.39 |  |  | 100% | 0.39 | Completed Phy.Works
615 | 31. Providing and fixing MS handles with necessary screws etc (a) 150mm | 0.01 | Tlabung Division | March 2023 | March-2024 | 100% | 0.002 |  |  | 100% | 0.002 | Completed Phy.Works
616 | 32. Providing and fixing MS hooks and eyes (a) 200mm | 0 | Tlabung Division | March 2023 | March-2024 | 100% | 0.0002 |  |  | 100% | 0.0002 | Completed Phy.Works
617 | 33. Providing and fixing MS tower bolts (socket bolts) bright finished with necessary screws etc. (a) 200mm | 0.03 | Tlabung Division | March 2023 | March-2024 | 100% | 0.1 |  |  | 100% | 0.1 | Completed Phy.Works
618 | (b) 150mm | 0 | Tlabung Division | March 2023 | March-2024 | 100% | 0.0001 |  |  | 100% | 0.0001 | Completed Phy.Works
619 | 34. Earthwork in excavation for foundation of structures upto 3m depth as per drawing and technical specification | 0.8 | Tlabung Division | March 2023 | March-2024 | 100% | 0.35 |  |  | 100% | 0.35 | Completed Phy.Works
620 | 35. Providing cement concrete M10 (1:3:6) in levelling cpurse below open foundation of head wall as per drawing and technical specification clause 1109. I. PCC grade M10 Mominal mix 1:3:6 (hand mixing) | 1.2 | Tlabung Division | March 2023 | March-2024 | 100% | 0.56 |  |  | 100% | 0.56 | Completed Phy.Works
621 | 36. Stone Masonry Work in cement mortar in foundation of head walls complete as per drawing and technical specification Clause 1109 (A) in 1:4 cement Mortar | 5.64 | Tlabung Division | March 2023 | March-2024 | 100% | 3.45 |  |  | 100% | 3.45 | Completed Phy.Works
622 | 37. Type-B (First class) bedding: Lating (first class) bedding of well compacted sand, moorum or approved granular materials as per clause 1105 (ii) | 0.14 | Tlabung Division | March 2023 | March-2024 | 100% | 0.07 |  |  | 100% | 0.07 | Completed Phy.Works
623 | 38. Providng and laying RCC Pipe NP3 for Culvert on first class bedding of granular material | 4.74 | Tlabung Division | March 2023 | March-2024 | 100% | 2.25 |  |  | 100% | 2.25 | Completed Phy.Works
624 | 39. Backfilling in abutment, wing wall and return wall complete as drawing and technical specification clause 1204.3.8 I. Granular material | 0.85 | Tlabung Division | March 2023 | March-2024 | 100% | 0.42 |  |  | 100% | 0.42 | Completed Phy.Works
625 | 40. Backfilling in Foundation Trenches as per drawing and techniical specification Clause 1108 II. Earth filling | 0.05 | Tlabung Division | March 2023 | March-2024 | 100% | 0.02 |  |  | 100% | 0.02 | Completed Phy.Works
626 | 41. Stone masonry in cement mortar 1:3 for parapet complete I. Random rubble masonry | 0.25 | Tlabung Division | March 2023 | March-2024 | 100% | 0.12 |  |  | 100% | 0.12 | Completed Phy.Works
627 | 42. Plastering with cement mortar (1:4) 15mm thick on Brick/Stone works | 0.08 | Tlabung Division | March 2023 | March-2024 | 100% | 0.04 |  |  | 100% | 0.04 | Completed Phy.Works
628 | 43. Providing PCC M20 architectural coping on the top of retaining wall complete between parapet walls | 0.13 | Tlabung Division | March 2023 | March-2024 | 100% | 0.06 |  |  | 100% | 0.06 | Completed Phy.Works
| Sttrengthening of Phairuangkai-Thenhlum Road Group-B | 1.79 | Tlabung Division | March 2023 | March-2024 | 100% | 0.83 |  |  | 100% | 0.83 | Completed Phy.Works
629 | 1. Clearing and Grubbing Road Land. (Clearing and gribbing road land including uprooting rank vegetation, grass, bushes, shribs, sapling and tress girth up to 300 mm, removal of stumps of tree cut earlier By Manual Means:- In area of thorny jungle
2. Cutting of Tress, including cutting of Trunks, Branches and Removal (Cutting of tress, including cutting of trunks, branches and removal of stumps, roots, stacking
630 | Girth from 300mm to 600mm | 0.09 | Tlabung Division | Mar'23 | Mar'24 | 100% | 0.04 |  |  | 100% | 0.04 | Phy.completed
631 | Girth from 600mm to 900mm | 0.07 | Tlabung Division | Mar'23 | Mar'24 | 100% | 0.03 |  |  | 100% | 0.03 | Phy.completed
632 | Girth from 900mm to 1800 | 0.12 | Tlabung Division | Mar'23 | Mar'24 | 100% | 0.06 |  |  | 100% | 0.06 | Phy.completed
633 | 3. Excavation in Soil by Mechanical means (Excavation for road way in soil by mechanical means including cutting | 12.88 | Tlabung Division | Mar'23 | Mar'24 | 100% | 5.99 |  |  | 100% | 5.99 | Phy.completed
634 | 4. Excavation in Ordinary Roak by Mechanical means (Excavation for roadway in ordinary rock by mechanical menas including cutting and pushing the earth | 9.46 | Tlabung Division | March 2023 | March-2024 | 100% | 4.4 |  |  | 100% | 4.4 | Completed Phy.Works
635 | 5. Restoration of Rain Cuts (Restoration of rain cuts with soil, moorum, gravel or a mixture of these, clearing the loose soil | 0.69 | Tlabung Division | March 2023 | March-2024 | 100% | 0.32 |  |  | 100% | 0.32 | Completed Phy.Works
636 | 6. Cement Concrete Pavement with a provision of edge stone (Construction of un-reinforced, dowel jointed, plain cement concrete pavement over a prepared sub base with 43 grade cement @400 kg per cum | 38.16 | Tlabung Division | March 2023 | March-2024 | 100% | 17.74 |  |  | 100% | 17.74 | Completed Phy.Works
637 | 7. Excavation of structures (Earth work in excavtion of foundation of structures as per drawing and technical specification, including setting out, construction of shoring and bracing, removal of stumps and other deleterious matter, dressing of sides and bottom and backfilling with approved material) I. Orinary soil (upto 3m depth) | 11.16 | Tlabung Division | March 2023 | March-2024 | 100% | 5.23 |  |  | 100% | 5.23 | Completed Phy.Works
638 | 8. Earthwork in excavation in foundation trenches etc, not exceeding 2 meters depth including dressing of bottom and sides of trenches Hard soil (pick work) | 0.66 | Tlabung Division | March 2023 | March-2024 | 100% | 0.31 |  |  | 100% | 0.31 | Completed Phy.Works
639 | 9. Excavation in Soil by Manual Means (Excavation for roadway in soil using manual means including loading in truck for carrying of cut earth to embankment site with all lifts and lead upto 1000 metres) | 0.5 | Tlabung Division | March 2023 | March-2024 | 100% | 0.23 |  |  | 100% | 0.23 | Completed Phy.Works
640 | 10. PCC 1:3:6 in Foundation (Plain cement concrete 1:3:6 nominal mix in foundation with crushed stone aggregate 40mm nominal size mechanical mixed, placed in foundation and compacted by vibration including curing for 14 days) | 20.18 | Tlabung Division | March 2023 | March-2024 | 100% | 9.38 |  |  | 100% | 9.38 | Completed Phy.Works
641 | 11. Plain/Reinforced cement concrete in sub-structure complete as per drawing and technical specifications A. PCC Grade M15 Nominal mix 1:3:6 (hand mixing) | 10.94 | Tlabung Division | March 2023 | March-2024 | 100% | 5.09 |  |  | 100% | 5.09 | Completed Phy.Works
642 | 12. Providing and laying in position reinforced cement concrete exluding cost of centering and shuttering, finishing and reinforcement in - 1:2:4 (1 cement:2 coarse sand: 4 graded stone aggregate) | 0.79 | Tlabung Division | March 2023 | March-2024 | 100% | 0.37 |  |  | 100% | 0.37 | Completed Phy.Works
643 | 13. Plain/Reinforced cement concrete in open foundation complete as per drawing and technical specifications A. PCC Grade M15 | 17.22 | Tlabung Division | March 2023 | March-2024 | 100% | 8.02 |  |  | 100% | 8.02 | Completed Phy.Works
644 | 14. Providing and laying in position cement concrete of specified grade excluding cost of centering and shuttering - All work upto plinth level: 1:2:4 (1 cement:2 coarse sand: 4 graded stone aggregate 20mm nominal size) | 1.23 | Tlabung Division | March 2023 | March-2024 | 100% | 0.57 |  |  | 100% | 0.57 | Completed Phy.Works
645 | 15. Stone Masonry work in cement mortar for substructure complete as per drawing and Technical specifications II. Course rubble masonry (1st sort) (iii) in cement mortar 1:3 | 47.05 | Tlabung Division | March 2023 | March-2024 | 100% | 21.98 |  |  | 100% | 21.98 | Completed Phy.Works
646 | 16. Complete as per drawing and technical specifications claises 702, 704, 1202 & 1203 II. Coursed rubble masonry (ii) In 1:4 cement mortar | 11.35 | Tlabung Division | March 2023 | March-2024 | 100% | 5.29 |  |  | 100% | 5.29 | Completed Phy.Works
647 | 17. Stone Masonry in cement mortar 1:3 for parapet complete as per drawing and technical specifications A.Random rubble masonry | 0.07 | Tlabung Division | March 2023 | March-2024 | 100% | 0.04 |  |  | 100% | 0.04 | Completed Phy.Works
648 | 18. Providing and laying filter media with granular crush aggregates as per specification to a thickness of not less than 600mm | 7.29 | Tlabung Division | March 2023 | March-2024 | 100% | 3.39 |  |  | 100% | 3.39 | Completed Phy.Works
649 | 19. Backfilling in abutment, wing wall and return wall complete as per drawing and technical specification I. Granular material | 0.46 | Tlabung Division | March 2023 | March-2024 | 100% | 0.21 |  |  | 100% | 0.21 | Completed Phy.Works
650 | 20. Filling available excavated earth (excluding rock) in trenches, plinth, sides of foundation etc. in layers not exceeding 20cm in depth, consolidating each deposited layer by ramming and watering, lead up to 50m and lift upto 15m | 1.01 | Tlabung Division | March 2023 | March-2024 | 100% | 0.004 |  |  | 100% | 0.004 | Completed Phy.Works
651 | 21. Providing and laying cement concrete in retaining wall, return walls, walls (any thickness) including pilasters, piers, columns, abutments, pillars, posts, 1:3:6 (1 cement : 3 course sand : 6 stone aggregate 40mm) | 0.62 | Tlabung Division | March 2023 | March-2024 | 100% | 0.29 |  |  | 100% | 0.29 | Completed Phy.Works
652 | 22. Plastering with cement mortar (1:4) 15mm thick on Brick/Stone works as per drawing and technical specification clauses 613.4 and 1204 | 0.58 | Tlabung Division | March 2023 | March-2024 | 100% | 0.27 |  |  | 100% | 0.27 | Completed Phy.Works
653 | 23. Providing and laying reinforced cement concrete 1:2:4 (b) Column, etc | 0.13 | Tlabung Division | March 2023 | March-2024 | 100% | 0.06 |  |  | 100% | 0.06 | Completed Phy.Works
654 | 24. Providing and laying reinforce cement concrete in super structure as per drawing and technical specifications clause 800, 1205.4 and 1205.5 II. RCC M25 grade | 0.79 | Tlabung Division | March 2023 | March-2024 | 100% | 0.47 |  |  | 100% | 0.47 | Completed Phy.Works
655 | 25. Steel reinforcement for RCC work including straighthening cutting, bending, placing in position and binding all complete Mild steel and Medium Tensile steel bars | 3.82 | Tlabung Division | March 2023 | March-2024 | 100% | 1.78 |  |  | 100% | 1.78 | Completed Phy.Works
656 | 26. Supplying, fitting and placing HYSD bar reinforcement in sub-structure complete as per drawing and technical specifications | 1.6 | Tlabung Division | March 2023 | March-2024 | 100% | 0.75 |  |  | 100% | 0.75 | Completed Phy.Works
657 | 27. Providing, fitting and placing GI pipe 100mm dia | 6.14 | Tlabung Division | March 2023 | March-2024 | 100% | 2.87 |  |  | 100% | 2.87 | Completed Phy.Works
658 | 28. Providing and fixing G.I Union in existing G.I pipeline, cutting and threading the pipe and making long screws including excavation refilling the earth or cutting of wall and making good the same complete wherever required. (f) 50mm nominal size | 0.01 | Tlabung Division | March 2023 | March-2024 | 100% | 0.01 |  |  | 100% | 0.01 | Completed Phy.Works
659 | 29. First class brickwork in foundation and plinth in: (b) in cement mortar 1:4 | 3.19 | Tlabung Division | March 2023 | March-2024 | 100% | 1.48 |  |  | 100% | 1.48 | Completed Phy.Works
660 | 30. Providing 1st class local wood in trusses etc.including purlin, hosting fixing in position supplying necessary fittings such as spikes bolts and nuts, nails etc and applying wood preservative for unexposed surface etc. complete | 1.49 | Tlabung Division | March 2023 | March-2024 | 100% | 0.69 |  |  | 100% | 0.69 | Completed Phy.Works
661 | 31. Providing and fixing 1st class teak wood pannelled and glazed shutters using 4mm thick plate sneet glass for doors and windows etc.including M.S butt hinges with necessary screws etc. comoplete | 0.34 | Tlabung Division | March 2023 | March-2024 | 100% | 0.16 |  |  | 100% | 0.16 | Completed Phy.Works
662 | 32. Providing corrugated G.S sheet roofing fixed with polymer coated J or L hooks, bolts and nuts 8mm diameter with bitumenn and G.I limpet washers 0.80 mm thick with zinc coating not less than 275gm/m2 | 0.71 | Tlabung Division | March 2023 | March-2024 | 100% | 0.36 |  |  | 100% | 0.36 | Completed Phy.Works
663 | 33. Painting with synthetic enamel paint of approved brand and manufacture in all shades on new work (two or more coats) | 0.12 | Tlabung Division | March 2023 | March-2024 | 100% | 0.06 |  |  | 100% | 0.06 | Completed Phy.Works
664 | Strenthening of Phairungkai-Thenhlum Road Group C | 1.71 | Tlabung Division | March 2023 | March-2024 | 100% | 0.86 |  |  | 100% | 0.86 | Completed Phy.Works
665 | 1. Construction of Subgrade and Earthen Shoulders (Construction of subgrade and eartheh shoulders with approved material obtained from borrow pits with all lifts & leads
666 | 2. Water Bound Macadam (Providng, laying, spreading and compactinf stone aggregates of specific sizes to water bound macadan specification including spreading in uniform thickness, A. By Manual Means (ii) Grading - 2 (53 mm to 22.4mm) (a) Using Screeining Crushable type such as Moorum of Gravel | 11.24 | Tlabung Division | March 2023 | March-2024 | 100% | 5.62 |  |  | 100% | 5.62 | Completed Phy.Works
667 | 3. Cement Concrete Pavement (Construction of unreinforced, dowel jointed, plain cement concrete pavement over a prepared sub base with 43 grade cement | 56.07 | Tlabung Division | March 2023 | March-2024 | 100% | 28.04 |  |  | 100% | 28.04 | Completed Phy.Works
668 | 4. Excavation for Structures (Earth work in excavation of foundation of structures as per drawing and technical specification. I. Ordinary soil (upto 3m depth) | 0.91 | Tlabung Division | March 2023 | March-2024 | 100% | 0.46 |  |  | 100% | 0.46 | Completed Phy.Works
669 | 5. Stone masonry work in cement mortar for substructure complete as per drawing and Technical Specifications II. Course rubble masonry (1st sort) (iii) in cement mortar 1:3 | 21.28 | Tlabung Division | March 2023 | March-2024 | 100% | 10.64 |  |  | 100% | 10.64 | Completed Phy.Works
670 | 6. Excavation for structure (Earth work in excavation for foundation of structures as per drawing and technical specification, (i) Ordinary soil A Manual Mean (Depth upto 3m) | 0.32 | Tlabung Division | March 2023 | March-2024 | 100% | 0.16 |  |  | 100% | 0.16 | Completed Phy.Works
671 | 7. PCC 1:3:6 Foundation (Plain cement concrete 1:3:6 in foundation including for 14 days) | 0.914 | Tlabung Division | March 2023 | March-2024 | 100% | 0.46 |  |  | 100% | 0.46 | Completed Phy.Works
672 | 8. Back filling behind abutment, wing wall and return wall complete as per drawing and Technical specification | 1.49 | Tlabung Division | March 2023 | March-2024 | 100% | 0.75 |  |  | 100% | 0.75 | Completed Phy.Works
673 | 9. Plastering with cement mortar (1:3) in sub-structure as per Technical Specifications | 0.13 | Tlabung Division | March 2023 | March-2024 | 100% | 0.07 |  |  | 100% | 0.07 | Completed Phy.Works
674 | 10. Excavation in Hilly areas in soil by Manual Means | 6.81 | Tlabung Division | March 2023 | March-2024 | 100% | 3.41 |  |  | 100% | 3.14 | Completed Phy.Works
675 | 11. Excavation in Hilly areas in ordinary Rock by Manual Means | 2.37 | Tlabung Division | March 2023 | March-2024 | 100% | 1.19 |  |  | 100% | 1.19 | Completed Phy.Works
676 | 12. Removal of unsuitable soil including excavtion, loading and disposals with a lead of 1000m | 0.95 | Tlabung Division | March 2023 | March-2024 | 100% | 0.48 |  |  | 100% | 0.48 | Completed Phy.Works
677 | 13. Reinforced cement concrete approach slab including reinforcement and formwork complete as per drawing and Technical specification | 0.41 | Tlabung Division | March 2023 | March-2024 | 100% | 0.21 |  |  | 100% | 0.21 | Completed Phy.Works
678 | 14. 12mm cement plaster 1:3 (1 cement : 3 fine sand) | 0.1 | Tlabung Division | March 2023 | March-2024 | 100% | 0.05 |  |  | 100% | 0.05 | Completed Phy.Works
679 | 15. Providng and fixing G.I pipe complete with G.I fitting including trenching and refilling etc. (external work) | 2.28 | Tlabung Division | March 2023 | March-2024 | 100% | 1.14 |  |  | 100% | 1.14 | Completed Phy.Works
680 | 16. Water Bound Macadam (Providing, layinf, spreading and compacting stone aggregates of specific sizes to water bound madacam specification (ii) Grading II (53mm - 22.4mm) (b) Using Screening type-B | 14.08 | Tlabung Division | March 2023 | March-2024 | 100% | 7.04 |  |  | 100% | 7.04 | Completed Phy.Works
681 | 17. Prime coat (Providing and applying primer coat with bitument emulsion on prepared surface of granular base including 1) Low Porosity | 1.55 | Tlabung Division | March 2023 | March-2024 | 100% | 0.78 |  |  | 100% | 0.78 | Completed Phy.Works
682 | 18. Tack Coat (Providing and applying tack coat with bitumen emulsion using emulsion pressure distributor (ii) Granular surface treated with primer | 0.93 | Tlabung Division | March 2023 | March-2024 | 100% | 0.47 |  |  | 100% | 0.47 | Completed Phy.Works
683 | 19. Open-Graded Premix Surfacing (Providng laying and rolling of open graded premix surfacing of 20mm thickness | 8.57 | Tlabung Division | March 2023 | March-2024 | 100% | 4.29 |  |  | 100% | 4.29 | Completed Phy.Works
684 | 20. Seal Coat (Providing and laying seal coat sealing the voids in a bituminous surface laid to the specified levels, grade and cross fall using Type A and B seal coat A using Bitumen 60/70 grade (i) Case - I : Type A | 2.96 | Tlabung Division | March 2023 | March-2024 | 100% | 1.48 |  |  | 100% | 1.48 | Completed Phy.Works
PROJECT DIVISION - II :
685 | Construction of Public Playground at Thenzawl (Sh: Const.of Public Playgound Galley of length 120 metre (6 block of 20 metre each including 3 (three) steps for sitting at Thenzawl | 25 | Project Division-II | 26.02.23 | 26.08.23 | 100% | 12.5 |  |  | 100% | 12.5 | Completed Phy.Works
686 | Construction of Community Hall at Chawilung (Sh: Construcytion of Steel Truss with dyna roofing) | 6 | Project Division-II | 24.02.23 | 24.04.23 | 100% | 3 |  |  | 100% | 3 | Completed Phy.Works
687 | Construction of Community Hall at Hualngohmun (Sh: Construction of Steel Truss with dyna roofing) | 8 | Project Division-II | 24.02.23 | 24.04.23 | 100% | 4 |  |  | 100% | 4 | Completed Phy.Works
688 | Construction of MUP House at Zamuang, Mamit District | 15 | Project Division-II | 26.02.23 | 26.06.23 | 100% | 7.5 |  |  | 100% | 7.5 | Completed Phy.Works
689 | Construction of Urinal Sheds (sh: Near Rambeiseia In, BBEC Pastor Qtrs, Pu Lalzama House, Lalaithai's House, C.Laltanpuia House, Darlak Peng at Tuidam, Urinal Sheds at Vengthar, W.Bunghmun, H/S Veng at Bunghmun, Near Baptist Church at New Eden, near Presbyterian Church at New Eden) | 5 | Project Division-II | 24.02.23 | 24.04.23 | 100% | 2.5 |  |  | 100% | 2.5 | Completed Phy.Works
690 | Construction of waiting Sheds (Sh: Const.of Waiting shed at Dilpeng, Kawrtethawveng 2. Repair of Waiting Shed at New Kawnpui Village 3. Construction of Buhfai Semna/Dahna Teireikam at Kananthar). | 7.5 | Project Division-II | 24.02.23 | 24.04.23 | 100% | 3.75 |  |  | 100% | 3.75 | Completed Phy.Works
691 | Construction of Pavement of Chequered Tiles (Sh: Near Pi Duhkungi House to Kawnghnuai at Tuidam 2. Ramrikawn to Pi Rinngaii In Kawng at Kawrtethawveng 3. Mualzawl (Hmarveng) to Arm Veng 4. KDZKT Road to Internal Road near Pi Nuntluangi In at Kawrtethawveng 5. Chequered Tile phah, step Repair approach to Tuikhuah tuikhur panna at Kawrtethawveng) | 9.5 | Project Division-II | 24.02.23 | 24.04.23 | 100% | 4.75 |  |  | 100% | 4.75 | Work phy.completed
692 | Construction of Tourist Lodge at Kawnpui | 50 | Project Division-II | 26.02.23 | 26.10.23 | 55% | 25 | 5% |  | 60% | 25 | Work in progress
693 | Construction of Futsal Ground at Kawnpui Chhimveng | 25 | Project Division-II | 25.02.23 | 25.06.23 | 66% | 12.5 | 4% |  | 70% | 12.5 | Work in progress
694 | Continuation of Public Playground at Serkhan | 15 | Project Division-II | 25.03.23 | 25.05.23 | 100% | 7.5 |  |  | 100% | 7.5 | Phy.Completed
695 | Construction of Community Hall at Hortoki | 70 | Project Division-II | 26.02.23 | 26.10.23 | 100% | 35 |  |  | 100% | 35 | Phy.Completed
696 | Continuation of Public Playground at Zanlawn | 15 | Project Division-II | 25.02.23 | 25.05.23 | 85% | 7.5 |  |  | 85% | 7.5 | Work in progress
697 | Continuation of Public Playground at Bualpui | 15 | Project Division-II | 25.02.23 | 25.05.23 | 100% | 7.5 |  |  | 100% | 7.5 | Phy.Completed
698 | Construction of Bazar Shed at Nisapui | 15 | Project Division-II | 25.02.23 | 25.05.23 | 80% | 7.5 | 20% |  | 100% | 7.5 | Phy.Completed
699 | Continuation of Futsal Ground at Lungdai | 25 | Project Division-II | 25.02.23 | 25.06.23 | 80% | 12.5 |  |  | 80% | 12.5 | Work in progress
PROJECT DIVISION - III :
700 | Construction of Govt.Serchhip College (Sh: Adninistrative Block) | 650 | Project Division-III | 27.02.23 | 27.02.25 | 23% | - | 2% |  | 25% | - | work in progress
LUNGLEI ROAD DIVISION -I
IMPROVEMENT OF CHANMARI - ELECTRIC VENG - RAMTHAR VENG AT LUNGLEI DISTRICT IN MIZORAM FOR THE YEAR 2022-2023 UNDER SASCI, Length = 9.000Kms
701 | Construction of Retaining Wall at Chanmari Cemetary Road | 6.76 | Lunglei Road Division-I |  |  | 100% |  |  | 3.35 | 100% | 3.35 | Phy.Completed
702 | Construction of Breast Wall near Horticulture Complex of District Road at Chanmari | 6.27 | Lunglei Road Division-I |  |  | 100% |  |  | 3.12 | 100% | 3.12 | Phy.Completed
703 | Construction of Breast wall opposite Pi Zidingi's house Block-I at Chanmari, Lunglei | 4.56 | Lunglei Road Division-I |  |  | 100% |  |  | 2.28 | 100% | 2.28 | Phy.Completed
704 | Construction of Breast Wall opposite Pi Zidingi's House Block-II at Chanmari, Lunglei | 2.69 | Lunglei Road Division-I |  |  | 100% |  |  | 1.34 | 100% | 1.34 | Phy.Completed
705 | Construction of Retaining Wall at GHSS Lunglei, Chanmari | 5.8 | Lunglei Road Division-I |  |  | 100% |  |  | 2.84 | 100% | 2.84 | Phy.Completed
706 | Construction of Retaining Wall at Leitlangpui HSS, Chanmari, Lunglei | 7.73 | Lunglei Road Division-I |  |  | 100% |  |  | 3.97 | 100% | 3.97 | Phy.Completed
707 | Construction of PCC pavement with Retaining Wall etc. from T.Vanlalremruata's House to H.Laldawla's House at Electric veng. (a) Construction of Breast Wall near T.Vanlalremruata's House at Electrict veng, Lunglei. (b)Construction of Embankment & Widening from T.Vanlalremruata's House to H.Laldawla's House at Electrict veng, Lunglei. | 13.11 | Lunglei Road Division-I |  |  | 100% |  |  |  | 100% |  | Phy.Completed
708 | Construction of Retaining Wall at Pu Zalawma Punte Land at Electrict veng | 3.42 | Lunglei Road Division-I |  |  | 100% |  |  |  | 100% |  | Phy.Completed
709 | Construction of Retaining Wall upto Pathian Nung Biakin at Electrict veng | 3.86 | Lunglei Road Division-I |  |  | 100% |  |  |  | 100% |  | Phy.Completed
710 | Construction of PCC pavement from Main road tp R.Rozika's House near BCM Church at Electrict veng | 2.9 | Lunglei Road Division-I |  |  | 100% |  |  |  | 100% |  | Phy.Completed
711 | Construction of PCC pavement from Muanzova's House to F.Lalsangliana's House at Electrict veng | 5.8 | Lunglei Road Division-I |  |  |  |  | 40% |  | 40% |  | Work in progress
712 | Construction of Curve Improvement of opposite of Pu Bawka Point at Farm Veng | 8.69 | Lunglei Road Division-I |  |  | 100% |  |  |  | 100% |  | Phy.Completed
713 | Construction of Retaining Wall with Widening between Sericulture Gate to Lalremruata's House at Farm veng | 8.69 | Lunglei Road Division-I |  |  | 100% |  |  |  | 100% |  | Phy.Completed
714 | Construction of Footpath between C.Lalthianghlima's House to Vety Gate at Farm veng | 7.73 | Lunglei Road Division-I |  |  | 100% | 14.84 |  |  | 100% | 14.84 | Phy.Completed
715 | Construction of Hume Pipe Culvert near H.Sanghmingthanga's House at Farm veng | 3.86 | Lunglei Road Division-I |  |  | 100% |  |  |  | 100% |  | Phy.Completed
716 | Construction of Retaining Wall at V.Lalnuntluanga's House to Rochungnunga's House at District Road, Chanmari, Lunglei | 4.88 | Lunglei Road Division-I |  |  | 100% |  |  |  | 100% |  | Phy.Completed
717 | Construction of Slab Culvert at Ramthar & Salem boundary at Ramthar | 21.83 | Lunglei Road Division-I |  |  | 100% |  |  |  | 100% |  | Phy.Completed
718 | Construction of Lined Side Drain from Nghaksangi's House to Venhima's House at Ramthar veng. | 3.38 | Lunglei Road Division-I |  |  | 100% |  |  |  | 100% |  | Phy.Completed
719 | Construction of PCC pavement from Remand Home to Salem Boundary at Ramthar veng | 9.66 | Lunglei Road Division-I |  |  | 100% |  |  |  | 100% |  | Phy.Completed
720 | Construction of Retaining Wall at F.Sapdawla Land & J.Lianngura Land at Ramthar veng | 3.86 | Lunglei Road Division-I |  |  | 100% |  |  | 26.99 | 100% | 26.99 | Phy.Completed
721 | Renovation of step from Saidingliana House to Hmuzuala House at Ramthar | 5.57 | Lunglei Road Division-I |  |  | 100% |  |  |  | 100% |  | Phy.Completed
722 | Construction of Retaining wall from V.Muankima House to Thangte Veng Tuikhur at Ramthar Veng | 1.98 | Lunglei Road Division-I |  |  | 100% |  |  |  | 100% |  | Phy.Completed
723 | Construction of PCC Pavement from Thathleia's House to T.Lalthianghlima House at Ramthar veng | 2.82 | Lunglei Road Division-I |  |  | 100% |  |  |  | 100% |  | Phy.Completed
724 | Construction of PCC pavement Zaii's House to lallawmzuali's House at Ramthar veng | 2.58 | Lunglei Road Division-I |  |  | 100% |  |  |  | 100% |  | Phy.Completed
725 | Laying of Chequerred Tiles from V.Muankima House to Tuikhur Kawng at Ramthar | 2.28 | Lunglei Road Division-I |  |  | 100% |  |  |  | 100% |  | Phy.Completed
726 | Construction of formation cutting of Agricultural Link Road at Mausen | 9.66 | Lunglei Road Division-I |  |  | 100% |  |  |  | 100% |  | Phy.Completed
727 | Construction of New Internal Road in remembrance of the Golden Jubilee of Pukpui Village to be named Jubilee Road | 19.32 | Lunglei Road Division-I |  |  | 85% |  | 5% |  | 90% |  | Work in progress
728 | Construction of formation cutting of Mausep Agricultural Link Road at Sekhum | 19.32 | Lunglei Road Division-I |  |  | 100% |  |  |  | 100% |  | Phy.Completed
IMPROVEMENT OF TLABUNG ROAD - THUAMLUAIA MUAL - COLLEGE VENG - RAHSI VENG AT LUNGLEI DISTRICT IN MIZORAM FOR THE YEAR 2022-2023 UNDER SASCI, Length = 11.500Kms
729 | Dismantling, Excavation/Lowering, Pavement, Sidedrain, RCC Step and HP Culverts at Tlabung peng junction | 77.29 | Lunglei Road Division-I |  |  | 100% |  |  | - | 100% |  | Phy.Completed
730 | Construction of PCC pavement between Tarmita Road Kikawn & College veng | 96.11 | Lunglei Road Division-I |  |  | 100% | 86.95 |  | - | 100% | 86.95 | Phy.Completed
731 | Construction of Blue Mount Farmers Society approach road from Thehlep. (Widening) | 28.98 | Lunglei Road Division-I |  |  | 100% |  |  |  | 100% |  | Phy.Completed
732 | Construction of Paneled cement concrete pavement from District Court Building to Pu Chuauva House | 28.98 | Lunglei Road Division-I |  |  | 100% | 45.84 |  |  | 100% | 45.84 | Phy.Completed
733 | Construction of Slab Culvert Lamhla Tuikhur, Tarmita road, Bazar veng Kikawn | 19.32 | Lunglei Road Division-I |  |  | 100% |  | - |  | 100% |  | Phy.Completed
734 | Construct of Slab Culvert at Kawngkan Lui | 14.49 | Lunglei Road Division-I |  |  | 100% |  |  |  | 100% |  | Phy.Completed
735 | Construction of Retaining Wall near Kailiana's House at Rahsi veng, Lunglei | 9.66 | Lunglei Road Division-I |  |  | 100% |  |  |  | 100% |  | Phy.Completed
736 | Const. of PCC pavement from Bazar veng Thlanmual No.2 BNRGSK Building to Pu Tawnga Garden | 28.98 | Lunglei Road Division-I |  |  | 100% | 48.31 |  |  | 100% | 48.31 | Phy.Completed
737 | Const. of PCC pavement approach road to Lunglei venghlun Cemetary | 28.98 | Lunglei Road Division-I |  |  | 100% |  |  |  | 100% |  | Phy.Completed
738 | Const. of PCC pavement from Ngaihlova's House to Mini Sport Complex | 28.98 | Lunglei Road Division-I |  |  | 100% |  |  |  | 100% |  | Phy.Completed
739 | Strengthening and Resurfacing of Aizawl - Thenzawl - Lunglei Road from 160.00-164.00 Kmp (Kikawn - AOC veng, Lunglei | 590.07 | Lunglei Road Division-I |  |  | 100% | 427 |  |  | 100% | 427 | Phy.Completed
WORKING ESTIMATE FOR CONSTRUCTION OF RCC PAVEMENT AND CULVERTS FROM BUNGHMUN - THENHLUM - Lungchem in Mizoram for the year 2022-2023 under SASCI.
740 | Const. of Retaining Wall at 4 places between Market Shed to Entrance of Pukpui along ATL Road | 50 | Lunglei Road Division-I |  |  | 50% |  |  |  | 50% |  | Work in progress
741 | Const. of PCC pavement from Santosh Mot's House to Duresh Chandra's house at Mauzam | 4.23 | Lunglei Road Division-I | [8 empty] | Not Yet Started
742 | Const. of PCC pavement from Main Road to Community Hall at Salmur | 2.82 | Lunglei Road Division-I |  |  | 100% | - | - | - | 100% | - | Phy.Completed
743 | Const. of PCC pavement from Lalremruata's House to Lalnunzira's House at New Sachan | 4.51 | Lunglei Road Division-I |  |  | 100% | - |  | - | 100% | - | Phy.Completed
744 | Const. of approach road with PCC pavement from PMGSY road to Phainuam | 10.15 | Lunglei Road Division-I |  |  | 100% | - |  | - | 100% | - | Phy.Completed
745 | Const. of Foot Step from Niachand's House to Lawngkai at Tuikawi | 3.07 | Lunglei Road Division-I |  |  | 13% | - |  | 115 | 13% | 115 | work in progress
746 | Const. of RCC Foot Bridge from Rody Ranjan's House to Jugodhi's House at Tuikawi | 3.54 | Lunglei Road Division-I |  |  | 100% | - |  | - | 100% | - | Phy.Completed
747 | Const. of Retaining Wall near Mandir at Sumasumi | 9.18 | Lunglei Road Division-I |  |  | 100% | - |  | - | 100% | - | Phy.Completed
748 | Const. of PCC pavement from Shantis Pryo's House to football field at Sumasumi | 0.56 | Lunglei Road Division-I |  |  | - | - |  | - | - | - | Not Yet Started
749 | Const. of PCC pavement at Bazar line Old Sachan | 3.38 | Lunglei Road Division-I |  |  | 100% | - |  | - | 100% | - | Phy.Completed
750 | Const. of PCC pavement from Gov't Primary School to Saimawia's House at Laisawral | 3.38 | Lunglei Road Division-I |  |  | 100% | - |  | - | 100% | - | Phy.Completed
751 | Const. of PCC pavement from Lalchhandama's House to Lalvulrenga's House at Laisawral | 1.69 | Lunglei Road Division-I |  |  | 100% | - |  | - | 100% | - | Phy.Completed
752 | Const. of PCC pavement from Internal road to Primary School at Laisawral | 0.34 | Lunglei Road Division-I |  |  | 100% | - |  | - | 100% | - | Work in progress
753 | Const. of PCC pavement from Internal road to P.Thanglura's House at Laisawral | 1.35 | Lunglei Road Division-I |  |  | 100% | - |  | - | 100% | - | Phy.Completed
754 | Const. of Foot Step from Saimawia's House to Baptist Church at Laisawral | 1.23 | Lunglei Road Division-I |  |  | 41% | - |  | - | 41% | - | Work in progress
755 | Const. of PCC pavement from Primary School to Thlanmual Road at Tleu | 2.26 | Lunglei Road Division -I |  |  | 100% |  |  |  | 100% |  | Phy.Completed
756 | Const. of PCC pavement from Saichhunga's House to Vengthar UPC Church at Sesawm | 5.64 | Lunglei Road Division -I |  |  | 100% |  |  |  | 100% |  | Phy.Completed
757 | Const. of PCC pavement from Lalrindika's House to Sahlam Tree at Lungchem | 4.23 | Lunglei Road Division -I |  |  | 100% |  |  |  | 100% |  | Phy.Completed
758 | Const. of PCC pavement from Sahlam Tree to C.Kairuma's House at Lungchem | 4.23 | Lunglei Road Division -I |  |  | 100% |  |  |  | 100% |  | Phy.Completed
759 | Const. of PCC pavement from Lalnunpuia's House to Sub-Centre at Lungchem | 0.42 | Lunglei Road Division -I |  |  | 100% |  |  |  | 100% |  | Phy.Completed
760 | Const. of Foot Step from NERGS House to Main road at Lungchem | 1.23 | Lunglei Road Division -I |  |  | 100% |  |  |  | 100% |  | Phy.Completed
761 | Const. of PCC pavement from Bharat Chandra's House to Priyo Ranjan's House at Marpara 'S' | 6.77 | Lunglei Road Division -I |  |  | 100% |  |  |  | 100% |  | Phy.Completed
762 | Const. of PCC pavement from Priyo Ranjan's House to Sneha Kumar's House at Marpara 'S' | 6.77 | Lunglei Road Division -I |  |  | 100% |  |  |  | 100% |  | Phy.Completed
763 | Const. of PCC pavement from Baptish School to Bazar Line at Marpara 'S' | 6.77 | Lunglei Road Division -I |  |  | 100% |  |  |  | 100% |  | Phy.Completed
764 | Const. of PCC pavement from Monu Ranjan's House to Kanchas House at Marpara 'S' | 7.05 | Lunglei Road Division -I |  |  | 100% |  |  |  | 100% |  | Phy.Completed
765 | Const. of PCC pavement from Lalnunkima's House to Lalnunpuii's House at Bunghmun | 3.38 | Lunglei Road Division -I |  |  | 100% |  |  |  | 100% |  | Phy.Completed
766 | Const. of Foot Step from B.Tlanghmingthanga's House to UPC Church at Bunghmun | 2.45 | Lunglei Road Division -I |  |  | 32% |  |  |  | 32% |  | Work in progress
767 | Const. of PCC pavement from Lalhmingthanga's House to Rochungnunga's House at Bunghmun | 5.08 | Lunglei Road Division -I | [8 empty] | Work not started
768 | Const. of PCC pavement from Primary School -II to High School at Bunghmun | 3.38 | Lunglei Road Division -I |  |  | 100% |  |  |  | 100% |  | Phy.Completed
769 | Const. of Newly Agricultural Link road from Hnawla Dil to Chulpui Lui | 17.22 | Lunglei Road Division -I |  |  | 100% |  |  |  | 100% |  | Phy.Completed
770 | Const. of Newly Agricultural Link road from Chulpui Lui to Sangkawi | 23.87 | Lunglei Road Division -I |  |  | 25% |  |  |  | 25% |  | Work in progress
771 | Const. of PCC pavement from Lalramhluna's House to Main road at Changpui | 1.69 | Lunglei Road Division -I |  |  | 100% |  |  |  | 100% |  | Phy.Completed
772 | Const. of PCC pavement from Changpui to Lunghar chho (Lungchem road) at Changpui | 1.69 | Lunglei Road Division -I |  |  | 100% |  |  |  | 100% |  | Phy.Completed
773 | Const. of PCC pavement from Health Worker's Quarter to Lalchawimawia's House at Dengsur | 2.82 | Lunglei Road Division -I |  |  | 100% |  |  |  | 100% |  | Phy.Completed
774 | Const. of PCC pavement from KV Thanmawia's House to High School at Dengsur | 2.82 | Lunglei Road Division -I |  |  | 100% |  |  |  | 100% |  | Phy.Completed
775 | Const. of PCC pavement from Zoramthanga's House to PWD Road at S.Khawlek | 0.51 | Lunglei Road Division -I |  |  | 100% |  |  |  | 100% |  | Work in progress
776 | Const. of PCC pavement near BCM Church to Primary School at S.Khawlek | 0.56 | Lunglei Road Division -I | [8 empty] | Work not started
777 | Const. of Foot Step near Liantluanga's House to Tuikhur at New Khawlek | 2.04 | Lunglei Road Division -I |  |  | 18% |  |  |  | 18% |  | Work in progress
778 | Const. of Foot Step near Suakthuama's House to Public play ground road near New Khawlek | 3.07 | Lunglei Road Division -I |  |  | 41% |  |  |  | 41% |  | Work in progress
779 | Const. of PCC pavement from BCM Church to Lalsangzuala's House at New Khawlek | 1.13 | Lunglei Road Division -I |  |  | 100% |  |  |  | 100% |  | Phy.Completed
780 | Const. of Slab Culvert near Ngurthangluaia's House at Thenhlum | 5.24 | Lunglei Road Division -I |  |  | 100% |  |  |  | 100% |  | Phy.Completed
781 | Const. of Slab Culvert near Thenhlum Play Ground- I | 7.5 | Lunglei Road Division -I |  |  | 100% |  |  |  | 100% |  | Phy.Completed
782 | Const. of PCC pavement from Main Road to Football Playground at Thenhlum | 0.47 | Lunglei Road Division -I |  |  | 32% |  |  |  | 32% |  | Work in Progress
783 | Const. of Foot Step from Main Road to Middle School | 1.53 | Lunglei Road Division -I |  |  | 14% |  |  |  | 14% |  | Work in Progress
784 | Construction of pavement on Approach Road to Pialthleng at Lunglei District | 724.85 | Lunglei Road Division -I |  |  | 15% |  |  | 119 | 15% | 119 | Work in Progress
HNAHTHIAL DIVISION ;
Improvement & Upgradation of Roads from Hnahthial to Thingsai
Improvement and upgradation of Hnahthial - Thingsai Road (50.00 lakhs)
785 | (a) Retaining Wall on H-T at Ch.3.750 Kmp | 5.18 | Hnahthial Division |  |  | 100% | 2.59 |  |  | 100% | 2.59 | Phy.Completed
786 | (b) Retaining Wall on H-T at Ch. 5.450 Kmp | 6.62 | Hnahthial Division |  |  | 100% | 3.31 |  |  | 100% | 3.31 | Phy.Completed
787 | © Retaininh Wall on H-T at Ch. 9.450 Kmp | 5.55 | Hnahthial Division |  |  | 100% | 2.78 |  |  | 100% | 2.78 | Phy.Completed
788 | (d) Retaining Wall on H-T at Ch. 43.300 Kmp | 2 | Hnahthial Division |  |  | 100% | 1 |  |  | 100% | 1 | Phy.Completed
789 | (e) Improvement and widening of H-T Road at Ch. 3.550 - 3.610 Kmp | 7.65 | Hnahthial Division |  |  | 100% | 3.83 |  |  | 100% | 3.83 | Phy.Completed
790 | Resurfacing of Hnahthial - Tumtukawn Road at Ch. 5.000-6.00 Kmp | 23 | Hnahthial Division |  |  | 100% | 11.5 |  |  | 100% | 11.5 | Phy.Completed
791 | Construction of Darzo (Kawipui) Saibuchhuah Road | 100 | Hnahthial Division |  |  | 100% | 50 |  |  | 100% | 50 | Phy.Completed
792 | Improvement of Internal Road within Thingsai Village | 50 | Hnahthial Division |  |  | 100% | 25 |  |  | 100% | 25 | Phy.Completed
793 | PCC Flooring of Tarpho to Aithur Roas | 170 | Hnahthial Division |  |  | 60% |  | 20% |  | 80% |  | Work in progress
794 | PCC pavement from MTR (Road) Tuipui D to Nghafuan (R.Tuipui) Road | 80 | Hnahthial Division |  |  | 100% | 40 |  |  | 100% | 40 | Phy.Completed
795 | (g) Improvement of road from Hnahthial Town to Takam tlaw | 50 | Hnahthial Division |  |  | 100% | 25 |  |  | 100% | 25 | Phy.Completed
Construction and Upgradation of Road from Bualpui V to River Mat via Lungmawi
796 | (a) Strengthening/Widening of Road between Bualpui V to River Mat via Lungmawi | 100 | Hnahthial Division |  |  | 70% | 25.58 | 10% |  | 80% | 25.58 | Work in progress
797 | (b) Const./FC of Road between Pangzawl to Tuichang | 30 | Hnahthial Division |  |  | 100% | 14.49 |  |  | 100% | 14.49 | Phy.Completed
798 | (c) Improvement of Internal Road between main Pangzawl Village to upper Pangzawl | 30 | Hnahthial Division |  |  | 100% | 14.5 |  |  | 100% | 14.5 | Phy.Completed
799 | (d) Const./FC of Agriculture Link Road at Thiltlang | 15 | Hnahthial Division |  |  | 100% | 7.25 |  |  | 100% | 7.25 | Work in progress
800 | (e) Const./FC of Agriculture Link Road at Rawpui | 10 | Hnahthial Division |  |  | 100% | 4.83 |  |  | 100% | 4.83 | Phy.Completed
801 | (f) Const./FC within Agriculture Link Road at Phaileng S | 10 | Hnahthial Division |  |  | 100% | 4.83 |  |  | 100% | 4.83 | Phy.Completed
802 | (g) Const of PCC Pavement from Haulawng to Community Hall | 8 | Hnahthial Division |  |  | 100% |  |  |  | 100% |  | Phy.Completed
Construction and Upgradation of Retaining Wall at Zobawk Ringroad
803 | (1) Re-Construction of permanent works at Tawipui N Mualcheng S at chainage 1.00 kmp, 2.500 kmp, 3.700 kmp, 3.720 kmp & 5.500 kmp | 38.4 | Hnahthial Division |  |  | 100% | 18.55 | - | 0.65 | 100% | 19.2 | Phy.Completed
804 | (2) Construction of PCC pavement Vanlalhmuaki House to Middle School Road at Lungpuizawl | 4 | Hnahthial Division |  |  | 100% | 2 |  |  | 100% | 2 | Phy.Completed
805 | (3) Construction of PCC Pavement at Hmingthana House to HS Lalhmunmawia House at Lungpuizawl | 3 | Hnahthial Division |  |  | 100% | 1.5 |  |  | 100% | 1.5 | Phy.Completed
806 | (4) Construction of PCC Pavement PCI Biakin to Public Playground at Lungpuizawl | 3 | Hnahthial Division |  |  | 100% | 1.5 |  |  | 100% | 1.5 | Phy.Completed
807 | (5) Construction of Retaining wall at NEI UPC Zobawk Local at Zobawk S | 9 | Hnahthial Division |  |  | 100% | 4.5 |  |  | 100% | 4.5 | Phy.Completed
808 | (6) Construction of Retaining Wall at Zobawk Venglai near Community Hall at Zobawk Venglai | 5 | Hnahthial Division |  |  | 100% | 2.5 |  |  | 100% | 2.5 | Phy.Completed
809 | Construction of Internal Road with Widening from Pu Kawlramtawna House to Tuitai Kawi at Zobawk Venglai | 9.5 | Hnahthial Division |  |  | 50% |  |  |  | 50% |  | Work in progress
810 | Construction of PCC Pavement Public playground to Transformer at Zobawk Vengthar | 4.5 | Hnahthial Division |  |  | 100% | 2.25 |  |  | 100% | 2.25 | Phy.Completed
811 | Construction of PCC Pavement Zabuanga House to Zailawma House at Zobawk Vengthar | 6 | Hnahthial Division |  |  | 100% | 3 |  |  | 100% | 3 | Phy.Completed
812 | Construction of Retaining Wall near Gov"t High School Road (Hmawng hnuai) at Zobawk Vengthar | 6 | Hnahthial Division |  |  | 100% | 3 |  |  | 100% | 3 | Phy.Completed
813 | Const.of Retaining Wall at B.Laltanpuia house at Zobawk Venghlun | 5 | Hnahthial Division |  |  | 100% | 2.5 |  |  | 100% | 2.5 | Phy.Completed
814 | Construction of PCC pavement between C.Vanlalhmuaka House to P.Lalromawia House at Zobawk Bazar | 10 | Hnahthial Division |  |  | 100% | 5 |  |  | 100% | 5 | Phy.Completed
815 | Construction of PCC pavement between Ralvawng mual Volley Ball Court at Zobawk Bazar | 5.5 | Hnahthial Division |  |  | 100% | 2.75 |  |  | 100% | 2.75 | Phy.Completed
816 | Const.of PCC Pavement between Pu Lallawma House to Pu V.Zoramthanga house at Zobawk Venghlun | 6 | Hnahthial Division |  |  | 100% | 3 |  |  | 100% | 3 | Phy.Completed
817 | Construction of RCC Steps C.Lalchungnunga House to Lallianpuii House at Zobawk Venghlun | 4.5 | Hnahthial Division |  |  | 100% |  |  |  | 100% |  | Phy.Completed
818 | Repairing and Widening of Road, Sairep to Hlumte Road | 12 | Hnahthial Division |  |  | 100% | 6 |  |  | 100% | 6 | Phy.Completed
819 | Construction of Retaining Wall near BCM Biakin and Lalramlawma House between Lalnunhlua house at Hlumte | 4 | Hnahthial Division |  |  | 100% | 2 |  |  | 100% | 2 | Phy.Completed
820 | Construction of Bawkzau (Sairep village potential area) Link Road from Sairep Village | 40 | Hnahthial Division |  |  | 100% | 20 |  |  | 100% | 20 | Phy.Completed
IMPROVEMENT OF HNAHTHIAL TOWN ROAD
821 | SMBT of approach Road to HDFA Playground | 63.6 | Hnahthial Division |  |  | 100% | 31.8 |  |  | 100% | 31.8 | Phy.Completed
822 | Resurfacing within Hnahthial Town | 31.51 | Hnahthial Division |  |  | 100% | 15.76 |  |  | 100% | 15.76 | Phy.Completed
823 | RCC Drain on approach Road to DC Office | 3 | Hnahthial Division |  |  | 100% | 1.5 |  |  | 100% | 1.5 | Phy.Completed
824 | Retaining wall at Ch: 0.4 Km on approach Road to Zosangliana House to Lalduhawma House | 1.89 | Hnahthial Division |  |  | 100% | 0.95 |  |  | 100% | 0.95 | Phy.Completed
Construction of Pavement at Tawipui S - Tawipui N
825 | (i) Const.of PCC Pavement Tawipui S approach road | 30 | Hnahthial Division |  |  | 100% | 15 |  |  | 100% | 15 | Phy.Completed
826 | (ii) Construction of PCC Pavement Tawipui N-II HS approach road | 40 | Hnahthial Division |  |  | 100% | 20 |  |  | 100% | 20 | Phy.Completed
827 | (iii) Const.of PCC Pavement Road from Tawipui S Bazar (NH 54) to Hermon Veng | 45 | Hnahthial Division |  |  | 100% | 22.5 |  |  | 100% | 22.5 | Phy.Completed
828 | (iv) Const.of PCC Pavement Road from NH 54 to Thualthu Bazar to Upper Thaulthu | 45 | Hnahthial Division |  |  | 100% | 22.5 |  |  | 100% | 22.5 | Phy.Completed
829 | (v) Const.of Thangpui and Thangte Village Road from Vaisam PMGSY Road (at Thangpui Khawhnuai Chainage) | 40 | Hnahthial Division |  |  | 100% | 20 |  |  | 100% | 20 | Phy.Completed
830 | (vi) Cons.of Ngengpui Zau Link road from Thlisam Road | 25 | Hnahthial Division |  |  | 100% | 12.5 |  |  | 100% | 12.5 | Work in progress
831 | (vii) Const.of Mat Zau Link road from Tawipui N-II | 50 | Hnahthial Division |  |  | 100% | 25 |  |  | 100% | 25 | Phy.Completed
832 | (viii) Const.of Ruangte river zau Link road from Vaisam PMGSY Road | 20 | Hnahthial Division |  |  | 100% | 10 |  |  | 100% | 10 | Phy.Completed
ROTLANG EAST & LEITE
833 | Construction of link road Silaitlak (Balu lakna) Road at Rotlang 'E' | 5 | Hnahthial Division |  |  | 100% | 2.42 |  |  | 100% | 2.42 | Phy.Completed
834 | Construction PCC Pavement at High School Road at Rotlang 'E' | 6 | Hnahthial Division |  |  | 100% | 2.9 |  |  | 100% | 2.9 | Phy.Completed
835 | Construction PCC Pavement near F.Malsawmthanga Gouse at Rotlang 'E' | 2 | Hnahthial Division |  |  | 100% | 0.97 |  |  | 100% | 0.97 | Phy.Completed
836 | Construction of Retaining Wall at Middle School at Rotlang 'E' | 2 | Hnahthial Division |  |  | 100% | 0.97 |  |  | 100% | 0.97 | Phy.Completed
837 | Construction of Waiting Shed at Chinrang Kawn and Ramrikawn at Ralvawng | 3 | Hnahthial Division |  |  | 100% | 1.45 |  |  | 100% | 1.45 | Phy.Completed
838 | Construction of Link Road at New Ralvawng to Old Ralvawng | 5 | Hnahthial Division |  |  | 100% | 2.42 |  |  | 100% | 2.42 | Phy.Completed
839 | Construction of PCC Pavement from Ramthim Dawr to Govt. Primary School at Leite | 3 | Hnahthial Division |  |  | 100% | 1.45 |  |  | 100% | 1.45 | Phy.Completed
840 | Construction of PCC Step with Railing and Side Drain between NH-54 to K.Vanramenga House at Leite | 7 | Hnahthial Division |  |  | 100% |  |  |  | 100% |  | Phy.Completed
SIAHA DIVISION :
841 | Strengthening and Improvement of Kawlchaw to Serkawr Road | 318 | Siaha Division | 21.03.23 | 21.03.24 | 26.66% | 53.91 |  |  | 26.66% | 53.91 | Work in progress.
842 | Improvement and Upgradation of Siaha to Thingsen Road upto NH 54B Junction (7.00km) | 778.53 | Siaha Division | 21.03.23 | 21.03.24 | 3.05% | 27.82 |  |  | 3.05% | 27.82 | Work in progress.
843 | Construction of RCC Slab Culvert on I&PRO Office to Upper Council Vaih Road at 0.200kmp | 38.29 | Siaha Division | 06.03.23 | 30.04.23 | 100% |  |  | 38.29 | 100% | 38.29 | Phy. completed
844 | Re-construction of Slab Culvert on Chheihlu to Chakhang Road at 9.100kmp | 9.4 | Siaha Division | 21.03.23 | 21.03.24 | 100% |  |  | 9.4 | 100% | 9.4 | Work Phy. completed
845 | Construction of Retaining Wall near EE, PWD Qtrs at Ch:0.020Km | 8.74 | Siaha Division | 21.23.23 | 30.04.23 | 100% |  |  | 8.74 | 100% | 8.74 | Work Phy. completed
846 | Wifening Road at Cheural - Lungzarhtum - Vartekkai - Sangau (11.50Km) in Mizoram for the year 2022-23 under SASCI Group-1. Widening of Road from BCM Church to BRTF Road via Middle School at Cheural Town Extension (L=1.800km) | 43.11 | Siaha Division | 09.04.23 | 08.07.23 | 42.53% | 0.75 |  | 9.34 | 42.53% | 10.09 | Work in progress
847 | Wifening Road at Cheural - Lungzarhtum - Vartekkai - Sangau (11.50Km) in Mizoram for the year 2022-23 under SASCI Group-2. Widening of Road from LIKBK Pastor Qtr to Pu H.Lalhranga House at Lungzarhtum (L=1.500km) | 44.54 | Siaha Division | 09.04.23 | 08.07.23 | 78.5% | 22.27 |  |  | 78.5% | 22.27 | Work in progress.
848 | Wifening Road at Cheural - Lungzarhtum - Vartekkai - Sangau (11.50Km) in Mizoram for the year 2022-23 under SASCI Group-3 Widening of Road from NEC road Junction to Vartekkai with construction of minor bridge (L=7.000km) | 207.28 | Siaha Division | 09.04.23 | 08.04.24 | 85.08% | 89.21 |  |  | 85.08% | 89.21 | Work in progress.
849 | Wifening Road at Cheural - Lungzarhtum - Vartekkai - Sangau (11.50Km) in Mizoram for the year 2022-23 under SASCI Group-4 Widening of Road from Tourist Lodge to Vengthar Field via SDO (C) Complex at Sangau (L=0.860km) | 20.07 | Siaha Division | 09.04.23 | 08.07.23 | 45.29% | 7.58 |  |  | 45.29% | 7.58 | Work in progress.
850 | Formation Cutting of Road to Sand Quarry at Bualpui 'NG' -Archhuang-Sangau-Lungpher (15.46Km) in Mizoram for the year 2022-23 under SASCI | 61.84 | Siaha Division | 09.04.23 | 08.07.23 | 40.52% | 21.89 |  | 8.61 | 40.52% | 30.5 | Work in progress.
851 | Formation Cutting of Road to Sand Quarry at Bualpui 'NG' -Archhuang-Sangau-Lungpher (15.46Km) in Mizoram for the year 2022-23 under SASCI | 49.63 | Siaha Division | 09.04.23 | 08.07.23 | 56.72% | 24.82 |  |  | 56.72% | 24.82 | Work in progress.
852 | Formation Cutting of Road to Sand Quarry at Bualpui 'NG' -Archhuang-Sangau-Lungpher (15.46Km) in Mizoram for the year 2022-23 under SASCI | 38.91 | Siaha Division | 09.04.26 | 08.07.26 | 75.93% | 16.42 |  |  | 75.93% | 16.42 | Work in progress.
853 | Formation Cutting of Road to Sand Quarry at Bualpui 'NG' -Archhuang-Sangau-Lungpher (15.46Km) in Mizoram for the year 2022-23 under SASCI | 125.86 | Siaha Division | 09.04.23 | 08.04.23 | 67.88% | 56.18 |  |  | 67.88% | 56.18 | Work in progress.
KAWRTHAH DIVISION :
854 | Construction & Upgradation of Bairabi-Zamuang Road (0.00-4.00Kmp) in Mizoram under SASCI | 330 | Kawrthah Division | 22.2.23 | 22.5.23 | 100% | 165 |  |  | 100% | 165 | Phy.Completed
MAMIT DIVISION :
855 | Construction of Mamit Ring Road (5.66) | 600 | Mamit Division | 22.2.24 | 22.5.24 | 76% | 293.79 | 2% |  | 78% | 293.79 | Work in Progress
856 | Pavement of Rawpuichhip to Buarpui Road (47.27-58.00Km) | 511 | Mamit Division | 22.2.25 | 22.5.25 | 94% | 255 | 1% |  | 95% | 255 | Work in progress
SERCHHIP DIVISION :
857 | Construction of Pavement, retaining wal, culverts and Balcony at Serchhip Internal Road | 269 | Serchhip Division | 27.2.23 | 27.2.24 | 100% | 134.46 |  |  | 100% | 134.46 | Phy.Completed
858 | Construction of Economic Road at Tuikum in Mizoram for the year 2022-2023 | 250 | Serchhip Division | 27.2.23 | 27.2.24 | 100% | 125 |  |  | 100% | 125 | Phy.Completed
859 | Improvement of Existing Road Artahkawn-Biate-Tuipui road within Srchhip District (Sh: Strengthening of Chekawn to Artahkawn Road 0.00-80.00Km) pothole filling and path repair of Biate-Tuipui Road 0.00-18.00Kmp) | 739 | Serchhip Division | 27.2.23 | 27.2.24 | 95% | 375.78 |  |  | 95% | 375.78 | Work in progress
860 | Construction of DS.Chawngtui-N.Vanlaiphai Road (0.00-14.800Kmp) Phase-II (Parmanent Works) | 295 | Serchhip Division | 15.2.23 | 27.10.24 | 45% | 93.03 |  |  | 45% | 93.03 | Work in progress
861 | Construction of Strengthening of double lane BUGS Bridge Over R.Tuichang at 6.00Kmp on Keitum-Artahkawn Road (40R-70R) | 343 | Serchhip Division | 15.2.23 | 31.3.23 | 100% | 116.81 |  |  | 100% | 116.81 | Phy.Completed
LAWNGTLAI DIVISION :
Improvement of Thlengang to river Chhimtuipui Road :
862 | Construction of RCC Dock along with approach Slab | 23.31 | Lawngtlai Division | 11.05.23 | 10.4.24 | 65% |  | 10% | 5.7 | 75% | 5.7 | Work in progress
863 | Widening of Lawngtlai to Sahriluichhuah (Kalodyne River) Balu Road | 94.8 | Lawngtlai Division | 11.05.23 | 10.4.24 | 80% |  | 10% |  | 90% |  | Work in progress
864 | Improvement of Bethel veng to Chengkawllui road at College veng, Lawngtlai | 90.84 | Lawngtlai Division | 11.05.23 | 10.4.24 | [6 empty] | Not yet started
Improvement of Thlengang to river Chhimtuipui Road :
865 | Formation cutting of Vathuampui to Mautlang Road | 70.47 | Lawngtlai Division | 11.05.23 | 10.4.24 | 100% |  |  | 35.21 | 100% | 35.21 | Phy.Completed
866 | Widening of Bungtlang 'S' to Saikhawthlir Road | 56.15 | Lawngtlai Division | 11.05.23 | 10.4.24 | 100% |  |  | 25.08 | 100% | 25.08 | Phy.Completed
867 | Widening of Hmawngbu to Kakichhuah Road | 61.99 | Lawngtlai Division | 11.05.23 | 10.4.24 | 100% |  |  | 15.84 | 100% | 15.84 | Phy.Completed
IMPROVEMENT OF DILTLANG TO CHAWNGTELUI ROAD
868 | Construction of Retaining Wall at Certain Location | 25.07 | Lawngtlai Division | 11.05.23 | 10.4.24 | 90% |  | 10% | 13.2 | 100% | 13.2 | Phy Completed
869 | Resurfacing of NH-54 to DTO Office (including courtyard) at Chanmari, Lawngtlai | 6.99 | Lawngtlai Division | 11.05.23 | 10.4.24 | [6 empty] | Not yet started
870 | Construction of Minor Bridge between Khawmawi Bazar Veng to Khawmawi Vengthar | 34.48 | Lawngtlai Division | 11.05.23 | 10.4.24 | 100% |  |  | 17.23 | 100% | 17.23 | Phy.Completed
871 | Black topping of internal road at Lawngpuighat | 81.65 | Lawngtlai Division | 11.05.23 | 10.4.24 | [6 empty] | Not yet started
872 | Construction of Playground approach road at Thingfal Mamte Veng | 19.49 | Lawngtlai Division | 11.05.23 | 10.4.24 | 100% |  |  |  | 100% |  | Phy.Completed
873 | Consultancy fee for Roads | 66.55 | Lawngtlai Division | 11.05.23 | 10.4.24 | 15% |  |  | 9.98 | 15% | 9.98 | Work iprogress
874 | Consultancy Fee for Bridges | 106.39 | Lawngtlai Division | 11.05.23 | 10.4.24 | 70% |  |  | 53.2 | 70% | 53.2 | Work progress
AIZAWL BUILDING DIVISION :
875 | Upgradation of Raj Bhavan, Chief Minister Bungalow, Secretsriat Building & Assembly Building | 117.34 | Aizawl Building Division | 30.03.2023 | 30.03.2024 | 100% | 117.34 |  |  | 100% | 117.34 | Phy Completed