## NABARD
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding: NABARD | [8 empty] | Month : January 2024
Sl. no | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Const.of BUSG Composite Bridges over R.Chepte on Bilkhawthlar to Saiphai Road | 508.45 | Kolasib Division | 24.6.19 | 31.03.22 | 42% | 128.5 |  | - | 42% | 128.5
2 | Const.of BUSG Composite Bridges over R.Sesih on Bilkhawthlar to Saiphai Road | 281.12 | Kolasib Division | 24.6.19 | 31.03.22 | 49% | 104.05 |  | 18.62 | 49% | 122.67
3 | Design & Construction of T-Beam Bridge Package-II at Bulung River (CH:10.20 KMP) | 996 | Kolasib Division | 24.12.21 | 24.06.23 | - | - | - | - | - | - | Soil sample taken on 29.11.2023 and submitted to MZU for design
4 | Design & Construction of T-Beam Bridge Package-II at Damdiai River (CH:23.50 KMP) | 996 | Kolasib Division | 24.12.21 | 24.06.23 | - | - | 5% | - | 5% | - | Foundation at Hortoki side is being constructed
5 | Design & Construction of T-Beam Bridge Package-I at Chhimluangte River (CH:0.450 KMP) | 969.01 | Kolasib Division | 18.12.21 | 18.06.23 | 23% | 28.56 |  | - | 23% | 28.56
6 | Design & Construction of T-Beam Bridge Package-I at Dumkhel River (CH:5.50 KMP) | 969.01 | Kolasib Division | 18.12.21 | 18.06.23 | 23% | - |  | - | 23% | -
7 | Const.of Meidum to Hortoki Road Phase -II (Km 9.100 to Km 26.000) SH: Earthworks and Permanent works from Km 9.100-Km 13.325) Package -I | 1087.32 | Kolasib Division | 24.12.21 | 09.03.24 | 80% | 830.99 | 1% |  | 81% | 830.99
8 | Const.of Meidum to Hortoki Road Phase -II (Km 13.325 to Km 17.500 SH: Earthworks and Permanent works from Km 13.325 to Km 17.500) Package -II | 1171 | Kolasib Division | 25.12.21 | 25.06.23 | 70% | 560.13 | 10% |  | 80% | 560.13
9 | Const.of Meidum to Hortoki Road Phase -II (Km 17.500 to Km 21.725 SH: Earthworks and Permanent works from Km 15.690 to Km 19.005) Package -III | 1422 | Kolasib Division | 18.12.21 | 18.06.23 | 80% | 1054.73 |  |  | 80% | 1054.73
10 | Const.of Meidum to Hortoki Road Phase -II (Km 21.725 to Km 26.000 SH: Earthworks and Permanent works from Km 19.005 to Km 22.360) Package -IV | 959 | Kolasib Division | 08.12.21 | 8.06.23 | 90% | 866.08 | 2% |  | 92% | 866.08
11 | Construction of Meidum to Hortoki Road Phase - II (Km 9.100 to 26.000): SH: Construction of Rigid pavement: Package-I (Km 9.100-Km 15.730) | 2390.08 | Kolasib Division | 03.08.22 | 03.08.23 | 0.14% | 440.93 | - |  | 0.14% | 440.93
12 | Construction of Meidum to Hortoki Road Phase - II (Km 9.100 to 26.000): SH: Construction of Rigid pavement: Package-II (Km 15.73-Km 22.36) | 2390.08 | Kolasib Division | 24.12.21 | 24.06.23 | 0.14% | 341.16 | - |  | 0.14% | 341.16
13 | Construction of link Road from NH-306 (PHE pump House) to R.Aitlang Lui Basin Crop Land : Length = 9.22 Kms | 465.66 | Kolasib Division | 12.08.22 | 12.08.23 | 60% | 266.35 | - | 177.97 | 60% | 444.32 | Works completed | Restricted Tender
14 | Construction of link Road from NH-306 (Vairengte) to Sabual Mual Arable Crop Land = 3.720 Kms | 418.89 | Kolasib Division | 13.08.22 | 13.08.23 | 55% | 211.4 | - |  | 55% | 211.4 |  | Restricted Tender
15 | Construction of Agriculture Link Road from NH-306 A to Buarchep Arable Crop Land : Length = 1.720 Kms | 175.03 | Kolasib Division | 27.08.22 | 27.08.23 | 100% | 101.65 |  | 68.91 | 100% | 170.56 | Work physically completed | Restricted Tender
16 | Construction of 24 Warehouses with associated Infrstructure in 23 locations in Mizoram under NABARD (Group-II Zuangtui/Sairang) | 440.97 | Project Division-I | 17.7.23 | 31.3.25 | 0.2% | - |  | - | 0.2% | - |  | EPC
17 | Re-Construction of Primary Health Centre at Bukpui | 267.004 | Project Division-II | 06.01.22 | 06.07.23 | 100% | 267.004 |  |  | 100% | 267.004 | Work Completed | Item Rate
18 | Re-Construction of Primary Health Centre at Marpara | 267.62 | Project Division-II | 25.03.22 | (O)25.9.23R)20.12.23 | 100% | 232.82 |  |  | 100% | 232.82 | Work Physically completed | Item Rate
19 | Construction of 24 Warehouses with associated Infrastructure in 23 locations in Mizoram Group-I (Scheme-NABARD) i) Construction of Warehouse and other amenities at Bairabi | 316.55 | Project Division-II | 17.07.23 | 31.03.25 | 5% |  |  |  | 5% |  | Work in progress | Item Rate
| ii) Construction of Warehouse and other amenities at Marpara | 235.73 | Project Division-II | 17.07.23 | 31.03.25 | 8% |  | 12% |  | 20% |  | Work in progress | Item Rate
| iii) Construction of Warehouse and other amenities at Sialsuk SC | 171.09 | Project Division-II | 17.07.23 | 31.03.25 | 5% |  | 2% |  | 7% |  | Work in progress | Item Rate
| iv) Construction of Warehouse and other amenities at Zawlnuam | 176 | Project Division-II | 17.07.23 | 31.03.25 | 3% |  | 2% |  | 5% |  | Work in progress | Item Rate
| v) Construction of Warehouse and other amenities at Zawlnuam | 175.8 | Project Division-II | 17.07.23 | 31.03.25 | 4% |  | 4% |  | 8% |  | Work in progress | Item Rate
20 | Construction of 24 Warehouses with associated Infrastructure in 23 lacations in Mizoram Group-IX (Scheme-NABARD) i) Construction of Warehouse and other amenities at Phuldungsei | 175.81 | Project Division-II | 17.07.23 | 31.03.25 | 3% |  | 5% |  | 8% |  | Work in progress | Item Rate
21 | Re-Construction of double storied PHC Building at Bungzung | 268.99 | Project Division-III | 3.1.21 | 3.6.23 | 100% | 268.99 |  |  | 100% | 268.99 | Work completed & Handed over to H&FW Deptt. | PWD Form-8
22 | Re-Construction of double storied PHC Building at Ngentiang | 266.51 | Project Division-III | 3.12.21 | 13.6.23 | 100% | 266.51 |  |  | 100% | 266.51 | Work completed & Handed over to H&FW Deptt. | PWD Form-8
23 | Construction of 24 Warehouses with associated Infrastructure in 23 locations in Mizoram under NABARD (Group-VII: Teikhang, Rabung & Dungtlang) | 336.53 | Project Division-III | 17.7.23 | 31.3.23 | [6 empty] | Dismantling of existing building required | PWD Form-8
24 | Construction of 200 MT Capacity warehouse & staff quarter at Zohmun | 170.99 | Project Division-IV | 17.07.23 | 31.03.25 | [6 empty] | Work could not be started due to non finalization of the work site. Actions are being taken by the client department (i.e FCS&CA) to solve the issues | Item Rate
25 | Improvement & Strengthening of Nalkawn - Chamdur Valley | 2616.41 | Lawngtlai Division | 09.08.22 | 31.12.24 | 55.42% | 1582.47 | 6.49% | 1.31 | 61.91% | 1583.78 | Supplementary Agreement has been signed on 16.01.24 pursuant to revised/reduced AA amount of Rs.26.16 cr. | Item Rate
26 | Const.of double lane built up Steel Girden Bridge over R.Teirei (Span -102m) at Ch.7.00 Kmp on Bairabi Zamuang Road | 2322.42 | Kawrthah Division | 5.8.17 | 30.6.24 | 55% | 1365.6 | 0.2% |  | 55.2% | 1365.6 | Work in progress | Contract after call of Restricted Tender
27 | Const.of double lane built up Steel Girden Bridge (Span-81m) over R.Langkaih on Mizoram-Tripura Border at Kanhmun | 2231.91 | Kawrthah Division | 6.4.18 | 30.11.24 | 41.2% | 1179.03 | 0.7% |  | 41.9% | 1179.03 | Work in progress | Contract after call of Restricted Tender
28 | Construction of Agriculture Link Road in Nothern Mizoram (Sh: Construction of Link Road from Saikhawthlir to R.Hnanglui Arable crop land, Length = 3.50 kms) | 362.02 | Kawrthah Division | 20.08.22 | 20.08.23 | 41.73% | 145.49 | 10.57% |  | 52.3% | 145.49 | Work in progress | Contract after call of Restricted Tender
29 | Construction of Agriculture Link Road in Nothern Mizoram (Sh: Construction of Link Road from Chuhvel to R.Hnanglui Arable crop land, Length = 2.35 kms) | 284.76 | Kawrthah Division | 18.08.22 | 30.4.24 | 47.9% | 133.77 |  |  | 47.9% | 133.77 | Work in progress | Contract after call of Restricted Tender
30 | Construction of Agriculture Link Road in Nothern Mizoram (Sh: Construction of Link Road from from Thinghlun to Hriphaw through permanent crop length=9.570 kmp) | 385.61 | Kawrthah Division | 20.08.22 | 31.5.24 | 70.22% | 209.62 | 1.64% | 86.35 | 71.86% | 295.97 | Work could not be progressed due to decision to be taken by authority regarding type of 3 bridges to be constructed | Contract after call of Restricted Tender
31 | Upgradation of Meidum to Hortoki Phase-I (0.0-9.10) | 4445 | NHD-III | 26.5.20 | 26.11.21 1st EOT=211 days (21.11.21-20.6.22) 2nd EOT=375 days (21.6.22-30.6.23) 3rd EOT =243 days (30.6.23-28.2.24) | 78.56% | 2776.23 | 0.93% |  | 79.49% | 2776.23 |  | Item Rate
32 | Construction of River Training Works for Protection of Tlawng River Bank at Bairabi Phase-I (Group-I) | 1111 | NHD-III | 17.10.22 | 17.10.23 1st EOT=166 days 18.10.23-31.3.24 | 100% | 198.7 |  |  | 100% | 198.7 |  | Item Rate
| Phase-I (Group-II) |  |  | 17.10.22 | 17.10.23 1st EOT=166 days 18.10.23-31.3.25 | 65.59% | 121.54 | 3.53% |  | 69.12% | 121.54 |  | Item Rate
| Phase-I (Group-III) |  |  | 17.10.22 | 17.10.23 | 100% | 216.65 |  |  | 100% | 216.65 |  | Item Rate
| Phase-I (Group-IV) |  |  | 17.10.22 | 17.10.23 | 100% | 246.7 |  |  | 100% | 246.7 |  | Item Rate
33 | Construction of MDR from Khamrang (Dilsei) to Selesih (Sh: Construction of approach road to Mualkhang Village) | 14529.27 | NHD-III | 08.02.21 | 08.08.22 | 100% | 122.25 |  |  | 100% | 122.25 |  | Item Rate
34 | Construction of Road from Khamrang to Selesih Phase-II Group-1 (11/00 to 22/00Km) |  |  | 8.11.21 | 8.5.23 1st EOT=210 days (wef 09.05.23- 04.12.23 | 27.06% | 547.46 | 0.03% | - | 27.09% | 547.46 |  | Item Rate
35 | Construction of Road from Khamrang to Selesih Phase-II Group-2 (22/00 to 25/00Km) |  |  | 22.11.21 | 22.11.22 1st EOT=90days (upto -20.02.23) 2nd EOT=90 days (wef 21.2.23-21.5.23) 3rd EOT = 90 days(22.5.23-19.8.23) | 30.09% | 219.81 |  |  | 30.09% | 219.81 |  | Item Rate
36 | Construction of Road from Khamrang to Selesih Phase-II Group-3 (25/00 to 28/00Km) |  |  | 11.11.21 | 11.11.22 1st EOT=104 days (upto -24.02.23) 2nd EOT=90 days (wef 10.2.23-11.5.23) 3rd EOT = 90 days(wef 12.5.23-9.8.23) | 15.34% | 207.28 | 1% |  | 16.34% | 207.28 |  | Item Rate
37 | Construction of Road from Khamrang to Selesih Phase-II (Sh: Construction of Rigid Pavement from 11/00 to 19/00 Kmp=8.00 Kms) Group A |  |  | 26.8.23 | 26.8.25 | [7 empty] | Item Rate
38 | Construction of Road from Khamrang to Selesih Phase-II (Sh: Construction of Rigid Pavement from 19/00 to 28/00 Kmp=9.00Kms) Group B |  |  | 26.8.23 | 26.8.25 | [7 empty] | Item Rate
39 | Construction of MDR from Khamrang-Dilsei to Selesih (Phase-I) (Length = 11.00 Kms) Group-A (0/00 to 3/600Km) | 6583.18 | NHD-III | 8.02.21 | 8.8.22 1st EOT=184 days (upto 08.02.23, 2nd EOT=150 days (upto 08.07.23) | 42.99% | 314.25 |  | - | 42.99% | 314.25 |  | Item Rate
40 | Construction of road from Khamrang to Selesih Phase-I (Length = 11.00 Kms) Group-B (3/60 to 7/200Km) |  | NHD-III | 8.02.21 | 8.8.22 1st EOT=184 days (upto 08.02.23, 2nd EOT=150 days (wef 09.02.23-08.07.23) | 55.63% | 434.62 | 0.08% |  | 55.71% | 434.62 |  | Item Rate
41 | Construction of road from Khamrang to Selesih Phase-I (Length = 11.00 Kms) Group-C (7/200 to 11/00Km) |  | NHD-III | 8.02.21 | 8.8.22 1st EOT=184 days (upto 08.02.23, 2nd EOT=150 days (wef 09.02.23-08.07.23) | 48.18% | 177.27 | 0.01% |  | 48.19% | 177.27 |  | Item Rate
42 | Construction of road from Khamrang to Selesih Phase-I (Sh: Construction of Rigid Pavement from 7/00 to 11/00 Kmp = 4.00 Kms) |  | NHD-III | 16.8.22 | 16.02.24 | 0.31% |  |  |  | 0.31% |  |  | Item Rate
43 | Const.of Double Storied PHC at Lungsen | 267.15 | Lunglei Building Project Division | 10.2.22 | 10.2.24 | 100% | 230.89 |  |  | 100% | 230.89 | Civil Works completed and I/E Works not yet done | Restricted Tender
44 | Const.of Infrastructure Support fro School of Agricultural Science at Hnahthial: Phase-II i) Boys Hostel ii) Staff Quarter Type-III iii) Staff Quarter Type-II iv) Guest House | 685 | Lunglei Building Project Division | 08.04.23 | 08.04.25 | 20% |  | 1% |  | 21% |  | Works in progress | Restricted Tender
45 | 1. Construction of 24 Warehouses with associated Infrastructure in 23 localities in Mizoram under NABARD Gr-III: Siaha, Chapui, Bungtlang South
| 1) Siaha SDC | 444.99 | Lunglei Building Project Division | 17.07.23 | 31.3.25 | 6% |  | 1% |  | 7% |  | Work in progress | Restricted Tender
| 2) Chapui | 197.82 | Lunglei Building Project Division | 17.07.23 | 31.3.25 | 2% |  | 0.5% |  | 2.5% |  | Work in progress
| 3) Bungtlang South | 162.63 | Lunglei Building Project Division | 17.07.23 | 31.3.25 | 7% |  | 10% |  | 17% |  | Work in progress
| 2. Gr-IV: Lungpher | 197.12 | Lunglei Building Project Division | 17.07.23 | 31.3.25 | 20% |  | 2% |  | 22% |  | Work in progress | Restricted Tender
3. Gr-VI: South Vanlaiphai and Vawmbuk
| 1) South Vanlaiphai | 187.15 | Lunglei Building Project Division | 17.07.23 | 31.3.25 | 10% |  | 2% |  | 12% |  | Work in progress | Restricted Tender
| 2) Vawmbuk | 197.82 | Lunglei Building Project Division | 17.07.23 | 31.3.25 | 9% |  | 2% |  | 11% |  | Work in progress
4. Gr-VIII: Hnahthial, Thingsai. Cherhlun and Siata
| 1) Hnahthial | 197.24 | Lunglei Building Project Division | 17.07.23 | 31.3.25 | 1% |  |  |  | 1% |  | Work stayed as selected site falls under Forest Reserve Area. Relocation of site is being awaited from Client Dept. | Restricted Tender
| 2) Thingsai | 160.32 | Lunglei Building Project Division | 17.07.23 | 31.3.25 | 2% |  | 3% |  | 5% |  | Work started
| 3) Cherhlun | 85.61 | Lunglei Building Project Division | 17.07.23 | 31.3.25 | 2% |  | 3% |  | 5% |  | Work started
| 4) Siata | 197.82 | Lunglei Building Project Division | 17.07.23 | 31.3.25 | 7% |  | 1% |  | 8% |  | Work in progress
5. Gr-X: Vaseikai and Tlabung
| 1) Vaseikai | 220.35 | Lunglei Building Project Division | 17.07.23 | 31.3.25 | 5% |  | 11% |  | 16% |  | Work in progress | Restricted Tender
| 2) Tlabung | 93.84 | Lunglei Building Project Division | 17.07.23 | 31.3.25 | 1% |  |  |  | 1% |  | Buillding layout already done. Material Collection undergoing
46 | Strengthening & Improvement of W.Phaileng to Marpara Road (00.00-30.00Kmp) Package-I | 1854.59 | Mamit Division | 15.03.23 | 15.03.25 | 29% |  |  | 291.63 | 29% | 291.63 | Machinery installation completed, operation of Quarry is being started. Physical progress is being achieved
47 | Strengthening & Improvement of W.Phaileng to Marpara Road (30.00-80.00Kmp) Package-II | 4778.8 | Mamit Division | 15.03.23 | 15.03.25 | 29% |  |  | 339.34 | 29% | 451.67
48 | Improvement of Chawngte - Borapansuri Road (0.00-30.00 Kmp) | 3987 | Tlabung Division | 15.3.23 | 15.3.25 | 3.2% |  | 3.1% |  | 6.3% |  | Work in progress | Item rate

## NEC
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding: NEC | [8 empty] | Month : January 2024
Sl. no | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the Month |  | Overall cumulative achievement |  | Remarks | Mode of Contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Lunglei Market and Trade Centre at Electric/Chanmari Veng, Lunglei (NEC) | 1403.4 | Lunglei Building Project Division | 25.08.22 | 25.08.24 | 42% | 298.74 including secured advance 284.86 lakh | 3% | 65.16 | 45% | 363.9 | Work in progress | Restricted Tender
2 | Construction of Mara Handloom & Weaving Centre at Council Vaih, Saiha | 458.61 | Lunglei Building Project Division | 13.04.22 | 13.04.24 | 59% | 131.01 | 2% |  | 61% | 131.01 | Work in progress | Restricted Tender
3 | Improvement & Upgradation of KDZKT Road (0.00 - 88.400Kmp) | 18327.42 | Kawrthah Division | 27.4.15 | 4.6.18 | 100% | 18290 | - |  | 100% | 18290 | Work Phy.Completed on 31.12.21 SMS of R.Revised estimate is being awaited for financial closure | Contract after call of Tender
4 | Const.of Patient Lodging at Mawdiangdiang near NEIGHRIMS, Shillong | 419.67 | Project Division-I | 9.9.21 | 31.7.24 | 20% | 167.87 |  |  | 20% | 167.87 |  | EPC
5 | Infrastructure Development of Biotechnology Cell in Mizoram (C/O Building at MINECO) | 386.6 | Project Division-I | 1.7.23 | 1.5.25 | 8% | 19.22 | 1% |  | 9% | 19.22 |  | EPC
6 | Establishment of Central Medical Warehouse at Aizawl, Mizoram | 1300 | Project Division-I | 4.8.23 | 14.8.25 | [7 empty] | EPC
7 | Construction of Aizawl Institute of Arts & Music for the NER, Tuivamit Tlang, Aizawl | 590.23 | Project Division-I | 4.9.23 | 4.9.25 | 28% |  | 2% |  | 30% |  |  | EPC
8 | Construction of Veterinary Information and Resource Centre at Aizawl | 439.2 | Project Division-I | 31.3.23 | 25.9.25 | 9% | 10 |  |  | 9% | 10 |  | EPC
9 | Construction of 60 Bedded Intern Hostel at ZMC, Falkawn | 679 | Project Division-II | 01.09.22 | 01.05.24 | 45% | 271.6 | 3% |  | 48% | 271.6 | Work in progress | Item Rate
10 | Construction of Market Building at West Phaileng, Mamit District | 278.242 | Project Division-II | 22.08.23 | 22.08.25 | 2% |  | 3% |  | 5% |  | Work in progress | Item Rate
11 | Creation of Passion fruit Processing unit at Cold Storage, New Champhai Mizoram | 185.36 | Project Division-III | 23.09.22 | 24.03.24 | 26% | 10 | 9% |  | 35% | 10 | As per revised sanction by NEC, only civil construction work is under PWD Work in progress | PWD Form-8
12 | Construction of Zomi cultural Centre and preservation of historical sites at Champhai | 478.69 | Project Division-III | 26.09.22 | 26.09.24 | 23% | 76 | 9% |  | 32% | 76 | Work in progress | PWD Form-8
13 | Construction of Biate Tea Tourism Circuit & Nature Camp in Mizoram | 369.62 | Project Division-III | 9.10.23 | 9.10.25 | 8% |  | 22% |  | 30% | - | Work in progress | PWD Form-8
14 | Forstering Industry, Innovation, Infrastructure and Livelihood Oppurtunities (SDG 9) at Lunglen-1 and Sialhawk, Mizoram and strengthening of Food Testing Laboratory (Sh: Construction of Pineapple precessing plant building at Sialhawk) | 65.7 | Project Division-III | 12.10.23 | 12.10.25 | 12% |  | 23% |  | 35% |  | Work in progress | PWD Form-8
15 | Construction of AYUSH Development Centre at MINECO Aizawl | 264.16 | Project Division-IV | 7.12.22 | 17.8.24 | 39.13% | 40 | 1.97% |  | 41.1% | 40 | Work in progress. | Item Rate
16 | Etablishment of Sinlung Hills Council Administrative Complex (Const.of Sinlung Hills Administrative Building at Sakawrdai) | 381.99 | Project Division-IV | 8.11.21 | 12.03.24 | 57.4% | 152.98 | 0.6% |  | 58% | 152.98 | Work in progress. Work programme submitted. 1st EOT granted for 125 days | Item Rate

## Deposit
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : Deposit | [9 empty] | Month : January 2024
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummutive Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of New Ward Building (Renovation & Upgradation of Central Jail) at Aizawl, Mizoram | 100 | Project Division-I | 28.8.22 | 23.3.24 | 28% | - | 2% | - | 30% | - |  | EPC

## PMGSY
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding: PMGSY | [8 empty] | Month : January 2024
Sl. no | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Diblibagh to Chengkawllui Road (0.000-19.520)Kmp | 2798.82 | Tlabung Division | 17.6.19 | 17.6.20 | 69.77% | 1509.2 | 0.84% |  | 70.61% | 1509.2 | Work delay due to Forest Clearance pending | Item Rate
2 | Diblibagh to Sugarbasora Road (0.000-2.000)Kmp | 305.81 | Tlabung Division | 28.9.18 | 28.9.19 | 73.5% | 211.07 |  |  | 73.5% | 211.07 | Work delay due to Forest Clearance pending Extension granted up to Dt.31.2.23 | Item Rate
3 | Diblibagh to Sugarbasora Road Group B (2.000-4.760)Kmp | 373.19 | Tlabung Division | 22.9.18 | 22.9.19 | 97.6% | 123.6 |  | - | 97.6% | 123.6 | Work delay due to Forest Clearance pending Extension granted upto Dt.31.3.23 | Item Rate
4 | Const & Maintenance of Tlabung-Nunsury Road (0.000-8.000) Kmp | 579.77 | Tlabung Division | 17.6.19 | 17.6.20 | 55.3% | 499.42 |  |  | 55.3% | 499.42 | Work in progress | Item Rate
5 | Const.of Serhuan-Lamthai Road | 1378.12 | Tlabung Division | 21.12.17 | 27.11.19 | 91.5% | 1175.33 |  |  | 91.5% | 1175.33 | Work in progress | Item Rate
6 | Chhotapansuri-Tungasora Road (0.000-2.000)Kmp | 303.43 | Tlabung Division | 22.9.18 | 22.9.19 | 70.6% | 100.06 |  | - | 70.6% | 100.06 | Extension granted upto Dt.13.12.23 | Item Rate
7 | Chhotapansuri-Tungasora Road (2.000-3.500)Kmp | 209.66 | Tlabung Division | 5.10.18 | 5.10.19 | 93.8% | 175.89 | 6.2% |  | 100% | 175.89 | Completed physical works | Item Rate
8 | Mandiasora-Ajasora Road (0.000 - 8.500) Kmp | 734.93 | Tlabung Division | 17.6.19 | 17.6.20 | 92.6% | 635.71 | 3.2% |  | 95.8% | 635.71 | Work in progress | Item Rate
9 | Construction & Maintenance of Sairang - Lengte-Nghalchawm (PMGSY) Road | 842.17 | NHD-I | 19.12.20 | 29.08.23 | 98% | 701.34 |  |  | 98% | 701.34 | Work in progress | Item rate contract
10 | Construction of Dilkhan to Tualbung Road (Sh:-Construction of Road using flexible pavement) | 503.66 | Saitual Division | 27.10.17 | 27.10.19 | 100% | 499.05 | - | - | 100% | 499.05 | EoT Dt.31.7.2022
11 | Construction and Maintenance of Lungpher to Buhban Road (Sh: Construction of road using flexible pavement) | 490.11 | Saitual Division | 13.11.17 | 13.5.19 | 100% | 478.12 | - | - | 100% | 478.12 | EoT Dt.31.11.19
12 | Construction and Maintenance of Phullen to Luangpawn Road (Sh: FC, Culvert & R/Wall and Construction of road using flexible pavement) | 993.46 | Saitual Division | 17.09.18 | 17.09.19 | 100% | 969.75 | - | - | 100% | 969.75 | EoT Dt.31.7.22
13 | Construction and Maintenance of E.Phaileng-Suangpuilawn Road (0.000-6.000Kmp) (Sh: Widening, Culverts & R/Wall and Contstruction of road using flexible pavement) | 831.6 | Saitual Division | 19.12.20 | 19.12.22 | 92.96% | 142.92 | 0.04% | - | 93% | 142.92 | EoT Dt.15.10.23
14 | Construction and Maintenance of E.Phaileng-Suangpuilawn Road (6.000-11.000Kmp) (Sh: Widening, Culverts & R/Wall and Construction of Road using flexible pavement) | 906.48 | Saitual Division | 19.12.20 | 19.12.22 | 78.08% | 116.25 | 0.25% | - | 78.33% | 116.25 | EoT Dt.15.10.23
15 | Construction and Maintenance of E.Phaileng-Suangpuilawn Road (11.000-16.000Kmp) (Sh: Widening, Culverts & R/Wall and Construction of Road using flexible pavement) | 807.85 | Saitual Division | 15.8.20 | 15.8.22 | 100% | 807.24 | - |  | 100% | 807.24 | EoT Dt.31.03.24
16 | [11 empty] | EoT Dt.24.13.24
17 | Construction and Maintenance of E.Phaileng-Suangpuilawn Road (16.000-22.000Kmp) (Sh: Widening, Culverts & R/Wall and Construction of Road using flexible pavement) | 826.35 | Saitual Division | 01.01.21 | 01.01.23 | 77.94% | 305.65 | 0.26% |  | 78.2% | 305.65 | EoT Dt.28.10.23
18 | Construction and Maintenance of E.Phaileng-Suangpuilawn Road (22.000-28.000Kmp) (Sh: Widening, Culverts & R/Wall and Construction of Road using flexible pavement) | 811.18 | Saitual Division | 01.01.21 | 01.01.23 | 100% | 632.27 | - | - | 100% | 632.27 | EoT Dt.28.10.23
19 | Construction and Maintenance of E.Phaileng-Suangpuilawn Road (28.000-34.000Kmp) (Sh: Widening, Culverts & R/Wall and Construction of Road using flexible pavement) | 1133.61 | Saitual Division | 10.02.20 | 10.02.22 | 100% | 531.51 | - | - | 100% | 531.51 | EoT Dt.31.12.22
20 | Construction and Maintenance of E.Phaileng-Suangpuilawn Road 34.000-40.000Kmp) (Sh: Widening, Culverts & R/Wall and Construction of Road using flexible pavement) | 1056.01 | Saitual Division | 6.01.20 | 6.01.22 | 77.74% | 324.95 | 0.11% | 508.38 | 77.85% | 833.33 | EoT Dt.22.05.23
21 | Construction and Maintenance of E.Phaileng-Suangpuilawn Road 40.000-46.000Kmp) (Sh: Widening, Culverts & R/Wall and Construction of Road using flexible pavement) | 1000.02 | Saitual Division | 6.01.20 | 6.01.22 | 77.79% | 342.05 | 0.07% |  | 77.86% | 342.05 | EoT Dt.26.03.23
22 | Construction and Maintenance of Bunghmun-W.Mualthuam Road (Sh: Cell filled Concrete Road) (0.00-13.500 Kmp) | 955.77 | Kawrthah Division | 27.11.17 | 16.9.22 | 100% | 918.23 | - | - | 100% | 918.23 | Works under maintenance from 16.9.22 | Contract after call of Tender
23 | Construction and Maintenance of Bunghmun to Thaidawr Road (0.00 Kmp-8.90 Kmp) | 745.77 | Kawrthah Division | 17.6.19 | 17.6.20 | 100% | 720.72 | - | - | 100% | 720.72 | Works under maintenance from 16.9.22 | Contract after call of Tender
24 | Construction & Maintenance of Khawzawl to Biate Road (0.00 kmp-6.00Km) Group-A | 780.49 | Khawzawl Division | 31.12.20 | 31.12.22 | 80.52% | 485.19 |  |  | 80.52% | 485.19 | EOT granted upto 31.03.24 | Item Rate Contract
25 | Construction & Maintenance of Khawzawl to Biate Road (6.00 kmp-12.00Km) Group-B | 760.98 | Khawzawl Division | 31.12.20 | 31.12.22 | 77.16% | 429.8 | - |  | 77.16% | 429.8 | EOT granted upto 31.03.24 | Item Rate Contract
26 | Construction & Maintenance of Khawzawl to Biate Road (12.00 kmp-18.00Km) Group-C | 817.47 | Khawzawl Division | 2.1.21 | 2.1.23 | 71% | 372.56 | 2% | 127.98 | 73% | 500.54 | EOT granted upto 29.10.23 | Item Rate Contract
27 | Construction & Maintenance of Khawzawl to Biate Road (18.00 kmp-24.00Km) Group-D | 750.94 | Khawzawl Division | 10.6.20 | 10.6.22 | 62.59% | 423.8 |  |  | 62.59% | 423.8 | EOT granted upto 31.03.24 | Item rate contract
28 | Construction & Maintenance of Khawzawl to Biate Road (24.00 kmp-30.00Km) Group-E | 766.62 | Khawzawl Division | 29.4.21 | 29.4.22 | 57% | 291.76 |  |  | 57% | 291.76 | EOT granted upto 1.04.23 | Item Rate Contract
29 | Construction & Maintenance of Khawzawl to Biate Road (30.00 kmp-36.00Km) Group-F | 1148.93 | Khawzawl Division | 7.2.20 | 7.2.22 | 85.54% | 664.74 | - |  | 85.54% | 664.74 | EOT granted upto 31.12.22 | Item Rate Contract
30 | Construction & Maintenance of Khawzawl to Biate Road (36.00 kmp-42.00Km) Group-G | 818.99 | Khawzawl Division | 1.1.21 | 1.1.23 | 91% | 680.48 | 8% |  | 99% | 680.48 | EOT granted upto 31.12.23 | Item Rate Contract
31 | Construction & Maintenance of Khawzawl to Biate Road (42.00 kmp-48.00Km) Group-H | 1430.26 | Khawzawl Division | 6.1.20 | 6.1.22 | 78.78% | 997.07 | 3.22% |  | 82% | 997.07 | EOT granted upto 31.03.24 | Item rate contract
32 | Construction & Maintenance of Khawzawl to Biate Road (48.00 kmp-54.00Km) Group-I | 1108.01 | Khawzawl Division | 24.3.21 | 24.3.22 | 75% | 407.28 |  | - | 75% | 407.28 | EOT granted upto 31.12.22 | Item Rate Contract
33 | Construction & Maintenance of Khawzawl to Biate Road (54.00 kmp-60.00Km) Group-J | 937.99 | Khawzawl Division | 4.1.21 | 4.1.23 | 67.5% | 442.83 | 1.5% |  | 69% | 442.83 | EOT granted upto 31.12.23 | Item Rate Contract
34 | Construction & Maintenance of Khawzawl-Ngaizawl Road | 817.57 | Khawzawl Division | 13.11.17 | 13.11.19 | 93% | 729.12 | - |  | 93% | 729.12 | EOT granted upto 09.12.22 | Item Rate Contract
35 | Construction & Maintenance of Khawhai - Tlangpuilian Road | 962.79 | Khawzawl Division | 13.11.17 | 31.12.19 | 100% | 855.19 |  |  | 100% | 855.19 | EOT granted upto 30.09.2022 | Item Rate Contract
36 | Construction & Maintenance of Khawzawl - Vankal Road | 1997.33 | Khawzawl Division | 13.12.18 | 13.12.19 | 88% | 1625.3 | - |  | 88% | 1625.3 | EOT granted upto 31.11.21 | Item rate contract
37 | Construction & Maintenance of Khawzawl - Hmuncheng Road | 1627.09 | Khawzawl Division | 1) 5.10.18 2)23.05.22 | 1) 5.10.19 2)30.09.22 | 83% | 1163.72 | 4% | 87.3 | 87% | 1251.02 | EOT granted upto 27.02.22 | Item rate contract
38 | Construction & Maintenance of Khawzawl - Hmuncheng Road | 1595.69 | Khawzawl Division | 05.10.18 | 05.10.19 | 75% | 959.03 | - | - | 75% | 959.03 | EOT granted upto 27.02.22 | Item rate contract
39 | Construction & Maintenance of Khawzawl - Hmuncheng Road | 636.68 | Khawzawl Division | 23.05.22 | 30.09.22 | 58% | 291.99 | 11% |  | 69% | 291.99 | EOT Not yet granted | Item rate contract
40 | Construction & Maintenance of Phuldungsei to Parvatui Road (0.00 Kmp - 17.30 Kmp) | 3340.55 | Mamit Division | 13.12.18 | 13.12.19 | 78.5% | 2888.4 | 0.5% | - | 79% | 2888.4 | Revised Target date of completion=31.03.24 Supplemen tary Estimate=36,95,51,610.56 | Item rate
41 | Construction & Maintenance of Tuipuibari to Andermanik Road (0.00 Kmp - 2.760 km) | 430.18 | Mamit Division | 17.9.18 | 17.9.19 | 95% | 297.93 | - | - | 95% | 297.93 | Revised Target date of completion= 31.03.24 | Item rate
42 | Construction & Maintenance of Andermanik to N.Belkhai Road (0.00 Kmp - 6.00 km) | 1016.7 | Mamit Division | 10.6.19 | 10.6.20 | 40% | 248.87 |  |  | 40% | 248.87 | Revised Target date of completion= 31.03.2024 | Item rate
43 | Thuampui - Lungchem Road (23.000 - 27.000 KMP) | 447.49 | Lunglei Road Division-I | 27.10.17 | 21.07.21 | 100% | 447.49 | - | - | 100% | 447.49 | Deviation already approved due to Some items are changed as mentioned in EE letter No.D-13024/5/2019(DV)/S&I/LD/PWD/Pt/10 Dt.18.02.21 Completed
44 | Thuampui - Lungchem Road (27.000 -32.000 KMP) | 395.75 | Lunglei Road Division-I | 27.10.17 | 24.09.21 | 100% | 378.64 | - | - | 100% | 378.64
45 | Thuampui - Lungchem Road (32.000 -37.000 KMP) | 372.33 | Lunglei Road Division-I | 27.11.17 | 30.09.22 | 100% | 372.31 | - |  | 100% | 372.31 | Completed
46 | Thuampui - Lungchem Road (37.000 - 40.900 KMP) | 307.24 | Lunglei Road Division-I | 27.10.17 | 13.08.21 | 100% | 336.09 | - | - | 100% | 336.09 | Completed
47 | Construction and Maintenance of Sachan to Sumasumi Road (0.00 - 24.09 Kmp) | 4005.26 | Lunglei Road Division-I | 10.06.19 | 31.08.22 | 50% | 1831.54 | 7% |  | 57% | 1831.54 | Work in progress
48 | Construction and Maintenance of Sumasumi - Tuikawi Road (0.00 - 19.22 Kmp) | 2882.21 | Lunglei Road Division-I | 14.06.19 | 26.12.21 | 37% | 697.5 | 2% | - | 39% | 697.5 | Work in progress
49 | Thuampui - Lungchem Road (0.000 - 4.000 KMP) | 85.83 | Lunglei Road Division-I | 01.04.21 | 31.03.22 | 100% | 85.83 | - | - | 100% | 85.53 | Completed
50 | Thuampui - Lungchem Road (4.000 - 7.000 KMP) | 268.21 | Lunglei Road Division-I | 27.10.17 | 14.07.21 | 100% | 268.19 | - | - | 100% | 268.19 | Completed
51 | Thuampui - Lungchem Road (7.000 - 10.000 KMP) | 306.59 | Lunglei Road Division-I | 27.10.17 | 15.08.21 | 100% | 306.56 | - | - | 100% | 306.56 | Completed
52 | Thuampui - Lungchem Road (10.000 - 14.000 KMP) | 387.7 | Lunglei Road Division-I | 27.10.17 | 04.07.21 | 100% | 387.68 | - | - | 100% | 387.68 | Completed
53 | Thuampui - Lungchem Road (14.000 - 18.000 KMP) | 394.46 | Lunglei Road Division-I | 13.11.17 | 31.12.22 | 100% | 385.57 | - |  | 100% | 385.57 | Completed
54 | Thuampui - Lungchem Road (18.000 - 21.000 KMP) | 418.83 | Lunglei Road Division-I | 27.10.17 | 07.11.21 | 100% | 418.88 | - |  | 100% | 418.88 | Some items are changes due to Deviation approval vide EE letter no.D-13024/5/2019(DV)/S&I/LDIPWD/28 dt.9.03.22 completed
55 | Thuampui - Lungchem Road (21.000 - 23.000 KMP) | 370.75 | Lunglei Road Division-I | 13.11.17 | 31.07.22 | 100% | 370.74 | - |  | 100% | 370.74 | Completed
56 | Const. & Maint.of Bunghmun to Sachan Road (0.00-9.07Kmp) | 1325.06 | Lunglei Road Division-I | 13.12.18 | 31.07.22 | 60% | 654.39 |  |  | 60% | 654.39
57 | Const. & Maint.of Cherhlun to Ngharchhip Road (0.00-7.64 Kmp) | 554.08 | Lunglei Road Division-II | 13.12.18 | Completed on 31.3.23 | 100% | 529.74 | - |  | 100% | 529.74 | Phy. completed | Open Tender
58 | Const. & Maint.of Khawhri to Chawngtui Road (0.00-17.81 Kmp) | 1280.59 | Lunglei Road Division-II | 8.10.18 | 31.3.24 | 81% | 950.32 |  |  | 81% | 950.32 | Work is in progress | Open Tender
59 | Const. & Maint.of Luangmual to Vaisam Road (0.00-26.700 Kmp) | 4711.5 | Lunglei Road Division-II | 10.06.19 | 31.3.24 | 63% | 2828.46 |  | 284.07 | 63% | 3112.53 |  | Open Tender
60 | Const. & Maint.of Haulawng to Dawn Road (0.00-6.00 Kmp) | 742.02 | Lunglei Road Division-II | 10.06.20 | 31.3.24 | 94% | 623.89 |  | 50.67 | 94% | 674.56 | Work is in progress | Open Tender
61 | Const. & Maint.of Haulawng to Dawn Road (6.00-12.000 Kmp) | 605.77 | Lunglei Road Division-II | 01.01.21 | 31.3.24 | 82% | 189.44 |  | - | 82% | 189.44 | Work is in progress | Open Tender
62 | Const. & Maint.of Haulawng to Dawn Road (12.00-18.000 Kmp) | 607.56 | Lunglei Road Division-II | 01.01.21 | 31.3.24 | 79% | 532.99 |  | 33.88 | 79% | 566.87 | Work in progress | Open Tender
63 | Const. & Maint.of Haulawng to Dawn Road (18.00-24.000 Kmp) | 743.96 | Lunglei Road Division-II | 01.01.21 | 31.3.24 | 85% | 385.71 |  |  | 85% | 385.71 | Work is in progress | Open Tender
64 | Const. & Maint.of Haulawng to Dawn Road (24.00-30.500 Kmp) | 840.58 | Lunglei Road Division-II | 01.01.21 | 31.3.24 | 92% | 492.06 |  |  | 92% | 492.06 | Work is in progress | Open Tender
65 | Construction of Nghalimlui to Bolisora (0.00-3.00)Kmp (Sh: FC, Culvert, R.Wall) | 158.34 | Lawngtlai Division | 27.10.17 | 30.04.20 | 100% | 158.33 | - | - | 100% | 158.33 | Completed | NIT
66 | Construction of Nghalimlui to Bolisora (3.00-5.00)Kmp (Sh: FC, Culvert, R.Wall) | 249.3 | Lawngtlai Division | 27.10.17 | 23.03.20 | 100% | 247.3 | - | - | 100% | 247.3 | Completed | NIT
67 | Construction of Nghalimlui to Bolisora (5.00-8.00)Kmp (Sh: FC, Culvert, R.Wall) | 206.24 | Lawngtlai Division | 27.10.17 | 10.08.20 | 100% | 206.24 | - | - | 100% | 206.24 | Completed | NIT
68 | Construction of Nghalimlui to Bolisora (8.00-12.65)Kmp (Sh: FC, Culvert, R.Wall) | 266.55 | Lawngtlai Division | 27.10.17 | 16.08.20 | 100% | 246.66 | - | - | 100% | 246.66 | Completed | NIT
69 | Construction of Karlui to Damlui (0.00-2.00)Kmp (Sh: FC, Culvert, R.Wall) | 207.84 | Lawngtlai Division | 27.10.17 | 28.2.20 | 100% | 207.66 | - | - | 100% | 207.66 | Completed | NIT
70 | Construction of Karlui to Damlui (2.00-6.00)Kmp (Sh: FC, Culvert, R.Wall) | 227.54 | Lawngtlai Division | 27.10.17 | 30.10.19 | 100% | 216.35 | - | - | 100% | 216.35 | Completed | NIT
71 | Construction of Karlui to Damlui (6.00-8.800)Kmp (Sh: FC, Culvert, R.Wall) | 147.71 | Lawngtlai Division | 13.11.17 | 25.10.19 | 100% | 147.69 | - | - | 100% | 147.69 | Completed | NIT
72 | Construction of Bolisora to Chamdurtlang (0.00 - 2.00) Kmp (Sh: FC, Culvert. R.Wall) | 155.49 | Lawngtlai Division | 27.10.17 | 20.05.20 | 100% | 155.49 | - | - | 100% | 155.49 | Completed | NIT
73 | Construction of Bolisora to Chamdurtlang(2.00-5.00)Kmp (Sh: FC, Culvert, R.Wall) | 229.32 | Lawngtlai Division | 27.10.17 | 16.03.20 | 100% | 229.32 | - | - | 100% | 229.32 | Completed | NIT
74 | Construction of Bolisora to Chamdurtlang(5.00-9.00)Kmp (Sh: FC, Culvert, R.Wall) | 359.96 | Lawngtlai Division | 01.04.19 | 29.09.21 | 100% | 359.95 | - | - | 100% | 359.95 | Completed | NIT
75 | Construction of Bolisora to Chamdurtlang(9.00-11.650)Kmp (Sh: FC, Culvert, R.Wall) | 251.92 | Lawngtlai Division | 27.10.17 | 16.03.20 | 100% | 251.9 | - | - | 100% | 251.9 | Completed | NIT
76 | Construction of Ajasora to Longpuighat (0.00-10.900)Kmp (Sh: Const.of road using Flexible Pavement Technology) | 934 | Lawngtlai Division | 13.11.17 | 19.12.21 | 100% | 857.32 | - | - | 100% | 857.32 | Ongoing | NIT
77 | Construction of Jognasury - Karlui Road (0.000-12.100)Kmp (Sh: Formation Cutting, Culvert & R.Walls & Const.of of Road Using Flexible Pavement) | 888.27 | Lawngtlai Division | 13.12.18 | 30.09.22 | 100% | 760.65 |  | - | 100% | 760.65 | Completed | NIT
78 | Construction of Maniababsora-I to Maniababsora-II Road (0.000-1.520)Kmp (Sh: FC, Culvert & R.Wall & Const.of road using Panelled Concrete Technology) | 212.32 | Lawngtlai Division | 27.12.18 | 22.11.20 | 100% | 212.32 | - | - | 100% | 212.32 | Completed | NIT
79 | Construction of Boroituli to Jaruldubasora Road (0.000-2.100)Kmp (Sh: FC, Culvert & R.Wall & Const.of road using Panelled Concrete Technology) | 257.02 | Lawngtlai Division | 17.09.18 | 10.02.22 | 100% | 257 | - | - | 100% | 257 | Completed | NIT
80 | Construction of Boroituli to Jaruldubasora Road (2.000-3.700)Kmp (Sh: FC, Culvert & R.Wall & Const.of road using Panelled Concrete Technology) | 269.85 | Lawngtlai Division | 28.09.18 | 30.09.22 | 100% | 268.54 | - | - | 100% | 268.54 | Completed | NIT
81 | Construction of Vaseitlang to Lokhisury Road(0.00-9.560)Kmp (Sh: FC, Culvert, R.Wall & Const.of road using Panelled Concrete Technology) | 1366.7 | Lawngtlai Division | 28.09.18 | 30.09.22 | 58.06% | 822.15 | 9.98% | - | 68.04% | 822.15 | Ongoing | NIT
82 | Construction of Vathuampui to Tuisentlang Road(0.000-9.600)Kmp (Sh: FC, Culvert, R.Wall & Const.of Road Using panelled Concrete) | 910.99 | Lawngtlai Division | 03.01.18 | 30.09.22 | 73% | 910.99 |  | - | 73% | 910.99 | Ongoing | NIT
83 | Construction of Vathuampui to Chamdur P-I Road(0.000-1.720)Kmp (Sh: FC, Culvert, R.Wall & Const.of Road Using panelled Concrete) | 263.08 | Lawngtlai Division | 15.10.18 | 30.09.22 | 100% | 261.11 | - | - | 100% | 261.11 | Completed | NIT
84 | Construction of Vathuampui to Chamdurtlang (0.000-1.720)Kmp (Sh: FC, Culvert, R.Wall & Const.of Road Using panelled Concrete) | 274.17 | Lawngtlai Division | 13.12.18 | 30.09.22 | 69.2% | 180.75 | - | - | 69.2% | 180.75 | Ongoing | NIT
85 | Construction of Vathuampui to Chamdurtlang (2.000-3.800)Kmp (Sh: FC, Culvert, R.Wall & Const.of Road Using panelled Concrete) | 360.89 | Lawngtlai Division | 22.09.18 | 30.09.22 | 100% | 356.27 | - |  | 100% | 356.27 | Completed | NIT
86 | Construction of Chamdurtlang to Mualtlang Road(0.000-7.970)Kmp (Sh: FC, Culvert, R.Wall & Const.of Road Using panelled Concrete) | 1152.2 | Lawngtlai Division | 13.12.18 | 30.09.22 | 100% | 1089.09 | - | - | 100% | 1089.1 | Completed | NIT
87 | Construction of Parva II to Zochachhuah Road(0.000-29.720)Kmp (Sh: FC, Culvert, R.Wall & Const.of Road Using panelled Concrete) | 5432.38 | Lawngtlai Division | 05.04.19 | 30.09.23 | 100% | 4745.79 | - |  | 100% | 4745.79 | Ongoing | NIT
88 | Construction of Parva II to Bondukbanga Road(0.000-2.000)Kmp (Sh: FC, Culvert, R.Wall & Const.of Road Using Flexible Pavement) | 269.72 | Lawngtlai Division | 28.09.18 | 12.01.22 | 100% | 269.14 | - | - | 100% | 269.14 | Completed | NIT
89 | Construction of Parva II to Bondukbanga Road(2.000-4.120)Kmp (Sh: FC, Culvert, R.Wall & Const.of Road Using Flexible Pavement) | 294.1 | Lawngtlai Division | 13.12.18 | 31.12.22 | 100% | 259.1 |  | - | 100% | 259.1 | Ongoing | NIT
90 | Construction &Maintenance of Parva-II - Kamtuli Road (0.000-25.550)Kmp (Sh: FC, Culvert, R.Wall & Const.of Road Using panelled Concrete) | 4139.88 | Lawngtlai Division | 17.06.19 | 30.09.22 | 85.12% | 2148.95 | 2.31% |  | 87.43% | 2148.95 | Ongoing | NIT
91 | Construction & Maintenance of Vaseitlang to Maniababsora Road (0.000-13.500)Kmp (Sh: FC, Culvert, R.Wall & Const.of Road Using panelled Concrete) | 2361.15 | Lawngtlai Division | 14.06.19 | 30.04.22 | 100% | 2358.27 | - | - | 100% | 2358.27 | Completed | NIT
92 | Construction & Maintenance of Sedailui to Tuikhurlui Road (0.000-1.720)Kmp (Sh: FC, Culvert, R.Wall & Const.of Road Using panelled Concrete Techonology) | 204.33 | Lawngtlai Division | 17.06.19 | 08.05.22 | 92.06% | 159.96 | - | - | 92.06% | 159.96 | Ongoing | NIT
93 | Construction &Maintenance of M.Kawnpui to Vathuampui Road (0.000-20.000)Kmp (Sh: FC, Culvert, R.Wall & Const.of Road Using panelled Concrete Technology) | 1976.47 | Lawngtlai Division | 14.06.19 | 30.09.22 | 68% | 880.39 | 7.17% |  | 75.17% | 880.39 | Ongoing | NIT
94 | Construction &Maintenance of Sumsului Road to Jognasury (0.000-15.44)Kmp (Sh: Const.of Road Using panelled Concrete Technology) | 1278.38 | Lawngtlai Division | 14.06.19 | 30.09.22 | 81.36% | 1065.69 | - |  | 81.36% | 1065.69 | Ongoing | NIT
95 | Construction &Maintenance of Chawngte 'P' to Sumsului Road (0.000-4.570)Kmp (Sh: FC, Culvert, R.Wall & Const.of Road Using panelled Concrete Technology) | 313.29 | Lawngtlai Division | 01.07.19 | 31.03.22 | 100% | 302.97 |  |  | 100% | 302.97 | Completed | NIT
96 | Construction of Niawhtlang - Chakhang Road Package No.MZ0761(0.000-23.260Kmp) | 870.43 | Siaha Division | 14.10.23 | 14.03.24 |  |  | 2% |  | 2% |  | Material being collected | Item rate contract
97 | Construction of Tawngkolong - Lawngmasu Road (0.00 - 22.700) Kmp | 1289.738 | Siaha Division | 14.02.22 | 30.09.22 | 43.62% | 660.23 | 14.7% |  | 58.32% | 660.23 | Latest EOT upto March 2024 | Item rate contract
98 | Construction of Rawlbuk-Lungtian Road (0.000-14.000 Kmp) | 667.62 | Siaha Division | 8.05.20 | 30.09.22 | 100% | 611.67 |  |  | 100% | 611.67 | Work phy.completed | Item rate contract
99 | Construction of Niawhtlang-Chakhang Road Package No.MZ 0771(0.000-20.790Kmp) | 879.2 | Siaha Division | 15.10.23 | 15.03.24 |  |  | 0.87% |  | 0.87% |  | Material being collected | Item rate contract
100 | Construction of Phura - Lungpuk Road Group 'A' (0.000 - 4.000) Kmp | 159.98 | Siaha Division | 27.11.17 | Works phy. completed on 20.03.23 | 100% | 81.87 |  |  | 100% | 81.87 | Work phy.completed | Item rate contract
101 | Construction of Phura - Vahai Road (0.000 - 17.000) Kmp | 1563.92 | Siaha Division | 13.11.17 | 13.11.19 | 100% | 1409.46 |  |  | 100% | 1409.46 | Failure of Machineries hinder work progress | Item rate contract
102 | Construction and Maintenance of Tawngkolong-Lawngmasu road (0.00-28.940) Km | 122.016 | Siaha Division | 13.10.23 | 13.03.24 | 60% |  | 24% |  | 84% |  |  | Item rate contract
103 | Const.& Maintenance of Mualcheng-N.Vanlaiphai Road Group 'A' (0.000-8.000 Kmp) | 535.67 | Serchhip Division | 31.12.20 | 31.12.22 | 100% | 303.31 | - | - | 100% | 303.13 | Physically completed | Item rate contract
104 | Const.& Maintenance of Mualcheng-N.Vanlaiphai Road Group 'B' (8.000-16.000 Kmp) | 606.37 | Serchhip Division | 31.12.20 | 31.12.22 | 100% | 393.51 | - | - | 100% | 393.51 | Physically completed | Item rate contract
105 | Construction of Tuithumhnar to Lunghauka (0.00 - 5.00) Kmp (Sh: FC, Culvert, R.Wall) | 189.03 | Multi Modal Project Division | 27.10.17 | 31.07.19 | 100% | 189.03 | - | - | 100% | 189.03 | Completed on 05/07/2019
106 | Construction of Tuithumhnar to Lunghauka (5.00 - 7.00) Kmp (Sh: FC, Culvert, R.Wall) | 196.98 | Multi Modal Project Division | 27.10.17 | 31.03.21 | 100% | 193.28 | - | - | 100% | 193.28 | Completed on 30/03/2021
107 | Construction of Tuithumhnar to Lunghauka (7.00 - 10.00) Kmp (Sh: FC, Culvert, R.Wall) | 247.04 | Multi Modal Project Division | 27.10.17 | 16.07.20 | 100% | 247.04 | - | - | 100% | 247.04 | Completed on 20/07/2020
108 | Construction of Tuithumhnar to Lunghauka (10.00 - 13.00) Kmp (Sh: FC, Culvert, R.Wall) | 184.6 | Multi Modal Project Division | 27.10.17 | 29.06.20 | 100% | 184.6 | - | - | 100% | 184.6 | Completed on 29/06/2020
109 | Construction of Tuithumhnar to Lunghauka (13.00 - 15.480) Kmp (Sh: FC, Culvert, R.Wall) | 198.08 | Multi Modal Project Division | 27.10.17 | 16.07.20 | 100% | 198.08 | - | - | 100% | 198.08 | Completed on 26/06/2020
110 | Construction & Maintenance of Ngenpuitlng to Darnamtlang (0.00 - 4.00) Kmp (Sh: FC, Culvert, R.Wall) | 233.08 | Multi Modal Project Division | 27.10.17 | 31.01.20 | 100% | 193.78 | - | - | 100% | 193.78 | Physically completed on 01/05/2020
111 | Construction & Maintenance of Ngenpuitlng to Darnamtlang (4.00 - 6.20) Kmp (Sh: FC, Culvert, R.Wall) | 161.44 | Multi Modal Project Division | 27.10.17 | 31.08.21 | 100% | 224.53 | - | - | 100% | 224.53 | Completed on 30/08/2021
112 | Construction & Maintenance of Tuithumhnar to Hmawngbu (0.00 - 6.720) Kmp (Sh: Construction of road using Grove Concrete Pavement) | 442.51 | Multi Modal Project Division | 12.11.17 | 1.10.21 | 100% | 441.76 | - |  | 100% | 441.76 | Completed on 16/06/2021
113 | Construction of Sabualtlang to Hmawngbuchhuah Road (0.00 - 1.760) Kmp (Sh:Formation Cutting, Culvert & Retaining Walls & Construction of Road Using Flexible Pavement) | 244.22 | Multi Modal Project Division | 17.12.18 | 24.10.21 | 100% | 244.22 | - |  | 100% | 244.22 | Completed on 23/10/2021
114 | Construction & Maintenance of Nalkawn to Rulkual Road (0.000-16.000) Kmp Group A (Sh: Const.of Road using Cold Mix Technology | 1078.79 | Multi Modal Project Division | 04.01.21 | 04.01.23 | 100% | 1194.51 | - | - | 100% | 1194.51 | Completed on 29.9.22
115 | Construction & Maintenance of Nalkawn to Rulkual Road (16.000-32.000) Kmp Group B (Sh: Const.of Road using Cold Mix Technology | 1315.37 | Multi Modal Project Division | 10.02.20 | 30.09.22 | 17.51% | 476.63 | - | - | 17.51% | 476.63 | Balance work is being started after re-tendering
116 | Construction & Maintenance of Rawmibawk to Phalrang Road (0.000-10.200) Kmp (Sh: Const.of Road usinggroove concrete Technology | 759.92 | Multi Modal Project Division | 13.12.18 | 30.09.22 | 100% | 758 | - |  | 100% | 758 | Completed on 29.9.22
117 | Construction & Maintenance of Saiha to Rawmibawk Road (0.000-22.30) Kmp (Sh: Const.of Road using groove concrete Technology | 1941.19 | Multi Modal Project Division | 17.06.19 | 30.09.22 | 100% | 1938.8 |  |  | 100% | 1938.8 | Phy. Completed on 29.03.23

## SEDP
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding: SEDP | [8 empty] | Month : January 2024
Sl. no | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Const. of Approach Road to Aizawl College at Mualpui | 415 | Aizawl Road South Division | 26.07.21 | 26.04.22 | 73% | 300 | - | - | 73% | 300 | Work in progress | Item Rate Contract
2 | Re-Construction of Concrete Pavement on Approach Road to Mission Vengthlang Cemetry, L=150M | 8.51 | Aizawl Road South Division | [8 empty] | Works not yet started
3 | Construction of High Court Parking Building at MINECO | 1960 | Project Division-I | 2.7.20 | 29.8.24 | 75% | 1082.48 |  | 5.09 | 75% | 1087.57 |  | EPC
4 | Construction of Govt.Staff Quarter (Block-A) at DIET Complex | 439.2 | Project Division-I | 23.4.22 | 22.4.24 | 100% | 421.6 |  | 2.73 | 100% | 424.33 | Original works completed | EPC
5 | Construction of Rest House & Chowkider Quarter at PWD Complex Bilkhawthlir | 412.39 | Project Division-II | 15.12.20 | (O)15.6.22 (R)28.02.23 | 100% | 406.57 | - |  | 100% | 406.57 | Work physically Completed | Item rate
6 | Const.of MBSE New Building and renovation of existing main Building | 1000 | Project Division-III | 22.2.21 | 6.7.24 | 80% | 568.57 | 4% |  | 84% | 568.57 | Work in progress | PWD Form-8
7 | Improvement of Khanpui - Tualbung Road Phase-II | 2935.99 | Saitual Division | 25.03.18 | 15.6.22 | 83.61% | 2231.91 |  | 19.69 | 83.61% | 2251.6
8 | Strenthening of Saitual - Phullen Road (28.300Km)(Tuivawl-Phullen) (28.700-57.000) | 1259.71 | Saitual Division | 18.12.19 | 18.04.21 | 100% | 800.01 |  |  | 100% | 800.01 | Phy. Completed
9 | Strenthening of Saitual - Phullen Road (28.300Km)(Tuivawl-Phullen) (28.700-57.000) | 320 | Saitual Division | 08.02.21 | 18.04.21 | 100% | 319.99 |  |  | 100% | 319.99
10 | Curve Improvement on ATL Road at Chainage 20.100 Kmp | 10 | Hmuifang Division | 18.02.23 | 31.03.23 | 100% | 10 |  |  | 100% | 10 | Completed
11 | Resurfacing of PWD Staff Lodge Approach Road at Aibawk | 10 | Hmuifang Division | 18.02.23 | 31.03.23 | 100% | 10 |  |  | 100% | 10 | Completed
12 | Resurfacing of Aizawl-Thenzawl-Lunglei Road (30.00 Kmp - 51.00 Kmp) | 1271.17 | Hmuifang Division | 18.02.23 | 31.03.23 | 87% | 310.11 |  |  | 87% | 310.11 | Work in progress
13 | Bad patch repair of Aizawl-Thenzawl-Lunglei Road (83.00 Kmp-100.00 Kmp) | 50 | Hmuifang Division | 18.12.23 | 31.03.23 | 100% | 50 |  |  | 100% | 50 | Completed
14 | Re-Construction of Hume pipe wing wall culvert at Ch.20.650 Kmp on Damdiai - Sialsuk Road (Location:20.650 Kmp) | 4.45 | Hmuifang Division | 18.12.23 | 31.03.23 | 100% | 4.45 |  |  | 100% | 4.45 | Completed
15 | Re-Construction of Hume pipe wing wall culvert at Ch.5.350 Kmp on Lungsei Road (Location:5.350 Kmp) | 6.5 | Hmuifang Division | 18.12.23 | 31.03.23 | 100% | 6.5 |  |  | 100% | 6.5 | Completed
16 | Patch Repair of Main Road at Thenzawl | 25 | Hmuifang Division | 18.02.23 | 31.03.23 | 100% | 25 |  |  | 100% | 25 | Completed
17 | Patch repair of Dinthar Veng Internal road at Thenzawl | 7.5 | Hmuifang Division | 18.02.23 | 31.03.23 | 100% | 7.5 |  |  | 100% | 7.5 | Completed
18 | Patch repair of Horticulture College approach road at Thenzawl | 10 | Hmuifang Division | 18.02.23 | 31.03.23 | 100% | 10 |  |  | 100% | 10 | Completed
19 | Patch repair of Rawpuichhip-Buarpui Road 81.000-88.000 Kmp (Section : S.Khawlek to New Khawlek) | 30 | Hmuifang Division | 18.02.23 | 31.03.23 | 100% | 30 |  |  | 100% | 30 | Completed
20 | Curve Improvement on ATL Road at Chainage 17.700 Kmp | 10 | Hmuifang Division | 18.02.23 | 31.03.23 | 100% | 10 |  |  | 100% | 10 | Completed
21 | Resurfacing of Doctor's Quarter Approach Road at Sialsuk. (Section: 0.00 Kmp to 0.090 Kmp) | 9 | Hmuifang Division | 18.02.23 | 31.03.23 | 100% | 9 |  |  | 100% | 9 | Completed
22 | Patch repair and resurfacing of Hualngohmun Internal Roads | 20 | Hmuifang Division | 18.02.23 | 31.03.23 | 100% | 20 |  |  | 100% | 20 | Completed
23 | Patch repair of Kelsih Internal Roads | 10 | Hmuifang Division | 18.02.23 | 31.03.23 | 100% | 10 |  |  | 100% | 10 | Completed
24 | Patch repair of Approach Road to Tachhip | 10 | Hmuifang Division | 18.02.23 | 31.03.23 | 100% | 10 |  |  | 100% | 10 | Completed
25 | Patch repair of Muallungthu to Khumtung Road | 20 | Hmuifang Division | 18.02.23 | 31.03.23 | 100% | 20 |  |  | 100% | 20 | Completed
26 | Patch repair of Aizawl-Thenzawl-Lunglei Road (63.00-71.00 Kmp) | 35 | Hmuifang Division | 18.02.23 | 31.03.23 | 100% | 35 |  |  | 100% | 35 | Completed
27 | Curve Improvement at ATL Road at Chainage 17.700 Kmp (Additional) | 6 | Hmuifang Division | 18.02.23 | 31.03.24 | 100% | 6 |  |  | 100% | 6 | Completed

## SEDP 4 (hidden)
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding: SEDP | [8 empty] | Month : May 2022
Sl. no | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the Month |  | Overall cumulative achievement |  | Remarks
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
25 | Widening of Road infront of CE, PWD Building at Tuikhuahtlang | 46.5 | Aizawl Road South Division |  |  | 100% | 46.5
26 | Const. of Approach Road to Aizawl College at Mualpui | 415 | Aizawl Road South Division |  |  | 35% | 120.12
27 | Const. of Approach Road to T.Romana College from ITI to Mualpui Road | 464.9 | Aizawl Road South Division |  |  | 49% | 171.33
28 | Wideing of Curve near Zokhuma's House on Bethlehem Vengthlang to College Road | 38.5 | Aizawl Road South Division |  |  | 100% | 38.5
29 | Const.of Approach Road to Zopar Vaipuanpho | 50 |  |  |  | 100% | 50
30 | Improvement at 0.50 Kmp on Hridaikawn to Power Sub Station at Tlangnuam | 12.3 | Aizawl Road South Division |  |  | 100% | 12.3
31 | Concrete pavement from Kohhran Thianghlim Biak In to PHE Pump House road within Maubawk | 30.5 | Aizawl Road South Division |  |  | 100% | 30.5
32 | Const.of Composite Retaining Wall at Kawilun Republic Veng | 7 | Aizawl Road South Division |  |  | 100% | 7
33 | Re-Construcrion of Retaining Wall near T.Lalhmuntiama's house on Nursery to Mission Veng Road via Kawltheihuan | 2.19 | Aizawl Road South Division |  |  | 100% | 2.19
34 | Const.of Bridge on Chhinga Vengthar to Tuithiang Road | 586.36 | Aizawl Road South Division |  |  | 59% | 60
35 | Widening of Approach road with rigid pavement from Thlanmual to Dam veng at Tlangnuam | 55 | Aizawl Road South Division |  |  | 100% | -

## CSS
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding: CSS | [8 empty] | Month : January 2024
Sl. no | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Polytechnic at Lawngtlai (Const.of Administrative cum Academic Block) | 800 | Lunglei Building Project Division | 18.3.13 | 14.10.15 | 100% | 624.62 | - | - | 100% | 624.62 | Civil Work Completed & I/E Works not yet executed | Restricted
2 | Construction of Judicial Quarter at Lawngtlai Grade-I Qtr. | 110.58 | Lunglei Building Project Division | 8.6.20 | 7.12.21 | 100% | 82.67 |  |  | 100% | 82.67 | Civil Works completed I/E not yet done | Restricted Tender
3 | Construction of Judicial Quarter at Lawngtlai Type-I & II Qtr. | 138.67 | Lunglei Building Project Division | 22.6.20 | 30.08.23 (Revised) | 100% | 36.25 |  |  | 100% | 36.25 | -do- | Restricted Tender
4 | Const.of Administrative cum Academic Block for Polytechnic Thingsen Saiha | 501.08 | Lunglei Building Project Division | 15.03.16 | 11.7.17 | 60% | 103.76 | - | - | 60% | 103.76 | The contractor has stopped work due to non release of fund from Central Government | Restricted Tender
5 | Const.of Hostel building for Polytechnic at Thingsen saiha | 191.83 | Lunglei Building Project Division | 15.3.16 | 11.04.17 | 80% | 80.41 | - | - | 80% | 80.41 | The contractor has stopped work due to non release of fund from Central Government | Restricted Tender
6 | Construction of Staff Qtr Type I, II & III for Polytechnic at Thingsen Saiha | 77.1 | Lunglei Building Project Division | 06.10.15 | 20.4.17 | 100% for civil works | 61.04 |  | - | 100% for civil works | 61.04 | The contractor has stopped work due to non release of fund from Central Government | Restricted Tender
7 | Const.of Type-IV Qtr for Polytechnic at Thingsen Saiha | 29.99 | Lunglei Building Project Division | 15.03.16 | 11.01.17 | 76.5% | 24.79 | - | - | 76.5% | 24.79 | The contractor has stopped work due to non release of fund from Central Government | Restricted
8 | Construction of District Court Building at Saiha. | 1803.39 | Lunglei Building Project Division | 10.9.18 | 31.10.23 (Revised) | 100% | 1803.395 |  |  | 100% | 1803.395 | Works completed on dt.28.4.23 and handover in process | Restricted Tender
9 | Construction of Security Wall at District Jail Siaha | 100 | Lunglei Building Project Division | 10.3.23 | 19.12.23 | 100% | 40.05 |  | 53.38 | 100% | 93.43 | Civil works completed | Restricted Tender
10 | Construction of fast truck Court at Kolasib | 1799.85 | Project Division II | 20.09.22 | 20.09.24 | 45% | 237.47 | 2% | - | 47% | 237.47 | Work in progress | Item Rate
11 | Const.of Tourist Logde at Champhai | 270 | Project Division-III | 09.12.10 | 30.11.20 | 100% | 300 | - | - | 100% | 300 | Taken over by the Deptt.on Dt.3.8.2021 LOC amounting to Rs.30.00 lakh submitted for clearing liability.Hence, release of LOC awaited for financial closure.
12 | Const.of Polytechnic at Chhiahtlang i) Approach Road | 800 | Project Division-III | 3.3.16 | 2.8.16 | 100% | 103.67 | - | - | 100% | 103.67 | Estimate based on SOR 2019 submitted as per written instruction of the client department. Waiting for approval.
ii) Administrative & Academic Block iii) Hostel Block iv) Staff Quarters
13 | Construction of General Nursing Midwifery Hostel at Champhai | 250 | Project Division-III | 13.07.22 | 13.07.24 | 87% | 150.51 | 1% |  | 88% | 150.51 | Work in progress | PWD Form-8
14 | Construction of Hostel for S.T Girls at Champhai | 462.75 | Project Division-III | 18.9.23 | 28.9.25 | 11% | 9.77 | 6% |  | 17% | 9.77 | Work in progress | PWD Form-8
15 | 10-Bedded Intergrated AYUSH Hospital at Keifang, Saitual District | 750 | Project Division-III | 13.10.23 | 13.10.25 | 0.5% |  |  |  | 0.5% |  | Full site clearance completed. Redesign of building and layout is under preparation as suggested by Client Dept.as the DPR was not for the new site | PWD Form-8
16 | Renovation of Mizram Secretariat Building at MINECO | 200 | Aizawl Building Division | 13.11.23 | 31.03.24 | 12% | 12.69 | 28% | 65.08 | 40% | 77.77 |  | Departmental

## MoRTH
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : NH(O) - MoRTH | [9 empty] | Month : January 2024
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummutive Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Steel Arch (Semi Through) Bridge with concrete Deck 90m Arch Span over River Tlawng at Km 5.200 on NH-44A In the State of Mizoram of EPC Mode (NHO) | 4244 | NHD-I | 30.01.21 | 21.10.23 | 75.5% | 2253.82 | 1.25% | 90.06 | 76.75% | 2343.88 |  | EPC Mode
2 | Ordinary Repair (DPP) for short term maintenance from Km 0.00 to Km 42.80 and from Km 60.30 to km 130.00 on NH-150 in the state of Mizoram | 418 | NHD-II | 05.11.21 | 02.02.22 | 100% | 327.67 | - | - | 100% | 327.67 |  | Item Rate
3 | Construction of 2 laning with paved shoulder flexible pavement from Km 42.80 to Km 60.30 of NH-150 road during 2016-17 within Mizoram State under NH(O) Scheme. (Job No. & Dtae of Sac Original/Revised : 150/MZ/2016-17/107) | 20594.82 | NHD-II | 29.11.17 | 22.05.21 | 100% | 13681.44 | - | - | 100% | 13681.44 | Phy. Completed | EPC Mode
4 | Reconstruction of single pavement from Km 130.00 to Km 140.00 on NH-150 in the State of Mizoram on EPC Mode (Job No.150/MZ/2019-20.119) | 3440.95 | NHD-II | 23.11.20 | 26.05.23 | 100% | 2441.16 | - | - | 100% | 2441.16 | Work under Defect Liability period | EPC Mode
5 | Consultancy Services for Project Management including prparation of Feasibility Study/Detailed {roject report fro laning with Paved Shoulders of stretches from Km 0/00 to Km 42/80 and from Km 60/00 to Km 140/00 on NH-150 NH (O) Package No. DPR/MZ/NER/2015/13 | 166.04 | NHD-II | 24.06.17 | 20.05.18 | 10% | 16.6 | 60% | - | 70% | 16.6 |  | MoRTH
6 | Periodical Renewal of NH-54 in the state of Mizoram under ARP for the year 2019-2020 between Km 118/00-133/00 Km (15.00Km) | 1477 | NHD-III | 20.04.21 | 20.04.22 1st Extension of Time = 96 day as (19.4.22=14.6.22) | 100% | 1110.48 |  |  | 100% | 1110.48 | Completed | EPC
7 | Strengthening of Km 10.00 to Km 33.00 (Length 23.00 Km) on NH-306A including Strengthening & Construction of Retaining Walls and Culverts and Strenthening of 3 Nos.of Bailey Bridges in the State of Mizoram | 6523 | NHD-III | 07.02.22 | 07.08.23 | 100% | 2727.53 |  |  | 100% | 2727.53 | Completed | EPC
8 | Strengthening/Construction/Widening to 2-lane from km 89/00 to km 105/00 of NH-154 (New NH-6) under NH Division III in the state of Mizoram for the year 2022-23 (Length=16Km) | 8681 | NHD-III | 04.09.23 | 04.03.25 | - | - | 0.04% | - | 0.04% | - |  | EPC

## Article 275
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : Article 275(1) of the Constitution | [9 empty] | Month : January 2024
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummutive Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Tribal Hostel at Suangpuilawn, Mizoram | 320 | Project Division-IV | 12.08.23 | 12.08.25 | 4.13% |  | 3.58% |  | 7.71% |  | Work in progress. | Item Rate
2 | Construction of Multipurpose Community Hall at Darlawn, Mizoram | 720 | Project Division-IV | 12.08.23 | 12.08.25 | 7.66% |  | 0.31% |  | 7.97% |  | Work in progress. | Item Rate

## ECRP-II
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : ECRP-II (Emergency Covid Response Package-II) | [9 empty] | Month : January 2024
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummutive Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of 50 Bedded critical care block at Champhai District Hospital Mizoram | 1346.4 | Project Division-III | 4.8.23 | 4.2.26 | 10% | 67.46 | 5% |  | 15% | 67.46 | Work in progress | PWD Form-8

## MAP
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding: Maintenance Action Plan | [8 empty] | Month : January 2024
Sl. no | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the Month |  | Overall cumulative achievement |  | Remarks | Mode of Contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Patch Repair and Full Resurfacing on Southern Gate of Raj Bhavan to E-in-C Office, Tuikhuahtlang | 38 | Aizawl Road South Division | 04.09.23 | 4.10.23 | 100% | 38 |  |  | 100% | 38 | Completed | Dept
2 | Patch Repair and Seal Coat on Kulikawn to Mission Veng Bazar | 10 | Aizawl Road South Division | 04.07.23 | 31.07.23 | 100% | 10 |  |  | 100% | 10 | Completed | Dept
3 | Junction Improvement with seal coat of road from YMA Hall to Liamduak at ITI Veng | 3 | Aizawl Road South Division | 04.07.23 | 20.07.23 | 100% | 3 |  |  | 100% | 3 | Completed | Dept
4 | Patch Repair and Resurfacing of Road from Pi Lalchawii (L) House to K.Lalramhmachhuana House at Bethlehem Vengthlang | 7 | Aizawl Road South Division | 12.09.23 | 29.09.23 | 100% | 7 |  |  | 100% | 7 | Completed | Dept
5 | Patch Repair of Upper Republic Junction to Governor Gate | 1.5 | Aizawl Road South Division | 03.07.23 | 14.07.23 | 100% | 1.5 |  |  | 100% | 1.5 | Completed | Dept
6 | Seal Coating of Approach Road & Courtyard of MLA Hostel at Tuikhuahtlang | 1.76 | Aizawl Road South Division | 10.5.23 | 16.5.23 | 100% | 1.76 |  |  | 100% | 1.76 | Completed | Dept
7 | Estimate for Patch Repair of Approach Road to Reiek Tourist Resort | 5 | Aizawl Road South Division | 25.08.23 | 16.09.23 | 100% | 5 |  |  | 100% | 5 | Completed | Dept
8 | Patch Repair and Seal Coating of Aizawl-Reiek-W.Lungdar Road 0.000-6.000 Kmp | 18 | Aizawl Road South Division | 23.08.23 | 17.9.23 | 100% | 18 |  |  | 100% | 18 | Completed | Dept
9 | Patch Repair and Seal Coating of MHNL Section-III | 5 | Aizawl Road South Division | 06.10.23 | 30.10.23 | 100% | 5 |  |  | 100% | 5 | Completed | Dept
10 | Patch Repair and Seal Coating of Sikulpuikawn to City Hospital Road | 4 | Aizawl Road South Division | 06.10.23 | 30.10.23 | 100% | 4 |  |  | 100% | 4 | Completed | Dept
11 | Patch Repair and Seal Coating of Bungkawn YMA Road | 3 | Aizawl Road South Division | 06.10.23 | 23.10.23 | 100% | 3 |  |  | 100% | 3 | Completed | Dept
12 | Patch Repair and Seal Coating of T.Sangkuna Road at Dinthar Tlang Veng | 6 | Aizawl Road South Division | 06.10.23 | 30.10.23 | 100% | 6 |  |  | 100% | 6 | Completed | Dept
13 | Patch Repair and Seal Coating of Sub-way below Vanapa Hall | 2 | Aizawl Road South Division | 10.4.23 | 20.4.23 | 100% | 2 |  |  | 100% | 2 | Completed | Dept
14 | Patch Repair and Seal Coating of Lower Dinthar to Tuikual (Aichhinga Road) | 5 | Aizawl Road South Division | 23.10.23 | 14.11.23 | 100% | 5 |  |  | 100% | 5 | Completed | Dept
15 | Extension and repair of Hume Pipe Culvert on Tlangnuam CP Road near Tlangnuam Vengthar Presbyterian Church | 6 | Aizawl Road South Division | 13.7.23 | 29.09.23 | 100% | 6 |  |  | 100% | 6 | Completed | Dept
16 | Patch Repair and Resurfacing of Pika Road at Kulikawn | 5 | Aizawl Road South Division | 03.08.23 | 17.08.23 | 100% | 5 |  |  | 100% | 5 | Completed | Dept
17 | Patch Repair and Resurfacing of Kulikawn to Saikhamakawn via Hridaikawn (CP Road) Road (Section: 1.000-1.874 Km) | 18 | Aizawl Road South Division | 4.09.23 | 28.09.23 | 70% | 18 | 30% |  | 100% | 18 | Completed | Dept
18 | Reconstruction of Culvert at CP Road, Tlangnuam | 5.6 | Aizawl Road South Division | 3.7.23 | 28.09.23 | 100% | 5.6 |  |  | 100% | 5.6 | Completed | Dept
19 | Resurfacing of approach road to Zobawm at Kulikawn | 5 | Aizawl Road South Division | 4.10.23 | 16.10.23 | 100% | 5 |  |  | 100% | 5 | Completed | Dept
20 | Resurfacing of Hridaikawn to Power Sub-Station Road at Tlangnuam | 15 | Aizawl Road South Division | 25.4.23 | 6.6.23 | 100% | 15 |  |  | 100% | 15 | Completed | Dept
21 | Construction of CD works with cover between Pu Ngura Sailo and Pu Remruata's House on Saikhamakawn - Tlangnuam Road | 3.5 | Aizawl Road South Division |  |  |  |  | 10% |  | 10% | 3.5 | On going | Dept
22 | SUB DIVISION-I Resurfacing of Sihpui to Ramhlun Vengthar Bus Turining Point at Ch: 1.357-2.172 Km | 30 | Aizawl Road North Division | 12.10.23 | 30.10.23 | 100% | 30 |  |  | 100% | 30 | Completed | Dept
23 | Resurfacing of Armed Veng South to Bethlehem Vengthlang Road at Ch:0.000-0.677 Km | 11.8 | Aizawl Road North Division |  |  | 100% | 11.8 |  |  | 100% | 11.8 | Completed | Dept
24 | Resurfacing of Ramhlun Sports Complex Road at Ch.0.000-0.326Km | 15.8 | Aizawl Road North Division |  |  | 100% | 15.8 |  |  | 100% | 15.8 | Completed | Dept
25 | SUB DIVISION-II Re-surfacing of DC Workshop to NH-54 via Chaltlang Lily Veng | 20 | Aizawl Road North Division | 29.5.23 | 31.5.23 | 100% | 20 |  |  | 100% | 20 | Completed | Depart mental
26 | Patch Repair of Leitan -Agape (Lower & Upper) Ring Road | 7 | Aizawl Road North Division | 17.7.23 | 19.7.23 | 100% | 7 |  |  | 100% | 7 | Completed | Depart mental
27 | Patch Repair & Seal Coating of Pema Road at Ramhlun North | 1.5 | Aizawl Road North Division | 17.7.23 | 18.7.23 | 100% | 1.5 |  |  | 100% | 1.5 | Completed | Depart mental
28 | Approach Road to Durtlang Cemetery | 12 | Aizawl Road North Division | 5.6.23 | 8.6.23 | 100% | 12 |  |  | 100% | 12 | Completed | Depart mental
29 | SUB DIVISION-III Re-surfacing of Lower Kanan to Dawrpui Vengthar | 11.43 | Aizawl Road North Division | 17.7.23 | 15.8.23 | 100% | 10.95 |  | 0.48 | 100% | 11.43 | Completed | Depart mental
30 | Re-surfacing of Balance portion of 7th Day Hospital to Ebenezer | 10.72 | Aizawl Road North Division | 24.7.23 | 22.8.23 | 100% | 10.56 |  | 0.16 | 100% | 10.72 | Completed | Depart mental
31 | Re-surfacing of Approach Road to AICS Shekina Hills Tanhril | 15.2 | Aizawl Road North Division | 17.3.23 | 15.8.23 | 100% | 10.6 |  | 4.6 | 100% | 15.2 | Completed | Depart mental
32 | Resurfacing of road from Pu Rfa's Kawn to Primary School including Construction of Rigid Pavement (PCC) at Tanhril | 25.05 | Aizawl Road North Division | 17.3.23 | 16.8.23 | 100% | 17.4 |  | 7.65 | 100% | 25.05 | Completed | Depart mental
33 | Patch repair of Chhangurkawn to High Court road | 40 | Aizawl Road North Division | 17.3.23 | 16.8.23 | 100% | 38.3 |  | 1.7 | 100% | 40 | Completed | Depart mental
34 | Re-Surfacing of Zonuam Police Outpost to Ainawn | 15 | Aizawl Road North Division | 17.3.23 | 16.8.23 | 100% | 14.36 |  | 0.64 | 100% | 15 | Completed | Depart mental
35 | Strengthening & Resurfacing of Zobawk Dispensary Approach Road (NH 54A Zobawk - PHC Zobawk) (Balance Portion) | 5.02 | Lunglei Road Division-II |  |  | 10% |  | 5% |  | 15% |  | Material being collected
36 | Re-Surfacing of Approach Road to Laveng, Haulawng (0.00-1.400Kmp) | 12.92 | Lunglei Road Division-II |  |  | 13% |  | 2% |  | 15% |  | Material being collected
37 | Extension of Wing Wall on Haulawng Bualpui 'V' upto Chhipphir Road (Chainage : 10.000 & 10.600 Kmp) | 7.81 | Lunglei Road Division-II |  |  | 100% |  |  |  | 100% |  | Completed
38 | Re-Surfacing of Approach Road from BRTF Canteen to Helipad upto ICDS Office at Hnahthial | 8.31 | Lunglei Road Division-II |  |  | 14% |  | 1% |  | 15% |  | Material being collected
39 | SMBT of Approach Road from Pu Dodina's House to Pu Thangkima's House at Hnahthial | 13.89 | Lunglei Road Division-II |  |  | 13% |  | 3% |  | 16% |  | Material being collected
40 | Resurfacing of Approach Road from Pu Sangkunga House to Pu Lalsiama House Peniel Veng Hnahthial | 6.25 | Lunglei Road Division-II |  |  | 15% |  | 2% |  | 17% |  | Material being collected
41 | Repair of Thingsai Shortcut Road | 5.61 | Lunglei Road Division-II |  |  | 100% |  |  |  | 100% |  | Completed
42 | Re-Surfacing of Approach Road from Pu F.Zosangliana's House to Pu F.Lalduhawma House via Model Veng, Hnahthial | 17.88 | Lunglei Road Division-II |  |  | 15% |  | 2% |  | 17% |  | Material being collected
43 | PWD SDO Quarter Approach Road at Hnahthial (IB Main Road to PWD SDO Qtr) | 3.31 | Lunglei Road Division-II |  |  | 14% |  | 3% |  | 17% |  | Material being collected
44 | Patch repair & Pot hole filling, Resurfacing & Seal coating of Approach road to ITI Complex (Nursing school approach road to ITI complex) | 5.05 | Lunglei Road Division-I | [8 empty] | Material being collected
45 | Patch repair & Pot hole filling, Resurfacing & Seal coating of Sertlangpui Internal Road (Sertlangpui main road-Sertlangpui PWD, IB) | 5.52 | Lunglei Road Division-I | [8 empty] | Material being collected
46 | Patch repair & Pot hole filling, Resurfacing & Seal coating of Approach road to Vety Farm, Farmveng) | 11.86 | Lunglei Road Division-I | [8 empty] | Material being collected
47 | Patch repair & Pot hole filling, Resurfacing & Seal coating off Bazar veng-Tlabung via LDSC Ground (Mandir peng to Thuamluia Mual Upper Road) | 11.35 | Lunglei Road Division-I | [8 empty] | Material being collected
48 | Seal coating of Dawrzawl to Tawngtaina Tlang, Theiriat | 3.81 | Lunglei Road Division-I | [8 empty] | Material being collected
49 | Patch repair & Pot hole filling, Resurfacing & Seal coating of haka to District road via Vety Dispensary | 10.9 | Lunglei Road Division-I | [8 empty] | Material being collected
50 | Patch repair & Resurfacing of Ramzotlang to Diet Road | 19.99 | Lunglei Road Division-I | [8 empty] | Material being collected
51 | Patch repair & Seal coating of Zohnuai approach road upto Community Hall (0.500-1.750 Kmp) | 9.8 | Lunglei Road Division-I | [8 empty] | Material being collected
52 | Patch repair & Seal coating of Mualthuam approach road | 11.72 | Lunglei Road Division-I | [8 empty] | Material being collected
53 | Patch repair & Pot hole filling, Resurfacing & Seal coating of Bunghmun Internal Road (MRB Junction to BDO Complex) | 6.45 | Lunglei Road Division-I | [8 empty] | Material being collected
54 | Patch repair & Pot hole filling, Resurfacing & Seal coating of Bunghmun Internal Road (Approach Road to BCM Bunghmun) | 3.55 | Lunglei Road Division-I | [8 empty] | Material being collected
55 | Resurfacing of Approach road to Assistant Commisioner of Excise from NH, Kolasib | 10 | Kolasib Division
56 | Patch Repair of road from Irrigation Complex to NH-54 at Kolasib | 5 | Kolasib Division | 10.01.24 |  |  |  | 100% |  | 100% |  | Completed
57 | Resurfacing of Approach road to Project Sub,Station via YMA Hall, Kolasib | 5 | Kolasib Division | 10.01.24 |  |  |  | 100% |  | 100% |  | Completed
58 | Resurfacing from BSNL Office to Presbyterian Church, Project Veng, Kolasib | 4 | Kolasib Division | 10.01.24 |  |  |  | 100% |  | 100% |  | Completed
59 | Resurfacing road from Hmarveng Presbyterian Centenary Hall to Hmar veng Kawnghnuai, Hmar Veng, Kolasib | 4 | Kolasib Division | 10.01.24 |  |  |  | 100% |  | 100% |  | Completed
60 | Resurfacing of CP Road to NH-54 via Forest Tlang, New Diakkawn, Kolasib | 5 | Kolasib Division
61 | Resurfacing from Tumpui Field to Tumpui Kawnghnuai at Tumpui, Kolasib | 3 | Kolasib Division | 10.01.24 |  |  |  | 100% |  | 100% |  | Completed
62 | Resurfacing of Approach road to Challui Veng from NH-54 Kolasib | 5 | Kolasib Division
63 | Construction of R/Wall @0.600Kmp on Rengtekawn to 0 point | 2.5 | Kolasib Division | 27.10.23 |  | 100% |  |  | 2.5 | 100% | 2.5 | Completed
64 | Construction of R/Wall @1.800Kmp on Rengtekawn to 0 point | 6.5 | Kolasib Division | 27.10.23 |  | 100% |  |  | 6.5 | 100% | 6.5 | Completed
65 | Patch Repair & Seal Coat of Dawr Veng Square to Lenhnuai ROad, Bilkhawthlir | 7.05 | Kolasib Division |  |  |  |  | 100% | 7.05 | 100% | 7.05 | Completed
66 | Resurfacing of of Hospital to Mualvum church road, Mualvum | 16.5 | Kolasib Division |  |  |  |  | 100% | 16.5 | 100% | 16.5 | Completed
67 | Patch Repair & Pot Holes filling, Resurfacing Seal Coat of Approach Road to Police Complex (Dawr Veng Police Station Bilkhawthlir)of Dawr Veng Square to Lenhnuai ROad, Bilkhawthlir | 4.24 | Kolasib Division |  |  |  |  | 100% | 4.24 | 100% | 4.24 | Completed
68 | Patch Repair & Pot Holes filling, Resurfacing Seal Coat of Kual Mawi Community Hall to NH-54 via BDO Quarter Approach road | 5.21 | Kolasib Division |  |  |  |  | 100% | 5.21 | 100% | 5.21 | Completed

## PM DeVINE
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : PM-DeVINE | [9 empty] | Month : January 2024
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummutive Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of Contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Bamboo Link Road from Lengpui to Saiphal Bamboo Plantation (41 Km) under PM-DeVINE | 4941 | NHD-I | 21.07.23 | 19.01.25 | 10% |  | 5% |  | 15% |  | Work in progress | EPC Mode
2 | Construction of Bamboo Link Road from Tuirial Airfield to North Chaltlang (18Km) under PM-DevINE | 2445.92 | Aizawl Road North Division | 1.8.23 | 31.1.25 |  |  | 11.11% |  | 11.11% |  | In progress | Item Rate

## ICMR
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : DIPHR (ICMR) | [9 empty] | Month : January 2024
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummutive Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of Contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Model Rural Health Research Units at Lungtian Ram, Aibawk | 207.5 | Project Division-II | 21.09.23 | 21.03.25 | 10% |  | 5% |  | 15% |  | Workin progress | Item Rate

## Ministry
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : Ministry of Tribal Affairs | [9 empty] | Month : January 2024
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummutive Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of Contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Auditorium at Pukpui Lunglei | 523 | Lunglei Building Project Division | 16.9.23 | 16.01.25 | 5% |  |  |  | 5% |  | Work stopped due to objection of site from Education Dept. Relocation of Site for Construction is beung awaited from Client Dept. | Retsricted Tender

## Interstate
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : Interstate Connectivity | [9 empty] | Month : January 2024
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummutive Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of Contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Road construction of Mizoram-Assam Interstate Border (Sh: Hlimen to Serlui Tuikhuah) Group-I | [11 empty] | Restricted Tender
| 1) Excavation in soil by Mechanical means | 68.43 | Kolasib Division | 10.08.23 | 31.01.24 | 100% | 68.43 |  |  | 100% | 68.43 | Completed
| 2) Excavation in Ordinary Rock by Mechanical means | 50.29 | Kolasib Division | 10.08.23 | 31.01.24 | 100% | 50.2 |  |  | 100% | 50.2
2 | Road construction of Mizoram-Assam Interstate Border (Sh: New Builum to Chemtlang Zau) Grou-2 (Phse-I & III) | [11 empty] | Restricted Tender
| 1) Excavation of soil by Mechanical means | 54.59 | Kolasib Division | 10.08.23 | 31.01.24 | 100% | 54.59 |  |  | 100% | 54.59 | Completed
| 5) Excavation in Ordinary Rock by Mechanical means | 62.36 | Kolasib Division | 10.08.23 | 31.01.24 | 100% | 45.69 |  |  | 100% | 45.69

## NLCPR
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : NLCPR | [9 empty] | Month : January 2024
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Community Hall at Various places in Mizoram (Sh: Construction of Community Hall at Saitual, Thingsulthliah, Maite, Tualbung, Lungpher, Buhban, Lenchim, Chawrtui and Puilo) | 206.49 | Project Division-III | 22.2.12 | 30.11.19 | 100% | 186.01 | - | - | 100% | 186.01 | Completed and balance fund of Rs.20.48 (Rs.16.35 lakhs NLCPR + Rs.4.13 lakhs SMS) a waited for clearing liabilities

## NEDP
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : NEDP | [9 empty] | Month: January 2024
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Officers & Staff Quarter Type-IV, 2 Units and Type-III 4 Units for Taxation Department Lunglei | 330 | Lunglei Building Project Division | 3.7.20 | 30.10.23 (Revised) | 100% | 161.35 |  |  | 100% | 161.35 | Civil Works completed and I/E Fund not yet done | Restricted Tender
2 | Construction of DC Bangalow Type-VI at Saiha | 110.9 | Lunglei Building Division | 26.11.08 | 23.05.24 (Revised) | 81% | 92.01 | 0.3% | - | 81.3% | 92.01 | Allocation of Balanced Fund of Rs.205.99 lakh is being awaited for completion of the whole projects i.e DC Office, DC Bungalow etc. Revised estimate resubmitted for approval | Restricted Tender
3 | Construction of DC Office Building at Saiha | 610.11 | Lunglei Building Division | 31.10.18 | 31.10.20 Revised 28.11.23 | 86.9% | 414.49 |  |  | 86.9% | 414.49 |  | Restricted Tender
3 | Improvement of Buarpui - Bunghmun - via Thenhlum Road (65.000-79.00) Kmp during 2016-2017 | 1000 | Lunglei Road Division-I | 17.5.17 | 31.3.23 | 74% | 870.29 | - | - | 74% | 870.29 | Contract work is terminated and joint inspection with contractors has already been done on balance work for which estimate has already being submitted to the competent authority for futher necessary action
4 | Resurfacing of MRB Junction to Mini Sport Complex | 5.93 | Lunglei Road Division-I |  |  | 100% | 5.93 |  |  | 100% | 5.93 | Completed
5 | Resurfacing of MRB Junction to Falkawn Bunghmun | 11.87 | Lunglei Road Division-I |  |  | 100% | 11.87 |  |  | 100% | 11.87 | Completed
6 | Retaining Wall of PWD Complex Bunghmun | 7.42 | Lunglei Road Division-I |  |  | 100% | 7.42 |  |  | 100% | 7.42 | Completed
7 | Strengthening of Pavement from Kikawn to AOC at Selected stretches | 44.46 | Lunglei Road Division-I |  |  | 100% | 44.46 |  |  | 100% | 44.46 | Completed
8 | Serkawn Hospital to DIET, Melte (Christian Hospital Serkawn to DIET, Lunglei (0.00 - 1.590Kmp) | 24.72 | Lunglei Road Division-I |  |  | 100% | 24.72 |  |  | 100% | 24.72 | Completed
9 | Patch Repair & Resurfacinf of YPC Hall Serkawn to Chawngbawla Point Zotlang (0.00-1.590Kmp) | 27.76 | Lunglei Road Division-I |  |  | 100% | 27.76 |  |  | 100% | 27.76 | Completed
10 | Patch Repair & Resurfacinf of Zohnuai approach road (0.00-0.50Kmp) | 11.01 | Lunglei Road Division-I |  |  | 100% | 11.01 |  |  | 100% | 11.01 | Completed
11 | Centenary Road Serkawn (Serkawn Christian Hospital, Serkawn Pastor Quarters (0.00-0.540) | 10.93 | Lunglei Road Division-I |  | 2023-11-01 |  | 9.59 | 100% |  | 100% | 9.59 | Not yet started/Material Procured
12 | AOC to Kikawn | 43.25 | Lunglei Road Division-I |  |  | 100% | 43.25 |  |  | 100% | 43.25 | Completed
13 | Construction of Retaining Wall on ATL Road to Kawmzawl Helipad Road Pukpui (At Ch=400.00m) | 3.08 | Lunglei Road Division-I |  |  | 100% | 3.08 |  |  | 100% | 3.08 | Completed
14 | Improvement of Drainage System from Kikawn to AOC (Culverts & Cross drainage) | 30.29 | Lunglei Road Division-I |  |  | 90% | 30.92 |  |  | 90% | 30.92 | Not yet Completed
15 | Approach Road to Kendriya School at Ramthar Veng (Nursing School Approach Road Kendriya School Ramthar Veng) | 34.21 | Lunglei Road Division-I |  | 2024-03-01 | 24.51% | 5.42 |  |  | 24.51% | 5.42 | Only widening completed WBM ongoing
16 | JB Press to Sobji Bazar (0.000-0.307 Kmp) | 5.41 | Lunglei Road Division-I |  |  | 100% | 5.41 |  |  | 100% | 5.41 | Completed
17 | AOC to District Road (AOC Ramthar District Road) | 5.95 | Lunglei Road Division-I |  |  | 100% | 5.95 |  |  | 100% | 5.95 | Completed
18 | MAO Complex Internal Road (Caommandant Bungalow to Thangte Peng) | 19.62 | Lunglei Road Division-I |  |  | 100% | 19.62 |  |  | 100% | 19.62 | Completed
19 | R.Zosanga Road at Lunglawn (NH-54A Z.Rosanga's House) | 2.96 | Lunglei Road Division-I |  |  | 100% | 2.96 |  |  | 100% | 2.96 | Completed
20 | NH 54A to Lunglawn Hmunhlui Tlang via Pu H.Lalzarliana's House (NG 54A Main Road PC Thlanmual's House) | 2.11 | Lunglei Road Division-I |  |  | 100% | 2.11 |  |  | 100% | 2.11 | Completed
21 | Parallel Road from Pu Lalpara's House to Prebyterian Church (Part 1) | 13.35 | Lunglei Road Division-I |  |  | 100% | 13.35 |  |  | 100% | 13.35 | Completed
22 | Approach Road to LDSC Ground No II from District Road (District Road LDSC Ground No II) | 4.41 | Lunglei Road Division-I |  |  | 100% | 4.41 |  |  | 100% | 4.41 | Completed
23 | Salem Internal Road (NH 54A to District Road) | 10.2 | Lunglei Road Division-I |  |  | 100% | 10.2 |  |  | 100% | 10.2 | Completed
24 | Falkawn to District Road (Falkawn District Road) | 9.26 | Lunglei Road Division-I |  |  | 100% | 9.26 |  |  | 100% | 9.26 | Only Pothole repair Completed
25 | Ramthar Veng Baptist Church Ring Road (AOC Ramthar Mazara's Spare Parts) | 4.36 | Lunglei Road Division-I |  |  | 100% | 4.36 |  |  | 100% | 4.36 | Completed
26 | Resurfacing of Approach Road DCs Office from MST Bus Station (MST Bus Station DC Office) | 12.44 | Lunglei Road Division-I |  |  | 100% | 12.44 |  |  | 100% | 12.44 | Completed
27 | Reusrfacing of Mizoram Rural Bank to DC Office via LAD Office (Mizoram Rural Bank DC Office) | 13.35 | Lunglei Road Division-I |  |  | 100% | 13.35 |  |  | 100% | 13.35 | Completed
28 | Resurfacing of District Road | 113.74 | Lunglei Road Division-I |  |  | 100% | 113.74 |  |  | 100% | 113.74 | Completed
29 | Resurfacing of LP Thangzika's Shop to Forest Check Gate) | 53.19 | Lunglei Road Division-I |  |  |  | 8.34 |  |  |  | 8.34 | Only Pothole repair completed
30 | Resuirfacing of Parallel Road from Pu Lalpara's House to BCM Kikawn Biak In (Part 2) | 97.86 | Lunglei Road Division-I |  |  | 100% | 97.86 |  |  | 100% | 97.86 | Completed
31 | Resurfacing of Rahsi Veng to Tlabung Road via Sazaikawn (Forest Check Gate to Tlabung Kawng) | 12.83 | Lunglei Road Division-I |  |  | 100% | 12.83 |  |  | 100% | 12.83 | Completed
32 | Resurfacing of Rahsi Veng to Tlabung Road via Sazaikawn (Forest Check Gate to Tlabung Kawng) | 22.07 | Lunglei Road Division-I |  |  |  | 13.77 |  |  |  | 13.77 | Only Pothole repair Completed
33 | SE PWD Residence Approach Road (DC's Office SE Office) | 2.1 | Lunglei Road Division-I |  |  | 100% | 2.1 |  |  | 100% | 2.1 | Completed
34 | DC Residence from SE PWD Qtr Approach road (SE PWD Qtr DC Residence) | 0.64 | Lunglei Road Division-I |  |  | 100% | 0.64 |  |  | 100% | 0.64 | Completed
35 | Construction of Breast Wall at 0.120Kmp on approach road to Kendryia School Lunglei | 26.75 | Lunglei Road Division-I |  |  | 100% | 26.75 |  |  | 100% | 26.75 | Completed
36 | Construction of Retaining Wall at 0.600 Kmp on Tlabung Peng to Colony PWD Road (Boundary of Venghlun and Rahsi veng) | 7.27 | Lunglei Road Division-I |  |  | 100% | 7.27 |  |  | 100% | 7.27 | Completed
37 | Construction of Retaining Wall at 1.100Kmp on 2nd Parallel Road, Bazar Veng, Lunglei | 6.02 | Lunglei Road Division-I |  |  | 100% | 6.02 |  |  | 100% | 6.02 | Completed
38 | Construction of Retaining Wall at 1.48 Kmp on Sangchem Road | 15.49 | Lunglei Road Division-I |  |  | 100% | 15.49 |  |  | 100% | 15.49 | Completed
39 | Construction of Retaining Wall at Ch:18.450Kmp on Lunglei to Buarpui Road | 26 | Lunglei Road Division-I |  |  | 100% | 26 |  |  | 100% | 26 | Completed
40 | Construction of Retaining Wall at Ch: 18.450Kmp on Lunglei to Buarpui Road | 7 | Lunglei Road Division-I |  |  | 100% | 7 |  |  | 100% | 7 | Completed
41 | Construction of Retaining Wall at 18.500Kmp on Lunglei to Buarpui Road | 4.3 | Lunglei Road Division-I |  |  | 100% | 4.3 |  |  | 100% | 4.3 | Completed
42 | Construction of Multi Level Parking cum Basketball Court beside the main Building | 541.8 | Project Division-I | 5.12.19 | 31.1.23 | 100% | 541.8 |  |  | 100% | 541.8 | Work Completed
43 | Const.of Bridge on Chhinga Vengthar to Tuithiang Road | 586.36 | Aizawl Road South Division | 19.04.21 | 31.10.22 | 100% | 200 | - |  | 100% | 200 | Phy.Work completed | Item Rate Contract

## STATE
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : STATE | [9 empty] | Month : November 2023
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Laboratory Building at Civil Hospital Lunglei Ground Floor | 192.98 | Lunglei Building Project Division | 28.10.21 | 28.10.22 | 100% | 192.98 | - |  | 100% | 192.98 | Completed | Restricted Tender
2 | Construction of Laboratory Building at Civil Hospital Lunglei (1st & 2nd Floor) Supplementary Works | 396 | Lunglei Building Project Division | 28.10.22 | 28.4.24 | 68% | 163.63 | 3% |  | 71% | 163.63 | Work in progress. Allocation of Balanced Fund of Rs.198.00 lakh awaited from the government | Restricted Tender

## SPA
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : SPA | [9 empty] | Month: December
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of District Transport Office at Lawngtlai | 228 | Lunglei Building Project Division | 27.9.16 | 27.9.17 | 100% | 227.98 | - | 0.02 | 100% | 228 | Liabilities already cleared. The building already handed and occupied by the client Dept. | Restricted Tender

## SPP
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : SPP | [9 empty] | Month : January 2024
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Office Building for IF & SL at Tuikhuahtlang | 401.18 | Project Division-III | 13.7.20 | 11.09.23 | 100% | 400.72 |  |  | 100% | 400.72 | Completed and handed over to Director IF&SL | PWD Form-8
2 | Construction of Circuit House at Serchhip | 358.18 | Project Division-III |  |  | - | - | - | - | - | - | Estimate amounting to Rs.3.58 Cr submitted as per new drawing. Waiting for approval for tender.
3 | Construction of Truckable Road between Tlangpui and Lungva | 480 | Khawzawl Division | 5.7.18 | 5.7.19 | 63% | 327.23 | - | - | 63% | 327.23 | EOT granted upto 7.10.2020 | Item rate contract

## DONER
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : One Time Special Assistance under Ministry of DONER | [9 empty] | Month : January 2024
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Re-Construction of safe House at Tlabung | 114.9 | Lunglei Building Project Division | 18.11.21 | 18.11.22 | 100% | 112.66 | - |  | 100% | 112.66 | Civil Works completed. and IE not yet done. Handover in process | Restricted Tender
2 | Re-Construction of safe shelter at Sairang | 115 | Project Division-II | 13.11.21 | 13.11.22 | 100% | 79.7 | - | - | 100% | 79.7 | Work physically completed | Item Rate

## NERSDS
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : NERSDS | [9 empty] | Month : January 2024
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Upgradation of Saiha-Lungbun-Tluangram-Haka Road in the State of Mizoram | 4307.95 | Saiha Division | 29.10.21 | 31.03.24 | 62.24% | 1947 |  |  | 62.24% | 1947 | A show Cause Notice has been served to Contractor due to delay of work | EPC Mode
2 | Upgradation of Hnahlan-Hmunhlui-Tuimang-Singngei Road (Length = 12.000 Kms) | 4417 | Champhai Division | 29.11.21 | 31.3.24 (as per4 EoT-01) | 72.19% | 1924.51 | 2.37% |  | 74.56% | 1924.51 | In progress
3 | Upgradation of Zote-Fartlang-Buanli-Tuipui-Tawnzang Road in the state of Mizoram under NERSDS (Length = 8.00 Kms) | 2547.32 | Champhai Division | 12.12.21 | 11.5.23 | 78.05% | 1465.42 | 0.02% |  | 78.07% | 1465.42 | In progress

## ISC Scheme
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : ISC Scheme & EI | [9 empty] | Month : January 2024
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of Contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Improvement of Tuipuibari - W.Kawnpui Road and ISC (0.00-9.00 Kmp) | 4870 | Mamit Division | 20.3.20 | 20.3.22 | 74% | 3978.3 |  |  | 74% | 3978.3 |  | EPC

## CRF
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : CRF | [9 empty] | Month : January 2024
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Two Lane from Sihhmui-Ramrikawn Road (Stage-I) | 8000 | Aizawl Road North Division | 1.10.18 | 1.10.20 | 92.28% | 4620.81 |  |  | 92.28% | 4620.81 | In progress | Item rate
2 | Widening and Improvement of Road from Durtlang Leitan to Sihphir Section (Length 10.25 Km) of Aizawl - Durtlang - Lungdai -Kawnpui Road in the State of Mizoram | 4657 | Aizawl Road North Division | 14.7.23 | 31.1.25 | 9.82% | 406.28 |  |  | 9.82% | 406.28
3 | Construction of BUG Bridge over Tlawng on Aizawl-Reiek-W.Lungdar Road at 14.800 Kmp | 757.56 | Aizawl Road South Division | 1.10.18 | 31.3.22 | 89% | 488.56 | 3% |  | 92% | 488.56 | Work in progress | EPC Mode
4 | Construction of Muallungthu-Lungphun Road | 5996 | Hmuifang Division | 23.11.17 | 23.11.19 | 33.39% | 1940.67 | - | - | 33.39% | 1940.67 | Work in progress
5 | Widening to single lane with geometric imprivement & Upgradation of Chhiahtlang-Lamchhip Road | 6668.18 | Hmuifang Division | 23.6.17 | 23.06.19 | 100% | 6283.78 | - |  | 100% | 6283.78 | Completed
6 | Construction of Chakkhei to Siasi Road (Permanent Work) (0.00-20.00 Kmp) | 1216.88 | Saiha Division | 8.7.19 | 30.9.23 | 96.62% | 856.38 |  |  | 96.62% | 856.38 | Work in progress | Item rate contract
7 | Construction of Chakkhei to Siasi Road (FC&Pavement Work) (0.00-20.00 Kmp) | 3617.05 | Saiha Division | 8.7.19 | 11.11.23 | 98.55% | 2277.26 |  | - | 98.55% | 2277.26 | Work in progress | Item rate contract
8 | Construction of Double Lane BUSG Bridge (68m span) over R.Tuichang on Keitum - Artahkawn Road | 754.75 | Serchhip Division | 1.12.16 | 31.3.23 | 100% | 754.74 |  |  | 100% | 754.74 | Completed | Item rate

## NESIDS
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : NESIDS | [9 empty] | Month : January 2024
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of 2 Residential Hostel at ZMC (Boys) | 1000 | Project Division-II | 14.10.21 | 29.10.23 | 100% | 1000 |  |  | 100% | 1000 | Work Completed | EPC
2 | Construction of 2 Residential Hotel at ZMC (Girls) | 1000 | Project Division-II | (O)14.10.21 (R) 15.04.24 | (O)27.10.23 (R)15.04.24 | 85% | 765.15 | 3% |  | 88% | 765.15 | Work in progress | EPC
3 | Construction of 100 Bedded Distict Hospital at Kolasib | 2200 | Project Division-II | 23.09.22 | 23.09.24 | 33% | 608.86 | 4% |  | 37% | 608.86 | Work in progress | EPC
4 | Construction of State Resource Centre for HIV/AIDS at Aizawl | 400 | Project Division-II | 22.09.22 | 22.09.24 | 35% | 134.2 | 3% |  | 38% | 134.2 | Work in progress | EPC
5 | Improvement /Upgradation of Operational/Non-operational facilities of Lengpui Aiport (elevated Road with connected components of Terminal Building) | 1959 | Project Division-III | 30.9.21 | 12.6.24 | 92.5% | 1317.31 | 0.2% |  | 92.7% | 1317.31 | Work in progress | Turnkey
6 | Improvement & Upgradation of Lawngtlai-Tuipui ferry Road under NESIDS | 2897.8 | Lawngtlai Division | 08.08.19 | 30.06.23 | 100% | 2666.68 |  |  | 100% | 2666.68 | Phy. Completed | Item rate

## SCA
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : S.C.A | [9 empty] | Month : January 2024
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummutive Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of Contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Improvement of MPSC Office Building at MINECO | 394 | Project Division-I | 29.10.22 | 29.10.24 | 91% | 267.04 | 3% | 6.21 | 94% | 273.25
2 | Construction of DIG (NR) Office Building at PHQ Complex, Aizawl | 320 | Project Division-I | 21.7.22 | 21.1.25 | 85% | 95.22 | 5% | 85.14 | 90% | 180.36
3 | Construction of Govt.Staff Qtrs.(Block-B) at DIET Complex | 386.6 | Project Division-I | 28.8.22 | 28.8.24 | 48% | 97.47 |  | 1 | 48% | 98.47 |  | EPC
4 | Strengthening of Infrastructure in 3 newly created Districts (Const.of DC Office Khawzawl) | 1000 | Project Division-III | 21.04.21 | 21.04.24 | 99.5% | 861.17 | 0.4% |  | 99.9% | 861.17 | Work in progress | PWD Form-8
5 | Strenthening of Infrastructure in 3 newly created Districts (Const.of DC Office Saitual) | 1000 | Project Division-III | 20.01.21 | 20.04.24 | 97% | 972.53 | 1% |  | 98% | 972.53 | Work in progress | PWD Form-8
6 | Construction of District Research Officers Office at Khawzawl (Sh: C/o DRO Office Ground Floor & C/O Quarters 1st Floor) | 43 | Project Division-III | 12.09.22 | 12.05.23 | 100% | 43 |  |  | 100% | 43 | Completed and handed over to Economic & Statistics Deptt | PWD Form-8
7 | Construction of District Research Officers Quarters and Staff Cum Chowkider Quarters at Keifang, Saitual District | 70 | Project Division-III | 9.9.22 | 24.2.24 | 70% | - | 5% | 11.03 | 75% | 11.03 | Work in progress | PWD Form-8
8 | Improvement & Upgradation of Operational/Non Operational facilities of Lengpui (Sh: Renovation of Terminal building) | 2124 | Project Division-III | 10.3.21 | 6.5.24 | 96.5% | 1254.05 | 0.2% | - | 96.7% | 1254.05 | Work in progress | PWD Form-8
9 | Construction of 100 Bedded Dist Hospital at Saitual (Sh: Construction of OPD building at District Hospital, Saitual | 200 | Project Division-III | 13.10.23 | 13.10.25 | 6% |  | 2% | 14.15 | 8% | 14.15 | Work in progress | PWD Form-8
10 | Strengthening of Aizawl-Thenzawl-Lunglei Road from (17.000-30.000 & 51.000-63.00 Kmp) | 1332 | Hmuifang Division | 12.10.21 | 31.03.22 | 100% | 1305.13 | - |  | 100% | 1305.13 | Completed
11 | Rehabilitation of Landslide Area within Hualngohmun Village at Chainage 9.400 | 162 | Hmuifang Division | 28.03.22 | 28.03.23 | 90% | 156.77 | 3% |  | 93% | 156.77 | Work in progress

## NLUP
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : NLUP | [9 empty] | Month : January 2024
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Re-Construction of District Transport Office at Champhai | 262 | Project Division-III | 11.7.22 | 11.01.24 | 100% | 259.5 |  |  | 100% | 259.5 | Handover under process | PWD Form-8

## SARDPNE
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : SARDP-NE | [9 empty] | Month : January 2024
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Widening to two laning/Re-alignment and geometric improvement from km.11+000 to 114+618 of NH-44 'A' in the state of Mizoram | 1,10,988.00 | NHD-I | 17.3.11 | 31.12.22 | 96.04% | 102146 |  |  | 96.04% | 102146 | Contract was terminated on 24.08.2023 Tender being floated for selection of new contractor | Item rate contract
2 | Construction of a new 2-lane Highway from km 0/00kmp to 38/00 in Mizoram to support Kaladan Multi Modal Transit Transport project in Phase-'A of SARDP-NE package-I | 43465 | Multi Modal Project Division |  |  | 100% | 42978 |  |  | 100% | 42978 | 1. Financial progress is upto RA 145 2. Work completed on 22.6.2023
3 | Construction of a new 2-lane Highway from km 38.00 to km 71.00 in Mizoram to support Kaladan Multi Modal Transit Transport project in Phase-'A of SARDP-NE package-II | 32224 | Multi Modal Project Division |  |  | 100% | 30977 |  | - | 100% | 30977 | 1. Financial progress is based on bill submitted by the Contractor after verifying at the spot by the Department. 2. Work completed on 30.04.22
4 | Construction of a new 2-lane Highway from km 71.00 to km 99.83 in Mizoram to support Kaladan Multi Modal Transit Transport project in Phase-'A of SARDP-NE package-III | 37459 | Multi Modal Project Division |  |  | 100% | 37689 |  |  | 100% | 37689 | 1. Financial progress is based on the figure shown in the MoP of the latest bill appproved by Regional Officer, MoRTH Guwahati i.e RA-145 (Retention Money Bill) 2. Work completed on 23.06.23

## MAJOR
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : Major & Minor Works and Deposit woks 8443-108, D-III | [9 empty] | Month : January 2024
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | I/E to Additional Court Room with Chamber at Kolasib | 4.26 | Electrical Division Aizawl |  |  | 100% | 4.26 | - | - | 100% | 4.26 | I/E Completed, S/C being process
2 | I/E to Arrival & Departure Passenger Lobby at Lengpui Airport | 25.27 | Electrical Division Aizawl |  |  | 90% | 25.27 | - | - | 90% | 25.27 | Panel Board not yet installed
3 | SITC 13 Passenger Lift-2 nos, 2-opening, 900mm centre opening Stainless Steel cable with Automatic Rescue Device (ARD) for Hydraulic Lift with Minor Civil Works at Lengpui Airport Mizoram | 77.91 | Electrical Division Aizawl |  |  | 50% | - |  | - | 50% | - | On going works
4 | I/E to Chowkider Qtrs at PWD Complex, Bilkhawthlir | 3.6 | Electrical Division Aizawl |  |  | 100% | 3.6 | - | - | 100% | 3.6 | Completed
5 | I/E to Rest House at PWD Complex, Bilkhawthlir | 30.91 | Electrical Division Aizawl |  |  | 100% | 30.88 | - |  | 100% | 30.88 | Completed
6 | I/E to Re-construction of Safe House at Sairang | 5.2 | Electrical Division Aizawl |  |  | 100% | 5.2 | - | - | 100% | 5.2 | Completed
7 | I/E to Paying Cabin for ZMC at Falkawn | 99.32 | Electrical Division Aizawl |  |  | 100% | 99.32 | - | - | 100% | 99.32 | Completed
8 | SITC with fire fighting system for paying cabin ZMC at Falkawn | 34.57 | Electrical Division Aizawl |  |  | 100% | 34.57 | - |  | 100% | 34.57 | Completed
9 | SITC of 15 passenger G+4MRL Hospital Lift with 900mm Central Opening with Automatic Resue Device (ARD) est (OTISmake) at Paying | 50 | Electrical Division Aizawl |  |  | 100% | 50 | - |  | 100% | 50 | Completed
10 | I/E to Fast Track Court (Judical Gr-I qtr) at Kolasib | 11.43 | Electrical Division Aizawl |  |  | 100% | 11.43 | - | - | 100% | 11.43 | Completed
11 | Street Light Parking light at Lengpui Airport | 37.32 | Electrical Division Aizawl |  |  | 90% | 37.31 |  | - | 90% | 37.31 | On going works
12 | Laying of XLPE Cable from Power House to Glide Path control at Lengpui Airport, Mizoram | 39.53 | Electrical Division Aizawl | 09.05.23 | 04.08.23 | 100% | 39.52 |  |  | 100% | 39.52 | Completed
13 | Estimate for I/E of Energy Meter for Terminal Building at Lengpui Airport | 7.99 | Electrical Division Aizawl |  |  | 70% | 7.99 |  | - | 70% | 7.99 | On going works
14 | I/E for Const.of Grade I Officers Qtr at Project veng Kolasib | 5.13 | Electrical Division Aizawl |  |  | 100% | 5.13 | - | - | 100% | 5.13 | Completed
15 | I/E & Fire fighting to Car Parking at Dist.Court MINECO | 32.48 | Electrical Division Aizawl |  |  | 60% | 16.99 | - | - | 60% | 16.99 | On going works
16 | SITC of Fire Fighting System of Dist.Court, MINECO | 125.4 | Electrical Division Aizawl |  |  | 100% | 124.83 | - | - | 100% | 124.83 | Completed
17 | Addl.Estimate for SITC of MRV/VRF Centralizes Air Conditioner Airport Fist Floor Departure Hall, Mizoram | 247.74 | Electrical Division Aizawl |  |  | 70% | 220.1 |  | - | 70% | 220.1 | On going works
18 | SITC of EPABX System for Lengpui Airport Terminal Building | 24.64 | Electrical Division Aizawl |  |  | 75% | 9.86 |  | - | 75% | 9.86 | On going works
19 | SITC of PA System at Lengpui Airport Terminal Building | 36.36 | Electrical Division Aizawl |  |  | 75% | 14.54 |  | - | 75% | 14.54 | On going works
20 | Supply & Installation of Integrated Fire Hydrant System (Wise Riser) & SiTC of Alarm System for Lengpui Airport Terminal building | 119.96 | Electrical Division Aizawl |  |  | 75% | 47.99 |  | - | 75% | 47.99 | On going works
21 | SITC of AVTRON IP Surveillance System for Lengpui Airport Terminal Building | 94.76 | Electrical Division Aizawl |  |  | 75% | 37.9 |  | - | 75% | 37.9 | On going works
22 | SITC of LANE SETUP at Lengpui Airport Terminal Building | 20.05 | Electrical Division Aizawl |  |  | 75% | 8.02 |  | - | 75% | 8.02 | On going works
23 | Estimate for XLPE Cable for Lengpui Airport | 27.23 | Electrical Division Aizawl |  |  | 90% | 27.23 |  | - | 90% | 27.23 | On going works
24 | Additional Estimate fo SITC of Air Conditioner Departer Pssenger Lobby at Lengpui Airport | 24.67 | Electrical Division Aizawl |  |  | 100% | 24.67 | - | - | 100% | 24.67 | Completed
25 | I/E works for Const. of MBSE Office | 57.37 | Electrical Division Aizawl |  |  | 40% | 57.37 | 10% |  | 50% | 57.37 | On going works
26 | I/E for DC Office at Saitual | 70 | Electrical Division Aizawl |  |  | 100% | 70 | - | - | 100% | 70 | I/E completed, S/C left due to non installation of required transformer
27 | I/E for Const. of IF &SL Office building at Tuikhuahtlang | 23.33 | Electrical Division Aizawl |  |  | 100% | 23.33 |  |  | 100% | 23.33 | Completed
28 | I/E to High Court Parking at MINECO | 109.5 | Electrical Division Aizawl |  |  | 40% | 65.73 | - | - | 40% | 65.73 | On going works
29 | I/E to Staff qtrr Block A for DIET, Chaltlang | 40.11 | Electrical Division Aizawl |  |  | 100% | 40.11 |  |  | 100% | 40.11 | Completed
30 | I/E to PHC at Bungzung | 18.18 | Electrical Division Aizawl |  |  | 100% | 18.18 |  | - | 100% | 18.18 | I/E Completed, S/C left due to non installation of required transformer
31 | I/E to PHC at Ngentiang | 15.72 | Electrical Division Aizawl |  |  | 100% | 15.72 | - |  | 100% | 15.72 | Completed
32 | Const.of DIG(NR) Office at Aizawl under SCA during 2022-23 (Sh:I/E) | 43.84 | Electrical Division Aizawl |  |  | 40% | 17.29 | - | - | 40% | 17.29 | On going works
33 | I/E to Mizoram Public Service Commission (MPSC) Building, Aizawl | 25.86 | Electrical Division Aizawl |  |  | 75% | 25.86 | 5%% |  | 80% | 25.86 | On going works
34 | Construction of DC Office at Khawzawl (Sh: Lift & I/E) | 90 | Electrical Division Aizawl |  |  | 100% | 55.73 |  |  | 100% | 55.73 | I/E Works completed
35 | I/W Multi Level Parking Cum Basketball Court | 11.4 | Electrical Division Aizawl |  |  | 100% | 11.4 |  |  | 100% | 11.4 | Completed
36 | Reconstruction of PHC Building at Marpara, Mamit District | 16.18 | Electrical Division Aizawl |  |  | 60% | 16.18 | 40% |  | 100% | 16.18 | Completed
37 | Reconstruction of PHC Building at Bukpui | 14.59 | Electrical Division Aizawl |  |  | 100% | 14.59 |  |  | 100% | 14.59 | Completed
38 | Type-III Qtr at Vairengte | 1.6 | Electrical Division Aizawl |  |  | 100% | 1.6 |  |  | 100% | 1.6 | Completed
39 | JCO/NCO & Jawan Mess at Vairengte | 1.1 | Electrical Division Aizawl |  |  | 100% | 1.1 |  |  | 100% | 1.1 | Completed
40 | JCO Qtr Barrack cum Hote Company Hqrs at Vairengte | 3.6 | Electrical Division Aizawl |  |  | 100% | 3.6 |  |  | 100% | 3.6 | Completed
41 | Barrack I at Vairengte | 2.2 | Electrical Division Aizawl |  |  | 100% | 2.2 |  |  | 100% | 2.2 | Completed
42 | Barrack II at Vairengte | 2.2 | Electrical Division Aizawl |  |  | 100% | 2.2 |  |  | 100% | 2.2 | Completed
43 | Barrack III at Vairengte | 2.2 | Electrical Division Aizawl |  |  | 100% | 2.2 |  |  | 100% | 2.2 | Completed
44 | Reconstruction of DTO Office at Champhai | 17 | Electrical Division Aizawl |  |  | 100% | 17 |  |  | 100% | 17 | Completed
45 | I/E to DRO Office at Khawzawl | 2.84 | Electrical Division Aizawl |  |  | 100% | 2.84 |  |  | 100% | 2.84 | Completed
46 | Impvt/Revamping of Lengpui Airport runway Lighting -Isolation Bay-DGCA Observation Reg. | 347.05 | Electrical Division Aizawl |  |  | 85% | 218.94 | 5% |  | 90% | 218.94 | On-going works
47 | Impvt/Revamping of Lengpui Airport runway Lighting -Isolation Bay-DGCA Observation Reg. | 10.91 | Electrical Division Aizawl |  |  | 85% |  | 5% |  | 90% |  | On-going works
48 | Impvt/Revamping of Lengpui Airport runway Lighting -Isolation Bay-DGCA Observation Reg. | 14.6 | Electrical Division Aizawl |  |  | 85% |  | 5% |  | 90% |  | On-going works
49 | Impvt of Mizoram House at Silchar-repair of Dak Bangla Ground Floor, DRC Office & DRC Qtr T-IV | 5.19 | Electrical Division Aizawl |  |  | 100% | 5.19 |  |  | 100% | 5.19 | Completed
50 | Renovation/Revamping of Internal Electrification to Polytechnic at Thingdawl (Sh: Automobile Engineering Block) | 18.65 | Electrical Division Aizawl |  |  | 90% |  |  |  | 90% |  | I/E completed, Service connection left
51 | Renovation/Revamping of Internal Electrification to Polytechnic at Thingdawl (Sh: Textile Technology Block) | 18.71 | Electrical Division Aizawl |  |  | 90% |  |  |  | 90% |  | I/E completed, Service connection left
52 | Renovation/Revamping of Internal Electrification to Polytechnic at Thingdawl (Sh: Administrative Block) | 9.52 | Electrical Division Aizawl |  |  | 90% |  |  |  | 90% |  | I/E completed, Service connection left
53 | Renovation/Revamping of Internal Electrification to Polytechnic at Thingdawl (Sh: Common facility Block) | 11.05 | Electrical Division Aizawl |  |  | 90% |  |  |  | 90% |  | Service connection left

## SASCE
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : SASCE | [9 empty] | Month : January 2024
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummutive Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Multi Utility Centre at Zemabawk, Aizawl, Mizoram. | 800 | Project Division-IV | 19.12.22 | 16.8.25 | 29.15% | 145.34 | 3.45% | 20.12 | 32.6% | 165.46 | Work in progress. | Item Rate
2 | Construction of Solid Waste Management Centre at Hualngohmun, Mizoram (Phase-I) | 1664 | Project Division-IV | 07.04.23 | 07.04.25 | 5% | 9.14 |  | 63.93 | 5% | 73.07 | Revised architectural drawing/plan is awaited from Architect Cell, MPWD. | Item Rate
3 | Const.of Road from IR Camp to Ramri Lui, Zophai, Bairabi (Sh: Group A-Formation Cutting, Permanent works and side drain) | 498 | NHD-III | 27.07.23 | 27.01.24 | 100% | 100 |  |  | 100% | 100 |  | Item Rate
| Group B-Pavement. Traffic Sign and Road Safety |  | NHD-III | 11.09.23 | 11.03.24 | [7 empty] | Item Rate

## SPF
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : State Plan Fund | [9 empty] | Month : January 2024
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummutive Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of Contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | 4202 Co-On Education etc. a) I/E to boys & girls Hostel for Govt.Saiha College bldg at Siaha | 2 | Electrical Division, Lunglei |  |  | 40% | - | - | - | 40% | - | Materials received, building not yet ready
2 | 8443-108-PWD Deposit-III a) I/E to DC Bungalow (Type-IV) at Siaha | 8.2 | Electrical Division, Lunglei |  |  | 40% | - |  | - | 40% | - | Materials received, building not yet ready
| b) I/E to Primary Health Centre (PHC) at Tawipui 'S' | 20 | Electrical Division, Lunglei | 1.6.23 | 13.7.23 | 100% |  |  |  | 100% |  | Completed | Electrical Licensed Contractor
| c) I/E to DRO Quarter & DRO Office at Hnahthial | 2.71 | Electrical Division, Lunglei |  |  | 100% |  |  |  | 100% |  | Completed | Depart mental
| d) I/E to DC Office Building at Hnahthial | 68.43 | Electrical Division, Lunglei |  |  | 100% |  |  |  | 100% |  | Completed | Depart mental
| e) I/E to Safe House at Tlabung | 8 | Electrical Division, Lunglei | [8 empty] | TS accorded
| f) I/E to PHC Building at Lungsen | 19 | Electrical Division, Lunglei | [8 empty] | TS accorded
| g) SiTC of 13 (Thirteen) Passengers 5-Opening for DC office Buiulding at Hnahthial | 50 | Electrical Division, Lunglei |  |  | 80% |  | 10% |  | 90% |  | On going works | Contractor
3 | 4059-Co on Public works (Plan) a) I/E to District Court Building at Siaha | 139 | Electrical Division, Lunglei |  |  | 100% | - |  | - | 100% | - | Completed | Depart mental
| b) SITC of 8 (Eight) Passenger Auto Elevator for District Court Building at Siaha | 42 | Electrical Division, Lunglei |  |  | 45% |  | 25% |  | 70% |  | On going works | Contractor
4 | 4047-Co on other Fiscal Sevice
| a) I/E to deputy Commissioner of State Tax, Siaha zone (Office( at Siaha | 17 | Electrical Division, Lunglei |  |  | 100% |  |  |  | 100% |  | Completed | Depart mental
| b) I/E to Staff Quarter for Deputy Commissioner of State Tax, Siaha Zone (Type-I & Type-III) at Siaha | 13 | Electrical Division, Lunglei |  |  | 100% |  |  |  | 100% |  | Completed | Depart mental
| c) I/E to Staff Quarter for Deputy Commissioner of State Tax, Siaha Zone (Type-IV) at Siaha | 5 | Electrical Division, Lunglei |  |  | 100% |  |  |  | 100% |  | Completed | Depart mental

## Under L & J
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : Under L & J | [9 empty] | Month : January 2024
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of District Court Complex at Vengsang, Champhai | 4915.35 | Project Division-III | 17.10.23 | 17.10.26 | 4% |  | 2% |  | 6% |  | Work in progress | PWD Form-8

## AMOP
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : AMOP | [9 empty] | Month : January 2024
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Annual Maintenance Operation Plan (AMOP) 2023-2024 under MRFB | 70 | Mamit Division | 23.06.23 | 17.10.26 | 75% | 61.68 | 25% | 3.05 | 100% | 64.73

## Aspirational
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
| Source of funding : Aspirational District Programme, Window-I | [8 empty] | Month : January 2024
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Link Road from W.Mualthuam to Sothapa Road (Length=7.300Kms) | 200 | Kawrthah Division | 15.10.23 | 14.4.24 | 6% |  | 15% |  | 21% |  | Work in progress | Contract after call of Restricted Tender

## SASCI
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
| Source of funding : SPECIAL ASSISTANT TO STATE FOR CAPITAL INVESTMENT | [8 empty] | Month : December, 2023
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of Contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
LUNGLEI BUILDING PROJECT DIVISION :
1 | Construction of Circuit House at Hnahthial 'A; | 304 | Lunglei Building Project Division | 13.04.23 | 13.10.24 | 14% |  | 2% |  | 16% |  | Work in progress | Restricted Tender
2 | Construction of Circuit House at Hnahthial 'B; | 200 | Lunglei Building Project Division | 13.04.23 | 13.10.24 | [6 empty] | Agreement not yet signed | Restricted Tender
3 | (a) Const. of Laboratory Building at Civil Hospital Lunglei (Ground floor0 | 192 | Lunglei Building Project Division | 28.10.21 | 28.10.22 | 100% | 192.98 |  |  | 100% | 192.98 | Completed | Restricted Tender
4 | (b) Const. of Laboratory Building at Civil Hospital, Lunglei (1st & 2nd floor) Supplementary Works | 396 | Lunglei Building Project Division | 28.10.22 | 28.04.24 | 71% | 163.63 | 4% |  | 75% | 163.63 | Work in progress | Restricted Tender
5 | Strengthening of Infrastrucrture in 3 (three) new Districts in Mizoram (Sh: Const.of DC Office Building at Hnahthial | 1000 | Lunglei Building Project Division | 27.08.21 | 27.08.24 | 100% | 998.03 |  | 1.97 | 100% | 1000 | Work Completed | Restricted Tender
6 | Construction of Sangau SDO© Office building at Sangau | 77 | Lunglei Building Project Division | 20.03.23 | 20.03.24 | 85% | 36.91 | 2% | 0.01 | 87% | 36.92 | Work in progress | Spot Quotation
7 | Construction of SDO© Quarter at Sangau | 80 | Lunglei Building Project Division | 20.03.23 | 20.03.24 | 85% | 40 | 2% |  | 87% | 40 | Work in progress | Spot Quotation
8 | Construction of Staff Quarter(2 Units) at Sangau | 50.45 | Lunglei Building Project Division | 20.03.23 | 20.03.24 | 85% | 25 | 2% |  | 87% | 25 | Work in progress | Spot Quotation
9 | Construction of Volleyball Court at Gulsil Chawngte 'L' | 20 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 10 |  |  | 100% | 10 | Phy.Completed | Spot Quotation
10 | Construction of Meisatla Futsal Ground at Siaha | 34.79 | Lunglei Building Project Division | 20.03.23 | 20.09.23 | 32% |  | 3% | 2.39 | 35% | 2.39 | Work in progress | Spot Quotation
11 | Construction of Futsal Playground at Gov't Higher secondary School at Siaha | 34.79 | Lunglei Building Project Division | 20.03.23 | 20.09.23 | [6 empty] | Not yet started | Spot Quotation
12 | Construction of New Football ground at Ramlaitui | 20 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 98% |  |  |  | 98% |  | Work in progress | Spot Quotation
13 | Construction of New Football Ground at Haulawng | 20 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 60% |  | 40% |  | 100% |  | Phy.Completed | Spot Quotation
14 | Construction of New Football Ground at Mualthuam 'N' | 20 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% |  |  |  | 100% |  | Phy.Completed | Spot Quotation
15 | Construction of New Football Ground at Mualthuam 'N' (on going) | 10 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% |  |  |  | 100% |  | Phy.Completed | Spot Quotation
16 | Construction of New Football Ground at Haulawng ( on going ) | 10 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 92% |  | 8% |  | 100% |  | Phy.Completed | Spot Quotation
17 | Construction of New Football Ground at Rawpui | 15 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 98% |  | 2% |  | 100% |  | Phy.Completed | Spot Quotation
18 | Construction of Community Hall at Pukpui | 80 | Lunglei Building Project Division | 20.03.23 | 20.03.24 | 60% | 0.2 | 15% | 2.01 | 75% | 2.21 | Work in progress | Spot Quotation
19 | Construction of New Badminton Hall at Chhipphir | 20 | Lunglei Building Project Division | 20.03.23 | 20.09.23 | 100% |  |  | 0.55 | 100% | 0.55 | Phy.Completed | Spot Quotation
20 | Renovation of Community Hall at Farm Veng | 10 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 5 |  |  | 100% | 5 | Phy.Completed | Spot Quotation
21 | Renovation of Community Hall at Zobawk 'S' | 10 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% |  |  | 0.27 | 100% | 0.27 | Phy.Completed | Spot Quotation
22 | Renovation of Sport recreation House ( TT Hall) at Zobawk 'N' at Zobawk Bazar | 10 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% |  |  | 0.84 | 100% | 0.84 | Phy.Completed | Spot Quotation
23 | Painting & Electrification of Zobawk 'N' Hall | 12 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% |  |  | 0.31 | 100% | 0.31 | Phy.Completed | Spot Quotation
24 | Land development & Earthwork for Community Hall at Ralvawng | 10 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 5 |  |  | 100% | 5 | Phy.Completed | Spot Quotation
25 | Renovation of Community Hall at Leite | 5 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% |  |  |  | 100% |  | Phy.Completed | Spot Quotation
26 | Renovation of Public NGO's House at Leite | 5 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 7.5 |  |  | 100% | 7.5 | Phy Completed | Spot Quotation
27 | Renovation of Community Hall at Rotlang 'E' | 5 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% |  |  |  | 100% |  | Phy.Completed | Spot Quotation
28 | Completion of Community Hall at Dawn | 8 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 97% |  | 3% | 0.22 | 100% | 0.22 | Phy.Completed | Spot Quotation
29 | Construction of Community Hall at Zehtet | 30 | Lunglei Building Project Division | 20.03.23 | 20.09.23 | 100% |  |  | 0.82 | 100% | 0.82 | Phy.Completed | Spot Quotation
30 | Construction of Community Hall at Lungrang 'S' | 40 | Lunglei Building Project Division | 20.03.23 | 20.03.24 | 20% |  |  | 1.1 | 20% | 1.1 | Work in progress | Spot Quotation
31 | Construction of Community Hall | 12 | Lunglei Building Project Division | 20.03.23 | 20.09.23 | 100% | 6 |  |  | 100% | 6 | Phy.Completed | Spot Quotation
32 | Construction of Community Hall at Chhumkhum | 27.47 | Lunglei Building Project Division | 20.03.23 | 20.09.23 | 100% | 13.75 |  |  | 100% | 13.75 | Phy Completed | Spot Quotation
33 | Construction of Community Hall at New Sachan | 27.47 | Lunglei Building Project Division | 20.03.23 | 20.09.23 | 100% | 13.75 |  |  | 100% | 13.75 | Phy.Completed | Spot Quotation
34 | Construction of Public Recreation House at Chanmari, Lunglei | 10 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 5 |  |  | 100% | 5 | Phy.Completed | Spot Quotation
34 | Construction of Old Aged Home cum Library House at Community Hall at Ramthar, Lunglei | 15 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% |  |  | 0.42 | 100% | 0.42 | Phy.Completed | Spot Quotation
36 | Construction of Women Recreation House or Cemetary House at Electric veng Lunglei (Women recreation house) | 10 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 4.9 |  | 2.01 | 100% | 6.91 | Phy.Completed | Spot Quotation
37 | Construction of NGO's House cum Library Room at Zobawk 'S' Vengthar | 10 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 5 |  |  | 100% | 5 | Phy.Completed | Spot Quotation
38 | Completion of NGO's Recreation House at Lungpuizawl | 5 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 7.5 |  | 0.14 | 100% | 7.64 | Phy.Completed | Spot Quotation
39 | Renovation of Women Recreation House at Lower Ramthar, Lunglei | 5 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 7.5 |  | 0.14 | 100% | 7.64 | Phy.Completed | Spot Quotation
40 | Construction of Waiting Shed & Godown of Animal Feed Building at dawn | 5 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 7.5 |  | 0.14 | 100% | 7.64 | Phy.Completed | Spot Quotation
41 | Construction of Women Recreation House at Upper Ramthar, Lunglei | 15 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 95% |  | 5% | 0.42 | 100% | 0.42 | Phy.Completed | Spot Quotation
42 | Construction of NGO's Recreation house at Farm Veng, lunglei | 10 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% |  |  | 3.97 | 100% | 3.97 | Phy.Completed | Spot Quotation
43 | Construction of Clinic Center Building at Bungtlang W | 5 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 2.5 |  |  | 100% | 2.5 | Phy.Completed | Spot Quotation
44 | Rahsiveng Market Shed | 52 | Lunglei Building Project Division | 20.03.23 | 20.09.23 | 100% | 26 |  |  | 100% | 26 | Phy Completed | Spot Quotation
Construction of Public Toilet, Cemetary House, Waiting Shed, Water Supply & Footpath at Lunglei and Bunghmun
45 | Constructuion of Toilet and Water Pint at Kawmzawl Helipad, aizawl to lunglei Helicopter service Station | 15 | Lunglei Building Project Division | 20.03.23 | 20.09.23 | 90% |  | 10% | 0.41 | 100% | 0.41 | Phy.Completed | Spot Quotation
46 | Construction of Cemetary House at Chanmari, Lunglei | 15 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 7.5 |  |  | 100% | 7.5 | Phy.Completed | Spot Quotation
47 | Construction of Fencing & Cement Flooring at YMA hall courtyard at Electric Veng, Lunglei | 15 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 0.2 |  | 0.22 | 100% | 0.42 | Phy.Completed | Spot Quotation
48 | Construction of Public Store house and Urinal Shed at Electric Veng, Lunglei | 15 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 0.2 |  |  | 100% | 0.2 | Phy.Completed | Spot Quotation
49 | Construction of Waiting Shed near PWD Turning Point | 10 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 5 |  |  | 100% | 5 | Phy.Completed | Spot Quotation
50 | Estimate for Construction of Cemetary House at College Veng, lunglei | 5 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 2.5 |  |  | 100% | 2.5 | Phy.Completed | Spot Quotation
51 | Construction of Cemetary House at Bazar Veng Thlanmual No. 3 | 5 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 2.5 |  |  | 100% | 2.5 | Phy.Completed | Spot Quotation
52 | Construction of Boat Waiting shed at New Sachan | 0.69 | Lunglei Building Project Division | 20.03.23 | 20.05.23 | 100% | 0.35 |  | 0.02 | 100% | 0.37 | Phy.Completed | Spot Quotation
53 | Construction of Waiting near border Fencing inside India at Terabonia | 10.8 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 0.53 |  | 0.4 | 100% | 0.93 | Phy.Completed | Spot Quotation
54 | Construction of Boat Waiting Shed at Tuikawi | 0.69 | Lunglei Building Project Division | 20.03.23 | 20.05.23 | 100% | 0.35 |  | 0.02 | 100% | 0.37 | Phy.Completed | Spot Quotation
55 | Construction of Boat Waiting Shed at Sumasuri | 0.69 | Lunglei Building Project Division | 20.03.23 | 20.05.23 | 100% | 0.35 |  | 0.02 | 100% | 0.37 | Phy.Completed | Spot Quotation
56 | Construction of Boat waiting Shed at Old Sachan | 0.69 | Lunglei Building Project Division | 20.03.23 | 20.05.23 | 100% | 0.35 |  |  | 100% | 0.35 | Phy.Completed | Spot Quotation
57 | Construction of Waiting shed at Bungkawn, Lungchem | 0.69 | Lunglei Building Project Division | 20.03.23 | 20.05.23 | 100% | 0.35 |  |  | 100% | 0.35 | Phy.Completed | Spot Quotation
58 | Construction of Public Urinal near Vanlalhriara's House at Changpui | 0.73 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% |  |  |  | 100% |  | Phy.Completed | Spot Quotation
59 | Construction of Public Urinal near Hrangthuama's House at Changpui | 0.73 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% |  |  |  | 100% |  | Phy.Completed | Spot Quotation
60 | Construction of Urinal near Vanlalpianga's House at Dengsur | 0.73 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% |  |  |  | 100% |  | Phy.Completed | Spot Quotation
61 | Construction of Urinal near Thanthianga's House at Dengsur | 0.73 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% |  |  |  | 100% |  | Phy.Completed | Spot Quotation
62 | Construction of Urinal near Community Hall at Dengsur | 0.73 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% |  |  |  | 100% |  | Phy.Completed | Spot Quotation
63 | construction of Waiting Shed at Mangkhan Kawn, Dengsur | 10.8 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 0.53 |  |  | 100% | 0.53 | Phy.Completed | Spot Quotation
64 | Construction of Waiting shed at sabual & Dengsur Boundary. | 10.8 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 0.53 |  |  | 100% | 0.53 | Phy.Completed | Spot Quotation
65 | Construction of Waiting Shed near K.Vanlalruata's House at S.Khawlek | 1.08 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 0.53 |  |  | 100% | 0.53 | Phy.Completed | Spot Quotation
66 | Construction of Public Urinal near Information Centre Building at S.Khawlek | 0.73 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% |  |  |  | 100% |  | Phy.Completed | Spot Quotation
67 | Construction of Waiting shed at Dampui | 1.08 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 0.53 |  |  | 100% | 0.53 | Phy.Completed | Spot Quotation
68 | Construction of Cemetary House at Thenhlum | 0.76 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 0.38 |  |  | 100% | 0.38 | Phy.Completed | Spot Quotation
69 | Construction of Waiting Shed at Tawngtaina Hmun Zawlpui | 1.08 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 0.53 |  |  | 100% | 0.53 | Phy.Completed | Spot Quotation
70 | Construction of Public Urinal at Tawngtaina hmun at Zawlpui | 0.73 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% |  |  |  | 100% |  | Phy.Completed | Spot Quotation
71 | Construction of Bus Waiting Shed near Thantluanga's House at Belthei | 0.88 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 0.44 |  |  | 100% | 0.44 | Phy.Completed | Spot Quotation
72 | Construction of Waiting Shed at Tuisenchhuah | 10.8 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 0.53 |  |  | 100% | 0.53 | Phy.Completed | Spot Quotation
73 | Construction of Cemetary House at Rangte | 0.76 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 0.38 |  |  | 100% | 0.38 | Phy.Completed | Spot Quotation
74 | Stainless Steel Railling with Checker Tiles | 6 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% |  |  |  | 100% |  | Phy.Completed | Spot Quotation
75 | River view & Resting shed. ( Tlabung) | 9.5 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 10.25 |  |  | 100% | 10.25 | Phy.Completed | Spot Quotation
76 | Urinal Building with Side Drain Cover (Tlabung) | 5 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% |  |  |  | 100% |  | Phy.Completed | Spot Quotation
77 | Lowering of Siahatla field at Siaha | 35.97 | Lunglei Building Project Division | 20.03.23 | 20.03.24 | 100% | 18 |  |  | 100% | 18 | Phy.Completed | Spot Quotation
78 | Construction of Bazar Shed at Tuichawng | 5 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 2.5 |  |  | 100% | 2.5 | Phy.Completed | Spot Quotation
79 | Construction of MHIP Building at Bunghmun | 17.71 | Lunglei Building Project Division | 20.03.23 | 20.09.23 | 100% | 8.8 |  |  | 100% | 8.8 | Phy.Completed | Spot Quotation
80 | Construction of Anganwadi Centre at Zodin | 4.5 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 2.2 |  | 2.3 | 100% | 2.2 | Phy.Completed | Spot Quotation
81 | Construction of Playground at Chawngte 'L' | 40 | Lunglei Building Project Division | 20.03.23 | 20.09.23 | 100% | 19.62 |  |  | 100% | 19.62 | Phy.Completed | Spot Quotation
82 | Construction of Anganwadi Centre at Mauzam | 4.02 | Lunglei Building Project Division | 20.03.23 | 20.09.23 | 90% | 2 |  | 0.12 | 90% | 2.12 | Work in progress | Spot Quotation
83 | Construction of Anganwadi Centre at Tuisenchhuah | 9 | Lunglei Building Project Division | 20.03.23 | 20.09.23 | 90% | 4.5 |  |  | 90% | 4.5 | Work in progress | Spot Quotation
84 | Construction of MUP Building at Thenhlum | 9 | Lunglei Building Project Division | 20.03.23 | 20.09.23 | 100% | 4.5 |  |  | 100% | 4.5 | Phy.Completed | Spot Quotation
AIZAWL ROAD NORTH DIVISION
1. CONSTRUCTION AND UPGRADATION OF ROAD FROM BAWNGKAWN TO RAMHLUN NORTH, AIZAWL
RAMHLUN NORTH
85 | Extension of Slab Culvert Side drain with cover Near Pi Duhawmi House at Ramhlun North | 0.81 | Aizawl Road North Division | 25.03.23 | 27.03.23 | 100% | 0.81 |  |  | 100% | 0.81 | Completed | Spot Quotation
86 | Construction of RCC Balcony Vety Qtr to Pu Lalrinsanga House Ramhlun North Basic Mual at Ramhlun North | 29.55 | Aizawl Road North Division | 14.02.23 | 03.07.23 | 100% | 29.55 |  |  | 100% | 29.55 | Completed | Spot Quotation
87 | Construction of PCC Pavement on AMC road Ramhlun North | 4.52 | Aizawl Road North Division | 27.03.23 | 29.04.23 | 100% | 4.52 |  |  | 100% | 4.52 | Completed | Spot Quotation
88 | Construction of Breast Wall near Pi Lalthlamuani at Ramhlun North | 2.49 | Aizawl Road North Division | 28.02.23 | 15.03.23 | 100% | 2.49 |  |  | 100% | 2.49 | Completed | Spot Quotation
89 | Construction of Retaining wall near Pi Duhawmi at Ramhlun North | 3.57 | Aizawl Road North Division | 15.03.23 | 22.03.23 | 100% | 3.57 |  |  | 100% | 3.57 | Completed | Spot Quotation
90 | Construction of Retaining Wall near Pi Thangluri at Ramhlun North | 7.66 | Aizawl Road North Division | 17.02.23 | 23.03.23 | 100% | 7.66 |  |  | 100% | 7.66 | Completed | Spot Quotation
RAMHLUN SOUTH
91 | Cons.of Side drain with cover steel on Centenary Tuikhur to rev.Vanlalbuaia House On Carmel road at Ramhlun South | 19.26 | Aizawl Road North Division | 15.02.23 | 25.03.23 | 100% | 19.26 |  |  | 100% | 19.26 | Completed | Spot Quotation
92 | Const.of RCC Rectangular Side drain with cover on Bawngkawn to ITI road at Ramhlun South | 30.88 | Aizawl Road North Division | 13.02.23 | 05.06.23 | 100% | 30.88 |  |  | 100% | 30.88 | Completed | Spot Quotation
93 | Const.of RCC Rectanggular Side drain with cover on Thlanmual to Darnam Lui at Ramhlun South | 10.05 | Aizawl Road North Division | 24.02.23 | 04.04.23 | 100% | 10.05 |  |  | 100% | 10.05 | Completed | Spot Quotation
94 | Const.of Retaining wall near Pu Rohnuna Varte house at Ramhlun South | 8.22 | Aizawl Road North Division | 23.02.23 | 25.03.23 | 100% | 8.22 |  |  | 100% | 8.22 | Completed | Spot Quotation
95 | Construction of RCC Retaining wall near Ralhnehthanga House at Ramhlun South | 5.22 | Aizawl Road North Division | 21.02.23 | 14.03.23 | 100% | 5.22 |  |  | 100% | 5.22 | Completed | Spot Quotation
RAMHLUN VENGLAI
96 | Const.of RCC Rectangular side drain with cover on Approach Road to NHC office near Lalnghakliani to Pi Vanhnuaithangi House at Ramhlun Venglai | 2.68 | Aizawl Road North Division | 17.04.23 | 28.04.23 | 100% | 2.68 |  |  | 100% | 2.68 | Completed | Spot Quotation
97 | Const.of RCC Rectangular side drain with cover Near Pu mabiaka House at Ramhlun Venglai | 6.12 | Aizawl Road North Division | 15.02.23 | 28.04.23 | 100% | 6.12 |  |  | 100% | 6.12 | Completed | Spot Quotation
98 | Const.of RCC Rectangular side drain with cover on Ramhlun Venglai PCI to PC.Vanlalena House at Ramhlun Venglai | 7.05 | Aizawl Road North Division | 20.02.23 | 18.03.23 | 100% | 7.05 |  |  | 100% | 7.05 | Completed | Spot Quotation
99 | Const.of RCC Rectangular side drain with cover near H.Lalbiakmawia House at Ramhlun Venglai | 3.02 | Aizawl Road North Division | 28.02.23 | 13.03.23 | 100% | 3.02 |  |  | 100% | 3.02 | Completed | Spot Quotation
100 | Const.of Steel cross drain near H.lalbiakmawia House (Lower) at Ramhlun Venglai | 0.75 | Aizawl Road North Division | 14.03.23 | 20.03.23 | 100% | 0.75 |  |  | 100% | 0.75 | Completed | Spot Quotation
101 | Const.of Widening & Breast Wall on Approach Road to NHC Office near Pi Lalnghakliani House to Pi Vanhnuaithangi House at Ramhlun Venglai | 15.88 | Aizawl Road North Division | 15.03.23 | 14.04.23 | 100% | 15.88 |  |  | 100% | 15.88 | Completed | Spot Quotation
102 | Const.of Breast Wall Extension with Side Drain on DIC Office at Ramhlun Venglai at Ramhlun Venglai | 13.1 | Aizawl Road North Division | 20.03.23 | 19.05.23 | 100% | 13.1 |  |  | 100% | 13.1 | Completed | Spot Quotation
RAMHLUN VENGTHAR
103 | Const.of RCC Rectangular side drain with cover near Ramhlun Vengthar taxi stand at Ramhlun Vengthar | 6.53 | Aizawl Road North Division | 15.02.23 | 24.02.23 | 100% | 6.53 |  |  | 100% | 6.53 | Completed | Spot Quotation
104 | Const.of RCC Rectangular side drain with cover on Tluangpui road (Pu lalthawmliana to Cosma Mantluanga House) at Ramhlun Vengthar | 4.71 | Aizawl Road North Division | 17.02.23 | 03.03.23 | 100% | 4.71 |  |  | 100% | 4.71 | Completed | Spot Quotation
105 | Const.of RCC Rectangular side drain with cover on Zohmasawna House to bangla Lui at ramhlun Vengthar | 6.63 | Aizawl Road North Division | 21.02.23 | 13.03.23 | 100% | 6.63 |  |  | 100% | 6.63 | Completed | Spot Quotation
106 | Const.of RCC Rectangular side drain with cover on Sihpui to Ramhlun Vengthar Bus turning point at Ramhlun Vengthar | 11.23 | Aizawl Road North Division | 14.03.23 | 31.03.23 | 100% | 11.23 |  |  | 100% | 11.23 | Completed | Spot Quotation
107 | Const.of RCC Rectangular Cross drain with cover near Waiting Shed at Ramhlun Vengthar | 0.75 | Aizawl Road North Division | 17.03.23 | 23.03.23 | 100% | 0.75 |  |  | 100% | 0.75 | Completed | Spot Quotation
108 | Const.of Link drain near V.Lalvela House at Ramhlun Vengthar | 1.68 | Aizawl Road North Division | 17.02.23 | 22.02.23 | 100% | 1.68 |  |  | 100% | 1.68 | Completed | Spot Quotation
RAMHLUN SPORT COMPLEX
109 | Const.of RCC Rectangular Cross drain with cover near B.Lalthlamuana (L) House at Ramhlun Sport Complex | 0.73 | Aizawl Road North Division | 21.03.23 | 25.03.23 | 100% | 0.73 |  |  | 100% | 0.73 | Completed | Spot Quotation
110 | Const.of RCC Rectangular Side drain with cover near B.Lalthlamuana (L) House at Ramhlun Sport Complex | 2.52 | Aizawl Road North Division | 23.02.23 | 14.03.23 | 100% | 2.52 |  |  | 100% | 2.52 | Completed | Spot Quotation
111 | Const.of Link drain near B.Lalthlamuana (L) House at Ramhlun Sport Complex | 1.61 | Aizawl Road North Division | 04.03.23 | 17.03.23 | 100% | 1.61 |  |  | 100% | 1.61 | Completed | Spot Quotation
112 | Const.of steel cross drain near Laldinliana House at Ramhlun Sport Complex | 0.55 | Aizawl Road North Division | 28.02.23 | 18.03.23 | 100% | 0.55 |  |  | 100% | 0.55 | Completed | Spot Quotation
113 | Const.of RCC Rectangular Side drain with cover near Laldinliana House at Ramhlun Sport Complex | 0.7 | Aizawl Road North Division | 17.03.23 | 22.03.23 | 100% | 0.7 |  |  | 100% | 0.7 | Completed | Spot Quotation
114 | Const.of PCC Pavement near ICI road at Ramhlun Sport Complex | 1.4 | Aizawl Road North Division | 18.04.23 | 02.05.23 | 100% | 1.4 |  |  | 100% | 1.4 | Completed | Spot Quotation
115 | Const.of Retaining Wall on ICI road at Ramhlun Sport Complex | 5.83 | Aizawl Road North Division | 12.04.23 | 17.04.23 | 100% | 5.83 |  |  | 100% | 5.83 | Completed | Spot Quotation
116 | Const.of PCC Pavement on Pu Hrekima House to Zohmingsanga House at Ramhlun Sport Complex | 2.53 | Aizawl Road North Division | 28.02.23 | 08.03.23 | 100% | 2.53 |  |  | 100% | 2.53 | Completed | Spot Quotation
117 | Const.of PCC Pavement near Laldinliana House at Ramhlun Sport Complex | 1.69 | Aizawl Road North Division | 31.03.23 | 01.04.23 | 100% | 1.69 |  |  | 100% | 1.69 | Completed | Spot Quotation
118 | Const.of Breast wall near Laldinliana House at Ramhlun Sport Complex | 2.22 | Aizawl Road North Division | 28.02.23 | 14.03.23 | 100% | 2.22 |  |  | 100% | 2.22 | Completed | Spot Quotation
119 | Const.of Retaining wall near Pu Hrekima House at Ramhlun Sport Complex | 2.25 | Aizawl Road North Division | 17.03.23 | 27.03.23 | 100% | 2.25 |  |  | 100% | 2.25 | Completed | Spot Quotation
120 | Const.of Retaining wall on LC Road to Lalfakawmi House at Ramhlun Sport Complex | 1.44 | Aizawl Road North Division | 06.03.23 | 16.03.23 | 100% | 1.44 |  |  | 100% | 1.44 | Completed | Spot Quotation
121 | Const.of Retaining wall near Pu Lingngoa at Ramhlun Sport Complex | 1.54 | Aizawl Road North Division | 09.03.23 | 16.03.23 | 100% | 1.54 |  |  | 100% | 1.54 | Completed | Spot Quotation
122 | Const.of Retaining wall near Kiamlova House at Ramhlun Sport Complex | 7.52 | Aizawl Road North Division | 23.02.23 | 14.03.23 | 100% | 7.52 |  |  | 100% | 7.52 | Completed | Spot Quotation
123 | Const.of Retaining wall block-I on LC road Lianhnuna House to Buchhawna ME School at Ramhlun Sport Complex | 3.69 | Aizawl Road North Division | 27.02.23 | 10.03.23 | 100% | 3.69 |  |  | 100% | 3.69 | Completed | Spot Quotation
124 | Const.of Retaining wall block-II on LC road Lianhnuna House to Buchhawna ME School at Ramhlun Sport Complex | 5.26 | Aizawl Road North Division | 27.02.23 | 17.03.23 | 100% | 5.26 |  |  | 100% | 5.26 | Completed | Spot Quotation
125 | Const.of Retaining wall block-III on LC road Lianhnuna House to Buchhawna ME School at Ramhlun Sport Complex | 7.56 | Aizawl Road North Division | 17.04.23 | 09.05.23 | 100% | 7.56 |  |  | 100% | 7.56 | Completed | Spot Quotation
126 | Const.of Retaining wall block-IV on LC road Lianhnuna House to Buchhawna ME School at Ramhlun Sport Complex | 7.03 | Aizawl Road North Division | 24.02.23 | 17.03.23 | 100% | 7.03 |  |  | 100% | 7.03 | Completed | Spot Quotation
127 | Const.of Retaining wall Near YMA ram at Ramhlun Sport Complex | 7.17 | Aizawl Road North Division | 23.02.23 | 29.03.23 | 100% | 7.17 |  |  | 100% | 7.17 | Completed | Spot Quotation
128 | Const.of Retaining wall Near Bangla Lui at Ramhlun Sport Complex | 13.45 | Aizawl Road North Division | 16.03.23 | 26.04.23 | 100% | 6.73 |  |  | 100% | 13.45 | Completed | Spot Quotation
129 | Const.of Retaining wall Near Bangla Lui Counterford at Ramhlun Sport Complex | 8.84 | Aizawl Road North Division | 06.03.23 | 29.03.23 | 100% | 8.84 |  |  | 100% | 8.84 | Completed | Spot Quotation
130 | Const.of PCC Pavement on Presbyterian Biak In road at Ramhlun Sport Complex Vengthlang | 3.89 | Aizawl Road North Division | 27.02.23 | 07.03.23 | 100% | 3.89 |  |  | 100% | 3.89 | Completed | Spot Quotation
131 | Const.of PCC Pavement on Ramhlun Vengthar road at Ramhlun Sport Complex Vengthlang | 4.11 | Aizawl Road North Division | 13.04.23 | 27.04.23 | 100% | 4.11 |  |  | 100% | 4.11 | Completed | Spot Quotation
132 | Const.of PCC Pavement on Ringzova road to Pu Lalbiakliana House at Ramhlun Sport Complex Vengthlang | 3.89 | Aizawl Road North Division | 07.03.23 | 24.03.23 | 100% | 3.89 |  |  | 100% | 3.89 | Completed | Spot Quotation
BAWNGKAWN SOUTH
133 | Const.of Link drain between Darringaia's House to Lalensanga's House at Bawngkawn 'S' | 9.55 | Aizawl Road North Division | 21.02.23 | 23.03.23 | 100% | 9.55 |  |  | 100% | 9.55 | Completed | Spot Quotation
134 | Const.of Hand Railing for Public Step near Pi Mangkungi House Bawngkawn 'S' | 3.11 | Aizawl Road North Division | 13.02.23 | 25.03.23 | 100% | 3.11 |  |  | 100% | 3.11 | Completed | Spot Quotation
135 | Const.of Hand Railing for Public Step near YMA Hall, Bawngkawn 'S' | 0.81 | Aizawl Road North Division | 13.02.23 | 27.02.23 | 100% | 0.81 |  |  | 100% | 0.81 | Completed | Spot Quotation
136 | Const.of Hand Railing for Public Step near Pu Tlangdingliana House Bawngkawn 'S' | 2.11 | Aizawl Road North Division | 13.02.23 | 25.03.23 | 100% | 2.11 |  |  | 100% | 2.11 | Completed | Spot Quotation
137 | Const.of Hand Railing for Public footpath near YMA Hall, Bawngkawn 'S' | 1.81 | Aizawl Road North Division | 13.02.23 | 25.03.23 | 100% | 1.81 |  |  | 100% | 1.81 | Completed | Spot Quotation
138 | Const.of Retaining wall near YMA Hall, Bawngkawn 'S' | 1.41 | Aizawl Road North Division | 17.03.23 | 20.03.23 | 100% | 1.41 |  |  | 100% | 1.41 | Completed | Spot Quotation
139 | Const.of Retaining wall near transformer on Pu Liansailova road at Bawngkawn 'S' | 1.66 | Aizawl Road North Division | 24.02.23 | 02.03.23 | 100% | 1.66 |  |  | 100% | 1.66 | Completed | Spot Quotation
140 | Construction of PCC Pavement on Pu Liansailova Road at Bawngkawn South | 3.36 | Aizawl Road North Division | 19.02.23 | 24.02.23 | 100% | 3.36 |  |  | 100% | 3.36 | Completed | Spot Quotation
141 | Repair of Side drain near Pu Tlangdingliana House | 0.36 | Aizawl Road North Division | 10.03.23 | 11.03.23 | 100% | 0.36 |  |  | 100% | 0.36 | Completed | Spot Quotation
2. CONSTRUCTION AND UPGRADATION OF ROAD FROM BAWNGKAWN TO RAMHLUN NORTH, AIZAWL, ZARKAWT
142 | Construction of Ahimsa to Jail Veng road at Zarkawt. | 77.98 | Aizawl Road North Division | 02.05.23 | 30.11.23 | 35% | 35.79 | 10% |  | 45% | 35.79 | Work in progress | Spot Quotation
AIZAWL VENGLAI
143 | Construction of of RCC Rectangular Side drain with cover on P.Lalvuana to R.Lalhmachhuana house at Aizawl Venglai | 3.36 | Aizawl Road North Division | 24.02.23 | 17.03.23 | 100% | 3.36 |  |  | 100% | 3.36 | Completed | Spot Quotation
144 | Construction of RCC Rectangular Side drain with cover on Taitea Tuikhur to YMA Hall at Aizawl Venglai | 7.01 | Aizawl Road North Division | 17.02.23 | 25.03.23 | 100% | 7.01 |  |  | 100% | 7.01 | Completed | Spot Quotation
145 | Construction of RCC Rectangular Side drain with cover on Pu Lalhluna House to Pu Nghinglova House at Aizawl Venglai | 1.26 | Aizawl Road North Division | 24.02.23 | 18.04.23 | 100% | 1.26 |  |  | 100% | 1.26 | Completed | Spot Quotation
146 | Construction of RCC Rectangular Side drain with cover on Pu Zosiama Garrage to Pi Lalbiaki House at Aizawl Venglai | 3.36 | Aizawl Road North Division | 20.02.23 | 10.03.23 | 100% | 3.36 |  |  | 100% | 3.36 | Completed | Spot Quotation
147 | Construction of Link drain on Chuangkimi to Benben step at Aizawl Venglai | 1.89 | Aizawl Road North Division | 02.02.23 | 15.03.23 | 100% | 1.89 |  |  | 100% | 1.89 | Completed | Spot Quotation
148 | Construction of Link drain on Pi Rosiami to Pi Lalmuanpuii House at Aizawl Venglai | 2.79 | Aizawl Road North Division | 25.02.23 | 18.03.23 | 100% | 2.79 |  |  | 100% | 2.79 | Completed | Spot Quotation
149 | Construction of Link drain near Pi Chuangkimi House at Aizawl Venglai | 2.7 | Aizawl Road North Division | 10.03.23 | 04.04.23 | 100% | 2.7 |  |  | 100% | 2.7 | Completed | Spot Quotation
150 | Construction of Link drain on Mini market to VDP House at Aizawl Venglai | 3.08 | Aizawl Road North Division | 16.02.23 | 28.02.23 | 100% | 3.08 |  |  | 100% | 3.08 | Completed | Spot Quotation
151 | Construction of V-Shape side drain on Zirtiri College to Pu Saptawnliana House at Aizawl Venglai | 2.68 | Aizawl Road North Division | 21.02.23 | 04.03.23 | 100% | 2.68 |  |  | 100% | 2.68 | Completed | Spot Quotation
152 | Construction of V-Shape side on Pu Sapliantawna to khurpui at Aizawl Venglai | 0.76 | Aizawl Road North Division | 27.02.23 | 18.03.23 | 100% | 0.78 |  |  | 100% | 0.78 | Completed | Spot Quotation
153 | Construction of V-Shape side on Lalnghinglova House to Chuangkimi House at Aizawl Venglai | 1.65 | Aizawl Road North Division | 20.02.23 | 10.03.23 | 100% | 1.65 |  |  | 100% | 1.65 | Completed | Spot Quotation
154 | Construction of V-Shape side drain on K.Zaneiha Garrage to Kawrhpui (Rozami House) at Aizawl Venglai | 2.16 | Aizawl Road North Division | 20.02.23 | 30.05.23 | 100% | 2.16 |  |  | 100% | 2.16 | Completed | Spot Quotation
155 | Construction of of Steel cross drain on near Pu J.Laltanpuia at Aizawl Venglai | 0.76 | Aizawl Road North Division | 21.02.23 | 24.02.23 | 100% | 0.76 |  |  | 100% | 0.76 | Completed | Spot Quotation
156 | Construction of of Steel cross drain on near Pi Chuangkimi House at Aizawl Venglai | 0.58 | Aizawl Road North Division | 21.02.23 | 06.03.23 | 100% | 0.58 |  |  | 100% | 0.58 | Phy.Completed | Spot Quotation
157 | Const. of Chequerred tile near MHIP House at Aizawl Venglai | 1.88 | Aizawl Road North Division | 27.02.23 | 08.03.23 | 100% | 1.88 |  |  | 100% | 1.88 | Completed | Spot Quotation
158 | Construction of Link drain cover near Pi Lalchawngpuii House at Aizawl Venglai | 1.88 | Aizawl Road North Division | 20.02.23 | 03.03.23 | 100% | 1.88 |  |  | 100% | 1.88 | Completed | Spot Quotation
159 | Construction of PCC Pavement on Middle School to Biakthuama House at Aizawl Venglai | 0.42 | Aizawl Road North Division | 24.02.23 | 27.02.23 | 100% | 0.42 |  |  | 100% | 0.42 | Completed | Spot Quotation
160 | Construction of Retaining Wall near VDP House at Aizawl Venglai | 0.58 | Aizawl Road North Division | 18.03.23 | 24.03.23 | 100% | 0.58 |  |  | 100% | 0.58 | Completed | Spot Quotation
161 | Const. of Link drain on Lalmuanpuii House to KC.Vanlalruata House at Aizawl Venglai | 1.45 | Aizawl Road North Division | 20.03.23 | 17.04.23 | 100% | 1.45 |  |  | 100% | 1.45 | Completed | Spot Quotation
162 | Construction of Lowering & RCC Pavement near Pu Sangmawia (L) House at Aizawl Venglai | 1.25 | Aizawl Road North Division | 21.02.23 | 23.02.23 | 100% | 1.25 |  |  | 100% | 1.25 | Completed | Spot Quotation
163 | Construction of Chequrred tile near near Basketball Court at Aizawl Venglai | 1.49 | Aizawl Road North Division | 23.02.23 | 03.03.23 | 100% | 1.49 |  |  | 100% | 1.49 | Completed | Spot Quotation
RAMTHAR
164 | Construction of RCC Rectangular side drain with cover on Sihpui Taxi stand to Electric Vengthlang PCI at Ramthar | 9.6 | Aizawl Road North Division | 19.03.23 | 17.04.23 | 100% | 9.6 |  |  | 100% | 9.6 | Completed | Spot Quotation
165 | Construction of RCC Rectangular Cross drain with cover near David Malsawma House at Ramthar | 1.66 | Aizawl Road North Division | 27.03.23 | 21.04.23 | 100% | 1.66 |  |  | 100% | 1.66 | Completed | Spot Quotation
166 | Construction of Breast wall Below Pu K.Lalchawimawia House at Ramthar | 1.37 | Aizawl Road North Division | 21.03.23 | 25.03.23 | 100% | 1.37 |  |  | 100% | 1.37 | Completed | Spot Quotation
167 | Construction of PCC Pavement on Tetea Road | 2.81 | Aizawl Road North Division | 24.03.23 | 10.04.23 | 100% | 2.81 |  |  | 100% | 2.81 | Completed | Spot Quotation
168 | Construction of Retaining Wall near Pu Biakzaua House at Ramthar | 4.24 | Aizawl Road North Division | 06.03.23 | 14.03.23 | 100% | 4.24 |  |  | 100% | 4.24 | Completed | Spot Quotation
169 | Construction of Breast Wall Near C.Zothantluanga House at Ramthar | 1.53 | Aizawl Road North Division | 13.03.23 | 24.03.23 | 100% | 1.53 |  |  | 100% | 1.53 | Completed | Spot Quotation
170 | Construction of Chequrred tile and Hand railing near UPC (NEI) Church at Ramthar | 3.78 | Aizawl Road North Division | 03.03.23 | 23.03.23 | 100% | 3.78 |  |  | 100% | 3.78 | Completed | Spot Quotation
171 | Construction of Breast Wall on Pu Zothansanga Near UPC (MZ) Church Upper Galilie at Ramthar Veng at Ramthar | 3.52 | Aizawl Road North Division | 21.02.23 | 20.03.23 | 100% | 3.52 |  |  | 100% | 3.52 | Completed | Spot Quotation
172 | Construction of Retaining Wall Near Pu Lalhmunsiama House at Ramthar | 4.99 | Aizawl Road North Division | 17.02.23 | 13.03.23 | 100% | 4.99 |  |  | 100% | 4.99 | Completed | Spot Quotation
173 | Construction of Breast Wall Near SH.Lalkhama House at Ramthar | 1.51 | Aizawl Road North Division | 13.03.23 | 18.03.23 | 100% | 1.51 |  |  | 100% | 1.51 | Completed | Spot Quotation
174 | Construction of Retaining Wall Near Cfootpath Sihpui to upper Galilie at Ramthar | 2.63 | Aizawl Road North Division | 13.02.23 | 18.02.23 | 100% | 2.63 |  |  | 100% | 2.63 | Completed | Spot Quotation
175 | Construction of Retaining Wall Near Pu Laltlankima House at Ramthar | 2.93 | Aizawl Road North Division | 28.02.23 | 07.03.23 | 100% | 2.93 |  |  | 100% | 2.93 | Completed | Spot Quotation
176 | Construction of Step, Hand Railing and Widening near Tlangveng Taxi Stand at Ramthar | 2.44 | Aizawl Road North Division | 22.03.23 | 08.04.23 | 100% | 2.44 |  |  | 100% | 2.44 | Completed | Spot Quotation
177 | Construction of Widening and Breast Wall below Bishop House at Ramthar | 7.61 | Aizawl Road North Division | 24.02.23 | 18.03.23 | 100% | 7.61 |  |  | 100% | 7.61 | Completed | Spot Quotation
178 | Construction of Widening and Breast Wall Near Pu Lalbuanga House at Ramthar | 5.45 | Aizawl Road North Division | 13.03.23 | 01.04.23 | 100% | 5.45 |  |  | 100% | 5.45 | Completed | Spot Quotation
179 | Construction of RCC Pavement on Pu Thianghlima House to Pu B.Lalmalsawma House at Ramthar | 4.64 | Aizawl Road North Division | 06.03.23 | 13.03.23 | 100% | 4.64 |  |  | 100% | 4.64 | Completed | Spot Quotation
180 | Construction of Breast Wall Near Republic High School at Ramthar | 1.47 | Aizawl Road North Division | 27.02.23 | 04.03.23 | 100% | 1.47 |  |  | 100% | 1.47 | Completed | Spot Quotation
181 | Construction of Retaining Wall at Chainage 0.100 Kmp on Ramthar Cemetrey to Sihpui via Upper Galilie | 23.17 | Aizawl Road North Division | 06.02.23 | 22.03.23 | 100% | 23.17 |  |  | 100% | 23.17 | Completed | Spot Quotation
182 | Construction of Retaining Wall at Chainage 0.060 Kmp on Ramthar Cemetry to Sihpui via Upper Galilie Pu Lalbuanga House at Ramthar | 14.1 | Aizawl Road North Division | 13.02.23 | 17.04.23 | 100% | 14.1 |  |  | 100% | 14.1 | Completed | Spot Quotation
RAMTHAR NORTH
183 | Construction of RCC Rectangular side drain with cover on Electric Cemetry to Ruali Tuikhur at Ramthar North | 0.87 | Aizawl Road North Division | 15.02.23 | 27.02.23 | 100% | 0.87 |  |  | 100% | 0.87 | Completed | Spot Quotation
184 | Construction of Breast Wall on Tetea Road at Ramthar North | 1.43 | Aizawl Road North Division | 14.03.23 | 21.03.23 | 100% | 1.43 |  |  | 100% | 1.43 | Completed | Spot Quotation
185 | Construction of RCC Balcony near Ruali Tuikhur at Ramthar North | 4.71 | Aizawl Road North Division | 17.02.23 | 22.03.23 | 100% | 4.71 |  |  | 100% | 4.71 | Completed | Spot Quotation
186 | Construction of RCC Balcony on Tetea Road at Ramthar North | 5.4 | Aizawl Road North Division | 16.02.23 | 12.04.23 | 100% | 5.4 |  |  | 100% | 5.4 | Completed | Spot Quotation
187 | Construction of Retaining Wall on Tetea Road at Ramthar North | 11.42 | Aizawl Road North Division | 14.02.23 | 25.03.23 | 100% | 11.42 |  |  | 100% | 11.42 | Completed | Spot Quotation
188 | Construction of Retaining Wall on Near Electric Cemetry at Ramthar North | 7.77 | Aizawl Road North Division | 24.03.23 | 15.04.23 | 100% | 7.77 |  |  | 100% | 7.77 | Completed | Spot Quotation
SARON VENG
189 | Construction of RCC Link Drain with Cover at Saron Veng | 50 | Aizawl Road North Division | 21.03.23 | 30.05.23 | 100% | 50 |  |  | 100% | 50 | Completed | Spot Quotation
25
3. CONSTRUCTION AND UPGRADATION OF ROAD FROM TUITHIANG - CHHINGA VENG - ARMED VENG - CHITE, AIZAWL
190 | Construction of PCC Pavement on District Jail to Lower Armed Veng Road (Service Road) | 68 | Aizawl Road North Division | 14.01.23 | 25.02.23 | 100% | 68 |  |  | 100% | 68 | Completed | Spot Quotation
191 | Construction of Concrete Pavement on Dawrpui Cemetery Internal Road betweenn Pu Thangdanga's House to Lalkima Sailo Site Junction | 16 | Aizawl Road North Division | 23.01.23 | 11.02.23 | 100% | 16 |  |  | 100% | 16 | Completed | Spot Quotation
192 | Construction of Concrete Pavement on District Jail to CRPF Road | 16 | Aizawl Road North Division | 16.01.23 | 04.02.23 | 100% | 16 |  |  | 100% | 16 | Completed | Spot Quotation
193 | Construction of New Road from Pu Lalhmingliana Sailo House to Pu Siamphunga Lei at Tuithiang Veng | 50 | Aizawl Road North Division | 17.02.23 | 17.07.23 | 100% | 50 |  |  | 100% | 50 | Completed | Spot Quotation
[12 empty] | Completed | Spot Quotation
[12 empty] | Completed | Spot Quotation
[12 empty] | Completed | Spot Quotation
[12 empty] | Completed | Spot Quotation
[12 empty] | Completed | Spot Quotation
194 | Consrtuction of Concrete Pavement on C.P Road chite Veng | 50 | Aizawl Road North Division | 14.02.23 | 15.05.23 | 100% | 50 |  |  | 100% | 50 | Completed | Spot Quotation
[12 empty] | Completed | Spot Quotation
[12 empty] | Completed | Spot Quotation
[12 empty] | Completed | Spot Quotation
[12 empty] | Completed | Spot Quotation
195 | Construction of RCC Balcony on Bethany Road at Chhinga Veng | 50 | Aizawl Road North Division | 20.02.23 | 02.08.23 | 100% | 50 |  |  | 100% | 50 | Completed | Spot Quotation
196 | Construction of Retaining Wall at Armed Veng near Pu lalkima House | 22 | Aizawl Road North Division | 23.01.23 | 18.02.23 | 100% | 22 |  |  | 100% | 22 | Completed | Spot Quotation
11
4. CONSTRUCTION CHECK DAM AT THEIHAI LUI, ARMED VENG
197 | Counterfort Retaining Wall at Armed Veng | 41.22 | Aizawl Road North Division | [8 empty] | Not yet started
198 | Toe Walls at Armed Veng side | 31.44 | Aizawl Road North Division | [8 empty] | Not yet started
199 | Retaining Wall at Ramthar side | 30.21 | Aizawl Road North Division | [8 empty] | Not yet started
200 | Counterfort Retaining Wall at Canara Bank | 43.62 | Aizawl Road North Division | 24.04.23 |  | 100% | 43.62 |  |  | 100% | 43.62 | Completed | Spot Quotation
201 | Retaining Wall at Canara Bank Bridge | 23.06 | Aizawl Road North Division | [8 empty] | Not yet started
202 | Const.of Breast Wall on Bazar Bungkawn to Chite Road near 1st Battalion MAP One Gate Armed Veng | 4.93 | Aizawl Road North Division | 11.02.23 | 14.03.23 | 100% | 4.93 |  |  | 100% | 4.93 | Completed | Spot Quotation
203 | Construction of RCC Link Drain near Pu Phirthanga's House | 24.79 | Aizawl Road North Division | [8 empty] | Not yet started
204 | Const.of RCC Link Drain between Pu Lalrinsanga Hmar House to Pu Lalhuliana's House | 12.09 | Aizawl Road North Division | 04.09.23 |  | 10% |  | 10% |  | 20% |  | Work in progress | Spot Quotation
205 | Const.of RCC Link Drain between Pu Ralkapa's House to Pu Darchhunga's House | 11.65 | Aizawl Road North Division |  |  | 10 |  | 90% |  | 100% |  | Phy.Completed
206 | Const.of RCC Link Drain Pu Lalhmingthanga's House | 12.48 | Aizawl Road North Division | 02.08.23 | 30.08.23 | 100% | 12.48 |  |  | 100% | 12.48 | Completed | Spot Quotation
207 | Const.of RCC Link Drain Pu Lalhmingthanga's House | 13.87 | Aizawl Road North Division | 04.09.23 | 15.11.23 | 100% | 13.87 |  |  | 100% | 13.87 | Completed | Spot Quotation
208 | Const.of RCC Link Drain near Pu Rallianzuala's Land | 50.65 | Aizawl Road North Division | [8 empty] | Not yet started
SUB-DIVISION-II
209 | Construction of Link Drain from Lalzarliana at High School Veng at Zemabawk | 6.4 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 6.4 |  |  | 100% | 6.4 | Completed | Spot Quotation
210 | Construction of Masonry Step from Pi Zahmingthangi to Dr.Robert Khawlhring Residence at Zemabawk | 7.51 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 7.51 |  |  | 100% | 7.51 | Completed | Spot Quotation
211 | Const.of Link Drain at Mellimual 2 Tuikhur at Zemabawk | 6.4 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 6.4 |  |  | 100% | 6.4 | Completed | Spot Quotation
212 | Construction of Slab Culvert Near Vety Dispensary at Zemabawk | 8.42 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 8.42 |  |  | 100% | 8.42 | Completed | Spot Quotation
213 | Construction of Link drain Near Lalrinmawia Residence at Zemabawk | 4.06 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 4.06 |  |  | 100% | 4.06 | Completed | Spot Quotation
214 | Construction of Side Drain with Cover at Approach Road to Cancer Hospital, Zemabawk | 3.71 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 3.71 |  |  | 100% | 3.71 | Completed | Spot Quotation
215 | Construction of Slab Culvert Including Cross Drainage Dinthar Veng at Zemabawk | 2.03 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 2.03 |  |  | 100% | 2.03 | Completed | Spot Quotation
216 | Construction of U-Shape Side Drain with Cover near Zemabawk North Biak In | 4.24 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 4.24 |  |  | 100% | 4.24 | Completed | Spot Quotation
217 | Construction of Slab Culvert (2 Nos) at Berawlui to Thlanmual to Berawlui School | 12.18 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 12.18 |  |  | 100% | 12.18 | Completed | Spot Quotation
218 | Construction of Slab Culvert including Link Drain at Middle School Veng, Zemabawk | 27 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 27 |  |  | 100% | 27 | Completed | Spot Quotation
219 | Strengthening of Bethel Veng to High School Veng at Zemabawk | 36.7 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 36.7 |  |  | 100% | 36.7 | Completed | Spot Quotation
220 | Construction of of RCC Frame Retaining Wall Including Concrete Pavement on Approach Road to Zemabawk Thlanmual No.1 | 12 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 12 |  |  | 100% | 12 | Completed | Spot Quotation
221 | Construction of Rertaining Wall on Zemabawk Borth Field | 2.8 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 2.8 |  |  | 100% | 2.8 | Completed | Spot Quotation
222 | Construction of RCC Frame Retaining Wall Beneath Zemabawk Thlanmual | 9.9 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 9.9 |  |  | 100% | 9.9 | Completed | Spot Quotation
223 | Patch repiar & Seal Coating of approach road to cancer Hospital at Zemabawk North | 11.63 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 11.63 |  |  | 100% | 11.63 | Completed | Spot Quotation
224 | Widening & Improvement of Approach Road to Cancer Hospital at Zemabawk | 136.46 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 136.46 |  |  | 100% | 136.46 | Completed | Spot Quotation
225 | Widening and Construction of Retaining Wall at landslide prone area on Old Lunglei Road | 11.16 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 11.16 |  |  | 100% | 11.16 | Completed | Spot Quotation
226 | Construction of Retaining Wall near Urban Hospital at Zemabawk | 7.81 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 7.81 |  |  | 100% | 7.81 | Completed | Spot Quotation
227 | Concrete pavement of ANM to CMO at Zemabawk Vengthar Road | 19.72 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 19.72 |  |  | 100% | 19.72 | Phy.Completed | Spot Quotation
228 | Construction of Cross drain & PCC Vshape side drain on approach Zemabawk road | 3.6 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 3.6 |  |  | 100% | 3.6 | Completed | Spot Quotation
229 | Construction of Retaining Wall Beneath Urban hospital at Zemabawk | 7.81 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 7.81 |  |  | 100% | 7.81 | Completed | Spot Quotation
230 | Construction of Galili Veng to Vailui road upon Falkland | 7.1 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 7.1 |  |  | 100% | 7.1 | Completed | Spot Quotation
231 | Construction of Footpath and Retaining Wall on NH-54 near CRPF Camp at Zembawk | 46.57 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 46.57 |  |  | 100% | 46.57 | Completed | Spot Quotation
232 | Construction of Retaining Wall at below R.D Godown at Zemabawk | 10.6 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 10.6 |  |  | 100% | 10.6 | Completed | Spot Quotation
233 | Additional requirement for Construction Retaining Wall at the on-going construction of RCC Balcony Berawtlang approach road due to slide from uphill side | 21.2 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 21.2 |  |  | 100% | 21.2 | Completed | Spot Quotation
234 | Construction of RCC frame R/wall on approach road to seventh Day Adventist Church at Zemabawk | 12.72 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 12.72 |  |  | 100% | 12.72 | Completed | Spot Quotation
235 | Widening and Lowering of Sericulture to Thlanmual including conrete pavement & retaining Wall at Zemabawk North | 34.88 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 34.88 |  |  | 100% | 34.88 | Completed | Spot Quotation
236 | Concrete pavement of Kailiana road (balance Portion) | 32.93 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 32.93 |  |  | 100% | 32.93 | Completed | Spot Quotation
237 | Construction of Retaining Wall near Primary School at Zemabawk North | 2.09 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 2.09 |  |  | 100% | 2.09 | Completed | Spot Quotation
238 | Concrete pavement of Dinthar to Muthi Lui kawng including Masonry U-Shape Side Drain at Zemabawk North | 29.87 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 29.87 |  |  | 100% | 29.87 | Completed | Spot Quotation
239 | Construction of RCC Frame retaining wall including temporary side drain at Zemabawk North, Dinthar Veng | 21.2 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 21.2 |  |  | 100% | 21.2 | Completed | Spot Quotation
240 | Widening at portion and construction of Retaining Wall at Zemabawk North Dinthar Veng | 6.36 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 6.36 |  |  | 100% | 6.36 | Completed | Spot Quotation
241 | Concrete pavement of Bungbangla approach road | 10.05 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 10.05 |  |  | 100% | 10.05 | Completed | Spot Quotation
242 | Formation cutting only Berawlui Thlanmual to School at Berawlui | 0.53 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 0.53 |  |  | 100% | 0.53 | Completed | Spot Quotation
243 | Construction of Retaining Wall at Lungbial Zemabawk | 10.6 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 10.6 |  |  | 100% | 10.6 | Completed | Spot Quotation
244 | Contsruction of Protection work on Lungbial Tuikhur to lalram farm (Landslide areas) (3.Nos.) | 20.99 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 20.99 |  |  | 100% | 20.99 | Completed | Spot Quotation
245 | Construction of RCC Balcony at Lungbial | 30.18 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 30.18 |  |  | 100% | 30.18 | Completed | Spot Quotation
246 | Construction of RCC Frame Retaining Wall Including Concrete Pavement on Approach Road to Zemabawk thlanmual No.1 | 12 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 12 |  |  | 100% | 12 | Completed | Spot Quotation
247 | Construction of Link Drain, Culvert near primary School including PCC Concrete Pavement at Tuirial | 15.77 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 15.77 |  |  | 100% | 15.77 | Completed | Spot Quotation
248 | Concrete pavement of NH 54 to Tlangveng Kawng at Tuirial (Balalnce portion) | 9.5 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 9.5 |  |  | 100% | 9.5 | Completed | Spot Quotation
249 | Construction of RCC Concrete pavement of approach road to tuirial Lui | 14.6 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 14.6 |  |  | 100% | 14.6 | Completed | Spot Quotation
250 | Concrete pavement of approach road to Tuirial Airfield from NH-54 | 110 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 110 |  |  | 100% | 110 | Completed | Spot Quotation
251 | Profile Correction of Kutcha Road to Tuirial Airfield Mual thlang | 0.11 | Aizawl Road North Division | 24.04.23 | 18.05.23 | 100% | 0.11 |  |  | 100% | 0.11 | Completed | Spot Quotation
252 | Construction of PCC V shape Side drain on Muthi peng to Muthi Kawn | 10.93 | Aizawl Road North Division | 24.04.23 | 18.05.23 | 100% | 10.93 |  |  | 100% | 10.93 | Completed | Spot Quotation
253 | Construction of concrete pavement, retaining wall, PCC V shape drain & U shape drain at Muthi | 5.3 | Aizawl Road North Division | 24.04.23 | 18.05.23 | 100% | 5.3 |  |  | 100% | 5.3 | Completed | Spot Quotation
254 | Construction of PCC pavement of Chawngdailova House Hmingthansanga house, Muthi Vengthlang | 5.94 | Aizawl Road North Division | 24.04.23 | 18.05.23 | 100% | 5.94 |  |  | 100% | 5.94 | Completed | Spot Quotation
255 | Construction of Retaining wall near Lamhnai Tuikhur, Muthi | 11.93 | Aizawl Road North Division | 24.04.23 | 18.05.23 | 100% | 11.93 |  |  | 100% | 11.93 | Completed | Spot Quotation
256 | Construction of RCC Frame Retaining wall near Biakmawii residence at Muthi | 6.29 | Aizawl Road North Division | 24.04.23 | 18.05.23 | 100% | 6.29 |  |  | 100% | 6.29 | Completed | Spot Quotation
257 | Construction of PCC pavement of Sangnghinglove house to Engzami house, Muthi | 4.16 | Aizawl Road North Division | 24.04.23 | 18.05.23 | 100% | 4.16 |  |  | 100% | 4.16 | Completed | Spot Quotation
258 | Construction of Retaining wall on approach road to Muthi (1.800 kmp) | 7.5 | Aizawl Road North Division | 24.04.23 | 18.05.23 | 100% | 7.5 |  |  | 100% | 7.5 | Completed | Spot Quotation
259 | Strengthening of Approach road to LAD Complex Muanna Veng including drainage work (Balance portion) Bituminous pavement | 54.7 | Aizawl Road North Division | 24.04.23 | 19.05.23 | 100% | 54.7 |  |  | 100% | 54.7 | Completed | Spot Quotation
260 | PCC U shape side drain |  |  | 24.04.23 | 19.05.23 | 100% |  |  |  | 100% |  | Completed | Spot Quotation
261 | Concrete pavement of approach road to Muanna Veng Cemetary | 20.29 | Aizawl Road North Division | 24.04.23 | 19.05.23 | 100% | 20.29 |  |  | 100% | 20.29 | Completed | Spot Quotation
262 | Concrete pavement of approach road to YMA House at Muanna Veng | 8.12 | Aizawl Road North Division | 24.04.23 | 19.05.23 | 100% | 8.12 |  |  | 100% | 8.12 | Completed | Spot Quotation
263 | Junction improvement & strengthening of Zeda approach road including side drain, retaining walls at Zuangtui Resurfacing | 84.27 | Aizawl Road North Division | 24.04.23 | 19.05.23 | 100% | 84.27 |  |  | 100% | 84.27 | Completed | Spot Quotation
| Concrete pavement | 0 |  |  |  | 100% | - |  |  | 100% | - | Completed | Spot Quotation
264 | Concrete Pevement of Swan Industry to RK Lianzuala House at Zuangtui | 27.18 | Aizawl Road North Division | 24.04.23 | 19.05.23 | 100% | 27.18 |  |  | 100% | 27.18 | Completed | Spot Quotation
265 | Concrete Pavementof Zuangtui Vengthar road at Zuangtui | 39.82 | Aizawl Road North Division | 24.04.23 | 19.05.23 | 100% | 39.82 |  |  | 100% | 39.82 | Completed | Spot Quotation
266 | Construction of Retaining Wall at Zuangtui Industry Mual | 9.64 | Aizawl Road North Division | 24.04.23 | 19.05.23 | 100% | 9.64 |  |  | 100% | 9.64 | Completed | Spot Quotation
267 | Construction of Retaining Wall on approach road to Chhim Veng near Pi Ronghaki's House at Zuangtui | 8.48 | Aizawl Road North Division | 24.04.23 | 18.05.23 | 100% | 8.48 |  |  | 100% | 8.48 | Completed | Spot Quotation
268 | Earth work cutting, Construction of Retaining Wall, & Concrete flooring of Futsal Ground at Zuangtui Industry Mual | 63.02 | Aizawl Road North Division | 24.04.23 | 18.05.23 | 100% | 63.02 |  |  | 100% | 63.02 | Completed | Spot Quotation
269 | Concrete flooring of Futsal Ground at zuangtui | 22.94 | Aizawl Road North Division | 24.04.23 | 18.05.23 | 100% | 22.94 |  |  | 100% | 22.94 | Completed | Spot Quotation
270 | Construction of PCC Pavement on Zuangtui Vengthar (Balance Portion) | 31 | Aizawl Road North Division | 24.04.23 | 18.05.23 | 100% | 31 |  |  | 100% | 31 | Completed | Spot Quotation
271 | Construction of PCC V-Shape side drain on Zuangtui road to Thuampui Primary School | 3.5 | Aizawl Road North Division | 24.04.23 | 18.05.23 | 100% | 3.5 |  |  | 100% | 3.5 | Completed | Spot Quotation
272 | Construction of PCC V-shaped side drain near Pu Kama House, Laipuitlang | 0.37 | Aizawl Road North Division | 24.04.23 | 18.05.23 | 100% | 0.37 |  |  | 100% | 0.37 | Completed | Spot Quotation
273 | Construction of PCC V-shaped Side Drain near Pu Zakamlova House, Laipuitlang | 0.53 | Aizawl Road North Division | 24.04.23 | 18.05.23 | 100% | 0.53 |  |  | 100% | 0.53 | Completed | Spot Quotation
274 | Construction of PCC V-shaped Side Drain near Pu Lalengmawia House, Laipuitlang | 0.63 | Aizawl Road North Division | 24.04.23 | 18.05.23 | 100% | 0.63 |  |  | 100% | 0.63 | Completed | Spot Quotation
275 | Construction of PCC V-shaped Side Drain near Pu Marka House, Laipuitlang | 0.46 | Aizawl Road North Division | 24.04.23 | 18.05.23 | 100% | 0.46 |  |  | 100% | 0.46 | Completed | Spot Quotation
276 | Construction of Side Drain near Nazareth Hospital to DIET Junction at Chaltlang | 8.05 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 8.05 |  |  | 100% | 8.05 | Completed | Spot Quotation
277 | Construction of of Side Drain with Cover between H.Hiato House to high School, Chaltlang | 8 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 8 |  |  | 100% | 8 | Completed | Spot Quotation
278 | Construction of Retaining Wall at Chaltlang mear Pu Rophira's House | 4 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 4 |  |  | 100% | 4 | Completed | Spot Quotation
279 | DIET Junction improvement | 57.03 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 57.03 |  |  | 100% | 57.03 | Completed | Spot Quotation
280 | Construction of concrete Pavement of Chanmari Thlanmual Courtyard including junction Improvement (Sh: Seal Coating) | 2.35 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 2.35 |  |  | 100% | 2.35 | Completed | Spot Quotation
| (Sh: RCC Frame Retaining Wall) | 3.25 |  | 24.04.23 | 17.05.23 | 100% | 3.26 |  |  | 100% | 3.26 | Completed | Spot Quotation
| (Sh: Concrete Pavement) | 12.42 |  | 24.04.23 | 17.05.23 | 100% | 12.42 |  |  | 100% | 12.42 | Completed | Spot Quotation
281 | Const. of Protection Work for P&E Transformer at DIET Junction Chaltlang | 9.54 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 9.54 |  |  | 100% | 9.54 | Completed | Spot Quotation
282 | Const. of Concrete Pavement Chaltlang Lily Veng Cemetrery Road | 7.26 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 7.26 |  |  | 100% | 7.26 | Completed | Spot Quotation
283 | Const. of Retaing Wall at Chaltlang Lily Veng Cemetrery Road | 4.82 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 4.82 |  |  | 100% | 4.82 | Completed | Spot Quotation
284 | Const. of Railing wih chequered tiles at Chaltlang Dawrkawn | 8 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 8 |  |  | 100% | 8 | Completed | Spot Quotation
285 | Const. of Retaining Wall and Footpath at Chaltlang Veng Cemetery | 10 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 10 |  |  | 100% | 10 | Completed | Spot Quotation
286 | Improvement of Chaltlang Lily Veng to Chaltlang Link step near R.Lalropuia House | 5 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 5 |  |  | 100% | 5 | Completed | Spot Quotation
287 | Const. of approach road PCC & Side Drain from Chaltlang Dingdi Veng Turning Point to H.Lalluaia (L) House at Chaltlang Venglai | 16 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 16 |  |  | 100% | 16 | Completed | Spot Quotation
288 | Reconstruction of Chaltlang Lily Veng to Chaltlang Link Road near Lalthuthlungliana House | 8 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 8 |  |  | 100% | 8 | Completed | Spot Quotation
289 | Construction of Retaining Wall near Pu Ralkapa House, Laipuitlang | 1.71 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 1.71 |  |  | 100% | 1.71 | Completed | Spot Quotation
290 | Construction of Retaining Wall near Pu Kama House, Laipuitlang | 1.19 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 1.19 |  |  | 100% | 1.19 | Completed | Spot Quotation
291 | Construction of Masonry Step including Hand Railing near Pu Kama House, Laipuitlang | 1.47 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 1.47 |  |  | 100% | 1.47 | Completed | Spot Quotation
292 | Construction of Retaining Wall near Pu Duhzuala House, Laipuitlang | 2.61 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 2.61 |  |  | 100% | 2.61 | Completed | Spot Quotation
293 | Construction of Step in concrete over Link Drain including Railing near Community Hall, Laipuitlang | 4.05 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 4.05 |  |  | 100% | 4.05 | Completed | Spot Quotation
294 | Construction of Retaining Wall including hand Railing near Pu Rama House, Laipuitlang | 1.86 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 1.86 |  |  | 100% | 1.86 | Completed | Spot Quotation
295 | Construction of Retaining Wall including hand Railing near Pi Dawli House, Laipuitlang | 3.37 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 3.37 |  |  | 100% | 3.37 | Completed | Spot Quotation
296 | Construction of Retaining Wall near Jubilee Hall Laipuitlang | 1.56 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 1.56 |  |  | 100% | 1.56 | Completed | Spot Quotation
297 | Construction of Hand Railing near C.Zonunmawia House, Laipuitlang | 0.63 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 0.63 |  |  | 100% | 0.63 | Completed | Spot Quotation
298 | Const.of Retaining Wall at Chaltlang near T.Thangchungnunga (L) | 4 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 4 |  |  | 100% | 4 | Completed | Spot Quotation
299 | Const. of PCC U-Shape Side Drain near Pu Thanseia House, Bawngkawn | 0.3 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 0.3 |  |  | 100% | 0.3 | Completed | Spot Quotation
300 | Construction of PCC U-Shape Side Drain including Steel Railing near Pu Lalduhkima House, Bawngkawn | 5.52 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 5.52 |  |  | 100% | 5.52 | Completed | Spot Quotation
301 | Construction of step over Link Drain including Railing near K.Lalhlunchhungi residence at Bawngkawn | 18.42 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 18.42 |  |  | 100% | 18.42 | Completed | Spot Quotation
302 | Construction of Link Drain Cover near Pu R.Romawia House at Bawngkawn | 4 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 4 |  |  | 100% | 4 | Completed | Spot Quotation
303 | Construction of Side Drain near Pu EL Bethela House at Bawngkawn | 0.4 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 0.4 |  |  | 100% | 0.4 | Completed | Spot Quotation
304 | Construction of Side Drain near Pu Salemthara House at Bawngkawn | 1.3 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 1.3 |  |  | 100% | 1.3 | Completed | Spot Quotation
305 | Const. of Concrete Pavement of Brigade Slaughter House Road Bawngkawn | 58.3 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 58.3 |  |  | 100% | 58.3 | Completed | Spot Quotation
306 | Construction of Brigade Internal Road at Bawngkawn | 14.84 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 14.84 |  |  | 100% | 14.84 | Completed | Spot Quotation
307 | Construction of Steel Railing near Pu Rintluanga House, Bawngkawn | 2.18 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 2.18 |  |  | 100% | 2.18 | Completed | Spot Quotation
308 | Construction of Step at Zotui Kawng at Bawngkawn | 2 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 2 |  |  | 100% | 2 | Completed | Spot Quotation
309 | Construction of Step near PC Mawia House, Bawngkawn | 11 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 11 |  |  | 100% | 11 | Completed | Spot Quotation
310 | Construction of Step and Hand railing at Shalom Veng | 8 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 8 |  |  | 100% | 8 | Completed | Spot Quotation
311 | Construction RCC Balcony at YMA Zampuimanga | 5 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 5 |  |  | 100% | 5 | Completed | Spot Quotation
312 | Construction of Step near Ramdinthara Tuikhur | 2 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 2 |  |  | 100% | 2 | Completed | Spot Quotation
313 | Const of Approach Road to Helipad from Bawngkawn Shalom Veng | 16 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 16 |  |  | 100% | 16 | Completed | Spot Quotation
314 | PCC Flooring near Upa Chaldailova House, Bawngkawn | 3 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 3 |  |  | 100% | 3 | Completed | Spot Quotation
315 | Construction of Step on Zotui Kawng | 2 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 2 |  |  | 100% | 2 | Completed | Spot Quotation
316 | Const. of Approach Road from JK Manga House to Thlanmual Kawng | 10 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 10 |  |  | 100% | 10 | Completed | Spot Quotation
317 | Const. of RCC Balcony on Approach Road to Bawngkawn Cemetry | 41.59 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 41.59 |  |  | 100% | 41.59 | Completed | Spot Quotation
318 | Const. of Masonry U-Shape Side Drain at Thuampui Internal Road | 4.24 | Aizawl Road North Division | 24.04.23 | 24.05.23 | 100% | 4.24 |  |  | 100% | 4.24 | Completed | Spot Quotation
319 | Construction of Side Drain with cover at Zemabawk North Presbyterian Church Courtyard | 3.71 | Aizawl Road North Division | 24.04.23 | 24.05.23 | 100% | 3.71 |  |  | 100% | 3.71 | Completed | Spot Quotation
320 | Const. of Culvert Side Drain & RCC Frame Retaining Wall on Approach Road to Thuampui Cemetry | 11.34 | Aizawl Road North Division | 24.04.23 | 24.05.23 | 100% | 11.34 |  |  | 100% | 11.34 | Completed | Spot Quotation
321 | Concrete Pavement & Drainage works on Thuampui PRIMARY School to Zuangtui Vengthar (Balance Portion ) | 53.57 | Aizawl Road North Division | 24.04.23 | 24.05.23 | 100% | 53.57 |  |  | 100% | 53.57 | Completed | Spot Quotation
322 | Const. of Retaining Wall at 8.040Kmp on Thuampui - selesih Road | 9.95 | Aizawl Road North Division | 24.04.23 | 24.05.23 | 100% | 9.95 |  |  | 100% | 9.95 | Completed | Spot Quotation
323 | Const. of Concrete Pavement Approach Road to PB Vanlalauva Camping Centre at Thuampui Selesih Road (Gospel Thunder Team) | 21.2 | Aizawl Road North Division | 24.04.23 | 24.05.23 | 100% | 21.2 |  |  | 100% | 21.2 | Completed | Spot Quotation
324 | Pavement of Thuampui Helipad | 24 | Aizawl Road North Division | 03.04.23 | 12.05.23 | 100% | 24 |  |  | 100% | 24 | Completed | Spot Quotation
325 | Construction of RCC Balcony on Durtlang Leitan to Thuampui Selesih Road at Ch:1.840 Kmp | 100.59 | Aizawl Road North Division | 24.04.23 | 24.05.23 | 60% | 100.59 | 40% |  | 100% | 100.59 | Phy.Completed | Spot Quotation
326 | Construction of Retaining Wall on Thuampui to Selesih Road at Ch:4.350 Kmp | 4 | Aizawl Road North Division | 24.04.23 | 24.05.23 | 100% | 4 |  |  | 100% | 4 | Completed | Spot Quotation
327 | Clearing of Landslip under Aizawl Road North Division | 9.2 | Aizawl Road North Division | 24.04.23 | 24.05.23 | 100% | 9.2 |  |  | 100% | 9.2 | Completed | Spot Quotation
328 | Seal Coating of Thuampui Cemetry Road | 29.83 | Aizawl Road North Division | 24.04.23 | 24.05.23 | 100% | 29.83 |  |  | 100% | 29.83 | Completed | Spot Quotation
329 | Construction of Retaining Wall at Salvation Army Turning Point, Thuampui | 3.94 | Aizawl Road North Division | 24.04.23 | 24.05.23 | 100% | 3.94 |  |  | 100% | 3.94 | Completed | Spot Quotation
330 | Concrete Pavement of Govt. Welfare Road at Thuampui | 37.94 | Aizawl Road North Division | 24.04.23 | 24.05.23 | 100% | 37.94 |  |  | 100% | 37.94 | Completed | Spot Quotation
331 | Earthwork Cutting, Construction of Retaining Wall & PCC Flooring of Futsal Ground at Thuampui | 51 | Aizawl Road North Division | 24.04.23 | 24.05.23 | 100% | 51 |  |  | 100% | 51 | Completed | Spot Quotation
332 | Construction of Approach Road to Thuampui Vengthar at Thuampui | 18.61 | Aizawl Road North Division | 24.04.23 | 24.05.23 | 100% | 18.61 |  |  | 100% | 18.61 | Completed | Spot Quotation
333 | Construction of Road below Thuampui Presbyterian Church | 15.9 | Aizawl Road North Division | 24.04.23 | 24.05.23 | 100% | 15.9 |  |  | 100% | 15.9 | Completed | Spot Quotation
334 | Concrete Pavement of liansailova Road, Thuampui | 26.97 | Aizawl Road North Division | 24.04.23 | 24.05.23 | 100% | 26.97 |  |  | 100% | 26.97 | Completed | Spot Quotation
335 | Construction of Gallery including Side Drain at Falkland | 6.9 | Aizawl Road North Division | 24.04.23 | 24.05.23 | 100% | 6.9 |  |  | 100% | 6.9 | Completed | Spot Quotation
336 | Const. of Masonry Link Drain near Mizoram UPC Chuech at Falkland | 5.32 | Aizawl Road North Division | 24.04.23 | 24.05.23 | 100% | 5.32 |  |  | 100% | 5.32 | Completed | Spot Quotation
337 | Seal Coating of Hebrai Veng at Falkland | 23.74 | Aizawl Road North Division | 24.04.23 | 24.05.23 | 100% | 23.74 |  |  | 100% | 23.74 | Completed | Spot Quotation
338 | Construction of Retaining Wall on Tuikhur thlang at Falkland East including Masonry Cross Drain | 11.32 | Aizawl Road North Division | 24.04.23 | 24.05.23 | 100% | 11.32 |  |  | 100% | 11.32 | Completed | Spot Quotation
339 | Concrete Pavement at Falkland Veng | 15.27 | Aizawl Road North Division | 24.04.23 | 24.05.23 | 100% | 15.27 |  |  | 100% | 15.27 | Completed | Spot Quotation
340 | Construction of Step at Falkland Cemetry | 4.77 | Aizawl Road North Division | 24.04.23 | 24.05.23 | 100% | 4.77 |  |  | 100% | 4.77 | Completed | Spot Quotation
341 | Construction of Thlanmual No. 1 Shed at Falkland | 5.3 | Aizawl Road North Division | 24.04.23 | 24.05.23 | 100% | 5.3 |  |  | 100% | 5.3 | Completed | Spot Quotation
342 | Concrete Pavement of Peniel Road at Falkland | 13 | Aizawl Road North Division | 24.04.23 | 24.05.23 | 100% | 13 |  |  | 100% | 13 | Completed | Spot Quotation
343 | Bituminous pavement of Falkland East internal Road | 15 | Aizawl Road North Division | 03.04.23 | 12.05.23 | 100% | 15 |  |  | 100% | 15 | Completed | Spot Quotation
344 | Patch repair and Seal Coating of Middle School | 19.88 | Aizawl Road North Division | 03.04.23 | 12.05.23 | 100% | 19.88 |  |  | 100% | 19.88 | Completed | Spot Quotation
345 | Improvement of Approach Road to Falkland East Junction (Sh:Construction of RCC Framed Structure Retaining Wall) | 4.72 | Aizawl Road North Division | 03.04.23 | 12.05.23 | 100% | 4.72 |  |  | 100% | 4.72 | Completed | Spot Quotation
346 | Improvement of Approach Road to Falkland East Junction (Sh:Pavement) | 2.79 | Aizawl Road North Division | 03.04.23 | 12.05.23 | 100% | 2.79 |  |  | 100% | 2.79 | Completed | Spot Quotation
347 | Const. of Link Drain Near Lalngamliana House to Sihphir Venglai | 6.96 | Aizawl Road North Division | 03.04.23 | 12.05.23 | 100% | 6.96 |  |  | 100% | 6.96 | Completed | Spot Quotation
348 | Construction of Concrete Pavement Link road from Sihphir Kawnveng to Khamrang Road (i/c Seal Coating of Sihphir Bypass Road via Selesih | 42.4 | Aizawl Road North Division | 03.04.23 | 10.05.23 | 100% | 42.4 |  |  | 100% | 42.4 | Completed | Spot Quotation
349 | Construction of PCC V-Shape Side Drain on Sihphir Lower Lane, Sihphir Venghlun | 1 | Aizawl Road North Division | 24.04.23 | 16.03.23 | 100% | 1 |  |  | 100% | 1 | Completed | Spot Quotation
350 | Construction of Link Drain including extention of Culvert Near Pu Lalruatvela House, Sihphir Venghlun | 2.98 | Aizawl Road North Division | 24.04.23 | 15.05.23 | 100% | 2.98 |  |  | 100% | 2.98 | Completed | Spot Quotation
351 | Construction of Link Drain near Pu Lalngamliana House to Sihphir Venglai Biak In, Sihphir (Balance) | 5.3 | Aizawl Road North Division | 24.04.23 | 15.05.23 | 100% | 5.3 |  |  | 100% | 5.3 | Completed | Spot Quotation
352 | Const. of Cross Drainage, Passing place on Approach Road to Nausel | 5.89 | Aizawl Road North Division | 24.04.23 | 15.05.23 | 100% | 5.89 |  |  | 100% | 5.89 | Completed | Spot Quotation
353 | Construction of PCC V-Shape Side Drain on Nausel Road | 10.6 | Aizawl Road North Division | 24.04.23 | 15.05.23 | 100% | 10.6 |  |  | 100% | 10.6 | Completed | Spot Quotation
354 | Construction of Retaining Wall Sihphir Bypass Road | 15.03 | Aizawl Road North Division | 24.04.23 | 15.05.23 | 100% | 15.03 |  |  | 100% | 15.03 | Completed | Spot Quotation
355 | Concrete Pavement of Approach Road to Lalbiaki Residence to YMA Park at Sihphir Hmar Veng | 19.89 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 19.89 |  |  | 100% | 19.89 | Completed | Spot Quotation
356 | Widening of Approach Road to SBI from Sihphir Lower lane Beneath Salvation Army Church | 7.89 | Aizawl Road North Division | 24.04.23 | 15.05.23 | 100% | 7.89 |  |  | 100% | 7.89 | Completed | Spot Quotation
357 | Construction of PCC Pavement High Atitude panna kawng | 16.23 | Aizawl Road North Division | 24.04.23 | 15.05.23 | 100% | 16.23 |  |  | 100% | 16.23 | Completed | Spot Quotation
358 | Constriction of Retaining Wall including Link Drain near K.Lalengzauva house at Sihphir Venghlun | 11.32 | Aizawl Road North Division | 24.04.23 | 15.05.23 | 100% | 11.32 |  |  | 100% | 11.32 | Completed | Spot Quotation
359 | Construction of Retaining Wall near Pi Remthangi Residence on Nausel Road, Sihphir Venghlun | 14.79 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 14.79 |  |  | 100% | 14.79 | Completed | Spot Quotation
360 | Concrete Pavement of Approach Road to Sihphir Venghlun Cemetry | 10.06 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 10.06 |  |  | 100% | 10.06 | Completed | Spot Quotation
361 | Concrete Pavement of Sihphir Venghlun Khawhnuai to Multipurpose Hall | 54.59 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 54.59 |  |  | 100% | 54.59 | Completed | Spot Quotation
362 | Concrete Pavement of Nausel Field Thlang | 12.23 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 12.23 |  |  | 100% | 12.23 | Completed | Spot Quotation
363 | Construction of Slab Culvert from Sihphir to Khamrang Road | 21.2 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 21.2 |  |  | 100% | 21.2 | Completed | Spot Quotation
364 | Construction of RCC V-Shape Side Drain on Durtlang Leitan | 3.17 | Aizawl Road North Division | 24.04.23 | 18.05.23 | 100% | 3.17 |  |  | 100% | 3.17 | Completed | Spot Quotation
365 | Construction of Masonry Cross Drain with Cover near Leitan 'S' Presbyterian Church | 2.61 | Aizawl Road North Division | 24.04.23 | 18.05.23 | 100% | 2.61 |  |  | 100% | 2.61 | Completed | Spot Quotation
366 | Construction of U-Shape Side Drain on BSNL Junction near Pu Rinawma House, Durtlang North | 4 | Aizawl Road North Division | 24.04.23 | 18.05.23 | 100% | 4 |  |  | 100% | 4 | Completed | Spot Quotation
367 | Extension of RCC Slab Culvert at Arbai Veng, Durtlang | 1.5 | Aizawl Road North Division | 24.04.23 | 18.05.23 | 100% | 1.5 |  |  | 100% | 1.5 | Completed | Spot Quotation
368 | Construction of RCC Slab Culvert between Pi Saii and Pi Purni House, Durtlang Leitan | 5.25 | Aizawl Road North Division | 24.04.23 | 18.05.23 | 100% | 5.25 |  |  | 100% | 5.25 | Completed | Spot Quotation
369 | Concrete Flooring, Drain with Cover & RCC Balcony from Zuangtui road to Pu Lalhmachhuana's House at Durtlang Venglai | 22.36 | Aizawl Road North Division | 24.04.23 | 18.05.23 | 80% | 22.36 |  |  | 80% | 22.36 | Work in Progress | Spot Quotation
370 | Construction of Step with Cheqered Tile including Railing near Pi Ngurmawii, Durtlang Leitan | 8 | Aizawl Road North Division | 24.04.23 | 18.05.23 | 100% | 8 |  |  | 100% | 8 | Completed | Spot Quotation
371 | Constrution of Retaining Wall near Prsbyterian Church, Dutlang North | 15 | Aizawl Road North Division | 24.04.23 | 18.05.23 | 100% | 15 |  |  | 100% | 15 | Completed | Spot Quotation
382 | Constrution of Retaining Wall No.1 at Arbai Peng, Durtlang | 2.83 | Aizawl Road North Division | 24.04.23 | 18.05.23 | 100% | 2.83 |  |  | 100% | 2.83 | Completed | Spot Quotation
383 | Constrution of Retaining Wall No.2 at Arbai Peng, Durtlang | 5.67 | Aizawl Road North Division | 24.04.23 | 18.05.23 | 100% | 5.67 |  |  | 100% | 5.67 | Completed | Spot Quotation
374 | Widening near Leitan's Presbyterian Church, Durtlang | 2.73 | Aizawl Road North Division | 24.04.23 | 18.05.23 | 100% | 2.73 |  |  | 100% | 2.73 | Completed | Spot Quotation
375 | PCC Pavement near Zakianglova House, Durtlang North | 4 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 4 |  |  | 100% | 4 | Completed | Spot Quotation
376 | Constrution of Retaining Wall Unit-I, Durtlang Leitan | 3.6 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 3.6 |  |  | 100% | 3.6 | Completed | Spot Quotation
377 | Constrution of Retaining Wall Unit-I, Durtlang Leitan | 0.82 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 0.82 |  |  | 100% | 0.82 | Completed | Spot Quotation
378 | Constrution of Retaining Wall Unit-I, Durtlang Leitan | 2.69 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 2.69 |  |  | 100% | 2.69 | Completed | Spot Quotation
379 | Constrution of Retaining Wall Unit-I, Durtlang Leitan | 2.8 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 2.8 |  |  | 100% | 2.8 | Completed | Spot Quotation
380 | PCC Pavement Zion Veng to Suaka Veng at Durtlang | 3 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 3 |  |  | 100% | 3 | Completed | Spot Quotation
381 | PCC Pavement Upper SL Road at Durtlang | 2.5 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 2.5 |  |  | 100% | 2.5 | Completed | Spot Quotation
382 | PCC Pavement Upper SL Road at Durtlang | 2.5 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 2.5 |  |  | 100% | 2.5 | Completed | Spot Quotation
383 | PCC Pavement on Local Council Road, Durtlang | 8 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 8 |  |  | 100% | 8 | Completed | Spot Quotation
384 | PCC Pavement on Chhingtei Road, Durtlang | 8 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 8 |  |  | 100% | 8 | Completed | Spot Quotation
385 | Construction of Kawmzawl to Centenary Road at durtlang including RCC pavement | 8 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 8 |  |  | 100% | 8 | Completed | Spot Quotation
386 | RCC Pavement at Lanu Road, Mizoram UPC to Presbyterian Chucrh at Suaka Veng, Durtlang | 8 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 8 |  |  | 100% | 8 | Completed | Spot Quotation
387 | RCC pavement at Selesih | 8 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 8 |  |  | 100% | 8 | Completed | Spot Quotation
388 | Construction of Slab Culvert near Pu Thawmtea's house | 7 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 7 |  |  | 100% | 7 | Completed | Spot Quotation
389 | Improvement of Y-Road Junction | 5.44 | Aizawl Road North Division | 03.04.23 | 10.05.23 | 100% | 5.44 |  |  | 100% | 5.44 | Completed | Spot Quotation
390 | Improvement of Y-Road near Pu Sajjal Residence | 0.96 | Aizawl Road North Division | 03.04.23 | 10.05.23 | 100% | 0.96 |  |  | 100% | 0.96 | Completed | Spot Quotation
391 | Pavement of Sihphir By-pass Road | 4.41 | Aizawl Road North Division | 03.04.23 | 10.05.23 | 100% | 4.41 |  |  | 100% | 4.41 | Completed | Spot Quotation
392 | Imrpvement of Road Profile and PCC Pavement at Falkland | 2.42 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 2.42 |  |  | 100% | 2.42 | Completed | Spot Quotation
393 | Construction of PCC V Shape side drain near Pu BM-a House | 0.3 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 0.3 |  |  | 100% | 0.3 | Completed | Spot Quotation
394 | Construction of Hand Railing near Papuia House | 0.72 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 0.72 |  |  | 100% | 0.72 | Completed | Spot Quotation
395 | Construction of Hand Railing near Chhunglawmi House at Durtlang Leitan | 3.7 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 3.7 |  |  | 100% | 3.7 | Completed | Spot Quotation
396 | Construction of Hand Railing Pu Malsawma House to Upa Zairemmawia House at Zotui Veng Durtlang | 2.65 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 2.65 |  |  | 100% | 2.65 | Completed | Spot Quotation
397 | Imrprovement of Bethel veng road at zemabawk, Aizawl in Mizoram for the the year 2022-2023 | 318 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 65% | 168.53 |  |  | 65% | 168.53 | Work in Progress | Spot Quotation
398 | Imrprovement of Thuampui-Selesih road (uoto 5.120 Km)Aiawl in Mizoram for the the year 2022-2024 | 370 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 366.79 |  |  | 100% | 366.79 | Phy.Completed | Spot Quotation
399 | Construction of Side Drain with cover at zemabawk North Presbyterian kawt | 12 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 12 |  |  | 100% | 12 | Completed | Spot Quotation
SUB DIVISION-III
Construction and Upgradation of connectivity from Kangthelhkawn - Ainawn - Luangmual by creating a new alternative road
400 | Repair of culvert wing wall near Mimi's House on Chhangurkawn to Govt.Complex | 1.27 | Aizawl Road North Division | 29.03.23 | 09.05.23 | 100% | 1.27 |  |  | 100% | 1.27 | Completed | Spot Quotation
401 | Improvement and Widening of approach road to MPRO Quarter (Sh: Construction of Pavement) | 75.88 | Aizawl Road North Division | 04.04.23 | 09.05.23 | 100% | 75.88 |  |  | 100% | 75.88 | Completed | Spot Quotation
402 | Improvement and Widening of approach road to MPRO Quarter (Sh: 1. Construction of Slab Culvert @ ch.0.050 Kmp | 3.51 | Aizawl Road North Division | 20.04.23 | 13.05.23 | 100% | 3.51 |  |  | 100% | 3.51 | Completed | Spot Quotation
403 | 2. Construction of Slab Culvert @ ch.0.510 Kmp | 3.5 | Aizawl Road North Division | 20.04.23 | 13.05.23 | 100% | 3.5 |  |  | 100% | 3.5 | Completed | Spot Quotation
404 | 3. Construction of Slab Culvert @ ch.0.650 Kmp | 3.52 | Aizawl Road North Division | 20.04.23 | 13.05.23 | 100% | 3.52 |  |  | 100% | 3.52 | Completed | Spot Quotation
405 | 4. Construction of Breast Wall @ ch.0.550 Kmp | 5.51 | Aizawl Road North Division | 20.04.23 | 13.05.23 | 100% | 5.51 |  |  | 100% | 5.51 | Completed | Spot Quotation
406 | 5. Construction of Breast Wall @ ch.0.410 Kmp | 8.06 | Aizawl Road North Division | 20.04.23 | 13.05.23 | 100% | 8.06 |  |  | 100% | 8.06 | Completed | Spot Quotation
407 | 6. Construction of Link Drain | 8.4 | Aizawl Road North Division | 20.04.23 | 13.05.23 | 100% | 8.4 |  |  | 100% | 8.4 | Completed | Spot Quotation
408 | 7. Construction of V-Shape side drain | 2.01 | Aizawl Road North Division | 20.04.23 | 13.05.23 | 100% | 2.01 |  |  | 100% | 2.01 | Completed | Spot Quotation
409 | Construction of RCC Frame struction Retaining Wall & Hume pipe Culvert with link drain on Approach Road to Govt.Housing Complex, at Luangmual at Ch 0.100Kmp Sh: 1. Retaining Wall | 14.03 | Aizawl Road North Division | 29.03.23 | 15.05.23 |  | 14.03 | 100% |  | 100% | 14.03 | Not Yet Started
410 | 2. Humne Pipe Culvert | 3.62 | Aizawl Road North Division | 29.03.23 | 15.05.23 | 100% | 3.62 |  |  | 100% | 3.62 | Completed | Spot Quotation
411 | 3. Linked Drain | 4.77 | Aizawl Road North Division | 29.03.23 | 15.05.23 |  | 4.77 | 100% |  | 100% | 4.77 | Completed
412 | Construction of Breast Wall near Pu Lalrinawma House at Luangmual | 5.08 | Aizawl Road North Division | 27.02.23 | 04.05.23 | 100% | 5.08 |  |  | 100% | 5.08 | Completed | Spot Quotation
413 | Construction of Road at Ainawn Veng, Aizawl Sh: 1. Earth Work Formation cutting | 41.17 | Aizawl Road North Division | 19.04.23 | 11.05.23 | 100% | 41.17 |  |  | 100% | 41.17 | Completed | Spot Quotation
414 | 2. Construction of RCC Slab Culvert Type-I | 13.58 | Aizawl Road North Division | 19.04.23 | 11.05.23 | 100% | 13.58 |  |  | 100% | 13.58 | Completed | Spot Quotation
415 | 3. Slab-Culvert-II | 16.79 | Aizawl Road North Division | 19.04.23 | 11.05.23 | 100% | 16.79 |  |  | 100% | 16.79 | Completed | Spot Quotation
416 | Construction of road at Chawnpui, Aizawl Sh: 1. Earth Work Formation cutting | 38.02 | Aizawl Road North Division | 03.04.23 | 03.05.23 | 100% | 38.02 |  |  | 100% | 38.02 | Completed | Spot Quotation
417 | 2. Construction og RCC Slab Vulvert Type-I | 13.57 | Aizawl Road North Division | 03.04.23 | 03.05.23 | 100% | 13.57 |  |  | 100% | 13.57 | Completed | Spot Quotation
418 | 3. Construction of TCC Slab Culvert Type-II | 8.4 | Aizawl Road North Division | 03.04.23 | 03.05.23 | 100% | 8.4 |  |  | 100% | 8.4 | Completed | Spot Quotation
419 | Resurfaccing of Kangthlehkawn to High Court (0.000 to 1.830 Kmp) | 59.29 | Aizawl Road North Division | 03.04.23 | 09.05.23 | 100% | 59.29 |  |  | 100% | 59.29 | Completed | Spot Quotation
420 | Const. of Approach Road (RCC Pavement) to Chhimveng Presby. Church at Ainawn Veng | 31.76 | Aizawl Road North Division | 03.04.23 | 09.05.23 | 100% | 31.76 |  |  | 100% | 31.76 | Completed | Spot Quotation
Construction of Upgradation of Road from Dawrpui Vengthar - Vaivakawn - Zotlang - MZU
421 | Construction of Link Drain near P/S at Vaivakawn | 13.92 | Aizawl Road North Division | 23.03.23 | 12.05.23 | 100% | 13.92 |  |  | 100% | 13.92 | Completed | Spot Quotation
422 | RCC Link Drain with Cover Step K.Buanga's House approach to NH-06, Vaivakawn | 25.42 | Aizawl Road North Division | 04.04.23 | 18.08.23 | 100% | 25.42 |  |  | 100% | 25.42 | Completed | Spot Quotation
423 | Rectangular Side Drain with cover near Salvation Army Church at k.Zamawia's House to MZU Road including Cross Drain cover, Vaivakawn | 11.55 | Aizawl Road North Division | 29.03.23 | 12.05.23 | 100% | 11.55 |  |  | 100% | 11.55 | Completed | Spot Quotation
424 | Const. of RCC Mini Bridge near Pi Malsawma's House (Dam veng) | 14.82 | Aizawl Road North Division | 29.03.23 | 10.06.23 | 100% | 14.82 |  |  | 100% | 14.82 | Completed | Spot Quotation
425 | Const. of RCC Foot path near Presbyterian Pastor Quarter to Zarkawt approach road at Dawrpui Vengthar | 15.96 | Aizawl Road North Division | 29.03.23 | 12.05.23 | 100% | 15.96 |  |  | 100% | 15.96 | Completed | Spot Quotation
426 | RCC approach road to Vanlalzuiliana's House Sh: 1. Construction of Rigid Pavement | 9.21 | Aizawl Road North Division | 29.03.23 | 16.06.23 | 100% | 9.21 |  |  | 100% | 9.21 | Completed | Spot Quotation
| 2. Construction of V-Shaped Side Drain | 2.22 | Aizawl Road North Division | 29.03.23 | 16.06.23 | 100% | 2.22 |  |  | 100% | 2.22 | Completed | Spot Quotation
427 | Improvement of road Zotlang, Aizawl Sh: 1.Earth Work Widening of existing road | 9 | Aizawl Road North Division | 28.03.23 | 11.05.23 | 100% | 9 |  |  | 100% | 9 | Completed | Spot Quotation
| 2. Construction of Retaining Wall | 28.52 | Aizawl Road North Division | 28.03.23 | 11.05.23 | 100% | 28.52 |  |  | 100% | 28.52 | Completed | Spot Quotation
| 3. Rigid Pavement | 5.58 | Aizawl Road North Division | 28.03.23 | 11.05.23 | 100% | 5.58 |  |  | 100% | 5.58 | Completed | Spot Quotation
428 | Road Widening and R/Wall at Pu Rosanga House to Neitumi House, Zohnuai Vaivakawn Sh: Earthwork | 5.41 | Aizawl Road North Division | 03.04.23 |  | 100% | 5.41 |  |  | 100% | 5.41 | Completed | Spot Quotation
| 2. Construction of Slab Culvert @ ch.0.115 Kmp | 3.5 | Aizawl Road North Division | 03.04.23 |  | 100% | 3.5 |  |  | 100% | 3.5 | Completed | Spot Quotation
| 3. Construction of Breast wall | 24.97 | Aizawl Road North Division | 03.04.23 |  | 100% | 24.97 |  |  | 100% | 24.97 | Completed | Spot Quotation
429 | Construction og Retaining Wall on Electric Veng Cemetery Road Sh: 1. Construction og Retaining Wall Section - 1 | 9.95 | Aizawl Road North Division | 29.03.23 | 26.06.23 | 100% | 9.95 |  |  | 100% | 9.95 | Completed | Spot Quotation
| 2. Construction og Retaining Wall Section - 2 | 4.76 | Aizawl Road North Division | 29.03.23 | 26.06.23 | 100% | 4.76 |  |  | 100% | 4.76 | Completed | Spot Quotation
| 3. Construction og Retaining Wall Section - 3 | 9.32 | Aizawl Road North Division | 29.03.23 | 26.06.23 | 100% | 9.32 |  |  | 100% | 9.32 | Completed | Spot Quotation
430 | Construction of Step near Seventh Day Church to Dosangvunga (L) House at Electrict Veng Sh: Construction of Step | 13.9 | Aizawl Road North Division | 29.03.23 | 26.06.23 | 100% | 13.9 |  |  | 100% | 13.9 | Completed | Spot Quotation
431 | Construction of Step in concrete over Link Drain including Railing near Presbyterian Jubilee Hall, Laipuitlang | 6.63 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 6.63 |  |  | 100% | 6.63 | Completed | Spot Quotation
Construction and Upgradation of Road from Chanmari West - Hunthar - Edenthar - Rangvamual
432 | Pot Hole Repair & Resurfacing and Seal Coating of Chanmari West to NH-54 | 11.01 | Aizawl Road North Division | 29.03.23 | 09.05.23 | 100% | 5.51 |  | 5.5 | 100% | 11.01 | Completed | Spot Quotation
433 | Pot Hole Repair & Resurfacing and Seal Coating of Chanmari West to Vaivakawn Road (0.000 - 0.550Kms) | 16.93 | Aizawl Road North Division | 29.03.23 | 09.05.23 | 100% | 16.93 |  |  | 100% | 16.93 | Completed | Spot Quotation
434 | Hole Repair & Resurfacing and Seal Coating of edenthar internal (0.000-1.175 Kms) | 15.25 | Aizawl Road North Division | 29.03.23 | 09.05.23 | 100% | 15.25 |  |  | 100% | 15.25 | Completed | Spot Quotation
435 | Pot Hole Repair & Resurfacing and Seal Coating of Bt Bakery to turning Point via Middle School at Hunthar (0.000 - 0.175Kms) | 10.16 | Aizawl Road North Division | 29.03.23 | 09.05.23 | 100% | 10.16 |  |  | 100% | 10.16 | Completed | Spot Quotation
436 | Pot Hole Repair & Resurfacing and Seal Coating of Edenthar Internal (0.000-1.175 Kms) | 17.46 | Aizawl Road North Division | 29.03.23 | 09.05.23 | 100% | 17.46 |  |  | 100% | 17.46 | Completed | Spot Quotation
437 | Const. of RCC pavement at Tuikhuahmual, Edenthar | 28.97 | Aizawl Road North Division |  |  | 100% | 28.97 |  |  | 100% | 28.97 | Completed | Spot Quotation
438
438 | Construction of RCC Pavement Edenthar to Chanmari West Road Sh: 1. Construction of RCC Pavement | 78 | Aizawl Road North Division | 20.04.23 | 22.05.23 | 100% | 78 |  |  | 100% | 78 | Completed | Spot Quotation
439 | 2. Construction of Hume Pipe Culvert at Ch.0.037 Kmp | 6.77 | Aizawl Road North Division | 20.04.23 | 22.05.23 | 100% | 6.77 |  |  | 100% | 6.77 | Completed | Spot Quotation
440 | Construction of Ram,lai Road at Edenthar Sh: Earth work for Widening of existing road) | 16.95 | Aizawl Road North Division | 28.03.23 | 29.09.23 | 100% | 16.95 |  |  | 100% | 16.95 | Completed | Spot Quotation
441 | Construction of Lunghlu Road at Chanmari West Sh: 1. Earth Work for Formation cutting | 17.52 | Aizawl Road North Division | 04.04.23 |  | 100% | 17.52 |  |  | 100% | 17.52 | Completed | Spot Quotation
442 | 2. Construction of RCC Slab Culvert Type-I | 8.03 | Aizawl Road North Division | 04.04.23 |  | 100% | 8.03 |  |  | 100% | 8.03 | Completed | Spot Quotation
443 | 3. Slab Culvert-II | 33.76 | Aizawl Road North Division | 04.04.23 |  | 100% | 33.76 |  |  | 100% | 33.76 | Not Yet Started | Spot Quotation
444 | Const. of RCC Link Drain near Volleyball Court, Hunthar | 28.96 | Aizawl Road North Division | 04.04.23 | [7 empty] | Not yet started | Spot Quotation
445 | Construction of road at Rangvamual, Aizawl Sh: 1. Earth Work for Formation Cutting | 107.52 | Aizawl Road North Division | 19.04.23 |  | 100% | 53.76 |  |  | 100% | 53.76 | Phy Completed | Spot Quotation
445 | Const. of RCC Slab Culvert Type-1 | 26.62 | Aizawl Road North Division | 19.04.23 | [7 empty] | Not yet started | Spot Quotation
446 | 3. Slab Culvert-II | 24.71 | Aizawl Road North Division | 19.04.23 | [7 empty] | Not yet started | Spot Quotation
Construction and Upgradation of Connectivity by Creating a new Alternative Route, Tanhril - Sakawrtuichhun.
447 | Patch repairs of Sakawrtuichhun to PTC Road due to vice President visit | 7.18 | Aizawl Road North Division | 27.02.23 | 23.03.23 | 100% | 7.18 |  |  | 100% | 7.18 | Completed | Spot Quotation
448 | Construction of Retaining Wall near Lallawmzuala's House at Sakawrtuichhun | 5.66 | Aizawl Road North Division | 24.02.23 | 21.03.23 | 100% | 5.66 |  |  | 100% | 5.66 | Completed | Spot Quotation
449 | Construction of Dumping Ground at Industrial Areas at Sakawrtuichhun Sh: 1. Earth Work for Formation Cutting of Internal Road | 10.53 | Aizawl Road North Division | 24.02.23 | 21.03.23 | 100% | 10.53 |  |  | 100% | 10.53 | Completed | Spot Quotation
450 | 2. Hume Pipe NP4 | 27.27 | Aizawl Road North Division | 24.02.23 | 21.03.23 | 100% | 27.27 |  |  | 100% | 27.27 | Completed | Spot Quotation
451 | Const. of Road at Tanhril, Aizawl Sh: 1. Earth Work for Formation Cutting | 80.48 | Aizawl Road North Division | 19.04.23 | 11.05.23 | 100% | 80.48 |  |  | 100% | 80.48 | Completed | Spot Quotation
452 | 2. Construction of RCC Slab Culvert Type-I | 27.15 | Aizawl Road North Division | 19.04.23 | 11.05.23 | 100% | 27.15 |  |  | 100% | 27.15 | Completed | Spot Quotation
453 | 3. Construction of RCC Slab Culvert Type-II | 16.79 | Aizawl Road North Division | 19.04.23 | 11.05.23 | 100% | 16.79 |  |  | 100% | 16.79 | Completed | Spot Quotation
454 | Construcytion of Road at Sakawrtuichhun, Aizawl Sh: 1. Earth Work for Widening of existing Road | 19.53 | Aizawl Road North Division | 19.04.23 | 12.05.23 | 100% | 19.53 |  |  | 100% | 19.53 | Completed | Spot Quotation
455 | 2. Construction of Flexible Pavement NBCC Road I & II | 24.82 | Aizawl Road North Division | 19.04.23 | 12.05.23 | 100% | 24.82 |  |  | 100% | 24.82 | Completed | Spot Quotation
456 | 3. Construction of RCC Slab Culvert Type-I | 17.84 | Aizawl Road North Division | 19.04.23 | 12.05.23 | 100% | 17.84 |  |  | 100% | 17.84 | Completed | Spot Quotation
IMPROVEMENT OF RAMRIKAWN TO NH-54 via SAKAWRTUICHHUN
457 | Improvement of Ramrikawn to NH-54 via Sakawrtuichhun Roads in Mizoram for the year 2022-2023 Sh: 1. Pavement of ramrikawn to NH-54 |  | Aizawl Road North Division | 07.04.23 |  | 60% |  |  |  | 60% |  | Work progress | Spot Quotation
458 | 2. Const.of R/Wall at Ch 5.950 Kmp at Sakawrtuichhun | 336 | Aizawl Road North Division | 07.04.23 |  | 100% | 168 |  | 168 | 100% | 336 | Completed | Spot Quotation
459 | 3. Const.of R/W near Zoo Gate, Lungverh |  | Aizawl Road North Division | 07.04.23 |  | 100% |  |  |  | 100% |  | Completed | Spot Quotation
460 | 4. Const.of Hume Pipe Culvert at 0.270 Kmp at Sakawrtuichhun |  | Aizawl Road North Division | 07.04.23 |  | 100% |  |  |  | 100% |  | Completed | Spot Quotation
461 | 5. Const.of Hume Pipe Culvert at 1.580 Kmp at Sakawrtuichhun |  | Aizawl Road North Division | 07.04.23 |  | 100% |  |  |  | 100% |  | Completed | Spot Quotation
AIZAWL ROAD SOUTH DIVISION
462 | Const. of Bethlehem Vengthlang Internal Road & Venghlui Junction Improvement. | 303 | Aizawl Road South Division | 28.02.23 | 30.12.23 | 100% | 147.39 |  |  | 100% | 147.39 | Phy.Completed | Item rate Contract
463 | Const. of Rehabilitation of Samtlang - Lungleng Road | 243 | Aizawl Road South Division | 28.02.23 | 30.12.23 | 99% | 106.21 |  |  | 99% | 106.21 | On going | Item rate Contract
464 | Improvement of Curves at Mission Vengthlang to Tlawng Road | 384 | Aizawl Road South Division | 28.02.23 | 30.12.23 | 100% | 198.56 |  |  | 100% | 198.56 | Phy.Completed | Item rate Contract
465 | Upgradation of Khatla to Tuikual to Dinthar Road | 343 | Aizawl Road South Division | 28.02.23 | 30.12.23 | 100% | 167.96 |  |  | 100% | 167.96 | Phy.Completed | Item rate Contract
466 | Const. and Upgradation of Republic Veng to Mualpui Road | 293 | Aizawl Road South Division | 28.02.23 | 30.12.23 | 100% | 96.08 |  |  | 100% | 96.08 | Phy.Completed | Item rate Contract
467 | Upgradation of Tuikhuahtlang to Saikhamakawn Road | 316 | Aizawl Road South Division | 28.02.23 | 30.12.23 | 100% | 146.15 |  |  | 100% | 146.15 | Phy.Completed | Item rate Contract
468 | Widening of Approach Road to City Bus Parking at S.Hlimen (Melthum - Hlimen Road ) | 576 | Aizawl Road South Division | 28.02.23 | 30.12.23 | 20% | 32.26 |  |  | 20% | 32.26 | On going | Item rate Contract
469 | Widening of S.Hlimen City Bus Parking - Samtlang Road (Hlimen-Samtlang Road) | 831 | Aizawl Road South Division | 28.02.23 | 30.12.23 | 60% | 203.61 |  |  | 60% | 203.61 | On going | Item rate Contract
Constraction of Bethlehem Vengthlang Internal Road & Venghlui Junction Improvement.
470 | Const. of concrete pavement on College Veng Field to PUC to Bethlehem Vengthlang kawn | 20.03 | Aizawl Road South Division |  |  | 100% | 20.03 |  |  | 100% | 20.03 | Completed | Item rate Contract
471 | Const. of Concrete Pavement on College Veng Taxi Stand to ITI Approach Road via Multipurpose Hall | 25.94 | Aizawl Road South Division |  |  | 100% | 25.94 |  |  | 100% | 25.94 | Completed | Item rate Contract
472 | Const. of Concrete pavement on Republic Presbyterian Pastor Quarter to Republic Field | 20.59 | Aizawl Road South Division |  |  | 100% | 20.59 |  |  | 100% | 20.59 | Completed | Item rate Contract
473 | Const. of Jeepable Road, Pi Sumi Lane at Republic Venghlun. | 29.28 | Aizawl Road South Division |  |  | 100% | 29.28 |  |  | 100% | 29.28 | Completed | Item rate Contract
474 | Const. of Road on Pu Bualchhuma's house to Pu Chhuanliana's house at Bethlehem Vengthlang. | 57.43 | Aizawl Road South Division |  |  | 100% | 57.43 |  |  | 100% | 57.43 | Completed | Item rate Contract
475 | Const. of Link Drain with covered Step on Sihlui to YMA Hall at Bethlehem Veng | 34.92 | Aizawl Road South Division |  |  | 100% | 34.92 |  |  | 100% | 34.92 | Completed | Item rate Contract
476 | Const. of Rectangular Side Drain with cover on Chhinga Veng to Sihtuikhur at Bethlehem Veng | 15.05 | Aizawl Road South Division |  |  | 100% | 15.05 |  |  | 100% | 15.05 | Completed | Item rate Contract
477 | Const. of U-Shape Side Drain on College Veng Field, College Veng | 7.63 | Aizawl Road South Division |  |  | 100% | 7.63 |  |  | 100% | 7.63 | Completed | Item rate Contract
478 | Const. of U-Shape Side Drain from PUC road to Pu Lalfamkima's House, Colleng Veng. | 7.62 | Aizawl Road South Division |  |  | 100% | 7.62 |  |  | 100% | 7.62 | Completed | Item rate Contract
479 | Levelling of Central High School Approach Road (Sh: Embankment) (Reconstruction of Culvert Wingwall on ACBR to College Veng Road at College Veng) | 1.31 | Aizawl Road South Division |  |  | 100% | 1.31 |  |  | 100% | 1.31 | Completed | Item rate Contract
480 | Const. of Breast Wall below Gov't. Middle school at College Veng. | 7.59 | Aizawl Road South Division |  |  | 100% | 7.59 |  |  | 100% | 7.59 | Completed | Item rate Contract
481 | Const. of Two Wheeler Way from PUC Road to Pu Selhnuna's House (Re-const. of Culvert Wing Wall near YMA Property House at Cillege Vengthlang Road) | 3.22 | Aizawl Road South Division |  |  | 100% | 3.22 |  |  | 100% | 3.22 | Completed | Item rate Contract
482 | Const. of Footpath from Zoziki Tuikhur to Umpupuk lui at F.Sangthanga's land at College Veng | 22.62 | Aizawl Road South Division |  |  | 100% | 22.62 |  |  | 100% | 22.62 | Completed | Item rate Contract
483 | Junction Improvement at Venghlui Approach Road. | 24.32 | Aizawl Road South Division |  |  | 100% | 24.32 |  |  | 100% | 24.32 | Completed | Item rate Contract
484 | Const. of RCC Pavement on Local Council Road, Presby. Pastor Quarter to Hmawngkai | 8.41 | Aizawl Road South Division |  |  | 100% | 8.41 |  |  | 100% | 8.41 | Completed | Item rate Contract
485 | Re-const. of Culvert near Pu H.Lalhmunliana's House at Venghlui (Sh: Abutment and Culvert Bed) | 4.87 | Aizawl Road South Division |  |  | 100% | 4.87 |  |  | 100% | 4.87 | Completed | Item rate Contract
486 | Const. of Breast Wall near Presby. Pastor Quarter at Venghlui. | 12.42 | Aizawl Road South Division |  |  | 100% | 12.42 |  |  | 100% | 12.42 | Completed | Item rate Contract
Construction. and Rehabilitation of Samtlang Road.
487 | Const. of RCC Balcony at Chekbawk Zau. | 25 | Aizawl Road South Division |  |  | 100% | 25 |  |  | 100% | 25 | Completed | Item rate Contract
488 | Const. of Turning Point at Biaka Vau, Saikhamakawn | 7.01 | Aizawl Road South Division |  |  | 100% | 7.01 |  |  | 100% | 7.01 | Completed | Item rate Contract
489 | PCC Pavement of Approach Road to Dartuaha Veng, Melthum. | 10 | Aizawl Road South Division |  |  | 100% | 10 |  |  | 100% | 10 | Completed | Item rate Contract
490 | Const. of Jeepable Approach Road to Thlanmual, Melthum. | 5 | Aizawl Road South Division |  |  | 100% | 5 |  |  | 100% | 5 | Completed | Item rate Contract
491 | Const. of Agriculture Link Road to Chuhvel Ram, Hlimen. | 5 | Aizawl Road South Division |  |  | 100% | 5 |  |  | 100% | 5 | Completed | Item rate Contract
492 | RCC Pavement of Internal Road at Hlimen Vengthlang chuanhnuai (Lianhmingthanga's House to Vanmawia's House) | 6 | Aizawl Road South Division |  |  | 100% | 6 |  |  | 100% | 6 | Completed | Item rate Contract
493 | Const. of Internal Road from Quarry Veng to Tuikhurdung Zau, Hlimen | 7 | Aizawl Road South Division |  |  | 100% | 7 |  |  | 100% | 7 | Completed | Item rate Contract
494 | Improvement of Approach Road to Hlimen Khurpui Veng | 5 | Aizawl Road South Division |  |  | 100% | 5 |  |  | 100% | 5 | Completed | Item rate Contract
495 | Improvement of Internal Road to Hlimen Vengchhak to Pu N.Zokunga's House | 5 | Aizawl Road South Division | [8 empty] | Not yet started | Item rate Contract
496 | Extention of Culvert at Samtlang to Lungleng Road at Bunglui kawr, Samtlang | 5 | Aizawl Road South Division |  |  | 100% | 5 |  |  | 100% | 5 | Completed | Item rate Contract
497 | Widening of Internal Road at Lungpawng Road, Samtlang | 6 | Aizawl Road South Division |  |  | 100% | 6 |  |  | 100% | 6 | Completed | Item rate Contract
498 | Const. of RCC Balcony near Samtlang Playground | 117.47 | Aizawl Road South Division |  |  | 100% | 117.47 |  |  | 100% | 117.47 | Completed | Item rate Contract
499 | Widening of Samtlang Playground | 9 | Aizawl Road South Division |  |  | 100% | 9 |  |  | 100% | 9 | Completed | Item rate Contract
500 | Widening and Construction of Retaining Wall at Mualveng, Samtlang (Hmangaihthangi Land) | 4 | Aizawl Road South Division |  |  | 100% | 4 |  |  | 100% | 4 | Completed | Item rate Contract
501 | Widening and Construction of Retaining Wall at Mualveng, Samtlang (Changliani Land) | 4 | Aizawl Road South Division |  |  | 100% | 4 |  |  | 100% | 4 | Completed | Item rate Contract
502 | Road Widening and Const. of Retaining Wall near SDA Biak In, N.Lungleng. | 6 | Aizawl Road South Division |  |  | 100% | 6 |  |  | 100% | 6 | Completed | Item rate Contract
503 | PCC Pavement of Agriculture Link Road between Khankawn leh Serzawl Zau, N.Lungleng. | 6 | Aizawl Road South Division |  |  | 100% | 6 |  |  | 100% | 6 | Completed | Item rate Contract
504 | PCC Pavement of Agriculture Link Road to Uilui, Lungleng-1 | 25 | Aizawl Road South Division |  |  | 100% | 25 |  |  | 100% | 25 | Completed | Item rate Contract
Improvement of Curves at Mission Vengthlang to Tlawng Road
505 | Improvement of Curves at Ch:0.00 Kmp and 0.600 Kmp on Mission Vengthlang Damphei to Tlawng Road | 72 | Aizawl Road South Division |  |  | 100% | 72 |  |  | 100% | 72 | Completed | Item rate Contract
506 | Patch repair and Seal coating of Aizawl - Reiek - W.Lungdar Road between Ch: 4.00 - 10.00 Kmp | 28.5 | Aizawl Road South Division |  |  | 100% | 28.5 |  |  | 100% | 28.5 | Completed | Item rate Contract
507 | Re-const. of endangered RCC Culvert Wing Wall at Ch : 0.700 Kmp on Aizawl - Reiek- W.Lungdar Road. | 3.31 | Aizawl Road South Division |  |  | 100% | 3.31 |  |  | 100% | 3.31 | Completed | Item rate Contract
508 | Const. of rigid pavement on widened portion of Cemetary Road at Mission Vengthlang. | 12 | Aizawl Road South Division |  |  | 100% | 12 |  |  | 100% | 12 | Completed | Item rate Contract
509 | Const. of Retaining Wall at Mission Vengthlang below Primary School. | 8.8 | Aizawl Road South Division |  |  | 100% | 8.8 |  |  | 100% | 8.8 | Completed | Item rate Contract
510 | Const. of Side Drain between Rodinga (L) and J.Thanglura's House on Aizawl - Reiek - W.Lungdar Road. | 2 | Aizawl Road South Division |  |  | 100% | 2 |  |  | 100% | 2 | Completed | Item rate Contract
511 | Const. of Side Drain between Vanlalhuma's House to Vailui on Aizawl - Reiek - W.Lungdar Road | 2.2 | Aizawl Road South Division |  |  | 100% | 2.2 |  |  | 100% | 2.2 | Completed | Item rate Contract
512 | Const. of RCC balcony on Mission Vengthlang Tlangveng Road. | 8.05 | Aizawl Road South Division |  |  | 100% | 8.05 |  |  | 100% | 8.05 | Completed | Item rate Contract
513 | Const. of Side Drain on Cemetary Road at Mission Vengthlang. | 3.78 | Aizawl Road South Division |  |  | 100% | 3.78 |  |  | 100% | 3.78 | Completed | Item rate Contract
514 | Const. of Retaining Wall below PCI Church on Aizawl - Reiek - W.Lungdar Road | 6.72 | Aizawl Road South Division |  |  | 100% | 6.72 |  |  | 100% | 6.72 | Completed | Item rate Contract
515 | Const. of Hand Railing near H.Thangdailova's House to H.Thangvela's House at Bungkawn Vengthar. | 1.5 | Aizawl Road South Division |  |  | 100% | 1.5 |  |  | 100% | 1.5 | Completed | Item rate Contract
516 | Const. of Jeepable Road over Rawngrut Lui from Lalrinliana's House to Vanlalnghaka's House. | 9 | Aizawl Road South Division |  |  | 100% | 9 |  |  | 100% | 9 | Completed | Item rate Contract
517 | Const. of Slope drain near Lalchhandama's House at Bungkawn Vengthar. | 1 | Aizawl Road South Division |  |  | 100% | 1 |  |  | 100% | 1 | Completed | Item rate Contract
518 | Const. of Saizahawla Tuikhur near R.Lalrinchhana's house Field Road | 14.2 | Aizawl Road South Division |  |  | 100% | 14.2 |  |  | 100% | 14.2 | Completed | Item rate Contract
519 | Const. of Turning Point near CS Lalnunthara's House at Khatla 'S' | 6 | Aizawl Road South Division |  |  | 100% | 6 |  |  | 100% | 6 | Completed | Item rate Contract
520 | Const. of RCC Over Drain Step between C.Vanlalringa's House & Lalzidinga's Sailo House at Khatla South. | 29 | Aizawl Road South Division |  |  | 100% | 29 |  |  | 100% | 29 | Completed | Item rate Contract
521 | Const. of RCC pavement and Side Drain near PC Zokhuma (L) House at Bungkawn. | 3.5 | Aizawl Road South Division |  |  | 100% | 3.5 |  |  | 100% | 3.5 | Completed | Item rate Contract
522 | Const. of Side Drain between C.Zabiaka (Tuikhur veng) to Pastor Quarter at Bungkawn. | 2.5 | Aizawl Road South Division |  |  | 100% | 2.5 |  |  | 100% | 2.5 | Completed | Item rate Contract
523 | Const. of Side Drain between Lianthangpuia (L) to Laldawngkima House at Bungkawn. | 0.5 | Aizawl Road South Division |  |  | 100% | 0.5 |  |  | 100% | 0.5 | Completed | Item rate Contract
524 | Const. of Retaining Wall near C.Ramhluna's House at Bungkawn | 7.01 | Aizawl Road South Division |  |  | 100% | 7.01 |  |  | 100% | 7.01 | Completed | Item rate Contract
525 | Const. of Retaining Wall near Zorinmawia's House at Bungkawn | 3.01 | Aizawl Road South Division |  |  | 100% | 3.01 |  |  | 100% | 3.01 | Completed | Item rate Contract
526 | Const. of Breast Wall near Zorinmawia's House at Bungkawn Tlangveng. | 0.5 | Aizawl Road South Division |  |  | 100% | 0.5 |  |  | 100% | 0.5 | Completed | Item rate Contract
527 | Improvement & Widening of Link Road between Bungkawn Venglai and Bungkawn Vengthar. | 10.02 | Aizawl Road South Division |  |  | 100% | 10.02 |  |  | 100% | 10.02 | Completed | Item rate Contract
528 | Const. of Side Drain between Mission veng Tuikhur to Neihchhunga's House at Khatla 'E' | 6.5 | Aizawl Road South Division |  |  | 100% | 6.5 |  |  | 100% | 6.5 | Completed | Item rate Contract
529 | Const. of Side Drain between Neihchhunga's House to R.Sangkhuma's House at Khatla E | 6.5 | Aizawl Road South Division |  |  | 100% | 6.5 |  |  | 100% | 6.5 | Completed | Item rate Contract
530 | Const. of U-Shape Side Drain between Prema (L) House to Khatla 'E' Approach Road. | 3.01 | Aizawl Road South Division |  |  | 100% | 3.01 |  |  | 100% | 3.01 | Completed | Item rate Contract
531 | Re-const. of Retaining Wall at Maubawk Baptist Church to Maubawk Kawnveng Road at 0.075 Kmp. | 4.3 | Aizawl Road South Division |  |  | 100% | 4.3 |  |  | 100% | 4.3 | Completed | Item rate Contract
532 | Const. of Maubawk Internal Road. | 44.54 | Aizawl Road South Division |  |  | 100% | 44.54 |  |  | 100% | 44.54 | Completed | Item rate Contract
533 | Const. of Approach Road between Lalsangzuali's House to Lalthanzara Sailo House. | 2 | Aizawl Road South Division |  |  | 100% | 2 |  |  | 100% | 2 | Completed | Item rate Contract
534 | Const. of Retaining Wall near Rotuahkhawli Grave at Maubawk Cemetary. | 2 | Aizawl Road South Division |  |  | 100% | 2 |  |  | 100% | 2 | Completed | Item rate Contract
535 | Const. of Footstep near Lalremtluangi's House at Damveng, Maubawk. | 2 | Aizawl Road South Division |  |  | 100% | 2 |  |  | 100% | 2 | Completed | Item rate Contract
536 | Const. of Approach Road to Maubawk New Cemetary at Lawipu. | 9.87 | Aizawl Road South Division |  |  | 100% | 9.87 |  |  | 100% | 9.87 | Completed | Item rate Contract
537 | Const. of Link Road between School Veng to Local Council House at Lawipu. | 13 | Aizawl Road South Division |  |  | 100% | 13 |  |  | 100% | 13 | Completed | Item rate Contract
538 | Patch repair and Seal Coat of ATI road between 0.00-5.00 Kmp. | 6.57 | Aizawl Road South Division |  |  | 100% | 6.57 |  |  | 100% | 6.57 | Completed | Item rate Contract
539 | Breaking and Clearing of Dangerous Stone from falling on the road at 0.750 Kmp on ATL Road. | 0.65 | Aizawl Road South Division |  |  | 100% | 0.65 |  |  | 100% | 0.65 | Completed | Item rate Contract
540 | Patch repair and Seal Coat of Kulikawn to Tlangnuam Road (Mary Mount School Road) | 13 | Aizawl Road South Division |  |  | 100% | 13 |  |  | 100% | 13 | Completed | Item rate Contract
541 | Patch Repair and Seal Coat of Temple - Dinthar peng. | 10 | Aizawl Road South Division |  |  | 100% | 10 |  |  | 100% | 10 | Completed | Item rate Contract
542 | Re-Const. of Gabion Wall on MHNL section-II (Dinthar veng) | 18.6 | Aizawl Road South Division |  |  | 100% | 18.6 |  |  | 100% | 18.6 | Completed | Item rate Contract
543 | Const. of RCC Cross Drain with Cover near H.Rammawia's House on Tennis Court to Dinthar Road. | 1.5 | Aizawl Road South Division |  |  | 100% | 1.5 |  |  | 100% | 1.5 | Completed | Item rate Contract
544 | Const. of Retaining Wall near J.Lianhlira's House at Khatla. | 5.5 | Aizawl Road South Division |  |  | 100% | 5.5 |  |  | 100% | 5.5 | Completed | Item rate Contract
UPGRADATION OF KHATLA TO TUIKUAL TO DINTHAR ROAD
Improvement and Widening of Road on Zawlzau to YMA Run at MINECO Internal Road.
545 | Widening and Const. of Stone Masonry Wall below High Court (Length=60m, Av Height=4.00m) | 30.59 | Aizawl Road South Division |  |  | 100% | 30.59 |  |  | 100% | 30.59 | Completed | Item rate Contract
546 | Widening & Const of Composite Retaining Wall below High Court (Length = 46.50m, Av Heigh = 4.80m) | 27.45 | Aizawl Road South Division |  |  | 100% | 27.45 |  |  | 100% | 27.45 | Completed | Item rate Contract
547 | Const. of RCC Balcony Roadway with extention of RCC Slab Culvert (Judicial - Science & Technology) (Length= 24.00m, Av Width 3.00m) | 21.17 | Aizawl Road South Division |  |  | 100% | 21.17 |  |  | 100% | 21.17 | Completed | Item rate Contract
548 | Const. of RCC Balcony Footpath (Zawlzau - MRB Office) (Length = 115.00m, Av Width= 1.50m) | 26.27 | Aizawl Road South Division |  |  | 100% | 26.27 |  |  | 100% | 26.27 | Completed | Item rate Contract
549 | Pavement of Widened Portion (Length=250.00m Av Width=1.78m) | 9.24 | Aizawl Road South Division |  |  | 100% | 9.24 |  |  | 100% | 9.24 | Completed | Item rate Contract
550 | Improvement of Road below High Court at MINECO Internal Road Phase - II | 26.53 | Aizawl Road South Division |  |  | 100% | 26.53 |  |  | 100% | 26.53 | Completed | Item rate Contract
551 | Const. of RCC Over Drain Step between Sainik Office and DCSO Office at Khatla. | 39 | Aizawl Road South Division |  |  | 100% | 39 |  |  | 100% | 39 | Completed | Item rate Contract
552 | RCC Link Drain With Cover Suakpuia Mual Approach Road to Tuikual North Field. | 45 | Aizawl Road South Division |  |  | 100% | 45 |  |  | 100% | 45 | Completed | Item rate Contract
553 | Re-Const. of Gabion Wall near Tuikual Indoor Stadium, Tuikual. | 58.7 | Aizawl Road South Division |  |  | 100% | 58.7 |  |  | 100% | 58.7 | Completed | Item rate Contract
554 | Renovation and Repairing of RCC Bridge and Cantilever at Tuikual 'S | 20 | Aizawl Road South Division |  |  | 100% | 20 |  |  | 100% | 20 | Completed | Item rate Contract
555 | Retaining Wall at Hipheia Road at Dinthar. | 8.68 | Aizawl Road South Division |  |  | 100% | 8.68 |  |  | 100% | 8.68 | Completed | Item rate Contract
556 | RCC Drain with Cover L =160Rm at Dinthar. | 10.47 | Aizawl Road South Division |  |  | 100% | 10.47 |  |  | 100% | 10.47 | Completed | Item rate Contract
557 | Seal Coating of Dinthar Thlanmual to Kanan Road. | 11.13 | Aizawl Road South Division |  |  | 100% | 11.13 |  |  | 100% | 11.13 | Completed | Item rate Contract
558 | Re-Const. of Culvert near Zila Sainik Welfare Office at Khatla. | 4.38 | Aizawl Road South Division |  |  | 100% | 4.38 |  |  | 100% | 4.38 | Completed | Item rate Contract
559 | Const. of RCC Side Drain with Cover at Khatla Kawn. | 2.07 | Aizawl Road South Division |  |  | 100% | 2.07 |  |  | 100% | 2.07 | Completed | Item rate Contract
560 | Patch Repair with part MBT for Profile Correction of Water Logged Area near Zokunga's House on Nursery Veng Road. | 2.53 | Aizawl Road South Division |  |  | 100% | 2.53 |  |  | 100% | 2.53 | Completed | Item rate Contract
Construction and Improvement of Republic Veng to Mualpui Road
561 | Improvement and Widening of Blind Curve on AH & Vety Land at Republic Veng, Aizawl. | 66 | Aizawl Road South Division |  |  | 100% | 66 |  |  | 100% | 66 | Completed | Item rate Contract
562 | Const. of Link Drain with Cover near Ruotmawi Taxi Stand to P.C.Biakzuala's House at Republic Vengthlang. | 30 | Aizawl Road South Division |  |  | 100% | 30 |  |  | 100% | 30 | Completed | Item rate Contract
563 | Const. of Retaining Wall on Approach Road to Slaughter House at Mualpui. | 57 | Aizawl Road South Division |  |  | 100% | 57 |  |  | 100% | 57 | Completed | Item rate Contract
564 | Catch Pit and some portion of the base of Culvert near Rochhuma's House at Republic Vengthlang. | 0.71 | Aizawl Road South Division |  |  | 100% | 0.71 |  |  | 100% | 0.71 | Completed | Item rate Contract
565 | Const. of Retaining Wall near Lalremthanga (L) House, Arhuan, Salem Veng. | 5 | Aizawl Road South Division |  |  | 100% | 5 |  |  | 100% | 5 | Completed | Item rate Contract
566 | Const. of RCC Pavement - HC Vanlalruata House to Vanlalruata Varte House at Mualpui, Salem Veng. | 5 | Aizawl Road South Division |  |  | 100% | 5 |  |  | 100% | 5 | Completed | Item rate Contract
567 | Const. of Step with Railing - Thanzingi House to Biakzami house at Salem Veng | 3 | Aizawl Road South Division |  |  | 100% | 3 |  |  | 100% | 3 | Completed | Item rate Contract
568 |  | 2 | Aizawl Road South Division |  |  | 100% | 2 |  |  | 100% | 2 | Completed | Item rate Contract
569 | Const. of RCC Pavement - Rochhungi House to Thlanmual Road at Salem Veng. | 5 | Aizawl Road South Division |  |  | 100% | 5 |  |  | 100% | 5 | Completed | Item rate Contract
570 | Const. of RCC Approach Road , World Bank Road to siby Futsal Ground Mualpui, Salem Veng | 10 | Aizawl Road South Division |  |  | 100% | 10 |  |  | 100% | 10 | Completed | Item rate Contract
571 | Const. of Retaining Wall near H.Manga's House at ITI Veng. | 4 | Aizawl Road South Division |  |  | 100% | 4 |  |  | 100% | 4 | Completed | Item rate Contract
572 | Const. of Footpath, ITI Kawn to Mualpui Road. | 10 | Aizawl Road South Division |  |  | 100% | 10 |  |  | 100% | 10 | Completed | Item rate Contract
573 | Consultancy Services for Preparation of DPR. | 95.32 | Aizawl Road South Division |  |  | 100% | 95.32 |  |  | 100% | 95.32 | Completed | Item rate Contract
574 | Upgradation of Tuikhuahtlang to Saikhamakawn Road at Aizawl Under SASCI 2022-2023 | 316 | Aizawl Road South Division |  |  | 100% | 316 |  |  | 100% | 146.15 | Completed | Item rate Contract
575 | Const. of Jeepable Road from Lalzamlova House to (CP road) to Sakhisih at Model Veng (Ch:0.00-0.115 Kmp) | 45 | Aizawl Road South Division |  |  | 100% | 45 |  |  | 100% | 45 | Completed | Item rate Contract
576 | Const. of RCC Pavement Tlangnuam to Serlui, Tlangnuam | 30 | Aizawl Road South Division |  |  | 100% | 30 |  |  | 100% | 30 | Completed | Item rate Contract
577 | Const. of Retaining/Breast Wall near Vanlalzara Land at Tlangnuam Field Road. | 2 | Aizawl Road South Division |  |  | 100% | 2 |  |  | 100% | 2 | Completed | Item rate Contract
578 | Const. of Side Drain near F.Vanlalhruaia House to Vanlalfela House at Tlangnuam Field Road. | 4 | Aizawl Road South Division |  |  | 100% | 4 |  |  | 100% | 4 | Completed | Item rate Contract
579 | Const. of Retaining/Breast Wall Tlangnuam Thlanmual near Library House at Tlangnuam. | 4 | Aizawl Road South Division |  |  | 100% | 4 |  |  | 100% | 4 | Completed | Item rate Contract
580 | Const. of PCC Pavement - Phunchawngkawn to Lalchhanhima House at Tlangnuam West. | 5 | Aizawl Road South Division |  |  | 100% | 5 |  |  | 100% | 5 | Completed | Item rate Contract
581 | Const. of RCC Pavement - Lalhmunsanga House to Chhawnsanga House at Tlangnuam West. | 5 | Aizawl Road South Division |  |  | 100% | 5 |  |  | 100% | 5 | Completed | Item rate Contract
582 | Const. of RCC Pavement - Zochungnunga House to Zoramthanga House below Tlangnuam Playground at Tlangnuam Vengthar. | 10 | Aizawl Road South Division |  |  | 100% | 10 |  |  | 100% | 10 | Completed | Item rate Contract
583 | Const. of Hlimen Basket Ball Court of Alpine Hut Road (Sh: Widening, RCC Pavement and Side Drain) | 23.25 | Aizawl Road South Division |  |  | 100% | 23.25 |  |  | 100% | 23.25 | Completed | Item rate Contract
584 | Approach Road to Together in Christ Ministry, Saikhamakawn. | 16.5 | Aizawl Road South Division |  |  | 100% | 16.5 |  |  | 100% | 16.5 | Completed | Item rate Contract
585 | Const. of Side Drain with Cover Assam Rifle Gate to PCCF Office Opposite at Tuikhuahtlang. | 10 | Aizawl Road South Division |  |  | 100% | 10 |  |  | 100% | 10 | Completed | Item rate Contract
586 | Const. of Retaining Wall Lalliansawta House to Rangthanga House at Thakthing Veng. | 7 | Aizawl Road South Division |  |  | 100% | 7 |  |  | 100% | 7 | Completed | Item rate Contract
587 | Const. of Retaining Wall near Mission Veng Basketball Court at Mission Veng. | 5 | Aizawl Road South Division |  |  | 100% | 5 |  |  | 100% | 5 | Completed | Item rate Contract
588 | Const. of Masonry Retaining Wall near Vanlalchhuanga's House at Kawltheihuan, Mission Veng. | 10 | Aizawl Road South Division |  |  | 100% | 10 |  |  | 100% | 10 | Completed | Item rate Contract
589 | Const. of Jeepable Road Sihpui Tuikhur to Damna In at Venghnuai. | 10 | Aizawl Road South Division |  |  | 100% | 10 |  |  | 100% | 10 | Completed | Item rate Contract
590 | Const. of Jeepable Road - C.Rohmingliana House to Laltinchhunga House, Venghnuai. | 5 | Aizawl Road South Division |  |  | 100% | 5 |  |  | 100% | 5 | Completed | Item rate Contract
591 | Const. of Retaining Wall near Dothanga House, Chawngliana Road at Dam Veng. | 5 | Aizawl Road South Division |  |  | 100% | 5 |  |  | 100% | 5 | Completed | Item rate Contract
592 | Const. of RCC pavement between Dr.Pika Road to Kulikawn YMA Hall approach road at Kulikawn. | 10 | Aizawl Road South Division |  |  | 100% | 10 |  |  | 100% | 10 | Completed | Item rate Contract
593 | Const. of Culvert - Near C.Thanliana (L) House, Zobawm at Kulikawn. | 10 | Aizawl Road South Division |  |  | 100% | 10 |  |  | 100% | 10 | Completed | Item rate Contract
594 | Const. of Rigid Pavement - Sihpui Tuikhur to World Bank Road at Kulikawn. | 20 | Aizawl Road South Division |  |  | 100% | 20 |  |  | 100% | 20 | Completed | Item rate Contract
595 | Const. of Rigid Pavement - Chuailova House to World Bank Road at Kulikawn. | 10 | Aizawl Road South Division |  |  | 100% | 10 |  |  | 100% | 10 | Completed | Item rate Contract
596 | Const. of Cross Drainage, U-Shape Side Drain near Mission Veng Field. | 16 | Aizawl Road South Division |  |  | 100% | 16 |  |  | 100% | 16 | Completed | Item rate Contract
597 | Const. of Widening and Retaining Wall at William Booth Road at ITI Veng. | 13.54 | Aizawl Road South Division |  |  | 100% | 13.54 |  |  | 100% | 13.54 | Completed | Item rate Contract
598 |  | 6.46 | Aizawl Road South Division |  |  | 100% | 6.46 |  |  | 100% | 6.46 | Completed | Item rate Contract
599 | Const. of RCC Pavement from Vanlalpeka House to C.Thanliana (L) House Zobawm Road at Kulikawn. | 22 | Aizawl Road South Division |  |  | 100% | 22 |  |  | 100% | 22 | Completed | Item rate Contract
600 | Const. of RCC Pavement Kulikawn East Presbyterian Biakin to Kulikawn Thlanmual. | 4 | Aizawl Road South Division |  |  | 100% | 4 |  |  | 100% | 4 | Completed | Item rate Contract
601 | Const. of Retaining Wall belowZomawii House, Tlangnuam | 3 | Aizawl Road South Division |  |  | 100% | 3 |  |  | 100% | 3 | Completed | Item rate Contract
602 | Const. of Retaining Wall near Tlangnuam Community Hall | 4 | Aizawl Road South Division |  |  | 100% | 4 |  |  | 100% | 4 | Completed | Item rate Contract
603 | Widening of Approach Road to City Bus Parking at S.Hlimen, Aizawl. (Melthum-Hlimen Road) Under SASCI 2022-2023 | 576 | Aizawl Road South Division |  |  | 15% | 32.26 | 5% |  | 20% | 32.26 | On going | Item rate Contract
604 | Widening of S. Hlimen City Bus Parking - Samtlang Road (Hlimen - Samtlang Road) under SASCI 2022-2023. | 831 | Aizawl Road South Division |  |  | 50% | 203.61 | 10% |  | 60% | 203.61 | Work in Progress | Item rate Contract
CHAMPHAI DIVISION
Const./Improvement of Road from Pamchung - Tualcheng - Chhangphut Field - Keifangtlang at Champhai District. 2022-2023
605 | Const. of Road from Pamchung to Tualcheng | 60 | Champhai Division | 21.03.23 | 21.04.23 | 100% | 57.88 |  |  | 100% | 57.88 | Completed | Spot Quatation
606 | Widening of Chhangphut Field to Keifangtlang | 90 | Champhai Division | 21.03.23 | 21.04.23 | 38.45% | 31.27 |  |  | 38.45% | 31.27 | Work in Progress | Spot Quatation
607 | Widening and Retaining Wall at Hnahlan Dawrkawn to BRTF Road | 20 | Champhai Division | 21.03.23 | 21.04.23 | 100% | 19.32 |  |  | 100% | 19.32 | Completed | Spot Quatation
608 | Const. and Widening of Champhai Vengthlang ( N.Saron) to PHE Road | 50 | Champhai Division | 21.03.23 | 21.04.23 | 100% | 38.22 |  |  | 100% | 38.22 | Phy.Completed | Spot Quatation
609 | Const. of Railing and Retaining Wall at Champhai, Awmpui Phei & IB Veng | 40 | Champhai Division | 21.03.23 | 21.04.23 | 90.94% | 38.54 |  |  | 90.94% | 38.54 | Completed | Spot Quatation
610 | Consultancy Fee | 77 | Champhai Division | 21.03.23 | 21.04.23 | 100% | 10.14 |  |  | 100% | 10.14 | Phy.Completed | Spot Quatation
Const. of Pavement Champhai Vengthar - BRTF Road - Zotlang at Champhai. 2022-2023
611 | Black Topping of Road from Champhai Vengthar to BRTF Road (Zotekai Short Cut Road) | 164.46 | Champhai Division | 30.03.23 | 31.04.23 | 100% | 162.99 |  |  | 100% | 162.99 | Completed | Spot Quatation
612 | White Topping of Khawulh Approach Road at Zotlang, Champhai (Cement Concrete Pavement ) | 30 | Champhai Division | 30.03.23 | 31.04.23 | 100% | 28.92 |  |  | 100% | 28.92 | Completed | Spot Quatation
613 | Widening of Road from Dinthar to Ramhrangkawn (7th Day Gate to LCN Filling Station ) | 45 | Champhai Division | 30.03.23 | 31.04.23 | 100% | 43.47 |  |  | 100% | 43.47 | Completed | Spot Quatation
614 | Widening of Approach Road to Kendriya Vidhyalaya School, Champhai | 10 | Champhai Division | 30.03.23 | 31.04.23 | 100% | 9.95 |  |  | 100% | 9.95 | Completed | Spot Quatation
Improvement of Road from IKK Zion Veng - Khawbung - Tuipui at Champhai District 2022-2023
615 | Widening and Flexible Pavement of Road from IKK Church to Zion Veng Boundary. | 135.54 | Champhai Division | 30.03.23 | 31.04.23 | 100% | 120.5 |  |  | 100% | 120.5 | Completed | Spot Quatation
616 | Bouldering of Road from ZBC Church to Mualnuam Road. | 15 | Champhai Division | 30.03.23 | 31.04.23 | 100% | 14.49 |  |  | 100% | 14.49 | Completed | Spot Quatation
617 | Const.and Widening of Road Zawlsei to Tuipui | 40 | Champhai Division | 30.03.23 | 31.04.23 | 100% | 38 |  |  | 100% | 38 | Completed | Spot Quatation
618 | Surfacing of Ruantlang Dawrkawn to CNV Road Via Lersia Field. | 17.3 | Champhai Division | 30.03.23 | 31.04.23 | 100% | 16.71 |  |  | 100% | 16.71 | Completed | Spot Quatation
619 | Patch Repair and Seal Coating of New Champhai to Tlangsam Road. | 25 | Champhai Division | 30.03.23 | 31.04.23 | 100% | 24.15 |  |  | 100% | 24.15 | Completed | Spot Quatation
620 | Pothole & Re-surfacing of Sasaw Road at Khawbung Internal Road (Khawbung to Tuipui Short Cut Road) | 42.28 | Champhai Division | 30.03.23 | 31.04.23 | 50% | 40.69 |  |  | 50% | 40.69 | Work in Progress | Spot Quatation
621 | Const. of Retaining Wall on Road Formation Collapse at 22.600 Kmp on Champhai to Khawbung Road. | 6.13 | Champhai Division | 30.03.23 | 31.04.23 | 100% | 5.9 |  |  | 100% | 5.9 | Liability | Spot Quatation
622 | Completion of Champhai - Zokhawthar Road under SASCI. 2023-2024 | 1311 | Champhai Division | 06.03.23 | 06.03.24 | 20% | 302.93 | 3% |  | 23% | 302.93 | Work in Progress | Restricted Tender
KOLASIB DIVISION :
623 | Formation cutting of Serlui Zau at Kawnpui | 47.84 | Kolasib Division | 01.04.23 | 01.04.24 | 100% | 47.84 |  |  | 100% | 47.84 | Completed
624 | Formation cutting of Panhnah kawn at N.Chaltlang | 29.12 | Kolasib Division | 01.04.23 | 01.04.24 | 100% | 29.12 |  |  | 100% | 29.12 | Completed
625 | Formation cutting of Kawnpui zau at Bukpui | 29.12 | Kolasib Division | 01.04.23 | 01.04.24 | 100% | 29.12 |  |  | 100% | 29.12 | Completed
626 | Formation cutting of Tuirial Road at Lungmuat | 29.12 | Kolasib Division | 01.04.23 | 01.04.24 | 100% | 29.12 |  |  | 100% | 29.12 | Completed
627 | Resurfacing of Mizo Hotelpui to NH-306 via IACR | 65.01 | Kolasib Division | 01.04.23 | 01.04.24 | 95% | 65.01 | 5% |  | 100% | 65.01 | Completed
628 | Hume Pipe Culvert near SIRD Quarter, Vengthar | 3.85 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 1.92 |  |  | 100% | 1.92 | Phy.Completed
629 | Hume Pipe Culvert near Pu Sawma's House | 8.72 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 4.35 |  |  | 100% | 4.35 | Phy.Completed
630 | Extention of Hume Pipe Culvert near K.Saigina, Vengthar | 2.21 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 1.11 |  | 1.1 | 100% | 2.21 | Phy.Completed
631 | Const. of V-Shape SD at Essential Places on Mizo Hotelpui-NH 306 via IACR | 9.89 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 4.94 |  | 4.95 | 100% | 9.89 | Phy.Completed
632 | Embankment in front of Pu Laltanpuia's House Vengthar | 0.89 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 0.44 |  | 0.45 | 100% | 0.89 | Phy.completed
633 | Road Widening below Remsiami's House, Vengthar | 0.125 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 0.06 |  | 0.06 | 100% | 0.12 | Phy.Completed
634 | : Road widening near Leitan, Vengthar | 0.89 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 0.44 |  |  | 100% | 0.44 | Phy.Completed
635 | Upgradation of CP Road, New Diakkawn Kolasib (Resurfacing of CP Road) | 26.09 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 26.09 |  |  | 100% | 26.09 | Completed
636 | Upgradation of CP Road, New Diakkawn Kolasib (Const.of LSD at CP Road) | 9.17 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 4.58 |  | 4.59 | 100% | 9.17 | Phy.Completed
637 | Improvement and Upgradation of Soil Peng to KVK (Kawnglaiphei) Resurfacing of Soil Dept.peng to KVK) | 52.39 | Kolasib Division | 2023-03-23 | 2023-03-24 | 20% | 52.39 | 50% |  | 70% | 52.39 | Work progress
638 | Improvement and Upgradation of Soil Peng to KVK (Kawnglaiphei) Hume Pipe Culvert at Middle of the Road) ) | 3.209 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 1.6 |  | 1.6 | 100% | 3.2 | Phy.Completed
639 | Improvement and Upgradation of Soil Peng to KVK (Kawnglaiphei) (Extension of Downstream Hume Pipe Culvert near Pu Lalchhuanawma's House, Vengthar) | 2.636 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 1.318 |  | 1.328 | 100% | 2.636 | Phy.Completed
640 | Improvement and Upgradation of Soil Peng to KVK (Kawnglaiphei) (Extension of Hume Pipe Culvert near Pu Lalthana House, Vengthar) | 7.43 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 3.71 |  |  | 100% | 3.71 | Phy.Completed
641 | Improvement and Upgradation of Soil Peng to KVK (Kawnglaiphei) (Const.of LSD at Essential Places of Soil Dept.peng to KVK | 10.78 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 5.39 |  |  | 100% | 5.39 | Phy.Completed
642 | Improvement and Upgradation of Soil Peng to KVK (Kawnglaiphei) Road Widening near Saichhungi House, Vengthar | 0.47 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 0.23 |  |  | 100% | 0.23 | Phy Completed
643 | Improvement and Upgradation of Soil Peng to KVK (Kawnglaiphei) (Road Widening near Masanga House to Pu Tanpuia House, Vengthar | 0.645 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 0.32 |  |  | 100% | 0.32 | Phy.Completed
644 | Kumtluang Run to Rammawia's House (Blacktopping) | 12.33 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 12.33 |  |  | 100% | 12.33 | Completed
645 | Const. of Breast Wall below Transformer on the road Kumtluang Run to Rammawia's House | 4.85 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 2.42 |  | 2.43 | 100% | 4.85 | Phy.Completed
646 | Const. of V-shape Side Drain on the Road Kumtluang Run to Rammawia's House | 16.58 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 8.29 |  | 8.29 | 100% | 16.58 | Phy.Completed
647 | Resurfacing of IACR to Dinthar Road | 22.09 | Kolasib Division | 2023-03-23 | 2023-03-24 |  | 22.09 | 20% |  | 20% | 22.09
648 | Const. of LSD at Essential places on IACR to Dinthar Road | 6.93 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 3.46 |  |  | 100% | 3.46 | Phy.Completed
649 | Clearing and Grubbing of the Road | 0.74 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 0.74 |  |  | 100% | 0.74 | Completed
650 | Const. of Hume Pipe Culvert near Sericulture Complex on the road Hmar veng | 6.95 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 3.47 |  | 3.74 | 100% | 6.94 | Completed
651 | Const. of Hume Pipe Culvert near Bellei Lui | 5.7 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 5.7 |  |  | 100% | 5.7 | Completed
652 | Const. of Hume Pipe Culvert near Saidan Primary School | 5.7 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 5.7 |  |  | 100% | 5.7 | Completed
653 | SMBT of Hmarveng Tuikhur to NH-306 | 73.7 | Kolasib Division | 2023-03-23 | 2023-03-24 | 90% | 73.7 |  |  | 90% | 73.7 | Work progress
654 | Resurfacing of Hmarveng to Saidan | 23.23 | Kolasib Division | 2023-03-23 | 2023-03-24 | 10% |  | 90% | 23.23 | 100% | 23.23 | Completed
655 | Hume Pipe Culvert below Pu Pakunga's House | 3.66 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 3.66 |  |  | 100% | 3.66 | Completed
656 | Const. of LSD at Essential places on Hmarveng to Saidan Field. | 5.92 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 5.92 |  |  | 100% | 5.92 | Completed
657 | Upgradation and Resurfacing of Helipad to Lungsumlui. | 19.75 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 19.75 |  |  | 100% | 19.75 | Completed
658 | Const. of LSD at Helipad to Lungsumlui | 1.5 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 1.5 |  |  | 100% | 1.5 | Completed
659 | Road Widening at Helipad to Lungsumlui | 22.71 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 22.7 |  |  | 100% | 22.7 | Completed
660 | Resurfacing of NH-306 to Challui Veng via Galili | 20.3 | Kolasib Division | 2023-03-23 | 2023-03-24 | 90% | 19.39 | 10% | 0.91 | 100% | 20.3 | Completed
661 | Cement Flooring of NH-306 to Challui Veng via Galili | 15.05 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 15.05 |  |  | 100% | 15.05 | Completed
662 | Const. of Retaining Wall near Pu Chuaudingliana's House | 3.62 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 3.62 |  |  | 100% | 3.62 | Completed
663 | Const. of LSD at essential places on NH-306 to Challui Veng via Galili. | 2.97 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 1.48 |  | 1.49 | 100% | 2.97 | Completed
664 | Lowering near Presbyterian Biakin | 1.12 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 0.56 |  |  | 100% | 0.56 | Phy.Completed
665 | PCC Flooring from NH-6 Rengtekawn Kualmawi to Hebron Veng | 28.97 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 28.97 |  |  | 100% | 28.97 | Completed
666 | PCC Flooring from PWD Town road near KVK Compound to Dinthar Vengthar | 28.98 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 14.49 |  |  | 100% | 14.49 | Phy.Completed
667 | Resurfacing of approach road to Electric veng from Banglakawn, Kolasib | 14.72 | Kolasib Division | 01.04.23 | 01.04.24 | 100% | 14.72 |  |  | 100% | 14.72 | Completed
668 | Improvement and Black topping of approach road to Pavillion at Football Playground at Bilkhawthlir | 15.32 | Kolasib Division | 01.04.23 | 01.04.24 | 100% | 15.32 |  |  | 100% | 15.32 | Completed
669 | Construction of Retaining wall at Kawnpui Hmarveng Graveland | 5.23 | Kolasib Division | 01.04.23 | 01.04.24 | 100% | 5.23 |  |  | 100% | 5.23 | Completed
670 | Resurfacing of Mualvum approach road from Chainage 1.150 Kmp to 2.800 Kmp9 Balance Stretch) | 29.45 | Kolasib Division | 01.04.23 | 01.04.24 | 100% | 29.45 |  |  | 100% | 29.45 | Completed
671 | Construction of Masonry Link drain with RCC Slab Cover at PWD Complex, Kawnpui | 4.8 | Kolasib Division | 01.04.23 | 01.04.24 | 100% | 4.8 |  |  | 100% | 4.8 | Completed
672 | Restoration of Shoulder subsidence at Ch: 7.35Kmp on Buhchang to Phaisen: a)Repairing of Rigid pavement from km 7/340 to km 7/370 (Length = 30 m) on Buhchang to Phaisen road in the State of Mizoram | 7.8 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 7.8 |  |  | 100% | 7.8 | Completed
673 | b) Construction of Gabion wall at the side shoulder. | 17.55 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 17.55 |  |  | 100% | 17.55 | Completed
674 | c) Construction of Gabion wall at the Toe of the Slip. | 7.35 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 7.35 |  |  | 100% | 7.35 | Completed
675 | d) Construction of Line Side Drain | 5.9 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 5.9 |  |  | 100% | 5.9 | Completed
Construction of PCC Pavement on Phainuam to Saihapui V (Muddy Portion)
676 | a) Repair of Damage Stretch on approach road to Saihapui V | 18 | Kolasib Division | 01.04.23 | 01.04.24 | 100% | 18 |  |  | 100% | 18 | Completed
677 | b) Construction of Police Camp approach road at Saihapui V | 7 | Kolasib Division | 01.04.23 | 01.04.24 | 100% | 7 |  |  | 100% | 7 | Completed
678 | Patch repair from Thirhruibankawn to Hmarveng via Fire Station | 9.92 | Kolasib Division | 01.04.23 | 01.04.24 | 100% | 9.92 |  |  | 100% | 9.92 | Completed
Const. of Road from Kawnpui to Bukpui Road (Length = 10.00 Kms) under SASCI 2023-2024
679 | Formation Cutting of Kawnpui to Bukpui Link Road. | 94.93 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not yet started | Restricted Tender
680 | Formation Cutting of Lungdai Dursaleng Bamboo Link Road to Tuirial. | 42.36 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not yet started | Restricted Tender
681 | Formation Cutting of Chhimveng Thlanmual to Chemlui (Raichawm zau) Link Road. | 29.65 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not yet started | Restricted Tender
682 | Formation Cutting of Zanlawn to Serlui Link Road | 25.42 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not yet started | Restricted Tender
683 | Formation Cutting/Widening of Ramnghaka Huan Kawn to Rophum Kawn Link Road at Thingdawl. | 17 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not yet started | Restricted Tender
684 | Formation Cutting of Kawnpui PHC to VC-II Field Approach Road. | 12.74 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not yet started | Restricted Tender
685 | Formation Cutting of Bamboo Link Road, Lungmuat to Tuirial. | 8.4 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not yet started | Restricted Tender
686 | Const. of Retaining Wall at N.Chaltlang near UPC Biakin. | 6.78 | Kolasib Division | 16.10.23 | 16.10.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
687 | Const. of RCC Slab Extention at Kawnpui Field No-II | 29.67 | Kolasib Division | 16.10.23 | 16.10.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
Const.of PCC Pavementfrom Hmarveng - Venglai - Diakkawn in Kolasib Town Part "A"
688 | Works within Hmarveng VC area at Different Location. | 27.93 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not yet started | Restricted Tender
689 | Works within Diakkawn VC area at Different Location. | 29.7 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not yet started | Restricted Tender
690 | Works within Khuangpuilam VC area at Different Location. | 11.71 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not yet started | Restricted Tender
691 | Works within New Diakkawn VC Area at Different Location. | 32.87 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not yet started | Restricted Tender
692 | Works within Project Veng VC Area at Different Location. | 33.57 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not yet started | Restricted Tender
693 | Works within Venglai East VC Area at Different Location. | 25.73 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not yet started | Restricted Tender
694 | Works within College Veng VC Area at Different Location. | 20.05 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not yet started | Restricted Tender
695 | Works within Tumpui Veng VC Area at Different Location. | 41.54 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not yet started | Restricted Tender
696 | Works within Electrict Veng VC Area at Different Location. | 18.84 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not yet started | Restricted Tender
697 | Works within Saidan Veng VC Area at Different Location. | 29.07 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not yet started | Restricted Tender
698 | Works within Tuitha Veng VC Area at Different Location. | 20 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not yet started | Restricted Tender
Const. of Rigid Pavement from Vairengte - Bilkhawthlir - Phainuam
699 | Const. of Cement Concrete Pavement from Approach Road to Community Hall at Saiphai. | 33.52 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not yet started | Restricted Tender
700 | Const. of Panelled Concrete Pavement within Saipum Town. | 33.68 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not yet started | Restricted Tender
701 | Const. of PCC Flooring at N.Hlimen | 19.2 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not yet started | Restricted Tender
702 | Const. of PCC Flooring at Thingthelh | 9.61 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not yet started | Restricted Tender
703 | Const. of PCC Flooring at Rengtekawn. | 33.81 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not yet started | Restricted Tender
704 | Const. of PCC Flooring at N.Builum | 4.83 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not yet started | Restricted Tender
705 | Const. of PCC Flooring at Gosen Veng. | 4.83 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not yet started | Restricted Tender
706 | Const. of Panelled Concrete Pavement at Saihapui 'K' | 14.42 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not yet started | Restricted Tender
707 | Const. of Panelled Concrete Pavement at Bukvannei. | 14.24 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not yet started | Restricted Tender
708 | Const. of Panelled Concrete Pavement at N.Thinglian | 4.8 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not yet started | Restricted Tender
709 | Const. of Panelled Concrete Pavement at Buhchangphai | 19.25 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not yet started | Restricted Tender
710 | Const. of Panelled Concrete Pavement at N.Chhimluang | 9.62 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not yet started | Restricted Tender
711 | Const. of Panelled Concrete Pavement at N.Chawnpui | 9.65 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not yet started | Restricted Tender
712 | Const. of Panelled Concrete Pavement at Phaisen | 9.73 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not yet started | Restricted Tender
713 | Const. of Panelled Concrete Pavement at Phainuam | 33.53 | Kolasib Division | 16.10.23 | 16.10.24 | 5.75% |  | 66.75% |  | 72.5% |  | Work in progress | Restricted Tender
714 | Const. of Panelled Concrete Pavement at Saihapui 'V' | 9.58 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not yet started | Restricted Tender
715 | Const. of Panelled Concrete Pavement at Bilkhawthlir | 62.68 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not yet started | Restricted Tender
716 | Const. of Panelled Concrete Pavement at Vairengte | 76.64 | Kolasib Division | 16.10.23 | 16.10.24 | 5% |  | 60.83% |  | 65.83% |  | Work in progress | Restricted Tender
717 | Const. of Formation Cutting at Phainuam to Bilkhawthlir, Buarchep Link Road. | 77.14 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not yet started | Restricted Tender
Const. of PCC Pavement from Hmarveng - Venglai - Diakkawn in Kolasib Town PART "B"
718 | Works within Hmarveng VC Area at Different Location. | 4 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not yet started | Spot Quatation
719 | Works within Venglai VC Area at Different Location. | 11.19 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not yet started | Spot Quatation
720 | Works within Diakkawn VC Area at Different Location. | 15.64 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not yet started | Spot Quatation
721 | Works within Khuangpuilam VC Area at Different Location. | 12.77 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not yet started | Spot Quatation
722 | Works within New Diakkawn VC Area at Different Location. | 16.6 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not yet started | Spot Quatation
723 | Works within Project Veng VC Area at Different Location. | 21.25 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not yet started | Spot Quatation
724 | Works within College Veng VC Area at Different Location. | 11.07 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not yet started | Spot Quatation
725 | Works within Saidan Veng VC Area at Different Location. | 21.57 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not yet started | Spot Quatation
Improvement of roads and Infrastructures at District Headquarters ;( Kolasib District)
726 | Kolasib Town Roads: Resurfacing of Diakkawn Traffic Point to Police Station. | 15 | Kolasib Division | 31.10.23 | 29.02.24 | [6 empty] | Not yet started | Departmental
727 | Patch Repair of Rengtekawn (NH-54) to Bawktlang (New Builum) 132 KV Sub-Station. | 31.5 | Kolasib Division | 31.10.23 | 29.02.24 | [6 empty] | Not yet started | Departmental
728 | Patch Repair Serkhan to Bagha Road. | 70 | Kolasib Division | 31.10.23 | 29.02.24 | [6 empty] | Not yet started | Departmental
729 | Repair of SPT Bridge over R.Chepte & Sesih and Repair of Diversion Road with WBM. | 8.5 | Kolasib Division | 31.10.23 | 29.02.24 |  |  | 70% |  | 70% |  | Work in progress | Departmental
PROJECT DIVISION - I
730 | Extension of Community Hall at Upper Republic | 53 | Project Division-I | 15.3.23 | 15.2.24 | 78% | 39.82 | 2% |  | 80% | 39.82 | Work progress
731 | Construction of RCC slab Dam veng YMA Hall | 4.83 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 4.81 |  |  | 100% | 4.81 | Completed
732 | Construction of Cequered tiles Near Local Council House Bungkawn Vengthar | 1.45 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 1.44 |  |  | 100% | 1.44 | Completed
733 | Construction of Saizahawla Tuikhur near R.Lalrinchhana Field Road | 7.72 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 7.68 |  |  | 100% | 7.68 | Completed
734 | Construction of RCC Structure at Electric Sub-Station, Khatla, Tlawng Road | 4.8 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 4.81 |  |  | 100% | 4.81 | Completed
735 | Laying of Chequered Tiles Between Zonghaka and Sk Thanga's House at Nursery | 2.12 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 2.11 |  |  | 100% | 2.11 | Completed
736 | Laying of Chequered Tiles tetween UPC (Mizoram) and RC Vanlalsawma (L) House at Nursery | 2.69 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 2.69 |  |  | 100% | 2.69 | Completed
737 | Construction of Chequered tiles near Khatla South Presbyterian | 1.43 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 1.43 |  |  | 100% | 1.43 | Completed
738 | Constrcution of Chequered tiles between J.Zangena House and Rinsanga Colney (L) near Khatla's Presbyterian Church | 0.98 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 0.49 |  |  | 100% | 0.49 | Completed
739 | Construction of Step Chequered tiles with Hand Railing near Khatla Pastor Quarter to J.Lianhlira House | 2.84 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 2.84 |  |  | 100% | 2.84 | Completed
740 | Renovation and linement of new Cemetary at Maubawk | 1.24 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 1.25 |  |  | 100% | 1.25 | Completed
741 | Renovation of Kanan Multipurpose Community Hall | 14.42 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 14.21 |  |  | 100% | 14.21 | Completed
742 | Renovation & Repair of Khatla Bazar Building | 3.86 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 3.86 |  |  | 100% | 3.86 | Completed
743 | Renovation of Mission Veng Health Clinic at Mission | 1.93 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 1.93 |  |  | 100% | 1.93 | Completed
744 | Construction of Anganwadi Centre-II, Aizawl | 4.79 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 4.79 |  |  | 100% | 4.79 | Completed
745 | Construction of Basketball Court at Dinthar | 52.99 | Project Division-I | 15.3.23 | 15.2.24 | 15% | 22.22 | 15% |  | 30% | 22.22 | Completed
746 | Construction of Basketball Court at Dinthar | 43.36 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 34.72 |  |  | 100% | 34.72 | Completed
747 | Construction of Basketball Court at Dinthar | 4.82 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 4.81 |  |  | 100% | 4.81 | Completed
748 | Renovation of Futsal Ground including Side Drain at Nursery veng | 4.4 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 4.4 |  |  | 100% | 4.4 | Contingencies of works
749 | Upgradation of Chief Minister Staff Quarter ( 5 nos of Quarters Phase-I | 193 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 177.42 |  | 13.65 | 100% | 191.07 | Completed
750 | Upgradation of Chief Minister Staff Quarter(5 nos of Qtrs Phase-II) | 95 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 78.89 |  |  | 100% | 78.89 | Completed | EPC
751 | Constructuction of Gov"t Staff Qtrs ( Block-C) at DIET Complex. | 544 | Project Division - I | 10.05.2023 | 10.05.2025 | 47% | 21.63 |  | 68.55 | 47% | 90.18 | Work in progress | EPC
752 | C/O Food Civil Supplies & Consumer Affairs 1500MTGodown at Sairang | 921 | Project Division - I | 20.4.23 | 20.4.26 | 15% |  |  |  | 15% |  | Work in progress | EPC
HMUIFANG DIVISION :
753 | Improvement & Strengthening of Aibawk-Darlung Road for 4.000-14.000 Kmp in Mizoram for the year 2022-2023 | 547 | Hmuifang Division | 20.12.23 | 31.03.23 | 78.45% | 331.3 | 1.55% | 87.9 | 80% | 419.2 | Work in progress
754 | Construction of Agriculture Link Road for Thingzam Zau, Tuirial Lui | 269.6 | Hmuifang Division | 15.02.23 | 14.05.23 | 100% | 218.43 |  | 29.49 | 100% | 247.92 | Completed
755 | Contsruction of Upgradation of Aizawl-Thenzawl-Lunglei Road 5.00 kmp-100.00 Kmp | 206 | Hmuifang Division | 15.02.23 | 14.05.23 | 100% | 158.25 |  | 19.31 | 100% | 177.56 | Phy.Completed
KHAWZAWL DIVISION
756 | Strengthening of approach road to IR Headquarter of Khawzawl in Mizoram for the year 2022-2023 under SASCI | 401 | Khawzawl Division | 15.02.23 | 30.06.23 | 100% | 369.38 |  | 11.63 | 100% | 381.01 | Phy.Completed | Departme-ntal
757 | Improvement of Farmual road at Khawzawl in Mizoram for the year 2022-2023 under SASCI | 343.5 | Khawzawl Division | 16.02.23 | 30.06.23 | 100% | 192.77 |  | 133.07 | 100% | 325.84 | Completed. | Departme-ntal
758 | Contsruction /Upgradation of Road from NE Khawdungsei-Tuivai-Mimbung in Mizoram for the year 2022-2023 under SASCI | 377 | Khawzawl Division | 15.02.23 | 31.03.23 | 100% | 281.33 |  | 6.97 | 100% | 288.3 | Phy.Completed | Spot Quotation
759 | Construction of Kawlkulh Bypass Road | 805 | Khawzawl Division | 01.02.23 | 30.06.23 | 21% | 276.13 |  | 51.57 | 21% | 327.7 | Work in progress | Restricted Tender
760 | Construction of road from Hliappui-Aiduzawl-Neihdawn in Mizoram for the year 2022-2023 under SASCI | 340 | Khawzawl Division | 15.02.23 | 30.06.23 | 100% | 316.04 |  |  | 100% | 316.04 | Phy.Completed | Restricted Tender
761 | Improvement & Strengthening of Vengthar Bazar toVengsang Presby. Church via Taidawnkawn at Khawzawl(Length: 7.50 KM) | 291 | Khawzawl Division | 3.10.23 | 3.4.24 | 23% |  | 13% |  | 36% |  | Work in progress | Spot Quotation
762 | Improvement of road at Chawngtlai - Biate - Ngopa- Khawhai & Pawlrang to Luangpawn | 377 | Khawzawl Division | 3.10.23 | 3.4.24 | 10% |  | 4% |  | 14% |  | Work in progress | Spot Quotation
763 | Const. of Agricultural Link road to Keltan Zau, Sihphai, Dawlzang, Lamzawl. (Length-8 Kms) | 229 | Khawzawl Division | 5.10.23 | 5.10.24 | 42% |  |  |  | 42% |  | Work in progress | Spot Quotation
764 | Improvement of roads and Infrastructures at District Headquarters ; Saiha, Lawngtlai, Lunglei, Hnahthial, Serchhip, Champhai, Khawzawl, Saitual, Kolasib and Mamit. | 168.7 | Khawzawl Division |  |  | 91% |  |  |  | 91% |  | Completed. (Committed Liability) | Spot Quotation
SAITUAL DIVISION :
765 | A.Section-I 1) Strengthening of Saitual-Phullen Road (28.30) Tuivawl-Phullen | 139.71 | Saitual Division | 13.2.2023 | 31.3.24 | 100% | 139.71 |  |  | 100% | 139.71 | Completed
766 | B.Section-II 1) Construction of concrete pavement between PWB IB to Thlanmual at Suangpuilawn & Improvement of Internal Roads | 28.98 | Saitual Division | 13.2.2023 | 31.3.24 | 100% | 28.98 |  |  | 100% | 28.98 | Completed
767 | 2) Construction of concrete pavement between Pu Zodinmawia's House to Lalsangbera's House at Vangbawng & Improvement of Internal Roads & Playground | 24.15 | Saitual Division | 13.2.23 | 31.3.24 | 100% | 24.15 | - |  | 100% | 24.15 | Completed
768 | 3) Construction of concrete pavement between RMSA school to Main road at Lamherh | 14.49 | Saitual Division | 13.2.23 | 31.3.24 | 100% | 14.49 | - |  | 100% | 14.49 | Completed
769 | 4) Construction and widening of road between N.Khawlek to Tuivawl Kai at N.Khawlek & Improvement of Internal Roads | 52.17 | Saitual Division | 13.2.23 | 31.3.24 | 100% | 52.17 | - |  | 100% | 52.17 | Completed
770 | 5) Construction of concrete pavement between Dawrkawn to High school at Khawlian & Improvement of Internal Roads | 35.75 | Saitual Division | 13.2.23 | 31.3.24 | 100% | 35.75 | - |  | 100% | 35.75 | Completed
771 | 6) Construction of concrete pavement between Anganwadi Centre I to YMA road at Phaibuang & Improvement of Internal Roads | 33.81 | Saitual Division | 13.2.23 | 31.3.24 | 100% | 33.81 |  |  | 100% | 33.81 | Completed
772 | 7) Construction of Approach Road to CC Puk at Luangpawn | 16.42 | Saitual Division | 13.2.23 | 31.3.24 | 100% | 16.42 |  |  | 100% | 16.42 | Completed
773 | 8) Construction of Community Hall at Phullen (Formation cutting and Retaining Wall) & Improvement of Internal Roads | 33.81 | Saitual Division | 13.2.23 | 31.3.24 | 100% | 33.81 |  |  | 100% | 33.81 | Completed
774 | 9) Widening of Mualkhang Road, Sihfa & Improvement of Internal Roads | 38.65 | Saitual Division | 13.2.23 | 31.3.24 | 100% | 38.65 | - |  | 100% | 38.65 | Completed
775 | 10) Improvement of High School Road, Daido | 9.66 | Saitual Division | 12.2.23 | 31.3.23 | 100% | 9.66 | - |  | 100% | 9.66 | Completed
776 | 11) PCC Flooring of Public Field Approach Road, Lailak & Improvement of Internal Roads | 19.32 | Saitual Division | 12.3.23 | 31.3.24 | 100% | 19.32 | - |  | 100% | 19.32 | Completed
| Improvement of Mualpheng to Maite Road |  | Saitual Division | 13.2.23 | 31.3.23 | 100% |  |  |  | 100%
777 | A.Section-I 1) Construction of Retaining Wall between main Road to Village extension peng at NE Tlangnuam | 9.66 |  |  |  |  | 9.66 |  |  |  | 9.66 | Completed
778 | 2) Widening cum PCC Flooring of Thlanmual Kawng. Thanglailung & Improvement of Internal Roads | 23.21 | Saitual Division | 13.2.23 | 31.3.23 | 100% | 23.21 | - |  | 100% | 23.21 | Completed
779 | 3) Formation cutting from Buhban to Tuivawl Road, Buhban | 28.98 | Saitual Division | 13.2.23 | 31.3.23 | 100% | 28.98 | - |  | 100% | 28.98 | Completed
780 | 4) PCC Flooring from Catholic Church to Presbyterian Church, Dilkhan & Improvement of Internal Roads | 14.49 | Saitual Division | 13.2.23 | 31.3.23 | 100% | 14.49 | - |  | 100% | 14.49 | Completed
781 | 5) PCC Flooring from Main Road to High School Road, N.Lungpher & Improvement of Internal Roads | 20.29 | Saitual Division | 13.2.23 | 31.3.23 | 100% | 20.29 | - |  | 100% | 20.29 | Completed
782 | 6) Construction of concrete pavement between Hmundo to Tuivawl at Zawngin & Improvement of Internal Roads | 19.32 | Saitual Division | 13.2.23 | 31.3.23 | 100% | 19.32 |  |  | 100% | 19.32 | Completed
783 | 7) Formation cutting of Khanpui road to Tlanghmawr Approach Road, Tualbung & Improvement of Internal Roads | 19.32 | Saitual Division | 13.2.23 | 31.3.23 | 100% | 19.32 | - |  | 100% | 19.32 | Completed
784 | B.Section-II 1) Resurfacing of Rulchawm to Ruallung | 85.64 | Saitual Division | 13.2.23 | 31.3.23 | 96% | 82.21 |  |  | 96% | 82.21 | Completed
785 | 2) Construction of Retaining Wall at 2.300 Km on Rulchawm - Mualpheng Road | 1.71 | Saitual Division | 13.2.23 | 31.3.23 | 100% | 1.71 | - |  | 100% | 1.71 | Completed
786 | 3) Construction of Retaining Wall at 2.50 Km on Rulchawm - Mualpheng Road | 5.32 | Saitual Division | 13.2.23 | 31.3.23 | 100% | 5032 | - |  | 100% | 5.32 | Completed
787 | 4) Construction of Retaining Wall at 4.70 Km on Rulchawm - Mualpheng Road | 3.55 | Saitual Division | 13.2.23 | 31.3.23 | 100% | 3.55 |  |  | 100% | 3.55 | Completed
788 | 5) Construction of Retaining Wall at 18.800 Km on Mualpheng - Maite Road | 3.34 | Saitual Division | 13.2.23 | 31.3.23 | 100% | 3.34 |  |  | 100% | 3.34 | Completed
789 | 6) Resurfacing of Ruallung - Maite Road up to Mualpheng | 211.69 | Saitual Division | 13.2.23 | 31.3.23 | 96% | 203.22 |  |  | 96% | 203.22 | Completed
790 | 7) Construction of RCC Side Drain between 0.400Km and 1.000 Km on Helipad Road, Saitual | 19.24 | Saitual Division | 13.2.23 | 31.3.23 | 100% | 19.24 |  |  | 100% | 19.24 | Completed
791 | 8) Construction of V Shape RCC Side Drain between 1.000 Km and 2.000 Km on Helipad Road, Saitual | 50.62 | Saitual Division | 13.2.23 | 31.3.23 | 100% | 50.62 |  |  | 100% | 50.62 | Completed
792 | 9) Construction of Retaining Wall at 18.900 Km on Mualpheng - Maite Road | 3.34 | Saitual Division | 13.2.23 | 31.3.23 | 100% | 3.34 |  |  | 100% | 3.34 | Completed
793 | 10) Construction of Retaining Wall at 0.70Km on Helipad Road, Saitual | 2.17 | Saitual Division | 13.2.23 | 31.3.23 | 100% | 2.17 |  |  | 100% | 2.17 | Completed
794 | 11) Construction of Retaining Wall at 0.90 Km on Helipad Road, Saitual | 2.22 | Saitual Division | 13.2.23 | 31.3.23 | 100% | 2.22 |  |  | 100% | 2.22 | Completed
795 | 12) Construction of Retaining Wall at 15.350 Km on Mualpheng - Maite Road | 4.28 | Saitual Division | 13.2.23 | 31.3.23 | 100% | 4.28 |  |  | 100% | 4.28 | Completed
796 | 13) Construction of RCC Covered Cross Drain at 1.250 Km on Helipad Road, Saitual | 2.67 | Saitual Division | 13.2.23 | 31.3.23 | 100% | 2.67 |  |  | 100% | 2.67 | Completed
797 | 14) Construction of Rigid Pavement of DC Complex Road, Saitual | 183.86 | Saitual Division | 13.2.23 | 31.3.23 | 100% | 183.86 |  |  | 100% | 183.86 | Completed
TLABUNG DIVISION :
| Strengthening of Phairuang - Thenhlum Road Group-A | 5.81 | Tlabung Division | 2023-03-01 | March-2024 | 100% | 2.65 |  | 2.64 | 100% | 5.29 | Completed Phy.Works
798 | 1. Excavation for Structure (Earth work in excavation of foundation of structures as per drawing and technical specification, including setting out I. Ordinary soil (upto 3m depth)
799 | 2. Plain/Reinforced cement concrete in sub-structure complete as per drawing and technical specifications, A.PCC Grade Grade M15 Nominal mix 1:3:6 (hand mixing) | 4.35 | Tlabung Division | 2023-03-23 | March-2024 | 100% | 2.02 |  | 2.01 | 100% | 4.03 | Completed Phy.Works
800 | 3. Stone Masonry work in cement mortar for substructure complete as per drawing and Technical Specifications II. Course rublle masonry (1st sort) iii) in cement mortar 1:3 | 15.75 | Tlabung Division | March 2023 | March-2024 | 100% | 7.45 |  | 7.45 | 100% | 14.9 | Completed Phy.Works
801 | 4. Providing and laying filter media with granular crush aggregates as per specification to a tickness of not less than 600mm | 4.34 | Tlabung Division | March 2023 | March-2024 | 100% | 2.02 |  | 2.02 | 100% | 4.04 | Completed Phy.Works
802 | 5. Restoration of Rain Cuts (Restoration of rain cuts with soil, moorum, gravel or a mixture of these, clearing the loose soil, benching for 300mm width | 0.82 | Tlabung Division | March 2023 | March-2024 | 100% | 0.38 |  | 0.38 | 100% | 0.76 | Completed Phy.Works
803 | 6. Cement Concrete Pavement with a provision of edge stone (Construction of un-reinforced, dowel jointed, plain cement concrete pavement over a prepared sub base with 43 grade cement | 18.19 | Tlabung Division | March 2023 | March-2024 | 100% | 6 |  | 6 | 100% | 12 | Completed Phy.Works
804 | 7. PCC 1:3:6 in Foundation (Plain cement concrete 1:3:6 nominal mix in foundation with crushed stone aggregate 40mm nominal size mechanically mixed, placed in foundation and compacted by vibration including curing 14 dyas) | 18.97 | Tlabung Division | March 2023 | March-2025 | 100% | 8.35 |  | 8.34 | 100% | 16.69 | Completed Phy.Works
805 | 8. Plain/Reinforced cement concrete in open foundation complete as per drawing and techincal specifications A.PCC Grade M15 | 8.55 | Tlabung Division | March 2023 | March-2024 | 100% | 3.98 |  | 3.98 | 100% | 7.96 | Completed Phy.Works
806 | 9. Earthwork in exvacation in foundation trenches etc.not exceeding 2 meters depth including dressing of bottom and sides of trenches Hard soil (Pick work) | 0.84 | Tlabung Division | March 2023 | March-2024 | 100% | 0.39 |  | 0.39 | 100% | 0.78 | Completed Phy.Works
807 | 10. Filling available excavated earth (excluding rock) in trenches, plinth, sides of foundations etc.in layers not exceeding 20cm in depth | 0.01 | Tlabung Division | March 2023 | March-2024 | 100% | 0.004 |  | 0.006 | 100% | 0.01 | Completed
808 | 11. Providing and laying cement concrete in retaining wall, return walls, walls (any thickness) including pilasters, 1:3:6 (1 cement: 3 course sand: 6 stone aggregate 40mm) | 0.52 | Tlabung Division | March 2023 | March-2024 | 100% | 0.24 |  | 0.23 | 100% | 0.47 | Completed Phy.Works
809 | 12. Steel reinforcement for RCC work including straighthening, cutting, bending, placing in position and binding all complete. Mild steel and medium Tensile steel bars | 2.33 | Tlabung Division | March 2023 | March-2024 | 100% | 1.08 |  | 1.07 | 100% | 2.15 | Completed Phy.Works
810 | 13. Providing, fitting and placing GI pipe 100mm dia | 5.07 | Tlabung Division | March 2023 | March-2024 | 100% | 2.36 |  | 2.35 | 100% | 4.71 | Completed Phy.Works
811 | 14 Excavation in soil by Manual Means (Excavation for roadway in soil using manual means including loading in truck for carrying of cut earth to embankment site with all lifts and lead upto 1000 meters | 0.45 | Tlabung Division | March 2023 | March-2024 | 100% | 0.21 |  | 0.21 | 100% | 0.42 | Completed Phy.Works
812 | 15. Stone Masonry work in cement mortar in foundation complete as per drawing and technical specifications clauses 702, 704, 1202 & 1203. II. Coursed rubble masonry ii) In 1:4 cement mortar | 10.45 | Tlabung Division | March 2023 | March-2024 | 100% | 6.72 |  | 6.71 | 100% | 13.43 | Completed
813 | 16. Providing and laying in position cement concrete of specified grade excluding cost of centering and shuttering-All work upto plinth level: 1:2:4 (Cement:2 course sand: 4 stone aggregate 20mm nominal size) | 2.21 | Tlabung Division | March 2023 | March-2024 | 100% | 1.03 |  | 1.02 | 100% | 2.05 | Completed Phy.Works
814 | 17. Providing and laying in position reinforced cement concrete excluding cost of centering and shuttering, finishing and reinforcement in- 1:2:4 (1 cement: 2 coarse sand:4 graded stone aggregate 20mm nominal size) | 0.47 | Tlabung Division | March 2023 | March-2024 | 100% | 0.22 |  | 0.21 | 100% | 0.43 | Completed Phy.Works
815 | 18. First class brickwork in foundation and plinth in: (b) in cement mortar 1:4 | 4.46 | Tlabung Division | March 2023 | March-2024 | 100% | 2.07 |  | 2.06 | 100% | 4.13 | Completed Phy.Works
816 | 19. Providing 1st class local wood in trusses etc.including purlin, hoisting fixingf in position supplying necessary fittings such as spikes bolts and nuts, nails etc and applying wood preservative for unexposed surface etc.complete | 0.7 | Tlabung Division | March 2023 | March-2024 | 100% | 0.33 |  | 0.32 | 100% | 0.65 | Completed Phy.Works
817 | 20. Providing corrugated G.S sheet roofing fixed with polymer coated J or L hooks, bolts and nuts 8mm diameter with nitumen and G.I limpet washers or with G.I limpet washers filled with white lead and including a coat of approved steel primer 0.80mm thick with zinc coating not less than 275gm/m2 | 0.65 | Tlabung Division | March 2023 | March-2024 | 100% | 0.33 |  | 0.32 | 100% | 0.65 | Completed Phy.Works
818 | 21. Providing and fixing 1st class teak wood panelled and glazed shutters using 4mm thick plate sneet glass for doors and windows etc.including M.S butt hinges with necessary screws etc. complete | 1.2 | Tlabung Division | March 2023 | March-2024 | 100% | 0.52 |  | 0.51 | 100% | 1.03 | Completed Phy.Works
819 | 22. Painting with synthetic enamel paint of approved brand and manufacture in all shades on new work. (two or more coats) | 0.22 | Tlabung Division | March 2023 | March-2024 | 100% | 0.14 |  | 0.14 | 100% | 0.28 | Completed Phy.Works
820 | 23. Supplying, fitting and placing HTSD bar reinforcement in sub-structure complete as per drawing and technical specifications | 19.1 | Tlabung Division | March 2023 | March-2024 | 100% | 9.05 |  | 9.05 | 100% | 18.1 | Completed Phy.Works
821 | 24. Providing and laying reinforce cement concrete in super structure as per drawing and technical specifications clause 800, 1205.4 and 1205.5 II. RCC M25 grade | 2.1 | Tlabung Division | March 2023 | March-2024 | 100% | 1.12 |  | 1.11 | 100% | 2.23 | Completed Phy.Works
822 | 25. Backfilling in abutment, wing wall and return wall complete as per drawing and technical specification clause 1204.3.8 I. Granular material | 1.46 | Tlabung Division | March 2023 | March-2024 | 100% | 0.68 |  | 0.67 | 100% | 1.35 | Completed Phy.Works
823 | 26. Stone masonry in cement mortar 1:3 for parapet complete as per drawing and technical specifications Clasues 700 and 1208.4 A.Random rubble masonry | 0.36 | Tlabung Division | March 2023 | March-2024 | 100% | 0.17 |  | 0.16 | 100% | 0.33 | Completed Phy.Works
824 | 27. Plastering with cement mortar (1:4) 15mm thick on Brick/Stone works as per drawing and technical specification clauses 613.4 and 1204 | 0.85 | Tlabung Division | March 2023 | March-2024 | 100% | 0.4 |  | 0.4 | 100% | 0.8 | Completed Phy.Works
825 | 28. Providing 1st class local wood work dressed in frames of sill, upright, batten, post, beams etc. as structural members fixed in position complete | 0.94 | Tlabung Division | March 2023 | March-2024 | 100% | 0.44 |  | 0.43 | 100% | 0.87 | Completed Phy.Works
826 | 29. Providing 2nd class local wood work dressed in frames of chaukut for doors, windows, clerestory windows fixed in postion | 0.2 | Tlabung Division | March 2023 | March-2024 | 100% | 0.09 |  | 0.08 | 100% | 0.17 | Completed Phy.Works
827 | 30. Providing and fixing 25mm thick and 2nd class local wood plank walling (both sides planned) tongue and groove joints including necessary nails, screws, etc.complete | 0.84 | Tlabung Division | March 2023 | March-2024 | 100% | 0.39 |  | 0.39 | 100% | 0.78 | Completed Phy.Works
828 | 31. Providing and fixing MS handles with necessary screws etc (a) 150mm | 0.01 | Tlabung Division | March 2023 | March-2024 | 100% | 0.002 |  | 0.003 | 100% | 0.005 | Completed Phy.Works
829 | 32. Providing and fixing MS hooks and eyes (a) 200mm | 0 | Tlabung Division | March 2023 | March-2024 | 100% | 0.0002 |  | 0.0003 | 100% | 0.0005 | Completed Phy.Works
830 | 33. Providing and fixing MS tower bolts (socket bolts) bright finished with necessary screws etc. (a) 200mm | 0.03 | Tlabung Division | March 2023 | March-2024 | 100% | 0.1 |  | 0.1 | 100% | 0.2 | Completed Phy.Works
831 | (b) 150mm | 0 | Tlabung Division | March 2023 | March-2024 | 100% | 0.0001 |  | 0.0001 | 100% | 0.0002 | Completed Phy.Works
832 | 34. Earthwork in excavation for foundation of structures upto 3m depth as per drawing and technical specification | 0.8 | Tlabung Division | March 2023 | March-2024 | 100% | 0.35 |  | 0.35 | 100% | 0.7 | Completed Phy.Works
833 | 35. Providing cement concrete M10 (1:3:6) in levelling cpurse below open foundation of head wall as per drawing and technical specification clause 1109. I. PCC grade M10 Mominal mix 1:3:6 (hand mixing) | 1.2 | Tlabung Division | March 2023 | March-2024 | 100% | 0.56 |  | 0.57 | 100% | 1.13 | Completed Phy.Works
834 | 36. Stone Masonry Work in cement mortar in foundation of head walls complete as per drawing and technical specification Clause 1109 (A) in 1:4 cement Mortar | 5.64 | Tlabung Division | March 2023 | March-2024 | 100% | 3.45 |  | 3.44 | 100% | 6.89 | Completed Phy.Works
835 | 37. Type-B (First class) bedding: Lating (first class) bedding of well compacted sand, moorum or approved granular materials as per clause 1105 (ii) | 0.14 | Tlabung Division | March 2023 | March-2024 | 100% | 0.07 |  | 0.07 | 100% | 0.14 | Completed Phy.Works
836 | 38. Providng and laying RCC Pipe NP3 for Culvert on first class bedding of granular material | 4.74 | Tlabung Division | March 2023 | March-2024 | 100% | 2.25 |  | 2.24 | 100% | 4.49 | Completed Phy.Works
837 | 39. Backfilling in abutment, wing wall and return wall complete as drawing and technical specification clause 1204.3.8 I. Granular material | 0.85 | Tlabung Division | March 2023 | March-2024 | 100% | 0.42 |  | 0.41 | 100% | 0.83 | Completed Phy.Works
838 | 40. Backfilling in Foundation Trenches as per drawing and techniical specification Clause 1108 II. Earth filling | 0.05 | Tlabung Division | March 2023 | March-2024 | 100% | 0.02 |  | 0.01 | 100% | 0.03 | Completed Phy.Works
839 | 41. Stone masonry in cement mortar 1:3 for parapet complete I. Random rubble masonry | 0.25 | Tlabung Division | March 2023 | March-2024 | 100% | 0.12 |  | 0.11 | 100% | 0.23 | Completed Phy.Works
840 | 42. Plastering with cement mortar (1:4) 15mm thick on Brick/Stone works | 0.08 | Tlabung Division | March 2023 | March-2024 | 100% | 0.04 |  | 0.03 | 100% | 0.07 | Completed Phy.Works
841 | 43. Providing PCC M20 architectural coping on the top of retaining wall complete between parapet walls | 0.13 | Tlabung Division | March 2023 | March-2024 | 100% | 0.06 |  | 0.06 | 100% | 0.12 | Completed Phy.Works
| Sttrengthening of Phairuangkai-Thenhlum Road Group-B | 1.79 | Tlabung Division | March 2023 | March-2024 | 100% | 0.83 |  | 0.83 | 100% | 1.66 | Completed Phy.Works
842 | 1. Clearing and Grubbing Road Land. (Clearing and gribbing road land including uprooting rank vegetation, grass, bushes, shribs, sapling and tress girth up to 300 mm, removal of stumps of tree cut earlier By Manual Means:- In area of thorny jungle
2. Cutting of Tress, including cutting of Trunks, Branches and Removal (Cutting of tress, including cutting of trunks, branches and removal of stumps, roots, stacking
843 | Girth from 300mm to 600mm | 0.09 | Tlabung Division | Mar'23 | Mar'24 | 100% | 0.04 |  | 0.04 | 100% | 0.08 | Phy.completed
844 | Girth from 600mm to 900mm | 0.07 | Tlabung Division | Mar'23 | Mar'24 | 100% | 0.03 |  | 0.04 | 100% | 0.07 | Phy.completed
845 | Girth from 900mm to 1800 | 0.12 | Tlabung Division | Mar'23 | Mar'24 | 100% | 0.06 |  | 0.06 | 100% | 0.12 | Phy.completed
846 | 3. Excavation in Soil by Mechanical means (Excavation for road way in soil by mechanical means including cutting | 12.88 | Tlabung Division | Mar'23 | Mar'24 | 100% | 5.99 |  | 5.99 | 100% | 11.98 | Phy.completed
847 | 4. Excavation in Ordinary Roak by Mechanical means (Excavation for roadway in ordinary rock by mechanical menas including cutting and pushing the earth | 9.46 | Tlabung Division | March 2023 | March-2024 | 100% | 4.4 |  | 4.4 | 100% | 8.8 | Completed Phy.Works
848 | 5. Restoration of Rain Cuts (Restoration of rain cuts with soil, moorum, gravel or a mixture of these, clearing the loose soil | 0.69 | Tlabung Division | March 2023 | March-2024 | 100% | 0.32 |  | 0.32 | 100% | 0.64 | Completed Phy.Works
849 | 6. Cement Concrete Pavement with a provision of edge stone (Construction of un-reinforced, dowel jointed, plain cement concrete pavement over a prepared sub base with 43 grade cement @400 kg per cum | 38.16 | Tlabung Division | March 2023 | March-2024 | 100% | 17.74 |  | 17.74 | 100% | 35.48 | Completed Phy.Works
850 | 7. Excavation of structures (Earth work in excavtion of foundation of structures as per drawing and technical specification, including setting out, construction of shoring and bracing, removal of stumps and other deleterious matter, dressing of sides and bottom and backfilling with approved material) I. Orinary soil (upto 3m depth) | 11.16 | Tlabung Division | March 2023 | March-2024 | 100% | 5.23 |  | 5.23 | 100% | 10.46 | Completed Phy.Works
851 | 8. Earthwork in excavation in foundation trenches etc, not exceeding 2 meters depth including dressing of bottom and sides of trenches Hard soil (pick work) | 0.66 | Tlabung Division | March 2023 | March-2024 | 100% | 0.31 |  | 0.31 | 100% | 0.62 | Completed Phy.Works
852 | 9. Excavation in Soil by Manual Means (Excavation for roadway in soil using manual means including loading in truck for carrying of cut earth to embankment site with all lifts and lead upto 1000 metres) | 0.5 | Tlabung Division | March 2023 | March-2024 | 100% | 0.23 |  | 0.23 | 100% | 0.46 | Completed Phy.Works
853 | 10. PCC 1:3:6 in Foundation (Plain cement concrete 1:3:6 nominal mix in foundation with crushed stone aggregate 40mm nominal size mechanical mixed, placed in foundation and compacted by vibration including curing for 14 days) | 20.18 | Tlabung Division | March 2023 | March-2024 | 100% | 9.38 |  | 9.38 | 100% | 18.76 | Completed Phy.Works
854 | 11. Plain/Reinforced cement concrete in sub-structure complete as per drawing and technical specifications A. PCC Grade M15 Nominal mix 1:3:6 (hand mixing) | 10.94 | Tlabung Division | March 2023 | March-2024 | 100% | 5.09 |  | 5.09 | 100% | 10.18 | Completed Phy.Works
855 | 12. Providing and laying in position reinforced cement concrete exluding cost of centering and shuttering, finishing and reinforcement in - 1:2:4 (1 cement:2 coarse sand: 4 graded stone aggregate) | 0.79 | Tlabung Division | March 2023 | March-2024 | 100% | 0.37 |  | 0.37 | 100% | 0.74 | Completed Phy.Works
856 | 13. Plain/Reinforced cement concrete in open foundation complete as per drawing and technical specifications A. PCC Grade M15 | 17.22 | Tlabung Division | March 2023 | March-2024 | 100% | 8.02 |  | 8.01 | 100% | 16.03 | Completed Phy.Works
857 | 14. Providing and laying in position cement concrete of specified grade excluding cost of centering and shuttering - All work upto plinth level: 1:2:4 (1 cement:2 coarse sand: 4 graded stone aggregate 20mm nominal size) | 1.23 | Tlabung Division | March 2023 | March-2024 | 100% | 0.57 |  | 0.57 | 100% | 1.14 | Completed Phy.Works
858 | 15. Stone Masonry work in cement mortar for substructure complete as per drawing and Technical specifications II. Course rubble masonry (1st sort) (iii) in cement mortar 1:3 | 47.05 | Tlabung Division | March 2023 | March-2024 | 100% | 21.98 |  | 21.98 | 100% | 43.96 | Completed Phy.Works
859 | 16. Complete as per drawing and technical specifications claises 702, 704, 1202 & 1203 II. Coursed rubble masonry (ii) In 1:4 cement mortar | 11.35 | Tlabung Division | March 2023 | March-2024 | 100% | 5.29 |  | 5.29 | 100% | 10.58 | Completed Phy.Works
860 | 17. Stone Masonry in cement mortar 1:3 for parapet complete as per drawing and technical specifications A.Random rubble masonry | 0.07 | Tlabung Division | March 2023 | March-2024 | 100% | 0.04 |  | 0.03 | 100% | 0.07 | Completed Phy.Works
861 | 18. Providing and laying filter media with granular crush aggregates as per specification to a thickness of not less than 600mm | 7.29 | Tlabung Division | March 2023 | March-2024 | 100% | 3.39 |  | 3.39 | 100% | 6.78 | Completed Phy.Works
862 | 19. Backfilling in abutment, wing wall and return wall complete as per drawing and technical specification I. Granular material | 0.46 | Tlabung Division | March 2023 | March-2024 | 100% | 0.21 |  | 0.21 | 100% | 0.42 | Completed Phy.Works
863 | 20. Filling available excavated earth (excluding rock) in trenches, plinth, sides of foundation etc. in layers not exceeding 20cm in depth, consolidating each deposited layer by ramming and watering, lead up to 50m and lift upto 15m | 1.01 | Tlabung Division | March 2023 | March-2024 | 100% | 0.004 |  | 0.006 | 100% | 0.01 | Completed Phy.Works
864 | 21. Providing and laying cement concrete in retaining wall, return walls, walls (any thickness) including pilasters, piers, columns, abutments, pillars, posts, 1:3:6 (1 cement : 3 course sand : 6 stone aggregate 40mm) | 0.62 | Tlabung Division | March 2023 | March-2024 | 100% | 0.29 |  | 0.29 | 100% | 0.58 | Completed Phy.Works
865 | 22. Plastering with cement mortar (1:4) 15mm thick on Brick/Stone works as per drawing and technical specification clauses 613.4 and 1204 | 0.58 | Tlabung Division | March 2023 | March-2024 | 100% | 0.27 |  | 0.27 | 100% | 0.54 | Completed Phy.Works
866 | 23. Providing and laying reinforced cement concrete 1:2:4 (b) Column, etc | 0.13 | Tlabung Division | March 2023 | March-2024 | 100% | 0.06 |  | 0.06 | 100% | 0.12 | Completed Phy.Works
867 | 24. Providing and laying reinforce cement concrete in super structure as per drawing and technical specifications clause 800, 1205.4 and 1205.5 II. RCC M25 grade | 0.79 | Tlabung Division | March 2023 | March-2024 | 100% | 0.47 |  | 0.48 | 100% | 0.95 | Completed Phy.Works
868 | 25. Steel reinforcement for RCC work including straighthening cutting, bending, placing in position and binding all complete Mild steel and Medium Tensile steel bars | 3.82 | Tlabung Division | March 2023 | March-2024 | 100% | 1.78 |  | 1.79 | 100% | 3.57 | Completed Phy.Works
869 | 26. Supplying, fitting and placing HYSD bar reinforcement in sub-structure complete as per drawing and technical specifications | 1.6 | Tlabung Division | March 2023 | March-2024 | 100% | 0.75 |  | 0.75 | 100% | 1.5 | Completed Phy.Works
870 | 27. Providing, fitting and placing GI pipe 100mm dia | 6.14 | Tlabung Division | March 2023 | March-2024 | 100% | 2.87 |  | 2.87 | 100% | 5.74 | Completed Phy.Works
871 | 28. Providing and fixing G.I Union in existing G.I pipeline, cutting and threading the pipe and making long screws including excavation refilling the earth or cutting of wall and making good the same complete wherever required. (f) 50mm nominal size | 0.01 | Tlabung Division | March 2023 | March-2024 | 100% | 0.01 |  |  | 100% | 0.01 | Completed Phy.Works
872 | 29. First class brickwork in foundation and plinth in: (b) in cement mortar 1:4 | 3.19 | Tlabung Division | March 2023 | March-2024 | 100% | 1.48 |  | 1.47 | 100% | 2.97 | Completed Phy.Works
873 | 30. Providing 1st class local wood in trusses etc.including purlin, hosting fixing in position supplying necessary fittings such as spikes bolts and nuts, nails etc and applying wood preservative for unexposed surface etc. complete | 1.49 | Tlabung Division | March 2023 | March-2024 | 100% | 0.69 |  | 0.7 | 100% | 1.39 | Completed Phy.Works
874 | 31. Providing and fixing 1st class teak wood pannelled and glazed shutters using 4mm thick plate sneet glass for doors and windows etc.including M.S butt hinges with necessary screws etc. comoplete | 0.34 | Tlabung Division | March 2023 | March-2024 | 100% | 0.16 |  | 0.15 | 100% | 0.31 | Completed Phy.Works
875 | 32. Providing corrugated G.S sheet roofing fixed with polymer coated J or L hooks, bolts and nuts 8mm diameter with bitumenn and G.I limpet washers 0.80 mm thick with zinc coating not less than 275gm/m2 | 0.71 | Tlabung Division | March 2023 | March-2024 | 100% | 0.36 |  | 0.35 | 100% | 0.71 | Completed Phy.Works
876 | 33. Painting with synthetic enamel paint of approved brand and manufacture in all shades on new work (two or more coats) | 0.12 | Tlabung Division | March 2023 | March-2024 | 100% | 0.06 |  | 0.05 | 100% | 0.11 | Completed Phy.Works
| Strenthening of Phairungkai-Thenhlum Road Group C | 1.71 | Tlabung Division | March 2023 | March-2024 | 100% | 0.86 |  |  | 100% | 1.72 | Completed Phy.Works
877 | 1. Construction of Subgrade and Earthen Shoulders (Construction of subgrade and eartheh shoulders with approved material obtained from borrow pits with all lifts & leads | [7 empty] | 0.86
878 | 2. Water Bound Macadam (Providng, laying, spreading and compactinf stone aggregates of specific sizes to water bound macadan specification including spreading in uniform thickness, A. By Manual Means (ii) Grading - 2 (53 mm to 22.4mm) (a) Using Screeining Crushable type such as Moorum of Gravel | 11.24 | Tlabung Division | March 2023 | March-2024 | 100% | 5.62 |  | 5.62 | 100% | 11.24 | Completed Phy.Works
879 | 3. Cement Concrete Pavement (Construction of unreinforced, dowel jointed, plain cement concrete pavement over a prepared sub base with 43 grade cement | 56.07 | Tlabung Division | March 2023 | March-2024 | 100% | 28.04 |  | 20.4 | 100% | 48.44 | Completed Phy.Works
880 | 4. Excavation for Structures (Earth work in excavation of foundation of structures as per drawing and technical specification. I. Ordinary soil (upto 3m depth) | 0.91 | Tlabung Division | March 2023 | March-2024 | 100% | 0.46 |  | 0.46 | 100% | 0.92 | Completed Phy.Works
881 | 5. Stone masonry work in cement mortar for substructure complete as per drawing and Technical Specifications II. Course rubble masonry (1st sort) (iii) in cement mortar 1:3 | 21.28 | Tlabung Division | March 2023 | March-2024 | 100% | 10.64 |  | 2.3 | 100% | 12.94 | Completed Phy.Works
882 | 6. Excavation for structure (Earth work in excavation for foundation of structures as per drawing and technical specification, (i) Ordinary soil A Manual Mean (Depth upto 3m) | 0.32 | Tlabung Division | March 2023 | March-2024 | 100% | 0.16 |  | 0.16 | 100% | 0.32 | Completed Phy.Works
883 | 7. PCC 1:3:6 Foundation (Plain cement concrete 1:3:6 in foundation including for 14 days) | 0.914 | Tlabung Division | March 2023 | March-2024 | 100% | 0.46 |  | 0.46 | 100% | 0.92 | Completed Phy.Works
884 | 8. Back filling behind abutment, wing wall and return wall complete as per drawing and Technical specification | 1.49 | Tlabung Division | March 2023 | March-2024 | 100% | 0.75 |  | 0.75 | 100% | 1.5 | Completed Phy.Works
885 | 9. Plastering with cement mortar (1:3) in sub-structure as per Technical Specifications | 0.13 | Tlabung Division | March 2023 | March-2024 | 100% | 0.07 |  | 0.07 | 100% | 0.14 | Completed Phy.Works
886 | 10. Excavation in Hilly areas in soil by Manual Means | 6.81 | Tlabung Division | March 2023 | March-2024 | 100% | 3.41 |  | 3.41 | 100% | 6.82 | Completed Phy.Works
887 | 11. Excavation in Hilly areas in ordinary Rock by Manual Means | 2.37 | Tlabung Division | March 2023 | March-2024 | 100% | 1.19 |  | 1.19 | 100% | 2.38 | Completed Phy.Works
888 | 12. Removal of unsuitable soil including excavtion, loading and disposals with a lead of 1000m | 0.95 | Tlabung Division | March 2023 | March-2024 | 100% | 0.48 |  | 0.48 | 100% | 0.96 | Completed Phy.Works
889 | 13. Reinforced cement concrete approach slab including reinforcement and formwork complete as per drawing and Technical specification | 0.41 | Tlabung Division | March 2023 | March-2024 | 100% | 0.21 |  | 0.21 | 100% | 0.42 | Completed Phy.Works
890 | 14. 12mm cement plaster 1:3 (1 cement : 3 fine sand) | 0.1 | Tlabung Division | March 2023 | March-2024 | 100% | 0.05 |  | 0.05 | 100% | 0.1 | Completed Phy.Works
891 | 15. Providng and fixing G.I pipe complete with G.I fitting including trenching and refilling etc. (external work) | 2.28 | Tlabung Division | March 2023 | March-2024 | 100% | 1.14 |  | 1.14 | 100% | 2.28 | Completed Phy.Works
892 | 16. Water Bound Macadam (Providing, layinf, spreading and compacting stone aggregates of specific sizes to water bound madacam specification (ii) Grading II (53mm - 22.4mm) (b) Using Screening type-B | 14.08 | Tlabung Division | March 2023 | March-2024 | 100% | 7.04 |  | 2.5 | 100% | 9.54 | Completed Phy.Works
893 | 17. Prime coat (Providing and applying primer coat with bitument emulsion on prepared surface of granular base including 1) Low Porosity | 1.55 | Tlabung Division | March 2023 | March-2024 | 100% | 0.78 |  | 0.5 | 100% | 1.28 | Completed Phy.Works
894 | 18. Tack Coat (Providing and applying tack coat with bitumen emulsion using emulsion pressure distributor (ii) Granular surface treated with primer | 0.93 | Tlabung Division | March 2023 | March-2024 | 100% | 0.47 |  | 0.25 | 100% | 0.72 | Completed Phy.Works
895 | 19. Open-Graded Premix Surfacing (Providng laying and rolling of open graded premix surfacing of 20mm thickness | 8.57 | Tlabung Division | March 2023 | March-2024 | 100% | 4.29 |  | 2.11 | 100% | 6.4 | Completed Phy.Works
896 | 20. Seal Coat (Providing and laying seal coat sealing the voids in a bituminous surface laid to the specified levels, grade and cross fall using Type A and B seal coat A using Bitumen 60/70 grade (i) Case - I : Type A | 2.96 | Tlabung Division | March 2023 | March-2024 | 100% | 1.48 |  | 1.4 | 100% | 2.88 | Completed Phy.Works
PROJECT DIVISION - II :
897 | Construction of Public Playground at Thenzawl (Sh: Const.of Public Playgound Galley of length 120 metre (6 block of 20 metre each including 3 (three) steps for sitting at Thenzawl | 25 | Project Division-II | 26.02.23 | 26.08.23 | 100% | 12.5 |  |  | 100% | 12.5 | Completed Phy.Works | Item Rate
898 | Construction of Community Hall at Chawilung (Sh: Construcytion of Steel Truss with dyna roofing) | 6 | Project Division-II | 24.02.23 | 24.04.23 | 100% | 3 |  |  | 100% | 3 | Completed Phy.Works | Item Rate
899 | Construction of Community Hall at Hualngohmun (Sh: Construction of Steel Truss with dyna roofing) | 8 | Project Division-II | 24.02.23 | 24.04.23 | 100% | 4 |  |  | 100% | 4 | Completed Phy.Works | Item Rate
900 | Construction of MUP House at Zamuang, Mamit District | 15 | Project Division-II | 26.02.23 | 26.06.23 | 100% | 7.5 |  |  | 100% | 7.5 | Completed Phy.Works | Item Rate
901 | Construction of Urinal Sheds (sh: Near Rambeiseia In, BBEC Pastor Qtrs, Pu Lalzama House, Lalaithai's House, C.Laltanpuia House, Darlak Peng at Tuidam, Urinal Sheds at Vengthar, W.Bunghmun, H/S Veng at Bunghmun, Near Baptist Church at New Eden, near Presbyterian Church at New Eden) | 5 | Project Division-II | 24.02.23 | 24.04.23 | 100% | 2.5 |  |  | 100% | 2.5 | Completed Phy.Works | Item Rate
902 | Construction of waiting Sheds (Sh: Const.of Waiting shed at Dilpeng, Kawrtethawveng 2. Repair of Waiting Shed at New Kawnpui Village 3. Construction of Buhfai Semna/Dahna Teireikam at Kananthar). | 7.5 | Project Division-II | 24.02.23 | 24.04.23 | 100% | 3.75 |  |  | 100% | 3.75 | Completed Phy.Works | Item Rate
903 | Construction of Pavement of Chequered Tiles (Sh: Near Pi Duhkungi House to Kawnghnuai at Tuidam 2. Ramrikawn to Pi Rinngaii In Kawng at Kawrtethawveng 3. Mualzawl (Hmarveng) to Arm Veng 4. KDZKT Road to Internal Road near Pi Nuntluangi In at Kawrtethawveng 5. Chequered Tile phah, step Repair approach to Tuikhuah tuikhur panna at Kawrtethawveng) | 9.5 | Project Division-II | 24.02.23 | 24.04.23 | 100% | 4.75 |  |  | 100% | 4.75 | Work phy.completed | Item Rate
904 | Construction of Tourist Lodge at Kawnpui | 50 | Project Division-II | 26.02.23 | 26.10.23 | 74% | 25 |  |  | 74% | 25 | Work in progress | Item Rate
905 | Construction of Futsal Ground at Kawnpui Chhimveng | 25 | Project Division-II | 25.02.23 | 25.06.23 | 83% | 12.5 |  |  | 83% | 12.5 | Work in progress | Item Rate
906 | Continuation of Public Playground at Serkhan | 15 | Project Division-II | 25.03.23 | 25.05.23 | 100% | 7.5 |  |  | 100% | 7.5 | Phy.Completed | Item Rate
907 | Construction of Community Hall at Hortoki | 70 | Project Division-II | 26.02.23 | 26.10.23 | 100% | 35 |  |  | 100% | 35 | Phy.Completed | Item Rate
908 | Continuation of Public Playground at Zanlawn | 15 | Project Division-II | 25.02.23 | 25.05.23 | 93% | 7.5 | 2% |  | 95% | 7.5 | Work in progress | Item Rate
909 | Continuation of Public Playground at Bualpui | 15 | Project Division-II | 25.02.23 | 25.05.23 | 100% | 7.5 |  |  | 100% | 7.5 | Phy.Completed | Item Rate
910 | Construction of Bazar Shed at Nisapui | 15 | Project Division-II | 25.02.23 | 25.05.23 | 100% | 7.5 |  |  | 100% | 7.5 | Phy.Completed | Item Rate
911 | Continuation of Futsal Ground at Lungdai | 25 | Project Division-II | 25.02.23 | 25.06.23 | 100% | 12.5 |  |  | 100% | 12.5 | Phy.Completed | Item Rate
PROJECT DIVISION - III :
912 | Construction of Govt.Serchhip College (Sh: Adninistrative Block) | 650 | Project Division-III | 27.02.23 | 27.02.25 | 29% | - | 1% | 91.04 | 30% | 91.04 | work in progress | PWD Form-8
913 | Const. of Football ground and Volleyball court at Vapar, Selam, Tualcheng, Hnahlan, Hmunhmeltha | 203 | Project Division-III | 13.10.23 | 13.10.24 | 2% |  |  |  | 2% |  | work in progress | PWD Form-8
914 | Const. of Khawbung Futsal ground, Gallery, Roofing, Lighting & Laying of Artificial Turf | 255.5 | Project Division-III | 14.10.23 | 14.10.24 | 2% |  |  |  | 2% |  | work in progress | PWD Form-8
915 | Const. of Community Hall at Dulte & Chhawrtui | 271 | Project Division-III | 13.10.23 | 13.10.24 | 2% |  |  |  | 2% |  | work in progress | PWD Form-8
916 | Development of Community Centre at Zotlang, Champhai (Sh: Const. of Market Building cum Community Hall & Futsal Ground) | 215 | Project Division-III | 14.10.23 | 14.10.24 | 2% |  |  |  | 2% |  | work in progress | PWD Form-8
917 | Additional works for Const. of General Nursing Midwifery (GNM) hostel and Nursing Hostel at Champhai | 438 | Project Division-III | 13.10.23 | 13.10.24 | 12% |  |  |  | 12% |  | work in progress | PWD Form-8
918 | Const. of Public Playground at Keitum, Lungchhuan. | 250 | Project Division-III | 13.10.23 | 13.10.24 | 2% |  |  |  | 2% |  | work in progress | PWD Form-8
919 | Const. of Gov't. Building at Serchhip District (Sh: PWD Staff Quarters, Extension of Gov't. Serchhip Cillege and Kitchen Cum Dining at PTS, Thenzawl, Mizoram) | 362 | Project Division-III | 13.10.23 | 13.10.24 | 2% |  |  |  | 2% |  | work in progress | PWD Form-8
920 | Const. of Community Resource Center at Baktawng and Chhuanthar | 350 | Project Division-III | 13.10.23 | 13.10.24 | 2% |  |  |  | 2% |  | work in progress | PWD Form-8
921 | Const. of Community Hall at Khawzawl Vengthar, Arro Village, khawzawl Dinthar and Khawhai South | 209 | Project Division-III | 13.10.23 | 13.10.24 | 2% |  |  |  | 2% |  | work in progress | PWD Form-8
LUNGLEI ROAD DIVISION -I
IMPROVEMENT OF CHANMARI - ELECTRIC VENG - RAMTHAR VENG AT LUNGLEI DISTRICT IN MIZORAM FOR THE YEAR 2022-2023 UNDER SASCI, Length = 9.000Kms
922 | Construction of Retaining Wall at Chanmari Cemetary Road | 6.76 | Lunglei Road Division-I |  |  | 100% | 3.35 |  |  | 100% | 3.35 | Phy.Completed | Spot Quotation
923 | Construction of Breast Wall near Horticulture Complex of District Road at Chanmari | 6.27 | Lunglei Road Division-I |  |  | 100% | 3.12 |  |  | 100% | 3.12 | Phy.Completed | Spot Quotation
924 | Construction of Breast wall opposite Pi Zidingi's house Block-I at Chanmari, Lunglei | 4.56 | Lunglei Road Division-I |  |  | 100% | 2.28 |  |  | 100% | 2.28 | Phy.Completed | Spot Quotation
925 | Construction of Breast Wall opposite Pi Zidingi's House Block-II at Chanmari, Lunglei | 2.69 | Lunglei Road Division-I |  |  | 100% | 1.34 |  |  | 100% | 1.34 | Phy.Completed | Spot Quotation
926 | Construction of Retaining Wall at GHSS Lunglei, Chanmari | 5.8 | Lunglei Road Division-I |  |  | 100% | 2.84 |  |  | 100% | 2.84 | Phy.Completed | Spot Quotation
927 | Construction of Retaining Wall at Leitlangpui HSS, Chanmari, Lunglei | 7.73 | Lunglei Road Division-I |  |  | 100% | 3.97 |  |  | 100% | 3.97 | Phy.Completed | Spot Quotation
928 | Construction of PCC pavement with Retaining Wall etc. from T.Vanlalremruata's House to H.Laldawla's House at Electric veng. (a) Construction of Breast Wall near T.Vanlalremruata's House at Electrict veng, Lunglei. (b)Construction of Embankment & Widening from T.Vanlalremruata's House to H.Laldawla's House at Electrict veng, Lunglei. | 13.11 | Lunglei Road Division-I |  |  | 100% |  |  |  | 100% |  | Phy.Completed | Spot Quotation
929 | Construction of Retaining Wall at Pu Zalawma Punte Land at Electrict veng | 3.42 | Lunglei Road Division-I |  |  | 100% |  |  |  | 100% |  | Phy.Completed | Spot Quotation
930 | Construction of Retaining Wall upto Pathian Nung Biakin at Electrict veng | 3.86 | Lunglei Road Division-I |  |  | 100% |  |  | 28.98 | 100% | 28.98 | Phy.Completed | Spot Quotation
931 | Construction of PCC pavement from Main road tp R.Rozika's House near BCM Church at Electrict veng | 2.9 | Lunglei Road Division-I |  |  | 100% |  |  |  | 100% |  | Phy.Completed | Spot Quotation
932 | Construction of PCC pavement from Muanzova's House to F.Lalsangliana's House at Electrict veng | 5.8 | Lunglei Road Division-I |  |  | 100% |  |  |  | 100% |  | Work in progress | Spot Quotation
933 | Construction of Curve Improvement of opposite of Pu Bawka Point at Farm Veng | 8.69 | Lunglei Road Division-I |  |  | 100% |  |  |  | 100% |  | Phy.Completed | Spot Quotation
934 | Construction of Retaining Wall with Widening between Sericulture Gate to Lalremruata's House at Farm veng | 8.69 | Lunglei Road Division-I |  |  | 100% |  |  |  | 100% |  | Phy.Completed | Spot Quotation
935 | Construction of Footpath between C.Lalthianghlima's House to Vety Gate at Farm veng | 7.73 | Lunglei Road Division-I |  |  | 100% | 14.84 |  |  | 100% | 14.84 | Phy.Completed | Spot Quotation
936 | Construction of Hume Pipe Culvert near H.Sanghmingthanga's House at Farm veng | 3.86 | Lunglei Road Division-I |  |  | 100% |  |  |  | 100% |  | Phy.Completed | Spot Quotation
937 | Construction of Retaining Wall at V.Lalnuntluanga's House to Rochungnunga's House at District Road, Chanmari, Lunglei | 4.88 | Lunglei Road Division-I |  |  | 100% |  |  |  | 100% |  | Phy.Completed | Spot Quotation
938 | Construction of Slab Culvert at Ramthar & Salem boundary at Ramthar | 21.83 | Lunglei Road Division-I |  |  | 100% |  |  |  | 100% |  | Phy.Completed | Spot Quotation
939 | Construction of Lined Side Drain from Nghaksangi's House to Venhima's House at Ramthar veng. | 3.38 | Lunglei Road Division-I |  |  | 100% |  |  |  | 100% |  | Phy.Completed | Spot Quotation
940 | Construction of PCC pavement from Remand Home to Salem Boundary at Ramthar veng | 9.66 | Lunglei Road Division-I |  |  | 100% |  |  |  | 100% |  | Phy.Completed | Spot Quotation
941 | Construction of Retaining Wall at F.Sapdawla Land & J.Lianngura Land at Ramthar veng | 3.86 | Lunglei Road Division-I |  |  | 100% | 88.88 |  |  | 100% | 88.88 | Phy.Completed | Spot Quotation
942 | Renovation of step from Saidingliana House to Hmuzuala House at Ramthar | 5.57 | Lunglei Road Division-I |  |  | 100% |  |  |  | 100% |  | Phy.Completed | Spot Quotation
943 | Construction of Retaining wall from V.Muankima House to Thangte Veng Tuikhur at Ramthar Veng | 1.98 | Lunglei Road Division-I |  |  | 100% |  |  |  | 100% |  | Phy.Completed | Spot Quotation
944 | Construction of PCC Pavement from Thathleia's House to T.Lalthianghlima House at Ramthar veng | 2.82 | Lunglei Road Division-I |  |  | 100% |  |  |  | 100% |  | Phy.Completed | Spot Quotation
945 | Construction of PCC pavement Zaii's House to lallawmzuali's House at Ramthar veng | 2.58 | Lunglei Road Division-I |  |  | 100% |  |  |  | 100% |  | Phy.Completed | Spot Quotation
946 | Laying of Chequerred Tiles from V.Muankima House to Tuikhur Kawng at Ramthar | 2.28 | Lunglei Road Division-I |  |  | 100% |  |  |  | 100% |  | Phy.Completed | Spot Quotation
947 | Construction of formation cutting of Agricultural Link Road at Mausen | 9.66 | Lunglei Road Division-I |  |  | 100% |  |  |  | 100% |  | Phy.Completed | Spot Quotation
948 | Construction of New Internal Road in remembrance of the Golden Jubilee of Pukpui Village to be named Jubilee Road | 19.32 | Lunglei Road Division-I |  |  | 100% | 24.04 |  |  | 100% | 24.04 | Phy.Completed | Spot Quotation
949 | Construction of formation cutting of Mausep Agricultural Link Road at Sekhum | 19.32 | Lunglei Road Division-I |  |  | 100% |  |  |  | 100% |  | Phy.Completed | Spot Quotation
IMPROVEMENT OF TLABUNG ROAD - THUAMLUAIA MUAL - COLLEGE VENG - RAHSI VENG AT LUNGLEI DISTRICT IN MIZORAM FOR THE YEAR 2022-2023 UNDER SASCI, Length = 11.500Kms
950 | Dismantling, Excavation/Lowering, Pavement, Sidedrain, RCC Step and HP Culverts at Tlabung peng junction | 77.29 | Lunglei Road Division-I |  |  | 100% |  |  | - | 100% |  | Phy.Completed | Spot Quotation
951 | Construction of PCC pavement between Tarmita Road Kikawn & College veng | 96.11 | Lunglei Road Division-I |  |  | 100% | 86.95 |  | - | 100% | 86.95 | Phy.Completed | Spot Quotation
952 | Construction of Blue Mount Farmers Society approach road from Thehlep. (Widening) | 28.98 | Lunglei Road Division-I |  |  | 100% |  |  |  | 100% |  | Phy.Completed | Spot Quotation
953 | Construction of Paneled cement concrete pavement from District Court Building to Pu Chuauva House | 28.98 | Lunglei Road Division-I |  |  | 100% | 178.63 |  |  | 100% | 178.63 | Phy.Completed | Spot Quotation
954 | Construction of Slab Culvert Lamhla Tuikhur, Tarmita road, Bazar veng Kikawn | 19.32 | Lunglei Road Division-I |  |  | 100% |  | - |  | 100% |  | Phy.Completed | Spot Quotation
955 | Construct of Slab Culvert at Kawngkan Lui | 14.49 | Lunglei Road Division-I |  |  | 100% |  |  |  | 100% |  | Phy.Completed | Spot Quotation
956 | Construction of Retaining Wall near Kailiana's House at Rahsi veng, Lunglei | 9.66 | Lunglei Road Division-I |  |  | 100% |  |  |  | 100% |  | Phy.Completed | Spot Quotation
957 | Const. of PCC pavement from Bazar veng Thlanmual No.2 BNRGSK Building to Pu Tawnga Garden | 28.98 | Lunglei Road Division-I |  |  | 100% | 96.61 |  |  | 100% | 96.61 | Phy.Completed | Spot Quotation
958 | Const. of PCC pavement approach road to Lunglei venghlun Cemetary | 28.98 | Lunglei Road Division-I |  |  | 100% |  |  |  | 100% |  | Phy.Completed | Spot Quotation
959 | Const. of PCC pavement from Ngaihlova's House to Mini Sport Complex | 28.98 | Lunglei Road Division-I |  |  | 100% |  |  |  | 100% |  | Phy.Completed | Spot Quotation
960 | Strengthening and Resurfacing of Aizawl - Thenzawl - Lunglei Road from 160.00-164.00 Kmp (Kikawn - AOC veng, Lunglei | 590.07 | Lunglei Road Division-I |  |  | 100% | 590.06 |  |  | 100% | 590.06 | Completed | Spot Quotation
WORKING ESTIMATE FOR CONSTRUCTION OF RCC PAVEMENT AND CULVERTS FROM BUNGHMUN - THENHLUM - Lungchem in Mizoram for the year 2022-2023 under SASCI.
961 | Const. of Retaining Wall at 4 places between Market Shed to Entrance of Pukpui along ATL Road | 50 | Lunglei Road Division-I |  |  | 100% |  |  |  | 100% |  | Work in progress | Spot Quotation
962 | Const. of PCC pavement from Santosh Mot's House to Duresh Chandra's house at Mauzam | 4.23 | Lunglei Road Division-I |  |  |  |  | 100% |  | 100% |  | Phy.Completed | Spot Quotation
963 | Const. of PCC pavement from Main Road to Community Hall at Salmur | 2.82 | Lunglei Road Division-I |  |  | 100% | - | - | - | 100% | - | Phy.Completed | Spot Quotation
964 | Const. of PCC pavement from Lalremruata's House to Lalnunzira's House at New Sachan | 4.51 | Lunglei Road Division-I |  |  | 100% | - |  | - | 100% | - | Phy.Completed | Spot Quotation
965 | Const. of approach road with PCC pavement from PMGSY road to Phainuam | 10.15 | Lunglei Road Division-I |  |  | 100% | - |  | - | 100% | - | Phy.Completed | Spot Quotation
966 | Const. of Foot Step from Niachand's House to Lawngkai at Tuikawi | 3.07 | Lunglei Road Division-I |  |  | 13% | - |  |  | 13% |  | work in progress | Spot Quotation
967 | Const. of RCC Foot Bridge from Rody Ranjan's House to Jugodhi's House at Tuikawi | 3.54 | Lunglei Road Division-I |  |  | 100% | - |  | - | 100% | - | Phy.Completed | Spot Quotation
968 | Const. of Retaining Wall near Mandir at Sumasumi | 9.18 | Lunglei Road Division-I |  |  | 100% | - |  | - | 100% | - | Phy.Completed | Spot Quotation
969 | Const. of PCC pavement from Shantis Pryo's House to football field at Sumasumi | 0.56 | Lunglei Road Division-I |  |  | 100% | - |  | - | 100% | - | Phy.Completed | Spot Quotation
970 | Const. of PCC pavement at Bazar line Old Sachan | 3.38 | Lunglei Road Division-I |  |  | 100% | - |  | - | 100% | - | Phy.Completed | Spot Quotation
971 | Const. of PCC pavement from Gov't Primary School to Saimawia's House at Laisawral | 3.38 | Lunglei Road Division-I |  |  | 100% | - |  | - | 100% | - | Phy.Completed | Spot Quotation
972 | Const. of PCC pavement from Lalchhandama's House to Lalvulrenga's House at Laisawral | 1.69 | Lunglei Road Division-I |  |  | 100% | - |  | - | 100% | - | Phy.Completed | Spot Quotation
973 | Const. of PCC pavement from Internal road to Primary School at Laisawral | 0.34 | Lunglei Road Division-I |  |  | 100% | - |  | - | 100% | - | Work in progress | Spot Quotation
974 | Const. of PCC pavement from Internal road to P.Thanglura's House at Laisawral | 1.35 | Lunglei Road Division-I |  |  | 100% | - |  | - | 100% | - | Phy.Completed | Spot Quotation
975 | Const. of Foot Step from Saimawia's House to Baptist Church at Laisawral | 1.23 | Lunglei Road Division-I |  |  | 41% | - |  | - | 41% | - | Work in progress | Spot Quotation
976 | Const. of PCC pavement from Primary School to Thlanmual Road at Tleu | 2.26 | Lunglei Road Division -I |  |  | 100% |  |  |  | 100% |  | Phy.Completed | Spot Quotation
977 | Const. of PCC pavement from Saichhunga's House to Vengthar UPC Church at Sesawm | 5.64 | Lunglei Road Division -I |  |  | 100% |  |  |  | 100% |  | Phy.Completed | Spot Quotation
978 | Const. of PCC pavement from Lalrindika's House to Sahlam Tree at Lungchem | 4.23 | Lunglei Road Division -I |  |  | 100% |  |  |  | 100% |  | Phy.Completed | Spot Quotation
979 | Const. of PCC pavement from Sahlam Tree to C.Kairuma's House at Lungchem | 4.23 | Lunglei Road Division -I |  |  | 100% |  |  |  | 100% |  | Phy.Completed | Spot Quotation
980 | Const. of PCC pavement from Lalnunpuia's House to Sub-Centre at Lungchem | 0.42 | Lunglei Road Division -I |  |  | 100% |  |  |  | 100% |  | Phy.Completed | Spot Quotation
981 | Const. of Foot Step from NERGS House to Main road at Lungchem | 1.23 | Lunglei Road Division -I |  |  | 100% |  |  |  | 100% |  | Phy.Completed | Spot Quotation
982 | Const. of PCC pavement from Bharat Chandra's House to Priyo Ranjan's House at Marpara 'S' | 6.77 | Lunglei Road Division -I |  |  | 100% |  |  |  | 100% |  | Phy.Completed | Spot Quotation
983 | Const. of PCC pavement from Priyo Ranjan's House to Sneha Kumar's House at Marpara 'S' | 6.77 | Lunglei Road Division -I |  |  | 100% |  |  |  | 100% |  | Phy.Completed | Spot Quotation
984 | Const. of PCC pavement from Baptish School to Bazar Line at Marpara 'S' | 6.77 | Lunglei Road Division -I |  |  | 100% |  |  |  | 100% |  | Phy.Completed | Spot Quotation
985 | Const. of PCC pavement from Monu Ranjan's House to Kanchas House at Marpara 'S' | 7.05 | Lunglei Road Division -I |  |  | 100% |  |  |  | 100% |  | Phy.Completed | Spot Quotation
986 | Const. of PCC pavement from Lalnunkima's House to Lalnunpuii's House at Bunghmun | 3.38 | Lunglei Road Division -I |  |  | 100% |  |  |  | 100% |  | Phy.Completed | Spot Quotation
987 | Const. of Foot Step from B.Tlanghmingthanga's House to UPC Church at Bunghmun | 2.45 | Lunglei Road Division -I |  |  | 32% |  |  |  | 32% |  | Work in progress | Spot Quotation
988 | Const. of PCC pavement from Lalhmingthanga's House to Rochungnunga's House at Bunghmun | 5.08 | Lunglei Road Division -I |  |  | 100% |  |  |  | 100% |  | Work not started | Spot Quotation
989 | Const. of PCC pavement from Primary School -II to High School at Bunghmun | 3.38 | Lunglei Road Division -I |  |  | 100% |  |  |  | 100% |  | Phy.Completed | Spot Quotation
990 | Const. of Newly Agricultural Link road from Hnawla Dil to Chulpui Lui | 17.22 | Lunglei Road Division -I |  |  | 100% |  |  |  | 100% |  | Phy.Completed | Spot Quotation
991 | Const. of Newly Agricultural Link road from Chulpui Lui to Sangkawi | 23.87 | Lunglei Road Division -I |  |  | 75% |  |  |  | 75% |  | Work in progress | Spot Quotation
992 | Const. of PCC pavement from Lalramhluna's House to Main road at Changpui | 1.69 | Lunglei Road Division -I |  |  | 100% |  |  |  | 100% |  | Phy.Completed | Spot Quotation
993 | Const. of PCC pavement from Changpui to Lunghar chho (Lungchem road) at Changpui | 1.69 | Lunglei Road Division -I |  |  | 100% |  |  |  | 100% |  | Phy.Completed | Spot Quotation
994 | Const. of PCC pavement from Health Worker's Quarter to Lalchawimawia's House at Dengsur | 2.82 | Lunglei Road Division -I |  |  | 100% |  |  |  | 100% |  | Phy.Completed | Spot Quotation
995 | Const. of PCC pavement from KV Thanmawia's House to High School at Dengsur | 2.82 | Lunglei Road Division -I |  |  | 100% |  |  |  | 100% |  | Phy.Completed | Spot Quotation
996 | Const. of PCC pavement from Zoramthanga's House to PWD Road at S.Khawlek | 0.51 | Lunglei Road Division -I |  |  | 100% | 115 |  | 78.8 | 100% | 193.8 | Phy.Completed | Spot Quotation
997 | Const. of PCC pavement near BCM Church to Primary School at S.Khawlek | 0.56 | Lunglei Road Division -I |  |  | 100% |  |  |  | 100% |  | Phy.Completed | Spot Quotation
998 | Const. of Foot Step near Liantluanga's House to Tuikhur at New Khawlek | 2.04 | Lunglei Road Division -I |  |  | 23% |  |  |  | 23% |  | Work in progress | Spot Quotation
999 | Const. of Foot Step near Suakthuama's House to Public play ground road near New Khawlek | 3.07 | Lunglei Road Division -I |  |  | 41% |  |  |  | 41% |  | Work in progress | Spot Quotation
1000 | Const. of PCC pavement from BCM Church to Lalsangzuala's House at New Khawlek | 1.13 | Lunglei Road Division -I |  |  | 100% |  |  |  | 100% |  | Phy.Completed | Spot Quotation
1001 | Const. of Slab Culvert near Ngurthangluaia's House at Thenhlum | 5.24 | Lunglei Road Division -I |  |  | 100% |  |  |  | 100% |  | Phy.Completed | Spot Quotation
1002 | Const. of Slab Culvert near Thenhlum Play Ground- I | 7.5 | Lunglei Road Division -I |  |  | 100% |  |  |  | 100% |  | Phy.Completed | Spot Quotation
1003 | Const. of PCC pavement from Main Road to Football Playground at Thenhlum | 0.47 | Lunglei Road Division -I |  |  | 65% |  |  |  | 65% |  | Work in Progress | Spot Quotation
1004 | Const. of Foot Step from Main Road to Middle School | 1.53 | Lunglei Road Division -I |  |  | 14% |  |  |  | 14% |  | Work in Progress | Spot Quotation
| TOTAL: | 231.28 |  |  |  | 96% | 115 |  | 78.8 | 96% | 193.8
1005 | Aizawl- Thenawl- Lunglei Road between Kanghmun 'S' and Kikawn, Lunglei Phase - I, (Sh: Group - A Between 100.00-120.00 Kmp) | 647.09 | Lunglei Road Division -I | 03.07.23 | 03.07.24 | 33% |  | 1% |  | 34% |  | Work in progress | Restricted Tender
1006 | Aizawl- Thenawl- Lunglei Road between Kanghmun 'S' and Kikawn, Lunglei Phase - I, (Sh: Group - B Between 120.00-143.00 Kmp) | 658.16 | Lunglei Road Division -I | 26.06.23 | 26.06.24 | 52% |  | 1% |  | 53% |  | Work in progress | Restricted Tender
1007 | Construction of pavement on Approach Road to Pialthleng at Lunglei District | 724.85 | Lunglei Road Division -I | 24.03.23 | 24.03.24 | 27% | 119 | 16% | 0.96 | 43% | 119.96 | Work in Progress | Restricted Tender
HNAHTHIAL DIVISION ;
Improvement & Upgradation of Roads from Hnahthial to Thingsai
Improvement and upgradation of Hnahthial - Thingsai Road (50.00 lakhs)
1008 | (a) Retaining Wall on H-T at Ch.3.750 Kmp | 5.18 | Hnahthial Division | 16.03.23 | 15.03.24 | 100% | 2.59 |  |  | 100% | 2.59 | Phy.Completed | Spot Quotation
1009 | (b) Retaining Wall on H-T at Ch. 5.450 Kmp | 6.62 | Hnahthial Division | 16.03.23 | 15.03.24 | 100% | 3.31 |  |  | 100% | 3.31 | Phy.Completed | Spot Quotation
1010 | © Retaininh Wall on H-T at Ch. 9.450 Kmp | 5.55 | Hnahthial Division | 16.03.23 | 15.03.24 | 100% | 2.78 |  |  | 100% | 2.78 | Phy.Completed | Spot Quotation
1011 | (d) Retaining Wall on H-T at Ch. 43.300 Kmp | 2 | Hnahthial Division | 16.03.23 | 15.03.24 | 100% | 1 |  |  | 100% | 1 | Phy.Completed | Spot Quotation
1012 | (e) Improvement and widening of H-T Road at Ch. 3.550 - 3.610 Kmp | 7.65 | Hnahthial Division | 16.03.23 | 15.03.24 | 100% | 3.83 |  |  | 100% | 3.83 | Phy.Completed | Spot Quotation
1013 | Resurfacing of Hnahthial - Tumtukawn Road at Ch. 5.000-6.00 Kmp | 23 | Hnahthial Division | 16.03.23 | 15.03.24 | 100% | 11.5 |  |  | 100% | 11.5 | Phy.Completed | Spot Quotation
1014 | Construction of Darzo (Kawipui) Saibuchhuah Road | 100 | Hnahthial Division | 16.03.23 | 15.03.24 | 100% | 50 |  |  | 100% | 50 | Phy.Completed | Spot Quotation
1015 | Improvement of Internal Road within Thingsai Village | 50 | Hnahthial Division | 16.03.23 | 15.03.24 | 100% | 25 |  |  | 100% | 25 | Phy.Completed | Spot Quotation
1016 | PCC Flooring of Tarpho to Aithur Roas | 170 | Hnahthial Division | 16.03.23 | 15.03.24 | 100% |  |  |  | 100% |  | Phy.Completed | Spot Quotation
1017 | PCC pavement from MTR (Road) Tuipui D to Nghafuan (R.Tuipui) Road | 80 | Hnahthial Division | 16.03.23 | 15.03.24 | 100% | 40 |  |  | 100% | 40 | Phy.Completed | Spot Quotation
1018 | (g) Improvement of road from Hnahthial Town to Takam tlaw | 50 | Hnahthial Division | 16.03.23 | 15.03.24 | 100% | 25 |  |  | 100% | 25 | Phy.Completed | Spot Quotation
Construction and Upgradation of Road from Bualpui V to River Mat via Lungmawi
1019 | (a) Strengthening/Widening of Road between Bualpui V to River Mat via Lungmawi | 100 | Hnahthial Division | 16.03.23 | 15.03.24 | 98% | 72.2 | 1% | 0.2 | 99% | 72.4 | Work in progress | Spot Quotation
1020 | (b) Const./FC of Road between Pangzawl to Tuichang | 30 | Hnahthial Division | 16.03.23 | 15.03.24 | 100% | 14.49 |  |  | 100% | 14.49 | Phy.Completed | Spot Quotation
1021 | (c) Improvement of Internal Road between main Pangzawl Village to upper Pangzawl | 30 | Hnahthial Division | 16.03.23 | 15.03.24 | 100% | 14.5 |  |  | 100% | 14.5 | Phy.Completed | Spot Quotation
1022 | (d) Const./FC of Agriculture Link Road at Thiltlang | 15 | Hnahthial Division | 16.03.23 | 15.03.24 | 100% | 7.25 |  |  | 100% | 7.25 | Work in progress | Spot Quotation
1023 | (e) Const./FC of Agriculture Link Road at Rawpui | 10 | Hnahthial Division | 16.03.23 | 15.03.24 | 100% | 4.83 |  |  | 100% | 4.83 | Phy.Completed | Spot Quotation
1024 | (f) Const./FC within Agriculture Link Road at Phaileng S | 10 | Hnahthial Division | 16.03.23 | 15.03.24 | 100% | 4.83 |  |  | 100% | 4.83 | Phy.Completed | Spot Quotation
1025 | (g) Const of PCC Pavement from Haulawng to Community Hall | 8 | Hnahthial Division | 16.03.23 | 15.03.24 | 100% | 3.87 |  |  | 100% | 3.87 | Phy.Completed | Spot Quotation
Construction and Upgradation of Retaining Wall at Zobawk Ringroad
1026 | (1) Re-Construction of permanent works at Tawipui N Mualcheng S at chainage 1.00 kmp, 2.500 kmp, 3.700 kmp, 3.720 kmp & 5.500 kmp | 38.4 | Hnahthial Division |  |  | 100% | 19.2 | - |  | 100% | 19.2 | Phy.Completed | Spot Quotation
1027 | (2) Construction of PCC pavement Vanlalhmuaki House to Middle School Road at Lungpuizawl | 4 | Hnahthial Division |  |  | 100% | 2 |  |  | 100% | 2 | Phy.Completed | Spot Quotation
1028 | (3) Construction of PCC Pavement at Hmingthana House to HS Lalhmunmawia House at Lungpuizawl | 3 | Hnahthial Division |  |  | 100% | 1.5 |  |  | 100% | 1.5 | Phy.Completed | Spot Quotation
1029 | (4) Construction of PCC Pavement PCI Biakin to Public Playground at Lungpuizawl | 3 | Hnahthial Division |  |  | 100% | 1.5 |  |  | 100% | 1.5 | Phy.Completed | Spot Quotation
1031 | (5) Construction of Retaining wall at NEI UPC Zobawk Local at Zobawk S | 9 | Hnahthial Division |  |  | 100% | 4.5 |  |  | 100% | 4.5 | Phy.Completed | Spot Quotation
1032 | (6) Construction of Retaining Wall at Zobawk Venglai near Community Hall at Zobawk Venglai | 5 | Hnahthial Division |  |  | 100% | 2.5 |  |  | 100% | 2.5 | Phy.Completed | Spot Quotation
1033 | Construction of Internal Road with Widening from Pu Kawlramtawna House to Tuitai Kawi at Zobawk Venglai | 9.5 | Hnahthial Division |  |  | 100% |  |  |  | 100% |  | Phy.Completed | Spot Quotation
1034 | Construction of PCC Pavement Public playground to Transformer at Zobawk Vengthar | 4.5 | Hnahthial Division |  |  | 100% | 2.25 |  |  | 100% | 2.25 | Phy.Completed | Spot Quotation
1035 | Construction of PCC Pavement Zabuanga House to Zailawma House at Zobawk Vengthar | 6 | Hnahthial Division |  |  | 100% | 3 |  |  | 100% | 3 | Phy.Completed | Spot Quotation
1036 | Construction of Retaining Wall near Gov"t High School Road (Hmawng hnuai) at Zobawk Vengthar | 6 | Hnahthial Division |  |  | 100% | 3 |  |  | 100% | 3 | Phy.Completed | Spot Quotation
1037 | Const.of Retaining Wall at B.Laltanpuia house at Zobawk Venghlun | 5 | Hnahthial Division |  |  | 100% | 2.5 |  |  | 100% | 2.5 | Phy.Completed | Spot Quotation
1038 | Construction of PCC pavement between C.Vanlalhmuaka House to P.Lalromawia House at Zobawk Bazar | 10 | Hnahthial Division |  |  | 100% | 5 |  |  | 100% | 5 | Phy.Completed | Spot Quotation
1039 | Construction of PCC pavement between Ralvawng mual Volley Ball Court at Zobawk Bazar | 5.5 | Hnahthial Division |  |  | 100% | 2.75 |  |  | 100% | 2.75 | Phy.Completed | Spot Quotation
1040 | Const.of PCC Pavement between Pu Lallawma House to Pu V.Zoramthanga house at Zobawk Venghlun | 6 | Hnahthial Division |  |  | 100% | 3 |  |  | 100% | 3 | Phy.Completed | Spot Quotation
1041 | Construction of RCC Steps C.Lalchungnunga House to Lallianpuii House at Zobawk Venghlun | 4.5 | Hnahthial Division |  |  | 100% | 2.25 |  |  | 100% | 2.25 | Phy.Completed | Spot Quotation
1042 | Repairing and Widening of Road, Sairep to Hlumte Road | 12 | Hnahthial Division |  |  | 100% | 6 |  |  | 100% | 6 | Phy.Completed | Spot Quotation
1043 | Construction of Retaining Wall near BCM Biakin and Lalramlawma House between Lalnunhlua house at Hlumte | 4 | Hnahthial Division |  |  | 100% | 2 |  |  | 100% | 2 | Phy.Completed | Spot Quotation
1044 | Construction of Bawkzau (Sairep village potential area) Link Road from Sairep Village | 40 | Hnahthial Division |  |  | 100% | 20 |  |  | 100% | 20 | Phy.Completed | Spot Quotation
IMPROVEMENT OF HNAHTHIAL TOWN ROAD
1045 | SMBT of approach Road to HDFA Playground | 63.6 | Hnahthial Division |  |  | 100% | 31.8 |  |  | 100% | 31.8 | Phy.Completed | Spot Quotation
1046 | Resurfacing within Hnahthial Town | 31.51 | Hnahthial Division |  |  | 100% | 15.76 |  |  | 100% | 15.76 | Phy.Completed | Spot Quotation
1047 | RCC Drain on approach Road to DC Office | 3 | Hnahthial Division |  |  | 100% | 1.5 |  |  | 100% | 1.5 | Phy.Completed | Spot Quotation
1048 | Retaining wall at Ch: 0.4 Km on approach Road to Zosangliana House to Lalduhawma House | 1.89 | Hnahthial Division |  |  | 100% | 0.95 |  |  | 100% | 0.95 | Phy.Completed | Spot Quotation
Construction of Pavement at Tawipui S - Tawipui N
1049 | (i) Const.of PCC Pavement Tawipui S approach road | 30 | Hnahthial Division |  |  | 100% | 15 |  |  | 100% | 15 | Phy.Completed | Spot Quotation
1050 | (ii) Construction of PCC Pavement Tawipui N-II HS approach road | 40 | Hnahthial Division |  |  | 100% | 20 |  |  | 100% | 20 | Phy.Completed | Spot Quotation
1051 | (iii) Const.of PCC Pavement Road from Tawipui S Bazar (NH 54) to Hermon Veng | 45 | Hnahthial Division |  |  | 100% | 22.5 |  |  | 100% | 22.5 | Phy.Completed | Spot Quotation
1052 | (iv) Const.of PCC Pavement Road from NH 54 to Thualthu Bazar to Upper Thaulthu | 45 | Hnahthial Division |  |  | 100% | 22.5 |  |  | 100% | 22.5 | Phy.Completed | Spot Quotation
1053 | (v) Const.of Thangpui and Thangte Village Road from Vaisam PMGSY Road (at Thangpui Khawhnuai Chainage) | 40 | Hnahthial Division |  |  | 100% | 20 |  |  | 100% | 20 | Phy.Completed | Spot Quotation
1054 | (vi) Cons.of Ngengpui Zau Link road from Thlisam Road | 25 | Hnahthial Division |  |  | 100% | 12.5 |  |  | 100% | 12.5 | Phy.Completed | Spot Quotation
1055 | (vii) Const.of Mat Zau Link road from Tawipui N-II | 50 | Hnahthial Division |  |  | 100% |  |  |  | 100% |  | Phy.Completed | Spot Quotation
1056 | (viii) Const.of Ruangte river zau Link road from Vaisam PMGSY Road | 20 | Hnahthial Division |  |  | 100% | 10 |  |  | 100% | 10 | Phy.Completed | Spot Quotation
CONST. & UPGRADATION OF RETAINING WALL AT ZOBAWK RINGROAD :
1057 | Construction of link road Silaitlak (Balu lakna) Road at Rotlang 'E' | 5 | Hnahthial Division |  |  | 100% | 2.42 |  |  | 100% | 2.42 | Phy.Completed | Spot Quotation
1058 | Construction PCC Pavement at High School Road at Rotlang 'E' | 6 | Hnahthial Division |  |  | 100% | 2.9 |  |  | 100% | 2.9 | Phy.Completed | Spot Quotation
1059 | Const. PCC Pavement near F.Malsawmthanga House at Rotlang 'E' | 2 | Hnahthial Division |  |  | 100% | 0.97 |  |  | 100% | 0.97 | Phy.Completed | Spot Quotation
1060 | Construction of Retaining Wall at Middle School at Rotlang 'E' | 2 | Hnahthial Division |  |  | 100% | 0.97 |  |  | 100% | 0.97 | Phy.Completed | Spot Quotation
1061 | Construction of Waiting Shed at Chinrang Kawn and Ramrikawn at Ralvawng | 3 | Hnahthial Division |  |  | 100% | 1.45 |  |  | 100% | 1.45 | Phy.Completed | Spot Quotation
1062 | Construction of Link Road at New Ralvawng to Old Ralvawng | 5 | Hnahthial Division |  |  | 100% | 2.42 |  |  | 100% | 2.42 | Phy.Completed | Spot Quotation
1063 | Construction of PCC Pavement from Ramthim Dawr to Govt. Primary School at Leite | 3 | Hnahthial Division |  |  | 100% | 1.45 |  |  | 100% | 1.45 | Phy.Completed | Spot Quotation
1064 | Construction of PCC Step with Railing and Side Drain between NH-54 to K.Vanramenga House at Leite | 7 | Hnahthial Division |  |  | 100% | 3.5 |  |  | 100% | 3.5 | Phy.Completed | Spot Quotation
SIAHA DIVISION :
1065 | Strengthening and Improvement of Kawlchaw to Serkawr Road | 318 | Siaha Division | 21.03.23 | 21.03.24 | 35% | 53.91 | 48.1% |  | 83.1% | 53.91 | Work in progress. | Item rate Contract
1066 | Improvement and Upgradation of Siaha to Thingsen Road upto NH 54B Junction (7.00km) | 778.53 | Siaha Division | 21.03.23 | 21.03.24 | 5.05% | 27.82 |  |  | 5.05% | 27.82 | Work in progress. | Item rate Contract
1067 | Construction of RCC Slab Culvert on I&PRO Office to Upper Council Vaih Road at 0.200kmp | 38.29 | Siaha Division | 06.03.23 | 30.04.23 | 100% | 38.29 |  |  | 100% | 38.29 | Completed | Item rate Contract
1068 | Re-construction of Slab Culvert on Chheihlu to Chakhang Road at 9.100kmp | 9.4 | Siaha Division | 21.03.23 | 21.03.24 | 100% | 9.4 |  |  | 100% | 9.4 | Completed | Item rate Contract
1069 | Construction of Retaining Wall near EE, PWD Qtrs at Ch:0.020Km | 8.74 | Siaha Division | 21.23.23 | 30.04.23 | 100% | 8.74 |  |  | 100% | 8.74 | Completed | Item rate Contract
1070 | Wifening Road at Cheural - Lungzarhtum - Vartekkai - Sangau (11.50Km) in Mizoram for the year 2022-23 under SASCI Group-1. Widening of Road from BCM Church to BRTF Road via Middle School at Cheural Town Extension (L=1.800km) | 43.12 | Siaha Division | 09.04.23 | 30.9.23 | 42.53% | 10.09 |  |  | 42.53% | 10.09 | Work in progress | Item rate Contract
1071 | Wifening Road at Cheural - Lungzarhtum - Vartekkai - Sangau (11.50Km) in Mizoram for the year 2022-23 under SASCI Group-2. Widening of Road from LIKBK Pastor Qtr to Pu H.Lalhranga House at Lungzarhtum (L=1.500km) | 44.54 | Siaha Division | 09.04.23 | 31.8.23 | 78.5% | 22.27 |  | 12.99 | 78.5% | 35.26 | Work in progress. | Item rate Contract
1072 | Wifening Road at Cheural - Lungzarhtum - Vartekkai - Sangau (11.50Km) in Mizoram for the year 2022-23 under SASCI Group-3 Widening of Road from NEC road Junction to Vartekkai with construction of minor bridge (L=7.000km) | 207.27 | Siaha Division | 09.04.23 | 08.04.24 | 85.08% | 89.21 |  | 36.83 | 85.08% | 126.04 | Work in progress. | Item rate Contract
1073 | Wifening Road at Cheural - Lungzarhtum - Vartekkai - Sangau (11.50Km) in Mizoram for the year 2022-23 under SASCI Group-4 Widening of Road from Tourist Lodge to Vengthar Field via SDO (C) Complex at Sangau (L=0.860km) | 20.07 | Siaha Division | 09.04.23 | 08.07.23 | 45.29% | 7.58 |  | 4.52 | 45.29% | 12.1 | Work in progress. | Item rate Contract
1074 | Formation Cutting of Road to Sand Quarry at Bualpui 'NG' -Archhuang-Sangau-Lungpher (15.46Km) in Mizoram for the year 2022-23 under SASCI | 61.85 | Siaha Division | 09.04.23 | 31.8.23 | 40.52% | 30.5 |  | 27.38 | 40.52% | 57.88 | Work in progress. | Item rate Contract
1075 | Formation Cutting of Road to Sand Quarry at Bualpui 'NG' -Archhuang-Sangau-Lungpher (15.46Km) in Mizoram for the year 2022-23 under SASCI | 49.63 | Siaha Division | 09.04.23 | 31.8.23 | 56.72% | 24.82 |  |  | 56.72% | 24.82 | Work in progress. | Item rate Contract
1076 | Formation Cutting of Road to Sand Quarry at Bualpui 'NG' -Archhuang-Sangau-Lungpher (15.46Km) in Mizoram for the year 2022-23 under SASCI | 38.68 | Siaha Division | 09.04.26 | 8.7.23 | 75.93% | 16.42 |  | 1.7 | 75.93% | 18.12 | Work in progress. | Item rate Contract
1077 | Formation Cutting of Road to Sand Quarry at Bualpui 'NG' -Archhuang-Sangau-Lungpher (15.46Km) in Mizoram for the year 2022-23 under SASCI | 125.86 | Siaha Division | 09.04.23 | 08.04.23 | 67.88% | 56.18 |  |  | 67.88% | 56.18 | Work in progress. | Item rate Contract
KAWRTHAH DIVISION :
1078 | Construction & Upgradation of Bairabi-Zamuang Road (0.00-4.00Kmp) in Mizoram . | 330 | Kawrthah Division | 22.2.23 | 22.5.23 | 100% | 302.85 |  |  | 100% | 302.85 | Phy.Completed | Contract after call of qoutation
MAMIT DIVISION :
1079 | Construction of Mamit Ring Road (5.66) | 600 | Mamit Division | 22.2.24 | 22.5.24 | 84% | 402 | 1% | 29.27 | 85% | 431.27 | Work in Progress | Item rate Contract
1080 | Pavement of Rawpuichhip to Buarpui Road (47.27-58.00Km) | 511 | Mamit Division | 22.2.25 | 22.5.25 | 100% | 402.41 |  | 102.53 | 100% | 504.94 | Phy.Completed | Depart- mental
SERCHHIP DIVISION :
1081 | Improvement of roadsInfrastucture at District Headquarters Saiha, Lawngtlai, Lunglei, Hnahthial, Serchhip, Champhai, Khawzawl, Saitual, Kolasib, Mamit. | 85 | Serchhip Division | 7.10.23 | 30.10.23 | 100% |  |  |  | 100% |  | Phy.Completed | Item rate
1082 | Construction of Pavement, retaining wal, culverts and Balcony at Serchhip Internal Road | 269 | Serchhip Division | 27.2.23 | 27.2.24 | 100% | 134.46 |  | 134.54 | 100% | 269 | Completed | Item rate
1083 | Construction of Economic Road at Tuikum in Mizoram for the year 2022-2023 | 250 | Serchhip Division | 27.2.23 | 27.2.24 | 100% | 125 |  | 125 | 100% | 250 | Completed | Item rate
1084 | Improvement of Existing Road Artahkawn-Biate-Tuipui road within Srchhip District (Sh: Strengthening of Chekawn to Artahkawn Road 0.00-80.00Km) pothole filling and path repair of Biate-Tuipui Road 0.00-18.00Kmp) | 739 | Serchhip Division | 27.2.23 | 27.2.24 | 100% | 375.78 |  | 363.22 | 100% | 739 | Completed | Item rate
1085 | Construction of DS.Chawngtui-N.Vanlaiphai Road (0.00-14.800Kmp) Phase-II (Parmanent Works) | 295 | Serchhip Division | 15.2.23 | 27.10.24 | 45% | 93.03 |  |  | 45% | 93.03 | Work in progress | Item rate
1086 | Construction of Strengthening of double lane BUGS Bridge Over R.Tuichang at 6.00Kmp on Keitum-Artahkawn Road (40R-70R) | 343 | Serchhip Division | 15.2.23 | 31.3.23 | 100% | 175.88 |  |  | 100% | 175.88 | Phy.Completed | Item rate
1087 | Widening, Strengthening & Improvement of Sports Complex Approach Road at Serchhip (Length =1.50Kms) Widening= 1.500Kms Retaining Wall = 80.00 mP.C.C. Pavement = 1.500 Km Side Drain = 1500.00 m Culvert = 8 nos. | 380 | Serchhip Division | 05.10.23 | 05.10.24 | 2.6% |  |  |  | 2.6% |  | Work Mobilized | Item rate
1088 | Additional works for Compietion of Strengthening of Chekawn - Artahkawn Road | 205.01 | Serchhip Division | 07.10.23 | 06.10.24 | 100% |  |  |  | 100% |  | Phy.Completed | Item rate
1089 | Const. of Agriculturre Link road to River Lungva from Hriangtlang, Sialsir, Hlaizawl. | 351.5 | Serchhip Division | 05.10.23 | 05.10.24 | 22.5% |  |  |  | 22.5% |  | Work in progress | Item rate
LAWNGTLAI DIVISION :
Improvement of Thlengang to river Chhimtuipui Road :
1090 | Construction of RCC Dock along with approach Slab | 23.31 | Lawngtlai Division | 11.05.23 | 10.4.24 | 75% | 5.7 | 15% | 5.7 | 90% | 11.4 | Work in progress
1091 | Widening of Lawngtlai to Sahriluichhuah (Kalodyne River) Balu Road | 94.8 | Lawngtlai Division | 11.05.23 | 10.4.24 | 90% | 54.31 | 10% | 37.25 | 100% | 91.56 | Completed
1092 | Improvement of Bethel veng to Chengkawllui road at College veng, Lawngtlai | 90.84 | Lawngtlai Division | 11.05.23 | 10.4.24 | [6 empty] | Not yet started
Improvement of Thlengang to river Chhimtuipui Road :
1093 | Formation cutting of Vathuampui to Mautlang Road | 70.47 | Lawngtlai Division | 11.05.23 | 10.4.24 | 100% | 35.21 |  | 35.21 | 100% | 70.42 | Phy.Completed
1094 | Widening of Bungtlang 'S' to Saikhawthlir Road | 56.15 | Lawngtlai Division | 11.05.23 | 10.4.24 | 100% | 25.08 |  | 25.05 | 100% | 50.13 | Phy.Completed
1095 | Widening of Hmawngbu to Kakichhuah Road | 61.99 | Lawngtlai Division | 11.05.23 | 10.4.24 | 100% | 15.84 |  | 15.84 | 100% | 31.68 | Phy.Completed
IMPROVEMENT OF DILTLANG TO CHAWNGTELUI ROAD
1096 | Construction of Retaining Wall at Certain Location | 25.07 | Lawngtlai Division | 11.05.23 | 10.4.24 | 100% | 15.58 |  | 8.58 | 100% | 24.16 | Phy Completed
1097 | Resurfacing of NH-54 to DTO Office (including courtyard) at Chanmari, Lawngtlai | 6.99 | Lawngtlai Division | 11.05.23 | 10.4.24 | [6 empty] | Not yet started
1098 | Construction of Minor Bridge between Khawmawi Bazar Veng to Khawmawi Vengthar | 34.48 | Lawngtlai Division | 11.05.23 | 10.4.24 | 100% | 17.23 |  | 17.23 | 100% | 34.46 | Phy.Completed
1099 | Black topping of internal road at Lawngpuighat | 81.65 | Lawngtlai Division | 11.05.23 | 10.4.24 | 12.17% | 9.3 | 87.83% | 67.26 | 100% | 76.56 | Completed
1100 | Construction of Playground approach road at Thingfal Mamte Veng | 19.49 | Lawngtlai Division | 11.05.23 | 10.4.24 | 100% |  |  | 9.74 | 100% | 9.74 | Phy.Completed
1101 | Consultancy fee for Roads | 66.55 | Lawngtlai Division | 11.05.23 | 10.4.24 | 15% | 9.98 |  |  | 15% | 9.98 | Work in progress
1102 | Consultancy Fee for Bridges | 106.39 | Lawngtlai Division | 11.05.23 | 10.4.24 | 70% | 53.2 |  | 21.48 | 70% | 74.68 | Work progress
AIZAWL BUILDING DIVISION : 2023 - 2024
1103 | Upgradation of Raj Bhavan, CM Bungalow, Secretariat Building & Assembly Building under SASCI. | 234.68 | Aizawl Building Division | 17.02.232 | 09.03.23 | 100% | 230.93 |  |  | 100% | 230.93 | Completed | Depart- mental
National Highway Division - I (SASCI 2023 - 2024)
1104 | Const. of Bamboo Link Road from Hmunpui to Mauhaklui & Tuidam approach Road in Mizoram. | 263 | National Highway Division - I | 15.12.23 | 15.12.24 | 53.33% |  |  |  | 53.33% |  | Work in Progress | Restricted Tender
1105 | Const. of Saiphai to Hortoki Road (13.800 Km) | 1200 | National Highway Division - I | 15.12.23 | 15.12.25 | [6 empty] | Not yet started | Restricted Tender
1106 | Improvement of Roads and Infrastructure at District Headquarters; Saiha, Lawngtlai, Lunglei, Hnahthial, Serchhip, Champhai, Khawzawl, Saitual, Kolasib, Mamit ; (Sh: Tuidam Approach Road) | 10 | National Highway Division - I | 31.03.23 | 31.03.24 | 50% |  |  |  | 50% |  | Work in Progress | Depart- mental
1107 | Improvement of Roads and Infrastructure at District Headquarters; Saiha, Lawngtlai, Lunglei, Hnahthial, Serchhip, Champhai, Khawzawl, Saitual, Kolasib, Mamit ; (Sh: Strengthening of Bailey Bridge over R. Teirei (Darlak) on NH-44A | 70 | National Highway Division - I | 31.03.23 | 31.03.24 |  |  | 10% |  | 10% |  | Work Started | Depart- mental
1108 | Improvement of Roads and Infrastructure at District Headquarters; Saiha, Lawngtlai, Lunglei, Hnahthial, Serchhip, Champhai, Khawzawl, Saitual, Kolasib, Mamit ; (Sh:Mamit to Bairabi Road) | 16 | National Highway Division - I | 31.03.23 | 31.03.24 | 50% |  |  |  | 50% |  | Work in Progress | Depart- mental
1109 | Improvement of Roads and Infrastructure at District Headquarters; Saiha, Lawngtlai, Lunglei, Hnahthial, Serchhip, Champhai, Khawzawl, Saitual, Kolasib, Mamit ; (Sh:Dampui Approach Road from NH-44A | 5 | National Highway Division - I | 31.03.23 | 31.03.24 | [6 empty] | Not yet started | Depart- mental
1110 | Improvement of Roads and Infrastructure at Aizawl City (Sh: Clearing, Grubbing of Roads Land and Jungle clearance of Saiphai Bamboo Plantation in Mizoram | 45 | National Highway Division - I | 31.03.23 | 31.03.24 | [6 empty] | Not yet started | Depart- mental
1111 | Improvement of Roads and Infrastructure at Aizawl City (Sh: Work under National Highway Division-I) | 30 | National Highway Division - I | 31.03.23 | 31.03.24 | [6 empty] | Not yet started | Depart- mental
1112 | Improvement of Roads and Infrastructure at Aizawl City (Sh: Estimate for Const. of Lengpui Catholic School Road PCC) | 15 | National Highway Division - I | 31.03.23 | 31.03.24 | 100% |  |  |  | 100% |  | Phy.Completed | Depart- mental
NATIONAL HIGHWAY DIVISION - III
1113 | Const. of Rigid Pavement at essential places between 133.00Kmp to 147.00Kmp on NH-54 (Total Length =400.00 m) | 267 | National Highway Division - III | 25.7.23 | 13.11.23 | 60% |  | 40% |  | 100% |  | Phy.Completed | Departmental
1114 | Upgradation of Saiphai, Zophai and Berhvakawn to Mualkhang Road. | 220 | National Highway Division - III
1115 | Improvement of Roads and Infrastructures at Aizawl City (Sh: Pot Hole filling and patches repair of NH-54(NH-6) for regular flow of traffic (Kawnpui - Sairang ) | 20 | National Highway Division - III | 18.9.23 | 15.11.23 | 100% |  |  |  | 100% |  | Phy.Completed | Departmental
QUALITY CONTROL RESEARCH & DEVELOPMENT DIVISION, ZUANGTUI : AIZAWL.
1116 | Improvement of Government Building, High Court, Government Polytechnic & E-in-C, PWD Office (Sh: Const. of Barbet Wire fencing of PWD Complex at Zuangtui. | 23.3 | Quality Control Research & Development Division. |  |  | 40% |  | 5% |  | 45% |  | Work in Progress | Spot Quotation
1117 | Improvement of Government Building, High Court, Government Polytechnic & E-in-C, PWD Office (Sh: Const. ofBeily Bridge PartsGodown at PWD Complex, Zuangtui | 20 | Quality Control Research & Development Division. |  |  | 10% |  |  |  | 10% |  | Work in Progress | Departmental