## NABARD
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding: NABARD | [8 empty] | Month : March 2024
Sl. no | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Const.of BUSG Composite Bridges over R.Chepte on Bilkhawthlar to Saiphai Road | 508.45 | Kolasib Division | 24.6.19 | 31.03.22 | 42% | 128.5 | 15% | - | 57% | 128.5
2 | Const.of BUSG Composite Bridges over R.Sesih on Bilkhawthlar to Saiphai Road | 281.12 | Kolasib Division | 24.6.19 | 31.03.22 | 58% | 122.67 | 12% | 39.36 | 70% | 162.03
3 | Design & Construction of T-Beam Bridge Package-II at Bulung River (CH:10.20 KMP) | 996 | Kolasib Division | 24.12.21 | 24.06.23 | 2% | - | 3% | 42.42 | 5% | 42.42
4 | Design & Construction of T-Beam Bridge Package-II at Damdiai River (CH:23.50 KMP) | 996 | Kolasib Division | 24.12.21 | 24.06.23 | 5% | - | 5% | 39.66% | 10% | 39.66 | Foundation at Hortoki side is being constructed
5 | Design & Construction of T-Beam Bridge Package-I at Chhimluangte River (CH:0.450 KMP) | 969.01 | Kolasib Division | 18.12.21 | 18.06.23 | 26% | 28.56 | 4% | 128.73 | 30% | 157.29
6 | Design & Construction of T-Beam Bridge Package-I at Dumkhel River (CH:5.50 KMP) | 969.01 | Kolasib Division | 18.12.21 | 18.06.23 | 23% | - |  | 115.75 | 23% | 115.75
7 | Const.of Meidum to Hortoki Road Phase -II (Km 9.100 to Km 26.000) SH: Earthworks and Permanent works from Km 9.100-Km 13.325) Package -I | 1087.32 | Kolasib Division | 24.12.21 | 09.03.24 | 96% | 830.99 | 4% | 143.56 | 100% | 974.55
8 | Const.of Meidum to Hortoki Road Phase -II (Km 13.325 to Km 17.500 SH: Earthworks and Permanent works from Km 13.325 to Km 17.500) Package -II | 1171 | Kolasib Division | 25.12.21 | 25.06.23 | 92% | 560.13 | 4% | 55.18 | 96% | 615.31
9 | Const.of Meidum to Hortoki Road Phase -II (Km 17.500 to Km 21.725 SH: Earthworks and Permanent works from Km 15.690 to Km 19.005) Package -III | 1422 | Kolasib Division | 18.12.21 | 18.06.23 | 96.74% | 1054.73 |  | 43.16 | 96.74% | 1097.89
10 | Const.of Meidum to Hortoki Road Phase -II (Km 21.725 to Km 26.000 SH: Earthworks and Permanent works from Km 19.005 to Km 22.360) Package -IV | 959 | Kolasib Division | 08.12.21 | 8.06.23 | 93.48% | 866.08 |  |  | 93.48% | 866.08
11 | Construction of Meidum to Hortoki Road Phase - II (Km 9.100 to 26.000): SH: Construction of Rigid pavement: Package-I (Km 9.100-Km 15.730) | 2390.08 | Kolasib Division | 03.08.22 | 03.08.23 | 5% | 440.93 |  |  | 5% | 440.93
12 | Construction of Meidum to Hortoki Road Phase - II (Km 9.100 to 26.000): SH: Construction of Rigid pavement: Package-II (Km 15.73-Km 22.36) | 2390.08 | Kolasib Division | 24.12.21 | 24.06.23 | 4% | 341.16 |  |  | 4% | 341.16
13 | Construction of link Road from NH-306 (PHE pump House) to R.Aitlang Lui Basin Crop Land : Length = 9.22 Kms | 465.66 | Kolasib Division | 12.08.22 | 12.08.23 | 60% | 444.32 | - | 1.43 | 60% | 445.75 | Works completed | Restricted Tender
14 | Construction of link Road from NH-306 (Vairengte) to Sabual Mual Arable Crop Land = 3.720 Kms | 418.89 | Kolasib Division | 13.08.22 | 13.08.23 | 92.42% | 309.39 |  | 58.63 | 92.42% | 368.02 |  | Restricted Tender
15 | Construction of Agriculture Link Road from NH-306 A to Buarchep Arable Crop Land : Length = 1.720 Kms | 175.03 | Kolasib Division | 27.08.22 | 27.08.23 | 100% | 170.56 |  |  | 100% | 170.56 | Work physically completed | Restricted Tender
16 | Construction of 24 Warehouses with associated Infrstructure in 23 locations in Mizoram under NABARD (Group-II Zuangtui/Sairang) | 440.97 | Project Division-I | 17.7.23 | 31.3.25 | 1% | - |  | - | 1% | - |  | EPC
18 | Re-Construction of Primary Health Centre at Marpara | 267.62 | Project Division-II | 25.03.22 | (O)25.9.23R)20.12.23 | 100% | 232.82 |  | 34.8 | 100% | 267.62 | Work completed | Item Rate
19 | Construction of 24 Warehouses with associated Infrastructure in 23 locations in Mizoram Group-I (Scheme-NABARD) i) Construction of Warehouse and other amenities at Bairabi | 316.55 | Project Division-II | 17.07.23 | 31.03.25 | 20% |  | 5% | 38.47 | 25% | 38.47 | Work in progress | Item Rate
| ii) Construction of Warehouse and other amenities at Marpara | 235.73 | Project Division-II | 17.07.23 | 31.03.25 | 35% |  | 1% | 63.62 | 36% | 63.61 | Work in progress | Item Rate
| iii) Construction of Warehouse and other amenities at Sialsuk SC | 171.09 | Project Division-II | 17.07.23 | 31.03.25 | 10% |  | 5% | 18.25 | 15% | 18.25 | Work in progress | Item Rate
| iv) Construction of Warehouse and other amenities at Zawlnuam | 176 | Project Division-II | 17.07.23 | 31.03.25 | 20% |  | 12% | 50.4 | 32% | 50.4 | Work in progress | Item Rate
| v) Construction of Warehouse and other amenities at Kanhmun | 175.8 | Project Division-II | 17.07.23 | 31.03.25 | 25% |  | 10% | 54.58 | 35% | 54.58 | Work in progress | Item Rate
20 | Construction of 24 Warehouses with associated Infrastructure in 23 lacations in Mizoram Group-IX (Scheme-NABARD) i) Construction of Warehouse and other amenities at Phuldungsei | 175.81 | Project Division-II | 17.07.23 | 31.03.25 | 8% |  | 32% | 60.9 | 40% | 60.9 | Work in progress | Item Rate
21 | Re-Construction of double storied PHC Building at Bungzung | 268.99 | Project Division-III | 3.1.21 | 3.6.23 | 100% | 268.99 |  |  | 100% | 268.99 | Work completed & Handed over to H&FW Deptt. | PWD Form-8
22 | Re-Construction of double storied PHC Building at Ngentiang | 266.51 | Project Division-III | 3.12.21 | 13.6.23 | 100% | 266.51 |  |  | 100% | 266.51 | Work completed & Handed over to H&FW Deptt. | PWD Form-8
23 | Construction of 24 Warehouses with associated Infrastructure in 23 locations in Mizoram under NABARD (Group-VII: Teikhang, Rabung & Dungtlang) | 336.53 | Project Division-III | 17.7.23 | 31.3.23 | 1% |  | 3% |  | 4% |  | Work in progress | PWD Form-8
24 | Construction of 200 MT Capacity warehouse & staff quarter at Zohmun | 170.99 | Project Division-IV | 17.07.23 | 31.03.25 |  |  | 3.51% |  | 3.51% |  | Work in progress | Item Rate
25 | Improvement & Strengthening of Nalkawn - Chamdur Valley | 2616.41 | Lawngtlai Division | 09.08.19 | 31.12.24 | 61.91% | 1583.78 |  |  | 61.91% | 1583.78 | Supplementary Agreement has been signed on 16.01.24 pursuant to revised/reduced AA amount of Rs.26.16 cr. | Item Rate
26 | Const.of double lane built up Steel Girden Bridge over R.Teirei (Span -102m) at Ch.7.00 Kmp on Bairabi Zamuang Road | 2322.42 | Kawrthah Division | 5.8.17 | 30.6.24 | 57% | 1365.6 | 2% |  | 59% | 1365.6 | Work in progress | Contract after call of Restricted Tender
27 | Const.of double lane built up Steel Girden Bridge (Span-81m) over R.Langkaih on Mizoram-Tripura Border at Kanhmun | 2231.91 | Kawrthah Division | 6.4.18 | 30.11.24 | 42% | 1179.03 | 2% |  | 44% | 1179.03 | Work in progress | Contract after call of Restricted Tender
28 | Construction of Agriculture Link Road in Nothern Mizoram (Sh: Construction of Link Road from Saikhawthlir to R.Hnanglui Arable crop land, Length = 3.50 kms) | 362.02 | Kawrthah Division | 20.08.22 | 20.08.23 | 55.85% | 186.13 | 15% |  | 70.85% | 186.13 | Work in progress | Contract after call of Restricted Tender
29 | Construction of Agriculture Link Road in Nothern Mizoram (Sh: Construction of Link Road from Chuhvel to R.Hnanglui Arable crop land, Length = 2.35 kms) | 284.76 | Kawrthah Division | 18.08.22 | 30.4.24 | 50.35% | 133.77 | 7% | 21.54 | 57.35% | 155.31 | Work in progress | Contract after call of Restricted Tender
30 | Construction of Agriculture Link Road in Nothern Mizoram (Sh: Construction of Link Road from from Thinghlun to Hriphaw through permanent crop length=9.570 kmp) | 385.61 | Kawrthah Division | 20.08.22 | 31.5.24 | 71.86% | 295.97 |  |  | 71.86% | 295.97 | Work could not be progressed due to decision to be taken by authority regarding type of 3 bridges to be constructed | Contract after call of Restricted Tender
31 | Upgradation of Meidum to Hortoki Phase-I (0.0-9.10) | 4445 | NHD-III | 26.5.20 | 26.11.21 1st EOT=211 days (21.11.21-20.6.22) 2nd EOT=375 days (21.6.22-30.6.23) 3rd EOT =243 days (30.6.23-28.2.24) | 98.96% | 3306.99 |  | 694.41 | 98.96% | 4001.4 |  | Item Rate
32 | Construction of River Training Works for Protection of Tlawng River Bank at Bairabi Phase-I (Group-I) | 1111 | NHD-III | 17.10.22 | 17.10.23 1st EOT=166 days 18.10.23-31.3.24 | 100% | 279.17 |  |  | 100% | 279.17 |  | Item Rate
| Phase-I (Group-II) |  |  | 17.10.22 | 17.10.23 1st EOT=166 days 18.10.23-31.3.25 | 100% | 279.17 |  |  | 100% | 279.17 |  | Item Rate
| Phase-I (Group-III) |  |  | 17.10.22 | 17.10.23 | 100% | 216.65 |  |  | 100% | 216.65 |  | Item Rate
| Phase-I (Group-IV) |  |  | 17.10.22 | 17.10.23 | 100% | 246.7 |  |  | 100% | 246.7 |  | Item Rate
33 | Construction of MDR from Khamrang (Dilsei) to Selesih (Sh: Construction of approach road to Mualkhang Village) | 14529.27 | NHD-III | 08.02.21 | 08.08.22 | 100% | 122.25 |  |  | 100% | 122.25 |  | Item Rate
34 | Construction of Road from Khamrang to Selesih Phase-II Group-1 (11/00 to 22/00Km) |  |  | 8.11.21 | 8.5.23 1st EOT=210 days (wef 09.05.23- 04.12.23 | 27.06% | 547.46 | 0.6% | - | 27.66% | 547.46 |  | Item Rate
35 | Construction of Road from Khamrang to Selesih Phase-II Group-2 (22/00 to 25/00Km) |  |  | 22.11.21 | 22.11.22 1st EOT=90days (upto -20.02.23) 2nd EOT=90 days (wef 21.2.23-21.5.23) 3rd EOT = 90 days(22.5.23-19.8.23) | 30.17% | 219.81 | 0.08% |  | 30.25% | 219.81 |  | Item Rate
36 | Construction of Road from Khamrang to Selesih Phase-II Group-3 (25/00 to 28/00Km) |  |  | 11.11.21 | 11.11.22 1st EOT=104 days (upto -24.02.23) 2nd EOT=90 days (wef 10.2.23-11.5.23) 3rd EOT = 90 days(wef 12.5.23-9.8.23) | 16.34% | 207.28 |  |  | 16.34% | 207.28 |  | Item Rate
37 | Construction of Road from Khamrang to Selesih Phase-II (Sh: Construction of Rigid Pavement from 11/00 to 19/00 Kmp=8.00 Kms) Group A |  |  | 26.8.23 | 26.8.25 | [7 empty] | Item Rate
38 | Construction of Road from Khamrang to Selesih Phase-II (Sh: Construction of Rigid Pavement from 19/00 to 28/00 Kmp=9.00Kms) Group B |  |  | 26.8.23 | 26.8.25 | [7 empty] | Item Rate
39 | Construction of MDR from Khamrang-Dilsei to Selesih (Phase-I) (Length = 11.00 Kms) Group-A (0/00 to 3/600Km) | 6583.18 | NHD-III | 8.02.21 | 8.8.22 1st EOT=184 days (upto 08.02.23, 2nd EOT=150 days (upto 08.07.23) | 42.99% | 314.25 |  | - | 42.99% | 314.25 |  | Item Rate
40 | Construction of road from Khamrang to Selesih Phase-I (Length = 11.00 Kms) Group-B (3/60 to 7/200Km) |  | NHD-III | 8.02.21 | 8.8.22 1st EOT=184 days (upto 08.02.23, 2nd EOT=150 days (wef 09.02.23-08.07.23) | 55.71% | 434.62 |  |  | 55.71% | 434.62 |  | Item Rate
41 | Construction of road from Khamrang to Selesih Phase-I (Length = 11.00 Kms) Group-C (7/200 to 11/00Km) |  | NHD-III | 8.02.21 | 8.8.22 1st EOT=184 days (upto 08.02.23, 2nd EOT=150 days (wef 09.02.23-08.07.23) | 48.23% | 177.27 |  |  | 48.23% | 177.27 |  | Item Rate
42 | Construction of road from Khamrang to Selesih Phase-I (Sh: Construction of Rigid Pavement from 7/00 to 11/00 Kmp = 4.00 Kms) |  | NHD-III | 16.8.22 | 16.02.24 | 0.32% |  |  |  | 0.32% |  |  | Item Rate
43 | Const.of Double Storied PHC at Lungsen | 267.15 | Lunglei Building Project Division | 10.2.22 | 10.2.24 | 100% | 230.89 |  |  | 100% | 230.89 | Civil Works completed and I/E Works not yet done | Restricted Tender
44 | Const.of Infrastructure Support fro School of Agricultural Science at Hnahthial: Phase-II i) Boys Hostel ii) Staff Quarter Type-III iii) Staff Quarter Type-II iv) Guest House | 685 | Lunglei Building Project Division | 08.04.23 | 08.04.25 | 31% |  |  |  | 21% |  | Works stayed due to necessity for Laboratory Rebound Hammer Test as per circular | Restricted Tender
45 | 1. Construction of 24 Warehouses with associated Infrastructure in 23 localities in Mizoram under NABARD Gr-III: Siaha, Chapui, Bungtlang South
| 1) Siaha SDC | 444.99 | Lunglei Building Project Division | 17.07.23 | 31.3.25 | 10% |  | 1% | 80.76 | 11% | 80.76 | Work in progress | Restricted Tender
| 2) Chapui | 197.82 | Lunglei Building Project Division | 17.07.23 | 31.3.25 | 2.5% |  | 4.5% | 17.71 | 7% | 17.71 | Work in progress
| 3) Bungtlang South | 162.63 | Lunglei Building Project Division | 17.07.23 | 31.3.25 | 22% |  | 5% | 14.83 | 27% | 14.83 | Work in progress
| 2. Gr-IV: Lungpher | 197.12 | Lunglei Building Project Division | 17.07.23 | 31.3.25 | 30% |  | 5% | 55.4 | 35% | 55.4 | Work in progress | Restricted Tender
3. Gr-VI: South Vanlaiphai and Vawmbuk
| 1) South Vanlaiphai | 187.15 | Lunglei Building Project Division | 17.07.23 | 31.3.25 | 17% |  | 3% |  | 20% |  | Work in progress | Restricted Tender
| 2) Vawmbuk | 197.82 | Lunglei Building Project Division | 17.07.23 | 31.3.25 | 26% |  | 2% |  | 28% |  | Work in progress
4. Gr-VIII: Hnahthial, Thingsai. Cherhlun and Siata
| 1) Hnahthial | 197.24 | Lunglei Building Project Division | 17.07.23 | 31.3.25 | 1% |  |  |  | 1% |  | Work stayed as selected site falls under Forest Reserve Area. Relocation of site is being awaited from Client Dept. | Restricted Tender
| 2) Thingsai | 160.32 | Lunglei Building Project Division | 17.07.23 | 31.3.25 | 7% |  | 3% |  | 10% |  | Work in progress
| 3) Cherhlun | 85.61 | Lunglei Building Project Division | 17.07.23 | 31.3.25 | 7% |  | 3% |  | 10% |  | Work in progress
| 4) Siata | 197.82 | Lunglei Building Project Division | 17.07.23 | 31.3.25 | 25% |  | 4% |  | 29% |  | Work in progress
5. Gr-X: Vaseikai and Tlabung
| 1) Vaseikai | 220.35 | Lunglei Building Project Division | 17.07.23 | 31.3.25 | 21% |  | 4% |  | 25% |  | Work in progress | Restricted Tender
| 2) Tlabung | 93.84 | Lunglei Building Project Division | 17.07.23 | 31.3.25 | 3.5% |  | 1.5% |  | 5% |  | Loweing of ground has been datretd after carrying out Building layout
46 | Strengthening & Improvement of W.Phaileng to Marpara Road (00.00-30.00Kmp) Package-I | 1854.59 | Mamit Division | 15.03.23 | 15.03.25 | 29% | 291.63 |  |  | 29% | 291.63 | Machinery installation completed, operation of Quarry is being started. Physical progress is being achieved
47 | Strengthening & Improvement of W.Phaileng to Marpara Road (30.00-80.00Kmp) Package-II | 4778.8 | Mamit Division | 15.03.23 | 15.03.25 | 29% | 453.47 |  | 0.98 | 29% | 454.45 | Machinery installation completed, operation of Quarry is being started. Physical progress is being achieved
48 | Improvement of Chawngte - Borapansuri Road (0.00-30.00 Kmp) | 3987 | Tlabung Division | 15.3.23 | 15.3.25 | 6.3% |  |  |  | 6.3% |  | Work in progress | Item rate

## NEC
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding: NEC | [8 empty] | Month : March 2024
Sl. no | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the Month |  | Overall cumulative achievement |  | Remarks | Mode of Contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Lunglei Market and Trade Centre at Electric/Chanmari Veng, Lunglei (NEC) | 1403.4 | Lunglei Building Project Division | 25.08.22 | 25.08.24 | 45% | 363.9 | 2% | 198.71 | 47% | 562.61 | Works halted for modification of drawings & design for Block-A which is being awaited | Restricted Tender
2 | Construction of Mara Handloom & Weaving Centre at Council Vaih, Saiha | 458.61 | Lunglei Building Project Division | 13.04.22 | 13.04.24 | 66% | 131.01 | 2% |  | 68% | 131.01 | Work in progress | Restricted Tender
3 | Improvement & Upgradation of KDZKT Road (0.00 - 88.400Kmp) | 18327.42 | Kawrthah Division | 27.4.15 | 4.6.18 | 100% | 18290 | - |  | 100% | 18290 | Work Phy.Completed on 31.12.21 SMS of R.Revised estimate is being awaited for financial closure | Contract after call of Tender
4 | Const.of Patient Lodging at Mawdiangdiang near NEIGHRIMS, Shillong | 419.67 | Project Division-I | 9.9.21 | 31.7.24 | 20% | 167.87 |  |  | 20% | 167.87 |  | EPC
5 | Infrastructure Development of Biotechnology Cell in Mizoram (C/O Building at MINECO) | 386.6 | Project Division-I | 1.7.23 | 1.5.25 | 11% | 19.22 | 5% |  | 16% | 19.22 |  | EPC
6 | Establishment of Central Medical Warehouse at Aizawl, Mizoram | 1300 | Project Division-I | 4.8.23 | 14.8.25 | 1% |  |  |  | 1% |  |  | EPC
7 | Construction of Aizawl Institute of Arts & Music for the NER, Tuivamit Tlang, Aizawl | 590.23 | Project Division-I | 4.9.23 | 4.9.25 | 33% |  |  | 120.03 | 33% | 120.03 |  | EPC
8 | Construction of Veterinary Information and Resource Centre at Aizawl | 439.2 | Project Division-I | 31.3.23 | 25.9.25 | 15% | 10 | 3% |  | 18% | 10 |  | EPC
9 | Construction of 60 Bedded Intern Hostel at ZMC, Falkawn | 679 | Project Division-II | 01.09.22 | 01.05.24 | 50% | 271.6 | 4% |  | 54% | 271.6 | Work in progress | Item Rate
10 | Construction of Market Building at West Phaileng, Mamit District | 278.242 | Project Division-II | 22.08.23 | 22.08.25 | 6% |  | 4% |  | 10% |  | Work in progress | Item Rate
11 | Creation of Passion fruit Processing unit at Cold Storage, New Champhai Mizoram | 185.36 | Project Division-III | 23.09.22 | 24.03.24 | 60% | 10 | 15% |  | 75% | 10 | As per revised sanction by NEC, only civil construction work is under PWD Work in progress | PWD Form-8
12 | Construction of Zomi cultural Centre and preservation of historical sites at Champhai | 478.69 | Project Division-III | 26.09.22 | 26.09.24 | 35% | 76 | 10% |  | 45% | 76 | Work in progress | PWD Form-8
13 | Construction of Biate Tea Tourism Circuit & Nature Camp in Mizoram | 369.62 | Project Division-III | 9.10.23 | 9.10.25 | 45% |  | 10% |  | 55% | - | Work in progress | PWD Form-8
14 | Forstering Industry, Innovation, Infrastructure and Livelihood Oppurtunities (SDG 9) at Lunglen-1 and Sialhawk, Mizoram and strengthening of Food Testing Laboratory (Sh: Construction of Pineapple precessing plant building at Sialhawk) | 65.7 | Project Division-III | 12.10.23 | 12.10.25 | 60% |  | 8% |  | 68% |  | Work in progress | PWD Form-8
15 | Establishing Mizo cultural heritage centre for protecting the historical and natural heritage of Mizo at Kawlri, Serchhip | 486.47 | Project Division-III | 16.2.24 | 16.2.26 | [6 empty] | Jungle clearance completed. Work being mobilized | PWD Form-8
16 | Construction of Community Hall at Bethel Veng Champhai | 1443.75 | Project Division-III | 16.2.24 | 16.2.26 | [6 empty] | Layout done. There is site problem which is being pursued | PWD Form-8
17 | Construction of AYUSH Development Centre at MINECO Aizawl | 264.16 | Project Division-IV | 7.12.22 | 17.8.24 | 42.3% | 40 | 1.38% |  | 43.68% | 40 | Work in progress. | Item Rate
18 | Etablishment of Sinlung Hills Council Administrative Complex (Const.of Sinlung Hills Administrative Building at Sakawrdai) | 381.99 | Project Division-IV | 8.11.21 | 12.03.24 | 59.1% | 152.98 | 2.9% |  | 62% | 152.98 | Work in progress. | Item Rate

## Deposit
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : Deposit | [9 empty] | Month : Marchy 2024
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummutive Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of New Ward Building (Renovation & Upgradation of Central Jail) at Aizawl, Mizoram | 100 | Project Division-I | 28.8.22 | 23.3.24 | 42% | - | 5% | - | 47% | - |  | EPC

## PMGSY
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding: PMGSY | [8 empty] | Month : March 2024
Sl. no | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Diblibagh to Chengkawllui Road (0.000-19.520)Kmp | 2798.82 | Tlabung Division | 17.6.19 | 17.6.20 | 70.61% | 1509.2 | 9.12% |  | 79.73% | 1509.2 |  | Item Rate
2 | Diblibagh to Sugarbasora Road (0.000-2.000)Kmp | 305.81 | Tlabung Division | 28.9.18 | 28.9.19 | 73.5% | 211.07 | 0.6% |  | 74.1% | 211.07 | Extension granted up to Dt.31.03.23 | Item Rate
3 | Diblibagh to Sugarbasora Road Group B (2.000-4.760)Kmp | 373.19 | Tlabung Division | 22.9.18 | 22.9.19 | 97.6% | 123.6 | 2.4% | 87.36 | 100% | 210.96 | Completed physical works Extension granted upto Dt.31.3.23 | Item Rate
4 | Const & Maintenance of Tlabung-Nunsury Road (0.000-8.000) Kmp | 579.77 | Tlabung Division | 17.6.19 | 17.6.20 | 55.3% | 499.42 | 44.5% |  | 99.8% | 499.42 | Completed phy.works | Item Rate
5 | Const.of Serhuan-Lamthai Road | 1378.12 | Tlabung Division | 21.12.17 | 27.11.19 | 91.5% | 1175.33 | 7.3% |  | 98.8% | 1175.33 | Completed phy.works | Item Rate
6 | Chhotapansuri-Tungasora Road (0.000-2.000)Kmp | 303.43 | Tlabung Division | 22.9.18 | 22.9.19 | 70.6% | 100.06 | 29.4% | - | 100% | 100.06 | Completed phy.works | Item Rate
7 | Chhotapansuri-Tungasora Road (2.000-3.500)Kmp | 209.66 | Tlabung Division | 5.10.18 | 5.10.19 | 100% | 175.89 |  |  | 100% | 175.89 | Completed physical works | Item Rate
8 | Mandiasora-Ajasora Road (0.000 - 8.500) Kmp | 734.93 | Tlabung Division | 17.6.19 | 17.6.20 | 95.8% | 648.92 | 4.2% |  | 100% | 648.92 | Completed physical works | Item Rate
9 | Construction & Maintenance of Sairang - Lengte-Nghalchawm (PMGSY) Road | 991.9 | NHD-I | 19.12.20 | 31.3.24 | 98% | 841.17 | 2% | 150.54 | 100% | 991.71 | Completed | Item rate contract
10 | Construction of Dilkhan to Tualbung Road (Sh:-Construction of Road using flexible pavement) | 503.66 | Saitual Division | 27.10.17 | 27.10.19 | 100% | 499.05 | - | - | 100% | 499.05 | EoT Dt.31.7.2022
11 | Construction and Maintenance of Lungpher to Buhban Road (Sh: Construction of road using flexible pavement) | 490.11 | Saitual Division | 13.11.17 | 13.5.19 | 100% | 478.12 | - | - | 100% | 478.12 | EoT Dt.13.11.19
12 | Construction and Maintenance of Phullen to Luangpawn Road (Sh: FC, Culvert & R/Wall and Construction of road using flexible pavement) | 993.46 | Saitual Division | 17.09.18 | 17.09.19 | 100% | 969.75 | - | - | 100% | 969.75 | EoT Dt.31.7.22
13 | Construction and Maintenance of E.Phaileng-Suangpuilawn Road (0.000-6.000Kmp) (Sh: Widening, Culverts & R/Wall and Contstruction of road using flexible pavement) | 831.6 | Saitual Division | 19.12.20 | 19.12.22 | 93.25% | 142.92 |  | - | 93.25% | 142.92 | EoT Dt.15.10.23
14 | Construction and Maintenance of E.Phaileng-Suangpuilawn Road (6.000-11.000Kmp) (Sh: Widening, Culverts & R/Wall and Construction of Road using flexible pavement) | 906.48 | Saitual Division | 19.12.20 | 19.12.22 | 78.73% | 211.36 | 9.19% |  | 87.92% | 211.36 | EoT Dt.31.3.24
15 | Construction and Maintenance of E.Phaileng-Suangpuilawn Road (11.000-16.000Kmp) (Sh: Widening, Culverts & R/Wall and Construction of Road using flexible pavement) | 807.85 | Saitual Division | 15.8.20 | 15.8.22 | 100% | 807.24 | - |  | 100% | 807.24 | EoT Dt.31.03.24
16 | Construction and Maintenance of E.Phaileng-Suangpuilawn Road (16.000-22.000Kmp) (Sh: Widening, Culverts & R/Wall and Construction of Road using flexible pavement) | 826.35 | Saitual Division | 01.01.21 | 01.01.23 | 78.2% | 305.65 | 0.2% | 70.12 | 78.4% | 375.77 | EoT Dt.28.10.23
17 | Construction and Maintenance of E.Phaileng-Suangpuilawn Road (22.000-28.000Kmp) (Sh: Widening, Culverts & R/Wall and Construction of Road using flexible pavement) | 811.18 | Saitual Division | 01.01.21 | 01.01.23 | 100% | 632.27 | - | - | 100% | 632.27 | EoT Dt.30.3.24
18 | Construction and Maintenance of E.Phaileng-Suangpuilawn Road (28.000-34.000Kmp) (Sh: Widening, Culverts & R/Wall and Construction of Road using flexible pavement) | 1133.61 | Saitual Division | 10.02.20 | 10.02.22 | 100% | 1027.86 | - | 100.75 | 100% | 1128.61 | EoT Dt.31.12.22
19 | Construction and Maintenance of E.Phaileng-Suangpuilawn Road 34.000-40.000Kmp) (Sh: Widening, Culverts & R/Wall and Construction of Road using flexible pavement) | 1056.01 | Saitual Division | 6.01.20 | 6.01.22 | 78% | 833.33 | 2.48% |  | 80.48% | 833.33 | EoT Dt.4.11.23
20 | Construction and Maintenance of E.Phaileng-Suangpuilawn Road 40.000-46.000Kmp) (Sh: Widening, Culverts & R/Wall and Construction of Road using flexible pavement) | 1000.02 | Saitual Division | 6.01.20 | 6.01.22 | 78.15% | 342.05 | 5.58% |  | 83.73% | 342.05 | EoT Dt.18.7.23
21 | Construction and Maintenance of Bunghmun-W.Mualthuam Road (Sh: Cell filled Concrete Road) (0.00-13.500 Kmp) | 955.77 | Kawrthah Division | 27.11.17 | 16.9.22 | 100% | 918.23 | - | - | 100% | 918.23 | Works under maintenance from 16.9.22 | Contract after call of Tender
22 | Construction and Maintenance of Bunghmun to Thaidawr Road (0.00 Kmp-8.90 Kmp) | 745.77 | Kawrthah Division | 17.6.19 | 16.9.22 | 100% | 720.72 | - | - | 100% | 720.72 | Works under maintenance from 16.9.22 | Contract after call of Tender
23 | Construction & Maintenance of Khawzawl to Biate Road (0.00 kmp-6.00Km) Group-A | 780.49 | Khawzawl Division | 31.12.20 | 31.12.22 | 81% | 485.19 | 12% | 136.97 | 93% | 622.16 | EOT granted upto 31.03.24 | Item Rate Contract
24 | Construction & Maintenance of Khawzawl to Biate Road (6.00 kmp-12.00Km) Group-B | 760.98 | Khawzawl Division | 31.12.20 | 31.12.22 | 84% | 429.8 | 14% | 217.6 | 98% | 647.4 | EOT granted upto 31.03.24 | Item Rate Contract
25 | Construction & Maintenance of Khawzawl to Biate Road (12.00 kmp-18.00Km) Group-C | 817.47 | Khawzawl Division | 2.1.21 | 2.1.23 | 84% | 500.54 | 10% | 158.62 | 94% | 659.16 | EOT granted upto 29.10.23 | Item Rate Contract
26 | Construction & Maintenance of Khawzawl to Biate Road (18.00 kmp-24.00Km) Group-D | 750.94 | Khawzawl Division | 10.6.20 | 10.6.22 | 64% | 423.8 | 11% | 91.92 | 75% | 515.72 | EOT granted upto 31.03.24 | Item rate contract
27 | Construction & Maintenance of Khawzawl to Biate Road (24.00 kmp-30.00Km) Group-E | 766.62 | Khawzawl Division | 29.4.21 | 29.4.22 | 61% | 326.07 | 6% | 107.66 | 67% | 433.73 | EOT granted upto 03.03.24 | Item Rate Contract
28 | Construction & Maintenance of Khawzawl to Biate Road (30.00 kmp-36.00Km) Group-F | 1148.93 | Khawzawl Division | 7.2.20 | 7.2.22 | 91% | 664.74 | 4% | 178.81 | 95% | 843.55 | EOT granted upto 31.12.22 | Item Rate Contract
29 | Construction & Maintenance of Khawzawl to Biate Road (36.00 kmp-42.00Km) Group-G | 818.99 | Khawzawl Division | 1.1.21 | 1.1.23 | 100% | 766.95 |  | 25.83 | 100% | 792.78 | Completed on 23.02.24 | Item Rate Contract
30 | Construction & Maintenance of Khawzawl to Biate Road (42.00 kmp-48.00Km) Group-H | 1430.26 | Khawzawl Division | 6.1.20 | 6.1.22 | 83% | 997.07 | 4% | 16.38 | 87% | 1013.45 | EOT granted upto 31.03.24 | Item rate contract
31 | Construction & Maintenance of Khawzawl to Biate Road (48.00 kmp-54.00Km) Group-I | 1108.01 | Khawzawl Division | 24.3.21 | 24.3.22 | 75% | 422.78 | 15% | 30.26 | 90% | 453.04 | EOT granted upto 31.12.22 | Item Rate Contract
32 | Construction & Maintenance of Khawzawl to Biate Road (54.00 kmp-60.00Km) Group-J | 937.99 | Khawzawl Division | 4.1.21 | 4.1.23 | 70% | 442.83 | 10% | 33.55 | 80% | 476.38 | EOT granted upto 31.12.23 | Item Rate Contract
33 | Construction & Maintenance of Khawzawl-Ngaizawl Road | 817.57 | Khawzawl Division | 13.11.17 | 13.11.19 | 93% | 729.12 | - |  | 93% | 729.12 | EOT granted upto 09.12.22 | Item Rate Contract
34 | Construction & Maintenance of Khawhai - Tlangpuilian Road | 962.79 | Khawzawl Division | 13.11.17 | 31.12.19 | 100% | 855.19 |  | 54.03 | 100% | 909.22 | EOT granted upto 01.03.24 | Item Rate Contract
35 | Construction & Maintenance of Khawzawl - Vankal Road | 1997.33 | Khawzawl Division | 13.12.18 | 13.12.19 | 88% | 1625.3 | - | 196.59 | 88% | 1821.89 | EOT granted upto 13.11.21 | Item rate contract
36 | Construction & Maintenance of Khawzawl - Hmuncheng Road | 1627.09 | Khawzawl Division | 1) 5.10.18 2)23.05.22 | 1) 5.10.19 2)30.09.22 | 92% | 1335.44 | 8% | 190.14 | 100% | 1525.58 | Work completed on 31.3.24 | Item rate contract
37 | Construction & Maintenance of Khawzawl - Hmuncheng Road | 1595.69 | Khawzawl Division | 05.10.18 | 05.10.19 | 75% | 959.03 | - | - | 75% | 959.03 | EOT granted upto 27.02.22 | Item rate contract
38 | Construction & Maintenance of Khawzawl - Hmuncheng Road | 636.68 | Khawzawl Division | 23.05.22 | 30.09.22 | 81% | 376.42 | 19% | 190.14 | 100% | 566.56 | Completed on 31.3.24 | Item rate contract
39 | Construction & Maintenance of Phuldungsei to Parvatui Road (0.00 Kmp - 17.30 Kmp) | 3340.55 | Mamit Division | 13.12.18 | 13.12.19 | 80% | 3272.5 | 16% | 540.15 | 96% | 3812.65 | Revised Target date of completion=31.03.24 Supplemen tary Estimate=36,95,51,610.56 | Item rate
40 | Construction & Maintenance of Tuipuibari to Andermanik Road (0.00 Kmp - 2.760 km) | 430.18 | Mamit Division | 17.9.18 | 17.9.19 | 98% | 315.99 | 1.11% | 112.44 | 99.11% | 428.43 | Revised Target date of completion= 31.03.24 | Item rate
41 | Construction & Maintenance of Andermanik to N.Belkhai Road (0.00 Kmp - 6.00 km) | 1016.7 | Mamit Division | 10.6.19 | 10.6.20 | 41% | 248.87 | 10.31% | 316.29 | 51.31% | 565.16 | Revised Target date of completion= 31.03.2024 | Item rate
42 | Thuampui - Lungchem Road (23.000 - 27.000 KMP) | 447.49 | Lunglei Road Division-I | 27.10.17 | 21.07.21 | 100% | 447.49 | - | - | 100% | 447.49 | Deviation already approved due to Some items are changed as mentioned in EE letter No.D-13024/5/2019(DV)/S&I/LD/PWD/Pt/10 Dt.18.02.21 Completed
43 | Thuampui - Lungchem Road (27.000 -32.000 KMP) | 395.75 | Lunglei Road Division-I | 27.10.17 | 24.09.21 | 100% | 378.64 | - | - | 100% | 378.64
44 | Thuampui - Lungchem Road (32.000 -37.000 KMP) | 372.33 | Lunglei Road Division-I | 27.11.17 | 30.09.22 | 100% | 372.31 | - |  | 100% | 372.31 | Completed
45 | Thuampui - Lungchem Road (37.000 - 40.900 KMP) | 307.24 | Lunglei Road Division-I | 27.10.17 | 13.08.21 | 100% | 336.09 | - | - | 100% | 336.09 | Completed
46 | Construction and Maintenance of Sachan to Sumasumi Road (0.00 - 24.09 Kmp) | 4005.26 | Lunglei Road Division-I | 10.06.19 | 31.08.22 | 65% | 2046.7 | 4% | 1394.16 | 69% | 3440.86 | Work in progress
47 | Construction and Maintenance of Sumasumi - Tuikawi Road (0.00 - 19.22 Kmp) | 2882.21 | Lunglei Road Division-I | 14.06.19 | 26.12.21 | 52% | 697.5 |  | 660.44 | 52% | 1357.94 | Work in progress
48 | Thuampui - Lungchem Road (0.000 - 4.000 KMP) | 85.83 | Lunglei Road Division-I | 01.04.21 | 31.03.22 | 100% | 85.83 | - |  | 100% | 85.83 | Completed
49 | Thuampui - Lungchem Road (4.000 - 7.000 KMP) | 268.21 | Lunglei Road Division-I | 27.10.17 | 14.07.21 | 100% | 268.19 | - | - | 100% | 268.19 | Completed
50 | Thuampui - Lungchem Road (7.000 - 10.000 KMP) | 306.59 | Lunglei Road Division-I | 27.10.17 | 15.08.21 | 100% | 306.56 | - | - | 100% | 306.56 | Completed
51 | Thuampui - Lungchem Road (10.000 - 14.000 KMP) | 387.7 | Lunglei Road Division-I | 27.10.17 | 04.07.21 | 100% | 387.68 | - | - | 100% | 387.68 | Completed
52 | Thuampui - Lungchem Road (14.000 - 18.000 KMP) | 394.46 | Lunglei Road Division-I | 13.11.17 | 31.12.22 | 100% | 385.57 | - | 36.46 | 100% | 422.03 | Completed
53 | Thuampui - Lungchem Road (18.000 - 21.000 KMP) | 418.83 | Lunglei Road Division-I | 27.10.17 | 07.11.21 | 100% | 418.88 | - | 38.87 | 100% | 457.75 | Some items are changes due to Deviation approval vide EE letter no.D-13024/5/2019(DV)/S&I/LDIPWD/28 dt.9.03.22 completed
54 | Thuampui - Lungchem Road (21.000 - 23.000 KMP) | 370.75 | Lunglei Road Division-I | 13.11.17 | 31.07.22 | 100% | 370.74 | - | 30 | 100% | 400.74 | Completed
55 | Const. & Maint.of Bunghmun to Sachan Road (0.00-9.07Kmp) | 1325.06 | Lunglei Road Division-I | 13.12.18 | 31.07.22 | 61% | 654.39 | 9% | 327.24 | 70% | 981.63
56 | Const. & Maint.of Cherhlun to Ngharchhip Road (0.00-7.64 Kmp) | 554.08 | Lunglei Road Division-II | 13.12.18 | Completed on 31.3.23 | 100% | 529.74 | - |  | 100% | 529.74 | Phy. completed | Open Tender
57 | Const. & Maint.of Khawhri to Chawngtui Road (0.00-17.81 Kmp) | 1280.59 | Lunglei Road Division-II | 8.10.18 | 31.3.24 | 82.9% | 1093.85 | 17.1% | 186.31 | 100% | 1280.16 | Some items are changes due to approval Deviation approval statement (vide No.B.15028/240/Ph-x/18/2023/PMGSY/EC/PWD/7 Date 5.January, 2024) | Open Tender
58 | Const. & Maint.of Luangmual to Vaisam Road (0.00-26.700 Kmp) | 4711.5 | Lunglei Road Division-II | 10.06.19 | 31.3.24 | 82.9% | 3268.52 | 3.41% | 775.59 | 86.31% | 4044.11 | 1) EOT Granted upto 31.3.2024 2) Deviation Sanction No.B-15028/240/2023/Ph-II/28/EC/PWD/PMGSY/8 of 9.10.23 | Open Tender
59 | Const. & Maint.of Haulawng to Dawn Road (0.00-6.00 Kmp) | 766.65 | Lunglei Road Division-II | 10.06.20 | 31.3.24 | 95% | 674.56 | 5% | 91.8 | 100% | 766.36 | Work is in progress | Open Tender
60 | Const. & Maint.of Haulawng to Dawn Road (6.00-12.000 Kmp) | 632.64 | Lunglei Road Division-II | 01.01.21 | 31.3.24 | 85% | 358.53 | 15% | 282.11 | 100% | 640.64 | Work is in progress | Open Tender
61 | Const. & Maint.of Haulawng to Dawn Road (12.00-18.000 Kmp) | 730.72 | Lunglei Road Division-II | 01.01.21 | 31.3.24 | 80% | 566.87 | 20% | 163.71 | 100% | 730.58 | Work in progress | Open Tender
62 | Const. & Maint.of Haulawng to Dawn Road (18.00-24.000 Kmp) | 850.56 | Lunglei Road Division-II | 01.01.21 | 31.3.24 | 87% | 385.71 | 13% | 456 | 100% | 841.71 | Work is in progress | Open Tender
63 | Const. & Maint.of Haulawng to Dawn Road (24.00-30.500 Kmp) | 840.58 | Lunglei Road Division-II | 01.01.21 | 31.3.24 | 93% | 492.06 | 7% | 391.16 | 100% | 883.22 | Work is in progress | Open Tender
64 | Construction of Nghalimlui to Bolisora (0.00-3.00)Kmp (Sh: FC, Culvert, R.Wall) | 158.33 | Lawngtlai Division | 27.10.17 | 30.04.20 | 100% | 158.33 | - | - | 100% | 158.33 | Completed | NIT
65 | Construction of Nghalimlui to Bolisora (3.00-5.00)Kmp (Sh: FC, Culvert, R.Wall) | 249.17 | Lawngtlai Division | 27.10.17 | 23.03.20 | 100% | 247.3 | - | - | 100% | 247.3 | Completed | NIT
66 | Construction of Nghalimlui to Bolisora (5.00-8.00)Kmp (Sh: FC, Culvert, R.Wall) | 206.24 | Lawngtlai Division | 27.10.17 | 10.08.20 | 100% | 206.24 | - | - | 100% | 206.24 | Completed | NIT
67 | Construction of Nghalimlui to Bolisora (8.00-12.65)Kmp (Sh: FC, Culvert, R.Wall) | 266.55 | Lawngtlai Division | 27.10.17 | 16.08.20 | 100% | 246.66 | - | - | 100% | 246.66 | Completed | NIT
68 | Construction of Karlui to Damlui (0.00-2.00)Kmp (Sh: FC, Culvert, R.Wall) | 207.84 | Lawngtlai Division | 27.10.17 | 28.2.20 | 100% | 207.66 | - | - | 100% | 207.66 | Completed | NIT
69 | Construction of Karlui to Damlui (2.00-6.00)Kmp (Sh: FC, Culvert, R.Wall) | 227.53 | Lawngtlai Division | 27.10.17 | 30.10.19 | 100% | 216.35 | - | - | 100% | 216.35 | Completed | NIT
70 | Construction of Karlui to Damlui (6.00-8.800)Kmp (Sh: FC, Culvert, R.Wall) | 147.71 | Lawngtlai Division | 13.11.17 | 25.10.19 | 100% | 147.69 | - | - | 100% | 147.69 | Completed | NIT
71 | Construction of Bolisora to Chamdurtlang (0.00 - 2.00) Kmp (Sh: FC, Culvert. R.Wall) | 155.5 | Lawngtlai Division | 27.10.17 | 20.05.20 | 100% | 155.49 | - | - | 100% | 155.49 | Completed | NIT
72 | Construction of Bolisora to Chamdurtlang(2.00-5.00)Kmp (Sh: FC, Culvert, R.Wall) | 229.32 | Lawngtlai Division | 27.10.17 | 16.03.20 | 100% | 229.32 | - | - | 100% | 229.32 | Completed | NIT
73 | Construction of Bolisora to Chamdurtlang(5.00-9.00)Kmp (Sh: FC, Culvert, R.Wall) | 359.96 | Lawngtlai Division | 01.04.19 | 29.09.21 | 100% | 359.95 | - | - | 100% | 359.95 | Completed | NIT
74 | Construction of Bolisora to Chamdurtlang(9.00-11.650)Kmp (Sh: FC, Culvert, R.Wall) | 251.92 | Lawngtlai Division | 27.10.17 | 16.03.20 | 100% | 251.9 | - | - | 100% | 251.9 | Completed | NIT
75 | Construction of Ajasora to Longpuighat (0.00-10.900)Kmp (Sh: Const.of road using Flexible Pavement Technology) | 934 | Lawngtlai Division | 13.11.17 | 19.12.21 | 100% | 857.32 | - | - | 100% | 857.32 | Ongoing | NIT
76 | Construction of Jognasury - Karlui Road (0.000-12.100)Kmp (Sh: Formation Cutting, Culvert & R.Walls & Const.of of Road Using Flexible Pavement) | 888.27 | Lawngtlai Division | 13.12.18 | 30.09.22 | 100% | 760.65 |  | - | 100% | 760.65 | Completed | NIT
77 | Construction of Maniababsora-I to Maniababsora-II Road (0.000-1.520)Kmp (Sh: FC, Culvert & R.Wall & Const.of road using Panelled Concrete Technology) | 212.32 | Lawngtlai Division | 27.12.18 | 22.11.20 | 100% | 212.32 | - | - | 100% | 212.32 | Completed | NIT
78 | Construction of Boroituli to Jaruldubasora Road (0.000-2.100)Kmp (Sh: FC, Culvert & R.Wall & Const.of road using Panelled Concrete Technology) | 257.02 | Lawngtlai Division | 17.09.18 | 10.02.22 | 100% | 257 | - | - | 100% | 257 | Completed | NIT
79 | Construction of Boroituli to Jaruldubasora Road (2.000-3.700)Kmp (Sh: FC, Culvert & R.Wall & Const.of road using Panelled Concrete Technology) | 269.85 | Lawngtlai Division | 28.09.18 | 30.09.22 | 100% | 268.54 | - | - | 100% | 268.54 | Completed | NIT
80 | Construction of Vaseitlang to Lokhisury Road(0.00-9.560)Kmp (Sh: FC, Culvert, R.Wall & Const.of road using Panelled Concrete Technology) | 1366.7 | Lawngtlai Division | 28.09.18 | 30.09.22 | 70.91% | 822.15 | 7.71% | - | 78.62% | 822.15 | Ongoing | NIT
81 | Construction of Vathuampui to Tuisentlang Road(0.000-9.600)Kmp (Sh: FC, Culvert, R.Wall & Const.of Road Using panelled Concrete) | 910.99 | Lawngtlai Division | 03.01.18 | 30.09.22 | 76% | 910.99 | 5% | - | 81% | 910.99 | Ongoing | NIT
82 | Construction of Vathuampui to Chamdur P-I Road(0.000-1.720)Kmp (Sh: FC, Culvert, R.Wall & Const.of Road Using panelled Concrete) | 263.08 | Lawngtlai Division | 15.10.18 | 30.09.22 | 100% | 261.11 | - | - | 100% | 261.11 | Completed | NIT
83 | Construction of Vathuampui to Chamdurtlang (0.000-1.720)Kmp (Sh: FC, Culvert, R.Wall & Const.of Road Using panelled Concrete) | 274.17 | Lawngtlai Division | 13.12.18 | 30.09.22 | 71.15% | 180.75 |  | 25.7 | 71.15% | 206.45 | Ongoing | NIT
84 | Construction of Vathuampui to Chamdurtlang (2.000-3.800)Kmp (Sh: FC, Culvert, R.Wall & Const.of Road Using panelled Concrete) | 360.89 | Lawngtlai Division | 22.09.18 | 30.09.22 | 100% | 356.27 | - |  | 100% | 356.27 | Completed | NIT
85 | Construction of Chamdurtlang to Mualtlang Road(0.000-7.970)Kmp (Sh: FC, Culvert, R.Wall & Const.of Road Using panelled Concrete) | 1152.2 | Lawngtlai Division | 13.12.18 | 30.09.22 | 100% | 1089.09 | - | - | 100% | 1089.1 | Completed | NIT
86 | Construction of Parva II to Zochachhuah Road(0.000-29.720)Kmp (Sh: FC, Culvert, R.Wall & Const.of Road Using panelled Concrete) | 5432.38 | Lawngtlai Division | 05.04.19 | 30.09.23 | 100% | 4745.79 | - |  | 100% | 4745.79 | Ongoing | NIT
87 | Construction of Parva II to Bondukbanga Road(0.000-2.000)Kmp (Sh: FC, Culvert, R.Wall & Const.of Road Using Flexible Pavement) | 269.72 | Lawngtlai Division | 28.09.18 | 12.01.22 | 100% | 269.14 | - | - | 100% | 269.14 | Completed | NIT
88 | Construction of Parva II to Bondukbanga Road(2.000-4.120)Kmp (Sh: FC, Culvert, R.Wall & Const.of Road Using Flexible Pavement) | 294.1 | Lawngtlai Division | 13.12.18 | 31.12.22 | 100% | 259.1 |  | 22.72 | 100% | 281.82 | Ongoing | NIT
89 | Construction &Maintenance of Parva-II - Kamtuli Road (0.000-25.550)Kmp (Sh: FC, Culvert, R.Wall & Const.of Road Using panelled Concrete) | 4139.88 | Lawngtlai Division | 17.06.19 | 30.09.22 | 89.83% | 2148.95 | 2.44% |  | 92.27% | 2148.95 | Ongoing | NIT
90 | Construction & Maintenance of Vaseitlang to Maniababsora Road (0.000-13.500)Kmp (Sh: FC, Culvert, R.Wall & Const.of Road Using panelled Concrete) | 2361.15 | Lawngtlai Division | 14.06.19 | 30.04.22 | 100% | 2358.27 | - | - | 100% | 2358.27 | Completed | NIT
91 | Construction & Maintenance of Sedailui to Tuikhurlui Road (0.000-1.720)Kmp (Sh: FC, Culvert, R.Wall & Const.of Road Using panelled Concrete Techonology) | 204.33 | Lawngtlai Division | 17.06.19 | 08.05.22 | 92.06% | 159.96 | - | - | 92.06% | 159.96 | Ongoing | NIT
92 | Construction &Maintenance of M.Kawnpui to Vathuampui Road (0.000-20.000)Kmp (Sh: FC, Culvert, R.Wall & Const.of Road Using panelled Concrete Technology) | 1976.47 | Lawngtlai Division | 14.06.19 | 30.09.22 | 78.29% | 880.39 | 3.1% | 241.23 | 81.39% | 1121.62 | Ongoing | NIT
93 | Construction &Maintenance of Sumsului Road to Jognasury (0.000-15.44)Kmp (Sh: Const.of Road Using panelled Concrete Technology) | 1278.38 | Lawngtlai Division | 14.06.19 | 30.09.22 | 85.26% | 1065.69 | 4.8% |  | 90.06% | 1065.69 | Ongoing | NIT
94 | Construction &Maintenance of Chawngte 'P' to Sumsului Road (0.000-4.570)Kmp (Sh: FC, Culvert, R.Wall & Const.of Road Using panelled Concrete Technology) | 313.29 | Lawngtlai Division | 01.07.19 | 31.03.22 | 100% | 302.97 |  |  | 100% | 302.97 | Completed | NIT
95 | Construction of Niawhtlang - Chakhang Road Package No.MZ0761(0.000-23.260Kmp) | 870.43 | Siaha Division | 14.10.23 | 14.03.24 | 9.55% |  | 37.6% | 268.12 | 47.15% | 268.12 | 1. Work in progress 2. Analysis for 4 km | Item rate contract
96 | Construction of Tawngkolong - Lawngmasu Road (0.00 - 22.700) Kmp | 1289.738 | Siaha Division | 14.02.22 | 30.09.22 | 67.48% | 743.9 |  | 576.24 | 67.48% | 1320.14 | Works completed. Approval of deviations for additional items vide letter No.B15028/240/2023/P-X/23/EC/PWD/PMGSY/7 dt.9.1.2024 | Item rate contract
97 | Construction of Rawlbuk-Lungtian Road (0.000-14.000 Kmp) | 681.45 | Siaha Division | 8.05.20 | 30.09.22 | 100% | 629.91 |  | 4.41 | 100% | 634.32 | Work completed | Item rate contract
98 | Construction of Niawhtlang-Chakhang Road Package No.MZ 0771(0.000-20.790Kmp) | 879.2 | Siaha Division | 15.10.23 | 15.03.24 | 0.87% |  | 34.93% | 255.28 | 35.8% | 255.28 | Show Cause Notice has been given to Contractor due to delaying of work | Item rate contract
99 | Construction of Phura - Lungpuk Road Group 'A' (0.000 - 4.000) Kmp | 159.98 | Siaha Division | 27.11.17 | Works phy. completed on 20.03.23 | 100% | 81.87 |  | 43.27 | 100% | 125.14 | Work completed | Item rate contract
100 | Construction of Phura - Vahai Road (0.000 - 17.000) Kmp | 1563.92 | Siaha Division | 13.11.17 | 13.11.19 | 100% | 1409.46 |  |  | 100% | 1409.46 | Pending legal case/Initiate for forclosure | Item rate contract
101 | Construction and Maintenance of Tawngkolong-Lawngmasu road (0.00-28.940) Km | 122.016 | Siaha Division | 13.10.23 | 13.03.24 | 97% | 95.55 | 3% | 24.09 | 100% | 119.64 | Works completed | Item rate contract
102 | Const.& Maintenance of Mualcheng-N.Vanlaiphai Road Group 'A' (0.000-8.000 Kmp) | 515.65 | Serchhip Division | 31.12.20 | 31.12.22 | 100% | 303.31 | - | - | 100% | 303.13 | Physically completed | Item rate contract
103 | Const.& Maintenance of Mualcheng-N.Vanlaiphai Road Group 'B' (8.000-16.000 Kmp) | 606.37 | Serchhip Division | 31.12.20 | 31.12.22 | 100% | 393.51 | - | - | 100% | 393.51 | Physically completed | Item rate contract
104 | Construction of Tuithumhnar to Lunghauka (0.00 - 5.00) Kmp (Sh: FC, Culvert, R.Wall) | 189.03 | Multi Modal Project Division | 27.10.17 | 31.07.19 | 100% | 189.03 | - | - | 100% | 189.03 | Completed on 05/07/2019
105 | Construction of Tuithumhnar to Lunghauka (5.00 - 7.00) Kmp (Sh: FC, Culvert, R.Wall) | 196.98 | Multi Modal Project Division | 27.10.17 | 31.03.21 | 100% | 193.28 | - | - | 100% | 193.28 | Completed on 30/03/2021
106 | Construction of Tuithumhnar to Lunghauka (7.00 - 10.00) Kmp (Sh: FC, Culvert, R.Wall) | 247.04 | Multi Modal Project Division | 27.10.17 | 16.07.20 | 100% | 247.04 | - | - | 100% | 247.04 | Completed on 20/07/2020
107 | Construction of Tuithumhnar to Lunghauka (10.00 - 13.00) Kmp (Sh: FC, Culvert, R.Wall) | 184.6 | Multi Modal Project Division | 27.10.17 | 29.06.20 | 100% | 184.6 | - | - | 100% | 184.6 | Completed on 29/06/2020
108 | Construction of Tuithumhnar to Lunghauka (13.00 - 15.480) Kmp (Sh: FC, Culvert, R.Wall) | 198.08 | Multi Modal Project Division | 27.10.17 | 16.07.20 | 100% | 198.08 | - | - | 100% | 198.08 | Completed on 26/06/2020
109 | Construction & Maintenance of Ngenpuitlng to Darnamtlang (0.00 - 4.00) Kmp (Sh: FC, Culvert, R.Wall) | 233.08 | Multi Modal Project Division | 27.10.17 | 31.01.20 | 100% | 193.78 | - | - | 100% | 193.78 | Physically completed on 01/05/2020
110 | Construction & Maintenance of Ngenpuitlng to Darnamtlang (4.00 - 6.20) Kmp (Sh: FC, Culvert, R.Wall) | 161.44 | Multi Modal Project Division | 27.10.17 | 31.08.21 | 100% | 224.53 | - | - | 100% | 224.53 | Completed on 30/08/2021
111 | Construction & Maintenance of Tuithumhnar to Hmawngbu (0.00 - 6.720) Kmp (Sh: Construction of road using Grove Concrete Pavement) | 442.51 | Multi Modal Project Division | 12.11.17 | 1.10.21 | 100% | 441.76 | - |  | 100% | 441.76 | Completed on 16/06/2021
112 | Construction of Sabualtlang to Hmawngbuchhuah Road (0.00 - 1.760) Kmp (Sh:Formation Cutting, Culvert & Retaining Walls & Construction of Road Using Flexible Pavement) | 244.22 | Multi Modal Project Division | 17.12.18 | 24.10.21 | 100% | 244.22 | - |  | 100% | 244.22 | Completed on 23/10/2021
113 | Construction & Maintenance of Nalkawn to Rulkual Road (0.000-16.000) Kmp Group A (Sh: Const.of Road using Cold Mix Technology | 1078.79 | Multi Modal Project Division | 04.01.21 | 04.01.23 | 100% | 1194.51 | - | - | 100% | 1194.51 | Completed on 29.9.22
114 | Construction & Maintenance of Nalkawn to Rulkual Road (16.000-32.000) Kmp Group B (Sh: Const.of Road using Cold Mix Technology | 1315.37 | Multi Modal Project Division | 12.12.23 | 30.3.24 | 20% | 476.63 | 10% | 448.97 | 30% | 925.6 | The work was retendered and newly awarded to the new contractor. the work is progress
115 | Construction & Maintenance of Rawmibawk to Phalrang Road (0.000-10.200) Kmp (Sh: Const.of Road usinggroove concrete Technology | 759.92 | Multi Modal Project Division | 13.12.18 | 30.09.22 | 100% | 758 | - |  | 100% | 758 | Completed on 29.9.22
116 | Construction & Maintenance of Saiha to Rawmibawk Road (0.000-22.30) Kmp (Sh: Const.of Road using groove concrete Technology | 1941.19 | Multi Modal Project Division | 17.06.19 | 30.09.22 | 100% | 1938.8 |  |  | 100% | 1938.8 | Phy. Completed on 29.03.23

## SEDP
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding: SEDP | [8 empty] | Month : March 2024
Sl. no | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Const. of Approach Road to Aizawl College at Mualpui | 415 | Aizawl Road South Division | 26.07.21 | 26.04.22 | 73% | 300 | - | - | 73% | 300 | Work in progress | Item Rate Contract
2 | Re-Construction of Concrete Pavement on Approach Road to Mission Vengthlang Cemetry, L=150M | 8.51 | Aizawl Road South Division | [8 empty] | Work connot be started due to land conflict with land owner
3 | Construction of High Court Parking Building at MINECO | 1960 | Project Division-I | 2.7.20 | 29.8.24 | 76% | 1082.48 | 4% | 5.09 | 80% | 1087.57 |  | EPC
4 | Construction of Govt.Staff Quarter (Block-A) at DIET Complex | 439.2 | Project Division-I | 23.4.22 | 22.4.24 | 100% | 424.33 |  | 14.2 | 100% | 438.53 | Works completed | EPC
5 | Construction of Rest House & Chowkider Quarter at PWD Complex Bilkhawthlir | 412.39 | Project Division-II | 15.12.20 | (O)15.6.22 (R)28.02.23 | 100% | 406.57 | - | 5.82 | 100% | 412.39 | Work physically Completed | Item rate
6 | Const.of MBSE New Building and renovation of existing main Building | 1000 | Project Division-III | 22.2.21 | 6.7.24 | 86% | 568.57 | 2% |  | 88% | 568.57 | Work in progress | PWD Form-8
7 | Improvement of Khanpui - Tualbung Road Phase-II | 2935.99 | Saitual Division | 25.03.18 | 15.6.22 | 83.61% | 2327.33 |  |  | 83.61% | 2327.33
8 | Strenthening of Saitual - Phullen Road (28.300Km)(Tuivawl-Phullen) (28.700-57.000) | 1259.71 | Saitual Division | 18.12.19 | 18.04.21 | 100% | 800.01 |  |  | 100% | 800.01 | Phy. Completed
9 | Curve Improvement on ATL Road at Chainage 20.100 Kmp | 10 | Hmuifang Division | 18.02.23 | 31.03.23 | 100% | 10 |  |  | 100% | 10 | Completed
10 | Resurfacing of PWD Staff Lodge Approach Road at Aibawk | 10 | Hmuifang Division | 18.02.23 | 31.03.23 | 100% | 10 |  |  | 100% | 10 | Completed
11 | Resurfacing of Aizawl-Thenzawl-Lunglei Road (30.00 Kmp - 51.00 Kmp) | 1271.17 | Hmuifang Division | 18.02.23 | 31.03.23 | 100% | 660.11 |  | 259.23 | 100% | 919.34 | Completed
12 | Bad patch repair of Aizawl-Thenzawl-Lunglei Road (83.00 Kmp-100.00 Kmp) | 50 | Hmuifang Division | 18.12.23 | 31.03.23 | 100% | 50 |  |  | 100% | 50 | Completed
13 | Re-Construction of Hume pipe wing wall culvert at Ch.20.650 Kmp on Damdiai - Sialsuk Road (Location:20.650 Kmp) | 4.45 | Hmuifang Division | 18.12.23 | 31.03.23 | 100% | 4.45 |  |  | 100% | 4.45 | Completed
14 | Re-Construction of Hume pipe wing wall culvert at Ch.5.350 Kmp on Lungsei Road (Location:5.350 Kmp) | 6.5 | Hmuifang Division | 18.12.23 | 31.03.23 | 100% | 6.5 |  |  | 100% | 6.5 | Completed
15 | Patch Repair of Main Road at Thenzawl | 25 | Hmuifang Division | 18.02.23 | 31.03.23 | 100% | 25 |  |  | 100% | 25 | Completed
16 | Patch repair of Dinthar Veng Internal road at Thenzawl | 7.5 | Hmuifang Division | 18.02.23 | 31.03.23 | 100% | 7.5 |  |  | 100% | 7.5 | Completed
17 | Patch repair of Horticulture College approach road at Thenzawl | 10 | Hmuifang Division | 18.02.23 | 31.03.23 | 100% | 10 |  |  | 100% | 10 | Completed
18 | Patch repair of Rawpuichhip-Buarpui Road 81.000-88.000 Kmp (Section : S.Khawlek to New Khawlek) | 30 | Hmuifang Division | 18.02.23 | 31.03.23 | 100% | 30 |  |  | 100% | 30 | Completed
19 | Curve Improvement on ATL Road at Chainage 17.700 Kmp | 10 | Hmuifang Division | 18.02.23 | 31.03.23 | 100% | 10 |  |  | 100% | 10 | Completed
20 | Resurfacing of Doctor's Quarter Approach Road at Sialsuk. (Section: 0.00 Kmp to 0.090 Kmp) | 9 | Hmuifang Division | 18.02.23 | 31.03.23 | 100% | 9 |  |  | 100% | 9 | Completed
21 | Patch repair and resurfacing of Hualngohmun Internal Roads | 20 | Hmuifang Division | 18.02.23 | 31.03.23 | 100% | 20 |  |  | 100% | 20 | Completed
22 | Patch repair of Kelsih Internal Roads | 10 | Hmuifang Division | 18.02.23 | 31.03.23 | 100% | 10 |  |  | 100% | 10 | Completed
23 | Patch repair of Approach Road to Tachhip | 10 | Hmuifang Division | 18.02.23 | 31.03.23 | 100% | 10 |  |  | 100% | 10 | Completed
24 | Patch repair of Muallungthu to Khumtung Road | 20 | Hmuifang Division | 18.02.23 | 31.03.23 | 100% | 20 |  |  | 100% | 20 | Completed
25 | Patch repair of Aizawl-Thenzawl-Lunglei Road (63.00-71.00 Kmp) | 35 | Hmuifang Division | 18.02.23 | 31.03.23 | 100% | 35 |  |  | 100% | 35 | Completed
26 | Curve Improvement at ATL Road at Chainage 17.700 Kmp (Additional) | 6 | Hmuifang Division | 18.02.23 | 31.03.24 | 100% | 6 |  |  | 100% | 6 | Completed

## SEDP 4 (hidden)
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding: SEDP | [8 empty] | Month : May 2022
Sl. no | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the Month |  | Overall cumulative achievement |  | Remarks
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
25 | Widening of Road infront of CE, PWD Building at Tuikhuahtlang | 46.5 | Aizawl Road South Division |  |  | 100% | 46.5
26 | Const. of Approach Road to Aizawl College at Mualpui | 415 | Aizawl Road South Division |  |  | 35% | 120.12
27 | Const. of Approach Road to T.Romana College from ITI to Mualpui Road | 464.9 | Aizawl Road South Division |  |  | 49% | 171.33
28 | Wideing of Curve near Zokhuma's House on Bethlehem Vengthlang to College Road | 38.5 | Aizawl Road South Division |  |  | 100% | 38.5
29 | Const.of Approach Road to Zopar Vaipuanpho | 50 |  |  |  | 100% | 50
30 | Improvement at 0.50 Kmp on Hridaikawn to Power Sub Station at Tlangnuam | 12.3 | Aizawl Road South Division |  |  | 100% | 12.3
31 | Concrete pavement from Kohhran Thianghlim Biak In to PHE Pump House road within Maubawk | 30.5 | Aizawl Road South Division |  |  | 100% | 30.5
32 | Const.of Composite Retaining Wall at Kawilun Republic Veng | 7 | Aizawl Road South Division |  |  | 100% | 7
33 | Re-Construcrion of Retaining Wall near T.Lalhmuntiama's house on Nursery to Mission Veng Road via Kawltheihuan | 2.19 | Aizawl Road South Division |  |  | 100% | 2.19
34 | Const.of Bridge on Chhinga Vengthar to Tuithiang Road | 586.36 | Aizawl Road South Division |  |  | 59% | 60
35 | Widening of Approach road with rigid pavement from Thlanmual to Dam veng at Tlangnuam | 55 | Aizawl Road South Division |  |  | 100% | -

## CSS
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding: CSS | [8 empty] | Month : March 2024
Sl. no | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Polytechnic at Lawngtlai (Const.of Administrative cum Academic Block) | 800 | Lunglei Building Project Division | 18.3.13 | 14.10.15 | 100% | 624.62 | - | - | 100% | 624.62 | Civil Work Completed & I/E Works not yet executed | Restricted
2 | Construction of Judicial Quarter at Lawngtlai Grade-I Qtr. | 110.58 | Lunglei Building Project Division | 8.6.20 | 7.12.21 | 100% | 100.64 |  |  | 100% | 100.64 | Civil Works completed I/E not yet done | Restricted Tender
3 | Construction of Judicial Quarter at Lawngtlai Type-I & II Qtr. | 138.67 | Lunglei Building Project Division | 22.6.20 | 30.08.23 (Revised) | 100% | 36.25 |  |  | 100% | 36.25 | -do- | Restricted Tender
4 | Const.of Administrative cum Academic Block for Polytechnic Thingsen Saiha | 501.08 | Lunglei Building Project Division | 15.03.16 | 11.7.17 | 60% | 118.02 | - | 49.62 | 60% | 167.64 | The contractor has stopped work due to non release of fund from Central Government | Restricted Tender
5 | Const.of Hostel building for Polytechnic at Thingsen saiha | 191.83 | Lunglei Building Project Division | 15.3.16 | 11.04.17 | 80% | 80.41 | - | 30 | 80% | 110.41 | The contractor has stopped work due to non release of fund from Central Government | Restricted Tender
6 | Construction of Staff Qtr Type I, II & III for Polytechnic at Thingsen Saiha | 77.1 | Lunglei Building Project Division | 06.10.15 | 20.4.17 | 100% | 67.14 |  |  | 100% | 67.14 | The contractor has stopped work due to non release of fund from Central Government | Restricted Tender
7 | Const.of Type-IV Qtr for Polytechnic at Thingsen Saiha | 29.99 | Lunglei Building Project Division | 15.03.16 | 11.01.17 | 76.5% | 24.79 | - | - | 76.5% | 24.79 | The contractor has stopped work due to non release of fund from Central Government | Restricted
8 | Construction of District Court Building at Saiha. | 1803.39 | Lunglei Building Project Division | 10.9.18 | 31.10.23 (Revised) | 100% | 1803.395 |  |  | 100% | 1803.395 | Works completed on dt.28.4.23 and handover paper submitted | Restricted Tender
9 | Construction of fast truck Court at Kolasib | 1799.85 | Project Division II | 20.09.22 | 20.09.24 | 50% | 237.47 | 5% | 281.89 | 55% | 519.36 | Work in progress | Item Rate
10 | Const.of Tourist Logde at Champhai | 328.73 | Project Division-III | 09.12.10 | 30.11.20 | 100% | 300 | - | - | 100% | 300 | Taken over by the Deptt.on Dt.3.8.2021 LOC amounting to Rs.30.00 lakh submitted for clearing liability.Hence, release of LOC awaited for financial closure.
11 | Const.of Polytechnic at Chhiahtlang i) Approach Road | 800 | Project Division-III | 3.3.16 | 2.8.16 | 100% | 103.67 | - | - | 100% | 103.67 | Revised estimate amounting to Rs.1230.00 lakh submitted as per instruction of the client department in February 2024
ii) Administrative & Academic Block iii) Hostel Block iv) Staff Quarters
12 | Construction of General Nursing Midwifery Hostel at Champhai | 250 | Project Division-III | 13.07.22 | 13.07.24 | 89% | 150.51 | 1% |  | 90% | 150.51 | Work in progress | PWD Form-8
13 | Construction of Hostel for S.T Girls at Champhai | 462.75 | Project Division-III | 18.9.23 | 28.9.25 | 22% | 9.77 | 8% | 57.8 | 30% | 67.57 | Work in progress | PWD Form-8
14 | 10-Bedded Intergrated AYUSH Hospital at Keifang, Saitual District | 750 | Project Division-III | 13.10.23 | 13.10.25 | 0.5% |  |  |  | 0.5% |  | Site clearance and approach road FC completed. New architecture design of main building submitted to Health Deptt for approval | PWD Form-8
15 | Renovation of Mizram Secretariat Building at MINECO | 200 | Aizawl Building Division | 13.11.23 | 31.03.24 | 50% | 77.77 | 20% |  | 70% | 77.77 |  | Departmental

## MoRTH
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : NH(O) - MoRTH | [9 empty] | Month : March 2024
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummutive Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Steel Arch (Semi Through) Bridge with concrete Deck 90m Arch Span over River Tlawng at Km 5.200 on NH-44A In the State of Mizoram of EPC Mode (NHO) | 4244 | NHD-I | 30.01.21 | 26.3.24 | 78% | 2579.88 | 0.5% | 226.06 | 78.5% | 2805.94 | On going | EPC Mode
2 | Periodical Renewal between Ch.183/00 Kmp to Ch.190/00 Kmp on NH-54A during 2022-23 in the state of Mizoram (Length=7.00Km) | 563.17 | NHD-I | 24.09.24 | 24.09.24 | 60% |  | 25.7% | 400.08 | 85.7% | 400.08 | On going | EPC Mode
3 | Periodical Renewal between Ch.183/00 Kmp to Ch.190/00 Kmp on NH-54A during 2022-23 in the state of Mizoram (Length=7.00Km) | 443.5 | NHD-I | 19.08.23 | 19.04.24 |  |  | 90% | 421.05 | 90% | 421.05 | On going | EPC Mode
4 | Ordinary Repair (DPP) for short term maintenance from Km 0.00 to Km 42.80 and from Km 60.30 to km 130.00 on NH-150 in the state of Mizoram | 418 | NHD-II | 05.11.21 | 02.02.22 | 100% | 327.67 | - | - | 100% | 327.67 |  | Item Rate
5 | Construction of 2 laning with paved shoulder flexible pavement from Km 42.80 to Km 60.30 of NH-150 road during 2016-17 within Mizoram State under NH(O) Scheme. (Job No. & Dtae of Sac Original/Revised : 150/MZ/2016-17/107) | 20594.82 | NHD-II | 29.11.17 | 22.05.21 | 100% | 13681.44 | - | - | 100% | 13681.44 | Phy. Completed | EPC Mode
6 | Reconstruction of single pavement from Km 130.00 to Km 140.00 on NH-150 in the State of Mizoram on EPC Mode (Job No.150/MZ/2019-20.119) | 3440.95 | NHD-II | 23.11.20 | 26.05.23 | 100% | 2441.16 | - | - | 100% | 2441.16 | Work under Defect Liability period | EPC Mode
7 | Consultancy Services for Project Management including prparation of Feasibility Study/Detailed {roject report fro laning with Paved Shoulders of stretches from Km 0/00 to Km 42/80 and from Km 60/00 to Km 140/00 on NH-150 NH (O) Package No. DPR/MZ/NER/2015/13 | 166.04 | NHD-II | 24.06.17 | 20.05.18 | 70% | 16.6 |  | - | 70% | 16.6 |  | MoRTH
8 | Periodical Renewal of NH-54 in the state of Mizoram under ARP for the year 2019-2020 between Km 118/00-133/00 Km (15.00Km) | 1477 | NHD-III | 20.04.21 | 20.04.22 1st Extension of Time = 96 day as (19.4.22=14.6.22) | 100% | 1178 |  |  | 100% | 1178 | Completed | EPC
9 | Strengthening of Km 10.00 to Km 33.00 (Length 23.00 Km) on NH-306A including Strengthening & Construction of Retaining Walls and Culverts and Strenthening of 3 Nos.of Bailey Bridges in the State of Mizoram | 6523 | NHD-III | 07.02.22 | 07.08.23 | 100% | 4167 |  | 11.05 | 100% | 4178.05 | Completed | EPC
10 | Strengthening/Construction/Widening to 2-lane from km 89/00 to km 105/00 of NH-154 (New NH-6) under NH Division III in the state of Mizoram for the year 2022-23 (Length=16Km) | 8681 | NHD-III | 04.09.23 | 04.03.25 | 5.64% | 136 | 19.67% | 864.14 | 25.31% | 1000.14 | Work in progress | EPC

## Article 275
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : Article 275(1) of the Constitution | [9 empty] | Month : March 2024
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummutive Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Tribal Hostel at Suangpuilawn, Mizoram | 320 | Project Division-IV | 12.08.23 | 12.08.25 | 11.52% |  | 2.24% | 32.02 | 13.76% | 32.02 | Work in progress. | Item Rate
2 | Construction of Multipurpose Community Hall at Darlawn, Mizoram | 720 | Project Division-IV | 12.08.23 | 12.08.25 | 11.26% |  | 4.82% | 72.6 | 16.08% | 72.6 | Work in progress. | Item Rate

## ECRP-II
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : ECRP-II (Emergency Covid Response Package-II) | [9 empty] | Month : March 2024
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummutive Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of 50 Bedded critical care block at Champhai District Hospital Mizoram | 1346.4 | Project Division-III | 4.8.23 | 4.2.26 | 18% | 67.46 | 2% |  | 20% | 67.46 | Work in progress | PWD Form-8

## MAP
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding: Maintenance Action Plan | [8 empty] | Month : March 2024
Sl. no | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the Month |  | Overall cumulative achievement |  | Remarks | Mode of Contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | SUB DIVISION-I Resurfacing of Sihpui to Ramhlun Vengthar Bus Turining Point at Ch: 1.357-2.172 Km | 30 | Aizawl Road North Division | 12.10.23 | 30.10.23 | 100% | 30 |  |  | 100% | 30 | Completed | Dept
2 | Resurfacing of Armed Veng South to Bethlehem Vengthlang Road at Ch:0.000-0.677 Km | 11.8 | Aizawl Road North Division |  |  | 100% | 11.8 |  |  | 100% | 11.8 | Completed | Dept
3 | Resurfacing of Ramhlun Sports Complex Road at Ch.0.000-0.326Km | 15.8 | Aizawl Road North Division |  |  | 100% | 15.8 |  |  | 100% | 15.8 | Completed | Dept
4 | SUB DIVISION-II Re-surfacing of DC Workshop to NH-54 via Chaltlang Lily Veng | 20 | Aizawl Road North Division | 29.5.23 | 31.5.23 | 100% | 20 |  |  | 100% | 20 | Completed | Depart mental
5 | Patch Repair of Leitan -Agape (Lower & Upper) Ring Road | 7 | Aizawl Road North Division | 17.7.23 | 19.7.23 | 100% | 7 |  |  | 100% | 7 | Completed | Depart mental
6 | Patch Repair & Seal Coating of Pema Road at Ramhlun North | 1.5 | Aizawl Road North Division | 17.7.23 | 18.7.23 | 100% | 1.5 |  |  | 100% | 1.5 | Completed | Depart mental
7 | Approach Road to Durtlang Cemetery | 12 | Aizawl Road North Division | 5.6.23 | 8.6.23 | 100% | 12 |  |  | 100% | 12 | Completed | Depart mental
8 | SUB DIVISION-III Re-surfacing of Lower Kanan to Dawrpui Vengthar | 11.43 | Aizawl Road North Division | 17.7.23 | 15.8.23 | 100% | 11.43 |  |  | 100% | 11.43 | Completed | Depart mental
9 | Re-surfacing of Balance portion of 7th Day Hospital to Ebenezer | 10.72 | Aizawl Road North Division | 24.7.23 | 22.8.23 | 100% | 1.72 |  |  | 100% | 1.72 | Completed | Depart mental
10 | Re-surfacing of Approach Road to AICS Shekina Hills Tanhril | 15.2 | Aizawl Road North Division | 17.3.23 | 15.8.23 | 100% | 15.2 |  |  | 100% | 15.2 | Completed | Depart mental
11 | Resurfacing of road from Pu Rfa's Kawn to Primary School including Construction of Rigid Pavement (PCC) at Tanhril | 25.05 | Aizawl Road North Division | 17.3.23 | 16.8.23 | 100% | 25.05 |  |  | 100% | 25.05 | Completed | Depart mental
12 | Patch repair of Chhangurkawn to High Court road | 40 | Aizawl Road North Division | 17.3.23 | 16.8.23 | 100% | 40 |  |  | 100% | 40 | Completed | Depart mental
13 | Re-Surfacing of Zonuam Police Outpost to Ainawn | 15 | Aizawl Road North Division | 17.3.23 | 16.8.23 | 100% | 15 |  |  | 100% | 15 | Completed | Depart mental
14 | Strengthening & Resurfacing of Zobawk Dispensary Approach Road (NH 54A Zobawk - PHC Zobawk) (Balance Portion) | 5.02 | Lunglei Road Division-II |  |  | 100% |  |  | 5.02 | 100% | 5.02 | Completed
15 | Re-Surfacing of Approach Road to Laveng, Haulawng (0.00-1.400Kmp) | 12.92 | Lunglei Road Division-II |  |  | 100% |  |  | 12.92 | 100% | 12.92 | Completed
16 | Extension of Wing Wall on Haulawng Bualpui 'V' upto Chhipphir Road (Chainage : 10.000 & 10.600 Kmp) | 7.81 | Lunglei Road Division-II |  |  | 100% |  |  | 7.81 | 100% | 7.81 | Completed
17 | Re-Surfacing of Approach Road from BRTF Canteen to Helipad upto ICDS Office at Hnahthial | 8.31 | Lunglei Road Division-II |  |  | 17% |  |  | 8.31 | 17% | 8.31 | Material being collected
18 | SMBT of Approach Road from Pu Dodina's House to Pu Thangkima's House at Hnahthial | 13.89 | Lunglei Road Division-II |  |  | 21% |  | 79% | 13.89 | 100% | 13.89 | Material being collected
19 | Resurfacing of Approach Road from Pu Sangkunga House to Pu Lalsiama House Peniel Veng Hnahthial | 6.25 | Lunglei Road Division-II |  |  | 100% |  |  | 6.25 | 100% | 6.25 | Completed
20 | Repair of Thingsai Shortcut Road | 5.61 | Lunglei Road Division-II |  |  | 100% |  |  | 5.61 | 100% | 5.61 | Completed
21 | Re-Surfacing of Approach Road from Pu F.Zosangliana's House to Pu F.Lalduhawma House via Model Veng, Hnahthial | 17.88 | Lunglei Road Division-II |  |  | 20% |  | 80% | 17.88 | 20% | 17.88 | Completed
22 | PWD SDO Quarter Approach Road at Hnahthial (IB Main Road to PWD SDO Qtr) | 3.31 | Lunglei Road Division-II |  |  | 21% |  | 79% | 3.31 | 100% | 3.31 | Completed
23 | Patch repair & Pot hole filling, Resurfacing & Seal coating of Approach road to ITI Complex (Nursing school approach road to ITI complex) | 5.05 | Lunglei Road Division-I |  |  |  |  | 100% | 5.05 | 100% | 5.05 | Completed
24 | Patch repair & Pot hole filling, Resurfacing & Seal coating of Sertlangpui Internal Road (Sertlangpui main road-Sertlangpui PWD, IB) | 5.52 | Lunglei Road Division-I |  |  |  |  | 100% | 5.52 | 100% | 5.52 | Completed
25 | Patch repair & Pot hole filling, Resurfacing & Seal coating of Approach road to Vety Farm, Farmveng) | 11.86 | Lunglei Road Division-I |  |  |  |  | 100% | 11.86 | 100% | 11.86 | Completed
26 | Patch repair & Pot hole filling, Resurfacing & Seal coating off Bazar veng-Tlabung via LDSC Ground (Mandir peng to Thuamluia Mual Upper Road) | 11.35 | Lunglei Road Division-I |  |  |  |  | 100% | 11.35 | 100% | 11.35 | Completed
27 | Seal coating of Dawrzawl to Tawngtaina Tlang, Theiriat | 3.81 | Lunglei Road Division-I |  |  | 100% |  |  | 3.81 | 100% | 3.81 | Completed
28 | Patch repair & Pot hole filling, Resurfacing & Seal coating of haka to District road via Vety Dispensary | 10.9 | Lunglei Road Division-I |  |  | 100% |  |  | 10.9 | 100% | 10.9 | Completed
29 | Patch repair & Resurfacing of Ramzotlang to Diet Road | 19.99 | Lunglei Road Division-I |  |  | 100% | 19.48 |  |  | 100% | 19.48 | Completed
30 | Patch repair & Seal coating of Zohnuai approach road upto Community Hall (0.500-1.750 Kmp) | 9.8 | Lunglei Road Division-I |  |  | 100% | 9.55 |  |  | 100% | 9.55 | Completed
31 | Patch repair & Seal coating of Mualthuam approach road | 11.72 | Lunglei Road Division-I |  |  | 100% | 11.42 |  |  | 100% | 11.42 | Completed
32 | Patch repair & Pot hole filling, Resurfacing & Seal coating of Bunghmun Internal Road (MRB Junction to BDO Complex) | 6.45 | Lunglei Road Division-I |  |  | 100% | 3.13 |  |  | 100% | 3.13 | Completed
33 | Patch repair & Pot hole filling, Resurfacing & Seal coating of Bunghmun Internal Road (Approach Road to BCM Bunghmun) | 3.55 | Lunglei Road Division-I |  |  | 100% | 1.72 |  |  | 100% | 1.72 | Completed
34 | Resurfacing of Approach road to Assistant Commisioner of Excise from NH, Kolasib | 10 | Kolasib Division |  |  | 100% | 10 |  |  | 100% | 10 | Completed
35 | Patch Repair of road from Irrigation Complex to NH-54 at Kolasib | 5 | Kolasib Division | 10.01.24 |  | 100% | 5 |  |  | 100% | 5 | Completed
36 | Resurfacing of Approach road to Project Sub,Station via YMA Hall, Kolasib | 5 | Kolasib Division | 10.01.24 |  | 100% | 5 |  |  | 100% | 5 | Completed
37 | Resurfacing from BSNL Office to Presbyterian Church, Project Veng, Kolasib | 4 | Kolasib Division | 10.01.24 |  | 100% | 4 |  |  | 100% | 4 | Completed
38 | Resurfacing road from Hmarveng Presbyterian Centenary Hall to Hmar veng Kawnghnuai, Hmar Veng, Kolasib | 4 | Kolasib Division | 10.01.24 |  | 100% | 4 |  |  | 100% | 4 | Completed
39 | Resurfacing of CP Road to NH-54 via Forest Tlang, New Diakkawn, Kolasib | 5 | Kolasib Division |  |  | 100% | 5 |  |  | 100% | 5 | Completed
40 | Resurfacing from Tumpui Field to Tumpui Kawnghnuai at Tumpui, Kolasib | 3 | Kolasib Division | 10.01.24 |  | 100% | 3 |  |  | 100% | 3 | Completed
41 | Resurfacing of Approach road to Challui Veng from NH-54 Kolasib | 5 | Kolasib Division |  |  | 100% | 5 |  |  | 100% | 5 | Completed
42 | Construction of R/Wall @0.600Kmp on Rengtekawn to 0 point | 2.5 | Kolasib Division | 27.10.23 |  | 100% | 2.5 |  |  | 100% | 2.5 | Completed
43 | Construction of R/Wall @1.800Kmp on Rengtekawn to 0 point | 6.5 | Kolasib Division | 27.10.23 |  | 100% | 6.5 |  |  | 100% | 6.5 | Completed
44 | Patch Repair & Seal Coat of Dawr Veng Square to Lenhnuai ROad, Bilkhawthlir | 7.05 | Kolasib Division |  |  | 100% | 7.05 |  |  | 100% | 7.05 | Completed
45 | Resurfacing of of Hospital to Mualvum church road, Mualvum | 16.5 | Kolasib Division |  |  | 100% | 16.5 |  |  | 100% | 16.5 | Completed
46 | Patch Repair & Pot Holes filling, Resurfacing Seal Coat of Approach Road to Police Complex (Dawr Veng Police Station Bilkhawthlir)of Dawr Veng Square to Lenhnuai ROad, Bilkhawthlir | 4.24 | Kolasib Division |  |  | 100% | 4.24 |  |  | 100% | 4.24 | Completed
47 | Patch Repair & Pot Holes filling, Resurfacing Seal Coat of Kual Mawi Community Hall to NH-54 via BDO Quarter Approach road | 5.21 | Kolasib Division |  |  | 100% | 5.21 |  |  | 100% | 5.21 | Completed
48 | Resurfacing of Phairuangkai to Bunghmun Road (Ch:1.500-2.000)Kms | 13.17 | Tlabung Division |  |  |  |  | 100% | 13.17 | 100% | 13.17 | Completed
49 | Resurfacing of Tlabung Bazar (Extension) Area | 20.9 | Tlabung Division |  |  |  |  | 100% | 20.9 | 100% | 20.9 | Completed
50 | Extension of RCC Slab Culvert on approach Road to PHE Pump House | 1.82 | Tlabung Division |  |  | 50% |  | 50% | 1.82 | 100% | 1.82 | Completed
51 | Resurfacing of Chawngte P-C Bridge to Bazar waiting shed | 14.11 | Tlabung Division |  |  |  |  | 100% | 14.11 | 100% | 14.11 | Completed

## PM DeVINE
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : PM-DeVINE | [9 empty] | Month : March 2024
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummutive Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of Contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Bamboo Link Road from Lengpui to Saiphal Bamboo Plantation (41 Km) under PM-DeVINE | 4941 | NHD-I | 21.07.23 | 19.01.25 | 17% |  | 1% | 300 | 18% | 300 | On going | EPC Mode
2 | Construction of Bamboo Link Road from Tuirial Airfield to North Chaltlang (18Km) under PM-DevINE | 3358 | Aizawl Road North Division | 1.8.23 | 31.1.25 | 18% |  |  |  | 18% |  | Work in progress

## ICMR
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : DIPHR (ICMR) | [9 empty] | Month : March 2024
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummutive Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of Contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Model Rural Health Research Units at Lungtian Ram, Aibawk | 207.5 | Project Division-II | 21.09.23 | 21.03.25 | 18% |  | 7% | 21.21 | 25% | 21.21 | Workin progress | Item Rate

## Ministry
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : Ministry of Tribal Affairs | [9 empty] | Month : March 2024
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummutive Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of Contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Auditorium at Pukpui Lunglei | 523 | Lunglei Building Project Division | 16.9.23 | 16.01.25 | 5% |  |  |  | 5% |  | Work stopped due to objection of site from Education Dept. Relocation of Site for Construction is beung awaited from Client Dept. | Retsricted Tender

## Interstate
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : Interstate Connectivity | [9 empty] | Month : March 2024
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummutive Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of Contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Road construction of Mizoram-Assam Interstate Border (Sh: Hlimen to Serlui Tuikhuah) Group-I | [11 empty] | Restricted Tender
| 1) Excavation in soil by Mechanical means | 68.43 | Kolasib Division | 10.08.23 | 31.01.24 | 100% | 68.43 |  |  | 100% | 68.43 | Completed
| 2) Excavation in Ordinary Rock by Mechanical means | 50.29 | Kolasib Division | 10.08.23 | 31.01.24 | 100% | 50.2 |  |  | 100% | 50.2
2 | Road construction of Mizoram-Assam Interstate Border (Sh: New Builum to Chemtlang Zau) Grou-2 (Phse-I & III) | [11 empty] | Restricted Tender
| 1) Excavation of soil by Mechanical means | 54.59 | Kolasib Division | 10.08.23 | 31.01.24 | 100% | 54.59 |  |  | 100% | 54.59 | Completed
| 5) Excavation in Ordinary Rock by Mechanical means | 62.36 | Kolasib Division | 10.08.23 | 31.01.24 | 100% | 62.36 |  |  | 100% | 62.36

## NLCPR
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : NLCPR | [9 empty] | Month :March 2024
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Community Hall at Various places in Mizoram (Sh: Construction of Community Hall at Saitual, Thingsulthliah, Maite, Tualbung, Lungpher, Buhban, Lenchim, Chawrtui and Puilo) | 206.49 | Project Division-III | 22.2.12 | 30.11.19 | 100% | 186.01 | - | - | 100% | 186.01 | Completed and balance fund of Rs.20.48 (Rs.16.35 lakhs NLCPR + Rs.4.13 lakhs SMS) a waited for clearing liabilities

## NEDP
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : NEDP | [9 empty] | Month: March 2024
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Officers & Staff Quarter Type-IV, 2 Units and Type-III 4 Units for Taxation Department Lunglei | 330 | Lunglei Building Project Division | 3.7.20 | 30.10.23 (Revised) | 100% | 200.39 |  | 129.61 | 100% | 330 | Civil Works completed and I/E Fund not yet done | Restricted Tender
2 | Construction of DC Bangalow Type-VI at Saiha | 110.9 | Lunglei Building Division | 26.11.08 | 23.05.24 (Revised) | 98.3% | 92.01 |  | - | 98.3% | 92.01 | The contractor has halted construction since Nov'23 and allocation of Balanced Fund of Rs.205.99 lakh has been awaited from the Govt.for completion of the whole projects i.e DC Office, DC Nugalow etc.Revised estimate resubmitted fro approval | Restricted Tender
3 | Construction of DC Office Building at Saiha | 610.11 | Lunglei Building Division | 31.10.18 | 31.10.20 Revised 28.11.23 | 90% | 414.49 |  |  | 90% | 414.49 |  | Restricted Tender
4 | Improvement of Buarpui - Bunghmun - via Thenhlum Road (65.000-79.00) Kmp during 2016-2017 | 170.467 | Lunglei Road Division-I | 4.3.24 | 4.3.25 |  |  | 12% | 43.96 | 12% | 43.96 | Material collection is now in progress, hence Physical achievement could not commensurate with the financial achievement
5 | Resurfacing of MRB Junction to Mini Sport Complex | 5.93 | Lunglei Road Division-I |  |  | 100% | 5.93 |  |  | 100% | 5.93 | Completed
6 | Resurfacing of MRB Junction to Falkawn Bunghmun | 11.87 | Lunglei Road Division-I |  |  | 100% | 11.87 |  |  | 100% | 11.87 | Completed
7 | Retaining Wall of PWD Complex Bunghmun | 7.42 | Lunglei Road Division-I |  |  | 100% | 7.42 |  |  | 100% | 7.42 | Completed
8 | Strengthening of Pavement from Kikawn to AOC at Selected stretches | 44.46 | Lunglei Road Division-I |  |  | 100% | 44.46 |  |  | 100% | 44.46 | Completed
9 | Serkawn Hospital to DIET, Melte (Christian Hospital Serkawn to DIET, Lunglei (0.00 - 1.590Kmp) | 24.72 | Lunglei Road Division-I |  |  | 100% | 24.72 |  |  | 100% | 24.72 | Completed
10 | Patch Repair & Resurfacinf of YPC Hall Serkawn to Chawngbawla Point Zotlang (0.00-1.590Kmp) | 27.76 | Lunglei Road Division-I |  |  | 100% | 27.76 |  |  | 100% | 27.76 | Completed
11 | Patch Repair & Resurfacinf of Zohnuai approach road (0.00-0.50Kmp) | 11.01 | Lunglei Road Division-I |  |  | 100% | 11.01 |  |  | 100% | 11.01 | Completed
12 | Centenary Road Serkawn (Serkawn Christian Hospital, Serkawn Pastor Quarters (0.00-0.540) | 10.93 | Lunglei Road Division-I |  | 2023-11-01 | 100% | 9.59 |  |  | 100% | 9.59 | Completed
13 | AOC to Kikawn | 43.25 | Lunglei Road Division-I |  |  | 100% | 43.25 |  |  | 100% | 43.25 | Completed
14 | Construction of Retaining Wall on ATL Road to Kawmzawl Helipad Road Pukpui (At Ch=400.00m) | 3.08 | Lunglei Road Division-I |  |  | 100% | 3.08 |  |  | 100% | 3.08 | Completed
15 | Improvement of Drainage System from Kikawn to AOC (Culverts & Cross drainage) | 30.29 | Lunglei Road Division-I |  |  | 90% | 30.92 |  |  | 90% | 30.92 | Not yet Completed
16 | Approach Road to Kendriya School at Ramthar Veng (Nursing School Approach Road Kendriya School Ramthar Veng) | 34.21 | Lunglei Road Division-I |  | 2024-03-01 | 24.51% | 5.42 | 75.49% |  | 100% | 5.42 | Completed
17 | JB Press to Sobji Bazar (0.000-0.307 Kmp) | 5.41 | Lunglei Road Division-I |  |  | 100% | 5.41 |  |  | 100% | 5.41 | Completed
18 | AOC to District Road (AOC Ramthar District Road) | 5.95 | Lunglei Road Division-I |  |  | 100% | 5.95 |  |  | 100% | 5.95 | Completed
19 | MAO Complex Internal Road (Caommandant Bungalow to Thangte Peng) | 19.62 | Lunglei Road Division-I |  |  | 100% | 19.62 |  |  | 100% | 19.62 | Completed
20 | R.Zosanga Road at Lunglawn (NH-54A Z.Rosanga's House) | 2.96 | Lunglei Road Division-I |  |  | 100% | 2.96 |  |  | 100% | 2.96 | Completed
21 | NH 54A to Lunglawn Hmunhlui Tlang via Pu H.Lalzarliana's House (NG 54A Main Road PC Thlanmual's House) | 2.11 | Lunglei Road Division-I |  |  | 100% | 2.11 |  |  | 100% | 2.11 | Completed
22 | Parallel Road from Pu Lalpara's House to Prebyterian Church (Part 1) | 13.35 | Lunglei Road Division-I |  |  | 100% | 13.35 |  |  | 100% | 13.35 | Completed
23 | Approach Road to LDSC Ground No II from District Road (District Road LDSC Ground No II) | 4.41 | Lunglei Road Division-I |  |  | 100% | 4.41 |  |  | 100% | 4.41 | Completed
24 | Salem Internal Road (NH 54A to District Road) | 10.2 | Lunglei Road Division-I |  |  | 100% | 10.2 |  |  | 100% | 10.2 | Completed
25 | Falkawn to District Road (Falkawn District Road) | 9.26 | Lunglei Road Division-I |  |  | 100% | 9.26 |  |  | 100% | 9.26 | Completed
26 | Ramthar Veng Baptist Church Ring Road (AOC Ramthar Mazara's Spare Parts) | 4.36 | Lunglei Road Division-I |  |  | 100% | 4.36 |  |  | 100% | 4.36 | Completed
27 | Resurfacing of Approach Road DCs Office from MST Bus Station (MST Bus Station DC Office) | 12.44 | Lunglei Road Division-I |  |  | 100% | 12.44 |  |  | 100% | 12.44 | Completed
28 | Reusrfacing of Mizoram Rural Bank to DC Office via LAD Office (Mizoram Rural Bank DC Office) | 13.35 | Lunglei Road Division-I |  |  | 100% | 13.35 |  |  | 100% | 13.35 | Completed
29 | Resurfacing of District Road | 113.74 | Lunglei Road Division-I |  |  | 100% | 113.74 |  |  | 100% | 113.74 | Completed
30 | Resurfacing of LP Thangzika's Shop to Forest Check Gate) | 53.19 | Lunglei Road Division-I |  |  | 100% | 58.71 |  |  | 100% | 58.71 | Completed
31 | Resuirfacing of Parallel Road from Pu Lalpara's House to BCM Kikawn Biak In (Part 2) | 97.86 | Lunglei Road Division-I |  |  | 100% | 97.86 |  |  | 100% | 97.86 | Completed
32 | Resurfacing of Rahsi Veng to Tlabung Road via Sazaikawn (Forest Check Gate to Tlabung Kawng) | 12.83 | Lunglei Road Division-I |  |  | 100% | 12.83 |  |  | 100% | 12.83 | Completed
33 | Resurfacing of Rahsi Veng to Tlabung Road via Sazaikawn (Forest Check Gate to Tlabung Kawng) | 22.07 | Lunglei Road Division-I |  |  | 100% | 23.05 |  |  | 100% | 23.05 | Completed
34 | SE PWD Residence Approach Road (DC's Office SE Office) | 2.1 | Lunglei Road Division-I |  |  | 100% | 2.1 |  |  | 100% | 2.1 | Completed
35 | DC Residence from SE PWD Qtr Approach road (SE PWD Qtr DC Residence) | 0.64 | Lunglei Road Division-I |  |  | 100% | 0.64 |  |  | 100% | 0.64 | Completed
36 | Construction of Breast Wall at 0.120Kmp on approach road to Kendryia School Lunglei | 26.75 | Lunglei Road Division-I |  |  | 100% | 26.75 |  |  | 100% | 26.75 | Completed
37 | Construction of Retaining Wall at 0.600 Kmp on Tlabung Peng to Colony PWD Road (Boundary of Venghlun and Rahsi veng) | 7.27 | Lunglei Road Division-I |  |  | 100% | 7.27 |  |  | 100% | 7.27 | Completed
38 | Construction of Retaining Wall at 1.100Kmp on 2nd Parallel Road, Bazar Veng, Lunglei | 6.02 | Lunglei Road Division-I |  |  | 100% | 6.02 |  |  | 100% | 6.02 | Completed
39 | Construction of Retaining Wall at 1.48 Kmp on Sangchem Road | 15.49 | Lunglei Road Division-I |  |  | 100% | 15.49 |  |  | 100% | 15.49 | Completed
40 | Construction of Retaining Wall at Ch:18.450Kmp on Lunglei to Buarpui Road | 26 | Lunglei Road Division-I |  |  | 100% | 26 |  |  | 100% | 26 | Completed
41 | Construction of Retaining Wall at Ch: 18.450Kmp on Lunglei to Buarpui Road | 7 | Lunglei Road Division-I |  |  | 100% | 7 |  |  | 100% | 7 | Completed
42 | Construction of Retaining Wall at 18.500Kmp on Lunglei to Buarpui Road | 4.3 | Lunglei Road Division-I |  |  | 100% | 4.3 |  |  | 100% | 4.3 | Completed
43 | Construction of Multi Level Parking cum Basketball Court beside the main Building | 541.8 | Project Division-I | 5.12.19 | 31.1.23 | 100% | 541.8 |  |  | 100% | 541.8 | Work Completed
44 | Const.of Bridge on Chhinga Vengthar to Tuithiang Road | 586.36 | Aizawl Road South Division | 19.04.21 | 31.10.22 | 100% | 200 | - |  | 100% | 200 | Phy.Work completed | Item Rate Contract
45 | Reconstruction of Concrete Pavement on approach road to Mission Vengthlang Cemetry, L=150m | 8.51 | Aizawl Road South Division | [8 empty] | Works not yet started

## SPP
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : SPP | [9 empty] | Month : March 2024
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Office Building for IF & SL at Tuikhuahtlang | 401.18 | Project Division-III | 13.7.20 | 11.09.23 | 100% | 400.72 |  | 0.46 | 100% | 401.18 | Completed and handed over to Director IF&SL | PWD Form-8
2 | Construction of Circuit House at Serchhip | 358.18 | Project Division-III |  |  | - | - | - | - | - | - | Estimate amounting to Rs.3.58 Cr submitted as per new drawing. Waiting for approval for tender.
3 | Construction of Truckable Road between Tlangpui and Lungva | 480 | Khawzawl Division | 5.7.18 | 5.7.19 | 63% | 327.23 | - | - | 63% | 327.23 | EOT granted upto 7.10.2020 | Item rate contract

## DONER
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : One Time Special Assistance under Ministry of DONER | [9 empty] | Month : March 2024
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Re-Construction of safe House at Tlabung | 114.9 | Lunglei Building Project Division | 18.11.21 | 18.11.22 | 100% | 112.66 | - |  | 100% | 112.66 | Civil Works completed. and IE not yet done. Handover in process | Restricted Tender
2 | Re-Construction of safe shelter at Sairang | 115 | Project Division-II | 13.11.21 | 13.11.22 | 100% | 79.7 | - | 34.1 | 100% | 113.8 | Work physically completed | Item Rate

## NERSDS
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : NERSDS | [9 empty] | Month : March 2024
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Upgradation of Saiha-Lungbun-Tluangram-Haka Road in the State of Mizoram | 5021 | Saiha Division | 29.10.21 | 31.03.24 | 62.24% | 1985 |  |  | 62.24% | 1985 | Work in progress | EPC Mode
2 | Upgradation of Hnahlan-Hmunhlui-Tuimang-Singngei Road (Length = 12.000 Kms) | 4417 | Champhai Division | 29.11.21 | 31.3.24 (as per4 EoT-01) | 83.44% | 1921.51 | 0.82% | 309.89 | 84.26% | 2231.4 |  | EPC
3 | Upgradation of Zote-Fartlang-Buanli-Tuipui-Tawnzang Road in the state of Mizoram under NERSDS (Length = 8.00 Kms) | 2926 | Champhai Division | 12.12.21 | 31.3.24 (as per4 EoT-01) | 86.73% | 1472.14 | 13.27% | 250.05 | 100% | 1722.19 |  | EPC

## ISC Scheme
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : ISC Scheme & EI | [9 empty] | Month : March 2024
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of Contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Improvement of Tuipuibari - W.Kawnpui Road and ISC (0.00-9.00 Kmp) | 4870 | Mamit Division | 20.3.20 | 20.3.22 | 76% | 3978.3 | 9% |  | 85% | 3978.3 |  | EPC

## CRF
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : CRF | [9 empty] | Month : March 2024
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Two Lane from Sihhmui-Ramrikawn Road (Stage-I) | 8000 | Aizawl Road North Division | 1.10.18 | 1.10.20 | 92.28% | 4620.81 |  |  | 92.28% | 4620.81 | In progress | Item rate
2 | Widening and Improvement of Road from Durtlang Leitan to Sihphir Section (Length 10.25 Km) of Aizawl - Durtlang - Lungdai -Kawnpui Road in the State of Mizoram | 4657 | Aizawl Road North Division | 14.7.23 | 31.1.25 | 37.77% | 200 | 2.23% |  | 40% | 200
3 | Construction of BUG Bridge over Tlawng on Aizawl-Reiek-W.Lungdar Road at 14.800 Kmp | 757.56 | Aizawl Road South Division | 10.10.18 | 31.3.22 | 92.6% | 488.56 |  |  | 92.6% | 488.56 | Work in progress | EPC Mode
4 | Patch Repair of Aizawl-Reiek Road for the upcoming G-20 Meeting | 88.87 | Aizawl Road South Division | 14.2.23 | 28.2.23 | 100% | 88.87 |  |  | 100% | 88.87 | Completed | Dept
5 | Construction of Muallungthu-Lungphun Road | 5996 | Hmuifang Division | 23.11.17 | 23.11.19 | 33.39% | 1940.67 | - | 299.99 | 33.39% | 2240.66 | Work in progress
6 | Widening to single lane with geometric imprivement & Upgradation of Chhiahtlang-Lamchhip Road | 6668.18 | Hmuifang Division | 23.6.17 | 23.06.19 | 100% | 6283.78 | - |  | 100% | 6283.78 | Completed
7 | Construction of Chakkhei to Siasi Road (Permanent Work) (0.00-20.00 Kmp) | 1216.88 | Saiha Division | 8.7.19 | 30.9.23 | 96.62% | 856.38 | 1.31% |  | 97.93% | 856.38 | Work in progress | Item rate contract
8 | Construction of Chakkhei to Siasi Road (FC&Pavement Work) (0.00-20.00 Kmp) | 3617.05 | Saiha Division | 8.7.19 | 11.11.23 | 98.55% | 2480.24 | 0.08% | 358.6 | 98.63% | 2838.84 | Work in progress | Item rate contract

## NESIDS
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : NESIDS | [9 empty] | Month : March 2024
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of 2 Residential Hostel at ZMC (Boys) | 1000 | Project Division-II | 14.10.21 | 29.10.23 | 100% | 1000 |  |  | 100% | 1000 | Work Completed | EPC
2 | Construction of 2 Residential Hotel at ZMC (Girls) | 1000 | Project Division-II | (O)14.10.21 (R) 15.04.24 | (O)27.10.23 (R)15.04.24 | 89% | 765.15 | 1% |  | 90% | 765.15 | Work in progress | EPC
3 | Construction of 100 Bedded Distict Hospital at Kolasib | 2200 | Project Division-II | 23.09.22 | 23.09.24 | 40% | 598.83 | 5% |  | 45% | 598.83 | Work in progress | EPC
4 | Construction of State Resource Centre for HIV/AIDS at Aizawl | 400 | Project Division-II | 22.09.22 | 22.09.24 | 41% | 134.2 | 9% |  | 50% | 134.2 | Work in progress | EPC
5 | Improvement /Upgradation of Operational/Non-operational facilities of Lengpui Aiport (elevated Road with connected components of Terminal Building) | 1959 | Project Division-III | 30.9.21 | 12.6.24 | 92.8% | 1317.31 | 1% | 133 | 93.8% | 1450.31 | Work in progress | Turnkey
6 | Improvement & Upgradation of Lawngtlai-Tuipui ferry Road under NESIDS | 2897.8 | Lawngtlai Division | 08.08.19 | 30.06.23 | 100% | 2666.68 |  |  | 100% | 2666.68 | U/C amounting to Rs.2666.68 Submitted on 29th June 2023 | Item rate

## SCA
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : S.C.A | [9 empty] | Month : March 2024
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummutive Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of Contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Improvement of MPSC Office Building at MINECO | 394 | Project Division-I | 29.10.22 | 29.10.24 | 94% | 315.23 | 6% | 2.32 | 100% | 317.55 |  | EPC
2 | Construction of DIG (NR) Office Building at PHQ Complex, Aizawl | 320 | Project Division-I | 21.7.22 | 21.1.25 | 92% | 180.36 | 5% |  | 97% | 180.36 |  | EPC
3 | Construction of Govt.Staff Qtrs.(Block-B) at DIET Complex | 386.6 | Project Division-I | 28.8.22 | 28.8.24 | 53% | 150.94 | 10% | 3.26 | 63% | 154.2 |  | EPC
4 | Strengthening of Infrastructure in 3 newly created Districts (Const.of DC Office Khawzawl) | 1000 | Project Division-III | 25.02.21 | 21.04.24 | 99.9% | 999.34 |  | 0.66 | 99.9% | 1000 | Work completed and handed over to DC Khawzawl | PWD Form-8
5 | Strenthening of Infrastructure in 3 newly created Districts (Const.of DC Office Saitual) | 1000 | Project Division-III | 25.02.21 | 20.04.24 | 99% | 972.53 | 0.5% |  | 99.5% | 972.53 | Work in progress | PWD Form-8
6 | Construction of District Research Officers Office at Khawzawl (Sh: C/o DRO Office Ground Floor & C/O Quarters 1st Floor) | 43 | Project Division-III | 18.08.22 | 12.05.23 | 100% | 43 |  |  | 100% | 43 | Completed and handed over to Economic & Statistics Deptt | PWD Form-8
7 | Construction of District Research Officers Quarters and Staff Cum Chowkider Quarters at Keifang, Saitual District | 70 | Project Division-III | 22.03.22 | 24.2.24 | 80% | 25 |  |  | 80% | 25 | Work in progress | PWD Form-8
8 | Improvement & Upgradation of Operational/Non Operational facilities of Lengpui (Sh: Renovation of Terminal building) | 2124 | Project Division-III | 16.03.21 | 21.10.23 Extended upto 6.05.24 | 96.9% | 1254.05 | 0.2% | - | 97.1% | 1254.05 | Work in progress | PWD Form-8
9 | Construction of 100 Bedded Dist Hospital at Saitual (Sh: Construction of OPD building at District Hospital, Saitual | 200 | Project Division-III | 22.3.22 | 13.10.25 | 10% | 14.15 | 3% |  | 13% | 14.15 | Work in progress | PWD Form-8
10 | Strengthening of Aizawl-Thenzawl-Lunglei Road from (17.000-30.000 & 51.000-63.00 Kmp) | 1332 | Hmuifang Division | 12.10.21 | 31.03.22 | 100% | 1322.2 | - |  | 100% | 1322.2 | Completed
11 | Rehabilitation of Landslide Area within Hualngohmun Village at Chainage 9.400 | 162 | Hmuifang Division | 28.03.22 | 28.03.23 | 100% | 162 |  |  | 100% | 162 | Completed

## NLUP
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : NLUP | [9 empty] | Month : March 2024
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Re-Construction of District Transport Office at Champhai | 262 | Project Division-III | 11.7.22 | 11.01.24 | 100% | 259.5 |  | 2.48 | 100% | 261.98 | Handover to Transport Department | PWD Form-8

## SARDPNE
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : SARDP-NE | [9 empty] | Month : March 2024
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Widening to two laning/Re-alignment and geometric improvement from km.11+000 to 114+618 of NH-44 'A' in the state of Mizoram | 1,10,988.00 | NHD-I | 17.3.11 | 31.12.22 | 96.04% | 102146 |  |  | 96.04% | 102146 | Contract was terminated on 24.08.2023 Tender be floated on EPC mode as per instruction from MoRTH | Item rate contract
2 | Construction of a new 2-lane Highway from km 0/00kmp to 38/00 in Mizoram to support Kaladan Multi Modal Transit Transport project in Phase-'A of SARDP-NE package-I | 43465 | Multi Modal Project Division |  |  | 100% | 42978 |  |  | 100% | 42978 | 1. Financial progress is upto RA 145 2. Work completed on 22.6.2023
3 | Construction of a new 2-lane Highway from km 38.00 to km 71.00 in Mizoram to support Kaladan Multi Modal Transit Transport project in Phase-'A of SARDP-NE package-II | 32224 | Multi Modal Project Division |  |  | 100% | 30977 |  | - | 100% | 30977 | 1. Financial progress is based on bill submitted by the Contractor after verifying at the spot by the Department. 2. Work completed on 30.04.22
4 | Construction of a new 2-lane Highway from km 71.00 to km 99.83 in Mizoram to support Kaladan Multi Modal Transit Transport project in Phase-'A of SARDP-NE package-III | 37459 | Multi Modal Project Division |  |  | 100% | 37689 |  |  | 100% | 37689 | 1. Financial progress is based on the figure shown in the MoP of the latest bill appproved by Regional Officer, MoRTH Guwahati i.e RA-145 (Retention Money Bill) 2. Work completed on 23.06.23

## MAJOR
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : Major & Minor Works and Deposit woks 8443-108, D-III | [9 empty] | Month : March 2024
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | I/E to Additional Court Room with Chamber at Kolasib | 4.26 | Electrical Division Aizawl |  |  | 100% | 4.26 | - | - | 100% | 4.26 | I/E Completed, S/C being process
2 | I/E to Arrival & Departure Passenger Lobby at Lengpui Airport | 25.27 | Electrical Division Aizawl |  |  | 90% | 25.27 | - | - | 90% | 25.27 | Panel Board not yet installed
3 | SITC 13 Passenger Lift-2 nos, 2-opening, 900mm centre opening Stainless Steel cable with Automatic Rescue Device (ARD) for Hydraulic Lift with Minor Civil Works at Lengpui Airport Mizoram | 77.91 | Electrical Division Aizawl |  |  | 50% | 38.33 |  |  | 50% | 38.33 | On going works
4 | I/E to Chowkider Qtrs at PWD Complex, Bilkhawthlir | 3.6 | Electrical Division Aizawl |  |  | 100% | 3.6 | - | - | 100% | 3.6 | Completed
5 | I/E to Rest House at PWD Complex, Bilkhawthlir | 30.91 | Electrical Division Aizawl |  |  | 100% | 30.88 | - |  | 100% | 30.88 | Completed
6 | I/E to Re-construction of Safe House at Sairang | 5.2 | Electrical Division Aizawl |  |  | 100% | 5.2 | - | - | 100% | 5.2 | Completed
7 | I/E to Paying Cabin for ZMC at Falkawn | 99.32 | Electrical Division Aizawl |  |  | 100% | 99.32 | - | - | 100% | 99.32 | Completed
8 | SITC with fire fighting system for paying cabin ZMC at Falkawn | 34.57 | Electrical Division Aizawl |  |  | 100% | 34.57 | - |  | 100% | 34.57 | Completed
9 | SITC of 15 passenger G+4MRL Hospital Lift with 900mm Central Opening with Automatic Resue Device (ARD) est (OTISmake) at Paying | 50 | Electrical Division Aizawl |  |  | 100% | 50 | - |  | 100% | 50 | Completed
10 | I/E to Fast Track Court (Judical Gr-I qtr) at Kolasib | 11.43 | Electrical Division Aizawl |  |  | 100% | 11.43 | - | - | 100% | 11.43 | Completed
11 | Street Light Parking light at Lengpui Airport | 37.32 | Electrical Division Aizawl |  |  | 90% | 37.31 |  | - | 90% | 37.31 | On going works
12 | Laying of XLPE Cable from Power House to Glide Path control at Lengpui Airport, Mizoram | 39.53 | Electrical Division Aizawl | 09.05.23 | 04.08.23 | 100% | 39.52 |  |  | 100% | 39.52 | Completed
13 | Estimate for I/E of Energy Meter for Terminal Building at Lengpui Airport | 7.99 | Electrical Division Aizawl |  |  | 90% | 7.99 |  | - | 90% | 7.99 | On going works
14 | I/E for Const.of Grade I Officers Qtr at Project veng Kolasib | 5.13 | Electrical Division Aizawl |  |  | 100% | 5.13 | - | - | 100% | 5.13 | Completed
15 | I/E & Fire fighting to Car Parking at Dist.Court MINECO | 32.48 | Electrical Division Aizawl |  |  | 60% | 16.99 | - | - | 60% | 16.99 | On going works
16 | SITC of Fire Fighting System of Dist.Court, MINECO | 125.4 | Electrical Division Aizawl |  |  | 100% | 124.83 | - | - | 100% | 124.83 | Completed
17 | Addl.Estimate for SITC of MRV/VRF Centralizes Air Conditioner Airport Fist Floor Departure Hall, Mizoram | 247.74 | Electrical Division Aizawl |  |  | 70% | 220.1 |  | - | 70% | 220.1 | On going works
18 | SITC of EPABX System for Lengpui Airport Terminal Building | 24.64 | Electrical Division Aizawl |  |  | 80% | 19.46 |  |  | 80% | 19.46 | On going works
19 | SITC of PA System at Lengpui Airport Terminal Building | 36.36 | Electrical Division Aizawl |  |  | 80% | 28.82 |  |  | 80% | 28.82 | On going works
20 | Supply & Installation of Integrated Fire Hydrant System (Wise Riser) & SiTC of Alarm System for Lengpui Airport Terminal building | 119.96 | Electrical Division Aizawl |  |  | 80% | 94.72 |  |  | 80% | 94.72 | On going works
21 | SITC of AVTRON IP Surveillance System for Lengpui Airport Terminal Building | 94.76 | Electrical Division Aizawl |  |  | 80% | 67.61 |  |  | 80% | 67.61 | On going works
22 | SITC of LANE SETUP at Lengpui Airport Terminal Building | 20.05 | Electrical Division Aizawl |  |  | 80% | 67.61 |  |  | 80% | 67.61 | On going works
23 | Estimate for XLPE Cable for Lengpui Airport | 27.23 | Electrical Division Aizawl |  |  | 90% | 27.23 | 10% | - | 100% | 27.23 | On going works
24 | Additional Estimate fo SITC of Air Conditioner Departer Pssenger Lobby at Lengpui Airport | 24.67 | Electrical Division Aizawl |  |  | 100% | 24.67 | - | - | 100% | 24.67 | Completed
25 | I/E works for Const. of MBSE Office | 57.37 | Electrical Division Aizawl |  |  | 70% | 57.37 | 10% |  | 80% | 57.37 | On going works
26 | I/E for DC Office at Saitual | 70 | Electrical Division Aizawl |  |  | 100% | 70 | - | - | 100% | 70 | I/E completed, S/C left due to non installation of required transformer
27 | I/E for Const. of IF &SL Office building at Tuikhuahtlang | 23.33 | Electrical Division Aizawl |  |  | 100% | 23.33 |  |  | 100% | 23.33 | Completed
28 | I/E to High Court Parking at MINECO | 109.5 | Electrical Division Aizawl |  |  | 40% | 65.73 | - | - | 40% | 65.73 | On going works
29 | I/E to Staff qtrr Block A for DIET, Chaltlang | 40.11 | Electrical Division Aizawl |  |  | 100% | 40.11 |  |  | 100% | 40.11 | Completed
30 | I/E to PHC at Bungzung | 18.18 | Electrical Division Aizawl |  |  | 100% | 18.18 |  | - | 100% | 18.18 | I/E Completed, S/C left due to non installation of required transformer
31 | I/E to PHC at Ngentiang | 15.72 | Electrical Division Aizawl |  |  | 100% | 15.72 | - |  | 100% | 15.72 | Completed
32 | Const.of DIG(NR) Office at Aizawl under SCA during 2022-23 (Sh:I/E) | 43.84 | Electrical Division Aizawl |  |  | 40% | 17.29 | 40% | - | 80% | 17.29 | On going works
33 | I/E to Mizoram Public Service Commission (MPSC) Building, Aizawl | 25.86 | Electrical Division Aizawl |  |  | 85% | 25.86 | 15% |  | 100% | 25.86 | Completed
34 | Construction of DC Office at Khawzawl (Sh: Lift & I/E) | 105.73 | Electrical Division Aizawl |  |  | 100% | 105.68 |  |  | 100% | 105.68 | I/E Works completed
35 | I/W Multi Level Parking Cum Basketball Court | 11.4 | Electrical Division Aizawl |  |  | 100% | 11.4 |  |  | 100% | 11.4 | Completed
36 | Reconstruction of PHC Building at Marpara, Mamit District | 16.18 | Electrical Division Aizawl |  |  | 100% | 16.18 |  |  | 100% | 16.18 | Completed
37 | Reconstruction of PHC Building at Bukpui | 14.59 | Electrical Division Aizawl |  |  | 100% | 14.59 |  |  | 100% | 14.59 | Completed
38 | Type-III Qtr at Vairengte | 1.6 | Electrical Division Aizawl |  |  | 100% | 1.6 |  |  | 100% | 1.6 | Completed
39 | JCO/NCO & Jawan Mess at Vairengte | 1.1 | Electrical Division Aizawl |  |  | 100% | 1.1 |  |  | 100% | 1.1 | Completed
40 | JCO Qtr Barrack cum Hote Company Hqrs at Vairengte | 3.6 | Electrical Division Aizawl |  |  | 100% | 3.6 |  |  | 100% | 3.6 | Completed
41 | Barrack I at Vairengte | 2.2 | Electrical Division Aizawl |  |  | 100% | 2.2 |  |  | 100% | 2.2 | Completed
42 | Barrack II at Vairengte | 2.2 | Electrical Division Aizawl |  |  | 100% | 2.2 |  |  | 100% | 2.2 | Completed
43 | Barrack III at Vairengte | 2.2 | Electrical Division Aizawl |  |  | 100% | 2.2 |  |  | 100% | 2.2 | Completed
44 | Reconstruction of DTO Office at Champhai | 17 | Electrical Division Aizawl |  |  | 100% | 17 |  |  | 100% | 17 | Completed
45 | I/E to DRO Office at Khawzawl | 2.84 | Electrical Division Aizawl |  |  | 100% | 2.84 |  |  | 100% | 2.84 | Completed
46 | Impvt/Revamping of Lengpui Airport runway Lighting -Isolation Bay-DGCA Observation Reg. | 347.05 | Electrical Division Aizawl |  |  | 95% | 218.94 | 5% |  | 100% | 218.94 | Completed
47 | Impvt/Revamping of Lengpui Airport runway Lighting -Isolation Bay-DGCA Observation Reg. | 10.91 | Electrical Division Aizawl |  |  | 95% |  | 5% |  | 100% |  | Completed
48 | Impvt/Revamping of Lengpui Airport runway Lighting -Isolation Bay-DGCA Observation Reg. | 14.6 | Electrical Division Aizawl |  |  | 95% |  | 5% |  | 100% |  | Completed
49 | Impvt of Mizoram House at Silchar-repair of Dak Bangla Ground Floor, DRC Office & DRC Qtr T-IV | 5.19 | Electrical Division Aizawl |  |  | 100% | 5.19 |  |  | 100% | 5.19 | Completed
50 | Renovation/Revamping of Internal Electrification to Polytechnic at Thingdawl (Sh: Automobile Engineering Block) | 18.65 | Electrical Division Aizawl |  |  | 90% |  |  |  | 90% |  | I/E completed, Service connection left
51 | Renovation/Revamping of Internal Electrification to Polytechnic at Thingdawl (Sh: Textile Technology Block) | 18.71 | Electrical Division Aizawl |  |  | 90% |  |  |  | 90% |  | I/E completed, Service connection left
52 | Renovation/Revamping of Internal Electrification to Polytechnic at Thingdawl (Sh: Administrative Block) | 9.52 | Electrical Division Aizawl |  |  | 90% |  |  |  | 90% |  | I/E completed, Service connection left
53 | Renovation/Revamping of Internal Electrification to Polytechnic at Thingdawl (Sh: Common facility Block) | 11.05 | Electrical Division Aizawl |  |  | 90% |  |  |  | 90% |  | I/E completed, Service connection left
54 | Renovation of I/E to BSUP 17 block @ 16 rooms at Durtlang | 40 | Electrical Division Aizawl |  |  |  |  | 100% |  | 100% |  | Completed

## SASCE
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : SASCE | [9 empty] | Month : March 2024
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummutive Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Multi Utility Centre at Zemabawk, Aizawl, Mizoram. | 800 | Project Division-IV | 19.12.22 | 16.8.25 | 34.81% | 165.46 | 1.57% |  | 36.38% | 165.46 | Work in progress. | Item Rate
2 | Construction of Solid Waste Management Centre at Hualngohmun, Mizoram (Phase-I) | 1664 | Project Division-IV | 07.04.23 | 07.04.25 | 5% | 73.07 | 1.5% |  | 6.5% | 73.07 | Work in progress. | Item Rate
3 | Const.of Road from IR Camp to Ramri Lui, Zophai, Bairabi (Sh: Group A-Formation Cutting, Permanent works and side drain) | 498 | NHD-III | 27.07.23 | 27.01.24 | 100% | 218.28 |  | 21.95 | 100% | 240.23 | Completed | Item Rate
| Group B-Pavement. Traffic Sign and Road Safety |  | NHD-III | 11.09.23 | 11.03.24 | [7 empty] | Item Rate
4 | Strengthening of Saitual - Phullen Road (28.300 Km) Tuivawl-Phullen (28.700-57.000 Kmp) | 320 | Saitual Division | 08.02.21 | 18.04.21 | 100% | 319.99 |  |  | 100% | 319.99

## SPF
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : State Plan Fund | [9 empty] | Month : March 2024
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummutive Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of Contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | 4202 Co-On Education etc. a) I/E to boys & girls Hostel for Govt.Saiha College bldg at Siaha | 2 | Electrical Division, Lunglei |  |  | 40% | - | - | - | 40% | - | Materials received, building not yet ready
2 | 8443-108-PWD Deposit-III a) I/E to DC Bungalow (Type-IV) at Siaha | 8.2 | Electrical Division, Lunglei |  |  | 40% | - |  | - | 40% | - | Materials received, building not yet ready
| b) I/E to Primary Health Centre (PHC) at Tawipui 'S' | 20 | Electrical Division, Lunglei | 1.6.23 | 13.7.23 | 100% |  |  |  | 100% |  | Completed | Electrical Licensed Contractor
| c) I/E to DRO Quarter & DRO Office at Hnahthial | 2.71 | Electrical Division, Lunglei |  |  | 100% |  |  |  | 100% |  | Completed | Depart mental
| d) I/E to DC Office Building at Hnahthial | 68.43 | Electrical Division, Lunglei |  |  | 100% |  |  |  | 100% |  | Completed | Depart mental
| e) I/E to Safe House at Tlabung | 8 | Electrical Division, Lunglei | [8 empty] | TS accorded
| f) I/E to PHC Building at Lungsen | 19 | Electrical Division, Lunglei | [8 empty] | TS accorded
| g) SiTC of 13 (Thirteen) Passengers 5-Opening for DC office Buiulding at Hnahthial | 50 | Electrical Division, Lunglei | 20.4.23 | 20.2.24 | 100% |  |  |  | 100% |  | Completed | Contractor
| h) I/E to Judicial Quarter Grade-I at Lawngtlai | 10 | Electrical Division, Lunglei | [8 empty] | TS accorded
| i) I/E to Judicial Quarter Type-I & Type-II at Lawngtlai | 13 | Electrical Division, Lunglei | [8 empty] | TS accorded
| j) I/E to Taxation Staff Quarter Type-III 4 units at Lunglei | 17 | Electrical Division, Lunglei | [8 empty] | TS accorded
| k) I/E to Taxation Officers Quarter Type-IV 2 Units at Lunglei | 9 | Electrical Division, Lunglei | [8 empty] | TS accorded
3 | 4059-Co on Public works (Plan) a) I/E to District Court Building at Siaha | 139 | Electrical Division, Lunglei |  |  | 100% | - |  | - | 100% | - | Completed | Depart mental
| b) SITC of 8 (Eight) Passenger Auto Elevator for District Court Building at Siaha | 42 | Electrical Division, Lunglei | 14.12.21 | 18.5.24 | 85% |  | 10% |  | 95% |  | On going works | Contractor
4 | 4047-Co on other Fiscal Sevice
| a) I/E to deputy Commissioner of State Tax, Siaha zone (Office( at Siaha | 17 | Electrical Division, Lunglei |  |  | 100% |  |  |  | 100% |  | Completed | Depart mental
| b) I/E to Staff Quarter for Deputy Commissioner of State Tax, Siaha Zone (Type-I & Type-III) at Siaha | 13 | Electrical Division, Lunglei |  |  | 100% |  |  |  | 100% |  | Completed | Depart mental
| c) I/E to Staff Quarter for Deputy Commissioner of State Tax, Siaha Zone (Type-IV) at Siaha | 5 | Electrical Division, Lunglei |  |  | 100% |  |  |  | 100% |  | Completed | Depart mental

## Under L & J
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : Under L & J | [9 empty] | Month : March 2024
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of District Court Complex at Vengsang, Champhai | 4915.35 | Project Division-III | 17.10.23 | 17.10.26 | 8% | 241.5 | 2% |  | 10% | 241.5 | Work in progress | PWD Form-8

## Aspirational
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
| Source of funding : Aspirational District Programme, Window-I | [8 empty] | Month :March 2024
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Link Road from W.Mualthuam to Sothapa Road (Length=7.300Kms) | 200 | Kawrthah Division | 15.10.23 | 14.4.24 | 40% |  | 5% | 33.62 | 45% | 33.62 | Work in progress | Contract after call of Restricted Tender

## SASCI
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
| Source of funding : SPECIAL ASSISTANT TO STATE FOR CAPITAL INVESTMENT | [8 empty] | Month : March, 2024
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of Contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 900% | 10 | 11 | 12 | 13 | 14
LUNGLEI BUILDING PROJECT DIVISION :
1 | Construction of Circuit House at Hnahthial 'A; | 304 | Lunglei Building Project Division | 13.04.23 | 13.10.24 | 25% |  | 5% |  | 30% |  | Work in progress | Restricted Tender
2 | Construction of Circuit House at Hnahthial 'B; | 200 | Lunglei Building Project Division | 13.04.23 | 13.10.24 | [6 empty] | Not yet started | Restricted Tender
3 | (a) Const. of Laboratory Building at Civil Hospital Lunglei (Ground floor0 | 192 | Lunglei Building Project Division | 28.10.21 | 28.10.22 | 100% | 192.98 |  |  | 100% | 192.98 | Completed | Restricted Tender
4 | (b) Const. of Laboratory Building at Civil Hospital, Lunglei (1st & 2nd floor) Supplementary Works | 396 | Lunglei Building Project Division | 28.10.22 | 28.04.24 | 80% | 290.45 | 5% |  | 85% | 290.45 | Work in progress | Restricted Tender
5 | Construction of Sangau SDO© Office building at Sangau | 77 | Lunglei Building Project Division | 20.03.23 | 20.03.24 | 100% | 36.92 |  | 5.69 | 100% | 42.61 | Phy.Completed | Spot Quotation
6 | Construction of SDO© Quarter at Sangau | 80 | Lunglei Building Project Division | 20.03.23 | 20.03.24 | 100% | 40 |  | 32.81 | 100% | 72.81 | Phy.Completed | Spot Quotation
7 | Construction of Staff Quarter(2 Units) at Sangau | 50.45 | Lunglei Building Project Division | 20.03.23 | 20.03.24 | 100% | 25 |  | 20.87 | 100% | 45.87 | Phy.Completed | Spot Quotation
8 | Construction of Volleyball Court at Gulsil Chawngte 'L' | 20 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 10 |  | 7.49 | 100% | 17.49 | Phy.Completed | Spot Quotation
9 | Construction of Meisatla Futsal Ground at Siaha | 34.79 | Lunglei Building Project Division | 20.03.23 | 20.09.23 | 49% | 17.29 |  | 3.46 | 49% | 20.75 | Work in progress | Spot Quotation
10 | Construction of Futsal Playground at Gov't Higher secondary School at Siaha | 34.79 | Lunglei Building Project Division | 20.03.23 | 20.09.23 | 90% |  | 10% | 31.3 | 100% | 31.3 | Work in progress | Spot Quotation
11 | Construction of New Football ground at Ramlaitui | 20 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 99% |  | 1% |  | 100% |  | Work in progress | Spot Quotation
12 | Construction of New Football Ground at Haulawng | 20 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 9.75 |  | 9.69 | 100% | 19.44 | Phy.Completed | Spot Quotation
13 | Construction of New Football Ground at Mualthuam 'N' | 20 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 9.75 |  | 10.07 | 100% | 19.82 | Phy.Completed | Spot Quotation
14 | Construction of New Football Ground at Mualthuam 'N' (on going) | 10 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 4.9 |  | 4.91 | 100% | 9.81 | Phy.Completed | Spot Quotation
15 | Construction of New Football Ground at Haulawng ( on going ) | 10 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 4.9 |  | 4.81 | 100% | 9.71 | Phy.Completed | Spot Quotation
16 | Construction of New Football Ground at Rawpui | 15 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% |  |  | 6.37 | 100% | 6.37 | Phy.Completed | Spot Quotation
17 | Construction of Community Hall at Pukpui | 80 | Lunglei Building Project Division | 20.03.23 | 20.03.24 | 98% | 2.21 |  |  | 98% | 2.21 | Work in progress | Spot Quotation
18 | Construction of New Badminton Hall at Chhipphir | 20 | Lunglei Building Project Division | 20.03.23 | 20.09.23 | 100% | 0.55 |  | 15.67 | 100% | 16.22 | Phy.Completed | Spot Quotation
19 | Renovation of Community Hall at Farm Veng | 10 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 5 |  | 0.7 | 100% | 5.7 | Phy.Completed | Spot Quotation
20 | Renovation of Community Hall at Zobawk 'S' | 10 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 5 |  |  | 100% | 5 | Phy.Completed | Spot Quotation
21 | Renovation of Sport recreation House ( TT Hall) at Zobawk 'N' at Zobawk Bazar | 10 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 5 |  |  | 100% | 5 | Phy.Completed | Spot Quotation
22 | Painting & Electrification of Zobawk 'N' Hall | 12 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 0.31 |  |  | 100% | 0.31 | Phy.Completed | Spot Quotation
23 | Land development & Earthwork for Community Hall at Ralvawng | 10 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 5 |  | 0.27 | 100% | 5.27 | Phy.Completed | Spot Quotation
24 | Renovation of Community Hall at Leite | 5 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 2.5 |  | 2.36 | 100% | 4.86 | Phy.Completed | Spot Quotation
25 | Renovation of Public NGO's House at Leite | 5 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 2.5 |  | 2.5 | 100% | 5 | Phy Completed | Spot Quotation
26 | Renovation of Community Hall at Rotlang 'E' | 5 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 2.5 |  | 2.5 | 100% | 5 | Phy.Completed | Spot Quotation
27 | Completion of Community Hall at Dawn | 8 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 0.22 |  | 4.88 | 100% | 5.1 | Phy.Completed | Spot Quotation
28 | Construction of Community Hall at Zehtet | 30 | Lunglei Building Project Division | 20.03.23 | 20.09.23 | 100% | 0.82 |  | 8.06 | 100% | 8.88 | Phy.Completed | Spot Quotation
29 | Construction of Community Hall at Lungrang 'S' | 40 | Lunglei Building Project Division | 20.03.23 | 20.03.24 | 36% | 1.1 | 4% |  | 40% | 1.1 | Work in progress | Spot Quotation
30 | Construction of Community Hall | 12 | Lunglei Building Project Division | 20.03.23 | 20.09.23 | 100% | 6 |  | 5.99 | 100% | 11.99 | Phy.Completed | Spot Quotation
31 | Construction of Community Hall at Chhumkhum | 27.47 | Lunglei Building Project Division | 20.03.23 | 20.09.23 | 100% | 13.75 |  | 13.71 | 100% | 27.46 | Phy Completed | Spot Quotation
32 | Construction of Community Hall at New Sachan | 27.47 | Lunglei Building Project Division | 20.03.23 | 20.09.23 | 100% | 13.75 |  | 13.71 | 100% | 27.46 | Phy.Completed | Spot Quotation
33 | Construction of Public Recreation House at Chanmari, Lunglei | 10 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 5 |  |  | 100% | 5 | Phy.Completed | Spot Quotation
34 | Construction of Old Aged Home cum Library House at Community Hall at Ramthar, Lunglei | 15 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 7.5 |  |  | 100% | 7.5 | Phy.Completed | Spot Quotation
35 | Construction of Women Recreation House or Cemetary House at Electric veng Lunglei (Women recreation house) | 10 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 6.91 |  | 3.08 | 100% | 9.99 | Phy.Completed | Spot Quotation
36 | Construction of NGO's House cum Library Room at Zobawk 'S' Vengthar | 10 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 5 |  | 0.28 | 100% | 5.28 | Phy.Completed | Spot Quotation
37 | Completion of NGO's Recreation House at Lungpuizawl | 5 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 2.64 |  | 2.35 | 100% | 4.99 | Phy.Completed | Spot Quotation
38 | Renovation of Women Recreation House at Lower Ramthar, Lunglei | 5 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 2.64 |  |  | 100% | 2.64 | Phy.Completed | Spot Quotation
39 | Construction of Waiting Shed & Godown of Animal Feed Building at dawn | 5 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 2.64 |  | 2.35 | 100% | 4.99 | Phy.Completed | Spot Quotation
40 | Construction of Women Recreation House at Upper Ramthar, Lunglei | 15 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 7.5 |  |  | 100% | 7.5 | Phy.Completed | Spot Quotation
41 | Construction of NGO's Recreation house at Farm Veng, lunglei | 10 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 3.97 |  | 5.24 | 100% | 9.21 | Phy.Completed | Spot Quotation
42 | Construction of Clinic Center Building at Bungtlang W | 5 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 2.5 |  | 2.5 | 100% | 5 | Phy.Completed | Spot Quotation
43 | Rahsiveng Market Shed | 52 | Lunglei Building Project Division | 20.03.23 | 20.09.23 | 100% | 26 |  | 22.58 | 100% | 48.58 | Phy Completed | Spot Quotation
Construction of Public Toilet, Cemetary House, Waiting Shed, Water Supply & Footpath at Lunglei and Bunghmun
44 | Constructuion of Toilet and Water Pint at Kawmzawl Helipad, aizawl to lunglei Helicopter service Station | 15 | Lunglei Building Project Division | 20.03.23 | 20.09.23 | 100% | 7.5 |  |  | 100% | 7.5 | Phy.Completed | Spot Quotation
45 | Construction of Cemetary House at Chanmari, Lunglei | 15 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 7.5 |  | 0.5 | 100% | 8 | Phy.Completed | Spot Quotation
46 | Construction of Fencing & Cement Flooring at YMA hall courtyard at Electric Veng, Lunglei | 15 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 7.5 |  | 7.49 | 100% | 14.99 | Phy.Completed | Spot Quotation
47 | Construction of Public Store house and Urinal Shed at Electric Veng, Lunglei | 15 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 0.2 |  | 2.35 | 100% | 2.55 | Phy.Completed | Spot Quotation
48 | Construction of Waiting Shed near PWD Turning Point | 10 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 5 |  | 4.99 | 100% | 9.99 | Phy.Completed | Spot Quotation
49 | Estimate for Construction of Cemetary House at College Veng, lunglei | 5 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 2.5 |  | 2.49 | 100% | 4.99 | Phy.Completed | Spot Quotation
50 | Construction of Cemetary House at Bazar Veng Thlanmual No. 3 | 5 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 2.5 |  | 2.49 | 100% | 4.99 | Phy.Completed | Spot Quotation
51 | Construction of Boat Waiting shed at New Sachan | 0.69 | Lunglei Building Project Division | 20.03.23 | 20.05.23 | 100% | 0.37 |  | 0.31 | 100% | 0.68 | Phy.Completed | Spot Quotation
52 | Construction of Waiting near border Fencing inside India at Terabonia | 10.8 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 0.93 |  | 0.45 | 100% | 1.38 | Phy.Completed | Spot Quotation
53 | Construction of Boat Waiting Shed at Tuikawi | 0.69 | Lunglei Building Project Division | 20.03.23 | 20.05.23 | 100% | 0.37 |  | 0.31 | 100% | 0.68 | Phy.Completed | Spot Quotation
54 | Construction of Boat Waiting Shed at Sumasuri | 0.69 | Lunglei Building Project Division | 20.03.23 | 20.05.23 | 100% | 0.37 |  | 0.31 | 100% | 0.68 | Phy.Completed | Spot Quotation
55 | Construction of Boat waiting Shed at Old Sachan | 0.69 | Lunglei Building Project Division | 20.03.23 | 20.05.23 | 100% | 0.35 |  | 0.31 | 100% | 0.66 | Phy.Completed | Spot Quotation
56 | Construction of Waiting shed at Bungkawn, Lungchem | 0.69 | Lunglei Building Project Division | 20.03.23 | 20.05.23 | 100% | 0.35 |  | 0.31 | 100% | 0.66 | Phy.Completed | Spot Quotation
57 | Construction of Public Urinal near Vanlalhriara's House at Changpui | 0.73 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 0.37 |  | 0.33 | 100% | 0.7 | Phy.Completed | Spot Quotation
58 | Construction of Public Urinal near Hrangthuama's House at Changpui | 0.73 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 0.37 |  | 0.33 | 100% | 0.7 | Phy.Completed | Spot Quotation
59 | Construction of Urinal near Vanlalpianga's House at Dengsur | 0.73 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 0.37 |  | 0.33 | 100% | 0.7 | Phy.Completed | Spot Quotation
60 | Construction of Urinal near Thanthianga's House at Dengsur | 0.73 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 0.37 |  | 0.33 | 100% | 0.7 | Phy.Completed | Spot Quotation
61 | Construction of Urinal near Community Hall at Dengsur | 0.73 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 0.37 |  | 0.33 | 100% | 0.7 | Phy.Completed | Spot Quotation
62 | construction of Waiting Shed at Mangkhan Kawn, Dengsur | 10.8 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 0.53 |  | 0.45 | 100% | 0.98 | Phy.Completed | Spot Quotation
63 | Construction of Waiting shed at sabual & Dengsur Boundary. | 10.8 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 0.53 |  | 0.45 | 100% | 0.98 | Phy.Completed | Spot Quotation
64 | Construction of Waiting Shed near K.Vanlalruata's House at S.Khawlek | 1.08 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 0.53 |  | 0.45 | 100% | 0.98 | Phy.Completed | Spot Quotation
65 | Construction of Public Urinal near Information Centre Building at S.Khawlek | 0.73 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 0.37 |  | 0.33 | 100% | 0.7 | Phy.Completed | Spot Quotation
66 | Construction of Waiting shed at Dampui | 1.08 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 0.53 |  | 0.45 | 100% | 0.98 | Phy.Completed | Spot Quotation
67 | Construction of Cemetary House at Thenhlum | 0.76 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 0.38 |  | 0.35 | 100% | 0.73 | Phy.Completed | Spot Quotation
68 | Construction of Waiting Shed at Tawngtaina Hmun Zawlpui | 1.08 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 0.53 |  | 0.45 | 100% | 0.98 | Phy.Completed | Spot Quotation
69 | Construction of Public Urinal at Tawngtaina hmun at Zawlpui | 0.73 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 0.37 |  | 0.33 | 100% | 0.7 | Phy.Completed | Spot Quotation
70 | Construction of Bus Waiting Shed near Thantluanga's House at Belthei | 0.88 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 0.44 |  | 0.4 | 100% | 0.84 | Phy.Completed | Spot Quotation
71 | Construction of Waiting Shed at Tuisenchhuah | 10.8 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 0.53 |  | 0.45 | 100% | 0.98 | Phy.Completed | Spot Quotation
72 | Construction of Cemetary House at Rangte | 0.76 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 0.38 |  | 0.35 | 100% | 0.73 | Phy.Completed | Spot Quotation
73 | Stainless Steel Railling with Checker Tiles | 6 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 3 |  | 2.85 | 100% | 5.85 | Phy.Completed | Spot Quotation
74 | River view & Resting shed. ( Tlabung) | 9.5 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 4.75 |  |  | 100% | 4.75 | Phy.Completed | Spot Quotation
75 | Urinal Building with Side Drain Cover (Tlabung) | 5 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 2.5 |  | 2.5 | 100% | 5 | Phy.Completed | Spot Quotation
76 | Lowering of Siahatla field at Siaha | 35.97 | Lunglei Building Project Division | 20.03.23 | 20.03.24 | 100% | 18 |  | 16.91 | 100% | 34.91 | Phy.Completed | Spot Quotation
77 | Construction of Bazar Shed at Tuichawng | 5 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 2.5 |  | 2.29 | 100% | 4.79 | Phy.Completed | Spot Quotation
78 | Construction of MHIP Building at Bunghmun | 17.71 | Lunglei Building Project Division | 20.03.23 | 20.09.23 | 100% | 8.8 |  | 8.9 | 100% | 17.7 | Phy.Completed | Spot Quotation
79 | Construction of Anganwadi Centre at Zodin | 4.5 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 4.5 |  |  | 100% | 4.5 | Completed | Spot Quotation
80 | Construction of Playground at Chawngte 'L' | 40 | Lunglei Building Project Division | 20.03.23 | 20.09.23 | 100% | 19.62 |  |  | 100% | 19.62 | Phy.Completed | Spot Quotation
81 | Construction of Anganwadi Centre at Mauzam | 4.02 | Lunglei Building Project Division | 20.03.23 | 20.09.23 | 90% | 2.12 | 10% | 1.89 | 100% | 4.01 | Work in progress | Spot Quotation
82 | Construction of Anganwadi Centre at Tuisenchhuah | 9 | Lunglei Building Project Division | 20.03.23 | 20.09.23 | 90% | 4.5 | 10% | 4.49 | 90% | 8.99 | Work in progress | Spot Quotation
83 | Construction of MUP Building at Thenhlum | 9 | Lunglei Building Project Division | 20.03.23 | 20.09.23 | 100% | 4.5 |  | 4.63 | 100% | 9.13 | Phy.Completed | Spot Quotation
A. Construction of Government Building at Hnahthial, PWD EE Quarters, Circuit House & DC office under SASCI 2023-2024
84 | Const. of PWD EE Quarters at Hnahthial. | 150 | Lunglei Building Project Division | 23.03.23 | 23.03.26 | [6 empty] | Work not yet started | Spot Quotation
85 | Hnahthial Circuit House. | 200 | Lunglei Building Project Division | 23.03.23 | 23.03.26 |  |  | 20% |  | 20% |  | Work in progress | Spot Quotation
B. Construction of Community Hall at Siasi, Phurai, Tawngkawlong, Tipa B, Meisavaih, Amotlah.
86 | Const. and Completion of MTP(H) Office. | 10 | Lunglei Building Project Division | 23.03.24 | 23.07.25 | [6 empty] | Work not yet started | Spot Quotation
87 | Const. of MTP Information Office | 15 | Lunglei Building Project Division | 23.03.24 | 23.07.25 |  |  | 10% |  | 10% |  | Work in progress | Spot Quotation
88 | Const. of Bazar Shed at New Siaha East-II | 17 | Lunglei Building Project Division | 23.03.24 | 23.07.25 | [6 empty] | Work not yet started | Spot Quotation
89 | Continuation of MYA Hall at New Siaha East-I | 20 | Lunglei Building Project Division | 23.03.24 | 23.07.25 |  |  | 15% |  | 15% |  | Work in progress | Spot Quotation
90 | Const. of MTP Hall and Retaining Wall at Amotlah. | 20 | Lunglei Building Project Division | 23.03.24 | 23.07.25 |  |  | 15% |  | 15% |  | Work in progress | Spot Quotation
91 | Const. of Model Middle School Ground and Retaining Wall at New Siaha West-I | 15 | Lunglei Building Project Division | 23.03.24 | 23.07.25 |  |  | 100% |  | 100% |  | Completed | Spot Quotation
92 | Const. of Retaining Wall at Futsal Ground at Tuipui Ferry. | 10 | Lunglei Building Project Division | 23.03.24 | 23.07.25 |  |  | 100% |  | 100% |  | Completed | Spot Quotation
C. Construction of Playground with Pavillion at Lungtian, Sangau, Bualpui(NG), Tuichawngtlang, Ngunlingkhua, T.Dumzau.
93 | Renovation of Community Hall Ramhlun Veng, Sangau. | 30 | Lunglei Building Project Division | 23.03.24 | 23.07.25 |  |  | 60% |  | 60% |  | Work in progress | Spot Quotation
94 | Const. of Community Hall at Council Veng, Lawngtlai. | 30 | Lunglei Building Project Division | 23.03.24 | 23.07.25 | [6 empty] | Work not yet started | Spot Quotation
95 | Vertical Extention of Central Young Lai Association Office, Lawngtlai. | 10 | Lunglei Building Project Division | 23.03.24 | 23.07.25 | [6 empty] | Work not yet started | Spot Quotation
96 | Const. of Futsal Ground at Lungtian-I | 30 | Lunglei Building Project Division | 23.03.24 | 23.07.25 |  |  | 45% |  | 45% |  | Work in progress | Spot Quotation
97 | Const. of Futsal Ground at Bualpui (NG) | 30 | Lunglei Building Project Division | 23.03.24 | 23.07.25 |  |  | 20% |  | 20% |  | Work in progress | Spot Quotation
98 | Const. of Futsal Ground at Sangau. | 30 | Lunglei Building Project Division | 23.03.24 | 23.07.25 |  |  | 30% |  | 30% |  | Work in progress | Spot Quotation
99 | Const. of Volleyball Court at Lungzalhtum. | 10 | Lunglei Building Project Division | 23.03.24 | 23.07.25 |  |  | 90% |  | 90% |  | Work in progress | Spot Quotation
D. Construction of Community Hall Cum Market Building at Luangmual, Lunglei.
100 | Const. of DM High School Building (Theiriat) | 35 | Lunglei Building Project Division | 23.03.24 | 23.07.25 | [6 empty] | Work not yet started | Spot Quotation
101 | Const. of Luangmual Market Building, Lunglei | 80 | Lunglei Building Project Division | 23.03.24 | 23.07.25 |  |  | 25% |  | 25% |  | Work in progress | Spot Quotation
102 | Const. of Sairep Community Hall | 20 | Lunglei Building Project Division | 23.03.24 | 23.07.25 |  |  | 2% |  | 2% |  | Work in progress | Spot Quotation
E. Vertical Extention of Market Building at Kamalanagar.
103 | Vertical Extention of Existing Bazar Building at Kamalanagar-I with Tin Roofing. | 50 | Lunglei Building Project Division | 23.03.24 | 23.07.25 | [6 empty] | Work not yet started | Spot Quotation
104 | Const. of Additional Bazar Building by Demolishing the existing dilapidated building that was constructed under BADP | 50 | Lunglei Building Project Division | 23.03.24 | 23.07.25 | [6 empty] | Work not yet started | Spot Quotation
105 | 2.Const. of Rest House at PWD Complex Bunghmun. | 24.52 | Lunglei Building Project Division | 23.03.24 | 23.07.25 | [6 empty] | Work not yet started | Spot Quotation
F. Construction of Community Hall Cum Health Clinic Center at Kawlhawk, Bungtlang West, South Lungdai and Serte.
106 | Const. of Higher Secondary School Building, Buarpui. | 30 | Lunglei Building Project Division | 23.03.24 | 23.07.25 | [6 empty] | Work not yet started | Spot Quotation
107 | Const. of Community Hall, Kawlhawk | 30 | Lunglei Building Project Division | 23.03.24 | 23.07.25 | [6 empty] | Work not yet started | Spot Quotation
108 | Const. of Health Clinic Bungtlang West. | 10 | Lunglei Building Project Division | 23.03.24 | 23.07.25 | [6 empty] | Work not yet started | Spot Quotation
109 | PWD IB repair, Sertlangpui | 5 | Lunglei Building Project Division | 23.03.24 | 23.07.25 | [6 empty] | Work not yet started | Spot Quotation
110 | Const. of Badminton Hall at Chhipphir. | 5 | Lunglei Building Project Division | 23.03.24 | 23.07.25 | [6 empty] | Work not yet started | Spot Quotation
111 | Completion of Badminton Hall at Chhipphir | 5 | Lunglei Building Project Division | 23.03.24 | 23.07.25 | [6 empty] | Work not yet started | Spot Quotation
112 | Anganwadi Centre-I, Sertlangpui | 5 | Lunglei Building Project Division | 23.03.24 | 23.07.25 | [6 empty] | Work not yet started | Spot Quotation
113 | Anganwadi Centre-I New Const. Serte. | 5 | Lunglei Building Project Division | 23.03.24 | 23.07.25 | [6 empty] | Work not yet started | Spot Quotation
114 | Health and Wellness Officer Quarter new const. Serte | 5 | Lunglei Building Project Division | 23.03.24 | 23.07.25 | [6 empty] | Work not yet started | Spot Quotation
115 | Health Clinic Office, South Lungdai | 10 | Lunglei Building Project Division | 23.03.24 | 23.07.25 | [6 empty] | Work not yet started | Spot Quotation
116 | Const. of Futsal Ground Flooring at Lalveng, Haulawng. | 5 | Lunglei Building Project Division | 23.03.24 | 23.07.25 | [6 empty] | Work not yet started | Spot Quotation
AIZAWL ROAD NORTH DIVISION
1. CONSTRUCTION AND UPGRADATION OF ROAD FROM BAWNGKAWN TO RAMHLUN NORTH, AIZAWL
RAMHLUN NORTH
117 | Extension of Slab Culvert Side drain with cover Near Pi Duhawmi House at Ramhlun North | 0.81 | Aizawl Road North Division | g | 27.03.23 | 100% | 0.81 |  |  | 100% | 0.81 | Completed | Spot Quotation
118 | Construction of RCC Balcony Vety Qtr to Pu Lalrinsanga House Ramhlun North Basic Mual at Ramhlun North | 29.55 | Aizawl Road North Division | 14.02.23 | 03.07.23 | 100% | 29.55 |  |  | 100% | 29.55 | Completed | Spot Quotation
119 | Construction of PCC Pavement on AMC road Ramhlun North | 4.52 | Aizawl Road North Division | 27.03.23 | 29.04.23 | 100% | 4.52 |  |  | 100% | 4.52 | Completed | Spot Quotation
120 | Construction of Breast Wall near Pi Lalthlamuani at Ramhlun North | 2.49 | Aizawl Road North Division | 28.02.23 | 15.03.23 | 100% | 2.49 |  |  | 100% | 2.49 | Completed | Spot Quotation
121 | Construction of Retaining wall near Pi Duhawmi at Ramhlun North | 3.57 | Aizawl Road North Division | 15.03.23 | 22.03.23 | 100% | 3.57 |  |  | 100% | 3.57 | Completed | Spot Quotation
122 | Construction of Retaining Wall near Pi Thangluri at Ramhlun North | 7.66 | Aizawl Road North Division | 17.02.23 | 23.03.23 | 100% | 7.66 |  |  | 100% | 7.66 | Completed | Spot Quotation
RAMHLUN SOUTH
123 | Cons.of Side drain with cover steel on Centenary Tuikhur to rev.Vanlalbuaia House On Carmel road at Ramhlun South | 19.26 | Aizawl Road North Division | 15.02.23 | 25.03.23 | 100% | 19.26 |  |  | 100% | 19.26 | Completed | Spot Quotation
124 | Const.of RCC Rectangular Side drain with cover on Bawngkawn to ITI road at Ramhlun South | 30.88 | Aizawl Road North Division | 13.02.23 | 05.06.23 | 100% | 30.88 |  |  | 100% | 30.88 | Completed | Spot Quotation
125 | Const.of RCC Rectanggular Side drain with cover on Thlanmual to Darnam Lui at Ramhlun South | 10.05 | Aizawl Road North Division | 24.02.23 | 04.04.23 | 100% | 10.05 |  |  | 100% | 10.05 | Completed | Spot Quotation
126 | Const.of Retaining wall near Pu Rohnuna Varte house at Ramhlun South | 8.22 | Aizawl Road North Division | 23.02.23 | 25.03.23 | 100% | 8.22 |  |  | 100% | 8.22 | Completed | Spot Quotation
127 | Construction of RCC Retaining wall near Ralhnehthanga House at Ramhlun South | 5.22 | Aizawl Road North Division | 21.02.23 | 14.03.23 | 100% | 5.22 |  |  | 100% | 5.22 | Completed | Spot Quotation
RAMHLUN VENGLAI
128 | Const.of RCC Rectangular side drain with cover on Approach Road to NHC office near Lalnghakliani to Pi Vanhnuaithangi House at Ramhlun Venglai | 2.68 | Aizawl Road North Division | 17.04.23 | 28.04.23 | 100% | 2.68 |  |  | 100% | 2.68 | Completed | Spot Quotation
129 | Const.of RCC Rectangular side drain with cover Near Pu mabiaka House at Ramhlun Venglai | 6.12 | Aizawl Road North Division | 15.02.23 | 28.04.23 | 100% | 6.12 |  |  | 100% | 6.12 | Completed | Spot Quotation
130 | Const.of RCC Rectangular side drain with cover on Ramhlun Venglai PCI to PC.Vanlalena House at Ramhlun Venglai | 7.05 | Aizawl Road North Division | 20.02.23 | 18.03.23 | 100% | 7.05 |  |  | 100% | 7.05 | Completed | Spot Quotation
131 | Const.of RCC Rectangular side drain with cover near H.Lalbiakmawia House at Ramhlun Venglai | 3.02 | Aizawl Road North Division | 28.02.23 | 13.03.23 | 100% | 3.02 |  |  | 100% | 3.02 | Completed | Spot Quotation
132 | Const.of Steel cross drain near H.lalbiakmawia House (Lower) at Ramhlun Venglai | 0.75 | Aizawl Road North Division | 14.03.23 | 20.03.23 | 100% | 0.75 |  |  | 100% | 0.75 | Completed | Spot Quotation
133 | Const.of Widening & Breast Wall on Approach Road to NHC Office near Pi Lalnghakliani House to Pi Vanhnuaithangi House at Ramhlun Venglai | 15.88 | Aizawl Road North Division | 15.03.23 | 14.04.23 | 100% | 15.88 |  |  | 100% | 15.88 | Completed | Spot Quotation
134 | Const.of Breast Wall Extension with Side Drain on DIC Office at Ramhlun Venglai at Ramhlun Venglai | 13.1 | Aizawl Road North Division | 20.03.23 | 19.05.23 | 100% | 13.1 |  |  | 100% | 13.1 | Completed | Spot Quotation
RAMHLUN VENGTHAR
135 | Const.of RCC Rectangular side drain with cover near Ramhlun Vengthar taxi stand at Ramhlun Vengthar | 6.53 | Aizawl Road North Division | 15.02.23 | 24.02.23 | 100% | 6.53 |  |  | 100% | 6.53 | Completed | Spot Quotation
136 | Const.of RCC Rectangular side drain with cover on Tluangpui road (Pu lalthawmliana to Cosma Mantluanga House) at Ramhlun Vengthar | 4.71 | Aizawl Road North Division | 17.02.23 | 03.03.23 | 100% | 4.71 |  |  | 100% | 4.71 | Completed | Spot Quotation
137 | Const.of RCC Rectangular side drain with cover on Zohmasawna House to bangla Lui at ramhlun Vengthar | 6.63 | Aizawl Road North Division | 21.02.23 | 13.03.23 | 100% | 6.63 |  |  | 100% | 6.63 | Completed | Spot Quotation
138 | Const.of RCC Rectangular side drain with cover on Sihpui to Ramhlun Vengthar Bus turning point at Ramhlun Vengthar | 11.23 | Aizawl Road North Division | 14.03.23 | 31.03.23 | 100% | 11.23 |  |  | 100% | 11.23 | Completed | Spot Quotation
139 | Const.of RCC Rectangular Cross drain with cover near Waiting Shed at Ramhlun Vengthar | 0.75 | Aizawl Road North Division | 17.03.23 | 23.03.23 | 100% | 0.75 |  |  | 100% | 0.75 | Completed | Spot Quotation
140 | Const.of Link drain near V.Lalvela House at Ramhlun Vengthar | 1.68 | Aizawl Road North Division | 17.02.23 | 22.02.23 | 100% | 1.68 |  |  | 100% | 1.68 | Completed | Spot Quotation
RAMHLUN SPORT COMPLEX
141 | Const.of RCC Rectangular Cross drain with cover near B.Lalthlamuana (L) House at Ramhlun Sport Complex | 0.73 | Aizawl Road North Division | 21.03.23 | 25.03.23 | 100% | 0.73 |  |  | 100% | 0.73 | Completed | Spot Quotation
142 | Const.of RCC Rectangular Side drain with cover near B.Lalthlamuana (L) House at Ramhlun Sport Complex | 2.52 | Aizawl Road North Division | 23.02.23 | 14.03.23 | 100% | 2.52 |  |  | 100% | 2.52 | Completed | Spot Quotation
143 | Const.of Link drain near B.Lalthlamuana (L) House at Ramhlun Sport Complex | 1.61 | Aizawl Road North Division | 04.03.23 | 17.03.23 | 100% | 1.61 |  |  | 100% | 1.61 | Completed | Spot Quotation
144 | Const.of steel cross drain near Laldinliana House at Ramhlun Sport Complex | 0.55 | Aizawl Road North Division | 28.02.23 | 18.03.23 | 100% | 0.55 |  |  | 100% | 0.55 | Completed | Spot Quotation
145 | Const.of RCC Rectangular Side drain with cover near Laldinliana House at Ramhlun Sport Complex | 0.7 | Aizawl Road North Division | 17.03.23 | 22.03.23 | 100% | 0.7 |  |  | 100% | 0.7 | Completed | Spot Quotation
146 | Const.of PCC Pavement near ICI road at Ramhlun Sport Complex | 1.4 | Aizawl Road North Division | 18.04.23 | 02.05.23 | 100% | 1.4 |  |  | 100% | 1.4 | Completed | Spot Quotation
147 | Const.of Retaining Wall on ICI road at Ramhlun Sport Complex | 5.83 | Aizawl Road North Division | 12.04.23 | 17.04.23 | 100% | 5.83 |  |  | 100% | 5.83 | Completed | Spot Quotation
148 | Const.of PCC Pavement on Pu Hrekima House to Zohmingsanga House at Ramhlun Sport Complex | 2.53 | Aizawl Road North Division | 28.02.23 | 08.03.23 | 100% | 2.53 |  |  | 100% | 2.53 | Completed | Spot Quotation
149 | Const.of PCC Pavement near Laldinliana House at Ramhlun Sport Complex | 1.69 | Aizawl Road North Division | 31.03.23 | 01.04.23 | 100% | 1.69 |  |  | 100% | 1.69 | Completed | Spot Quotation
150 | Const.of Breast wall near Laldinliana House at Ramhlun Sport Complex | 2.22 | Aizawl Road North Division | 28.02.23 | 14.03.23 | 100% | 2.22 |  |  | 100% | 2.22 | Completed | Spot Quotation
151 | Const.of Retaining wall near Pu Hrekima House at Ramhlun Sport Complex | 2.25 | Aizawl Road North Division | 17.03.23 | 27.03.23 | 100% | 2.25 |  |  | 100% | 2.25 | Completed | Spot Quotation
152 | Const.of Retaining wall on LC Road to Lalfakawmi House at Ramhlun Sport Complex | 1.44 | Aizawl Road North Division | 06.03.23 | 16.03.23 | 100% | 1.44 |  |  | 100% | 1.44 | Completed | Spot Quotation
153 | Const.of Retaining wall near Pu Lingngoa at Ramhlun Sport Complex | 1.54 | Aizawl Road North Division | 09.03.23 | 16.03.23 | 100% | 1.54 |  |  | 100% | 1.54 | Completed | Spot Quotation
154 | Const.of Retaining wall near Kiamlova House at Ramhlun Sport Complex | 7.52 | Aizawl Road North Division | 23.02.23 | 14.03.23 | 100% | 7.52 |  |  | 100% | 7.52 | Completed | Spot Quotation
155 | Const.of Retaining wall block-I on LC road Lianhnuna House to Buchhawna ME School at Ramhlun Sport Complex | 3.69 | Aizawl Road North Division | 27.02.23 | 10.03.23 | 100% | 3.69 |  |  | 100% | 3.69 | Completed | Spot Quotation
156 | Const.of Retaining wall block-II on LC road Lianhnuna House to Buchhawna ME School at Ramhlun Sport Complex | 5.26 | Aizawl Road North Division | 27.02.23 | 17.03.23 | 100% | 5.26 |  |  | 100% | 5.26 | Completed | Spot Quotation
157 | Const.of Retaining wall block-III on LC road Lianhnuna House to Buchhawna ME School at Ramhlun Sport Complex | 7.56 | Aizawl Road North Division | 17.04.23 | 09.05.23 | 100% | 7.56 |  |  | 100% | 7.56 | Completed | Spot Quotation
158 | Const.of Retaining wall block-IV on LC road Lianhnuna House to Buchhawna ME School at Ramhlun Sport Complex | 7.03 | Aizawl Road North Division | 24.02.23 | 17.03.23 | 100% | 7.03 |  |  | 100% | 7.03 | Completed | Spot Quotation
159 | Const.of Retaining wall Near YMA ram at Ramhlun Sport Complex | 7.17 | Aizawl Road North Division | 23.02.23 | 29.03.23 | 100% | 7.17 |  |  | 100% | 7.17 | Completed | Spot Quotation
160 | Const.of Retaining wall Near Bangla Lui at Ramhlun Sport Complex | 13.45 | Aizawl Road North Division | 16.03.23 | 26.04.23 | 100% | 6.73 |  |  | 100% | 13.45 | Completed | Spot Quotation
161 | Const.of Retaining wall Near Bangla Lui Counterford at Ramhlun Sport Complex | 8.84 | Aizawl Road North Division | 06.03.23 | 29.03.23 | 100% | 8.84 |  |  | 100% | 8.84 | Completed | Spot Quotation
162 | Const.of PCC Pavement on Presbyterian Biak In road at Ramhlun Sport Complex Vengthlang | 3.89 | Aizawl Road North Division | 27.02.23 | 07.03.23 | 100% | 3.89 |  |  | 100% | 3.89 | Completed | Spot Quotation
163 | Const.of PCC Pavement on Ramhlun Vengthar road at Ramhlun Sport Complex Vengthlang | 4.11 | Aizawl Road North Division | 13.04.23 | 27.04.23 | 100% | 4.11 |  |  | 100% | 4.11 | Completed | Spot Quotation
164 | Const.of PCC Pavement on Ringzova road to Pu Lalbiakliana House at Ramhlun Sport Complex Vengthlang | 3.89 | Aizawl Road North Division | 07.03.23 | 24.03.23 | 100% | 3.89 |  |  | 100% | 3.89 | Completed | Spot Quotation
BAWNGKAWN SOUTH
165 | Const.of Link drain between Darringaia's House to Lalensanga's House at Bawngkawn 'S' | 9.55 | Aizawl Road North Division | 21.02.23 | 23.03.23 | 100% | 9.55 |  |  | 100% | 9.55 | Completed | Spot Quotation
166 | Const.of Hand Railing for Public Step near Pi Mangkungi House Bawngkawn 'S' | 3.11 | Aizawl Road North Division | 13.02.23 | 25.03.23 | 100% | 3.11 |  |  | 100% | 3.11 | Completed | Spot Quotation
167 | Const.of Hand Railing for Public Step near YMA Hall, Bawngkawn 'S' | 0.81 | Aizawl Road North Division | 13.02.23 | 27.02.23 | 100% | 0.81 |  |  | 100% | 0.81 | Completed | Spot Quotation
168 | Const.of Hand Railing for Public Step near Pu Tlangdingliana House Bawngkawn 'S' | 2.11 | Aizawl Road North Division | 13.02.23 | 25.03.23 | 100% | 2.11 |  |  | 100% | 2.11 | Completed | Spot Quotation
169 | Const.of Hand Railing for Public footpath near YMA Hall, Bawngkawn 'S' | 1.81 | Aizawl Road North Division | 13.02.23 | 25.03.23 | 100% | 1.81 |  |  | 100% | 1.81 | Completed | Spot Quotation
170 | Const.of Retaining wall near YMA Hall, Bawngkawn 'S' | 1.41 | Aizawl Road North Division | 17.03.23 | 20.03.23 | 100% | 1.41 |  |  | 100% | 1.41 | Completed | Spot Quotation
171 | Const.of Retaining wall near transformer on Pu Liansailova road at Bawngkawn 'S' | 1.66 | Aizawl Road North Division | 24.02.23 | 02.03.23 | 100% | 1.66 |  |  | 100% | 1.66 | Completed | Spot Quotation
172 | Construction of PCC Pavement on Pu Liansailova Road at Bawngkawn South | 3.36 | Aizawl Road North Division | 19.02.23 | 24.02.23 | 100% | 3.36 |  |  | 100% | 3.36 | Completed | Spot Quotation
173 | Repair of Side drain near Pu Tlangdingliana House | 0.36 | Aizawl Road North Division | 10.03.23 | 11.03.23 | 100% | 0.36 |  |  | 100% | 0.36 | Completed | Spot Quotation
2. CONSTRUCTION AND UPGRADATION OF ROAD FROM BAWNGKAWN TO RAMHLUN NORTH, AIZAWL, ZARKAWT
174 | Construction of Ahimsa to Jail Veng road at Zarkawt. | 77.98 | Aizawl Road North Division | 02.05.23 | 30.11.23 | 45% | 35.79 | 5% |  | 50% | 35.79 | Work in progress | Spot Quotation
AIZAWL VENGLAI
175 | Construction of of RCC Rectangular Side drain with cover on P.Lalvuana to R.Lalhmachhuana house at Aizawl Venglai | 3.36 | Aizawl Road North Division | 24.02.23 | 17.03.23 | 100% | 3.36 |  |  | 100% | 3.36 | Completed | Spot Quotation
176 | Construction of RCC Rectangular Side drain with cover on Taitea Tuikhur to YMA Hall at Aizawl Venglai | 7.01 | Aizawl Road North Division | 17.02.23 | 25.03.23 | 100% | 7.01 |  |  | 100% | 7.01 | Completed | Spot Quotation
177 | Construction of RCC Rectangular Side drain with cover on Pu Lalhluna House to Pu Nghinglova House at Aizawl Venglai | 1.26 | Aizawl Road North Division | 24.02.23 | 18.04.23 | 100% | 1.26 |  |  | 100% | 1.26 | Completed | Spot Quotation
178 | Construction of RCC Rectangular Side drain with cover on Pu Zosiama Garrage to Pi Lalbiaki House at Aizawl Venglai | 3.36 | Aizawl Road North Division | 20.02.23 | 10.03.23 | 100% | 3.36 |  |  | 100% | 3.36 | Completed | Spot Quotation
179 | Construction of Link drain on Chuangkimi to Benben step at Aizawl Venglai | 1.89 | Aizawl Road North Division | 02.02.23 | 15.03.23 | 100% | 1.89 |  |  | 100% | 1.89 | Completed | Spot Quotation
180 | Construction of Link drain on Pi Rosiami to Pi Lalmuanpuii House at Aizawl Venglai | 2.79 | Aizawl Road North Division | 25.02.23 | 18.03.23 | 100% | 2.79 |  |  | 100% | 2.79 | Completed | Spot Quotation
181 | Construction of Link drain near Pi Chuangkimi House at Aizawl Venglai | 2.7 | Aizawl Road North Division | 10.03.23 | 04.04.23 | 100% | 2.7 |  |  | 100% | 2.7 | Completed | Spot Quotation
182 | Construction of Link drain on Mini market to VDP House at Aizawl Venglai | 3.08 | Aizawl Road North Division | 16.02.23 | 28.02.23 | 100% | 3.08 |  |  | 100% | 3.08 | Completed | Spot Quotation
183 | Construction of V-Shape side drain on Zirtiri College to Pu Saptawnliana House at Aizawl Venglai | 2.68 | Aizawl Road North Division | 21.02.23 | 04.03.23 | 100% | 2.68 |  |  | 100% | 2.68 | Completed | Spot Quotation
184 | Construction of V-Shape side on Pu Sapliantawna to khurpui at Aizawl Venglai | 0.76 | Aizawl Road North Division | 27.02.23 | 18.03.23 | 100% | 0.76 |  |  | 100% | 0.76 | Completed | Spot Quotation
185 | Construction of V-Shape side on Lalnghinglova House to Chuangkimi House at Aizawl Venglai | 1.65 | Aizawl Road North Division | 20.02.23 | 10.03.23 | 100% | 1.65 |  |  | 100% | 1.65 | Completed | Spot Quotation
186 | Construction of V-Shape side drain on K.Zaneiha Garrage to Kawrhpui (Rozami House) at Aizawl Venglai | 2.16 | Aizawl Road North Division | 20.02.23 | 30.05.23 | 100% | 2.16 |  |  | 100% | 2.16 | Completed | Spot Quotation
187 | Construction of of Steel cross drain on near Pu J.Laltanpuia at Aizawl Venglai | 0.75 | Aizawl Road North Division | 21.02.23 | 24.02.23 | 100% | 0.75 |  |  | 100% | 0.75 | Completed | Spot Quotation
188 | Construction of of Steel cross drain on near Pi Chuangkimi House at Aizawl Venglai | 0.58 | Aizawl Road North Division | 21.02.23 | 06.03.23 | 100% | 0.58 |  |  | 100% | 0.58 | Completed | Spot Quotation
189 | Const. of Chequerred tile near MHIP House at Aizawl Venglai | 1.88 | Aizawl Road North Division | 27.02.23 | 08.03.23 | 100% | 1.88 |  |  | 100% | 1.88 | Completed | Spot Quotation
190 | Construction of Link drain cover near Pi Lalchawngpuii House at Aizawl Venglai | 1.88 | Aizawl Road North Division | 20.02.23 | 03.03.23 | 100% | 1.88 |  |  | 100% | 1.88 | Completed | Spot Quotation
191 | Construction of PCC Pavement on Middle School to Biakthuama House at Aizawl Venglai | 0.42 | Aizawl Road North Division | 24.02.23 | 27.02.23 | 100% | 0.42 |  |  | 100% | 0.42 | Completed | Spot Quotation
192 | Construction of Retaining Wall near VDP House at Aizawl Venglai | 0.58 | Aizawl Road North Division | 18.03.23 | 24.03.23 | 100% | 0.58 |  |  | 100% | 0.58 | Completed | Spot Quotation
193 | Const. of Link drain on Lalmuanpuii House to KC.Vanlalruata House at Aizawl Venglai | 1.45 | Aizawl Road North Division | 20.03.23 | 17.04.23 | 100% | 1.45 |  |  | 100% | 1.45 | Completed | Spot Quotation
194 | Construction of Lowering & RCC Pavement near Pu Sangmawia (L) House at Aizawl Venglai | 1.25 | Aizawl Road North Division | 21.02.23 | 23.02.23 | 100% | 1.25 |  |  | 100% | 1.25 | Completed | Spot Quotation
195 | Construction of Chequrred tile near near Basketball Court at Aizawl Venglai | 1.49 | Aizawl Road North Division | 23.02.23 | 03.03.23 | 100% | 1.49 |  |  | 100% | 1.49 | Completed | Spot Quotation
RAMTHAR
196 | Construction of RCC Rectangular side drain with cover on Sihpui Taxi stand to Electric Vengthlang PCI at Ramthar | 9.6 | Aizawl Road North Division | 19.03.23 | 17.04.23 | 100% | 9.6 |  |  | 100% | 9.6 | Completed | Spot Quotation
197 | Construction of RCC Rectangular Cross drain with cover near David Malsawma House at Ramthar | 1.66 | Aizawl Road North Division | 27.03.23 | 21.04.23 | 100% | 1.66 |  |  | 100% | 1.66 | Completed | Spot Quotation
198 | Construction of Breast wall Below Pu K.Lalchawimawia House at Ramthar | 1.37 | Aizawl Road North Division | 21.03.23 | 25.03.23 | 100% | 1.37 |  |  | 100% | 1.37 | Completed | Spot Quotation
199 | Construction of PCC Pavement on Tetea Road | 2.81 | Aizawl Road North Division | 24.03.23 | 10.04.23 | 100% | 2.81 |  |  | 100% | 2.81 | Completed | Spot Quotation
200 | Construction of Retaining Wall near Pu Biakzaua House at Ramthar | 4.24 | Aizawl Road North Division | 06.03.23 | 14.03.23 | 100% | 4.24 |  |  | 100% | 4.24 | Completed | Spot Quotation
201 | Construction of Breast Wall Near C.Zothantluanga House at Ramthar | 1.53 | Aizawl Road North Division | 13.03.23 | 24.03.23 | 100% | 1.53 |  |  | 100% | 1.53 | Completed | Spot Quotation
202 | Construction of Chequrred tile and Hand railing near UPC (NEI) Church at Ramthar | 3.78 | Aizawl Road North Division | 03.03.23 | 23.03.23 | 100% | 3.78 |  |  | 100% | 3.78 | Completed | Spot Quotation
203 | Construction of Breast Wall on Pu Zothansanga Near UPC (MZ) Church Upper Galilie at Ramthar Veng at Ramthar | 3.52 | Aizawl Road North Division | 21.02.23 | 20.03.23 | 100% | 3.52 |  |  | 100% | 3.52 | Completed | Spot Quotation
204 | Construction of Retaining Wall Near Pu Lalhmunsiama House at Ramthar | 4.99 | Aizawl Road North Division | 17.02.23 | 13.03.23 | 100% | 4.99 |  |  | 100% | 4.99 | Completed | Spot Quotation
205 | Construction of Breast Wall Near SH.Lalkhama House at Ramthar | 1.51 | Aizawl Road North Division | 13.03.23 | 18.03.23 | 100% | 1.51 |  |  | 100% | 1.51 | Completed | Spot Quotation
206 | Construction of Retaining Wall Near Cfootpath Sihpui to upper Galilie at Ramthar | 2.63 | Aizawl Road North Division | 13.02.23 | 18.02.23 | 100% | 2.63 |  |  | 100% | 2.63 | Completed | Spot Quotation
207 | Construction of Retaining Wall Near Pu Laltlankima House at Ramthar | 2.93 | Aizawl Road North Division | 28.02.23 | 07.03.23 | 100% | 2.93 |  |  | 100% | 2.93 | Completed | Spot Quotation
208 | Construction of Step, Hand Railing and Widening near Tlangveng Taxi Stand at Ramthar | 2.44 | Aizawl Road North Division | 22.03.23 | 08.04.23 | 100% | 2.44 |  |  | 100% | 2.44 | Completed | Spot Quotation
209 | Construction of Widening and Breast Wall below Bishop House at Ramthar | 7.61 | Aizawl Road North Division | 24.02.23 | 18.03.23 | 100% | 7.61 |  |  | 100% | 7.61 | Completed | Spot Quotation
210 | Construction of Widening and Breast Wall Near Pu Lalbuanga House at Ramthar | 5.45 | Aizawl Road North Division | 13.03.23 | 01.04.23 | 100% | 5.45 |  |  | 100% | 5.45 | Completed | Spot Quotation
211 | Construction of RCC Pavement on Pu Thianghlima House to Pu B.Lalmalsawma House at Ramthar | 4.64 | Aizawl Road North Division | 06.03.23 | 13.03.23 | 100% | 4.64 |  |  | 100% | 4.64 | Completed | Spot Quotation
212 | Construction of Breast Wall Near Republic High School at Ramthar | 1.47 | Aizawl Road North Division | 27.02.23 | 04.03.23 | 100% | 1.47 |  |  | 100% | 1.47 | Completed | Spot Quotation
213 | Construction of Retaining Wall at Chainage 0.100 Kmp on Ramthar Cemetrey to Sihpui via Upper Galilie | 23.17 | Aizawl Road North Division | 06.02.23 | 22.03.23 | 100% | 23.17 |  |  | 100% | 23.17 | Completed | Spot Quotation
214 | Construction of Retaining Wall at Chainage 0.060 Kmp on Ramthar Cemetry to Sihpui via Upper Galilie Pu Lalbuanga House at Ramthar | 14.1 | Aizawl Road North Division | 13.02.23 | 17.04.23 | 100% | 14.1 |  |  | 100% | 14.1 | Completed | Spot Quotation
RAMTHAR NORTH
215 | Construction of RCC Rectangular side drain with cover on Electric Cemetry to Ruali Tuikhur at Ramthar North | 0.87 | Aizawl Road North Division | 15.02.23 | 27.02.23 | 100% | 0.87 |  |  | 100% | 0.87 | Completed | Spot Quotation
216 | Construction of Breast Wall on Tetea Road at Ramthar North | 1.43 | Aizawl Road North Division | 14.03.23 | 21.03.23 | 100% | 1.43 |  |  | 100% | 1.43 | Completed | Spot Quotation
217 | Construction of RCC Balcony near Ruali Tuikhur at Ramthar North | 4.71 | Aizawl Road North Division | 17.02.23 | 22.03.23 | 100% | 4.71 |  |  | 100% | 4.71 | Completed | Spot Quotation
218 | Construction of RCC Balcony on Tetea Road at Ramthar North | 5.4 | Aizawl Road North Division | 16.02.23 | 12.04.23 | 100% | 5.4 |  |  | 100% | 5.4 | Completed | Spot Quotation
219 | Construction of Retaining Wall on Tetea Road at Ramthar North | 11.42 | Aizawl Road North Division | 14.02.23 | 25.03.23 | 100% | 11.42 |  |  | 100% | 11.42 | Completed | Spot Quotation
220 | Construction of Retaining Wall on Near Electric Cemetry at Ramthar North | 7.77 | Aizawl Road North Division | 24.03.23 | 15.04.23 | 100% | 7.77 |  |  | 100% | 7.77 | Completed | Spot Quotation
SARON VENG
221 | Construction of RCC Link Drain with Cover at Saron Veng | 50 | Aizawl Road North Division | 21.03.23 | 30.05.23 | 100% | 50 |  |  | 100% | 50 | Completed | Spot Quotation
25
3. CONSTRUCTION AND UPGRADATION OF ROAD FROM TUITHIANG - CHHINGA VENG - ARMED VENG - CHITE, AIZAWL
222 | Construction of PCC Pavement on District Jail to Lower Armed Veng Road (Service Road) | 68 | Aizawl Road North Division | 14.01.23 | 25.02.23 | 100% | 68 |  |  | 100% | 68 | Completed | Spot Quotation
223 | Construction of Concrete Pavement on Dawrpui Cemetery Internal Road betweenn Pu Thangdanga's House to Lalkima Sailo Site Junction | 16 | Aizawl Road North Division | 23.01.23 | 11.02.23 | 100% | 16 |  |  | 100% | 16 | Completed | Spot Quotation
224 | Construction of Concrete Pavement on District Jail to CRPF Road | 16 | Aizawl Road North Division | 16.01.23 | 04.02.23 | 100% | 16 |  |  | 100% | 16 | Completed | Spot Quotation
225 | Construction of New Road from Pu Lalhmingliana Sailo House to Pu Siamphunga Lei at Tuithiang Veng | 50 | Aizawl Road North Division | 17.02.23 | 17.07.23 | 100% | 50 |  |  | 100% | 50 | Completed | Spot Quotation
[12 empty] | Completed | Spot Quotation
[12 empty] | Completed | Spot Quotation
[12 empty] | Completed | Spot Quotation
[12 empty] | Completed | Spot Quotation
[12 empty] | Completed | Spot Quotation
226 | Consrtuction of Concrete Pavement on C.P Road chite Veng | 50 | Aizawl Road North Division | 14.02.23 | 15.05.23 | 100% | 50 |  |  | 100% | 50 | Completed | Spot Quotation
[12 empty] | Completed | Spot Quotation
[12 empty] | Completed | Spot Quotation
[12 empty] | Completed | Spot Quotation
[12 empty] | Completed | Spot Quotation
227 | Construction of RCC Balcony on Bethany Road at Chhinga Veng | 50 | Aizawl Road North Division | 20.02.23 | 02.08.23 | 100% | 50 |  |  | 100% | 50 | Completed | Spot Quotation
228 | Construction of Retaining Wall at Armed Veng near Pu lalkima House | 22 | Aizawl Road North Division | 23.01.23 | 18.02.23 | 100% | 22 |  |  | 100% | 22 | Completed | Spot Quotation
11
4. CONSTRUCTION CHECK DAM AT THEIHAI LUI, ARMED VENG
229 | Counterfort Retaining Wall at Armed Veng | 41.22 | Aizawl Road North Division |  |  | 25% |  | 55% |  | 80% |  | Work in progress | Spot Quotation
230 | Toe Walls at Armed Veng side | 31.44 | Aizawl Road North Division |  |  |  |  | 15% |  | 15% |  | Work in progress | Spot Quotation
231 | Retaining Wall at Ramthar side | 30.21 | Aizawl Road North Division |  |  | 15% |  | 35% |  | 50% |  | Work in progress | Spot Quotation
232 | Counterfort Retaining Wall at Canara Bank | 43.62 | Aizawl Road North Division | 24.04.23 |  | 100% | 43.62 |  |  | 100% | 43.62 | Completed | Spot Quotation
233 | Retaining Wall at Canara Bank Bridge | 23.06 | Aizawl Road North Division |  |  | 100% | 23.06 |  |  | 100% | 23.06 | Completed | Spot Quotation
234 | Const.of Breast Wall on Bazar Bungkawn to Chite Road near 1st Battalion MAP One Gate Armed Veng | 4.93 | Aizawl Road North Division | 11.02.23 | 14.03.23 | 100% | 4.93 |  |  | 100% | 4.93 | Completed | Spot Quotation
235 | Construction of RCC Link Drain near Pu Phirthanga's House | 24.79 | Aizawl Road North Division |  |  | 60% |  | 40% | 24.79 | 100% | 24.79 | Completed | Spot Quotation
236 | Const.of RCC Link Drain between Pu Lalrinsanga Hmar House to Pu Lalhuliana's House | 12.09 | Aizawl Road North Division | 04.09.23 |  | 100% |  |  | 12.09 | 100% | 12.09 | Completed | Spot Quotation
237 | Const.of RCC Link Drain between Pu Ralkapa's House to Pu Darchhunga's House | 11.65 | Aizawl Road North Division |  |  | 100% | 11.65 |  |  | 100% | 11.65 | Completed | Spot Quotation
238 | Const.of RCC Link Drain Pu Lalhmingthanga's House | 12.48 | Aizawl Road North Division | 02.08.23 | 30.08.23 | 100% | 12.48 |  |  | 100% | 12.48 | Completed | Spot Quotation
239 | Const.of RCC Link Drain Pu Lalhmingthanga's House | 13.87 | Aizawl Road North Division | 04.09.23 | 15.11.23 | 100% | 13.87 |  |  | 100% | 13.87 | Completed | Spot Quotation
240 | Const.of RCC Link Drain near Pu Rallianzuala's Land | 50.65 | Aizawl Road North Division |  |  | 30% |  | 60% |  | 90% |  | Work in progress
SUB-DIVISION-II
241 | Construction of Link Drain from Lalzarliana at High School Veng at Zemabawk | 6.4 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 6.4 |  |  | 100% | 6.4 | Completed | Spot Quotation
242 | Construction of Masonry Step from Pi Zahmingthangi to Dr.Robert Khawlhring Residence at Zemabawk | 7.51 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 7.51 |  |  | 100% | 7.51 | Completed | Spot Quotation
243 | Const.of Link Drain at Mellimual 2 Tuikhur at Zemabawk | 6.4 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 6.4 |  |  | 100% | 6.4 | Completed | Spot Quotation
244 | Construction of Slab Culvert Near Vety Dispensary at Zemabawk | 8.42 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 8.42 |  |  | 100% | 8.42 | Completed | Spot Quotation
245 | Construction of Link drain Near Lalrinmawia Residence at Zemabawk | 4.06 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 4.06 |  |  | 100% | 4.06 | Completed | Spot Quotation
246 | Construction of Side Drain with Cover at Approach Road to Cancer Hospital, Zemabawk | 3.71 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 3.71 |  |  | 100% | 3.71 | Completed | Spot Quotation
247 | Construction of Slab Culvert Including Cross Drainage Dinthar Veng at Zemabawk | 2.03 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 2.03 |  |  | 100% | 2.03 | Completed | Spot Quotation
248 | Construction of U-Shape Side Drain with Cover near Zemabawk North Biak In | 4.24 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 4.24 |  |  | 100% | 4.24 | Completed | Spot Quotation
249 | Construction of Slab Culvert (2 Nos) at Berawlui to Thlanmual to Berawlui School | 12.18 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 12.18 |  |  | 100% | 12.18 | Completed | Spot Quotation
250 | Construction of Slab Culvert including Link Drain at Middle School Veng, Zemabawk | 27 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 27 |  |  | 100% | 27 | Completed | Spot Quotation
251 | Strengthening of Bethel Veng to High School Veng at Zemabawk | 36.7 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 36.7 |  |  | 100% | 36.7 | Completed | Spot Quotation
252 | Construction of of RCC Frame Retaining Wall Including Concrete Pavement on Approach Road to Zemabawk Thlanmual No.1 | 12 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 12 |  |  | 100% | 12 | Completed | Spot Quotation
253 | Construction of Rertaining Wall on Zemabawk Borth Field | 2.8 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 2.8 |  |  | 100% | 2.8 | Completed | Spot Quotation
254 | Construction of RCC Frame Retaining Wall Beneath Zemabawk Thlanmual | 9.9 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 9.9 |  |  | 100% | 9.9 | Completed | Spot Quotation
255 | Patch repiar & Seal Coating of approach road to cancer Hospital at Zemabawk North | 11.63 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 11.63 |  |  | 100% | 11.63 | Completed | Spot Quotation
256 | Widening & Improvement of Approach Road to Cancer Hospital at Zemabawk | 136.46 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 136.46 |  |  | 100% | 136.46 | Completed | Spot Quotation
257 | Widening and Construction of Retaining Wall at landslide prone area on Old Lunglei Road | 11.16 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 11.16 |  |  | 100% | 11.16 | Completed | Spot Quotation
258 | Construction of Retaining Wall near Urban Hospital at Zemabawk | 7.81 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 7.81 |  |  | 100% | 7.81 | Completed | Spot Quotation
259 | Concrete pavement of ANM to CMO at Zemabawk Vengthar Road | 19.72 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 19.72 |  |  | 100% | 19.72 | Completed | Spot Quotation
260 | Construction of Cross drain & PCC Vshape side drain on approach Zemabawk road | 3.6 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 3.6 |  |  | 100% | 3.6 | Completed | Spot Quotation
261 | Construction of Retaining Wall Beneath Urban hospital at Zemabawk | 7.81 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 7.81 |  |  | 100% | 7.81 | Completed | Spot Quotation
262 | Construction of Galili Veng to Vailui road upon Falkland | 7.1 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 7.1 |  |  | 100% | 7.1 | Completed | Spot Quotation
263 | Construction of Footpath and Retaining Wall on NH-54 near CRPF Camp at Zembawk | 46.57 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 46.57 |  |  | 100% | 46.57 | Completed | Spot Quotation
264 | Construction of Retaining Wall at below R.D Godown at Zemabawk | 10.6 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 10.6 |  |  | 100% | 10.6 | Completed | Spot Quotation
265 | Additional requirement for Construction Retaining Wall at the on-going construction of RCC Balcony Berawtlang approach road due to slide from uphill side | 21.2 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 21.2 |  |  | 100% | 21.2 | Completed | Spot Quotation
266 | Construction of RCC frame R/wall on approach road to seventh Day Adventist Church at Zemabawk | 12.72 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 12.72 |  |  | 100% | 12.72 | Completed | Spot Quotation
267 | Widening and Lowering of Sericulture to Thlanmual including conrete pavement & retaining Wall at Zemabawk North | 34.88 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 34.88 |  |  | 100% | 34.88 | Completed | Spot Quotation
268 | Concrete pavement of Kailiana road (balance Portion) | 32.93 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 32.93 |  |  | 100% | 32.93 | Completed | Spot Quotation
269 | Construction of Retaining Wall near Primary School at Zemabawk North | 2.09 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 2.09 |  |  | 100% | 2.09 | Completed | Spot Quotation
270 | Concrete pavement of Dinthar to Muthi Lui kawng including Masonry U-Shape Side Drain at Zemabawk North | 29.87 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 29.87 |  |  | 100% | 29.87 | Completed | Spot Quotation
271 | Construction of RCC Frame retaining wall including temporary side drain at Zemabawk North, Dinthar Veng | 21.2 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 21.2 |  |  | 100% | 21.2 | Completed | Spot Quotation
272 | Widening at portion and construction of Retaining Wall at Zemabawk North Dinthar Veng | 6.36 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 6.36 |  |  | 100% | 6.36 | Completed | Spot Quotation
273 | Concrete pavement of Bungbangla approach road | 10.05 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 10.05 |  |  | 100% | 10.05 | Completed | Spot Quotation
274 | Formation cutting only Berawlui Thlanmual to School at Berawlui | 0.53 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 0.53 |  |  | 100% | 0.53 | Completed | Spot Quotation
275 | Construction of Retaining Wall at Lungbial Zemabawk | 10.6 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 10.6 |  |  | 100% | 10.6 | Completed | Spot Quotation
276 | Contsruction of Protection work on Lungbial Tuikhur to lalram farm (Landslide areas) (3.Nos.) | 20.99 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 20.99 |  |  | 100% | 20.99 | Completed | Spot Quotation
277 | Construction of RCC Balcony at Lungbial | 30.18 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 30.18 |  |  | 100% | 30.18 | Completed | Spot Quotation
278 | Construction of RCC Frame Retaining Wall Including Concrete Pavement on Approach Road to Zemabawk thlanmual No.1 | 12 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 12 |  |  | 100% | 12 | Completed | Spot Quotation
279 | Construction of Link Drain, Culvert near primary School including PCC Concrete Pavement at Tuirial | 15.77 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 15.77 |  |  | 100% | 15.77 | Completed | Spot Quotation
280 | Concrete pavement of NH 54 to Tlangveng Kawng at Tuirial (Balalnce portion) | 9.5 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 9.5 |  |  | 100% | 9.5 | Completed | Spot Quotation
281 | Construction of RCC Concrete pavement of approach road to tuirial Lui | 14.6 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 14.6 |  |  | 100% | 14.6 | Completed | Spot Quotation
282 | Concrete pavement of approach road to Tuirial Airfield from NH-54 | 110 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 110 |  |  | 100% | 110 | Completed | Spot Quotation
283 | Profile Correction of Kutcha Road to Tuirial Airfield Mual thlang | 0.11 | Aizawl Road North Division | 24.04.23 | 18.05.23 | 100% | 0.11 |  |  | 100% | 0.11 | Completed | Spot Quotation
284 | Construction of PCC V shape Side drain on Muthi peng to Muthi Kawn | 10.93 | Aizawl Road North Division | 24.04.23 | 18.05.23 | 100% | 10.93 |  |  | 100% | 10.93 | Completed | Spot Quotation
285 | Construction of concrete pavement, retaining wall, PCC V shape drain & U shape drain at Muthi | 5.3 | Aizawl Road North Division | 24.04.23 | 18.05.23 | 100% | 5.3 |  |  | 100% | 5.3 | Completed | Spot Quotation
286 | Construction of PCC pavement of Chawngdailova House Hmingthansanga house, Muthi Vengthlang | 5.94 | Aizawl Road North Division | 24.04.23 | 18.05.23 | 100% | 5.94 |  |  | 100% | 5.94 | Completed | Spot Quotation
287 | Construction of Retaining wall near Lamhnai Tuikhur, Muthi | 11.93 | Aizawl Road North Division | 24.04.23 | 18.05.23 | 100% | 11.93 |  |  | 100% | 11.93 | Completed | Spot Quotation
288 | Construction of RCC Frame Retaining wall near Biakmawii residence at Muthi | 6.29 | Aizawl Road North Division | 24.04.23 | 18.05.23 | 100% | 6.29 |  |  | 100% | 6.29 | Completed | Spot Quotation
289 | Construction of PCC pavement of Sangnghinglove house to Engzami house, Muthi | 4.16 | Aizawl Road North Division | 24.04.23 | 18.05.23 | 100% | 4.16 |  |  | 100% | 4.16 | Completed | Spot Quotation
290 | Construction of Retaining wall on approach road to Muthi (1.800 kmp) | 7.5 | Aizawl Road North Division | 24.04.23 | 18.05.23 | 100% | 7.5 |  |  | 100% | 7.5 | Completed | Spot Quotation
291 | Strengthening of Approach road to LAD Complex Muanna Veng including drainage work (Balance portion) Bituminous pavement | 54.7 | Aizawl Road North Division | 24.04.23 | 19.05.23 | 100% | 54.7 |  |  | 100% | 54.7 | Completed | Spot Quotation
292 | PCC U shape side drain |  |  | 24.04.23 | 19.05.23 | 100% |  |  |  | 100% |  | Completed | Spot Quotation
293 | Concrete pavement of approach road to Muanna Veng Cemetary | 20.29 | Aizawl Road North Division | 24.04.23 | 19.05.23 | 100% | 20.29 |  |  | 100% | 20.29 | Completed | Spot Quotation
294 | Concrete pavement of approach road to YMA House at Muanna Veng | 8.12 | Aizawl Road North Division | 24.04.23 | 19.05.23 | 100% | 8.12 |  |  | 100% | 8.12 | Completed | Spot Quotation
295 | Junction improvement & strengthening of Zeda approach road including side drain, retaining walls at Zuangtui Resurfacing | 84.27 | Aizawl Road North Division | 24.04.23 | 19.05.23 | 100% | 84.27 |  |  | 100% | 84.27 | Completed | Spot Quotation
| Concrete pavement | 0 |  |  |  | 100% | - |  |  | 100% | - | Completed | Spot Quotation
296 | Concrete Pevement of Swan Industry to RK Lianzuala House at Zuangtui | 27.18 | Aizawl Road North Division | 24.04.23 | 19.05.23 | 100% | 27.18 |  |  | 100% | 27.18 | Completed | Spot Quotation
297 | Concrete Pavementof Zuangtui Vengthar road at Zuangtui | 39.82 | Aizawl Road North Division | 24.04.23 | 19.05.23 | 100% | 39.82 |  |  | 100% | 39.82 | Completed | Spot Quotation
298 | Construction of Retaining Wall at Zuangtui Industry Mual | 9.64 | Aizawl Road North Division | 24.04.23 | 19.05.23 | 100% | 9.64 |  |  | 100% | 9.64 | Completed | Spot Quotation
299 | Construction of Retaining Wall on approach road to Chhim Veng near Pi Ronghaki's House at Zuangtui | 8.48 | Aizawl Road North Division | 24.04.23 | 18.05.23 | 100% | 8.48 |  |  | 100% | 8.48 | Completed | Spot Quotation
300 | Earth work cutting, Construction of Retaining Wall, & Concrete flooring of Futsal Ground at Zuangtui Industry Mual | 63.02 | Aizawl Road North Division | 24.04.23 | 18.05.23 | 100% | 63.02 |  |  | 100% | 63.02 | Completed | Spot Quotation
301 | Concrete flooring of Futsal Ground at zuangtui | 22.94 | Aizawl Road North Division | 24.04.23 | 18.05.23 | 100% | 22.94 |  |  | 100% | 22.94 | Completed | Spot Quotation
302 | Construction of PCC Pavement on Zuangtui Vengthar (Balance Portion) | 31 | Aizawl Road North Division | 24.04.23 | 18.05.23 | 100% | 31 |  |  | 100% | 31 | Completed | Spot Quotation
303 | Construction of PCC V-Shape side drain on Zuangtui road to Thuampui Primary School | 3.5 | Aizawl Road North Division | 24.04.23 | 18.05.23 | 100% | 3.5 |  |  | 100% | 3.5 | Completed | Spot Quotation
304 | Construction of PCC V-shaped side drain near Pu Kama House, Laipuitlang | 0.37 | Aizawl Road North Division | 24.04.23 | 18.05.23 | 100% | 0.37 |  |  | 100% | 0.37 | Completed | Spot Quotation
305 | Construction of PCC V-shaped Side Drain near Pu Zakamlova House, Laipuitlang | 0.53 | Aizawl Road North Division | 24.04.23 | 18.05.23 | 100% | 0.53 |  |  | 100% | 0.53 | Completed | Spot Quotation
306 | Construction of PCC V-shaped Side Drain near Pu Lalengmawia House, Laipuitlang | 0.63 | Aizawl Road North Division | 24.04.23 | 18.05.23 | 100% | 0.63 |  |  | 100% | 0.63 | Completed | Spot Quotation
307 | Construction of PCC V-shaped Side Drain near Pu Marka House, Laipuitlang | 0.46 | Aizawl Road North Division | 24.04.23 | 18.05.23 | 100% | 0.46 |  |  | 100% | 0.46 | Completed | Spot Quotation
308 | Construction of Side Drain near Nazareth Hospital to DIET Junction at Chaltlang | 8.05 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 8.05 |  |  | 100% | 8.05 | Completed | Spot Quotation
309 | Construction of of Side Drain with Cover between H.Hiato House to high School, Chaltlang | 8 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 8 |  |  | 100% | 8 | Completed | Spot Quotation
310 | Construction of Retaining Wall at Chaltlang mear Pu Rophira's House | 4 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 4 |  |  | 100% | 4 | Completed | Spot Quotation
311 | DIET Junction improvement | 57.03 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 57.03 |  |  | 100% | 57.03 | Completed | Spot Quotation
312 | Construction of concrete Pavement of Chanmari Thlanmual Courtyard including junction Improvement (Sh: Seal Coating) | 2.35 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 2.35 |  |  | 100% | 2.35 | Completed | Spot Quotation
| (Sh: RCC Frame Retaining Wall) | 3.25 |  | 24.04.23 | 17.05.23 | 100% | 3.26 |  |  | 100% | 3.26 | Completed | Spot Quotation
| (Sh: Concrete Pavement) | 12.42 |  | 24.04.23 | 17.05.23 | 100% | 12.42 |  |  | 100% | 12.42 | Completed | Spot Quotation
313 | Const. of Protection Work for P&E Transformer at DIET Junction Chaltlang | 9.54 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 9.54 |  |  | 100% | 9.54 | Completed | Spot Quotation
314 | Const. of Concrete Pavement Chaltlang Lily Veng Cemetrery Road | 7.26 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 7.26 |  |  | 100% | 7.26 | Completed | Spot Quotation
315 | Const. of Retaing Wall at Chaltlang Lily Veng Cemetrery Road | 4.82 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 4.82 |  |  | 100% | 4.82 | Completed | Spot Quotation
316 | Const. of Railing wih chequered tiles at Chaltlang Dawrkawn | 8 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 8 |  |  | 100% | 8 | Completed | Spot Quotation
317 | Const. of Retaining Wall and Footpath at Chaltlang Veng Cemetery | 10 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 10 |  |  | 100% | 10 | Completed | Spot Quotation
318 | Improvement of Chaltlang Lily Veng to Chaltlang Link step near R.Lalropuia House | 5 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 5 |  |  | 100% | 5 | Completed | Spot Quotation
319 | Const. of approach road PCC & Side Drain from Chaltlang Dingdi Veng Turning Point to H.Lalluaia (L) House at Chaltlang Venglai | 16 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 16 |  |  | 100% | 16 | Completed | Spot Quotation
320 | Reconstruction of Chaltlang Lily Veng to Chaltlang Link Road near Lalthuthlungliana House | 8 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 8 |  |  | 100% | 8 | Completed | Spot Quotation
321 | Construction of Retaining Wall near Pu Ralkapa House, Laipuitlang | 1.71 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 1.71 |  |  | 100% | 1.71 | Completed | Spot Quotation
322 | Construction of Retaining Wall near Pu Kama House, Laipuitlang | 1.19 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 1.19 |  |  | 100% | 1.19 | Completed | Spot Quotation
323 | Construction of Masonry Step including Hand Railing near Pu Kama House, Laipuitlang | 1.47 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 1.47 |  |  | 100% | 1.47 | Completed | Spot Quotation
324 | Construction of Retaining Wall near Pu Duhzuala House, Laipuitlang | 2.61 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 2.61 |  |  | 100% | 2.61 | Completed | Spot Quotation
325 | Construction of Step in concrete over Link Drain including Railing near Community Hall, Laipuitlang | 4.05 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 4.05 |  |  | 100% | 4.05 | Completed | Spot Quotation
326 | Construction of Retaining Wall including hand Railing near Pu Rama House, Laipuitlang | 1.86 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 1.86 |  |  | 100% | 1.86 | Completed | Spot Quotation
327 | Construction of Retaining Wall including hand Railing near Pi Dawli House, Laipuitlang | 3.37 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 3.37 |  |  | 100% | 3.37 | Completed | Spot Quotation
328 | Construction of Retaining Wall near Jubilee Hall Laipuitlang | 1.56 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 1.56 |  |  | 100% | 1.56 | Completed | Spot Quotation
329 | Construction of Hand Railing near C.Zonunmawia House, Laipuitlang | 0.63 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 0.63 |  |  | 100% | 0.63 | Completed | Spot Quotation
330 | Const.of Retaining Wall at Chaltlang near T.Thangchungnunga (L) | 4 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 4 |  |  | 100% | 4 | Completed | Spot Quotation
331 | Const. of PCC U-Shape Side Drain near Pu Thanseia House, Bawngkawn | 0.3 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 0.3 |  |  | 100% | 0.3 | Completed | Spot Quotation
332 | Construction of PCC U-Shape Side Drain including Steel Railing near Pu Lalduhkima House, Bawngkawn | 5.52 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 5.52 |  |  | 100% | 5.52 | Completed | Spot Quotation
333 | Construction of step over Link Drain including Railing near K.Lalhlunchhungi residence at Bawngkawn | 18.42 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 18.42 |  |  | 100% | 18.42 | Completed | Spot Quotation
334 | Construction of Link Drain Cover near Pu R.Romawia House at Bawngkawn | 4 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 4 |  |  | 100% | 4 | Completed | Spot Quotation
335 | Construction of Side Drain near Pu EL Bethela House at Bawngkawn | 0.4 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 0.4 |  |  | 100% | 0.4 | Completed | Spot Quotation
336 | Construction of Side Drain near Pu Salemthara House at Bawngkawn | 1.3 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 1.3 |  |  | 100% | 1.3 | Completed | Spot Quotation
337 | Const. of Concrete Pavement of Brigade Slaughter House Road Bawngkawn | 58.3 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 58.3 |  |  | 100% | 58.3 | Completed | Spot Quotation
338 | Construction of Brigade Internal Road at Bawngkawn | 14.84 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 14.84 |  |  | 100% | 14.84 | Completed | Spot Quotation
339 | Construction of Steel Railing near Pu Rintluanga House, Bawngkawn | 2.18 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 2.18 |  |  | 100% | 2.18 | Completed | Spot Quotation
340 | Construction of Step at Zotui Kawng at Bawngkawn | 2 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 2 |  |  | 100% | 2 | Completed | Spot Quotation
341 | Construction of Step near PC Mawia House, Bawngkawn | 11 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 11 |  |  | 100% | 11 | Completed | Spot Quotation
342 | Construction of Step and Hand railing at Shalom Veng | 8 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 8 |  |  | 100% | 8 | Completed | Spot Quotation
343 | Construction RCC Balcony at YMA Zampuimanga | 5 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 5 |  |  | 100% | 5 | Completed | Spot Quotation
344 | Construction of Step near Ramdinthara Tuikhur | 2 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 2 |  |  | 100% | 2 | Completed | Spot Quotation
345 | Const of Approach Road to Helipad from Bawngkawn Shalom Veng | 16 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 16 |  |  | 100% | 16 | Completed | Spot Quotation
346 | PCC Flooring near Upa Chaldailova House, Bawngkawn | 3 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 3 |  |  | 100% | 3 | Completed | Spot Quotation
347 | Construction of Step on Zotui Kawng | 2 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 2 |  |  | 100% | 2 | Completed | Spot Quotation
348 | Const. of Approach Road from JK Manga House to Thlanmual Kawng | 10 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 10 |  |  | 100% | 10 | Completed | Spot Quotation
349 | Const. of RCC Balcony on Approach Road to Bawngkawn Cemetry | 41.59 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 41.59 |  |  | 100% | 41.59 | Completed | Spot Quotation
350 | Const. of Masonry U-Shape Side Drain at Thuampui Internal Road | 4.24 | Aizawl Road North Division | 24.04.23 | 24.05.23 | 100% | 4.24 |  |  | 100% | 4.24 | Completed | Spot Quotation
351 | Construction of Side Drain with cover at Zemabawk North Presbyterian Church Courtyard | 3.71 | Aizawl Road North Division | 24.04.23 | 24.05.23 | 100% | 3.71 |  |  | 100% | 3.71 | Completed | Spot Quotation
352 | Const. of Culvert Side Drain & RCC Frame Retaining Wall on Approach Road to Thuampui Cemetry | 11.34 | Aizawl Road North Division | 24.04.23 | 24.05.23 | 100% | 11.34 |  |  | 100% | 11.34 | Completed | Spot Quotation
353 | Concrete Pavement & Drainage works on Thuampui PRIMARY School to Zuangtui Vengthar (Balance Portion ) | 53.57 | Aizawl Road North Division | 24.04.23 | 24.05.23 | 100% | 53.57 |  |  | 100% | 53.57 | Completed | Spot Quotation
354 | Const. of Retaining Wall at 8.040Kmp on Thuampui - selesih Road | 9.95 | Aizawl Road North Division | 24.04.23 | 24.05.23 | 100% | 9.95 |  |  | 100% | 9.95 | Completed | Spot Quotation
355 | Const. of Concrete Pavement Approach Road to PB Vanlalauva Camping Centre at Thuampui Selesih Road (Gospel Thunder Team) | 21.2 | Aizawl Road North Division | 24.04.23 | 24.05.23 | 100% | 21.2 |  |  | 100% | 21.2 | Completed | Spot Quotation
356 | Pavement of Thuampui Helipad | 24 | Aizawl Road North Division | 03.04.23 | 12.05.23 | 100% | 24 |  |  | 100% | 24 | Completed | Spot Quotation
357 | Construction of RCC Balcony on Durtlang Leitan to Thuampui Selesih Road at Ch:1.840 Kmp | 100.59 | Aizawl Road North Division | 24.04.23 | 24.05.23 | 100% | 100.59 |  |  | 100% | 100.59 | Completed | Spot Quotation
358 | Construction of Retaining Wall on Thuampui to Selesih Road at Ch:4.350 Kmp | 4 | Aizawl Road North Division | 24.04.23 | 24.05.23 | 100% | 4 |  |  | 100% | 4 | Completed | Spot Quotation
359 | Clearing of Landslip under Aizawl Road North Division | 9.2 | Aizawl Road North Division | 24.04.23 | 24.05.23 | 100% | 9.2 |  |  | 100% | 9.2 | Completed | Spot Quotation
360 | Seal Coating of Thuampui Cemetry Road | 29.83 | Aizawl Road North Division | 24.04.23 | 24.05.23 | 100% | 29.83 |  |  | 100% | 29.83 | Completed | Spot Quotation
361 | Construction of Retaining Wall at Salvation Army Turning Point, Thuampui | 3.94 | Aizawl Road North Division | 24.04.23 | 24.05.23 | 100% | 3.94 |  |  | 100% | 3.94 | Completed | Spot Quotation
362 | Concrete Pavement of Govt. Welfare Road at Thuampui | 37.94 | Aizawl Road North Division | 24.04.23 | 24.05.23 | 100% | 37.94 |  |  | 100% | 37.94 | Completed | Spot Quotation
363 | Earthwork Cutting, Construction of Retaining Wall & PCC Flooring of Futsal Ground at Thuampui | 51 | Aizawl Road North Division | 24.04.23 | 24.05.23 | 100% | 51 |  |  | 100% | 51 | Completed | Spot Quotation
364 | Construction of Approach Road to Thuampui Vengthar at Thuampui | 18.61 | Aizawl Road North Division | 24.04.23 | 24.05.23 | 100% | 18.61 |  |  | 100% | 18.61 | Completed | Spot Quotation
365 | Construction of Road below Thuampui Presbyterian Church | 15.9 | Aizawl Road North Division | 24.04.23 | 24.05.23 | 100% | 15.9 |  |  | 100% | 15.9 | Completed | Spot Quotation
366 | Concrete Pavement of liansailova Road, Thuampui | 26.97 | Aizawl Road North Division | 24.04.23 | 24.05.23 | 100% | 26.97 |  |  | 100% | 26.97 | Completed | Spot Quotation
367 | Construction of Gallery including Side Drain at Falkland | 6.9 | Aizawl Road North Division | 24.04.23 | 24.05.23 | 100% | 6.9 |  |  | 100% | 6.9 | Completed | Spot Quotation
368 | Const. of Masonry Link Drain near Mizoram UPC Chuech at Falkland | 5.32 | Aizawl Road North Division | 24.04.23 | 24.05.23 | 100% | 5.32 |  |  | 100% | 5.32 | Completed | Spot Quotation
369 | Seal Coating of Hebrai Veng at Falkland | 23.74 | Aizawl Road North Division | 24.04.23 | 24.05.23 | 100% | 23.74 |  |  | 100% | 23.74 | Completed | Spot Quotation
370 | Construction of Retaining Wall on Tuikhur thlang at Falkland East including Masonry Cross Drain | 11.32 | Aizawl Road North Division | 24.04.23 | 24.05.23 | 100% | 11.32 |  |  | 100% | 11.32 | Completed | Spot Quotation
371 | Concrete Pavement at Falkland Veng | 15.27 | Aizawl Road North Division | 24.04.23 | 24.05.23 | 100% | 15.27 |  |  | 100% | 15.27 | Completed | Spot Quotation
372 | Construction of Step at Falkland Cemetry | 4.77 | Aizawl Road North Division | 24.04.23 | 24.05.23 | 100% | 4.77 |  |  | 100% | 4.77 | Completed | Spot Quotation
373 | Construction of Thlanmual No. 1 Shed at Falkland | 5.3 | Aizawl Road North Division | 24.04.23 | 24.05.23 | 100% | 5.3 |  |  | 100% | 5.3 | Completed | Spot Quotation
374 | Concrete Pavement of Peniel Road at Falkland | 13 | Aizawl Road North Division | 24.04.23 | 24.05.23 | 100% | 13 |  |  | 100% | 13 | Completed | Spot Quotation
375 | Bituminous pavement of Falkland East internal Road | 15 | Aizawl Road North Division | 03.04.23 | 12.05.23 | 100% | 15 |  |  | 100% | 15 | Completed | Spot Quotation
376 | Patch repair and Seal Coating of Middle School | 19.88 | Aizawl Road North Division | 03.04.23 | 12.05.23 | 100% | 19.88 |  |  | 100% | 19.88 | Completed | Spot Quotation
377 | Improvement of Approach Road to Falkland East Junction (Sh:Construction of RCC Framed Structure Retaining Wall) | 4.72 | Aizawl Road North Division | 03.04.23 | 12.05.23 | 100% | 4.72 |  |  | 100% | 4.72 | Completed | Spot Quotation
378 | Improvement of Approach Road to Falkland East Junction (Sh:Pavement) | 2.79 | Aizawl Road North Division | 03.04.23 | 12.05.23 | 100% | 2.79 |  |  | 100% | 2.79 | Completed | Spot Quotation
379 | Const. of Link Drain Near Lalngamliana House to Sihphir Venglai | 6.96 | Aizawl Road North Division | 03.04.23 | 12.05.23 | 100% | 6.96 |  |  | 100% | 6.96 | Completed | Spot Quotation
380 | Construction of Concrete Pavement Link road from Sihphir Kawnveng to Khamrang Road (i/c Seal Coating of Sihphir Bypass Road via Selesih | 42.4 | Aizawl Road North Division | 03.04.23 | 10.05.23 | 100% | 42.4 |  |  | 100% | 42.4 | Completed | Spot Quotation
381 | Construction of PCC V-Shape Side Drain on Sihphir Lower Lane, Sihphir Venghlun | 1 | Aizawl Road North Division | 24.04.23 | 16.03.23 | 100% | 1 |  |  | 100% | 1 | Completed | Spot Quotation
382 | Construction of Link Drain including extention of Culvert Near Pu Lalruatvela House, Sihphir Venghlun | 2.98 | Aizawl Road North Division | 24.04.23 | 15.05.23 | 100% | 2.98 |  |  | 100% | 2.98 | Completed | Spot Quotation
383 | Construction of Link Drain near Pu Lalngamliana House to Sihphir Venglai Biak In, Sihphir (Balance) | 5.3 | Aizawl Road North Division | 24.04.23 | 15.05.23 | 100% | 5.3 |  |  | 100% | 5.3 | Completed | Spot Quotation
384 | Const. of Cross Drainage, Passing place on Approach Road to Nausel | 5.89 | Aizawl Road North Division | 24.04.23 | 15.05.23 | 100% | 5.89 |  |  | 100% | 5.89 | Completed | Spot Quotation
385 | Construction of PCC V-Shape Side Drain on Nausel Road | 10.6 | Aizawl Road North Division | 24.04.23 | 15.05.23 | 100% | 10.6 |  |  | 100% | 10.6 | Completed | Spot Quotation
386 | Construction of Retaining Wall Sihphir Bypass Road | 15.03 | Aizawl Road North Division | 24.04.23 | 15.05.23 | 100% | 15.03 |  |  | 100% | 15.03 | Completed | Spot Quotation
387 | Concrete Pavement of Approach Road to Lalbiaki Residence to YMA Park at Sihphir Hmar Veng | 19.89 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 19.89 |  |  | 100% | 19.89 | Completed | Spot Quotation
388 | Widening of Approach Road to SBI from Sihphir Lower lane Beneath Salvation Army Church | 7.89 | Aizawl Road North Division | 24.04.23 | 15.05.23 | 100% | 7.89 |  |  | 100% | 7.89 | Completed | Spot Quotation
389 | Construction of PCC Pavement High Atitude panna kawng | 16.23 | Aizawl Road North Division | 24.04.23 | 15.05.23 | 100% | 16.23 |  |  | 100% | 16.23 | Completed | Spot Quotation
390 | Constriction of Retaining Wall including Link Drain near K.Lalengzauva house at Sihphir Venghlun | 11.32 | Aizawl Road North Division | 24.04.23 | 15.05.23 | 100% | 11.32 |  |  | 100% | 11.32 | Completed | Spot Quotation
391 | Construction of Retaining Wall near Pi Remthangi Residence on Nausel Road, Sihphir Venghlun | 14.79 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 14.79 |  |  | 100% | 14.79 | Completed | Spot Quotation
392 | Concrete Pavement of Approach Road to Sihphir Venghlun Cemetry | 10.06 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 10.06 |  |  | 100% | 10.06 | Completed | Spot Quotation
393 | Concrete Pavement of Sihphir Venghlun Khawhnuai to Multipurpose Hall | 54.59 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 54.59 |  |  | 100% | 54.59 | Completed | Spot Quotation
394 | Concrete Pavement of Nausel Field Thlang | 12.23 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 12.23 |  |  | 100% | 12.23 | Completed | Spot Quotation
395 | Construction of Slab Culvert from Sihphir to Khamrang Road | 21.2 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 21.2 |  |  | 100% | 21.2 | Completed | Spot Quotation
396 | Construction of RCC V-Shape Side Drain on Durtlang Leitan | 3.17 | Aizawl Road North Division | 24.04.23 | 18.05.23 | 100% | 3.17 |  |  | 100% | 3.17 | Completed | Spot Quotation
397 | Construction of Masonry Cross Drain with Cover near Leitan 'S' Presbyterian Church | 2.61 | Aizawl Road North Division | 24.04.23 | 18.05.23 | 100% | 2.61 |  |  | 100% | 2.61 | Completed | Spot Quotation
398 | Construction of U-Shape Side Drain on BSNL Junction near Pu Rinawma House, Durtlang North | 4 | Aizawl Road North Division | 24.04.23 | 18.05.23 | 100% | 4 |  |  | 100% | 4 | Completed | Spot Quotation
399 | Extension of RCC Slab Culvert at Arbai Veng, Durtlang | 1.5 | Aizawl Road North Division | 24.04.23 | 18.05.23 | 100% | 1.5 |  |  | 100% | 1.5 | Completed | Spot Quotation
400 | Construction of RCC Slab Culvert between Pi Saii and Pi Purni House, Durtlang Leitan | 5.25 | Aizawl Road North Division | 24.04.23 | 18.05.23 | 100% | 5.25 |  |  | 100% | 5.25 | Completed | Spot Quotation
401 | Concrete Flooring, Drain with Cover & RCC Balcony from Zuangtui road to Pu Lalhmachhuana's House at Durtlang Venglai | 22.36 | Aizawl Road North Division | 24.04.23 | 18.05.23 | 80% | 22.36 | 20% |  | 100% | 22.36 | Completed | Spot Quotation
402 | Construction of Step with Cheqered Tile including Railing near Pi Ngurmawii, Durtlang Leitan | 8 | Aizawl Road North Division | 24.04.23 | 18.05.23 | 100% | 8 |  |  | 100% | 8 | Completed | Spot Quotation
403 | Constrution of Retaining Wall near Prsbyterian Church, Dutlang North | 15 | Aizawl Road North Division | 24.04.23 | 18.05.23 | 100% | 15 |  |  | 100% | 15 | Completed | Spot Quotation
404 | Constrution of Retaining Wall No.1 at Arbai Peng, Durtlang | 2.83 | Aizawl Road North Division | 24.04.23 | 18.05.23 | 100% | 2.83 |  |  | 100% | 2.83 | Completed | Spot Quotation
405 | Constrution of Retaining Wall No.2 at Arbai Peng, Durtlang | 5.67 | Aizawl Road North Division | 24.04.23 | 18.05.23 | 100% | 5.67 |  |  | 100% | 5.67 | Completed | Spot Quotation
406 | Widening near Leitan's Presbyterian Church, Durtlang | 2.73 | Aizawl Road North Division | 24.04.23 | 18.05.23 | 100% | 2.73 |  |  | 100% | 2.73 | Completed | Spot Quotation
407 | PCC Pavement near Zakianglova House, Durtlang North | 4 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 4 |  |  | 100% | 4 | Completed | Spot Quotation
408 | Constrution of Retaining Wall Unit-I, Durtlang Leitan | 3.6 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 3.6 |  |  | 100% | 3.6 | Completed | Spot Quotation
409 | Constrution of Retaining Wall Unit-I, Durtlang Leitan | 0.82 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 0.82 |  |  | 100% | 0.82 | Completed | Spot Quotation
410 | Constrution of Retaining Wall Unit-I, Durtlang Leitan | 2.69 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 2.69 |  |  | 100% | 2.69 | Completed | Spot Quotation
411 | Constrution of Retaining Wall Unit-I, Durtlang Leitan | 2.8 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 2.8 |  |  | 100% | 2.8 | Completed | Spot Quotation
412 | PCC Pavement Zion Veng to Suaka Veng at Durtlang | 3 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 3 |  |  | 100% | 3 | Completed | Spot Quotation
413 | PCC Pavement Upper SL Road at Durtlang | 2.5 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 2.5 |  |  | 100% | 2.5 | Completed | Spot Quotation
414 | PCC Pavement Upper SL Road at Durtlang | 2.5 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 2.5 |  |  | 100% | 2.5 | Completed | Spot Quotation
415 | PCC Pavement on Local Council Road, Durtlang | 8 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 8 |  |  | 100% | 8 | Completed | Spot Quotation
416 | PCC Pavement on Chhingtei Road, Durtlang | 8 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 8 |  |  | 100% | 8 | Completed | Spot Quotation
417 | Construction of Kawmzawl to Centenary Road at durtlang including RCC pavement | 8 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 8 |  |  | 100% | 8 | Completed | Spot Quotation
418 | RCC Pavement at Lanu Road, Mizoram UPC to Presbyterian Chucrh at Suaka Veng, Durtlang | 8 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 8 |  |  | 100% | 8 | Completed | Spot Quotation
419 | RCC pavement at Selesih | 8 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 8 |  |  | 100% | 8 | Completed | Spot Quotation
420 | Construction of Slab Culvert near Pu Thawmtea's house | 7 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 7 |  |  | 100% | 7 | Completed | Spot Quotation
421 | Improvement of Y-Road Junction | 5.44 | Aizawl Road North Division | 03.04.23 | 10.05.23 | 100% | 5.44 |  |  | 100% | 5.44 | Completed | Spot Quotation
422 | Improvement of Y-Road near Pu Sajjal Residence | 0.96 | Aizawl Road North Division | 03.04.23 | 10.05.23 | 100% | 0.96 |  |  | 100% | 0.96 | Completed | Spot Quotation
423 | Pavement of Sihphir By-pass Road | 4.41 | Aizawl Road North Division | 03.04.23 | 10.05.23 | 100% | 4.41 |  |  | 100% | 4.41 | Completed | Spot Quotation
424 | Imrpvement of Road Profile and PCC Pavement at Falkland | 2.42 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 2.42 |  |  | 100% | 2.42 | Completed | Spot Quotation
425 | Construction of PCC V Shape side drain near Pu BM-a House | 0.3 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 0.3 |  |  | 100% | 0.3 | Completed | Spot Quotation
426 | Construction of Hand Railing near Papuia House | 0.72 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 0.72 |  |  | 100% | 0.72 | Completed | Spot Quotation
427 | Construction of Hand Railing near Chhunglawmi House at Durtlang Leitan | 3.7 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 3.7 |  |  | 100% | 3.7 | Completed | Spot Quotation
428 | Construction of Hand Railing Pu Malsawma House to Upa Zairemmawia House at Zotui Veng Durtlang | 2.65 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 2.65 |  |  | 100% | 2.65 | Completed | Spot Quotation
429 | Imrprovement of Bethel veng road at zemabawk, Aizawl in Mizoram for the the year 2022-2023 | 318 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 85% | 244.8 | 15% | 70.26 | 100% | 315.06 | Completed | Spot Quotation
430 | Imrprovement of Thuampui-Selesih road (uoto 5.120 Km)Aiawl in Mizoram for the the year 2022-2024 | 370 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 366.79 |  |  | 100% | 366.79 | Completed | Spot Quotation
431 | Construction of Side Drain with cover at zemabawk North Presbyterian kawt | 12 | Aizawl Road North Division | 24.04.23 | 16.05.23 | 100% | 12 |  |  | 100% | 12 | Completed | Spot Quotation
SUB DIVISION-III
Construction and Upgradation of connectivity from Kangthelhkawn - Ainawn - Luangmual by creating a new alternative road
432 | Repair of culvert wing wall near Mimi's House on Chhangurkawn to Govt.Complex | 1.27 | Aizawl Road North Division | 29.03.23 | 09.05.23 | 100% | 1.27 |  |  | 100% | 1.27 | Completed | Spot Quotation
433 | Improvement and Widening of approach road to MPRO Quarter (Sh: Construction of Pavement) | 75.88 | Aizawl Road North Division | 04.04.23 | 09.05.23 | 100% | 75.88 |  |  | 100% | 75.88 | Completed | Spot Quotation
434 | Improvement and Widening of approach road to MPRO Quarter (Sh: 1. Construction of Slab Culvert @ ch.0.050 Kmp | 3.51 | Aizawl Road North Division | 20.04.23 | 13.05.23 | 100% | 3.51 |  |  | 100% | 3.51 | Completed | Spot Quotation
435 | 2. Construction of Slab Culvert @ ch.0.510 Kmp | 3.5 | Aizawl Road North Division | 20.04.23 | 13.05.23 | 100% | 3.5 |  |  | 100% | 3.5 | Completed | Spot Quotation
436 | 3. Construction of Slab Culvert @ ch.0.650 Kmp | 3.52 | Aizawl Road North Division | 20.04.23 | 13.05.23 | 100% | 3.52 |  |  | 100% | 3.52 | Completed | Spot Quotation
437 | 4. Construction of Breast Wall @ ch.0.550 Kmp | 5.51 | Aizawl Road North Division | 20.04.23 | 13.05.23 | 100% | 5.51 |  |  | 100% | 5.51 | Completed | Spot Quotation
438 | 5. Construction of Breast Wall @ ch.0.410 Kmp | 8.06 | Aizawl Road North Division | 20.04.23 | 13.05.23 | 100% | 8.06 |  |  | 100% | 8.06 | Completed | Spot Quotation
439 | 6. Construction of Link Drain | 8.4 | Aizawl Road North Division | 20.04.23 | 13.05.23 | 100% | 8.4 |  |  | 100% | 8.4 | Completed | Spot Quotation
440 | 7. Construction of V-Shape side drain | 2.01 | Aizawl Road North Division | 20.04.23 | 13.05.23 | 100% | 2.01 |  |  | 100% | 2.01 | Completed | Spot Quotation
441 | Construction of RCC Frame struction Retaining Wall & Hume pipe Culvert with link drain on Approach Road to Govt.Housing Complex, at Luangmual at Ch 0.100Kmp Sh: 1. Retaining Wall | 14.03 | Aizawl Road North Division | 29.03.23 | 15.05.23 | 100% | 14.03 |  |  | 100% | 14.03 | Completed | Spot Quotation
442 | 2. Humne Pipe Culvert | 3.62 | Aizawl Road North Division | 29.03.23 | 15.05.23 | 100% | 3.62 |  |  | 100% | 3.62 | Completed | Spot Quotation
443 | 3. Linked Drain | 4.77 | Aizawl Road North Division | 29.03.23 | 15.05.23 | 100% | 4.77 |  |  | 100% | 4.77 | Completed | Spot Quotation
445 | Construction of Breast Wall near Pu Lalrinawma House at Luangmual | 5.08 | Aizawl Road North Division | 27.02.23 | 04.05.23 | 100% | 5.08 |  |  | 100% | 5.08 | Completed | Spot Quotation
446 | Construction of Road at Ainawn Veng, Aizawl Sh: 1. Earth Work Formation cutting | 41.17 | Aizawl Road North Division | 19.04.23 | 11.05.23 | 100% | 41.17 |  |  | 100% | 41.17 | Completed | Spot Quotation
447 | 2. Construction of RCC Slab Culvert Type-I | 13.58 | Aizawl Road North Division | 19.04.23 | 11.05.23 | 100% | 13.58 |  |  | 100% | 13.58 | Completed | Spot Quotation
448 | 3. Slab-Culvert-II | 16.79 | Aizawl Road North Division | 19.04.23 | 11.05.23 | 100% | 16.79 |  |  | 100% | 16.79 | Completed | Spot Quotation
449 | Construction of road at Chawnpui, Aizawl Sh: 1. Earth Work Formation cutting | 38.02 | Aizawl Road North Division | 03.04.23 | 03.05.23 | 100% | 38.02 |  |  | 100% | 38.02 | Completed | Spot Quotation
450 | 2. Construction og RCC Slab Vulvert Type-I | 13.57 | Aizawl Road North Division | 03.04.23 | 03.05.23 | 100% | 13.57 |  |  | 100% | 13.57 | Completed | Spot Quotation
451 | 3. Construction of TCC Slab Culvert Type-II | 8.4 | Aizawl Road North Division | 03.04.23 | 03.05.23 | 100% | 8.4 |  |  | 100% | 8.4 | Completed | Spot Quotation
452 | Resurfaccing of Kangthlehkawn to High Court (0.000 to 1.830 Kmp) | 59.29 | Aizawl Road North Division | 03.04.23 | 09.05.23 | 100% | 59.29 |  |  | 100% | 59.29 | Completed | Spot Quotation
453 | Const. of Approach Road (RCC Pavement) to Chhimveng Presby. Church at Ainawn Veng | 31.76 | Aizawl Road North Division | 03.04.23 | 09.05.23 | 100% | 31.76 |  |  | 100% | 31.76 | Completed | Spot Quotation
Construction of Upgradation of Road from Dawrpui Vengthar - Vaivakawn - Zotlang - MZU
454 | Construction of Link Drain near P/S at Vaivakawn | 13.92 | Aizawl Road North Division | 23.03.23 | 12.05.23 | 100% | 13.92 |  |  | 100% | 13.92 | Completed | Spot Quotation
455 | RCC Link Drain with Cover Step K.Buanga's House approach to NH-06, Vaivakawn | 25.42 | Aizawl Road North Division | 04.04.23 | 18.08.23 | 100% | 25.42 |  |  | 100% | 25.42 | Completed | Spot Quotation
456 | Rectangular Side Drain with cover near Salvation Army Church at k.Zamawia's House to MZU Road including Cross Drain cover, Vaivakawn | 11.55 | Aizawl Road North Division | 29.03.23 | 12.05.23 | 100% | 11.55 |  |  | 100% | 11.55 | Completed | Spot Quotation
457 | Const. of RCC Mini Bridge near Pi Malsawma's House (Dam veng) | 14.82 | Aizawl Road North Division | 29.03.23 | 10.06.23 | 100% | 14.82 |  |  | 100% | 14.82 | Completed | Spot Quotation
458 | Const. of RCC Foot path near Presbyterian Pastor Quarter to Zarkawt approach road at Dawrpui Vengthar | 15.96 | Aizawl Road North Division | 29.03.23 | 12.05.23 | 100% | 15.96 |  |  | 100% | 15.96 | Completed | Spot Quotation
459 | RCC approach road to Vanlalzuiliana's House Sh: 1. Construction of Rigid Pavement | 9.21 | Aizawl Road North Division | 29.03.23 | 16.06.23 | 100% | 9.21 |  |  | 100% | 9.21 | Completed | Spot Quotation
| 2. Construction of V-Shaped Side Drain | 2.22 | Aizawl Road North Division | 29.03.23 | 16.06.23 | 100% | 2.22 |  |  | 100% | 2.22 | Completed | Spot Quotation
460 | Improvement of road Zotlang, Aizawl Sh: 1.Earth Work Widening of existing road | 9 | Aizawl Road North Division | 28.03.23 | 11.05.23 | 100% | 9 |  |  | 100% | 9 | Completed | Spot Quotation
| 2. Construction of Retaining Wall | 28.52 | Aizawl Road North Division | 28.03.23 | 11.05.23 | 100% | 28.52 |  |  | 100% | 28.52 | Completed | Spot Quotation
| 3. Rigid Pavement | 5.58 | Aizawl Road North Division | 28.03.23 | 11.05.23 | 100% | 5.58 |  |  | 100% | 5.58 | Completed | Spot Quotation
461 | Road Widening and R/Wall at Pu Rosanga House to Neitumi House, Zohnuai Vaivakawn Sh: Earthwork | 5.41 | Aizawl Road North Division | 03.04.23 |  | 100% | 5.41 |  |  | 100% | 5.41 | Completed | Spot Quotation
| 2. Construction of Slab Culvert @ ch.0.115 Kmp | 3.5 | Aizawl Road North Division | 03.04.23 |  | 100% | 3.5 |  |  | 100% | 3.5 | Completed | Spot Quotation
| 3. Construction of Breast wall | 24.97 | Aizawl Road North Division | 03.04.23 |  | 100% | 24.97 |  |  | 100% | 24.97 | Completed | Spot Quotation
462 | Construction og Retaining Wall on Electric Veng Cemetery Road Sh: 1. Construction og Retaining Wall Section - 1 | 9.95 | Aizawl Road North Division | 29.03.23 | 26.06.23 | 100% | 9.95 |  |  | 100% | 9.95 | Completed | Spot Quotation
| 2. Construction og Retaining Wall Section - 2 | 4.76 | Aizawl Road North Division | 29.03.23 | 26.06.23 | 100% | 4.76 |  |  | 100% | 4.76 | Completed | Spot Quotation
| 3. Construction og Retaining Wall Section - 3 | 9.32 | Aizawl Road North Division | 29.03.23 | 26.06.23 | 100% | 9.32 |  |  | 100% | 9.32 | Completed | Spot Quotation
463 | Construction of Step near Seventh Day Church to Dosangvunga (L) House at Electrict Veng Sh: Construction of Step | 13.9 | Aizawl Road North Division | 29.03.23 | 26.06.23 | 100% | 13.9 |  |  | 100% | 13.9 | Completed | Spot Quotation
464 | Construction of Step in concrete over Link Drain including Railing near Presbyterian Jubilee Hall, Laipuitlang | 6.63 | Aizawl Road North Division | 24.04.23 | 17.05.23 | 100% | 6.63 |  |  | 100% | 6.63 | Completed | Spot Quotation
Construction and Upgradation of Road from Chanmari West - Hunthar - Edenthar - Rangvamual
465 | Pot Hole Repair & Resurfacing and Seal Coating of Chanmari West to NH-54 | 11.01 | Aizawl Road North Division | 29.03.23 | 09.05.23 | 100% | 11.01 |  |  | 100% | 11.01 | Completed | Spot Quotation
466 | Pot Hole Repair & Resurfacing and Seal Coating of Chanmari West to Vaivakawn Road (0.000 - 0.550Kms) | 16.93 | Aizawl Road North Division | 29.03.23 | 09.05.23 | 100% | 16.93 |  |  | 100% | 16.93 | Completed | Spot Quotation
467 | Hole Repair & Resurfacing and Seal Coating of edenthar internal (0.000-1.175 Kms) | 15.25 | Aizawl Road North Division | 29.03.23 | 09.05.23 | 100% | 15.25 |  |  | 100% | 15.25 | Completed | Spot Quotation
468 | Pot Hole Repair & Resurfacing and Seal Coating of Bt Bakery to turning Point via Middle School at Hunthar (0.000 - 0.175Kms) | 10.16 | Aizawl Road North Division | 29.03.23 | 09.05.23 | 100% | 10.16 |  |  | 100% | 10.16 | Completed | Spot Quotation
469 | Pot Hole Repair & Resurfacing and Seal Coating of Edenthar Internal (0.000-1.175 Kms) | 17.46 | Aizawl Road North Division | 29.03.23 | 09.05.23 | 100% | 17.46 |  |  | 100% | 17.46 | Completed | Spot Quotation
470 | Const. of RCC pavement at Tuikhuahmual, Edenthar | 28.97 | Aizawl Road North Division |  |  | 100% | 28.97 |  |  | 100% | 28.97 | Completed | Spot Quotation
470
471 | Construction of RCC Pavement Edenthar to Chanmari West Road Sh: 1. Construction of RCC Pavement | 78 | Aizawl Road North Division | 20.04.23 | 22.05.23 | 100% | 78 |  |  | 100% | 78 | Completed | Spot Quotation
472 | 2. Construction of Hume Pipe Culvert at Ch.0.037 Kmp | 6.77 | Aizawl Road North Division | 20.04.23 | 22.05.23 | 100% | 6.77 |  |  | 100% | 6.77 | Completed | Spot Quotation
473 | Construction of Ram,lai Road at Edenthar Sh: Earth work for Widening of existing road) | 16.95 | Aizawl Road North Division | 28.03.23 | 29.09.23 | 100% | 16.95 |  |  | 100% | 16.95 | Completed | Spot Quotation
474 | Construction of Lunghlu Road at Chanmari West Sh: 1. Earth Work for Formation cutting | 17.52 | Aizawl Road North Division | 04.04.23 |  | 100% | 17.52 |  |  | 100% | 17.52 | Completed | Spot Quotation
475 | 2. Construction of RCC Slab Culvert Type-I | 8.03 | Aizawl Road North Division | 04.04.23 |  | 100% | 8.03 |  |  | 100% | 8.03 | Completed | Spot Quotation
476 | 3. Slab Culvert-II | 33.76 | Aizawl Road North Division | 04.04.23 |  | 100% | 33.76 |  |  | 100% | 33.76 | Completed | Spot Quotation
477 | Const. of RCC Link Drain near Volleyball Court, Hunthar | 28.96 | Aizawl Road North Division | 04.04.23 |  |  |  | 100% | 28.96 | 100% | 28.96 | Completed | Spot Quotation
478 | Construction of road at Rangvamual, Aizawl Sh: 1. Earth Work for Formation Cutting | 107.52 | Aizawl Road North Division | 19.04.23 |  | 100% | 53.76 |  |  | 100% | 53.76 | Phy Completed | Spot Quotation
479 | Const. of RCC Slab Culvert Type-1 | 26.62 | Aizawl Road North Division | 19.04.23 | [7 empty] | Not yet started | Spot Quotation
480 | 3. Slab Culvert-II | 24.71 | Aizawl Road North Division | 19.04.23 | [7 empty] | Not yet started | Spot Quotation
Construction and Upgradation of Connectivity by Creating a new Alternative Route, Tanhril - Sakawrtuichhun.
481 | Patch repairs of Sakawrtuichhun to PTC Road due to vice President visit | 7.18 | Aizawl Road North Division | 27.02.23 | 23.03.23 | 100% | 7.18 |  |  | 100% | 7.18 | Completed | Spot Quotation
482 | Construction of Retaining Wall near Lallawmzuala's House at Sakawrtuichhun | 5.66 | Aizawl Road North Division | 24.02.23 | 21.03.23 | 100% | 5.66 |  |  | 100% | 5.66 | Completed | Spot Quotation
483 | Construction of Dumping Ground at Industrial Areas at Sakawrtuichhun Sh: 1. Earth Work for Formation Cutting of Internal Road | 10.53 | Aizawl Road North Division | 24.02.23 | 21.03.23 | 100% | 10.53 |  |  | 100% | 10.53 | Completed | Spot Quotation
484 | 2. Hume Pipe NP4 | 27.27 | Aizawl Road North Division | 24.02.23 | 21.03.23 | 100% | 27.27 |  |  | 100% | 27.27 | Completed | Spot Quotation
485 | Const. of Road at Tanhril, Aizawl Sh: 1. Earth Work for Formation Cutting | 80.48 | Aizawl Road North Division | 19.04.23 | 11.05.23 | 100% | 80.48 |  |  | 100% | 80.48 | Completed | Spot Quotation
486 | 2. Construction of RCC Slab Culvert Type-I | 27.15 | Aizawl Road North Division | 19.04.23 | 11.05.23 | 100% | 27.15 |  |  | 100% | 27.15 | Completed | Spot Quotation
487 | 3. Construction of RCC Slab Culvert Type-II | 16.79 | Aizawl Road North Division | 19.04.23 | 11.05.23 | 100% | 16.79 |  |  | 100% | 16.79 | Completed | Spot Quotation
488 | Construcytion of Road at Sakawrtuichhun, Aizawl Sh: 1. Earth Work for Widening of existing Road | 19.53 | Aizawl Road North Division | 19.04.23 | 12.05.23 | 100% | 19.53 |  |  | 100% | 19.53 | Completed | Spot Quotation
489 | 2. Construction of Flexible Pavement NBCC Road I & II | 24.82 | Aizawl Road North Division | 19.04.23 | 12.05.23 | 100% | 24.82 |  |  | 100% | 24.82 | Completed | Spot Quotation
490 | 3. Construction of RCC Slab Culvert Type-I | 17.84 | Aizawl Road North Division | 19.04.23 | 12.05.23 | 100% | 17.84 |  |  | 100% | 17.84 | Completed | Spot Quotation
491 | Improvement of Ramrikawn to NH-54 via Sakawrtuichhun Roads in Mizoram for the year 2022-2023 Sh: 1. Pavement of ramrikawn to NH-54 |  | Aizawl Road North Division | 07.04.23 |  | 100% |  |  |  | 100% |  | Completed | Spot Quotation
492 | 2. Const.of R/Wall at Ch 5.950 Kmp at Sakawrtuichhun | 336 | Aizawl Road North Division | 07.04.23 |  | 100% | 336 |  |  | 100% | 336 | Completed | Spot Quotation
493 | 3. Const.of R/W near Zoo Gate, Lungverh |  | Aizawl Road North Division | 07.04.23 |  | 100% |  |  |  | 100% |  | Completed | Spot Quotation
494 | 4. Const.of Hume Pipe Culvert at 0.270 Kmp at Sakawrtuichhun |  | Aizawl Road North Division | 07.04.23 |  | 100% |  |  |  | 100% |  | Completed | Spot Quotation
495 | 5. Const.of Hume Pipe Culvert at 1.580 Kmp at Sakawrtuichhun |  | Aizawl Road North Division | 07.04.23 |  | 100% |  |  |  | 100% |  | Completed | Spot Quotation
AIZAWL ROAD SOUTH DIVISION - 2023-2024
496 | Const. of Bethlehem Vengthlang Internal Road & Venghlui Junction Improvement. | 303 | Aizawl Road South Division | 28.02.23 | 30.12.23 | 100% | 147.39 |  | 155.61 | 100% | 303 | Completed | Item rate Contract
497 | Const. of Rehabilitation of Samtlang - Lungleng Road | 243 | Aizawl Road South Division | 28.02.23 | 30.12.23 | 99% | 106.21 |  |  | 99% | 106.21 | On going | Item rate Contract
498 | Improvement of Curves at Mission Vengthlang to Tlawng Road | 384 | Aizawl Road South Division | 28.02.23 | 30.12.23 | 100% | 198.56 |  | 185.44 | 100% | 384 | Completed | Item rate Contract
499 | Upgradation of Khatla to Tuikual to Dinthar Road | 343 | Aizawl Road South Division | 28.02.23 | 30.12.23 | 100% | 167.96 |  | 175.04 | 100% | 343 | Completed | Item rate Contract
500 | Const. and Upgradation of Republic Veng to Mualpui Road | 293 | Aizawl Road South Division | 28.02.23 | 30.12.23 | 100% | 96.08 |  | 196.92 | 100% | 293 | Completed | Item rate Contract
501 | Upgradation of Tuikhuahtlang to Saikhamakawn Road | 316 | Aizawl Road South Division | 28.02.23 | 30.12.23 | 100% | 146.15 |  | 169.85 | 100% | 316 | Completed | Item rate Contract
502 | Widening of Approach Road to City Bus Parking at S.Hlimen (Melthum - Hlimen Road ) | 576 | Aizawl Road South Division | 28.02.23 | 30.12.23 | 33% | 32.26 | 2% |  | 35% | 32.26 | On going | Item rate Contract
503 | Widening of S.Hlimen City Bus Parking - Samtlang Road (Hlimen-Samtlang Road) | 831 | Aizawl Road South Division | 28.02.23 | 30.12.23 | 75% | 301.59 | 5% |  | 80% | 301.59 | On going | Item rate Contract
SASCI - 2023-2024
504 | Overlaying of road with PCC Pavement from Mission veng to Khatla with Retaining Wall and Minor Bridge at Aizawl under SASCI Phase - I Part-1 | 94.54 | Aizawl Road South Division |  |  |  |  | 5.27% |  | 5.27% |  | On going | Restricted Tender
505 | Improvement of Saikhamakawn to Kulikawn via Tlangnuam under SASCI Phase-I Part-1 | 97 | Aizawl Road South Division |  |  |  |  | 33.6% |  | 33.6% |  | On going | Restricted Tender
506 | Const. of PCC Pavement, PCC Side drain and Retaining Wall at Upper Republic to Bethlehem via College veng under SASCI Phase-I Part-1 | 173.16 | Aizawl Road South Division |  |  |  |  | 5.55% |  | 5.55% |  | On going | Restricted Tender
507 | Improvement of Venghnuai to Salem Road under SASCI Phase-I, Part-1. | 150 | Aizawl Road South Division |  |  |  |  | 5.14% |  | 5.14% |  | On going | Restricted Tender
508 | Const. of Road from Nursery to Tamdo to Lawipu (2.50 kms) under SASCI during 2023-2024 Phase-II | 477.16 | Aizawl Road South Division |  |  |  |  | 49.22% |  | 49.22% |  | On going | Restricted Tender
509 | Const. of road from Tlawng road to Model Veng under SASCI during 2023-2024 | 247.34 | Aizawl Road South Division |  |  |  |  | 1.5% |  | 1.5% |  | On going | Restricted Tender
510 | Upgradation of Internal roads at Tuikual, Venghlui and Republic veng under SASCI 2023-2024 Phase-II | 104.58 | Aizawl Road South Division |  |  |  |  | 14.16% |  | 14.16% |  | On going | Restricted Tender
511 | Improvement of Roads and Infrastructtures at Aizawl City under SASCI 2023-2024 | 217 | Aizawl Road South Division |  |  |  |  | 62.66% |  | 62.66% |  | On going | Restricted Tender
CHAMPHAI DIVISION
Const./Improvement of Road from Pamchung - Tualcheng - Chhangphut Field - Keifangtlang at Champhai District. 2022-2023
512 | Const. of Road from Pamchung to Tualcheng | 60 | Champhai Division | 21.03.23 | 21.04.23 | 100% | 57.88 |  |  | 100% | 57.88 | Completed | Spot Quatation
513 | Widening of Chhangphut Field to Keifangtlang | 90 | Champhai Division | 21.03.23 | 21.04.23 | 92.3% | 31.28 | 7.7% |  | 100% | 31.28 | Work in Progress | Spot Quatation
514 | Widening and Retaining Wall at Hnahlan Dawrkawn to BRTF Road | 20 | Champhai Division | 21.03.23 | 21.04.23 | 100% | 19.32 |  |  | 100% | 19.32 | Completed | Spot Quatation
515 | Const. and Widening of Champhai Vengthlang ( N.Saron) to PHE Road | 50 | Champhai Division | 21.03.23 | 21.04.23 | 100% | 48.31 |  |  | 100% | 48.31 | Phy.Completed | Spot Quatation
516 | Const. of Railing and Retaining Wall at Champhai, Awmpui Phei & IB Veng | 40 | Champhai Division | 21.03.23 | 21.04.23 | 100% | 38.54 |  |  | 100% | 38.54 | Completed | Spot Quatation
517 | Consultancy Fee | 77 | Champhai Division | 21.03.23 | 21.04.23 | 100% | 10.14 |  |  | 100% | 10.14 | Phy.Completed | Spot Quatation
Const. of Pavement Champhai Vengthar - BRTF Road - Zotlang at Champhai. 2022-2023
518 | Black Topping of Road from Champhai Vengthar to BRTF Road (Zotekai Short Cut Road) | 164.46 | Champhai Division | 30.03.23 | 31.04.23 | 100% | 162.99 |  |  | 100% | 162.99 | Completed | Spot Quatation
519 | White Topping of Khawulh Approach Road at Zotlang, Champhai (Cement Concrete Pavement ) | 30 | Champhai Division | 30.03.23 | 31.04.23 | 100% | 28.92 |  |  | 100% | 28.92 | Completed | Spot Quatation
520 | Widening of Road from Dinthar to Ramhrangkawn (7th Day Gate to LCN Filling Station ) | 45 | Champhai Division | 30.03.23 | 31.04.23 | 100% | 43.47 |  |  | 100% | 43.47 | Completed | Spot Quatation
521 | Widening of Approach Road to Kendriya Vidhyalaya School, Champhai | 10 | Champhai Division | 30.03.23 | 31.04.23 | 100% | 9.95 |  |  | 100% | 9.95 | Completed | Spot Quatation
Improvement of Road from IKK Zion Veng - Khawbung - Tuipui at Champhai District 2022-2023
522 | Widening and Flexible Pavement of Road from IKK Church to Zion Veng Boundary. | 135.54 | Champhai Division | 30.03.23 | 31.04.23 | 100% | 120.5 |  |  | 100% | 120.5 | Completed | Spot Quatation
523 | Bouldering of Road from ZBC Church to Mualnuam Road. | 15 | Champhai Division | 30.03.23 | 31.04.23 | 100% | 14.49 |  |  | 100% | 14.49 | Completed | Spot Quatation
524 | Const.and Widening of Road Zawlsei to Tuipui | 40 | Champhai Division | 30.03.23 | 31.04.23 | 100% | 38 |  |  | 100% | 38 | Completed | Spot Quatation
525 | Surfacing of Ruantlang Dawrkawn to CNV Road Via Lersia Field. | 17.3 | Champhai Division | 30.03.23 | 31.04.23 | 100% | 16.71 |  |  | 100% | 16.71 | Completed | Spot Quatation
526 | Patch Repair and Seal Coating of New Champhai to Tlangsam Road. | 25 | Champhai Division | 30.03.23 | 31.04.23 | 100% | 24.15 |  |  | 100% | 24.15 | Completed | Spot Quatation
527 | Pothole & Re-surfacing of Sasaw Road at Khawbung Internal Road (Khawbung to Tuipui Short Cut Road) | 42.28 | Champhai Division | 30.03.23 | 31.04.23 | 90% | 40.69 | 10% |  | 100% | 40.69 | Work in Progress | Spot Quatation
528 | Const. of Retaining Wall on Road Formation Collapse at 22.600 Kmp on Champhai to Khawbung Road. | 6.13 | Champhai Division | 30.03.23 | 31.04.23 | 100% | 5.9 |  |  | 100% | 5.9 | Liability | Spot Quatation
529 | Completion of Champhai - Zokhawthar Road under SASCI. 2023-2024 | 1311 | Champhai Division | 06.03.23 | 06.03.24 | 33% | 302.93 | 12% | 250 | 45% | 552.93 | Work in Progress | Restricted Tender
Construction of Hruaikawn - Zokhawthar Road (8.00 Km) 2023-2024
530 | Const. of Hruaikawn-Zokhawthar | 50 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
531 | Const. of Bungzung to Tuipui Road (Biate kai) Part-I | 100 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
532 | Const. of Vaphai to Chawngtui 'East' Road | 210 | Champhai Division | 05.10.23 | 05.10.24 |  |  | 25% |  | 25% |  | Work in Progress | Spot Quatation
533 | Const. of Approach Road to PHC at Bungzung | 60 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
534 | Const. of Bungzung to Zawngtetui Road | 280 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
Construction of Road from Samthang to Farkawn via Lamsial.
535 | Const. of Samthang to Farkawn via Lamsial Road | 350 | Champhai Division | 05.10.23 | 05.10.24 | 0.05% |  | 59.95% |  | 60% |  | Work stayed as per instruction from Ministry on 05.12.'23 | Spot Quatation
536 | Const. of Road from Selam to Tuisa Lui | 125 | Champhai Division | 05.10.23 | 05.10.24 | 100% |  |  |  | 100% |  | Phy.Completed | Spot Quatation
537 | Const. of Vanzau to Dungtlang (Balance work - Rocky portions)-I | 50 | Champhai Division | 05.10.23 | 05.10.24 | 0.05% |  | 59.95% |  | 60% |  | Work stayed as per instruction from Ministry on 05.12.'23 | Spot Quatation
Construction of Vaphai to Tiau Road
538 | Const. of Vaphai to Tiau Road | 200 | Champhai Division | 05.10.23 | 05.10.24 | 5% |  | 65% |  | 70% |  | Work in Progress | Spot Quatation
539 | Const. of Vanzau to Dungtlang Road Part - II | 70 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
540 | Const. of Sesih to Bulfek Road | 165 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
541 | Const. of Khawbung to Tuipui Shortcut Road (Balance portion) | 24.21 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
542 | Const. of Truck Lay by (Terminal) at Khuangleng | 10.79 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
543 | Const. of Pavillion at Farkawn (Frame Structure) | 30 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
Improvement & Widening of Road from Bungzung to R.Tuipui (Length = 5.00 Km)
544 | Improvement & Widening of Road Bungzung to Tuipui | 20 | Champhai Division | 05.10.23 | 05.10.24 | 0.01% |  | 9.99% |  | 10% |  | Work stayed as per instruction from Ministry on 05.12.'23 | Spot Quatation
545 | Const. of Road Leisenzo to Lianpui | 9 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
546 | Maintenance of Road Vangchhia to Lianpui | 9 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
547 | Const. of Road Khamkhanthanga's House to Bulfekzawl Road at Sesih | 4 | Champhai Division | 05.10.23 | 05.10.24 | 100% |  |  |  | 100% |  | Phy.Completed | Spot Quatation
548 | Maintenance of Road Khankawn to Tlawva | 9.5 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
549 | Maintenance of Road Thekte to Lurh-Zo | 3.5 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
550 | Const. of Gov't. Khuangthing M/S Court Yard PCC Flooring and Fencing. | 9 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
551 | Const. of PCC Flooring Internal Roads at Farkawn. | 30 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
552 | Const. of PCC Flooring from Kapchhunga's House to Singkawnga's House at Farkawn. | 4 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
553 | Const. of PCC Flooring from Theirekawn Culvert to Rinchhana's House at Farkawn. | 4 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
554 | Const. of PCC Flooring from Vanbiakawia House to Rinliana House at Farkawn. | 4 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
555 | Const. of PCC Flooring from Zasanga House to Hriattira House at Farkawn. | 4 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
556 | Const. of PCC Flooring from Kawn veng to Sub-Centre at Khawbung. | 3 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
557 | Const. of PCC Flooring from Lalnimawia House to Main Road at Khawbung. | 3 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
558 | Const. of PCC Flooring approach road Pathian veng Thlanmual at Khawbung. | 3 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
559 | Const. of PCC Flooring approach road Vengthlang Cemetary at Vaphai. | 3 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
560 | Const. of PCC Flooring between Water Reservoir and Challiana House at Vaphai. | 3 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
561 | Const. of PCC Flooring between Tialthuama House and Sanghnuna House at Vaphai. | 3 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
562 | Const. of PCC Flooring between High School and Nginliankhupa House at Khuangleng. | 9 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
563 | Const. of PCC Flooring J.Vanlalmawia House to Vety Quarter at Khuangleng. | 3 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
564 | Const. of PCC Flooring from Lalmuansanga House to Remmawia House at Khuangthing. | 5 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
565 | Const. of PCC Flooring approach road Gov't. P/S-I at Khuangthing. | 5 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
566 | Const. of PCC Flooring from Khummanga House to Tinngaihliana House at Sesih. | 5 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
567 | Const. of PCC Flooring & Step near Liandothanga House at Sesih. | 5 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
568 | Const. of PCC Flooring from Lalnunpuia House to Lalthlana House at Bungzung. | 7 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
569 | Const. of PCC Flooring approach road Cemetary at Samthang. | 3 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
570 | Const. of PCC Flooring near Lalhmunmawia House at Samthang. | 3 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
571 | Const. of PCC Flooring Lane chung road at Dungtlang. | 4 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
572 | Const. of PCC Flooring from Liandawnga House to Playground at Leisenzo. | 5 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
573 | Const. of PCC Flooring approach road Cemetary at Leisenzo. | 3 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
574 | Const. of PCC Flooring approach road Health Clinic Centre at Vangchhia. | 4 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
575 | Const. of PCC Flooring approach road Gov't. M/S at Vanzau. | 3 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
576 | Const. of PCC Flooring Sub-Centre approach road at Khankawn. | 4 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
577 | Const. of PCC Flooring Internal Road Lane hnuai at Lianpui. | 3 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
578 | Const. of PCC Flooring approach road Cemetary at Thekte. | 3 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
579 | Const. of PCC Flooring approach road Presby. Church at Leithum. | 3 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
580 | Const. of PCC Flooring Internal Road near Laldinmawia House at Sazep. | 3 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
581 | Const. of PCC Flooring approach road Gov't. P/S at Zawlsei. | 3 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
582 | Const. of PCC Flooring near Community Hall at Buang. | 3 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
583 | Const. of PCC Flooring from T.Hranglawta House to Chhunkhuma House at Bulfekzawl. | 3 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
584 | Const. of PCC Flooring from Waiting Shed to Cemetary at Hruaikawn. | 15 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
585 | Const. of PCC Flooring approach road Gov't. P/S at Thekpui. | 3 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
586 | Const. of PCC Flooring near Biakliana House at Zawngtetui. | 2 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
587 | Const. of PCC Flooring between Thangvhuanga House to Lalsawma House at Chawngtui 'E' | 2 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
588 | Const. of PCC Flooring Tiau road at Saikhumphai. | 1.5 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
589 | Const. of Side Drain from Lallianmanga House to Lalremruata House at N.Hruaikawn. | 2 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
590 | Const. of Zalhva Link Road Culvert at Samthang. | 2.5 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
Construction of PCC Pavement from Dilkawn to Kelkang (Length = 7.00 Km)
591 | Approach road for Tuipui Village from NH-6 with 1(one) Bridge (3Kms. Approx). | 20 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
592 | Const. of Road Kanan veng to Jail veng with Culvert. | 20 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
593 | Const. of PCC Flooring from Khawulh Peng to Presby. Church at Tlangnuam ,Vengthar. | 20 | Champhai Division | 05.10.23 | 05.10.24 | 0.1% |  |  |  | 0.1% |  | Work stayed as per instruction from Ministry on 05.12.'23 | Spot Quatation
594 | White-Topping of Road from KC Lalzarliana House to Chauleng Veng | 10 | Champhai Division | 05.10.23 | 05.10.24 | 0.1% |  |  |  | 0.1% |  | Work stayed as per instruction from Ministry on 05.12.'23 | Spot Quatation
595 | Widening and Bouldering of Road from Cold Storage, New Champhai to Tlangnuam Vengthar Presbyterian Church. | 10 | Champhai Division | 05.10.23 | 05.10.24 | 0.1% |  |  |  | 0.1% |  | Work stayed as per instruction from Ministry on 05.12.'23 | Spot Quatation
596 | Const. of Road from Zion Veng Thlanmual Peng to Emmanuel After Care Centre. | 10 | Champhai Division | 05.10.23 | 05.10.24 | 0.1% |  |  |  | 0.1% |  | Work stayed as per instruction from Ministry on 05.12.'23 | Spot Quatation
597 | White-Topping of Circular road from Pauchinthanga House to Thangkhanpuma House at Helipad Veng, New Champhai. | 10 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
598 | Const. of Side Drain from PWD Road near Lianthuama Car Wash to Petrol Pump, New Champhai. | 15 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
599 | Const. of White-topping of road from Community Hall to World Bank Road with 2 Culverts. | 10 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
600 | Widening of road between Lersia Field and Vanlaltluanga House. | 10 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
601 | Const. of Retaining Wall at Dilkawn | 10 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
602 | Const. of PCC Flooring from Saitawngkawn to Thlanmual. | 10 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
603 | Const. of PCC Flooring from B.Sanga House to Ramthanzauvi House at Melbuk. | 10 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
604 | Const. of PCC Flooring from Dilkawn to Kelkang. | 30 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
605 | Const. of Road from Hausiama Lungphun to Hmingzauva Leilet. | 30 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
606 | Const. of Road from Thangzuala House to Bangla Lui. | 30 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
607 | Widening of approach road from Melbuk to New Hruaikawn. | 5 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
608 | Const. of PCC Flooring from Hlunthanga House to Genesaret Gospel Home. | 5 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
609 | Const. of PCC Flooring from Zonunsiama House to P.School. | 5 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
610 | Const. of Black-Topping of Road from Thangzuala House to F.Lalhnawla House at Zotlang. | 10 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
611 | Const. of PCC Flooring at Hranga High School Tual, Kanan Veng. | 5 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
Construction of Road from Pamchung to Tualcheng (Length = 5.00 Kms)
612 | Improvement of Pamchung to Tualcheng (5.00 Kms.) | 150 | Champhai Division | 05.10.23 | 05.10.24 | 85% |  | 15% |  | 100% |  | Phy.Completed | Spot Quatation
613 | Const. of Hliappui to Aiduzawl. | 30 | Champhai Division | 05.10.23 | 05.10.24 | 100% |  |  |  | 100% |  | Clearance for Liability of SASCI - 2022-2023 | Spot Quatation
614 | Const. of Ngaizawl to Neihdawn. | 20 | Champhai Division | 05.10.23 | 05.10.24 | 100% |  |  |  | 100% |  | Clearance for Liability of SASCI - 2022-2023 | Spot Quatation
615 | Const. of PCC Flooring from Methodist Church to C.Zoramlawma House at Vengthlang, Champhai. | 15 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
616 | Const. of PCC Flooring from Rengchhuani House to Nukami House at Rahsi Veng, Champhai. | 10 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
617 | Const. of Side Drain & Culvert from Lalringa House to Challiankunga House at Kahrawt, Champhai. | 7 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
618 | PCC Flooring from Hospital Veng Biak In to Joseph Paua at Vengsang, Champhai | 10 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
619 | PCC Flooring from Leitlahniam to Lumikawr at IB veng, Champhai. | 10 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
620 | Const. of PCC Flooring from Dawrkawn to MUP House at Hnahlan | 10 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
621 | Const. of PCC Flooring from Community Hall to Ramnunsanga House, N.Diltlang. | 1 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
622 | Const. of PCC Flooring of Ngur High School Road, Ngur. | 5 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
623 | Const. of PCC Flooring at PHC, Rabung. | 5 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
624 | Const. of Agriculture Link Road from Selam to Leiva River, Selam. | 24 | Champhai Division | 05.10.23 | 05.10.24 | 100% |  |  |  | 100% |  | Phy.Completed | Spot Quatation
KOLASIB DIVISION :
625 | Resurfacing of Mizo Hotelpui to NH-306 via IACR | 65.01 | Kolasib Division | 01.04.23 | 01.04.24 | 100% | 65.01 |  |  | 100% | 65.01 | Completed
626 | Hume Pipe Culvert near SIRD Quarter, Vengthar | 3.85 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 3.85 |  |  | 100% | 3.85 | Completed
627 | Hume Pipe Culvert near Pu Sawma's House | 8.72 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 8.72 |  |  | 100% | 8.72 | Completed
628 | Extention of Hume Pipe Culvert near K.Saigina, Vengthar | 2.21 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 2.21 |  |  | 100% | 2.21 | Completed
629 | Const. of V-Shape SD at Essential Places on Mizo Hotelpui-NH 306 via IACR | 9.89 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 9.89 |  |  | 100% | 9.89 | Completed
630 | Embankment in front of Pu Laltanpuia's House Vengthar | 0.89 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 0.89 |  |  | 100% | 0.89 | Completed
631 | Road Widening below Remsiami's House, Vengthar | 0.125 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 0.125 |  |  | 100% | 0.125 | Completed
632 | : Road widening near Leitan, Vengthar | 0.89 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 0.89 |  |  | 100% | 0.89 | Completed
633 | Upgradation of CP Road, New Diakkawn Kolasib (Resurfacing of CP Road) | 26.09 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 26.09 |  |  | 100% | 26.09 | Completed
634 | Upgradation of CP Road, New Diakkawn Kolasib (Const.of LSD at CP Road) | 9.17 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 9.17 |  |  | 100% | 9.17 | Completed
635 | Improvement and Upgradation of Soil Peng to KVK (Kawnglaiphei) Resurfacing of Soil Dept.peng to KVK) | 52.39 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 52.39 |  |  | 100% | 52.39 | Completed
636 | Improvement and Upgradation of Soil Peng to KVK (Kawnglaiphei) Hume Pipe Culvert at Middle of the Road) ) | 3.209 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 3.2 |  |  | 100% | 3.2 | Completed
637 | Improvement and Upgradation of Soil Peng to KVK (Kawnglaiphei) (Extension of Downstream Hume Pipe Culvert near Pu Lalchhuanawma's House, Vengthar) | 2.636 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 2.636 |  |  | 100% | 2.636 | Completed
638 | Improvement and Upgradation of Soil Peng to KVK (Kawnglaiphei) (Extension of Hume Pipe Culvert near Pu Lalthana House, Vengthar) | 7.43 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 7.43 |  |  | 100% | 7.43 | Completed
639 | Improvement and Upgradation of Soil Peng to KVK (Kawnglaiphei) (Const.of LSD at Essential Places of Soil Dept.peng to KVK | 10.78 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 10.78 |  |  | 100% | 10.78 | Completed
640 | Improvement and Upgradation of Soil Peng to KVK (Kawnglaiphei) Road Widening near Saichhungi House, Vengthar | 0.47 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 0.47 |  |  | 100% | 0.47 | Completed
641 | Improvement and Upgradation of Soil Peng to KVK (Kawnglaiphei) (Road Widening near Masanga House to Pu Tanpuia House, Vengthar | 0.645 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 0.64 |  |  | 100% | 0.64 | Completed
642 | Kumtluang Run to Rammawia's House (Blacktopping) | 12.33 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 12.33 |  |  | 100% | 12.33 | Completed
643 | Const. of Breast Wall below Transformer on the road Kumtluang Run to Rammawia's House | 4.85 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 4.85 |  |  | 100% | 4.85 | Completed
644 | Const. of V-shape Side Drain on the Road Kumtluang Run to Rammawia's House | 16.58 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 16.58 |  |  | 100% | 16.58 | Completed
645 | Resurfacing of IACR to Dinthar Road | 22.09 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 22.09 |  |  | 100% | 22.09 | Completed
646 | Const. of LSD at Essential places on IACR to Dinthar Road | 6.93 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 6.93 |  |  | 100% | 6.93 | Completed
647 | Clearing and Grubbing of the Road | 0.74 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 0.74 |  |  | 100% | 0.74 | Completed
648 | Const. of Hume Pipe Culvert near Sericulture Complex on the road Hmar veng | 6.95 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 6.95 |  |  | 100% | 6.95 | Completed
649 | Const. of Hume Pipe Culvert near Bellei Lui | 5.7 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 5.7 |  |  | 100% | 5.7 | Completed
650 | Const. of Hume Pipe Culvert near Saidan Primary School | 5.7 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 5.7 |  |  | 100% | 5.7 | Completed
651 | SMBT of Hmarveng Tuikhur to NH-306 | 73.7 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 73.7 |  |  | 100% | 73.7 | Completed
652 | Resurfacing of Hmarveng to Saidan | 23.23 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 23.23 |  |  | 100% | 23.23 | Completed
653 | Hume Pipe Culvert below Pu Pakunga's House | 3.66 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 3.66 |  |  | 100% | 3.66 | Completed
654 | Const. of LSD at Essential places on Hmarveng to Saidan Field. | 5.92 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 5.92 |  |  | 100% | 5.92 | Completed
655 | Upgradation and Resurfacing of Helipad to Lungsumlui. | 19.75 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 19.75 |  |  | 100% | 19.75 | Completed
656 | Const. of LSD at Helipad to Lungsumlui | 1.5 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 1.5 |  |  | 100% | 1.5 | Completed
657 | Road Widening at Helipad to Lungsumlui | 22.71 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 22.71 |  |  | 100% | 22.71 | Completed
658 | Resurfacing of NH-306 to Challui Veng via Galili | 20.3 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 20.3 |  |  | 100% | 20.3 | Completed
659 | Cement Flooring of NH-306 to Challui Veng via Galili | 15.03 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 15.03 |  |  | 100% | 15.03 | Completed
660 | Const. of Retaining Wall near Pu Chuaudingliana's House | 3.62 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 3.62 |  |  | 100% | 3.62 | Completed
661 | Const. of LSD at essential places on NH-306 to Challui Veng via Galili. | 2.97 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 1.48 |  |  | 100% | 2.97 | Completed
662 | Lowering near Presbyterian Biakin | 1.12 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 1.12 |  |  | 100% | 1.12 | Completed
663 | PCC Flooring from NH-6 Rengtekawn Kualmawi to Hebron Veng | 28.97 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 28.97 |  |  | 100% | 28.97 | Completed
664 | PCC Flooring from PWD Town road near KVK Compound to Dinthar Vengthar | 28.98 | Kolasib Division | 2023-03-23 | 2023-03-24 | 100% | 28.98 |  |  | 100% | 28.98 | Completed
Const. of Road from Kawnpui to Bukpui Road (Length = 10.00 Kms) under SASCI 2023-2024
665 | Formation Cutting of Kawnpui to Bukpui Link Road. | 112 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not yet started | Restricted Tender
666 | Formation Cutting of Lungdai Dursaleng Bamboo Link Road to Tuirial. | 50 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not yet started | Restricted Tender
667 | Formation Cutting of Chhimveng Thlanmual to Chemlui (Raichawm zau) Link Road. | 35 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not yet started | Restricted Tender
668 | Formation Cutting of Zanlawn to Serlui Link Road | 30 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not yet started | Restricted Tender
669 | Formation Cutting/Widening of Ramnghaka Huan Kawn to Rophum Kawn Link Road at Thingdawl. | 20 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not yet started | Restricted Tender
670 | Formation Cutting of Kawnpui PHC to VC-II Field Approach Road. | 15 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not yet started | Restricted Tender
671 | Formation Cutting of Bamboo Link Road, Lungmuat to Tuirial. | 10 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not yet started | Restricted Tender
672 | Const. of Retaining Wall at N.Chaltlang near UPC Biakin. | 8 | Kolasib Division | 16.10.23 | 16.10.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
673 | Const. of RCC Slab Extention at Kawnpui Field No-II | 35 | Kolasib Division | 16.10.23 | 16.10.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
Const.of PCC Pavementfrom Hmarveng - Venglai - Diakkawn in Kolasib Town Part "A" ( SASCI : 2023-2024 )
674 | Works within Hmarveng VC area at Different Location. | 32.93 | Kolasib Division | 16.10.23 | 16.10.24 |  |  | 16.6% |  | 16.6% |  | Work in progress | Restricted Tender
675 | Works within Diakkawn VC area at Different Location. | 35.02 | Kolasib Division | 16.10.23 | 16.10.24 |  |  | 20% |  | 20% |  | Work in progress | Restricted Tender
676 | Works within Khuangpuilam VC area at Different Location. | 13.8 | Kolasib Division | 16.10.23 | 16.10.24 |  |  | 33.33% |  | 33.33% |  | Work in progress | Restricted Tender
677 | Works within New Diakkawn VC Area at Different Location. | 38.76 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not yet started | Restricted Tender
678 | Works within Project Veng VC Area at Different Location. | 45.49 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not yet started | Restricted Tender
679 | Works within Venglai East VC Area at Different Location. | 24.39 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not yet started | Restricted Tender
680 | Works within College Veng VC Area at Different Location. | 23.62 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not yet started | Restricted Tender
681 | Works within Tumpui Veng VC Area at Different Location. | 49 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not yet started | Restricted Tender
682 | Works within Electrict Veng VC Area at Different Location. | 22.22 | Kolasib Division | 16.10.23 | 16.10.24 |  |  | 75% |  | 75% |  | Work in progress | Restricted Tender
683 | Works within Saidan Veng VC Area at Different Location. | 34.29 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not yet started | Restricted Tender
684 | Works within Tuitha Veng VC Area at Different Location. | 23.59 | Kolasib Division | 16.10.23 | 16.10.24 |  |  | 33.33% |  | 33.33% |  | Work in progress | Restricted Tender
Const. of Rigid Pavement from Vairengte - Bilkhawthlir - Phainuam (SASCI : 2023-2024)
685 | Const. of Cement Concrete Pavement from Approach Road to Community Hall at Saiphai. | 35 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not yet started | Restricted Tender
686 | Const. of Panelled Concrete Pavement within Saipum Town. | 35 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not yet started | Restricted Tender
687 | Const. of PCC Flooring at N.Hlimen | 20 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not yet started | Restricted Tender
688 | Const. of PCC Flooring at Thingthelh | 10 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not yet started | Restricted Tender
689 | Const. of PCC Flooring at Rengtekawn. | 35 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not yet started | Restricted Tender
690 | Const. of PCC Flooring at N.Builum | 5 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not yet started | Restricted Tender
691 | Const. of PCC Flooring at Gosen Veng. | 5 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not yet started | Restricted Tender
692 | Const. of Panelled Concrete Pavement at Saihapui 'K' | 15 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not yet started | Restricted Tender
693 | Const. of Panelled Concrete Pavement at Bukvannei. | 15 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not yet started | Restricted Tender
694 | Const. of Panelled Concrete Pavement at N.Thinglian | 5 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not yet started | Restricted Tender
695 | Const. of Panelled Concrete Pavement at Buhchangphai | 20 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not yet started | Restricted Tender
696 | Const. of Panelled Concrete Pavement at N.Chhimluang | 10 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not yet started | Restricted Tender
697 | Const. of Panelled Concrete Pavement at N.Chawnpui | 10 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not yet started | Restricted Tender
698 | Const. of Panelled Concrete Pavement at Phaisen | 10 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not yet started | Restricted Tender
699 | Const. of Panelled Concrete Pavement at Phainuam | 35 | Kolasib Division | 16.10.23 | 16.10.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
700 | Const. of Panelled Concrete Pavement at Saihapui 'V' | 10 | Kolasib Division | 16.10.23 | 16.10.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
701 | Const. of Panelled Concrete Pavement at Bilkhawthlir | 65 | Kolasib Division | 16.10.23 | 16.10.24 |  |  | 100% |  | 100% |  | Phy.Completed | Restricted Tender
702 | Const. of Panelled Concrete Pavement at Vairengte | 80 | Kolasib Division | 16.10.23 | 16.10.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
703 | Const. of Formation Cutting at Phainuam to Bilkhawthlir, Buarchep Link Road. | 80 | Kolasib Division | 16.10.23 | 16.10.24 |  |  | 70% |  | 70% |  | Work in progress | Restricted Tender
Const. of PCC Pavement from Hmarveng - Venglai - Diakkawn in Kolasib Town PART "B" (SASCI : 2023-2024)
704 | Works within Hmarveng VC Area at Different Location. | 4.72 | Kolasib Division | 16.10.23 | 16.10.24 |  |  | 100% |  | 100% |  | Phy.Completed | Spot Quatation
705 | Works within Venglai VC Area at Different Location. | 13.16 | Kolasib Division | 16.10.23 | 16.10.24 |  |  | 83.33% |  | 83.33% |  | Work in progress | Spot Quatation
706 | Works within Diakkawn VC Area at Different Location. | 18.43 | Kolasib Division | 16.10.23 | 16.10.24 |  |  | 100% |  | 100% |  | Phy.Completed | Spot Quatation
707 | Works within Khuangpuilam VC Area at Different Location. | 15.05 | Kolasib Division | 16.10.23 | 16.10.24 |  |  | 100% |  | 100% |  | Phy.Completed | Spot Quatation
708 | Works within New Diakkawn VC Area at Different Location. | 19.58 | Kolasib Division | 16.10.23 | 16.10.24 |  |  | 100% |  | 100% |  | Phy.Completed | Spot Quatation
709 | Works within Project Veng VC Area at Different Location. | 25.06 | Kolasib Division | 16.10.23 | 16.10.24 |  |  | 100% |  | 100% |  | Phy.Completed | Spot Quatation
710 | Works within College Veng VC Area at Different Location. | 13.04 | Kolasib Division | 16.10.23 | 16.10.24 |  |  | 100% |  | 100% |  | Phy.Completed | Spot Quatation
711 | Works within Saidan Veng VC Area at Different Location. | 25.44 | Kolasib Division | 16.10.23 | 16.10.24 |  |  | 100% |  | 100% |  | Phy.Completed | Spot Quatation
Improvement of roads and Infrastructures at District Headquarters ;( Kolasib District) (SASCI : 2023-2024)
712 | Kolasib Town Roads: Resurfacing of Diakkawn Traffic Point to Police Station. | 15 | Kolasib Division | 31.10.23 | 29.02.24 |  |  | 100% |  | 100% |  | Phy.Completed | Departmental
713 | Patch Repair of Rengtekawn (NH-54) to Bawktlang (New Builum) 132 KV Sub-Station. | 31.5 | Kolasib Division | 31.10.23 | 29.02.24 | 5% |  | 95% |  | 100% |  | Phy.Completed | Departmental
714 | Patch Repair Serkhan to Bagha Road. | 69.5 | Kolasib Division | 31.10.23 | 29.02.24 | [6 empty] | Not yet started | Departmental
715 | Repair of SPT Bridge over R.Chepte & Sesih and Repair of Diversion Road with WBM. | 8.5 | Kolasib Division | 31.10.23 | 29.02.24 | 70% |  | 30% |  | 100% |  | Phy.Completed | Departmental
PROJECT DIVISION - I
716 | Extension of Community Hall at Upper Republic | 53 | Project Division-I | 15.3.23 | 15.2.24 | 90% | 39.82 | 10% |  | 100% | 39.82 | Phy.Completed
717 | Construction of RCC slab Dam veng YMA Hall | 4.83 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 4.81 |  |  | 100% | 4.81 | Completed
718 | Construction of Cequered tiles Near Local Council House Bungkawn Vengthar | 1.45 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 1.45 |  |  | 100% | 1.45 | Completed
719 | Construction of Saizahawla Tuikhur near R.Lalrinchhana Field Road | 7.72 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 7.68 |  |  | 100% | 7.68 | Completed
720 | Construction of RCC Structure at Electric Sub-Station, Khatla, Tlawng Road | 4.8 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 4.81 |  |  | 100% | 4.81 | Completed
721 | Laying of Chequered Tiles Between Zonghaka and Sk Thanga's House at Nursery | 2.12 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 2.11 |  |  | 100% | 2.11 | Completed
722 | Laying of Chequered Tiles tetween UPC (Mizoram) and RC Vanlalsawma (L) House at Nursery | 2.69 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 2.69 |  |  | 100% | 2.69 | Completed
723 | Construction of Chequered tiles near Khatla South Presbyterian | 1.43 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 1.43 |  |  | 100% | 1.43 | Completed
724 | Constrcution of Chequered tiles between J.Zangena House and Rinsanga Colney (L) near Khatla's Presbyterian Church | 0.98 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 0.49 |  |  | 100% | 0.49 | Completed
725 | Construction of Step Chequered tiles with Hand Railing near Khatla Pastor Quarter to J.Lianhlira House | 2.84 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 2.84 |  |  | 100% | 2.84 | Completed
726 | Renovation and linement of new Cemetary at Maubawk | 1.24 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 1.25 |  |  | 100% | 1.25 | Completed
727 | Renovation of Kanan Multipurpose Community Hall | 14.42 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 14.21 |  |  | 100% | 14.21 | Completed
728 | Renovation & Repair of Khatla Bazar Building | 3.86 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 3.86 |  |  | 100% | 3.86 | Completed
729 | Renovation of Mission Veng Health Clinic at Mission | 1.93 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 1.93 |  |  | 100% | 1.93 | Completed
730 | Construction of Anganwadi Centre-II, Aizawl | 4.79 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 4.79 |  |  | 100% | 4.79 | Completed
731 | Construction of Basketball Court at Dinthar | 52.99 | Project Division-I | 15.3.23 | 15.2.24 | 30% | 22.22 |  |  | 30% | 22.22 | Work in progress
732 | Construction of Basketball Court at Dinthar | 43.36 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 34.72 |  |  | 100% | 34.72 | Phy.Completed
733 | Construction of Basketball Court at Dinthar | 4.82 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 4.81 |  |  | 100% | 4.81 | Completed
734 | Renovation of Futsal Ground including Side Drain at Nursery veng | 4.4 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 4.4 |  |  | 100% | 4.4 | Contingencies of works
735 | Upgradation of Chief Minister Staff Quarter ( 5 nos of Quarters Phase-I | 193 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 191.07 |  |  | 100% | 191.07 | Completed
736 | Upgradation of Chief Minister Staff Quarter(5 nos of Qtrs Phase-II) | 95 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 78.89 |  |  | 100% | 78.89 | Phy.Completed | EPC
737 | Constructuction of Gov"t Staff Qtrs ( Block-C) at DIET Complex. | 544 | Project Division - I | 10.05.2023 | 10.05.2025 | 53% | 90.18 | 1% |  | 54% | 90.18 | Work in progress | EPC
738 | C/O Food Civil Supplies & Consumer Affairs 1500MTGodown at Sairang | 921 | Project Division - I | 20.4.23 | 20.4.26 | 15% | 144.83 |  | 2.45 | 15% | 147.29 | Work in progress | EPC
SASCI - 2023-2024 under Project Division - I
739 | Improvement of Government Buildings, High Court, Gov't Polytechnic & E-in-C PWD Office | 272.71 | Project Division - I |  |  |  |  | 66.66% |  | 66.66% |  | Work in progress | EPC
740 | Const. of Steps, Footpath, Bazar Shed, Hall Property House, Internal Road at Zemabawk, Thuampui, Zotlang, Chawnpui, Vaivakawn, Kanan. | 115 | Project Division - I |  |  |  |  | 10% |  | 10% |  | Work in progress | EPC
741 | Const. & Improvement of Public Buildings, YMA Zawlbuk at Chanmari West, Improvement of Electric Veng Hall | 188.29 | Project Division - I |  |  |  |  | 8.57% |  | 8.57% |  | Work in progress | EPC
742 | Const. & Improvement of Public Buildings. | 200 | Project Division - I |  |  |  |  | 10% |  | 10% |  | Work in progress | EPC
HMUIFANG DIVISION : 2022-2023
743 | Improvement & Strengthening of Aibawk-Darlung Road for 4.000-14.000 Kmp in Mizoram for the year 2022-2023 | 547 | Hmuifang Division | 20.12.23 | 31.03.23 | 95% | 455.28 | 5% | 91.69 | 100% | 546.97 | Work in progress
744 | Construction of Agriculture Link Road for Thingzam Zau, Tuirial Lui | 269.6 | Hmuifang Division | 15.02.23 | 14.05.23 | 100% | 247.92 |  | 1.8 | 100% | 249.72 | Completed
745 | Contsruction of Upgradation of Aizawl-Thenzawl-Lunglei Road 5.00 kmp-100.00 Kmp | 206 | Hmuifang Division | 15.02.23 | 14.05.23 | 100% | 177.56 |  | 21.27 | 100% | 198.83 | Phy.Completed
SASCI - 2023-2024 under Hmuifang Division.
746 | Strengthening of Aizawl-Thenzawl- Lunglei Road (83.00-100.00Kmp) | 1322 | Hmuifang division | 15.08.23 | 15.08.24 | 65% |  | 25% |  | 90% |  | Work in progress
747 | Const. of Agriculture Link Road to R.Mat from Chawilung, Lungsei, Samlukhai, Sialsuk. | 161.58 | Hmuifang division | 14.12.23 | 14.12.24 | 7.7% |  | 52.3% |  | 60% |  | Work in progress
748 | Improvement of Roads and Infrastructure at Aizawl City. | 30 | Hmuifang division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed
749 | Rigid Pavement of sinking area on Hualngohmun on Aizawl-Thenzawl -Lunglei Road. | 40.01 | Hmuifang division | 14.12.23 | 14.12.24 | 88.88% |  | 11.22% |  | 100% |  | Phy.Completed
750 | Completion of Approach Road to Upper Republic Thlanmual at Hualngohmun. | 2.5 | Hmuifang division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed
751 | Patch Repair of Maubuang approach road & Const. of Permanent Works at essential location on Maubuang. | 29.86 | Hmuifang division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed
KHAWZAWL DIVISION- 2022-2023
752 | Strengthening of approach road to IR Headquarter of Khawzawl in Mizoram for the year 2022-2023 under SASCI | 401 | Khawzawl Division | 15.02.23 | 30.06.23 | 100% | 391.86 |  | 4.49 | 100% | 396.35 | Completed | Departme-ntal
753 | Improvement of Farmual road at Khawzawl in Mizoram for the year 2022-2023 under SASCI | 343.5 | Khawzawl Division | 16.02.23 | 30.06.23 | 100% | 325.84 |  |  | 100% | 325.84 | Completed. | Departme-ntal
754 | Contsruction /Upgradation of Road from NE Khawdungsei-Tuivai-Mimbung in Mizoram for the year 2022-2023 under SASCI | 377 | Khawzawl Division | 15.02.23 | 31.03.23 | 100% | 392.49 |  |  | 100% | 392.49 | Completed | Spot Quotation
755 | Construction of Kawlkulh Bypass Road | 805 | Khawzawl Division | 01.02.23 | 30.06.23 | 21% | 328.82 | 1% | 156.63 | 22% | 485.45 | Work in progress | Restricted Tender
756 | Construction of road from Hliappui-Aiduzawl-Neihdawn in Mizoram for the year 2022-2023 under SASCI | 340 | Khawzawl Division | 15.02.23 | 30.06.23 | 100% | 316.04 |  |  | 100% | 316.04 | Phy.Completed | Restricted Tender
SASCI - 2023-2024 Under Khawzawl Division.
757 | Improvement & Strengthening of Vengthar Bazar toVengsang Presby. Church via Taidawnkawn at Khawzawl(Length: 7.50 KM) | 128.45 | Khawzawl Division | 3.10.23 | 3.4.24 | 36% |  | 64% |  | 100% |  | Phy.Completed | Spot Quotation
758 | Improvement of road at Chawngtlai - Biate - Ngopa- Khawhai & Pawlrang to Luangpawn | 166.5 | Khawzawl Division | 3.10.23 | 3.4.24 | 14% |  | 77% |  | 91% |  | Work in progress | Spot Quotation
759 | Const. of Agricultural Link road to Keltan Zau, Sihphai, Dawlzang, Lamzawl. (Length-8 Kms) | 101.1 | Khawzawl Division | 5.10.23 | 5.10.24 | 42% |  | 52% |  | 94% |  | Work in progress | Spot Quotation
760 | Improvement of roads and Infrastructures at District Headquarters ; Saiha, Lawngtlai, Lunglei, Hnahthial, Serchhip, Champhai, Khawzawl, Saitual, Kolasib and Mamit. | 168.7 | Khawzawl Division |  |  | 91% |  |  |  | 91% |  | Completed. (Committed Liability) | Spot Quotation
SAITUAL DIVISION :
761 | A.Section-I 1) Strengthening of Saitual-Phullen Road (28.30) Tuivawl-Phullen | 139.71 | Saitual Division | 13.2.2023 | 31.3.24 | 100% | 139.71 |  |  | 100% | 139.71 | Completed
762 | B.Section-II 1) Construction of concrete pavement between PWB IB to Thlanmual at Suangpuilawn & Improvement of Internal Roads | 28.98 | Saitual Division | 13.2.2023 | 31.3.24 | 100% | 28.98 |  |  | 100% | 28.98 | Completed
763 | 2) Construction of concrete pavement between Pu Zodinmawia's House to Lalsangbera's House at Vangbawng & Improvement of Internal Roads & Playground | 24.15 | Saitual Division | 13.2.23 | 31.3.24 | 100% | 24.15 | - |  | 100% | 24.15 | Completed
764 | 3) Construction of concrete pavement between RMSA school to Main road at Lamherh | 14.49 | Saitual Division | 13.2.23 | 31.3.24 | 100% | 14.49 | - |  | 100% | 14.49 | Completed
765 | 4) Construction and widening of road between N.Khawlek to Tuivawl Kai at N.Khawlek & Improvement of Internal Roads | 52.17 | Saitual Division | 13.2.23 | 31.3.24 | 100% | 52.17 | - |  | 100% | 52.17 | Completed
766 | 5) Construction of concrete pavement between Dawrkawn to High school at Khawlian & Improvement of Internal Roads | 35.75 | Saitual Division | 13.2.23 | 31.3.24 | 100% | 35.75 | - |  | 100% | 35.75 | Completed
767 | 6) Construction of concrete pavement between Anganwadi Centre I to YMA road at Phaibuang & Improvement of Internal Roads | 33.81 | Saitual Division | 13.2.23 | 31.3.24 | 100% | 33.81 |  |  | 100% | 33.81 | Completed
768 | 7) Construction of Approach Road to CC Puk at Luangpawn | 16.42 | Saitual Division | 13.2.23 | 31.3.24 | 100% | 16.42 |  |  | 100% | 16.42 | Completed
769 | 8) Construction of Community Hall at Phullen (Formation cutting and Retaining Wall) & Improvement of Internal Roads | 33.81 | Saitual Division | 13.2.23 | 31.3.24 | 100% | 33.81 |  |  | 100% | 33.81 | Completed
770 | 9) Widening of Mualkhang Road, Sihfa & Improvement of Internal Roads | 38.65 | Saitual Division | 13.2.23 | 31.3.24 | 100% | 38.65 | - |  | 100% | 38.65 | Completed
771 | 10) Improvement of High School Road, Daido | 9.66 | Saitual Division | 12.2.23 | 31.3.23 | 100% | 9.66 | - |  | 100% | 9.66 | Completed
772 | 11) PCC Flooring of Public Field Approach Road, Lailak & Improvement of Internal Roads | 19.32 | Saitual Division | 12.3.23 | 31.3.24 | 100% | 19.32 | - |  | 100% | 19.32 | Completed
| Improvement of Mualpheng to Maite Road |  | Saitual Division | 13.2.23 | 31.3.23 | 100% |  |  |  | 100%
773 | A.Section-I 1) Construction of Retaining Wall between main Road to Village extension peng at NE Tlangnuam | 9.66 |  |  |  |  | 9.66 |  |  |  | 9.66 | Completed
774 | 2) Widening cum PCC Flooring of Thlanmual Kawng. Thanglailung & Improvement of Internal Roads | 23.21 | Saitual Division | 13.2.23 | 31.3.23 | 100% | 23.21 | - |  | 100% | 23.21 | Completed
775 | 3) Formation cutting from Buhban to Tuivawl Road, Buhban | 28.98 | Saitual Division | 13.2.23 | 31.3.23 | 100% | 28.98 | - |  | 100% | 28.98 | Completed
776 | 4) PCC Flooring from Catholic Church to Presbyterian Church, Dilkhan & Improvement of Internal Roads | 14.49 | Saitual Division | 13.2.23 | 31.3.23 | 100% | 14.49 | - |  | 100% | 14.49 | Completed
777 | 5) PCC Flooring from Main Road to High School Road, N.Lungpher & Improvement of Internal Roads | 20.29 | Saitual Division | 13.2.23 | 31.3.23 | 100% | 20.29 | - |  | 100% | 20.29 | Completed
778 | 6) Construction of concrete pavement between Hmundo to Tuivawl at Zawngin & Improvement of Internal Roads | 19.32 | Saitual Division | 13.2.23 | 31.3.23 | 100% | 19.32 |  |  | 100% | 19.32 | Completed
779 | 7) Formation cutting of Khanpui road to Tlanghmawr Approach Road, Tualbung & Improvement of Internal Roads | 19.32 | Saitual Division | 13.2.23 | 31.3.23 | 100% | 19.32 | - |  | 100% | 19.32 | Completed
780 | B.Section-II 1) Resurfacing of Rulchawm to Ruallung | 85.64 | Saitual Division | 13.2.23 | 31.3.23 | 100% | 82.21 |  | 3.43 | 100% | 85.64 | Completed
781 | 2) Construction of Retaining Wall at 2.300 Km on Rulchawm - Mualpheng Road | 1.71 | Saitual Division | 13.2.23 | 31.3.23 | 100% | 1.71 | - |  | 100% | 1.71 | Completed
782 | 3) Construction of Retaining Wall at 2.50 Km on Rulchawm - Mualpheng Road | 5.32 | Saitual Division | 13.2.23 | 31.3.23 | 100% | 5032 | - |  | 100% | 5.32 | Completed
783 | 4) Construction of Retaining Wall at 4.70 Km on Rulchawm - Mualpheng Road | 3.55 | Saitual Division | 13.2.23 | 31.3.23 | 100% | 3.55 |  |  | 100% | 3.55 | Completed
784 | 5) Construction of Retaining Wall at 18.800 Km on Mualpheng - Maite Road | 3.34 | Saitual Division | 13.2.23 | 31.3.23 | 100% | 3.34 |  |  | 100% | 3.34 | Completed
785 | 6) Resurfacing of Ruallung - Maite Road up to Mualpheng | 211.69 | Saitual Division | 13.2.23 | 31.3.23 | 97% | 203.22 | 3% | 8.47 | 100% | 203.22 | Completed
786 | 7) Construction of RCC Side Drain between 0.400Km and 1.000 Km on Helipad Road, Saitual | 19.24 | Saitual Division | 13.2.23 | 31.3.23 | 100% | 19.24 |  |  | 100% | 19.24 | Completed
787 | 8) Construction of V Shape RCC Side Drain between 1.000 Km and 2.000 Km on Helipad Road, Saitual | 50.62 | Saitual Division | 13.2.23 | 31.3.23 | 100% | 50.62 |  |  | 100% | 50.62 | Completed
788 | 9) Construction of Retaining Wall at 18.900 Km on Mualpheng - Maite Road | 3.34 | Saitual Division | 13.2.23 | 31.3.23 | 100% | 3.34 |  |  | 100% | 3.34 | Completed
789 | 10) Construction of Retaining Wall at 0.70Km on Helipad Road, Saitual | 2.17 | Saitual Division | 13.2.23 | 31.3.23 | 100% | 2.17 |  |  | 100% | 2.17 | Completed
790 | 11) Construction of Retaining Wall at 0.90 Km on Helipad Road, Saitual | 2.22 | Saitual Division | 13.2.23 | 31.3.23 | 100% | 2.22 |  |  | 100% | 2.22 | Completed
791 | 12) Construction of Retaining Wall at 15.350 Km on Mualpheng - Maite Road | 4.28 | Saitual Division | 13.2.23 | 31.3.23 | 100% | 4.28 |  |  | 100% | 4.28 | Completed
792 | 13) Construction of RCC Covered Cross Drain at 1.250 Km on Helipad Road, Saitual | 2.67 | Saitual Division | 13.2.23 | 31.3.23 | 100% | 2.67 |  |  | 100% | 2.67 | Completed
793 | 14) Construction of Rigid Pavement of DC Complex Road, Saitual | 183.86 | Saitual Division | 13.2.23 | 31.3.23 | 100% | 183.86 |  |  | 100% | 183.86 | Completed
TLABUNG DIVISION :
794 | Strengthening of Phairuang - Thenhlum Road Group-A | 146.09 | Tlabung Division | 2023-03-01 | March-2024 | 100% | 138.79 |  |  | 100% | 138.79 | Completed
881
795 | Strengthening of Phairuang - Thenhlum Road Group-B | 211.71 | Tlabung Division | 2023-03-23 | March-2024 | 100% | 201.13 |  |  | 100% | 201.13 | Completed
796 | Strengthening of Phairuang - Thenhlum Road Group-C | 135.06 | Tlabung Division | March 2023 | March-2024 | 100% | 129.29 |  |  | 100% | 129.29 | Completed Phy.Works
PROJECT DIVISION - II :
797 | Construction of Public Playground at Thenzawl (Sh: Const.of Public Playgound Galley of length 120 metre (6 block of 20 metre each including 3 (three) steps for sitting at Thenzawl | 25 | Project Division-II | 26.02.23 | 26.08.23 | 100% | 12.5 |  |  | 100% | 12.5 | Completed Phy.Works | Item Rate
798 | Construction of Community Hall at Chawilung (Sh: Construcytion of Steel Truss with dyna roofing) | 6 | Project Division-II | 24.02.23 | 24.04.23 | 100% | 3 |  |  | 100% | 3 | Completed Phy.Works | Item Rate
799 | Construction of Community Hall at Hualngohmun (Sh: Construction of Steel Truss with dyna roofing) | 8 | Project Division-II | 24.02.23 | 24.04.23 | 100% | 4 |  |  | 100% | 4 | Completed Phy.Works | Item Rate
800 | Construction of MUP House at Zamuang, Mamit District | 15 | Project Division-II | 26.02.23 | 26.06.23 | 100% | 7.5 |  |  | 100% | 7.5 | Completed Phy.Works | Item Rate
801 | Construction of Urinal Sheds (sh: Near Rambeiseia In, BBEC Pastor Qtrs, Pu Lalzama House, Lalaithai's House, C.Laltanpuia House, Darlak Peng at Tuidam, Urinal Sheds at Vengthar, W.Bunghmun, H/S Veng at Bunghmun, Near Baptist Church at New Eden, near Presbyterian Church at New Eden) | 5 | Project Division-II | 24.02.23 | 24.04.23 | 100% | 2.5 |  |  | 100% | 2.5 | Completed Phy.Works | Item Rate
802 | Construction of waiting Sheds (Sh: Const.of Waiting shed at Dilpeng, Kawrtethawveng 2. Repair of Waiting Shed at New Kawnpui Village 3. Construction of Buhfai Semna/Dahna Teireikam at Kananthar). | 7.5 | Project Division-II | 24.02.23 | 24.04.23 | 100% | 3.75 |  |  | 100% | 3.75 | Completed Phy.Works | Item Rate
803 | Construction of Pavement of Chequered Tiles (Sh: Near Pi Duhkungi House to Kawnghnuai at Tuidam 2. Ramrikawn to Pi Rinngaii In Kawng at Kawrtethawveng 3. Mualzawl (Hmarveng) to Arm Veng 4. KDZKT Road to Internal Road near Pi Nuntluangi In at Kawrtethawveng 5. Chequered Tile phah, step Repair approach to Tuikhuah tuikhur panna at Kawrtethawveng) | 9.5 | Project Division-II | 24.02.23 | 24.04.23 | 100% | 4.75 |  |  | 100% | 4.75 | Work phy.completed | Item Rate
804 | Construction of Tourist Lodge at Kawnpui | 50 | Project Division-II | 26.02.23 | 26.10.23 | 90% | 25 | 10% |  | 100% | 25 | Work in progress | Item Rate
805 | Construction of Futsal Ground at Kawnpui Chhimveng | 25 | Project Division-II | 25.02.23 | 25.06.23 | 85% | 12.5 | 3% |  | 88% | 12.5 | Work in progress | Item Rate
806 | Continuation of Public Playground at Serkhan | 15 | Project Division-II | 25.03.23 | 25.05.23 | 100% | 7.5 |  |  | 100% | 7.5 | Phy.Completed | Item Rate
807 | Construction of Community Hall at Hortoki | 70 | Project Division-II | 26.02.23 | 26.10.23 | 100% | 35 |  |  | 100% | 35 | Phy.Completed | Item Rate
808 | Continuation of Public Playground at Zanlawn | 15 | Project Division-II | 25.02.23 | 25.05.23 | 97% | 7.5 | 1% |  | 98% | 7.5 | Work in progress | Item Rate
809 | Continuation of Public Playground at Bualpui | 15 | Project Division-II | 25.02.23 | 25.05.23 | 100% | 7.5 |  |  | 100% | 7.5 | Phy.Completed | Item Rate
810 | Construction of Bazar Shed at Nisapui | 15 | Project Division-II | 25.02.23 | 25.05.23 | 100% | 7.5 |  |  | 100% | 7.5 | Phy.Completed | Item Rate
811 | Continuation of Futsal Ground at Lungdai | 25 | Project Division-II | 25.02.23 | 25.06.23 | 100% | 12.5 |  |  | 100% | 12.5 | Phy.Completed | Item Rate
SASCI : 2023-2024 Under Project Division - II
812 | Const. of Public Meeting Hall at Chamring | 7.5 | Project Division-II | 13.03.24 | 15.10.24 |  |  | 1% |  | 1% |  | Work in progress | Item Rate
813 | Const. of Health Clinic Building at Aibawk. | 6.5 | Project Division-II | 13.03.24 | 15.10.24 |  |  | 1% |  | 1% |  | Work in progress | Item Rate
814 | Partial Re-const. of Community Hall at Kelsih. | 11 | Project Division-II | 13.03.24 | 15.10.24 | [6 empty] | Not yet started | Item Rate
815 | Extention of Melthum Community Hall. | 34 | Project Division-II | 13.03.24 | 15.10.24 | [6 empty] | Not yet started | Item Rate
816 | Extention of YMA House at Saikhamakawn. | 20 | Project Division-II | 13.03.24 | 15.10.24 |  |  | 2% |  | 2% |  | Work in progress | Item Rate
817 | Const. of Samtlang High School Building. | 20 | Project Division-II | 13.03.24 | 15.10.24 | [6 empty] | Not yet started | Item Rate
818 | Const. of Futsal Ground at Hortoki. | 20 | Project Division-II | 13.03.24 | 15.10.24 | 60% |  | 20% |  | 80% |  | Work in progress | Item Rate
819 | Const. of Public Playground Pavillion & Fencing at Bukpui. | 15 | Project Division-II | 13.03.24 | 15.10.24 | 10% |  | 10% |  | 20% |  | Work in progress | Item Rate
820 | Const. of Public Playground Pavillion & Fencing at N.Chaltlang-I | 15 | Project Division-II | 13.03.24 | 15.10.24 | 30% |  | 10% |  | 40% |  | Work in progress | Item Rate
821 | Const. of Gurkha Community Hall at Bualpui. | 15 | Project Division-II | 13.03.24 | 15.10.24 | 15% |  | 10% |  | 25% |  | Work in progress | Item Rate
822 | New Const. of Futsal Ground at Lungmuat. | 10 | Project Division-II | 13.03.24 | 15.10.24 | 80% |  | 10% |  | 90% |  | Work in progress | Item Rate
823 | Continuation of Public Playground at Serkhan. | 10 | Project Division-II | 13.03.24 | 15.10.24 | 90% |  | 10% |  | 100% |  | Phy.Completed | Item Rate
824 | Renovation of Polytechnic Building at Thingdawl. | 49 | Project Division-II | 13.03.24 | 15.10.24 | 90% |  | 10% |  | 100% |  | Phy.Completed
825 | Const. of Playground at Tuipuibari, Tuirum, Dapchhuah, New Mamit, Rajivnagar-I | 245 | Project Division-II | 13.03.24 | 15.10.24 | 49.37% |  |  |  | 49.37% |  | Work in progress | Item Rate
PROJECT DIVISION - III : (2023-2024 )
826 | Construction of Govt.Serchhip College (Sh: Adninistrative Block) | 650 | Project Division-III | 27.02.23 | 27.02.25 | 32% | 91.04 | 2% |  | 34% | 91.04 | work in progress | PWD Form-8
827 | Const. of Football ground and Volleyball court at Vapar, Selam, Tualcheng, Hnahlan, Hmunhmeltha | 203 | Project Division-III | 13.10.23 | 13.10.24 | 18% |  | 17% |  | 35% |  | work in progress | PWD Form-8
828 | Const. of Khawbung Futsal ground, Gallery, Roofing, Lighting & Laying of Artificial Turf | 255.5 | Project Division-III | 14.10.23 | 14.10.24 | 2% |  | 2% |  | 4% |  | work in progress | PWD Form-8
829 | Const. of Community Hall at Dulte & Chhawrtui | 271 | Project Division-III | 13.10.23 | 13.10.24 | 2% |  |  |  | 2% |  | work in progress | PWD Form-8
830 | Development of Community Centre at Zotlang, Champhai (Sh: Const. of Market Building cum Community Hall & Futsal Ground) | 215 | Project Division-III | 14.10.23 | 14.10.24 | 2% |  | 2% |  | 4% |  | work in progress | PWD Form-8
831 | Additional works for Const. of General Nursing Midwifery (GNM) hostel and Nursing Hostel at Champhai | 438 | Project Division-III | 13.10.23 | 13.10.24 | 18% |  | 7% |  | 25% |  | work in progress | PWD Form-8
832 | Const. of Public Playground at Keitum, Lungchhuan. | 250 | Project Division-III | 13.10.23 | 13.10.24 | 2% |  | 10% |  | 12% |  | work in progress | PWD Form-8
833 | Const. of Gov't. Building at Serchhip District (Sh: PWD Staff Quarters, Extension of Gov't. Serchhip Cillege and Kitchen Cum Dining at PTS, Thenzawl, Mizoram) | 362 | Project Division-III | 13.10.23 | 13.10.24 | 3% |  | 10% |  | 13% |  | work in progress | PWD Form-8
834 | Const. of Community Resource Center at Baktawng and Chhuanthar | 350 | Project Division-III | 13.10.23 | 13.10.24 | 2% |  | 3% |  | 5% |  | work in progress | PWD Form-8
835 | Const. of Community Hall at Khawzawl Vengthar, Arro Village, khawzawl Dinthar and Khawhai South | 209 | Project Division-III | 13.10.23 | 13.10.24 | 4% |  | 26% |  | 30% |  | work in progress | PWD Form-8
LUNGLEI ROAD DIVISION -I, SASCI : 2022-2023
836 | Improvement of Chanmari - Electric Veng - Ramthar Veng at Lunglei. | 199.01 | Lunglei Road Division-I |  |  | 100% | 149.01 |  |  | 100% | 149.01 | Phy.Completed | Spot Quotation
837 | Improvement of Tlabung Road - Thuamluaia Mual - College Veng - Rahsi Veng, Lunglei. | 362.27 | Lunglei Road Division-I |  |  | 100% | 362.19 |  |  | 100% | 362.19 | Completed | Spot Quotation
838 | Strengthening and Resurfacing of Aizawl - Thenzawl - Lunglei Road from 160.00-164.00 Kmp (Kikawn - AOC veng, Lunglei | 590.07 | Lunglei Road Division-I |  |  | 100% | 590.06 |  |  | 100% | 590.06 | Completed | Spot Quotation
839 | Working estimate for Const. of RCC Pavement and Culverts from Bunghmun-Thenhlum - Lungchem. | 231.28 | Lunglei Road Division-I |  |  | 100% | 197.34 |  |  | 100% | 197.34 | Completed | Spot Quotation
840 | Construction of pavement on Approach Road to Pialthleng at Lunglei District | 724.85 | Lunglei Road Division -I | 24.03.23 | 24.03.24 | 57% | 119.96 | 16% | 275.98 | 73% | 395.94 | Work in Progress | Restricted Tender
841 | Aizawl- Thenawl- Lunglei Road between Kanghmun 'S' and Kikawn, Lunglei Phase - I, (Sh: Group - A Between 100.00-120.00 Kmp) | 647.09 | Lunglei Road Division -I | 03.07.23 | 03.07.24 | 37% |  | 1% |  | 38% |  | Work in progress | Restricted Tender
842 | Aizawl- Thenawl- Lunglei Road between Kanghmun 'S' and Kikawn, Lunglei Phase - I, (Sh: Group - B Between 120.00-143.00 Kmp) | 658.16 | Lunglei Road Division -I | 26.06.23 | 26.06.24 | 67% |  |  |  | 67% |  | Work in progress | Restricted Tender
SASCI : 2023-2024 under Lunglei Road Division- I
843 | Improvement of Bazar Veng - College Veng - Venghlun at Lunglei District. | 130.05 | Lunglei Road Division -I |  |  |  |  | 32.42% |  | 32.42% |  | Work in progress
845 | Const. of Bamboo Link Road Phunchawngzau at Pukpui. | 76.92 | Lunglei Road Division -I |  |  |  |  | 26.66% |  | 26.66% |  | Work in progress
846 | Const. of Link Road from Vaisam Tlang - Zawlte - Phunchawng at Bunghmun. | 95.08 | Lunglei Road Division -I |  |  |  |  | 20% |  | 20% |  | Work in progress
LUNGLEI ROAD DIVISION - II
Improvement & Upgradation of Roads from Hnahthial to Thingsai
Improvement and upgradation of Hnahthial - Thingsai Road (50.00 lakhs)
847 | (a) Retaining Wall on H-T at Ch.3.750 Kmp | 5.18 | Lunglei Road Division-II | 16.03.23 | 15.03.24 | 100% | 5.18 |  |  | 100% | 5.18 | Completed | Spot Quotation
848 | (b) Retaining Wall on H-T at Ch. 5.450 Kmp | 6.62 | Lunglei Road Division-II | 16.03.23 | 15.03.24 | 100% | 6.62 |  |  | 100% | 6.62 | Completed | Spot Quotation
849 | © Retaininh Wall on H-T at Ch. 9.450 Kmp | 5.55 | Lunglei Road Division-II | 16.03.23 | 15.03.24 | 100% | 5.55 |  |  | 100% | 5.55 | Completed | Spot Quotation
850 | (d) Retaining Wall on H-T at Ch. 43.300 Kmp | 2 | Lunglei Road Division-II | 16.03.23 | 15.03.24 | 100% | 2 |  |  | 100% | 2 | Completed | Spot Quotation
851 | (e) Improvement and widening of H-T Road at Ch. 3.550 - 3.610 Kmp | 7.65 | Lunglei Road Division-II | 16.03.23 | 15.03.24 | 100% | 7.65 |  |  | 100% | 7.65 | Completed | Spot Quotation
852 | Resurfacing of Hnahthial - Tumtukawn Road at Ch. 5.000-6.00 Kmp | 23 | Lunglei Road Division-II | 16.03.23 | 15.03.24 | 100% | 23 |  |  | 100% | 23 | Completed | Spot Quotation
853 | Construction of Darzo (Kawipui) Saibuchhuah Road | 100 | Lunglei Road Division-II | 16.03.23 | 15.03.24 | 100% | 100 |  |  | 100% | 100 | Completed | Spot Quotation
854 | Improvement of Internal Road within Thingsai Village | 50 | Lunglei Road Division-II | 16.03.23 | 15.03.24 | 100% | 50 |  |  | 100% | 50 | Completed | Spot Quotation
855 | PCC Flooring of Tarpho to Aithur Roas | 170 | Lunglei Road Division-II | 16.03.23 | 15.03.24 | 100% | 170 |  |  | 100% | 170 | Completed | Spot Quotation
856 | PCC pavement from MTR (Road) Tuipui D to Nghafuan (R.Tuipui) Road | 80 | Lunglei Road Division-II | 16.03.23 | 15.03.24 | 100% | 80 |  |  | 100% | 80 | Completed | Spot Quotation
857 | (g) Improvement of road from Hnahthial Town to Takam tlaw | 50 | Lunglei Road Division-II | 16.03.23 | 15.03.24 | 100% | 50 |  |  | 100% | 50 | Completed | Spot Quotation
Construction and Upgradation of Road from Bualpui V to River Mat via Lungmawi
858 | (a) Strengthening/Widening of Road between Bualpui V to River Mat via Lungmawi | 100 | Lunglei Road Division-II | 16.03.23 | 15.03.24 | 100% | 74.5 |  |  | 100% | 74.5 | Phy.Completed | Spot Quotation
859 | (b) Const./FC of Road between Pangzawl to Tuichang | 30 | Lunglei Road Division-II | 16.03.23 | 15.03.24 | 100% | 30 |  |  | 100% | 30 | Completed | Spot Quotation
860 | (c) Improvement of Internal Road between main Pangzawl Village to upper Pangzawl | 30 | Lunglei Road Division-II | 16.03.23 | 15.03.24 | 100% | 30 |  |  | 100% | 30 | Completed | Spot Quotation
861 | (d) Const./FC of Agriculture Link Road at Thiltlang | 15 | Lunglei Road Division-II | 16.03.23 | 15.03.24 | 100% | 15 |  |  | 100% | 15 | Completed | Spot Quotation
862 | (e) Const./FC of Agriculture Link Road at Rawpui | 10 | Lunglei Road Division-II | 16.03.23 | 15.03.24 | 100% | 10 |  |  | 100% | 10 | Completed | Spot Quotation
863 | (f) Const./FC within Agriculture Link Road at Phaileng S | 10 | Lunglei Road Division-II | 16.03.23 | 15.03.24 | 100% | 10 |  |  | 100% | 10 | Completed | Spot Quotation
864 | (g) Const of PCC Pavement from Haulawng to Community Hall | 8 | Lunglei Road Division-II | 16.03.23 | 15.03.24 | 100% | 8 |  |  | 100% | 8 | Completed | Spot Quotation
865
Construction and Upgradation of Retaining Wall at Zobawk Ringroad
865 | (1) Re-Construction of permanent works at Tawipui N Mualcheng S at chainage 1.00 kmp, 2.500 kmp, 3.700 kmp, 3.720 kmp & 5.500 kmp | 38.4 | Lunglei Road Division-II |  |  | 100% | 38.4 | - |  | 100% | 38.4 | Completed | Spot Quotation
866 | (2) Construction of PCC pavement Vanlalhmuaki House to Middle School Road at Lungpuizawl | 4 | Lunglei Road Division-II |  |  | 100% | 4 |  |  | 100% | 4 | Completed | Spot Quotation
867 | (3) Construction of PCC Pavement at Hmingthana House to HS Lalhmunmawia House at Lungpuizawl | 3 | Lunglei Road Division-II |  |  | 100% | 3 |  |  | 100% | 3 | Completed | Spot Quotation
868 | (4) Construction of PCC Pavement PCI Biakin to Public Playground at Lungpuizawl | 3 | Lunglei Road Division-II |  |  | 100% | 3 |  |  | 100% | 3 | Completed | Spot Quotation
869 | (5) Construction of Retaining wall at NEI UPC Zobawk Local at Zobawk S | 9 | Lunglei Road Division-II |  |  | 100% | 9 |  |  | 100% | 9 | Completed | Spot Quotation
870 | (6) Construction of Retaining Wall at Zobawk Venglai near Community Hall at Zobawk Venglai | 5 | Lunglei Road Division-II |  |  | 100% | 5 |  |  | 100% | 5 | Completed | Spot Quotation
871 | Construction of Internal Road with Widening from Pu Kawlramtawna House to Tuitai Kawi at Zobawk Venglai | 9.5 | Lunglei Road Division-II |  |  | 100% | 9.5 |  |  | 100% | 9.5 | Completed | Spot Quotation
872 | Construction of PCC Pavement Public playground to Transformer at Zobawk Vengthar | 4.5 | Lunglei Road Division-II |  |  | 100% | 4.5 |  |  | 100% | 4.5 | Completed | Spot Quotation
873 | Construction of PCC Pavement Zabuanga House to Zailawma House at Zobawk Vengthar | 6 | Lunglei Road Division-II |  |  | 100% | 6 |  |  | 100% | 6 | Completed | Spot Quotation
874 | Construction of Retaining Wall near Gov"t High School Road (Hmawng hnuai) at Zobawk Vengthar | 6 | Lunglei Road Division-II |  |  | 100% | 6 |  |  | 100% | 6 | Completed | Spot Quotation
875 | Const.of Retaining Wall at B.Laltanpuia house at Zobawk Venghlun | 5 | Lunglei Road Division-II |  |  | 100% | 2.5 |  | 2.5 | 100% | 5 | Phy.Completed | Spot Quotation
876 | Construction of PCC pavement between C.Vanlalhmuaka House to P.Lalromawia House at Zobawk Bazar | 10 | Lunglei Road Division-II |  |  | 100% | 5 |  | 5 | 100% | 10 | Phy.Completed | Spot Quotation
877 | Construction of PCC pavement between Ralvawng mual Volley Ball Court at Zobawk Bazar | 5.5 | Lunglei Road Division-II |  |  | 100% | 2.75 |  | 2.75 | 100% | 5.5 | Phy.Completed | Spot Quotation
878 | Const.of PCC Pavement between Pu Lallawma House to Pu V.Zoramthanga house at Zobawk Venghlun | 6 | Lunglei Road Division-II |  |  | 100% | 3 |  | 3 | 100% | 6 | Phy.Completed | Spot Quotation
879 | Construction of RCC Steps C.Lalchungnunga House to Lallianpuii House at Zobawk Venghlun | 4.5 | Lunglei Road Division-II |  |  | 100% | 2.25 |  | 2.25 | 100% | 4.5 | Phy.Completed | Spot Quotation
880 | Repairing and Widening of Road, Sairep to Hlumte Road | 12 | Lunglei Road Division-II |  |  | 100% | 12 |  |  | 100% | 12 | Completed | Spot Quotation
881 | Construction of Retaining Wall near BCM Biakin and Lalramlawma House between Lalnunhlua house at Hlumte | 4 | Lunglei Road Division-II |  |  | 100% | 4 |  |  | 100% | 4 | Completed | Spot Quotation
882 | Construction of Bawkzau (Sairep village potential area) Link Road from Sairep Village | 40 | Lunglei Road Division-II |  |  | 100% | 40 |  |  | 100% | 40 | Completed | Spot Quotation
IMPROVEMENT OF HNAHTHIAL TOWN ROAD
883 | SMBT of approach Road to HDFA Playground | 63.6 | Lunglei Road Division-II |  |  | 100% | 63.6 |  |  | 100% | 63.6 | Completed | Spot Quotation
884 | Resurfacing within Hnahthial Town | 31.51 | Lunglei Road Division-II |  |  | 100% | 31.51 |  |  | 100% | 31.51 | Completed | Spot Quotation
885 | RCC Drain on approach Road to DC Office | 3 | Lunglei Road Division-II |  |  | 100% | 3 |  |  | 100% | 3 | Completed | Spot Quotation
886 | Retaining wall at Ch: 0.4 Km on approach Road to Zosangliana House to Lalduhawma House | 1.89 | Lunglei Road Division-II |  |  | 100% | 1.89 |  |  | 100% | 1.89 | Completed | Spot Quotation
Construction of Pavement at Tawipui S - Tawipui N
887 | (i) Const.of PCC Pavement Tawipui S approach road | 30 | Lunglei Road Division-II |  |  | 100% | 30 |  |  | 100% | 30 | Completed | Spot Quotation
888 | (ii) Construction of PCC Pavement Tawipui N-II HS approach road | 40 | Lunglei Road Division-II |  |  | 100% | 40 |  |  | 100% | 40 | Completed | Spot Quotation
889 | (iii) Const.of PCC Pavement Road from Tawipui S Bazar (NH 54) to Hermon Veng | 45 | Lunglei Road Division-II |  |  | 100% | 45 |  |  | 100% | 45 | Completed | Spot Quotation
890 | (iv) Const.of PCC Pavement Road from NH 54 to Thualthu Bazar to Upper Thaulthu | 45 | Lunglei Road Division-II |  |  | 100% | 45 |  |  | 100% | 45 | Completed | Spot Quotation
891 | (v) Const.of Thangpui and Thangte Village Road from Vaisam PMGSY Road (at Thangpui Khawhnuai Chainage) | 40 | Lunglei Road Division-II |  |  | 100% | 40 |  |  | 100% | 40 | Completed | Spot Quotation
892 | (vi) Cons.of Ngengpui Zau Link road from Thlisam Road | 25 | Lunglei Road Division-II |  |  | 100% | 25 |  |  | 100% | 25 | Completed | Spot Quotation
893 | (vii) Const.of Mat Zau Link road from Tawipui N-II | 50 | Lunglei Road Division-II |  |  | 100% | 50 |  |  | 100% | 50 | Completed | Spot Quotation
894 | (viii) Const.of Ruangte river zau Link road from Vaisam PMGSY Road | 20 | Lunglei Road Division-II |  |  | 100% | 20 |  |  | 100% | 20 | Completed | Spot Quotation
CONST. & UPGRADATION OF RETAINING WALL AT ZOBAWK RINGROAD :
895 | Construction of link road Silaitlak (Balu lakna) Road at Rotlang 'E' | 5 | Lunglei Road Division-II |  |  | 100% | 5 |  |  | 100% | 5 | Completed | Spot Quotation
896 | Construction PCC Pavement at High School Road at Rotlang 'E' | 6 | Lunglei Road Division-II |  |  | 100% | 6 |  |  | 100% | 6 | Completed | Spot Quotation
897 | Const. PCC Pavement near F.Malsawmthanga House at Rotlang 'E' | 2 | Lunglei Road Division-II |  |  | 100% | 2 |  |  | 100% | 2 | Completed | Spot Quotation
898 | Construction of Retaining Wall at Middle School at Rotlang 'E' | 2 | Lunglei Road Division-II |  |  | 100% | 2 |  |  | 100% | 2 | Completed | Spot Quotation
899 | Construction of Waiting Shed at Chinrang Kawn and Ramrikawn at Ralvawng | 3 | Lunglei Road Division-II |  |  | 100% | 3 |  |  | 100% | 3 | Completed | Spot Quotation
900 | Construction of Link Road at New Ralvawng to Old Ralvawng | 5 | Lunglei Road Division-II |  |  | 100% | 5 |  |  | 100% | 5 | Completed | Spot Quotation
901 | Construction of PCC Pavement from Ramthim Dawr to Govt. Primary School at Leite | 3 | Lunglei Road Division-II |  |  | 100% | 3 |  |  | 100% | 3 | Completed | Spot Quotation
902 | Construction of PCC Step with Railing and Side Drain between NH-54 to K.Vanramenga House at Leite | 7 | Lunglei Road Division-II |  |  | 100% | 7 |  |  | 100% | 7 | Completed | Spot Quotation
SASCI : 2023-2024 Under Lunglei Road Division - II
903 | Const. of PCC Road to Public Playground at Zobawk South. | 71 | Lunglei Road Division-II |  |  |  |  | 29% |  | 29% |  | Work in progress
904 | Const. of Bamboo Link Road at Phunchawngzau, Pukpui (Group-B) | 85 | Lunglei Road Division-II |  |  | 40% |  | 20% |  | 60% |  | Work in progress
905 | Improvement of Hnahthial to Takam Tiau Road. | 183.34 | Lunglei Road Division-II |  |  |  |  | 17% |  | 17% |  | Work in progress
906 | Const. of Agriculture Link Road between Tuikhurhlu to Batluang at Pangzawl. | 97.09 | Lunglei Road Division-II |  |  | 70% |  | 21.88% |  | 91.88% |  | Work in progress
SIAHA DIVISION :
907 | Strengthening and Improvement of Kawlchaw to Serkawr Road | 318 | Siaha Division | 21.03.23 | 21.03.24 | 87.21% | 165.78 | 12.79% | 149.45 | 100% | 315.23 | Completed | Item rate Contract
908 | Improvement and Upgradation of Siaha to Thingsen Road upto NH 54B Junction (7.00km) | 778.53 | Siaha Division | 21.03.23 | 21.03.24 | 30.4% | 27.82 | 8.25% | 195.51 | 38.65% | 223.33 | Work in progress. | Item rate Contract
909 | Widening Road at Cheural - Lungzarhtum - Vartekkai - Sangau (11.50Km) in Mizoram for the year 2022-23 under SASCI Group-1. Widening of Road from BCM Church to BRTF Road via Middle School at Cheural Town Extension (L=1.800km) | 43.12 | Siaha Division | 09.04.23 | 30.9.23 | 87.15% | 23.36 |  |  | 87.15% | 23.36 | Work in progress | Item rate Contract
910 | Wifening Road at Cheural - Lungzarhtum - Vartekkai - Sangau (11.50Km) in Mizoram for the year 2022-23 under SASCI Group-2. Widening of Road from LIKBK Pastor Qtr to Pu H.Lalhranga House at Lungzarhtum (L=1.500km) | 44.54 | Siaha Division | 09.04.23 | 31.8.23 | 82.73% | 35.26 |  |  | 82.73% | 35.26 | Work in progress. | Item rate Contract
911 | Wifening Road at Cheural - Lungzarhtum - Vartekkai - Sangau (11.50Km) in Mizoram for the year 2022-23 under SASCI Group-3 Widening of Road from NEC road Junction to Vartekkai with construction of minor bridge (L=7.000km) | 207.27 | Siaha Division | 09.04.23 | 08.04.24 | 99.98% | 126.05 |  |  | 99.98% | 126.05 | Work in progress. | Item rate Contract
912 | Wifening Road at Cheural - Lungzarhtum - Vartekkai - Sangau (11.50Km) in Mizoram for the year 2022-23 under SASCI Group-4 Widening of Road from Tourist Lodge to Vengthar Field via SDO (C) Complex at Sangau (L=0.860km) | 20.07 | Siaha Division | 09.04.23 | 08.07.23 | 51.51% | 12.1 |  |  | 51.51% | 12.1 | Work in progress. | Item rate Contract
913 | Formation Cutting of Road to Sand Quarry at Bualpui 'NG' -Archhuang-Sangau-Lungpher (15.46Km) in Mizoram for the year 2022-23 under SASCI | 61.85 | Siaha Division | 09.04.23 | 31.8.23 | 97% | 57.88 |  |  | 97% | 57.88 | Work in progress. | Item rate Contract
914 | Formation Cutting of Road to Sand Quarry at Bualpui 'NG' -Archhuang-Sangau-Lungpher (15.46Km) in Mizoram for the year 2022-23 under SASCI | 49.63 | Siaha Division | 09.04.23 | 31.8.23 | 96.04% | 24.82 |  |  | 96.04% | 24.82 | Work in progress. | Item rate Contract
915 | Formation Cutting of Road to Sand Quarry at Bualpui 'NG' -Archhuang-Sangau-Lungpher (15.46Km) in Mizoram for the year 2022-23 under SASCI | 38.68 | Siaha Division | 09.04.26 | 8.7.23 | 90.05% | 26.72 |  |  | 90.05% | 26.72 | Work in progress. | Item rate Contract
916 | Formation Cutting of Road to Sand Quarry at Bualpui 'NG' -Archhuang-Sangau-Lungpher (15.46Km) in Mizoram for the year 2022-23 under SASCI | 125.86 | Siaha Division | 09.04.23 | 08.04.23 | 93.4% | 56.18 |  |  | 93.4% | 56.18 | Work in progress. | Item rate Contract
SASCI : 2023-2024 Under Siaha Division.
917 | Const. of Thiahra to Tuipui with Bridge Over River Tuisumpui (Phase-1) | 144.24 | Siaha Division | 20.10.23 | 31.03.25 |  |  | 1.88% |  | 1.88% |  | Work in progress. | Item rate Contract
918 | Improvement & Widening of Balu Road between BRTF Road at River Tuipui (Lopu) | 19.23 | Siaha Division | 20.10.23 | 31.03.25 |  |  | 75% |  | 75% |  | Work in progress. | Item rate Contract
919 | Improvement & Widening of Balu Road between BRTF Road at River Tuipui (Chakhei) | 24.04 | Siaha Division | 20.10.23 | 31.03.25 |  |  | 66.67% |  | 66.67% |  | Work in progress. | Item rate Contract
920 | Improvement & Widening of Balu Road between BRTF Road at River Tuipui (Iana and Tuipui) | 14.42 | Siaha Division | 20.10.23 | 31.03.25 |  |  | 75% |  | 75% |  | Work in progress. | Item rate Contract
921 | Improvement of Siaha Town from Meisatla to Tlangkawn via College Veng (7.50 kms) | 269.23 | Siaha Division | 20.10.23 | 31.03.25 |  |  | 69.58% |  | 69.58% |  | Work in progress. | Item rate Contract
922 | Improvement of Siaha Town from Meisatla to Tlangkawn via College Veng (7.50 kms) Tisopi-CC pavement. | 14.42 | Siaha Division | 20.10.23 | 31.03.25 |  |  | 66.67% |  | 66.67% |  | Work in progress. | Item rate Contract
923 | Improvement of Siaha Town from Meisatla to Tlangkawn via College Veng (7.50 kms) College vaih-II and New Siaha East-II. | 28.85 | Siaha Division | 20.10.23 | 31.03.25 |  |  | 2.43% |  | 2.43% |  | Work in progress. | Item rate Contract
924 | Improvement of Siaha Town from Meisatla to Tlangkawn via College Veng (7.50 kms) Between Elim School and AR Ground.. | 19.23 | Siaha Division | 20.10.23 | 31.03.25 | [7 empty] | Item rate Contract
925 | Improvement of Siaha Town from Meisatla to Tlangkawn via College Veng (7.50 kms) Between J.Vialu House to Siaha Vaihpi | 14.43 | Siaha Division | 20.10.23 | 31.03.25 |  |  | 100% |  | 100% |  | Phy.Completed | Item rate Contract
926 | Improvement of Siaha Town from Meisatla to Tlangkawn via College Veng (7.50 kms) Council vaih Cemetary. | 28.85 | Siaha Division | 20.10.23 | 31.03.25 |  |  | 35% |  | 35% |  | Work in progress. | Item rate Contract
927 | Improvement of Siaha Town from Meisatla to Tlangkawn via College Veng (7.50 kms) K.Paichho House to Gilgal Church. | 11.54 | Siaha Division | 20.10.23 | 31.03.25 |  |  | 100% |  | 100% |  | Work in progress. | Item rate Contract
928 | Improvement of Siaha Town from Meisatla to Tlangkawn via College Veng (7.50 kms) Horti Link Road. | 12.5 | Siaha Division | 20.10.23 | 31.03.25 |  |  | 93.8% |  | 93.8% |  | Work in progress. | Item rate Contract
929 | Improvement of Siaha Town from Meisatla to Tlangkawn via College Veng (7.50 kms) Agri. Link Road. | 28.85 | Siaha Division | 20.10.23 | 31.03.25 |  |  | 66.67% |  | 66.67% |  | Work in progress. | Item rate Contract
930 | Improvement of Siaha Town from Meisatla to Tlangkawn via College Veng (7.50 kms) Chhaolo.. | 19.23 | Siaha Division | 20.10.23 | 31.03.25 |  |  | 92.42% |  | 92.42% |  | Work in progress. | Item rate Contract
931 | Improvement of Siaha Town from Meisatla to Tlangkawn via College Veng (7.50 kms) Noaotla | 24.04 | Siaha Division | 20.10.23 | 31.03.25 |  |  | 100% |  | 100% |  | Phy.Completed | Item rate Contract
932 | Improvement of Siaha Town from Meisatla to Tlangkawn via College Veng (7.50 kms) Thanngerh Agri. Link Road Thaltlang. | 28.85 | Siaha Division | 20.10.23 | 31.03.25 |  |  | 33.33% |  | 33.33% |  | Work in progress. | Item rate Contract
933 | Improvement of Siaha Town from Meisatla to Tlangkawn via College Veng (7.50 kms) Rawlbuk. | 9.62 | Siaha Division | 20.10.23 | 31.03.25 |  |  | 100% |  | 100% |  | Phy.Completed | Item rate Contract
934 | Improvement of Siaha Town from Meisatla to Tlangkawn via College Veng (7.50 kms) S.Lungpher | 9.62 | Siaha Division | 20.10.23 | 31.03.25 |  |  | 80% |  | 80% |  | Work in progress. | Item rate Contract
935 | Improvement of Siaha Town from Meisatla to Tlangkawn via College Veng (7.50 kms) Lungtian-II | 9.62 | Siaha Division | 20.10.23 | 31.03.25 |  |  | 73.33% |  | 73.33% |  | Work in progress. | Item rate Contract
936 | Improvement of Siaha Town from Meisatla to Tlangkawn via College Veng (7.50 kms) Vawmbuk | 9.62 | Siaha Division | 20.10.23 | 31.03.25 |  |  | 100% |  | 100% |  | Work in progress. | Item rate Contract
937 | Improvement And Widening of Balu Road between BRTF Road at River Tuipui (8.50 kms) | 197.12 | Siaha Division | 20.10.23 | 31.03.25 |  |  | 49.05% |  | 49.05% |  | Work in progress. | Item rate Contract
938 | Improvement And Widening of Balu Road between BRTF Road at River Tuipui (8.50 kms) Supha and Miepu | 24.04 | Siaha Division | 20.10.23 | 31.03.25 |  |  | 17.5% |  | 17.5% |  | Work in progress. | Item rate Contract
939 | Improvement And Widening of Balu Road between BRTF Road at River Tuipui (8.50 kms) New Laty. | 19.23 | Siaha Division | 20.10.23 | 31.03.25 |  |  | 35% |  | 35% |  | Work in progress. | Item rate Contract
940 | Improvement And Widening of Balu Road between BRTF Road at River Tuipui (8.50 kms) | 38.46 | Siaha Division | 20.10.23 | 31.03.25 |  |  | 77.5% |  | 77.5% |  | Work in progress. | Item rate Contract
941 | Improvement And Widening of Balu Road between BRTF Road at River Tuipui (8.50 kms) Laki | 19.23 | Siaha Division | 20.10.23 | 31.03.25 | [7 empty] | Item rate Contract
942 | Improvement And Widening of Balu Road between BRTF Road at River Tuipui (8.50 kms) Tisi | 19.23 | Siaha Division | 20.10.23 | 31.03.25 |  |  | 94.78% |  | 94.78% |  | Work in progress. | Item rate Contract
943 | Improvement And Widening of Balu Road between BRTF Road at River Tuipui (8.50 kms) New Ahmypi & Old Ahmypi | 19.23 | Siaha Division | 20.10.23 | 31.03.25 | [7 empty] | Item rate Contract
KAWRTHAH DIVISION :
944 | Strengthening of Hriphaw - Kolalian - Dulupcherra Road (14.00Kms) | 500 | Kawrthah Division | 16.12.23 | 15.12.24 | 15% |  | 10% |  | 25% |  | Work in progress | Restricted Tender
945 | Const. of W.Mualthuam - Belkhai Road (3.100 Kms) | 360 | Kawrthah Division | 16.12.23 | 15.12.24 | 39% |  | 3% |  | 42% |  | Work in progress | Restricted Tender
946 | Strengthening of Zamuang - Hriphaw - Kolalian - Dulupcherra (KDZKT) Road (28.00 Kmp) | 500 | Kawrthah Division | 16.12.23 | 15.12.24 | 18% |  | 15.5% |  | 33.5% |  | Work in progress | Restricted Tender
947 | Additional Works and Completion of Double Lane Bridge Over R.Teirei on Bairabi - Zamuang. | 1400 | Kawrthah Division | 16.12.23 | 15.12.24 |  |  | 20% |  | 20% |  | Work in progress | Restricted Tender
MAMIT DIVISION :
948 | Construction of Mamit Ring Road (5.66) | 600 | Mamit Division | 31.03.23 | 31.03.24 | 95% | 562.65 | 5% | 37.35 | 100% | 600 | Completed | Item rate Contract
SERCHHIP DIVISION :
949 | Improvement of roadsInfrastucture at District Headquarters Saiha, Lawngtlai, Lunglei, Hnahthial, Serchhip, Champhai, Khawzawl, Saitual, Kolasib, Mamit. | 85 | Serchhip Division | 7.10.23 | 30.10.23 | 100% |  |  |  | 100% |  | Phy.Completed | Item rate
950 | Construction of DS.Chawngtui-N.Vanlaiphai Road (0.00-14.800Kmp) Phase-II (Parmanent Works) | 295 | Serchhip Division | 15.2.23 | 27.10.24 | 70% | 155.73 | 10% |  | 80% | 155.73 | Work in progress | Item rate
951 | Construction of Strengthening of double lane BUGS Bridge Over R.Tuichang at 6.00Kmp on Keitum-Artahkawn Road (40R-70R) | 343 | Serchhip Division | 15.2.23 | 31.3.23 | 100% | 299.74 |  |  | 100% | 299.74 | Phy.Completed | Item rate
952 | Widening, Strengthening & Improvement of Sports Complex Approach Road at Serchhip (Length =1.50Kms) Widening= 1.500Kms Retaining Wall = 80.00 mP.C.C. Pavement = 1.500 Km Side Drain = 1500.00 m Culvert = 8 nos. | 380 | Serchhip Division | 05.10.23 | 05.10.24 | 2.6% |  | 4.4% |  | 7% |  | Work Mobilized | Item rate
953 | Additional works for Compietion of Strengthening of Chekawn - Artahkawn Road | 205.01 | Serchhip Division | 07.10.23 | 06.10.24 | 100% |  |  |  | 100% |  | Phy.Completed | Item rate
954 | Const. of Agriculturre Link road to River Lungva from Hriangtlang, Sialsir, Hlaizawl. | 351.5 | Serchhip Division | 05.10.23 | 05.10.24 | 26.48% |  | 11.11% |  | 37.59% |  | Work in progress | Item rate
LAWNGTLAI DIVISION :
Improvement of Thlengang to river Chhimtuipui Road :
955 | Construction of RCC Dock along with approach Slab | 23.31 | Lawngtlai Division | 11.05.23 | 10.4.24 | 100% | 11.42 |  | 11.89 | 100% | 23.31 | Completed
956 | Widening of Lawngtlai to Sahriluichhuah (Kalodyne River) Balu Road | 94.8 | Lawngtlai Division | 11.05.23 | 10.4.24 | 100% | 94.8 |  |  | 100% | 94.8 | Completed
957 | Improvement of Bethel veng to Chengkawllui road at College veng, Lawngtlai | 90.84 | Lawngtlai Division | 11.05.23 | 10.4.24 | 100% | 90.83 |  |  | 100% | 90.83 | Completed
Improvement of Thlengang to river Chhimtuipui Road :
958 | Formation cutting of Vathuampui to Mautlang Road | 70.47 | Lawngtlai Division | 11.05.23 | 10.4.24 | 100% | 70.42 |  |  | 100% | 70.42 | Completed
959 | Widening of Bungtlang 'S' to Saikhawthlir Road | 56.15 | Lawngtlai Division | 11.05.23 | 10.4.24 | 100% | 50.13 |  |  | 100% | 50.13 | Completed
960 | Widening of Hmawngbu to Kakichhuah Road | 61.99 | Lawngtlai Division | 11.05.23 | 10.4.24 | 100% | 31.68 |  | 30.29 | 100% | 61.97 | Completed
IMPROVEMENT OF DILTLANG TO CHAWNGTELUI ROAD
961 | Construction of Retaining Wall at Certain Location | 25.07 | Lawngtlai Division | 11.05.23 | 10.4.24 | 100% | 17.19 |  |  | 100% | 17.19 | Phy Completed
962 | Resurfacing of NH-54 to DTO Office (including courtyard) at Chanmari, Lawngtlai | 6.99 | Lawngtlai Division | 11.05.23 | 10.4.24 | 100% | 6.99 |  |  | 100% | 6.99 | Completed
963 | Construction of Minor Bridge between Khawmawi Bazar Veng to Khawmawi Vengthar | 34.48 | Lawngtlai Division | 11.05.23 | 10.4.24 | 100% | 34.47 |  |  | 100% | 34.47 | Completed
964 | Black topping of internal road at Lawngpuighat | 81.65 | Lawngtlai Division | 11.05.23 | 10.4.24 | 100% | 81.63 |  |  | 100% | 81.63 | Completed
965 | Construction of Playground approach road at Thingfal Mamte Veng | 19.49 | Lawngtlai Division | 11.05.23 | 10.4.24 | 100% | 19.49 |  |  | 100% | 19.49 | Completed
966 | Consultancy fee for Roads | 66.55 | Lawngtlai Division | 11.05.23 | 10.4.24 | 15% | 9.98 |  |  | 15% | 9.98 | Work in progress
967 | Consultancy Fee for Bridges | 106.39 | Lawngtlai Division | 11.05.23 | 10.4.24 | 70% | 74.68 |  |  | 70% | 74.68 | Work progress
SASCI : 2023-2024 Under Lawngtlai Division.
968 | Improvement of Approach Road to Kawrthindeng WRC Area. | 121.77 | Lawngtlai Division | 26.02.24 | 31.12.24 | 19.54% |  | 13.18% |  | 32.72% |  | Work progress
969 | Const. of Mautlang to Borogusuri | 117 | Lawngtlai Division | 26.02.24 | 31.12.24 | 66% |  |  |  | 66% |  | Work progress
AIZAWL BUILDING DIVISION : 2023 - 2024
970 | Upgradation of Raj Bhavan, CM Bungalow, Secretariat Building & Assembly Building under SASCI. | 234.68 | Aizawl Building Division | 17.02.232 | 09.03.23 | 100% | 234.68 |  |  | 100% | 234.68 | Completed | Depart- mental
National Highway Division - I (SASCI 2023 - 2024)
Improvement of Road from HN - 44A to Mamit and Rawpuichhip within Mamit in Mizoram for the year 2022-2023 under SASCI (Length=8.45 Km)
971 | Repair of bad patches of existing NH-44A on internal road at Rawpuichhip (Balance work =2.00 Km) | 25 | National Highway Division - I | 17.02.23 | 17.03.23 | 100% | 24.15 |  |  | 100% | 24.15 | Completed | Spot Quotation
972 | Patch repair of approach road to Mamit from NH-44A upto Mamit Playground (Section : 0.00 Kmp to 5.00 Kmp) | 60.13 | National Highway Division - I | 17.02.23 | 17.03.23 | 100% | 58.09 |  |  | 100% | 58.09 | Completed | Spot Quotation
973 | Improvement of Junction for Approach road to Mamit Town with NH-44A: retaining wall | 37 | National Highway Division - I | 17.02.23 | 18.03.23 | 100% | 35.75 |  |  | 100% | 35.75 | Completed | Spot Quotation
974 | Feasibility study and preparation of DPR for upgradation of Lengpui to Saiphai to Hortoki Road (Length=52.108 Km) | 17.84 | National Highway Division - I | 21.02.23 | 21.03.23 | 100% | 17.23 |  |  | 100% | 17.23 | Completed | Spot Quotation
975 | Const. of Rigid/Concrete Pavement for New Approach road to Rawpuichhip from NH-44A | 56.89 | National Highway Division - I | 21.02.23 | 21.03.23 | 30% |  |  |  | 30% |  | Work in progress | Spot Quotation
976 | Repair of bad patches of Lengpui to Hmunpui Road (Section 0.00 - 10.50 Kmp) | 10 | National Highway Division - I | 17.02.23 | 18.03.23 | 100% | 9.68 |  |  | 100% | 9.68 | Completed | Spot Quotation
977 | Const. of Humepipe Culvert at Ch:4.300kmp on NH-44A diverted road at Rawpuichhip Area (L=6.25, H=5m) | 9 | National Highway Division - I | 22.02.23 | 22.03.23 | 100% |  |  |  | 100% |  | Phy.Completed | Spot Quotation
978 | Consultancy for preparation of DPR for approach road const. to Railway station at Khamrang, Tuitum, Sairang, Hortoki and Vairengte to NH-306 | 16.1 | National Highway Division - I | 22.02.23 | 22.03.23 | 100% | 15.54 |  |  | 100% | 15.54 | Completed | Spot Quotation
Const. of Bamboo Link Road from Hmunpui to Mauhaklui & Tuidam approach Road in Mizoram. SASCI : 2023-2024
979 | Repair and Maintenance of Tuidam Approach Road. | 103 | National Highway Division - I | 15.12.23 | 15.12.24 | 100% |  |  |  | 100% |  | The work was started and completed on emergency basis as per higher authority. | Restricted Tender
980 | Hmunpui Bamboo Link Road (Length = 8.00 Km) | 150 | National Highway Division - I | 15.12.23 | 15.12.24 | [7 empty] | Restricted Tender
981 | Const. of Lengpui Advantist Road (Length = 60m) | 10 | National Highway Division - I | 15.12.23 | 15.12.24 | [6 empty] | Patch repair work | Restricted Tender
982 | Const. of Saiphai to Hortoki Road (13.800 Km) | 1200 | National Highway Division - I | 15.12.23 | 15.12.25 | [6 empty] | Work could not be started due to propose change of alignment as per instruction of higher authority | Restricted Tender
983 | Improvement of Roads and Infrastructure at District Headquarters; Saiha, Lawngtlai, Lunglei, Hnahthial, Serchhip, Champhai, Khawzawl, Saitual, Kolasib, Mamit ; (Sh: Tuidam Approach Road) | 10 | National Highway Division - I | 31.03.23 | 31.03.24 | 50% |  |  |  | 50% |  | Work started on emergency basis as per instruction of higher authority | Depart- mental
984 | Improvement of Roads and Infrastructure at District Headquarters; Saiha, Lawngtlai, Lunglei, Hnahthial, Serchhip, Champhai, Khawzawl, Saitual, Kolasib, Mamit ; (Sh: Strengthening of Bailey Bridge over R. Teirei (Darlak) on NH-44A | 70 | National Highway Division - I | 31.03.23 | 31.03.24 | 60% |  |  |  | 60% |  | Work in progress | Depart- mental
985 | Improvement of Roads and Infrastructure at District Headquarters; Saiha, Lawngtlai, Lunglei, Hnahthial, Serchhip, Champhai, Khawzawl, Saitual, Kolasib, Mamit ; (Sh:Mamit to Bairabi Road) | 16 | National Highway Division - I | 31.03.23 | 31.03.24 | 50% |  |  |  | 50% |  | Work in Progress | Depart- mental
986 | Improvement of Roads and Infrastructure at District Headquarters; Saiha, Lawngtlai, Lunglei, Hnahthial, Serchhip, Champhai, Khawzawl, Saitual, Kolasib, Mamit ; (Sh:Dampui Approach Road from NH-44A | 5 | National Highway Division - I | 31.03.23 | 31.03.24 | [6 empty] | Not yet started | Depart- mental
987 | Improvement of Roads and Infrastructure at Aizawl City (Sh: Clearing, Grubbing of Roads Land and Jungle clearance of Saiphai Bamboo Plantation in Mizoram | 45 | National Highway Division - I | 31.03.23 | 31.03.24 | [6 empty] | Not yet started | Depart- mental
988 | Improvement of Roads and Infrastructure at Aizawl City (Sh: Work under National Highway Division-I) | 30 | National Highway Division - I | 31.03.23 | 31.03.24 | [6 empty] | Not yet started | Depart- mental
989 | Improvement of Roads and Infrastructure at Aizawl City (Sh: Estimate for Const. of Lengpui Catholic School Road PCC) | 15 | National Highway Division - I | 31.03.23 | 31.03.24 | 100% |  |  |  | 100% |  | Phy.Completed | Depart- mental
NATIONAL HIGHWAY DIVISION - III SASCI : 2023-2024
990 | Const. of Rigid Pavement at essential places between 133.00Kmp to 147.00Kmp on NH-54 (Total Length =400.00 m) | 267 | National Highway Division - III | 25.7.23 | 13.11.23 | 100% |  |  |  | 100% |  | Phy.Completed | Departmental
991 | Upgradation of Saiphai, Zophai and Berhvakawn to Mualkhang Road. | 220 | National Highway Division - III | [8 empty] | Not yet started
992 | Improvement of Roads and Infrastructures at Aizawl City (Sh: Pot Hole filling and patches repair of NH-54(NH-6) for regular flow of traffic (Kawnpui - Sairang ) | 20 | National Highway Division - III | 18.9.23 | 15.11.23 | 100% |  |  |  | 100% |  | Phy.Completed | Departmental
1119
QUALITY CONTROL RESEARCH & DEVELOPMENT DIVISION, ZUANGTUI : AIZAWL.
993 | Improvement of Government Building, High Court, Government Polytechnic & E-in-C, PWD Office (Sh: Const. of Barbet Wire fencing of PWD Complex at Zuangtui. | 23.3 | Quality Control Research & Development Division. |  |  | 100% |  |  |  | 100% |  | Phy.Completed | Spot Quotation
994 | Improvement of Government Building, High Court, Government Polytechnic & E-in-C, PWD Office (Sh: Const. ofBeily Bridge PartsGodown at PWD Complex, Zuangtui | 20 | Quality Control Research & Development Division. |  |  | 60% |  | 10% |  | 70% |  | Work in Progress | Departmental