## NABARD
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding: NABARD | [8 empty] | Month : June 2024
Sl. no | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Const.of BUSG Composite Bridges over R.Chepte on Bilkhawthlar to Saiphai Road | 508.45 | Kolasib Division | 24.6.19 | 24.12.20 | 57% | 128.5 |  | - | 57% | 128.5
2 | Const.of BUSG Composite Bridges over R.Sesih on Bilkhawthlar to Saiphai Road | 281.12 | Kolasib Division | 24.6.19 | 24.12.20 | 75% | 162.03 |  |  | 75% | 162.03
3 | Design & Construction of T-Beam Bridge Package-II at Bulung River (CH:10.20 KMP) | 1015.92 | Kolasib Division | 24.12.21 | 24.06.23 | 9% | 42.42 | 2% |  | 11% | 42.42
4 | Design & Construction of T-Beam Bridge Package-II at Damdiai River (CH:23.50 KMP) | 1015.92 | Kolasib Division | 24.12.21 | 24.06.23 | 31% | 39.66 |  |  | 31% | 39.66
5 | Design & Construction of T-Beam Bridge Package-I at Chhimluangte River (CH:0.450 KMP) | 969.01 | Kolasib Division | 18.12.21 | 18.06.23 | 42% | 157.29 | 8% |  | 50% | 157.29 |  | Initially the mode of contract is restricted tender and later it is handed over to departmental work
6 | Design & Construction of T-Beam Bridge Package-I at Dumkhel River (CH:5.50 KMP) | 969.01 | Kolasib Division | 18.12.21 | 18.06.23 | 23% | 115.75 |  |  | 23% | 115.75
7 | Const.of Meidum to Hortoki Road Phase -II (Km 9.100 to Km 26.000) SH: Earthworks and Permanent works from Km 9.100-Km 13.325) Package -I | 1087.32 | Kolasib Division | 24.12.21 | 24.06.23 | 100% | 974.55 |  |  | 100% | 974.55
8 | Const.of Meidum to Hortoki Road Phase -II (Km 13.325 to Km 17.500 SH: Earthworks and Permanent works from Km 13.325 to Km 17.500) Package -II | 1171 | Kolasib Division | 25.12.21 | 25.06.23 | 100% | 615.31 |  |  | 100% | 615.31
9 | Const.of Meidum to Hortoki Road Phase -II (Km 17.500 to Km 21.725 SH: Earthworks and Permanent works from Km 15.690 to Km 19.005) Package -III | 1422 | Kolasib Division | 18.12.21 | 18.06.23 | 100% | 1097.89 |  |  | 100% | 1097.89
10 | Const.of Meidum to Hortoki Road Phase -II (Km 21.725 to Km 26.000 SH: Earthworks and Permanent works from Km 19.005 to Km 22.360) Package -IV | 959 | Kolasib Division | 08.12.21 | 8.06.23 | 100% | 856.72 |  |  | 100% | 856.72
11 | Construction of Meidum to Hortoki Road Phase - II (Km 9.100 to 26.000): SH: Construction of Rigid pavement: Package-I (Km 9.100-Km 15.730) | 2390.08 | Kolasib Division | 03.08.22 | 03.08.23 | 13.98% | 440.93 |  |  | 13.98% | 440.93
12 | Construction of Meidum to Hortoki Road Phase - II (Km 9.100 to 26.000): SH: Construction of Rigid pavement: Package-II (Km 15.73-Km 22.36) | 2390.08 | Kolasib Division | 03.08.22 | 03.08.23 | 7% | 341.16 |  |  | 7% | 341.16
13 | Construction of link Road from NH-306 (PHE pump House) to R.Aitlang Lui Basin Crop Land : Length = 9.22 Kms | 465.66 | Kolasib Division | 12.08.22 | 12.08.23 | 60% | 445.75 | - |  | 60% | 445.75 | Works completed 16.96 lakh have been kept in D-III | Restricted Tender
14 | Construction of link Road from NH-306 (Vairengte) to Sabual Mual Arable Crop Land = 3.720 Kms | 418.89 | Kolasib Division | 13.08.22 | 13.08.23 | 100% | 368.02 |  |  | 100% | 368.02 |  | Restricted Tender
15 | Construction of Agriculture Link Road from NH-306 A to Buarchep Arable Crop Land : Length = 1.720 Kms | 175.03 | Kolasib Division | 27.08.22 | 27.08.23 | 100% | 170.56 |  |  | 100% | 170.56 | Work physically completed | Restricted Tender
16 | Construction of 24 Warehouses with associated Infrstructure in 23 locations in Mizoram under NABARD (Group-II Zuangtui/Sairang) | 440.97 | Project Division-I | 17.7.23 | 31.3.25 | 35% | - | 13% | - | 48% | - | Work progress delayed due to shortage of labour who obeve Eid-ul-Adha | EPC
17 | Construction of 24 Warehouses with associated Infrastructure in 23 locations in Mizoram Group-I (Scheme-NABARD) i) Construction of Warehouse and other amenities at Bairabi | 316.55 | Project Division-II | 17.07.23 | 31.03.25 | 26% | 38.47 | 3% |  | 29% | 38.47 | Work in progress | Item Rate
| ii) Construction of Warehouse and other amenities at Marpara | 235.73 | Project Division-II | 17.07.23 | 31.03.25 | 42% | 63.61 | 2% |  | 44% | 63.61 | Work in progress | Item Rate
| iii) Construction of Warehouse and other amenities at Sialsuk SC | 171.09 | Project Division-II | 17.07.23 | 31.03.25 | 17% | 18.25 | 8% |  | 25% | 18.25 | Work in progress | Item Rate
| iv) Construction of Warehouse and other amenities at Zawlnuam | 176 | Project Division-II | 17.07.23 | 31.03.25 | 33% | 50.4 | 2% |  | 35% | 50.4 | Work in progress | Item Rate
| v) Construction of Warehouse and other amenities at Kanhmun | 175.8 | Project Division-II | 17.07.23 | 31.03.25 | 36% | 54.58 | 2% |  | 38% | 54.58 | Work in progress | Item Rate
18 | Construction of 24 Warehouses with associated Infrastructure in 23 lacations in Mizoram Group-IX (Scheme-NABARD) i) Construction of Warehouse and other amenities at Phuldungsei | 175.81 | Project Division-II | 17.07.23 | 31.03.25 | 41% | 60.9 | 2% |  | 43% | 60.9 | Work in progress | Item Rate
19 | Construction of 24 Warehouses with associated Infrastructure in 23 locations in Mizoram under NABARD (Group-VII: Teikhang, Rabung & Dungtlang) | 336.53 | Project Division-III | 17.7.23 | 31.3.25 | 10% |  | 5% |  | 15% |  | Work in progress | PWD Form-8
20 | Construction of 200 MT Capacity warehouse & staff quarter at Zohmun | 170.99 | Project Division-IV | 17.07.23 | 31.03.25 | 10.3% |  | 13.09% |  | 23.39% |  | Work in progress | Item Rate
21 | Improvement & Strengthening of Nalkawn - Chamdur Valley | 2616.41 | Lawngtlai Division | 09.08.19 | 31.12.24 | 61.91% | 1672.31 |  |  | 61.91% | 1672.31 | WBM & Wearing course repair works in progress along with mobilization of materials | Item Rate
22 | Const.of double lane built up Steel Girden Bridge over R.Teirei (Span -102m) at Ch.7.00 Kmp on Bairabi Zamuang Road | 2322.42 | Kawrthah Division | 5.8.17 | 30.6.24 | 64% | 1365.6 | 0.1% |  | 64.1% | 1365.6 | Work in progress | Contract after call of Restricted Tender
23 | Const.of double lane built up Steel Girden Bridge (Span-81m) over R.Langkaih on Mizoram-Tripura Border at Kanhmun | 2231.91 | Kawrthah Division | 6.4.18 | 30.11.24 | 44% | 1179.03 |  |  | 44% | 1179.03 | Work could not be progressed as dismantling of existing Bailey bridge is required to progress further. However, Construction of Auro plyable Suspension Bridge of sub-Way is in progress now | Contract after call of Restricted Tender
24 | Construction of Agriculture Link Road in Nothern Mizoram (Sh: Construction of Link Road from Saikhawthlir to R.Hnanglui Arable crop land, Length = 3.50 kms) | 362.02 | Kawrthah Division | 20.08.22 | 20.3.24 | 75% | 186.13 |  |  | 75% | 186.13 | Work in progress | Contract after call of Restricted Tender
25 | Construction of Agriculture Link Road in Nothern Mizoram (Sh: Construction of Link Road from Chuhvel to R.Hnanglui Arable crop land, Length = 2.35 kms) | 284.76 | Kawrthah Division | 18.08.22 | 30.4.24 | 63% | 155.31 | 3% |  | 66% | 155.31 | Work in progress | Contract after call of Restricted Tender
26 | Construction of Agriculture Link Road in Nothern Mizoram (Sh: Construction of Link Road from from Thinghlun to Hriphaw through permanent crop length=9.570 kmp) | 385.61 | Kawrthah Division | 20.08.22 | 31.5.24 | 76.86% | 295.97 | 1% |  | 77.86% | 295.97 | Work in progress | Contract after call of Restricted Tender
27 | Upgradation of Meidum to Hortoki Phase-I (0.0-9.10) | 4445 | NHD-III | 26.5.20 | 26.11.21 1st EOT=211 days (21.11.21-20.6.22) 2nd EOT=375 days (21.6.22-30.6.23) 3rd EOT =243 days (30.6.23-28.2.24) | 99% | 4001.4 |  | 92.79 | 99% | 4094.19 |  | Item Rate
28 | Construction of River Training Works for Protection of Tlawng River Bank at Bairabi Phase-I (Group-I) | 1111 | NHD-III | 17.10.22 | 17.10.23 1st EOT=166 days 18.10.23-31.3.24 | 100% | 279.17 |  |  | 100% | 279.17 |  | Item Rate
| Phase-I (Group-II) |  |  | 17.10.22 | 17.10.23 1st EOT=166 days 18.10.23-31.3.25 | 100% | 279.09 |  |  | 100% | 279.09 |  | Item Rate
| Phase-I (Group-III) |  |  | 17.10.22 | 17.10.23 | 100% | 216.65 |  |  | 100% | 216.65 |  | Item Rate
| Phase-I (Group-IV) |  |  | 17.10.22 | 17.10.23 | 100% | 246.7 |  |  | 100% | 246.7 |  | Item Rate
| Construction of river training works for protection of Tlawng river bank at Bairabi Phase-I |  |  | Departmental |  |  | 22.5 |  | 7.25 |  | 29.75 | Contingency
29 | Construction of MDR from Khamrang (Dilsei) to Selesih (Sh: Construction of approach road to Mualkhang Village) | 14529.27 | NHD-III | 08.02.21 | 08.08.22 | 100% | 122.25 |  |  | 100% | 122.25 |  | Item Rate
30 | Construction of Road from Khamrang to Selesih Phase-II Group-1 (11/00 to 22/00Km) |  |  | 8.11.21 | 8.5.23 1st EOT=210 days (wef 09.05.23- 04.12.23 | 32.31% | 547.46 |  | - | 32.31% | 547.46 |  | Item Rate
31 | Construction of Road from Khamrang to Selesih Phase-II Group-2 (22/00 to 25/00Km) |  |  | 22.11.21 | 22.11.22 1st EOT=90days (upto -20.02.23) 2nd EOT=90 days (wef 21.2.23-21.5.23) 3rd EOT = 90 days(22.5.23-19.8.23) | 30.25% | 219.81 |  | 104.46 | 30.25% | 324.27 |  | Item Rate
32 | Construction of Road from Khamrang to Selesih Phase-II Group-3 (25/00 to 28/00Km) |  |  | 11.11.21 | 11.11.22 1st EOT=104 days (upto -24.02.23) 2nd EOT=90 days (wef 10.2.23-11.5.23) 3rd EOT = 90 days(wef 12.5.23-9.8.23) | 16.87% | 207.28 |  |  | 16.87% | 207.28 |  | Item Rate
33 | Construction of Road from Khamrang to Selesih Phase-II (Sh: Construction of Rigid Pavement from 11/00 to 19/00 Kmp=8.00 Kms) Group A |  |  | 26.8.23 | 26.8.25 | [7 empty] | Item Rate
34 | Construction of Road from Khamrang to Selesih Phase-II (Sh: Construction of Rigid Pavement from 19/00 to 28/00 Kmp=9.00Kms) Group B |  |  | 26.8.23 | 26.8.25 | [7 empty] | Item Rate
35 | Construction of road from Khamrang to Selesih Phase-II |  |  | Departmental |  |  | 1.18 |  |  |  | 1.18 | Contingency
36 | Construction of MDR from Khamrang-Dilsei to Selesih (Phase-I) (Length = 11.00 Kms) Group-A (0/00 to 3/600Km) | 6583.18 | NHD-III | 8.02.21 | 8.8.22 1st EOT=184 days (upto 08.02.23, 2nd EOT=150 days (upto 08.07.23) | 65.35% | 314.25 |  |  | 65.35% | 314.25 |  | Item Rate
37 | Construction of road from Khamrang to Selesih Phase-I (Length = 11.00 Kms) Group-B (3/60 to 7/200Km) |  | NHD-III | 8.02.21 | 8.8.22 1st EOT=184 days (upto 08.02.23, 2nd EOT=150 days (wef 09.02.23-08.07.23) | 55.75% |  | 0.04% |  | 55.75% | 434.62 |  | Item Rate
38 | Construction of road from Khamrang to Selesih Phase-I (Length = 11.00 Kms) Group-C (7/200 to 11/00Km) |  | NHD-III | 8.02.21 | 8.8.22 1st EOT=184 days (upto 08.02.23, 2nd EOT=150 days (wef 09.02.23-08.07.23) | 47.78% | 177.27 |  |  | 47.78% | 177.27 |  | Item Rate
39 | Construction of road from Khamrang to Selesih Phase-I (Sh: Construction of Rigid Pavement from 7/00 to 11/00 Kmp = 4.00 Kms) |  | NHD-III | 16.8.22 | 16.02.24 | 1.67% |  | 1.33% |  | 3% |  |  | Item Rate
40 | Constuction of road from Khamrang to Selesih Phase-I |  | NHD-III | Departmental |  |  | 189.75 |  |  |  | 189.75 | Contingency
41 | Const.of Double Storied PHC at Lungsen | 267.15 | Lunglei Building Project Division | 10.2.22 | 10.2.24 | 100% | 267.15 |  |  | 100% | 267.15 | Civil Works completed and I/E Works not yet done | Restricted Tender
42 | Const.of Infrastructure Support fro School of Agricultural Science at Hnahthial: Phase-II | 685 | Lunglei Building Project Division | 08.04.23 | 08.04.25 | 23.75% | 142.44 | 5.5% |  | 29.25% | 142.44 | Work in progress | Restricted Tender
| i) Boys Hostel | 156.1 | Lunglei Building Project Division | 08.04.23 | 08.04.25 | 30% |  | 3% |  | 33% |  |  | Restricted Tender
| ii) Staff Quarter Type-III | 130.1 | Lunglei Building Project Division | 08.04.23 | 08.04.25 | 14% |  | 3% |  | 17%
| iii) Staff Quarter Type-II | 155.78 | Lunglei Building Project Division | 08.04.23 | 08.04.25 | 29% |  | 3% |  | 32%
| iv) Guest House | 112.79 | Lunglei Building Project Division | 08.04.23 | 08.04.25 | 32% |  | 3% |  | 35%
43 | 1. Construction of 24 Warehouses with associated Infrastructure in 23 localities in Mizoram under NABARD Gr-III: Siaha, Chapui, Bungtlang South
| 1) Siaha SDC | 444.99 | Lunglei Building Project Division | 17.07.23 | 31.3.25 | 25% | 80.76 | 3% |  | 28% | 80.76 | Work in progress | Restricted Tender
| 2) Chapui | 197.82 | Lunglei Building Project Division | 17.07.23 | 31.3.25 | 22% | 17.71 | 5% |  | 27% | 17.71 | Work in progress
| 3) Bungtlang South | 162.63 | Lunglei Building Project Division | 17.07.23 | 31.3.25 | 50% | 14.83 | 5% |  | 55% | 14.83 | Work in progress
| 2. Gr-IV: Lungpher | 197.12 | Lunglei Building Project Division | 17.07.23 | 31.3.25 | 40% | 55.4 | 5% |  | 45% | 55.4 | Work in progress | Restricted Tender
3. Gr-VI: South Vanlaiphai and Vawmbuk
| 1) South Vanlaiphai | 187.15 | Lunglei Building Project Division | 17.07.23 | 31.3.25 | 27% |  | 2% |  | 29% |  | Work in progress | Restricted Tender
| 2) Vawmbuk | 197.82 | Lunglei Building Project Division | 17.07.23 | 31.3.25 | 38% |  | 1% |  | 39% |  | Work in progress
4. Gr-VIII: Hnahthial, Thingsai. Cherhlun and Siata
| 1) Hnahthial | 197.24 | Lunglei Building Project Division | 17.07.23 | 31.3.25 | 1% |  |  |  | 1% |  | Work stayed as selected site falls under Forest Reserve Area. Relocation of site is being awaited from Client Dept. | Restricted Tender
| 2) Thingsai | 160.32 | Lunglei Building Project Division | 17.07.23 | 31.3.25 | 15% |  | 5% |  | 20% |  | Work in progress
| 3) Cherhlun | 85.61 | Lunglei Building Project Division | 17.07.23 | 31.3.25 | 14% |  | 1% |  | 15% |  | Work in progress
| 4) Siata | 197.82 | Lunglei Building Project Division | 17.07.23 | 31.3.25 | 45% |  | 5% |  | 50% |  | Work in progress
5. Gr-X: Vaseikai and Tlabung
| 1) Vaseikai | 220.35 | Lunglei Building Project Division | 17.07.23 | 31.3.25 | 35% |  | 5% |  | 40% |  | Work in progress | Restricted Tender
| 2) Tlabung | 93.84 | Lunglei Building Project Division | 17.07.23 | 31.3.25 | 15% |  | 1% |  | 16% |  | Work in progress
44 | Strengthening & Improvement of W.Phaileng to Marpara Road (00.00-30.00Kmp) Package-I | 1854.59 | Mamit Division | 15.03.23 | 15.03.25 | 29% | 291.63 |  |  | 29% | 291.63
45 | Strengthening & Improvement of W.Phaileng to Marpara Road (30.00-80.00Kmp) Package-II | 4778.8 | Mamit Division | 15.03.23 | 15.03.25 | 30% | 454.45 |  | 75.79 | 30% | 530.24
46 | Improvement of Chawngte - Borapansuri Road (0.00-30.00 Kmp) | 3987 | Tlabung Division | 15.3.23 | 15.3.25 | 8% |  | 4% | 291.63 | 12% | 291.63 | Work in progress | Item rate

## NEC
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding: NEC | [8 empty] | Month : June 2024
Sl. no | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the Month |  | Overall cumulative achievement |  | Remarks | Mode of Contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Lunglei Market and Trade Centre at Electric/Chanmari Veng, Lunglei (NEC) | 1403.4 | Lunglei Building Project Division | 25.08.22 | 25.08.24 | 50% | 562.61 | 3% |  | 53% | 562.61 | Works slowed due to modification of drawings & designs for Block-A which is being awaited | Restricted Tender
2 | Construction of Mara Handloom & Weaving Centre at Council Vaih, Saiha | 458.61 | Lunglei Building Project Division | 13.04.22 | 13.04.24 | 72% | 131.01 | 15% |  | 87% | 131.01 | Work in progress | Restricted Tender
3 | Improvement & Upgradation of KDZKT Road (0.00 - 88.400Kmp) | 18327.42 | Kawrthah Division | 27.4.15 | 4.6.18 | 100% | 18290 | - |  | 100% | 18290 | Work Phy.Completed on 31.12.21 SMS of R.Revised estimate is being awaited for financial closure | Contract after call of Tender
4 | Const.of Patient Lodging at Mawdiangdiang near NEIGHRIMS, Shillong | 419.67 | Project Division-I | 9.9.21 | 31.7.24 | 20% | 167.87 | 5% |  | 25% | 167.87 | Revised Target date of completion 9.9.25 | EPC
5 | Infrastructure Development of Biotechnology Cell in Mizoram (C/O Building at MINECO) | 386.6 | Project Division-I | 10.7.23 | 10.1.25 | 20% | 69.55 | 4% |  | 24% | 69.55 |  | EPC
6 | Establishment of Central Medical Warehouse at Aizawl, Mizoram | 1305 | Project Division-I | 4.8.23 | 14.8.25 | 5% |  | 1% |  | 6% |  |  | EPC
7 | Construction of Aizawl Institute of Arts & Music for the NER, Tuivamit Tlang, Aizawl | 590.23 | Project Division-I | 4.9.23 | 4.9.25 | 33% | 120.03 | 2% |  | 35% | 120.03 |  | EPC
8 | Construction of Veterinary Information and Resource Centre at Aizawl | 439.2 | Project Division-I | 25.9.23 | 25.9.25 | 35% | 10 | 2% |  | 37% | 10 |  | EPC
9 | Construction of 60 Bedded Intern Hostel at ZMC, Falkawn | 679 | Project Division-II | 01.09.22 | 01.05.24 | 57% | 271.6 | 2% |  | 59% | 271.6 | Work in progress. EOT being process | Item Rate
10 | Construction of Market Building at West Phaileng, Mamit District | 278.242 | Project Division-II | 22.08.23 | 22.08.25 | 16% |  | 6% |  | 22% |  | Work in progress | Item Rate
11 | Creation of Passion fruit Processing unit at Cold Storage, New Champhai Mizoram | 185.36 | Project Division-III | 23.09.22 | 24.03.24 | 90% | 45.42 | 3% |  | 93% | 45.42 | As per revised sanction by NEC, only civil construction work is under PWD Work in progress | PWD Form-8
12 | Construction of Zomi cultural Centre and preservation of historical sites at Champhai | 478.69 | Project Division-III | 26.09.22 | 26.09.24 | 70% | 126 | 10% |  | 80% | 126 | Work in progress | PWD Form-8
13 | Construction of Biate Tea Tourism Circuit & Nature Camp in Mizoram | 369.62 | Project Division-III | 9.10.23 | 9.10.25 | 70% | 11.17 | 10% |  | 80% | 11.17 | Work in progress | PWD Form-8
14 | Forstering Industry, Innovation, Infrastructure and Livelihood Oppurtunities (SDG 9) at Lunglen-1 and Sialhawk, Mizoram and strengthening of Food Testing Laboratory (Sh: Construction of Pineapple precessing plant building at Sialhawk) | 65.7 | Project Division-III | 12.10.23 | 12.10.25 | 85% |  | 5% |  | 90% |  | Work in progress | PWD Form-8
15 | Establishing Mizo cultural heritage centre for protecting the historical and natural heritage of Mizo at Kawlri, Serchhip | 486.47 | Project Division-III | 16.2.24 | 16.2.26 | 1% |  | 4% |  | 5% |  | Work in progress | PWD Form-8
16 | Construction of Community Hall at Bethel Veng Champhai | 1443.75 | Project Division-III | 16.2.24 | 16.2.26 | [6 empty] | New design of building is being done by architecture cell and work cannot be atarted till approval is obtained | PWD Form-8
17 | Construction of AYUSH Development Centre at MINECO Aizawl | 264.16 | Project Division-IV | 7.12.22 | 17.8.24 | 48.6% | 40 | 1.4% | 61.82 | 50% | 101.82 | Work in progress | Item Rate
18 | Etablishment of Sinlung Hills Council Administrative Complex (Const.of Sinlung Hills Administrative Building at Sakawrdai) | 381.99 | Project Division-IV | 8.11.21 | 12.03.24 | 67.3% | 152.98 | 2.7% | 52.42 | 70% | 205.4 | Work in progress | Item Rate

## Deposit
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : Deposit | [9 empty] | Month : June 2024
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummutive Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of New Ward Building (Renovation & Upgradation of Central Jail) at Aizawl, Mizoram | 100 | Project Division-I | 23.3.23 | 23.3.24 (15.7.24 EOT) | 60% | - | 10% | - | 70% | - | As working site is inside Jail workers cannot go in and out freely and material needs to be taken headload about 100m. Due to this progress cannot be expected EoT being applied | EPC

## PMGSY
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding: PMGSY | [8 empty] | Month : June 2024
Sl. no | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Diblibagh to Chengkawllui Road (0.000-19.520)Kmp | 2798.82 | Tlabung Division | 17.6.19 | 17.6.20 | 80.15% | 1509.2 |  |  | 80.15% | 1509.2 |  | Item Rate
2 | Diblibagh to Sugarbasora Road (0.000-2.000)Kmp | 305.81 | Tlabung Division | 28.9.18 | 28.9.19 | 75.4% | 211.07 |  |  | 75.4% | 211.07 | Extension granted up to Dt.31.03.23 | Item Rate
3 | Diblibagh to Sugarbasora Road Group B (2.000-4.760)Kmp | 373.19 | Tlabung Division | 22.9.18 | 22.9.19 | 100% | 210.96 |  |  | 100% | 210.96 | Completed physical works Extension granted upto Dt.31.3.23 | Item Rate
4 | Const & Maintenance of Tlabung-Nunsury Road (0.000-8.000) Kmp | 579.77 | Tlabung Division | 17.6.19 | 17.6.20 | 99.8% | 499.42 |  |  | 99.8% | 499.42 | Completed phy.works | Item Rate
5 | Const.of Serhuan-Lamthai Road | 1378.12 | Tlabung Division | 21.12.17 | 27.11.19 | 98.8% | 1175.33 |  |  | 98.8% | 1175.33 | Completed phy.works | Item Rate
6 | Chhotapansuri-Tungasora Road (0.000-2.000)Kmp | 312.61 | Tlabung Division | 22.9.18 | 22.9.19 | 100% | 100.06 |  | - | 100% | 100.06 | Completed phy.works | Item Rate
7 | Chhotapansuri-Tungasora Road (2.000-3.500)Kmp | 209.66 | Tlabung Division | 5.10.18 | 5.10.19 | 100% | 175.89 |  |  | 100% | 175.89 | Completed physical works | Item Rate
8 | Mandiasora-Ajasora Road (0.000 - 8.500) Kmp | 827.44 | Tlabung Division | 17.6.19 | 17.6.20 | 100% | 771.57 |  |  | 100% | 771.57 | Completed physical works | Item Rate
9 | Construction & Maintenance of Sairang - Lengte-Nghalchawm (PMGSY) Road | 991.9 | NHD-I | 19.12.20 | 31.3.24 | 100% | 991.71 |  |  | 100% | 991.71 | Phy. Completed | Item rate contract
10 | Construction and Maintenance of E.Phaileng-Suangpuilawn Road (0.000-6.000Kmp) (Sh: Widening, Culverts & R/Wall and Contstruction of road using flexible pavement) | 831.6 | Saitual Division | 19.12.20 | 19.12.22 | 96.08% | 142.92 | 1.96% | - | 98.04% | 142.92 | EoT Dt.15.10.23
11 | Construction and Maintenance of E.Phaileng-Suangpuilawn Road (6.000-11.000Kmp) (Sh: Widening, Culverts & R/Wall and Construction of Road using flexible pavement) | 906.48 | Saitual Division | 19.12.20 | 19.12.22 | 91.31% | 211.36 | 3.3% |  | 94.61% | 211.36 | EoT Dt.31.3.24
12 | Construction and Maintenance of E.Phaileng-Suangpuilawn Road (11.000-16.000Kmp) (Sh: Widening, Culverts & R/Wall and Construction of Road using flexible pavement) | 807.85 | Saitual Division | 15.8.20 | 15.8.22 | 100% | 807.24 | - |  | 100% | 807.24 | EoT Dt.31.03.24
13 | Construction and Maintenance of E.Phaileng-Suangpuilawn Road (16.000-22.000Kmp) (Sh: Widening, Culverts & R/Wall and Construction of Road using flexible pavement) | 826.35 | Saitual Division | 01.01.21 | 01.01.23 | 92.81% | 375.77 | 4.32% |  | 97.13% | 375.77 | EoT Dt.28.10.23
14 | Construction and Maintenance of E.Phaileng-Suangpuilawn Road (22.000-28.000Kmp) (Sh: Widening, Culverts & R/Wall and Construction of Road using flexible pavement) | 811.18 | Saitual Division | 01.01.21 | 01.01.23 | 100% | 632.27 | - | - | 100% | 632.27 | EoT Dt.30.3.24
15 | Construction and Maintenance of E.Phaileng-Suangpuilawn Road (28.000-34.000Kmp) (Sh: Widening, Culverts & R/Wall and Construction of Road using flexible pavement) | 1133.61 | Saitual Division | 10.02.20 | 10.02.22 | 100% | 1128.61 | - |  | 100% | 1128.61 | EoT Dt.31.12.22
16 | Construction and Maintenance of E.Phaileng-Suangpuilawn Road 34.000-40.000Kmp) (Sh: Widening, Culverts & R/Wall and Construction of Road using flexible pavement) | 1056.01 | Saitual Division | 6.01.20 | 6.01.22 | 85.04% | 508.37 | 3.72% | 54.89 | 88.76% | 563.26 | EoT Dt.4.11.23
17 | Construction and Maintenance of E.Phaileng-Suangpuilawn Road 40.000-46.000Kmp) (Sh: Widening, Culverts & R/Wall and Construction of Road using flexible pavement) | 1000.02 | Saitual Division | 6.01.20 | 6.01.22 | 87.72% | 619.07 | 0.44% |  | 88.16% | 619.07 | EoT Dt.18.7.23
18 | Construction and Maintenance of Bunghmun-W.Mualthuam Road (Sh: Cell filled Concrete Road) (0.00-13.500 Kmp) | 955.77 | Kawrthah Division | 27.11.17 | 16.9.22 | 100% | 918.23 | - | - | 100% | 918.23 | Works under maintenance from 16.9.22 | Contract after call of Tender
19 | Construction and Maintenance of Bunghmun to Thaidawr Road (0.00 Kmp-8.90 Kmp) | 745.77 | Kawrthah Division | 17.6.19 | 16.9.22 | 100% | 720.72 | - | - | 100% | 720.72 | Works under maintenance from 16.9.22 | Contract after call of Tender
20 | Construction & Maintenance of Khawzawl to Biate Road (0.00 kmp-6.00Km) Group-A | 780.49 | Khawzawl Division | 31.12.20 | 31.12.22 | 100% | 732.3 |  |  | 100% | 732.3 | EOT granted upto 31.03.24 Work completed | Item Rate Contract
21 | Construction & Maintenance of Khawzawl to Biate Road (6.00 kmp-12.00Km) Group-B | 760.98 | Khawzawl Division | 31.12.20 | 31.12.22 | 100% | 704.47 |  |  | 100% | 704.47 | EOT granted upto 31.03.24 Work completed | Item Rate Contract
22 | Construction & Maintenance of Khawzawl to Biate Road (12.00 kmp-18.00Km) Group-C | 817.47 | Khawzawl Division | 2.1.21 | 2.1.23 | 100% | 764.53 |  |  | 100% | 764.53 | EOT granted upto 29.10.23 Work completed | Item Rate Contract
23 | Construction & Maintenance of Khawzawl to Biate Road (18.00 kmp-24.00Km) Group-D | 750.94 | Khawzawl Division | 10.6.20 | 10.6.22 | 100% | 691.87 |  |  | 100% | 691.87 | EOT granted upto 31.03.24 Work completed | Item rate contract
24 | Construction & Maintenance of Khawzawl to Biate Road (24.00 kmp-30.00Km) Group-E | 754.41 | Khawzawl Division | 29.4.21 | 29.4.22 | 100% | 671.58 |  |  | 100% | 671.58 | EOT granted upto 03.03.24 Work completed | Item Rate Contract
25 | Construction & Maintenance of Khawzawl to Biate Road (30.00 kmp-36.00Km) Group-F | 1148.93 | Khawzawl Division | 7.2.20 | 7.2.22 | 100% | 988.06 |  |  | 100% | 988.06 | EOT granted upto 31.12.22 Work completed | Item Rate Contract
26 | Construction & Maintenance of Khawzawl to Biate Road (36.00 kmp-42.00Km) Group-G | 818.99 | Khawzawl Division | 1.1.21 | 1.1.23 | 100% | 792.78 |  |  | 100% | 792.78 | Completed on 23.02.24 | Item Rate Contract
27 | Construction & Maintenance of Khawzawl to Biate Road (42.00 kmp-48.00Km) Group-H | 1430.82 | Khawzawl Division | 6.1.20 | 6.1.22 | 100% | 1324.75 |  |  | 100% | 1324.75 | EOT granted upto 31.03.24 Work completed | Item rate contract
28 | Construction & Maintenance of Khawzawl to Biate Road (48.00 kmp-54.00Km) Group-I | 1108.01 | Khawzawl Division | 24.3.21 | 24.3.22 | 100% | 985.77 |  |  | 100% | 985.77 | EOT granted upto 31.03.24 Work completed | Item Rate Contract
29 | Construction & Maintenance of Khawzawl to Biate Road (54.00 kmp-60.00Km) Group-J | 937.99 | Khawzawl Division | 4.1.21 | 4.1.23 | 100% | 944.43 |  |  | 100% | 944.43 | EOT granted upto 31.12.23 Work completed | Item Rate Contract
30 | Construction & Maintenance of Khawzawl-Ngaizawl Road | 853.85 | Khawzawl Division | 13.11.17 | 13.11.19 | 93% | 729.12 | - |  | 93% | 729.12 | EOT granted upto 09.12.22 | Item Rate Contract
31 | Construction & Maintenance of Khawhai - Tlangpuilian Road | 962.79 | Khawzawl Division | 13.11.17 | 31.12.19 | 100% | 909.22 |  |  | 100% | 909.22 | EOT granted upto 01.03.24 | Item Rate Contract
32 | Construction & Maintenance of Khawzawl - Vankal Road | 1997.33 | Khawzawl Division | 13.12.18 | 13.12.19 | 88% | 1821.89 | - |  | 88% | 1821.89 | EOT granted upto 13.11.21 | Item rate contract
33 | Construction & Maintenance of Khawzawl - Hmuncheng Road | 1627.09 | Khawzawl Division | 1) 5.10.18 2)23.05.22 | 1) 5.10.19 2)30.09.22 | 100% | 1525.58 |  |  | 100% | 1525.58 | Work completed on 31.3.24 | Item rate contract
34 | Construction & Maintenance of Khawzawl - Hmuncheng Road | 1595.69 | Khawzawl Division | 05.10.18 | 05.10.19 | 75% | 959.03 | - | - | 75% | 959.03 | EOT granted upto 27.02.22 | Item rate contract
35 | Construction & Maintenance of Khawzawl - Hmuncheng Road | 668.08 | Khawzawl Division | 23.05.22 | 30.09.22 | 100% | 576.56 |  |  | 100% | 576.56 | Completed on 31.3.24 | Item rate contract
36 | Construction & Maintenance of Phuldungsei to Parvatui Road (0.00 Kmp - 17.30 Kmp) | 3340.55 | Mamit Division | 13.12.18 |  | 100% | 3812.65 |  |  | 100% | 3812.65 |  | Item rate
37 | Construction & Maintenance of Tuipuibari to Andermanik Road (0.00 Kmp - 2.760 km) | 430.18 | Mamit Division | 17.9.18 | 17.9.19 | 100% | 428.43 |  |  | 100% | 428.43 |  | Item rate
38 | Construction & Maintenance of Andermanik to N.Belkhai Road (0.00 Kmp - 6.00 km) | 1016.7 | Mamit Division | 10.6.19 | 10.6.20 | 51.31% | 565.16 |  |  | 51.31% | 565.16 | Revised Target date of completion= 31.03.2024 | Item rate
39 | Thuampui - Lungchem Road (23.000 - 27.000 KMP) | 447.49 | Lunglei Road Division-I | 27.10.17 | 21.07.21 | 100% | 447.49 | - | - | 100% | 447.49 | Deviation already approved due to Some items are changed as mentioned in EE letter No.D-13024/5/2019(DV)/S&I/LD/PWD/Pt/10 Dt.18.02.21 Completed
40 | Thuampui - Lungchem Road (27.000 -32.000 KMP) | 395.75 | Lunglei Road Division-I | 27.10.17 | 24.09.21 | 100% | 378.64 | - | - | 100% | 378.64
41 | Thuampui - Lungchem Road (32.000 -37.000 KMP) | 372.33 | Lunglei Road Division-I | 27.11.17 | 30.09.22 | 100% | 372.31 | - |  | 100% | 372.31 | Completed
42 | Thuampui - Lungchem Road (37.000 - 40.900 KMP) | 336.09 | Lunglei Road Division-I | 27.10.17 | 13.08.21 | 100% | 336.09 | - | - | 100% | 336.09 | Completed
43 | Construction and Maintenance of Sachan to Sumasumi Road (0.00 - 24.09 Kmp) | 4005.26 | Lunglei Road Division-I | 10.06.19 | 31.03.24 | 84% | 3421.35 |  |  | 84% | 3421.35 | Work in progress
44 | Construction and Maintenance of Sumasumi - Tuikawi Road (0.00 - 19.22 Kmp) | 2882.21 | Lunglei Road Division-I | 14.06.19 | 1.11.22 | 56% | 1384.83 | 3% |  | 59% | 1384.83 | Work in progress
45 | Thuampui - Lungchem Road (0.000 - 4.000 KMP) | 85.83 | Lunglei Road Division-I | 01.04.21 | 31.03.22 | 100% | 85.83 | - |  | 100% | 85.83 | Completed
46 | Thuampui - Lungchem Road (4.000 - 7.000 KMP) | 268.21 | Lunglei Road Division-I | 27.10.17 | 14.07.21 | 100% | 268.19 | - | - | 100% | 268.19 | Completed
47 | Thuampui - Lungchem Road (7.000 - 10.000 KMP) | 306.59 | Lunglei Road Division-I | 27.10.17 | 15.08.21 | 100% | 306.56 | - | - | 100% | 306.56 | Completed
48 | Thuampui - Lungchem Road (10.000 - 14.000 KMP) | 387.7 | Lunglei Road Division-I | 27.10.17 | 04.07.21 | 100% | 387.68 | - | - | 100% | 387.68 | Completed
49 | Thuampui - Lungchem Road (14.000 - 18.000 KMP) | 422.04 | Lunglei Road Division-I | 13.11.17 | 31.12.22 | 100% | 422.03 | - |  | 100% | 422.03 | Completed
50 | Thuampui - Lungchem Road (18.000 - 21.000 KMP) | 457.75 | Lunglei Road Division-I | 27.10.17 | 07.11.21 | 100% | 457.75 | - |  | 100% | 457.75 | Some items are changes due to Deviation approval vide EE letter no.D-13024/5/2019(DV)/S&I/LDIPWD/28 dt.9.03.22 completed
51 | Thuampui - Lungchem Road (21.000 - 23.000 KMP) | 400.74 | Lunglei Road Division-I | 13.11.17 | 31.07.22 | 100% | 400.74 | - |  | 100% | 400.74 | Completed
52 | Const. & Maint.of Bunghmun to Sachan Road (0.00-9.07Kmp) | 1325.06 | Lunglei Road Division-I | 13.12.18 | 31.03.24 | 74% | 899.05 |  |  | 74% | 899.05
53 | Const. & Maint.of Khawhri to Chawngtui Road (0.00-17.81 Kmp) | 1280.59 | Lunglei Road Division-II | 8.10.18 | 31.3.24 | 100% | 1280.16 |  |  | 100% | 1280.16 | Phy. Completed | Open Tender
54 | Const. & Maint.of Luangmual to Vaisam Road (0.00-26.700 Kmp) | 4711.5 | Lunglei Road Division-II | 10.06.19 | 31.3.24 | 86.31% | 4044.11 |  |  | 86.31% | 4044.11 | 1) EOT Granted upto 31.3.2024 2) Deviation Sanction No.B-15028/240/2023/Ph-II/28/EC/PWD/PMGSY/8 of 9.10.23 | Open Tender
55 | Const. & Maint.of Haulawng to Dawn Road (0.00-6.00 Kmp) | 766.65 | Lunglei Road Division-II | 10.06.20 | 31.3.24 | 100% | 766.36 |  |  | 100% | 766.36 | Phy. Completed | Open Tender
56 | Const. & Maint.of Haulawng to Dawn Road (6.00-12.000 Kmp) | 632.64 | Lunglei Road Division-II | 01.01.21 | 31.3.24 | 100% | 632.64 |  |  | 100% | 632.64 | Phy. Completed | Open Tender
57 | Const. & Maint.of Haulawng to Dawn Road (12.00-18.000 Kmp) | 730.72 | Lunglei Road Division-II | 01.01.21 | 31.3.24 | 100% | 730.58 |  |  | 100% | 730.58 | Phy. Completed | Open Tender
58 | Const. & Maint.of Haulawng to Dawn Road (18.00-24.000 Kmp) | 850.56 | Lunglei Road Division-II | 01.01.21 | 31.3.24 | 100% | 841.71 |  |  | 100% | 841.71 | Phy. Completed | Open Tender
59 | Const. & Maint.of Haulawng to Dawn Road (24.00-30.500 Kmp) | 883.22 | Lunglei Road Division-II | 01.01.21 | 31.3.24 | 100% | 883.22 |  |  | 100% | 883.22 | Phy. Completed | Open Tender
60 | Construction of Nghalimlui to Bolisora (0.00-3.00)Kmp (Sh: FC, Culvert, R.Wall) | 158.33 | Lawngtlai Division | 27.10.17 | 30.04.20 | 100% | 158.33 | - | - | 100% | 158.33 | Completed | NIT
61 | Construction of Nghalimlui to Bolisora (3.00-5.00)Kmp (Sh: FC, Culvert, R.Wall) | 249.17 | Lawngtlai Division | 27.10.17 | 23.03.20 | 100% | 247.3 | - | - | 100% | 247.3 | Completed | NIT
62 | Construction of Nghalimlui to Bolisora (5.00-8.00)Kmp (Sh: FC, Culvert, R.Wall) | 206.24 | Lawngtlai Division | 27.10.17 | 10.08.20 | 100% | 206.24 | - | - | 100% | 206.24 | Completed | NIT
63 | Construction of Nghalimlui to Bolisora (8.00-12.65)Kmp (Sh: FC, Culvert, R.Wall) | 266.55 | Lawngtlai Division | 27.10.17 | 16.08.20 | 100% | 246.66 | - | - | 100% | 246.66 | Completed | NIT
64 | Construction of Karlui to Damlui (0.00-2.00)Kmp (Sh: FC, Culvert, R.Wall) | 207.84 | Lawngtlai Division | 27.10.17 | 28.2.20 | 100% | 207.66 | - | - | 100% | 207.66 | Completed | NIT
65 | Construction of Karlui to Damlui (2.00-6.00)Kmp (Sh: FC, Culvert, R.Wall) | 227.53 | Lawngtlai Division | 27.10.17 | 30.10.19 | 100% | 216.35 | - | - | 100% | 216.35 | Completed | NIT
66 | Construction of Karlui to Damlui (6.00-8.800)Kmp (Sh: FC, Culvert, R.Wall) | 147.71 | Lawngtlai Division | 13.11.17 | 25.10.19 | 100% | 147.69 | - | - | 100% | 147.69 | Completed | NIT
67 | Construction of Bolisora to Chamdurtlang (0.00 - 2.00) Kmp (Sh: FC, Culvert. R.Wall) | 155.5 | Lawngtlai Division | 27.10.17 | 20.05.20 | 100% | 155.49 | - | - | 100% | 155.49 | Completed | NIT
68 | Construction of Bolisora to Chamdurtlang(2.00-5.00)Kmp (Sh: FC, Culvert, R.Wall) | 229.32 | Lawngtlai Division | 27.10.17 | 16.03.20 | 100% | 229.32 | - | - | 100% | 229.32 | Completed | NIT
69 | Construction of Bolisora to Chamdurtlang(5.00-9.00)Kmp (Sh: FC, Culvert, R.Wall) | 359.96 | Lawngtlai Division | 01.04.19 | 29.09.21 | 100% | 359.95 | - | - | 100% | 359.95 | Completed | NIT
70 | Construction of Bolisora to Chamdurtlang(9.00-11.650)Kmp (Sh: FC, Culvert, R.Wall) | 251.92 | Lawngtlai Division | 27.10.17 | 16.03.20 | 100% | 251.9 | - | - | 100% | 251.9 | Completed | NIT
71 | Construction of Ajasora to Longpuighat (0.00-10.900)Kmp (Sh: Const.of road using Flexible Pavement Technology) | 934 | Lawngtlai Division | 13.11.17 | 19.12.21 | 100% | 857.32 | - | - | 100% | 857.32 | Ongoing | NIT
72 | Construction of Jognasury - Karlui Road (0.000-12.100)Kmp (Sh: Formation Cutting, Culvert & R.Walls & Const.of of Road Using Flexible Pavement) | 888.27 | Lawngtlai Division | 13.12.18 | 30.09.22 | 100% | 760.65 |  | - | 100% | 760.65 | Completed | NIT
73 | Construction of Maniababsora-I to Maniababsora-II Road (0.000-1.520)Kmp (Sh: FC, Culvert & R.Wall & Const.of road using Panelled Concrete Technology) | 212.32 | Lawngtlai Division | 27.12.18 | 22.11.20 | 100% | 212.32 | - | - | 100% | 212.32 | Completed | NIT
74 | Construction of Boroituli to Jaruldubasora Road (0.000-2.100)Kmp (Sh: FC, Culvert & R.Wall & Const.of road using Panelled Concrete Technology) | 257.02 | Lawngtlai Division | 17.09.18 | 10.02.22 | 100% | 257 | - | - | 100% | 257 | Completed | NIT
75 | Construction of Boroituli to Jaruldubasora Road (2.000-3.700)Kmp (Sh: FC, Culvert & R.Wall & Const.of road using Panelled Concrete Technology) | 269.85 | Lawngtlai Division | 28.09.18 | 30.09.22 | 100% | 268.54 | - | - | 100% | 268.54 | Completed | NIT
76 | Construction of Vaseitlang to Lokhisury Road(0.00-9.560)Kmp (Sh: FC, Culvert, R.Wall & Const.of road using Panelled Concrete Technology) | 1366.7 | Lawngtlai Division | 28.09.18 | 30.09.22 | 82.73% | 899.62 |  |  | 82.73% | 899.62 | Ongoing | NIT
77 | Construction of Vathuampui to Tuisentlang Road(0.000-9.600)Kmp (Sh: FC, Culvert, R.Wall & Const.of Road Using panelled Concrete) | 910.99 | Lawngtlai Division | 03.01.18 | 30.09.22 | 85.63% | 910.99 | 2.83% | - | 88.46% | 910.99 | Ongoing | NIT
78 | Construction of Vathuampui to Chamdur P-I Road(0.000-1.720)Kmp (Sh: FC, Culvert, R.Wall & Const.of Road Using panelled Concrete) | 263.08 | Lawngtlai Division | 15.10.18 | 30.09.22 | 100% | 261.11 | - | - | 100% | 261.11 | Completed | NIT
79 | Construction of Vathuampui to Chamdurtlang (0.000-1.720)Kmp (Sh: FC, Culvert, R.Wall & Const.of Road Using panelled Concrete) | 274.17 | Lawngtlai Division | 13.12.18 | 30.09.22 | 71.15% | 206.45 |  |  | 71.15% | 206.45 | Ongoing | NIT
80 | Construction of Vathuampui to Chamdurtlang (2.000-3.800)Kmp (Sh: FC, Culvert, R.Wall & Const.of Road Using panelled Concrete) | 360.89 | Lawngtlai Division | 22.09.18 | 30.09.22 | 100% | 356.27 | - |  | 100% | 356.27 | Completed | NIT
81 | Construction of Chamdurtlang to Mualtlang Road(0.000-7.970)Kmp (Sh: FC, Culvert, R.Wall & Const.of Road Using panelled Concrete) | 1152.2 | Lawngtlai Division | 13.12.18 | 30.09.22 | 100% | 1089.09 | - | - | 100% | 1089.1 | Completed | NIT
82 | Construction of Parva II to Zochachhuah Road(0.000-29.720)Kmp (Sh: FC, Culvert, R.Wall & Const.of Road Using panelled Concrete) | 5432.38 | Lawngtlai Division | 05.04.19 | 30.09.23 | 100% | 4745.79 | - |  | 100% | 4745.79 | Ongoing | NIT
83 | Construction of Parva II to Bondukbanga Road(0.000-2.000)Kmp (Sh: FC, Culvert, R.Wall & Const.of Road Using Flexible Pavement) | 269.72 | Lawngtlai Division | 28.09.18 | 12.01.22 | 100% | 269.14 | - | - | 100% | 269.14 | Completed | NIT
84 | Construction of Parva II to Bondukbanga Road(2.000-4.120)Kmp (Sh: FC, Culvert, R.Wall & Const.of Road Using Flexible Pavement) | 294.1 | Lawngtlai Division | 13.12.18 | 31.12.22 | 100% | 281.42 |  |  | 100% | 281.42 | Ongoing | NIT
85 | Construction &Maintenance of Parva-II - Kamtuli Road (0.000-25.550)Kmp (Sh: FC, Culvert, R.Wall & Const.of Road Using panelled Concrete) | 4139.88 | Lawngtlai Division | 17.06.19 | 30.09.22 | 96.64% | 2727.3 |  |  | 96.64% | 2727.3 | Ongoing | NIT
86 | Construction & Maintenance of Vaseitlang to Maniababsora Road (0.000-13.500)Kmp (Sh: FC, Culvert, R.Wall & Const.of Road Using panelled Concrete) | 2361.15 | Lawngtlai Division | 14.06.19 | 30.04.22 | 100% | 2358.27 | - | - | 100% | 2358.27 | Completed | NIT
87 | Construction & Maintenance of Sedailui to Tuikhurlui Road (0.000-1.720)Kmp (Sh: FC, Culvert, R.Wall & Const.of Road Using panelled Concrete Techonology) | 204.33 | Lawngtlai Division | 17.06.19 | 08.05.22 | 92.06% | 159.96 | - | - | 92.06% | 159.96 | Ongoing | NIT
88 | Construction &Maintenance of M.Kawnpui to Vathuampui Road (0.000-20.000)Kmp (Sh: FC, Culvert, R.Wall & Const.of Road Using panelled Concrete Technology) | 1976.47 | Lawngtlai Division | 14.06.19 | 30.09.22 | 93.02% | 1204.58 | 4.41% |  | 97.43% | 1204.58 | Ongoing | NIT
89 | Construction &Maintenance of Sumsului Road to Jognasury (0.000-15.44)Kmp (Sh: Const.of Road Using panelled Concrete Technology) | 1278.38 | Lawngtlai Division | 14.06.19 | 30.09.22 | 93.53% | 1065.69 |  |  | 93.53% | 1065.69 | Ongoing | NIT
90 | Construction &Maintenance of Chawngthe 'P to Sumsului Road (0.000 - 4.570) Kmp | 313.29 | Lawngtlai Division | 1.07.19 | 31.03.22 | 100% | 302.97 |  |  | 100% | 302.97 | Ongoing | NIT
91 | Construction of Niawhtlang - Chakhang Road Package No.MZ0761(0.000-23.260Kmp) | 870.43 | Siaha Division | 10.14.23 | 3.14.24 | 47.15% | 268.12 |  |  | 47.15% | 268.12 | 1. Work in progress 2. Analysis for 4 km | Item rate contract
92 | Construction of Niawhtlang-Chakhang Road Package No.MZ 0771(0.000-20.790Kmp) | 879.2 | Siaha Division | 15.10.23 | 15.03.24 | 35.8% | 255.28 |  |  | 35.8% | 255.28 | Work in progress | Item rate contract
93 | Construction of Phura - Vahai Road (0.000 - 17.000) Kmp | 1563.92 | Siaha Division | 13.11.17 | 13.11.19 | 77% | 1409.46 |  |  | 77% | 1409.46 | Pending legal case/Initiate for forclosure | Item rate contract
94 | Const.& Maintenance of Mualcheng-N.Vanlaiphai Road Group 'A' (0.000-8.000 Kmp) | 515.65 | Serchhip Division | 31.12.20 | 31.12.22 | 100% | 303.31 | - | - | 100% | 303.13 | Physically completed | Item rate contract
95 | Const.& Maintenance of Mualcheng-N.Vanlaiphai Road Group 'B' (8.000-16.000 Kmp) | 586.35 | Serchhip Division | 31.12.20 | 31.12.22 | 100% | 586.34 | - |  | 100% | 586.34 | Physically completed | Item rate contract
96 | Construction of Tuithumhnar to Lunghauka (0.00 - 5.00) Kmp (Sh: FC, Culvert, R.Wall) | 189.03 | Multi Modal Project Division | 27.10.17 | 31.07.19 | 100% | 189.03 | - | - | 100% | 189.03 | Completed on 05/07/2019
97 | Construction of Tuithumhnar to Lunghauka (5.00 - 7.00) Kmp (Sh: FC, Culvert, R.Wall) | 196.98 | Multi Modal Project Division | 27.10.17 | 31.03.21 | 100% | 193.28 | - | - | 100% | 193.28 | Completed on 30/03/2021
98 | Construction of Tuithumhnar to Lunghauka (7.00 - 10.00) Kmp (Sh: FC, Culvert, R.Wall) | 247.04 | Multi Modal Project Division | 27.10.17 | 16.07.20 | 100% | 247.04 | - | - | 100% | 247.04 | Completed on 20/07/2020
99 | Construction of Tuithumhnar to Lunghauka (10.00 - 13.00) Kmp (Sh: FC, Culvert, R.Wall) | 184.6 | Multi Modal Project Division | 27.10.17 | 29.06.20 | 100% | 184.6 | - | - | 100% | 184.6 | Completed on 29/06/2020
100 | Construction of Tuithumhnar to Lunghauka (13.00 - 15.480) Kmp (Sh: FC, Culvert, R.Wall) | 198.08 | Multi Modal Project Division | 27.10.17 | 16.07.20 | 100% | 198.08 | - | - | 100% | 198.08 | Completed on 26/06/2020
101 | Construction & Maintenance of Ngenpuitlng to Darnamtlang (0.00 - 4.00) Kmp (Sh: FC, Culvert, R.Wall) | 233.08 | Multi Modal Project Division | 27.10.17 | 31.01.20 | 100% | 193.78 | - | - | 100% | 193.78 | Physically completed on 01/05/2020
102 | Construction & Maintenance of Ngenpuitlng to Darnamtlang (4.00 - 6.20) Kmp (Sh: FC, Culvert, R.Wall) | 161.44 | Multi Modal Project Division | 27.10.17 | 31.08.21 | 100% | 224.53 | - | - | 100% | 224.53 | Completed on 30/08/2021
103 | Construction & Maintenance of Tuithumhnar to Hmawngbu (0.00 - 6.720) Kmp (Sh: Construction of road using Grove Concrete Pavement) | 442.51 | Multi Modal Project Division | 12.11.17 | 1.10.21 | 100% | 441.76 | - |  | 100% | 441.76 | Completed on 16/06/2021
104 | Construction of Sabualtlang to Hmawngbuchhuah Road (0.00 - 1.760) Kmp (Sh:Formation Cutting, Culvert & Retaining Walls & Construction of Road Using Flexible Pavement) | 244.22 | Multi Modal Project Division | 17.12.18 | 24.10.21 | 100% | 244.22 | - |  | 100% | 244.22 | Completed on 23/10/2021
105 | Construction & Maintenance of Nalkawn to Rulkual Road (0.000-16.000) Kmp Group A (Sh: Const.of Road using Cold Mix Technology | 1078.79 | Multi Modal Project Division | 04.01.21 | 04.01.23 | 100% | 1194.51 | - | - | 100% | 1194.51 | Completed on 29.9.22
106 | Construction & Maintenance of Nalkawn to Rulkual Road (16.000-32.000) Kmp Group B (Sh: Const.of Road using Cold Mix Technology | 1315.37 | Multi Modal Project Division | 12.12.23 | 30.3.24 | 75.93% | 925.6 |  |  | 75.93% | 925.6 | The work was retendered and newly awarded to the new contractor. the work is progress
107 | Construction & Maintenance of Rawmibawk to Phalrang Road (0.000-10.200) Kmp (Sh: Const.of Road usinggroove concrete Technology | 759.92 | Multi Modal Project Division | 13.12.18 | 30.09.22 | 100% | 758 | - |  | 100% | 758 | Completed on 29.9.22
108 | Construction & Maintenance of Saiha to Rawmibawk Road (0.000-22.30) Kmp (Sh: Const.of Road using groove concrete Technology | 1941.19 | Multi Modal Project Division | 17.06.19 | 30.09.22 | 100% | 1938.8 |  |  | 100% | 1938.8 | Phy. Completed on 29.03.23

## SEDP
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding: SEDP | [8 empty] | Month : June 2024
Sl. no | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Const. of Approach Road to Aizawl College at Mualpui | 415 | Aizawl Road South Division | 26.07.21 | 26.04.22 | 73% | 300 | - | - | 73% | 300 | Work in progress | Item Rate Contract
2 | Re-Construction of Concrete Pavement on Approach Road to Mission Vengthlang Cemetry, L=150M | 8.51 | Aizawl Road South Division | [8 empty] | Work connot be started due to land conflict with land owner
3 | Construction of High Court Parking Building at MINECO | 1960 | Project Division-I | 2.7.20 | 29.8.24 | 85% | 11652.32 | 5% |  | 90% | 11652.32 |  | EPC
4 | Const.of MBSE New Building and renovation of existing main Building | 1000 | Project Division-III | 22.2.21 | 6.7.24 | 90% | 679.68 | 2% |  | 92% | 679.68 | Work in progress | PWD Form-8
5 | Improvement of Khanpui - Tualbung Road Phase-II | 2935.99 | Saitual Division | 25.03.18 | 15.6.22 | 83.61% | 2327.33 |  | 77.09 | 83.61% | 2404.42
6 | Strenthening of Saitual - Phullen Road (28.300Km)(Tuivawl-Phullen) (28.700-57.000) | 1259.71 | Saitual Division | 18.12.19 | 18.04.21 | 100% | 800.01 |  |  | 100% | 800.01 | Phy. Completed
7 | Resurfacing of Aizawl-Thenzawl-Lunglei Road (30.00 Kmp - 51.00 Kmp) | 1271.17 | Hmuifang Division | 20.02.23 | 20.07.23 | 100% | 1252.49 |  |  | 100% | 1252.49 | Phy. Completed | Item rate

## SEDP 4 (hidden)
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding: SEDP | [8 empty] | Month : May 2022
Sl. no | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the Month |  | Overall cumulative achievement |  | Remarks
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
25 | Widening of Road infront of CE, PWD Building at Tuikhuahtlang | 46.5 | Aizawl Road South Division |  |  | 100% | 46.5
26 | Const. of Approach Road to Aizawl College at Mualpui | 415 | Aizawl Road South Division |  |  | 35% | 120.12
27 | Const. of Approach Road to T.Romana College from ITI to Mualpui Road | 464.9 | Aizawl Road South Division |  |  | 49% | 171.33
28 | Wideing of Curve near Zokhuma's House on Bethlehem Vengthlang to College Road | 38.5 | Aizawl Road South Division |  |  | 100% | 38.5
29 | Const.of Approach Road to Zopar Vaipuanpho | 50 |  |  |  | 100% | 50
30 | Improvement at 0.50 Kmp on Hridaikawn to Power Sub Station at Tlangnuam | 12.3 | Aizawl Road South Division |  |  | 100% | 12.3
31 | Concrete pavement from Kohhran Thianghlim Biak In to PHE Pump House road within Maubawk | 30.5 | Aizawl Road South Division |  |  | 100% | 30.5
32 | Const.of Composite Retaining Wall at Kawilun Republic Veng | 7 | Aizawl Road South Division |  |  | 100% | 7
33 | Re-Construcrion of Retaining Wall near T.Lalhmuntiama's house on Nursery to Mission Veng Road via Kawltheihuan | 2.19 | Aizawl Road South Division |  |  | 100% | 2.19
34 | Const.of Bridge on Chhinga Vengthar to Tuithiang Road | 586.36 | Aizawl Road South Division |  |  | 59% | 60
35 | Widening of Approach road with rigid pavement from Thlanmual to Dam veng at Tlangnuam | 55 | Aizawl Road South Division |  |  | 100% | -

## CSS
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding: CSS | [8 empty] | Month : June 2024
Sl. no | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Polytechnic at Lawngtlai (Const.of Administrative cum Academic Block) | 800 | Lunglei Building Project Division | 18.3.13 | 14.10.15 | 100% | 624.62 | - | - | 100% | 624.62 | Civil Work Completed & I/E Works not yet executed | Open Tender
2 | Construction of Judicial Quarter at Lawngtlai Grade-I Qtr. | 110.58 | Lunglei Building Project Division | 8.6.20 | 7.12.21 | 100% | 100.64 |  |  | 100% | 100.64 | Civil Works completed I/E not yet done | Restricted Tender
3 | Construction of Judicial Quarter at Lawngtlai Type-I & II Qtr. | 138.67 | Lunglei Building Project Division | 22.6.20 | 30.08.23 (Revised) | 100% | 36.25 |  | 85.12 | 100% | 121.37 | -do- | Restricted Tender
4 | Const.of Administrative cum Academic Block for Polytechnic Thingsen Saiha | 501.08 | Lunglei Building Project Division | 15.03.16 | 11.7.17 | 60% | 167.64 | - |  | 60% | 167.64 | The contractor has stopped Work till date due to non-release of Fund from Central Government. However, fresh LOC have been allocated and payments being made for contractors of Sl.No (i) & (iii) | Open Tender
5 | Const.of Hostel building for Polytechnic at Thingsen saiha | 191.83 | Lunglei Building Project Division | 15.3.16 | 11.04.17 | 80% | 110.41 | - |  | 80% | 110.41
6 | Construction of Staff Qtr Type I, II & III for Polytechnic at Thingsen Saiha | 77.1 | Lunglei Building Project Division | 06.10.15 | 20.4.17 | 100% | 87.51 |  |  | 100% | 87.51
7 | Const.of Type-IV Qtr for Polytechnic at Thingsen Saiha | 29.99 | Lunglei Building Project Division | 15.03.16 | 11.01.17 | 76.5% | 24.79 | - | - | 76.5% | 24.79
8 | Construction of District Court Building at Saiha. | 1803.39 | Lunglei Building Project Division | 10.9.18 | 31.10.23 (Revised) | 100% | 1803.395 |  |  | 100% | 1803.395 | Works completed on dt.28.4.23 and handover paper submitted | Restricted Tender
9 | Construction of fast truck Court at Kolasib | 1799.85 | Project Division II | 20.09.22 | 20.09.24 | 59% | 519.36 | 5% | 200 | 64% | 719.36 | Work in progress | Item Rate
10 | Const.of Tourist Logde at Champhai | 328.73 | Project Division-III | 09.12.10 | 30.11.20 | 100% | 300 | - | - | 100% | 300 | Taken over by the Deptt.on Dt.3.8.2021 LOC amounting to Rs.30.00 lakh submitted for clearing liability.Hence, release of LOC awaited for financial closure.
11 | Const.of Polytechnic at Chhiahtlang i) Approach Road | 800 | Project Division-III | 3.3.16 | 2.8.16 | 100% | 103.67 | - | - | 100% | 103.67 | As desired by H&TE Department revised estimate amounting to Rs.1669.26 lakh is submitted in February 2024
ii) Administrative & Academic Block iii) Hostel Block iv) Staff Quarters
12 | Construction of General Nursing Midwifery Hostel at Champhai | 250 | Project Division-III | 13.07.22 | 13.07.24 | 92% | 150.51 | 1% |  | 93% | 150.51 | Work in progress | PWD Form-8
13 | Construction of Hostel for S.T Girls at Champhai | 462.75 | Project Division-III | 18.9.23 | 28.9.25 | 38% | 67.57 | 7% |  | 45% | 67.57 | Work in progress | PWD Form-8
14 | 10-Bedded Intergrated AYUSH Hospital at Keifang, Saitual District | 750 | Project Division-III | 13.10.23 | 13.10.25 | 2% |  | 1% |  | 3% |  | New architecture design is approved and work in progress | PWD Form-8
15 | Renovation of Mizram Secretariat Building at MINECO | 200 | Aizawl Building Division | 13.11.23 | 31.03.24 | 90% | 146.87 | 6% | 77.6 | 96% | 224.47 |  | Departmental

## MoRTH
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : NH(O) - MoRTH | [9 empty] | Month : May 2024
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummutive Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Steel Arch (Semi Through) Bridge with concrete Deck 90m Arch Span over River Tlawng at Km 5.200 on NH-44A In the State of Mizoram of EPC Mode (NHO) | 4244 | NHD-I | 30.01.21 | 26.3.24 | 79.5% | 3013.37 | 0.5% | 6.88 | 80% | 3020.25 | On going | EPC Mode
2 | Periodical Renewal between Ch.183/00 Kmp to Ch.190/00 Kmp on NH-54A during 2022-23 in the state of Mizoram (Length=7.00Km) | 563.17 | NHD-I | 24.01.24 | 24.09.24 | 96.07% | 400.08 |  |  | 96.07% | 400.08 | On going | EPC Mode
3 | Periodical Renewal between Ch.183/00 Kmp to Ch.190/00 Kmp on NH-54A during 2022-23 in the state of Mizoram (Length=7.00Km) | 443.5 | NHD-I | 19.08.23 | 19.04.24 | 100% | 421.05 |  | 0.8 | 100% | 421.85 | Phy. completed | EPC Mode
4 | Ordinary Repair (DPP) for short term maintenance from Km 0.00 to Km 42.80 and from Km 60.30 to km 130.00 on NH-150 in the state of Mizoram | 327.82 | NHD-II | 05.11.21 | 02.02.22 | 100% | 327.67 | - | - | 100% | 325.68 | Payment pending for RA-IV and witheld amount from RA-III Rs.21,30,839.90 | Item Rate
5 | Construction of 2 laning with paved shoulder flexible pavement from Km 42.80 to Km 60.30 of NH-150 road during 2016-17 within Mizoram State under NH(O) Scheme. (Job No. & Dtae of Sac Original/Revised : 150/MZ/2016-17/107) | 20594.82 | NHD-II | 29.11.17 | 22.05.21 | 100% | 13681.44 | - | 318.56 | 100% | 14000 | Phy. Completed | EPC Mode
6 | Reconstruction of single pavement from Km 130.00 to Km 140.00 on NH-150 in the State of Mizoram on EPC Mode (Job No.150/MZ/2019-20.119) | 3440.95 | NHD-II | 23.11.20 | 26.05.23 | 100% | 2441.16 | - | - | 100% | 2441.16 | Work under Defect Liability period | EPC Mode
7 | Consultancy Services for Project Management including prparation of Feasibility Study/Detailed {roject report fro laning with Paved Shoulders of stretches from Km 0/00 to Km 42/80 and from Km 60/00 to Km 140/00 on NH-150 NH (O) Package No. DPR/MZ/NER/2015/13 | 166.04 | NHD-II | 24.06.17 | 20.05.18 | 70% | 16.6 |  | - | 70% | 16.6 |  | MoRTH
8 | Short term Maintenance Contract for NH-150(60/30 to 130/000kmp) i.e 69.70Km Length for the year 2023-2024 under national Highway Division-II, Aizawl in the state of Mizoram (Job: RW/GHT/STMC/MZ/23-24/3) | 265.15 | NHD-II | 09.03.24 | 08.03.25 | 85% | 48.37 | 5% | 22.08 | 90% | 70.45 | On going | Item rate
9 | Short Term Maintenance Contract to NH-150 for the year 2023-2024 for chaninage Km 63/300 Km) under National Hoigway Division-II, Aizawl in the state of Mizoram | 166.8 | NHD-II | 09.03.24 | 08.03.25 | 95% | 59.59 | 5% | 16.64 | 100% | 76.23 | On going | Item rate
10 | Periodical Renewal of NH-54 in the state of Mizoram under ARP for the year 2019-2020 between Km 118/00-133/00 Km (15.00Km) | 1477 | NHD-III | 20.04.21 | 20.04.22 1st Extension of Time = 96 day as (19.4.22=14.6.22) | 100% | 1178 |  |  | 100% | 1178 | Completed | EPC
11 | Strengthening of Km 10.00 to Km 33.00 (Length 23.00 Km) on NH-306A including Strengthening & Construction of Retaining Walls and Culverts and Strenthening of 3 Nos.of Bailey Bridges in the State of Mizoram | 6523 | NHD-III | 07.02.22 | 07.08.23 | 100% | 4178.05 |  |  | 100% | 4178.05 | Completed | EPC
12 | Strengthening/Construction/Widening to 2-lane from km 89/00 to km 105/00 of NH-154 (New NH-6) under NH Division III in the state of Mizoram for the year 2022-23 (Length=16Km) | 8681 | NHD-III | 04.09.23 | 04.03.25 | 45.22% | 1032.03 | 22.21% | 575.86 | 67.43% | 1607.89 | Work in progress | EPC
13 | Short term Maintenance Contract on KM0/00 to 10/00 and Km 33/00 to 45/00 (22km) on Nh 306A in the state of Mizoram (Job No.RE/GHT/STMC/MZ/23-24/7) | 458 | NHD-III | 17.2.24 | 31.3.25 | 87.33% |  | 5.35% |  | 92.68% |  | Work in progress | EPC
14 | PR of NH-54 in the state of Mizoram under Annual Renewal Programme for the year 2019-20 from Km 70/00 to Km 98/00 (25.00Km) on EPC mode (job No.154/MZ/2020-212/120) | 1961 | NHD-III | 28.9.20 | 28.9.21 | 100% | 1771 |  |  | 100% | 1771 | Completed | EPC
15 | Strengthening between Km 119/00 to Km 147/00 on NH-154 including construction of retaining walls at essential places in the state of Mizoram on EPC mode (Job No.154/MZ/2020-212/120) | 2407 | NHD-III | 23.12.20 | 23.06.22 | 100% | 2407.2 |  |  | 100% | 2407.2 | Completed | EPC

## Article 275
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : Article 275(1) of the Constitution | [9 empty] | Month : June 2024
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummutive Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Tribal Hostel at Suangpuilawn, Mizoram | 320 | Project Division-IV | 12.08.23 | 12.08.25 | 20.64% | 54.94 | 3.86% |  | 24.5% | 54.94 | Work in progress. | Item Rate
2 | Construction of Multipurpose Community Hall at Darlawn, Mizoram | 720 | Project Division-IV | 12.08.23 | 12.08.25 | 23.59% | 72.6 | 1.41% | 84.91 | 25% | 157.51 | Work in progress. | Item Rate

## ECRP-II
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : ECRP-II (Emergency Covid Response Package-II) | [9 empty] | Month : June 2024
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummutive Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of 50 Bedded critical care block at Champhai District Hospital Mizoram | 1346.4 | Project Division-III | 4.8.23 | 4.2.26 | 25% | 129.26 | 2% |  | 27% | 129.26 | Work in progress | PWD Form-8

## PM DeVINE
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : PM-DeVINE | [9 empty] | Month : June 2024
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummutive Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of Contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Bamboo Link Road from Lengpui to Saiphal Bamboo Plantation (41 Km) under PM-DeVINE | 6642 | NHD-I | 21.07.23 | 19.01.25 | 18% | 300 |  |  | 18% | 300
2 | Construction of Bamboo Link Road from Tuirial Airfield to North Chaltlang (18Km) under PM-DevINE | 3358 | Aizawl Road North Division | 1.08.23 | 31.01.25 | 26% |  | 1.58% |  | 27.58% |  | Work in progress

## ICMR
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : DIPHR (ICMR) | [9 empty] | Month : June 2024
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummutive Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of Contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Model Rural Health Research Units at Lungtian Ram, Aibawk | 207.5 | Project Division-II | 21.09.23 | 21.03.25 | 33% | 69.04 | 8% |  | 41% | 69.04 | Workin progress | Item Rate

## NLCPR
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : NLCPR | [9 empty] | Month : June 2024
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Community Hall at Various places in Mizoram (Sh: Construction of Community Hall at Saitual, Thingsulthliah, Maite, Tualbung, Lungpher, Buhban, Lenchim, Chawrtui and Puilo) | 206.49 | Project Division-III | 22.2.12 | 30.11.19 | 100% | 186.01 | - | - | 100% | 186.01 | Completed and balance fund of Rs.20.48 (Rs.16.35 lakhs NLCPR + Rs.4.13 lakhs SMS) a waited for clearing liabilities

## NEDP
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : NEDP | [9 empty] | Month: June 2024
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Officers & Staff Quarter Type-IV, 2 Units and Type-III 4 Units for Taxation Department Lunglei | 330 | Lunglei Building Project Division | 3.7.20 | 30.10.23 (Revised) | 100% | 330 |  |  | 100% | 330 | Civil Works completed and I/E Fund not yet done | Restricted Tender
2 | Construction of DC Bangalow Type-VI at Saiha | 110.9 | Lunglei Building Division | 26.11.08 | 23.05.24 (Revised) | 98.3% | 92.01 |  | - | 98.3% | 92.01 | The contractor has halted construction since Nov'23 and allocation of Balanced Fund of Rs.205.99 lakh has been awaited from the Govt.for completion of the whole projects i.e DC Office, DC Bugalow etc.Revised estimate resubmitted for approval | Restricted Tender
3 | Construction of DC Office Building at Saiha | 610.11 | Lunglei Building Division | 31.10.18 | 31.10.20 Revised 28.11.23 | 90% | 414.49 |  |  | 90% | 414.49 |  | Restricted Tender
4 | Improvement of Buarpui - Bunghmun - via Thenhlum Road (65.000-79.00) Kmp during 2016-2017 | 170.467 | Lunglei Road Division-I | 4.3.24 | 4.3.25 | 66% | 43.96 | 12% |  | 78% | 43.96 | Material collection is now in progress, hence Physical achievement could not commensurate with the financial achievement
5 | Approach Road to Kendriya School at Ramthar Veng (Nursing School Approach Road Kendriya School Ramthar Veng) | 857.5 | Lunglei Road Division-I | 2024-03-24 | 2025-03-25 | 100% | 849.26 |  |  | 100% | 849.26 | Completed
6 | Const.of Bridge on Chhinga Vengthar to Tuithiang Road | 586.36 | Aizawl Road South Division | 19.04.21 | 31.10.22 | 100% | 200 | - |  | 100% | 200 | Phy.Work completed | Item Rate Contract
7 | Reconstruction of Concrete Pavement on approach road to Mission Vengthlang Cemetry, L=150m | 8.51 | Aizawl Road South Division | [8 empty] | Work cannot be started due to land conflict with land owner

## SPP
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : SPP | [9 empty] | Month : June 2024
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Circuit House at Serchhip | 358.18 | Project Division-III |  |  | - | - | - | - | - | - | Estimate amounting to Rs.3.58 Cr submitted as per new drawing. Waiting for approval for tender.
2 | Construction of Truckable Road between Tlangpui and Lungva | 480 | Khawzawl Division | 5.7.18 | 5.7.19 | 63% | 327.23 | - | - | 63% | 327.23 | EOT granted upto 7.10.2020 | Item rate contract

## DONER
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : One Time Special Assistance under Ministry of DONER | [9 empty] | Month : June 2024
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Re-Construction of safe House at Tlabung | 114.9 | Lunglei Building Project Division | 18.11.21 | 18.11.22 | 100% | 112.66 | - |  | 100% | 112.66 | Civil Works completed. and IE not yet done. Handover in process | Restricted Tender
2 | Re-Construction of safe shelter at Sairang | 115 | Project Division-II | 13.11.21 | 13.11.22 | 100% | 113.8 |  |  | 100% | 113.8 | Work physically completed | Item Rate

## NERSDS
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : NERSDS | [9 empty] | Month : June 2024
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Upgradation of Saiha-Lungbun-Tluangram-Haka Road in the State of Mizoram | 5021 | Saiha Division | 29.10.21 | 31.03.24 | 64.72% | 1994 |  |  | 64.72% | 1994 | UC amounting to Rs.10.65 Cr submitted on 21st july 2023 | EPC Mode
2 | Upgradation of Hnahlan-Hmunhlui-Tuimang-Singngei Road (Length = 12.000 Kms) | 4417 | Champhai Division | 29.11.21 | 31.3.24 (as per4 EoT-01) | 92.62% | 2231.4 | 0.08% | 730.44 | 92.7% | 2961.84 |  | EPC
3 | Upgradation of Zote-Fartlang-Buanli-Tuipui-Tawnzang Road in the state of Mizoram under NERSDS (Length = 8.00 Kms) | 2926 | Champhai Division | 12.12.21 | 31.3.24 (as per4 EoT-01) | 100% | 1722.19 |  |  | 100% | 1722.19 |  | EPC

## ISC Scheme
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : ISC Scheme & EI | [9 empty] | Month : June 2024
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of Contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Improvement of Tuipuibari - W.Kawnpui Road and ISC (0.00-9.00 Kmp) | 4870 | Mamit Division | 20.3.20 | 20.3.22 | 87.35% | 3978.3 | 11.65% |  | 99% | 3978.3 |  | EPC

## CRF
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : CRF | [9 empty] | Month : June 2024
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Two Lane from Sihhmui-Ramrikawn Road (Stage-I) | 8000 | Aizawl Road North Division | 1.10.18 | 1.10.20 | 93% | 4875.07 |  |  | 93% | 4875.07 | In progress | Item rate
2 | Widening and Improvement of Road from Durtlang Leitan to Sihphir Section (Length 10.25 Km) of Aizawl - Durtlang - Lungdai -Kawnpui Road in the State of Mizoram | 4657 | Aizawl Road North Division | 14.7.23 | 31.1.25 | 55% | 1000 |  |  | 55% | 1000
3 | Construction of BUG Bridge over Tlawng on Aizawl-Reiek-W.Lungdar Road at 14.800 Kmp | 757.56 | Aizawl Road South Division | 10.10.18 | 28.2.23 | 98% | 488.56 |  | 115.01 | 98% | 603.57 | Work in progress | EPC Mode
4 | Construction of Muallungthu-Lungphun Road | 5996 | Hmuifang Division | 23.11.17 | 23.11.19 | 33.39% | 2240 | - |  | 33.39% | 2240 | Work in progress | Item rate contract
5 | Widening to single lane with geometric imprivement & Upgradation of Chhiahtlang-Lamchhip Road | 6668.18 | Hmuifang Division | 23.6.17 | 23.06.19 | 100% | 6283.78 | - |  | 100% | 6282.93 | Completed | Item rate contract
6 | Construction of Chakkhei to Siasi Road (Permanent Work) (0.00-20.00 Kmp) | 1216.88 | Saiha Division | 8.7.19 | 27.05.24 | 98.99% | 856.56 | 0.08% |  | 99.07% | 856.56 | Work in progress | Item rate contract
7 | Construction of Chakkhei to Siasi Road (FC&Pavement Work) (0.00-20.00 Kmp) | 3617.05 | Saiha Division | 8.7.19 | 23.02.24 | 98.81% | 2838.84 |  |  | 98.81% | 2838.84 | Work in progress | Item rate contract

## NESIDS
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : NESIDS | [9 empty] | Month : June 2024
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of 2 Residential Hostel at ZMC (Boys) | 1000 | Project Division-II | 14.10.21 | 29.10.23 | 100% | 1000 |  |  | 100% | 1000 | Work Completed | EPC
2 | Construction of 2 Residential Hotel at ZMC (Girls) | 1000 | Project Division-II | (O)14.10.21 (R) 15.04.24 | (O)14.10.23 (R)15.04.24 | 93% | 865.1 | 1% | 67.18 | 94% | 932.28 | Work in progress EOT under process | EPC
3 | Construction of 100 Bedded Distict Hospital at Kolasib | 2200 | Project Division-II | 23.09.22 | 23.09.24 | 51% | 598.83 | 2% |  | 53% | 598.83 | Work in progress | EPC
4 | Construction of State Resource Centre for HIV/AIDS at Aizawl | 400 | Project Division-II | 22.09.22 | 22.09.24 | 58% | 134.2 | 7% |  | 65% | 134.2 | Work in progress | EPC
5 | Improvement /Upgradation of Operational/Non-operational facilities of Lengpui Aiport (elevated Road with connected components of Terminal Building) | 1959 | Project Division-III | 30.9.21 | 12.6.24 | 94.9% | 1450.31 | 0.1% |  | 95% | 1450.31 | Work in progress | Turnkey
6 | Improvement /Upgradation of Operational/Non-operational facilities of Lengpui Aiport (elevated Road with connected components of Terminal Building) | 1775 | Project Division-III | 11.4.24 | 1.10.27 |  |  | 1% |  | 1% |  | Work just started | Turnkey
7 | Improvement /Upgradation of Operational/Non-operational facilities of Lengpui Aiport (elevated Road with connected components of Terminal Building) | 1696 | Project Division-III | 10.6.24 | 8.10.27 |  |  | 0.5% |  | 0.5% |  | Work just started | Turnkey
8 | Improvement & Upgradation of Lawngtlai-Tuipui ferry Road under NESIDS | 2897.8 | Lawngtlai Division | 08.08.19 | 30.06.23 | 100% | 2666.68 |  |  | 100% | 2666.68 | Phy. Completed | Item rate
9 | Improvement & Upgradation of Daido to Vawngkawt-Buangpuilawn (manipur) Road (Daido to Vawngkawt: Mizoram Area, Length 5.639 kms) | 3319 | Saitual Division | 14.03.24 | 14.09.25 | 19.54% |  | 9.05% |  | 28.59% |  |  | EPC

## SCA
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : S.C.A | [9 empty] | Month : June 2024
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummutive Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of Contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Improvement of MPSC Office Building at MINECO | 394 | Project Division-I | 29.10.22 | 29.10.24 | 100% | 317.55 |  | 53.45 | 100% | 371 |  | EPC
2 | Construction of DIG (NR) Office Building at PHQ Complex, Aizawl | 320 | Project Division-I | 21.7.22 | 21.1.25 | 100% | 180.36 |  |  | 100% | 180.36 |  | EPC
3 | Construction of Govt.Staff Qtrs.(Block-B) at DIET Complex | 386.6 | Project Division-I | 28.8.22 | 28.8.24 | 83% | 155.84 | 5% |  | 88% | 155.84 |  | EPC
4 | Strenthening of Infrastructure in 3 newly created Districts (Const.of DC Office Saitual) | 1000 | Project Division-III | 20.1.21 | 20.4.24 | 99.5% | 975.63 |  |  | 99.5% | 975.63 | Work completed | PWD Form-8
5 | Construction of District Research Officers Quarters and Staff Cum Chowkider Quarters at Keifang, Saitual District | 70 | Project Division-III | 9.9.22 | 24.2.24 | 92% | 25 | 2% |  | 94% | 25 | Work in progress | PWD Form-8
6 | Improvement & Upgradation of Operational/Non Operational facilities of Lengpui (Sh: Renovation of Terminal building) | 2124 | Project Division-III | 10.3.21 | 6.5.24 | 97.5% | 1254.05 | 0.2% | - | 97.7% | 1254.05 | Work in progress | PWD Form-8
7 | Construction of 100 Bedded Dist Hospital at Saitual (Sh: Construction of OPD building at District Hospital, Saitual | 200 | Project Division-III | 13.10.23 | 13.10.25 | 23% | 14.15 | 2% |  | 25% | 14.15 | Work in progress | PWD Form-8

## SARDPNE
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : SARDP-NE | [9 empty] | Month : June 2024
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Widening to two laning/Re-alignment and geometric improvement from km.11+000 to 114+618 of NH-44 'A' in the state of Mizoram | 1,10,988.00 | NHD-I | 17.3.11 | 31.12.22 | 96.04% | 102146 |  |  | 96.04% | 102146 | Contract was terminated on 24.08.2023 Tender be re-floated as soon as sanction of balance work estimate is obtained | Item rate contract
2 | Construction of a new 2-lane Highway from km 0/00kmp to 38/00 in Mizoram to support Kaladan Multi Modal Transit Transport project in Phase-'A of SARDP-NE package-I | 43465 | Multi Modal Project Division |  |  | 100% | 42978 |  |  | 100% | 42978 | 1. Financial progress is upto RA 145 2. Work completed on 22.6.2023
3 | Construction of a new 2-lane Highway from km 38.00 to km 71.00 in Mizoram to support Kaladan Multi Modal Transit Transport project in Phase-'A of SARDP-NE package-II | 32224 | Multi Modal Project Division |  |  | 100% | 30977 |  | - | 100% | 30977 | 1. Financial progress is based on bill submitted by the Contractor after verifying at the spot by the Department. 2. Work completed on 30.04.22
4 | Construction of a new 2-lane Highway from km 71.00 to km 99.83 in Mizoram to support Kaladan Multi Modal Transit Transport project in Phase-'A of SARDP-NE package-III | 37459 | Multi Modal Project Division |  |  | 100% | 37689 |  |  | 100% | 37689 | 1. Financial progress is based on the figure shown in the MoP of the latest bill appproved by Regional Officer, MoRTH Guwahati i.e RA-145 (Retention Money Bill) 2. Work completed on 23.06.23

## MAJOR
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : Major & Minor Works and Deposit woks 8443-108, D-III | [9 empty] | Month : June 2024
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | I/E to Additional Court Room with Chamber at Kolasib | 4.26 | Electrical Division Aizawl |  |  | 100% | 4.26 | - | - | 100% | 4.26 | I/E Completed, S/C being process
2 | I/E to Arrival & Departure Passenger Lobby at Lengpui Airport | 25.27 | Electrical Division Aizawl | 19.12.20 |  | 90% | 25.27 | - | - | 90% | 25.27 | Room for installation Panel Board not yet installed
3 | SITC 13 Passenger Lift-2 nos, 2-opening, 900mm centre opening Stainless Steel cable with Automatic Rescue Device (ARD) for Hydraulic Lift with Minor Civil Works at Lengpui Airport Mizoram | 77.91 | Electrical Division Aizawl | 08.09.21 | 01.04.24 | 50% | 38.33 |  |  | 50% | 38.33 | On going works
4 | Street Light Parking light at Lengpui Airport | 37.32 | Electrical Division Aizawl | 06.07.22 |  | 95% | 37.31 |  | - | 95% | 37.31 | On going works
5 | Laying of XLPE Cable from Power House to Glide Path control at Lengpui Airport, Mizoram | 39.53 | Electrical Division Aizawl | 09.05.23 | 04.08.23 | 100% | 39.52 |  |  | 100% | 39.52 | Completed
6 | Estimate for I/E of Energy Meter for Terminal Building at Lengpui Airport | 7.99 | Electrical Division Aizawl | 06.07.22 |  | 90% | 7.99 |  | - | 90% | 7.99 | On going works
7 | I/E & Fire fighting to Car Parking at Dist.Court MINECO | 32.48 | Electrical Division Aizawl |  |  | 60% | 16.99 | - | - | 60% | 16.99 | On going works
8 | Addl.Estimate for SITC of MRV/VRF Centralizes Air Conditioner Airport Fist Floor Departure Hall, Mizoram | 247.74 | Electrical Division Aizawl | 12.03.22 | 04.03.24 | 70% | 220.1 | 10% | - | 80% | 220.1 | On going works
9 | SITC of EPABX System for Lengpui Airport Terminal Building | 24.64 | Electrical Division Aizawl | 06.07.22 | 29.06.24 | 80% | 19.46 |  |  | 80% | 19.46 | On going works
10 | SITC of PA System at Lengpui Airport Terminal Building | 36.36 | Electrical Division Aizawl | 06.07.22 | 29.06.24 | 80% | 28.82 |  |  | 80% | 28.82 | On going works
11 | Supply & Installation of Integrated Fire Hydrant System (Wise Riser) & SiTC of Alarm System for Lengpui Airport Terminal building | 119.96 | Electrical Division Aizawl | 06.07.22 | 29.06.24 | 80% | 94.72 |  |  | 80% | 94.72 | On going works
12 | SITC of AVTRON IP Surveillance System for Lengpui Airport Terminal Building | 94.76 | Electrical Division Aizawl | 06.07.22 | 29.06.24 | 80% | 67.61 |  |  | 80% | 67.61 | Control/CCTV Room was not yet ready
13 | SITC of LANE SETUP at Lengpui Airport Terminal Building | 20.05 | Electrical Division Aizawl | 06.07.22 | 29.06.24 | 80% | 15.76 |  |  | 80% | 15.76 | On going works
14 | Estimate for XLPE Cable for Lengpui Airport | 27.23 | Electrical Division Aizawl |  |  | 100% | 27.23 |  | - | 100% | 27.23 | Completed
15 | Additional Estimate fo SITC of Air Conditioner Departer Pssenger Lobby at Lengpui Airport | 24.67 | Electrical Division Aizawl |  |  | 100% | 24.67 | - | - | 100% | 24.67 | Completed
16 | I/E works for Const. of MBSE Office | 57.37 | Electrical Division Aizawl |  |  | 80% | 57.37 | 10% |  | 90% | 57.37 | On going works
17 | I/E for DC Office at Saitual | 70 | Electrical Division Aizawl |  |  | 100% | 70 | - | - | 100% | 70 | I/E completed, S/C left due to non installation of required transformer
18 | I/E to High Court Parking at MINECO | 109.5 | Electrical Division Aizawl | 07.03.23 | 20.12.24 | 40% | 65.73 | - | - | 40% | 65.73 | On going works
19 | I/E to PHC at Bungzung | 18.18 | Electrical Division Aizawl |  |  | 100% | 18.18 |  | - | 100% | 18.18 | I/E Completed, S/C left due to non installation of required transformer
20 | Const.of DIG(NR) Office at Aizawl under SCA during 2022-23 (Sh:I/E) | 43.84 | Electrical Division Aizawl | 23.01.23 | 10.05.24 | 90% | 17.29 | 10% | 23.98 | 80% | 41.27 | Completed
| Sh: Computer Conduiting |  |  |  | 10.05.24 | [6 empty] | On going works
| Sh: Telephone Conduiting |  |  |  | 10.05.24 | [6 empty] | On going works
| Sh: Fire Hydrant (Wet Riser) |  |  | 23.01.23 | 10.05.24 | 40% |  | 60% |  | 100% |  | Completed
| Sh: Automatic Fire Alarm System |  |  | 23.01.23 | 10.05.24 | 40% |  | 60% |  | 100% |  | Completed
21 | Construction of DC Office at Khawzawl (Sh: Lift & I/E) | 105.73 | Electrical Division Aizawl |  |  | 100% | 105.68 |  |  | 100% | 105.68 | Completed
22 | Impvt/Revamping of Lengpui Airport runway Lighting -Isolation Bay-DGCA Observation Reg. | 347.05 | Electrical Division Aizawl |  |  | 100% | 218.94 |  |  | 100% | 218.94 | Completed
23 | Impvt/Revamping of Lengpui Airport runway Lighting -Isolation Bay-DGCA Observation Reg. | 10.91 | Electrical Division Aizawl |  |  | 100% |  |  |  | 100% |  | Completed
24 | Impvt/Revamping of Lengpui Airport runway Lighting -Isolation Bay-DGCA Observation Reg. | 14.6 | Electrical Division Aizawl |  |  | 100% |  |  |  | 100% |  | Completed
25 | Renovation/Revamping of Internal Electrification to Polytechnic at Thingdawl (Sh: Automobile Engineering Block) | 18.65 | Electrical Division Aizawl | 04.10.23 | 18.11.23 | 90% |  |  |  | 90% |  | I/E completed, Service connection left
26 | Renovation/Revamping of Internal Electrification to Polytechnic at Thingdawl (Sh: Textile Technology Block) | 18.71 | Electrical Division Aizawl | 04.10.23 | 18.11.23 | 90% |  |  | 5.77 | 90% | 5.77 | I/E completed, Service connection left
27 | Renovation/Revamping of Internal Electrification to Polytechnic at Thingdawl (Sh: Administrative Block) | 9.52 | Electrical Division Aizawl | 04.10.23 | 18.11.23 | 90% |  |  |  | 90% |  | I/E completed, Service connection left
28 | Renovation/Revamping of Internal Electrification to Polytechnic at Thingdawl (Sh: Common facility Block) | 11.05 | Electrical Division Aizawl | 04.10.23 | 18.11.23 | 90% |  |  |  | 90% |  | I/E completed, Service connection left
29 | Renovation of I/E to BSUP 17 block @ 16 rooms at Durtlang | 40 | Electrical Division Aizawl |  |  | 100% |  |  | 40 | 100% | 4 | Completed
30 | SITC of 5 passenger Lift at E-in-C Office Building | 44.96 | Electrical Division Aizawl | 14.11.23 | 28.03.24 | 100% |  |  | 44.96 | 100% | 44.96 | Completed
31 | SITC of 5 passenger Lift for Fast Track Court Building at Kolasib | 3.9 | Electrical Division Aizawl | 26.12.23 | 20.06.24 | 20% |  |  |  | 20% |  | On going works
32 | SITC of 13 passenger Lift for Fast Track Court Building at Kolasib | 49.85 | Electrical Division Aizawl | 26.12.23 | 20.06.24 | 20% |  |  |  | 20% |  | Completed
33 | I/E Provision for Main Gate at MINECO | 0.76 | Electrical Division Aizawl | 22.04.24 | 30.04.24 | 100% |  |  | 0.76 | 100% | 0.76 | Completed
34 | Additional I/E to Mizoram Public Service Commission (MPSC) Building Aizawl | 7.22 | Electrical Division Aizawl | 22.04.25 | 30.04.25 | 80% |  | 20% |  | 100% |  | Completed

## SASCE
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : SASCE | [9 empty] | Month : June 2024
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummutive Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Multi Utility Centre at Zemabawk, Aizawl, Mizoram. | 800 | Project Division-IV | 19.12.22 | 16.8.25 | 43.2% | 165.46 | 2.8% | 81.63 | 46% | 247.09 | Work in progress. | Item Rate
2 | Construction of Solid Waste Management Centre at Hualngohmun, Mizoram (Phase-I) | 1664 | Project Division-IV | 07.04.23 | 07.04.25 | 12.15% | 73.07 | 7.85% |  | 20% | 73.07 | Work in progress. | Item Rate
3 | Const.of Road from IR Camp to Ramri Lui, Zophai, Bairabi (Sh: Group A-Formation Cutting, Permanent works and side drain) | 498 | NHD-III | 27.07.23 | 27.01.24 | 100% | 240.23 |  |  | 100% | 240.23 | Completed | Item Rate
| Group B-Pavement. Traffic Sign and Road Safety |  | NHD-III | 11.09.23 | 11.03.24 | [7 empty] | Item Rate

## SPF
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : State Plan Fund | [9 empty] | Month : June 2024
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummutive Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of Contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | 4202 Co-On Education etc. a) I/E to boys & girls Hostel for Govt.Saiha College bldg at Siaha | 2 | Electrical Division, Lunglei |  |  | 40% | - | - | - | 40% | - | Materials received, building not yet ready
2 | 8443-108-PWD Deposit-III a) I/E to DC Bungalow (Type-IV) at Siaha | 8.2 | Electrical Division, Lunglei |  |  | 40% | - |  | - | 40% | - | Materials received, building not yet ready
| b) I/E to Safe House at Tlabung | 8 | Electrical Division, Lunglei | [8 empty] | Material awaited
| c) I/E to PHC Building at Lungsen | 19 | Electrical Division, Lunglei |  |  |  |  | 95% |  | 95% |  | I/E completed S/C left
| d) I/E to Judicial Quarter Grade-I at Lawngtlai | 10 | Electrical Division, Lunglei |  |  |  |  | 40% |  | 40% |  | Material received
| e) I/E to Judicial Quarter Type-I & Type-II at Lawngtlai | 13 | Electrical Division, Lunglei |  |  |  |  | 40% |  | 40% |  | Material received
| f) I/E to Taxation Staff Quarter Type-III 4 units at Lunglei | 17 | Electrical Division, Lunglei | [8 empty] | Material awaited
| g) I/E to Taxation Officers Quarter Type-IV 2 Units at Lunglei | 9 | Electrical Division, Lunglei | [8 empty] | Material awaited
3 | SITC of 8 (Eight) Passenger Auto Elevator for District Court Building at Siaha | 42 | Electrical Division, Lunglei | 14.12.21 | 18.5.24 | 100% |  |  | 41.7 | 100% | 41.7 | Completed | Contractor

## Under L & J
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : Under L & J | [9 empty] | Month : June 2024
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of District Court Complex at Vengsang, Champhai | 4915.35 | Project Division-III | 17.10.23 | 17.10.26 | 20% | 241.5 | 3% | 72.14 | 23% | 313.64 | Work in progress | PWD Form-8

## Aspirational
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
| Source of funding : Aspirational District Programme, Window-I | [8 empty] | Month : June 2024
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Link Road from W.Mualthuam to Sothapa Road (Length=7.300Kms) | 200 | Kawrthah Division | 15.10.23 | 14.4.24 | 99% | 33.62 |  | 66.38 | 99% | 100 | Road formation cutting completed | Contract after call of Restricted Tender

## Ministry
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : Ministry of Tribal Affairs | [9 empty] | Month : June 2024
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummutive Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of Contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Auditorium at Pukpui Lunglei | 523 | Lunglei Building Project Division | 16.9.23 | 16.01.25 | 5% |  |  |  | 5% |  | Work not yet started till date due to objection of site from Education Dept. Relocation of Site for Construction is being awaited from Client Dept. | Retsricted Tender

## SASCI
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
| Source of funding : SPECIAL ASSISTANT TO STATE FOR CAPITAL INVESTMENT | [7 empty] | Month : June, 2024
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of Contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
LUNGLEI BUILDING PROJECT DIVISION : 2022-2023
1 | Construction of Circuit House at Hnahthial 'A' | 304 | Lunglei Building Project Division | 13.04.23 | 13.10.24 | 40% |  | 6% |  | 46% |  | Work in progress | Restricted Tender
2 | Construction of Circuit House at Hnahthial 'B' | 200 | Lunglei Building Project Division | 13.04.23 | 13.10.24 | [6 empty] | Not yet started | Restricted Tender
3 | (a) Const. of Laboratory Building at Civil Hospital Lunglei (Ground floor0 | 192 | Lunglei Building Project Division | 28.10.21 | 28.10.22 | 100% | 192.98 |  |  | 100% | 192.98 | Completed | Restricted Tender
4 | (b) Const. of Laboratory Building at Civil Hospital, Lunglei (1st & 2nd floor) Supplementary Works | 396 | Lunglei Building Project Division | 28.10.22 | 28.04.24 | 90% | 290.45 | 10% |  | 100% | 290.45 | Work in progress | Restricted Tender
5 | Construction of Sangau SDO© Office building at Sangau | 77 | Lunglei Building Project Division | 20.03.23 | 20.03.24 | 100% | 70.19 |  | 0.11 | 100% | 70.3 | Phy.Completed | Spot Quotation
6 | Construction of SDO© Quarter at Sangau | 80 | Lunglei Building Project Division | 20.03.23 | 20.03.24 | 100% | 72.81 |  | 0.67 | 100% | 73.48 | Phy.Completed | Spot Quotation
7 | Construction of Staff Quarter(2 Units) at Sangau | 50.45 | Lunglei Building Project Division | 20.03.23 | 20.03.24 | 100% | 45.87 |  | 0.12 | 100% | 45.99 | Phy.Completed | Spot Quotation
8 | Construction of Volleyball Court at Gulsil Chawngte 'L' | 20 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 19.44 |  | 0.56 | 100% | 20 | Phy.Completed | Spot Quotation
9 | Construction of Meisatla Futsal Ground at Siaha | 34.79 | Lunglei Building Project Division | 20.03.23 | 20.09.23 | 49% | 20.75 |  | 1.09 | 49% | 21.84 | Work in progress | Spot Quotation
10 | Construction of Futsal Playground at Gov't Higher secondary School at Siaha | 34.79 | Lunglei Building Project Division | 20.03.23 | 20.09.23 | 100% | 31.3 |  | 3.49 | 100% | 34.79 | Phy.Completed | Spot Quotation
11 | Construction of New Football ground at Ramlaitui | 20 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 20 |  |  | 100% | 20 | Completed | Spot Quotation
12 | Construction of New Football Ground at Haulawng | 20 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 19.75 |  | 0.25 | 100% | 20 | Completed | Spot Quotation
13 | Construction of New Football Ground at Mualthuam 'N' | 20 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 19.69 |  | 0.31 | 100% | 20 | Completed | Spot Quotation
14 | Construction of New Football Ground at Mualthuam 'N' (on going) | 10 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 9.81 |  | 0.19 | 100% | 10 | Completed | Spot Quotation
15 | Construction of New Football Ground at Haulawng ( on going ) | 10 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 9.81 |  | 0.19 | 100% | 10 | Completed | Spot Quotation
16 | Construction of New Football Ground at Rawpui | 15 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 14.73 |  | 0.27 | 100% | 15 | Completed | Spot Quotation
17 | Lowering of Siahatla Field, Siaha | 35.97 | Lunglei Building Project Division | 20.03.23 | 20.03.24 | 100% | 34.91 |  | 1.06 | 100% | 35.97 | Completed | Spot Quotation
18 | Const. of Playground Chawngte 'L' | 40 | Lunglei Building Project Division | 20.03.23 | 20.03.24 | 100% | 39.51 |  | 0.49 | 100% | 40 | Completed | Spot Quotation
19 | Construction of Community Hall at Pukpui | 80 | Lunglei Building Project Division | 20.03.23 | 20.03.24 | 98% | 26.66 | 2% |  | 100% | 26.66 | Work in progress | Spot Quotation
20 | Construction of New Badminton Hall at Chhipphir | 20 | Lunglei Building Project Division | 20.03.23 | 20.09.23 | 100% | 19.99 |  | 0.01 | 100% | 20 | Completed | Spot Quotation
21 | Renovation of Community Hall at Farm Veng | 10 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 9.99 |  | 0.01 | 100% | 10 | Completed | Spot Quotation
22 | Renovation of Community Hall at Zobawk 'S' | 10 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 9.57 |  |  | 100% | 9.57 | Completed | Spot Quotation
23 | Renovation of Sport recreation House ( TT Hall) at Zobawk 'N' at Zobawk Bazar | 10 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 9.55 |  | 0.02 | 100% | 9.57 | Completed | Spot Quotation
24 | Painting & Electrification of Zobawk 'N' Hall | 12 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 10.77 |  | 0.01 | 100% | 10.78 | Phy.Completed | Spot Quotation
25 | Land development & Earthwork for Community Hall at Ralvawng | 10 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 9.99 |  | 0.01 | 100% | 10 | Completed | Spot Quotation
26 | Renovation of Community Hall at Leite | 5 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 5 |  |  | 100% | 5 | Completed | Spot Quotation
27 | Renovation of Public NGO's House at Leite | 5 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 5 |  |  | 100% | 5 | Completed | Spot Quotation
28 | Renovation of Community Hall at Rotlang 'E' | 5 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 4.95 |  | 0.05 | 100% | 5 | Completed | Spot Quotation
29 | Completion of Community Hall at Dawn | 8 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 7.99 |  | 0.01 | 100% | 8 | Completed | Spot Quotation
30 | Construction of Community Hall at Zehtet | 30 | Lunglei Building Project Division | 20.03.23 | 20.09.23 | 100% | 29.98 |  | 0.02 | 100% | 30 | Completed | Spot Quotation
31 | Construction of Community Hall at Lungrang 'S' | 40 | Lunglei Building Project Division | 20.03.23 | 20.03.24 | 50% | 1.1 |  | 14.15 | 50% | 15.25 | Work in progress | Spot Quotation
32 | Construction of Community Hall | 12 | Lunglei Building Project Division | 20.03.23 | 20.09.23 | 100% | 11.99 |  | 0.01 | 100% | 12 | Completed | Spot Quotation
33 | Construction of Community Hall at Chhumkhum | 27.47 | Lunglei Building Project Division | 20.03.23 | 20.09.23 | 100% | 27.46 |  | 0.01 | 100% | 27.47 | Completed | Spot Quotation
34 | Construction of Community Hall at New Sachan | 27.47 | Lunglei Building Project Division | 20.03.23 | 20.09.23 | 100% | 27.46 |  |  | 100% | 27.46 | Completed | Spot Quotation
35 | Construction of Public Recreation House at Chanmari, Lunglei | 10 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 9.99 |  | 0.01 | 100% | 10 | Completed | Spot Quotation
36 | Construction of Old Aged Home cum Library House at Community Hall at Ramthar, Lunglei | 15 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 14.99 |  | 0.01 | 100% | 15 | Completed | Spot Quotation
37 | Construction of Women Recreation House or Cemetary House at Electric veng Lunglei (Women recreation house) | 10 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 9.99 |  | 0.01 | 100% | 10 | Completed | Spot Quotation
38 | Construction of NGO's House cum Library Room at Zobawk 'S' Vengthar | 10 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 9.99 |  | 0.01 | 100% | 10 | Completed | Spot Quotation
39 | Completion of NGO's Recreation House at Lungpuizawl | 5 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 5 |  |  | 100% | 5 | Completed | Spot Quotation
40 | Renovation of Women Recreation House at Lower Ramthar, Lunglei | 5 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 5 |  |  | 100% | 5 | Completed | Spot Quotation
41 | Construction of Waiting Shed & Godown of Animal Feed Building at dawn | 5 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 4.99 |  | 0.01 | 100% | 5 | Completed | Spot Quotation
42 | Construction of Women Recreation House at Upper Ramthar, Lunglei | 15 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 14.99 |  | 0.01 | 100% | 15 | Completed | Spot Quotation
43 | Construction of NGO's Recreation house at Farm Veng, lunglei | 10 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 9.96 |  | 0.04 | 100% | 10 | Completed | Spot Quotation
44 | Construction of Clinic Center Building at Bungtlang W | 5 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 4.99 |  | 0.01 | 100% | 5 | Completed | Spot Quotation
45 | Rahsiveng Market Shed | 52 | Lunglei Building Project Division | 20.03.23 | 20.09.23 | 100% | 48.58 |  | 3.42 | 100% | 52 | Completed | Spot Quotation
46 | Constructuion of Toilet and Water Pint at Kawmzawl Helipad, aizawl to lunglei Helicopter service Station | 15 | Lunglei Building Project Division | 20.03.23 | 20.09.23 | 100% | 14.99 |  | 0.01 | 100% | 15 | Completed | Spot Quotation
47 | Construction of Cemetary House at Chanmari, Lunglei | 15 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 14.99 |  | 0.01 | 100% | 15 | Completed | Spot Quotation
48 | Construction of Fencing & Cement Flooring at YMA hall courtyard at Electric Veng, Lunglei | 15 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 14.99 |  | 0.01 | 100% | 15 | Completed | Spot Quotation
49 | Construction of Public Store house and Urinal Shed at Electric Veng, Lunglei | 15 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 14.99 |  | 0.01 | 100% | 15 | Completed | Spot Quotation
50 | Construction of Waiting Shed near PWD Turning Point | 10 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 9.99 |  | 0.01 | 100% | 10 | Completed | Spot Quotation
51 | Estimate for Construction of Cemetary House at College Veng, lunglei | 5 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 5 |  |  | 100% | 5 | Completed | Spot Quotation
52 | Construction of Cemetary House at Bazar Veng Thlanmual No. 3 | 5 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 4.99 |  | 0.01 | 100% | 5 | Completed | Spot Quotation
53 | Construction of Boat Waiting shed at New Sachan | 0.69 | Lunglei Building Project Division | 20.03.23 | 20.05.23 | 100% | 0.69 |  |  | 100% | 0.69 | Completed | Spot Quotation
54 | Construction of Waiting near border Fencing inside India at Terabonia | 1.08 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 1.07 |  | 0.01 | 100% | 1.08 | Phy.Completed | Spot Quotation
55 | Construction of Boat Waiting Shed at Tuikawi | 0.69 | Lunglei Building Project Division | 20.03.23 | 20.05.23 | 100% | 0.69 |  |  | 100% | 0.69 | Completed | Spot Quotation
56 | Construction of Boat Waiting Shed at Sumasuri | 0.69 | Lunglei Building Project Division | 20.03.23 | 20.05.23 | 100% | 0.69 |  |  | 100% | 0.69 | Completed | Spot Quotation
57 | Construction of Boat waiting Shed at Old Sachan | 0.69 | Lunglei Building Project Division | 20.03.23 | 20.05.23 | 100% | 0.67 |  | 0.02 | 100% | 0.69 | Completed | Spot Quotation
58 | Construction of Waiting shed at Bungkawn, Lungchem | 0.69 | Lunglei Building Project Division | 20.03.23 | 20.05.23 | 100% | 0.66 |  | 0.03 | 100% | 0.69 | Completed | Spot Quotation
59 | Construction of Public Urinal near Vanlalhriara's House at Changpui | 0.73 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 0.7 |  | 0.03 | 100% | 0.73 | Completed | Spot Quotation
60 | Construction of Public Urinal near Hrangthuama's House at Changpui | 0.73 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 0.7 |  | 0.03 | 100% | 0.73 | Completed | Spot Quotation
61 | Construction of Urinal near Vanlalpianga's House at Dengsur | 0.73 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 0.7 |  | 0.03 | 100% | 0.73 | Completed | Spot Quotation
62 | Construction of Urinal near Thanthianga's House at Dengsur | 0.73 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 0.7 |  | 0.03 | 100% | 0.73 | Completed | Spot Quotation
63 | Construction of Urinal near Community Hall at Dengsur | 0.73 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 0.7 |  | 0.03 | 100% | 0.73 | Completed | Spot Quotation
64 | construction of Waiting Shed at Mangkhan Kawn, Dengsur | 1.08 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 1.04 |  | 0.04 | 100% | 1.08 | Phy.Completed | Spot Quotation
65 | Construction of Waiting shed at sabual & Dengsur Boundary. | 1.08 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 1.04 |  | 0.04 | 100% | 1.08 | Phy.Completed | Spot Quotation
66 | Construction of Waiting Shed near K.Vanlalruata's House at S.Khawlek | 1.08 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 1.04 |  | 0.04 | 100% | 1.08 | Completed | Spot Quotation
67 | Construction of Public Urinal near Information Centre Building at S.Khawlek | 0.73 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 0.7 |  | 0.03 | 100% | 0.73 | Completed | Spot Quotation
68 | Construction of Waiting shed at Dampui | 1.08 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 1.04 |  | 0.04 | 100% | 1.08 | Completed | Spot Quotation
69 | Construction of Cemetary House at Thenhlum | 0.76 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 0.73 |  | 0.03 | 100% | 0.76 | Completed | Spot Quotation
70 | Construction of Waiting Shed at Tawngtaina Hmun Zawlpui | 1.08 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 1.04 |  | 0.04 | 100% | 1.08 | Completed | Spot Quotation
71 | Construction of Public Urinal at Tawngtaina hmun at Zawlpui | 0.73 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 0.7 |  | 0.03 | 100% | 0.73 | Completed | Spot Quotation
72 | Construction of Bus Waiting Shed near Thantluanga's House at Belthei | 0.88 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 0.84 |  | 0.04 | 100% | 0.88 | Completed | Spot Quotation
73 | Construction of Waiting Shed at Tuisenchhuah | 1.08 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 1.04 |  | 0.04 | 100% | 1.08 | Phy.Completed | Spot Quotation
74 | Construction of Cemetary House at Rangte | 0.76 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 0.73 |  | 0.03 | 100% | 0.76 | Completed | Spot Quotation
75 | Stainless Steel Railling with Checker Tiles | 6 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 5.82 |  | 0.18 | 100% | 6 | Completed | Spot Quotation
76 | River view & Resting shed. ( Tlabung) | 9.5 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 9.36 |  | 0.14 | 100% | 9.5 | Completed | Spot Quotation
77 | Urinal Building with Side Drain Cover (Tlabung) | 5 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 4.86 |  | 0.14 | 100% | 5 | Completed | Spot Quotation
78 | Construction of Bazar Shed at Tuichawng | 5 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 4.99 |  | 0.01 | 100% | 5 | Completed | Spot Quotation
79 | Construction of MHIP Building at Bunghmun | 17.71 | Lunglei Building Project Division | 20.03.23 | 20.09.23 | 100% | 17.7 |  | 0.01 | 100% | 17.71 | Completed | Spot Quotation
80 | Construction of Anganwadi Centre at Zodin | 4.5 | Lunglei Building Project Division | 20.03.23 | 20.06.23 | 100% | 4.49 |  | 0.01 | 100% | 4.5 | Completed | Spot Quotation
81 | Construction of Anganwadi Centre at Mauzam | 4.02 | Lunglei Building Project Division | 20.03.23 | 20.09.23 | 100% | 4.01 |  | 0.01 | 100% | 4.02 | Completed | Spot Quotation
82 | Construction of Anganwadi Centre at Tuisenchhuah | 9 | Lunglei Building Project Division | 20.03.23 | 20.09.23 | 100% | 8.99 |  | 0.01 | 100% | 9 | Completed | Spot Quotation
83 | Construction of MUP Building at Thenhlum | 9 | Lunglei Building Project Division | 20.03.23 | 20.09.23 | 100% | 9 |  |  | 100% | 9 | Completed | Spot Quotation
A. Construction of Government Building at Hnahthial, PWD EE Quarters, Circuit House & DC office under SASCI 2023-2024
84 | Const. of PWD EE Quarters at Hnahthial. | 150 | Lunglei Building Project Division | 23.03.23 | 23.03.26 | [6 empty] | Work not yet started | Spot Quotation
85 | Hnahthial Circuit House. | 200 | Lunglei Building Project Division | 23.03.23 | 23.03.26 | 40% |  | 7% |  | 47% |  | Work in progress | Spot Quotation
B. Construction of Community Hall at Siasi, Phurai, Tawngkawlong, Tipa B, Meisavaih, Amotlah.
86 | Const. and Completion of MTP(H) Office. | 10 | Lunglei Building Project Division | 23.03.24 | 23.07.25 | 70% |  | 30% | 0.13 | 100% | 0.13 | Phy.Completed | Spot Quotation
87 | Const. of MTP Information Office | 15 | Lunglei Building Project Division | 23.03.24 | 23.07.25 | 60% |  | 20% |  | 80% |  | Work in progress | Spot Quotation
88 | Const. of Bazar Shed at New Siaha East-II | 17 | Lunglei Building Project Division | 23.03.24 | 23.07.25 | 60% |  | 20% | 0.48 | 80% | 0.48 | Work in progress | Spot Quotation
89 | Continuation of MYA Hall at New Siaha East-I | 20 | Lunglei Building Project Division | 23.03.24 | 23.07.25 | 100% |  |  |  | 100% |  | Phy.Completed | Spot Quotation
90 | Const. of MTP Hall and Retaining Wall at Amotlah. | 20 | Lunglei Building Project Division | 23.03.24 | 23.07.25 | 55% |  | 20% |  | 75% |  | Work in progress | Spot Quotation
91 | Const. of Model Middle School Ground and Retaining Wall at New Siaha West-I | 15 | Lunglei Building Project Division | 23.03.24 | 23.07.25 | 100% |  |  | 13.99 | 100% | 13.99 | Completed | Spot Quotation
92 | Const. of Retaining Wall at Futsal Ground at Tuipui Ferry. | 10 | Lunglei Building Project Division | 23.03.24 | 23.07.25 | 100% |  |  | 9.35 | 100% | 9.35 | Completed | Spot Quotation
C. Construction of Playground with Pavillion at Lungtian, Sangau, Bualpui(NG), Tuichawngtlang, Ngunlingkhua, T.Dumzau.
93 | Renovation of Community Hall Ramhlun Veng, Sangau. | 30 | Lunglei Building Project Division | 23.03.24 | 23.07.25 | 100% |  |  |  | 100% |  | Phy.Completed | Spot Quotation
94 | Const. of Community Hall at Council Veng, Lawngtlai. | 30 | Lunglei Building Project Division | 23.03.24 | 23.07.25 | 30% |  | 20% |  | 50% |  | Work in progress | Spot Quotation
95 | Vertical Extention of Central Young Lai Association Office, Lawngtlai. | 10 | Lunglei Building Project Division | 23.03.24 | 23.07.25 | 30% |  | 20% |  | 50% |  | Work in progress | Spot Quotation
96 | Const. of Futsal Ground at Lungtian-I | 30 | Lunglei Building Project Division | 23.03.24 | 23.07.25 | 90% |  |  |  | 90% |  | Work in progress | Spot Quotation
97 | Const. of Futsal Ground at Bualpui (NG) | 30 | Lunglei Building Project Division | 23.03.24 | 23.07.25 | 90% |  |  |  | 90% |  | Work in progress | Spot Quotation
98 | Const. of Futsal Ground at Sangau. | 30 | Lunglei Building Project Division | 23.03.24 | 23.07.25 | 90% |  |  |  | 90% |  | Work in progress | Spot Quotation
99 | Const. of Volleyball Court at Lungzalhtum. | 10 | Lunglei Building Project Division | 23.03.24 | 23.07.25 | 100% |  |  |  | 100% |  | Phy.Completed | Spot Quotation
D. Construction of Community Hall Cum Market Building at Luangmual, Lunglei.
100 | Const. of DM High School Building (Theiriat) | 35 | Lunglei Building Project Division | 23.03.24 | 23.07.25 | 85% |  | 15% |  | 100% |  | Phy.Completed | Spot Quotation
101 | Const. of Luangmual Market Building, Lunglei | 80 | Lunglei Building Project Division | 23.03.24 | 23.07.25 | 70% |  | 30% | 2.07 | 100% | 2.07 | Phy.Completed | Spot Quotation
102 | Const. of Sairep Community Hall | 20 | Lunglei Building Project Division | 23.03.24 | 23.07.25 | 80% |  | 20% |  | 100% |  | Phy.Completed | Spot Quotation
E. Vertical Extention of Market Building at Kamalanagar.
103 | Vertical Extention of Existing Bazar Building at Kamalanagar-I with Tin Roofing. | 50 | Lunglei Building Project Division | 23.03.24 | 23.07.25 | [6 empty] | Work not yet started | Spot Quotation
104 | Const. of Additional Bazar Building by Demolishing the existing dilapidated building that was constructed under BADP | 50 | Lunglei Building Project Division | 23.03.24 | 23.07.25 | [6 empty] | Work not yet started | Spot Quotation
105 | 2.Const. of Rest House at PWD Complex Bunghmun. | 24.52 | Lunglei Building Project Division | 23.03.24 | 23.07.25 | [6 empty] | Work not yet started | Spot Quotation
F. Construction of Community Hall Cum Health Clinic Center at Kawlhawk, Bungtlang West, South Lungdai and Serte.
106 | Const. of Higher Secondary School Building, Buarpui. | 30 | Lunglei Building Project Division | 23.03.24 | 23.07.25 | 10% |  | 10% |  | 20% |  | Work in progress | Spot Quotation
107 | Const. of Community Hall, Kawlhawk | 30 | Lunglei Building Project Division | 23.03.24 | 23.07.25 | 50% |  | 10% |  | 60% |  | Work in progress | Spot Quotation
108 | Const. of Health Clinic Bungtlang West. | 10 | Lunglei Building Project Division | 23.03.24 | 23.07.25 | 15% |  | 55% |  | 70% |  | Work in progress | Spot Quotation
109 | PWD IB repair, Sertlangpui | 5 | Lunglei Building Project Division | 23.03.24 | 23.07.25 |  |  | 85% |  | 85% |  | Work in progress | Spot Quotation
110 | Const. of Badminton Hall at Chhipphir. | 5 | Lunglei Building Project Division | 23.03.24 | 23.07.25 |  |  | 20% |  | 20% |  | Work in progress | Spot Quotation
111 | Completion of Badminton Hall at Chhipphir | 5 | Lunglei Building Project Division | 23.03.24 | 23.07.25 |  |  | 20% |  | 20% |  | Work in progress | Spot Quotation
112 | Anganwadi Centre-I, Sertlangpui | 5 | Lunglei Building Project Division | 23.03.24 | 23.07.25 |  |  | 85% |  | 85% |  | Work in progress | Spot Quotation
113 | Anganwadi Centre-I New Const. Serte. | 5 | Lunglei Building Project Division | 23.03.24 | 23.07.25 |  |  | 85% |  | 85% |  | Work in progress | Spot Quotation
114 | Health and Wellness Officer Quarter new const. Serte | 5 | Lunglei Building Project Division | 23.03.24 | 23.07.25 | 10% |  | 75% |  | 85% |  | Work in progress | Spot Quotation
115 | Health Clinic Office, South Lungdai | 10 | Lunglei Building Project Division | 23.03.24 | 23.07.25 | 15% |  | 60% |  | 75% |  | Work in progress | Spot Quotation
116 | Const. of Futsal Ground Flooring at Lalveng, Haulawng. | 5 | Lunglei Building Project Division | 23.03.24 | 23.07.25 | [6 empty] | Work not yet started | Spot Quotation
AIZAWL ROAD NORTH DIVISION
2. CONSTRUCTION AND UPGRADATION OF ROAD FROM RAMTHAR - RAMTHAR NORTH - ZARKAWT -SARON, AIZAWL: 2022-23
117 | Construction of Ahimsa to Jail Veng road at Zarkawt. | 77.98 | Aizawl Road North Division | 02.05.23 | 30.11.23 | 50% | 35.79 |  |  | 50% | 35.79 | Work in progress | Spot Quotation
CONSTRUCTION OF CHECK DAM AT THEIHAI LUI, ARMED VENG. 2022-23
118 | Counterfort Retaining Wall at Armed Veng. | 41.22 | Aizawl Road North Division |  |  | 100% |  |  |  | 100% |  | Phy.Completed | Spot Quotation
119 | Toe Walls at Armed Veng Side | 31.44 | Aizawl Road North Division |  |  | 100% |  |  |  | 100% |  | Phy.Completed | Spot Quotation
120 | Retaining Wall at Ramthar Side | 30.21 | Aizawl Road North Division |  |  | 70% |  | 30% |  | 100% |  | Phy.Completed | Spot Quotation
121 | Const. of RCC Link Drain near Rallianzuala Land. | 50.65 | Aizawl Road North Division |  |  | 100% |  |  |  | 100% |  | Phy.Completed | Spot Quotation
SUB-DIVISION - I
CONSTRUCTION OF RCC DRAIN AND RCC PAVEMENT AT CHHINGA VENG AND ELECTRIC VENG. SASCI 2023-2024
122 | Resurfacing of Armed Veng South to Bethlehem Vengthlang Road at Ch : 0.677 - 1.230 Km. | 10.91 | Aizawl Road North Division | 06.12.23 | 15.12.23 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
123 | Re-const. of Collapsed RCC Slab Culvert on Armed Veng South to Bethlehem Vengthlang (Old Zoo Road ) near Rawra chhutna. | 1.2 | Aizawl Road North Division | [8 empty] | Not yet started | Restricted Tender
124 | Balance Work of Const. of RCC Pavement on District Jail to Lower Armed Veng Road (Service Road) | 1.84 | Aizawl Road North Division | 10.04.23 | 11.04.23 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
125 | Const. of New Road from Lalhmingliana Sailo House to Siamphunga Lei at Tuithiang Phase-II | 30.14 | Aizawl Road North Division | 11.03.24 |  | 30% |  | 70% |  | 100% |  | Work in progress | Restricted Tender
126 | Const. of Drainage System at Aizawl Civil Hospital, Dawrpui West Area | 14.52 | Aizawl Road North Division | 18.03.23 |  | 90% |  | 10% |  | 100% |  | Work in progress | Restricted Tender
127 | Const. of Retaining Wall on Dawrpui Thlanmual Plot - 3. | 6.03 | Aizawl Road North Division | 24.04.24 |  | 50% |  | 10% |  | 60% |  | Work in progress | Restricted Tender
128 | Const. of RCC Pavement on Hostel Square at Armed Veng South. | 4.17 | Aizawl Road North Division |  |  |  |  | 10% |  | 10% |  | Work in progress | Restricted Tender
129 | Const. of RCC Pavement between Thansanga House to Ronghakliana House on Armed Veng South Local Council Road. | 2.17 | Aizawl Road North Division |  |  |  |  | 100% |  | 100% |  | Phy.Completed | Restricted Tender
130 | Const. of PCC Pavement near Larry Lalrava House Saron Veng. | 4.24 | Aizawl Road North Division | 08.04.24 | 13.04.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
131 | Const. of V-Shape Side Drain near Rawra chhutna. | 0.12 | Aizawl Road North Division | [8 empty] | Not yet started | Restricted Tender
132 | Const. of Retaining Wall on Dawrpui Thlanmual Plot - 1 | 10.95 | Aizawl Road North Division |  |  | 10% |  | 10% |  | 20% |  | Work in progress | Restricted Tender
133 | Const. of Retaining Wall on Dawrpui Thlanmual Plot - 2. | 8.11 | Aizawl Road North Division |  |  | 10% |  | 10% |  | 20% |  | Work in progress | Restricted Tender
134 | Const. of Breast Wall on Armed Veng South Local Council Road near Lalnghakliana House. | 5.94 | Aizawl Road North Division | 15.04.24 | 20.04.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
135 | Const. of Breast Wall between Chawngneihkunga House to Khupneihvunga House. | 6.41 | Aizawl Road North Division |  |  | 10% |  | 90% |  | 100% |  | Work in progress | Restricted Tender
136 | Widening of Road between Chawngneihkunga House to Khupneihvunga House. | 86 | Aizawl Road North Division | 22.04.24 |  | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
137 | Const. of Retaining Wall below Chhinga Veng Thlanmual. | 46 | Aizawl Road North Division | 26.02.24 |  | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
IMPROVEMENT OF ROAD FROM RAMHLUN VENGTHAR TO RAMHLUN SPORT COMPLEX, AIZAWL.
138 | Const. of RCC Balcony on Ramhlun South Cemetary at Ramhlun South. | 42.94 | Aizawl Road North Division | 08.03.24 |  | 7% |  | 3% |  | 10% |  | Work in progress | Restricted Tender
139 | Const. of RCC Frame Structure Breast Wall near Ramhlun South Cemetary | 25.61 | Aizawl Road North Division | 08.02.24 |  | 90% |  | 10% |  | 100% |  | Phy.Completed | Restricted Tender
140 | Const. of Retaining Wall below Presbyterian Church, Laipuitlang. | 3.93 | Aizawl Road North Division | 16.01.24 | 13.02.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
141 | Const. of RCC Pavement & Lowering on Jubilee Road at Ramhlun Vengthar. | 58.59 | Aizawl Road North Division | 04.03.24 |  | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
142 | Const. of RCC Rectangular Side Drain with Cover near Jubilee Road at Ramhlun Vengthar. | 3.65 | Aizawl Road North Division | 03.04.24 |  | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
143 | Const. of Steel Grate Cover Side Drain near Jubilee Road at Ramhlun Vengthar. | 1.49 | Aizawl Road North Division | 03.04.24 |  | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
144 | Const. of Breast Wall on Turning Point at Tetea Road Ramthar North. | 5.65 | Aizawl Road North Division | 06.02.24 | 23.02.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
145 | Const. of RCC Pavement on Tetea Road (Below Dawngliana House) at Ramthar North. | 7.89 | Aizawl Road North Division | 02.04.24 | 26.04.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
146 | Const. of Retaining Wall on Tetea Road Block-I at Ramthar North. | 6.63 | Aizawl Road North Division |  |  | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
147 | Const. of Retaining Wall on Tetea Road Block-II at Ramthar North. | 1.83 | Aizawl Road North Division | 13.01.24 | 12.02.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
148 | Const. of Breast Wall below step at NHC Ramhlun Venglai. | 3.33 | Aizawl Road North Division | 15.01.24 | 16.02.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
149 | Const. of Breast Wall Vertical Extension NHC at Ramhlun Venglai. | 5.6 | Aizawl Road North Division | 01.02.24 | 19.02.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
150 | Const. of RCC Rectangular Side Drain with Cover NHC at Ramhlun Venglai | 0.97 | Aizawl Road North Division | 02.02.24 | 20.02.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
151 | Const. of RCC Rectangular Side Drain with Cover on Rokhuma Colney to PC. Lalzuiliana House (Bishop Road) at Ramthar. | 2.98 | Aizawl Road North Division | 12.03.24 | 25.04.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
152 | Const. of Breast Wall below St.Lawrence School at Ramthar. | 6.56 | Aizawl Road North Division | 06.03.24 | 22.03.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
153 | Const. of Breast Wall near Boxing Hall at Ramhlun Venglai. | 9.38 | Aizawl Road North Division | 26.03.24 |  | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
154 | Const. of Retaining Wall on Sihpui to Tlaklui road at Pu C,.Lalnunmawia House. | 8.81 | Aizawl Road North Division | 05.03.24 | 21.03.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
155 | Const. of PCC Pavement on ICI road Complex Vengthlang at Ramhlun Sport Complex. | 3.51 | Aizawl Road North Division | 08.03.24 | 20.03.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
156 | Const. of Retaining Wall near Rosangpuia House at Ramhlun Sport Complex. | 4.22 | Aizawl Road North Division | 05.03.24 | 24.04.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
157 | Const. of Breast Wall on LC Road near Lianhnuna Road at Ramhlun Sport Complex. | 3.09 | Aizawl Road North Division | 04.03.24 | 25.03.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
158 | Const. of RCC Side Drain near Pu Para House at Ramhlun Sport Complex. | 0.49 | Aizawl Road North Division | 05.03.24 | 20.03.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
159 | Const. of RCC Footpath on LC Road near HC. Thangvela House to B.Zanghinglova House. | 16.85 | Aizawl Road North Division | 12.03.24 |  | 90% |  | 10% |  | 100% |  | Phy.Completed | Restricted Tender
CONSTRUCTION OF LUNGHLU ROAD AT CHANMARI WEST, AIZAWL.
160 | Const. of RCC Link Drain near Hotel Platinum at Zarkawt. | 0.85 | Aizawl Road North Division | 06.12.23 | 09.12.23 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
161 | Improvement of Zarkawt Valley Approach Road Phase-II | 47 | Aizawl Road North Division | 19.02.24 |  | 40% |  | 10% |  | 50% |  | Work in progress | Restricted Tender
162 | Const. of Retaining Wall near Babula's House at Chanmari. | 13.27 | Aizawl Road North Division | 05.02.24 |  | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
163 | Repair of Link Drain with Cover near J.Thangdailova House at Electric Veng. | 9.64 | Aizawl Road North Division | 08.02.24 |  | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
164 | Const. of New Cemetary Road at Electric Veng. | 28 | Aizawl Road North Division | 02.02.24 |  | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
UPGRADATION OF INTERNAL ROADS AT DURTLANG, BAWNGKAWN, CHALTLANG, ZUANGTUI, RAMHLUN & RAMTHAR.
165 | Steel Grade Cover Side Drain on PC Malsawma House to Rev. C. Vanlalhruaia House at Ramhlun 'S' | 8.04 | Aizawl Road North Division | 20.03.24 |  | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
166 | Const. of RCC Foot Step near PC. Lalzuiliana House, Ramthar. | 16.58 | Aizawl Road North Division | 06.03.24 |  | 90% |  | 10% |  | 100% |  | Phy.Completed | Restricted Tender
167 | Const. of RCC Link Drain near PC. Lalzuiliana House at Ramthar. | 8.42 | Aizawl Road North Division | 06.03.24 |  | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
168 | Const. of Breast Wall below PC. Laltanpuia House at Ramthar North | 7.37 | Aizawl Road North Division | 28.03.24 | 24.04.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
|  |  | Aizawl Road North Division | [8 empty] | Phy.Completed | Restricted Tender
|  |  | Aizawl Road North Division | [8 empty] | Phy.Completed | Restricted Tender
|  |  | Aizawl Road North Division | [8 empty] | Phy.Completed | Restricted Tender
|  |  | Aizawl Road North Division | [8 empty] | Phy.Completed | Restricted Tender
|  |  | Aizawl Road North Division | [8 empty] | Phy.Completed | Restricted Tender
169 | Const. of Breast Wall near Lalrammuana Ralte House at Ramthar North. | 5.76 | Aizawl Road North Division | 05.03.24 | 27.03.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
|  |  | Aizawl Road North Division | [8 empty] | Work in progress | Restricted Tender
|  |  | Aizawl Road North Division | [8 empty] | Work in progress | Restricted Tender
|  |  | Aizawl Road North Division | [8 empty] | Work in progress | Restricted Tender
|  |  | Aizawl Road North Division | [8 empty] | Work in progress | Restricted Tender
170 | Const. of RCC Foot Step near Pi Manmawii House at Ramhlun 'S' | 6.68 | Aizawl Road North Division | 04.03.24 |  | 90% |  | 10% |  | 100% |  | Phy.Completed | Restricted Tender
Aizawl Road North Division
Aizawl Road North Division
Aizawl Road North Division
WORK IMPLEMENTATION OF ARTICLE 275(1) PHASE - II
171 | Const. of Bethany Road at Chhinga Veng, Aizawl. | 70 | Aizawl Road North Division | 07.10.23 |  | 95% |  |  |  | 95% |  | Work in progress | Restricted Tender
SUB-DIVISION - II
UPGRADATION OF BETHEL VENG ROAD AT ZEMABAWK WITH APPROACH ROAD TO ZOKHAWSANG BYPASS ROAD.
172 | PCC Pavement at Ch: 0.000 - 0.580 Kmp. | 57.53 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
173 | Const. of PCC V-Shape Side Drain at Ch: 0.000 Kmp | 1.57 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
174 | Clearance of Landslip | 20.83 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
ADDITIONAL REQUIREMENT FOR UPGRADATION OF BETHEL VENG ROAD AT ZEMABAWK.
175 | Earth Work for Widening (Additional ) | 69.54 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
176 | RCC Frame Retaining Walls No.1 | 5.2 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
IMPROVEMENT OF MUTHI - TUIRIAL LINK ROAD.
177 | Widening & Curve Improvement. | 134.74 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 60% |  | 10% |  | 70% |  | Work in progress | Restricted Tender
CONSTRUCTION OF SLAB CULVERT :
178 | Slab Culvert Type - I | 11.5 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
CONSTRUCTION OF RETAINING WALL
179 | Retaining Wall Type - I | 10 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
180 | Retaining Wall Type - II | 14 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
CONSTRUCTION OF BAMBOO LINK ROAD FROM NAUSEL, CHAMDUR, LUNGSANG, PUMPELHSEI, KAWRBEL.
181 | Const. of Nausel - Tuirial Bamboo Link Road.
| 1) Formation Cutting | 36.01 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 50% |  |  |  | 50% |  | Work in progress | Restricted Tender
2) Const. of Slab Culvert.
182 | Chainage between 0.000-3.500Kmp | 59.39 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
183 | Retaining Wall | 30.93 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
184 | Concrete Pavement of Sihphir Neihbawih khawhnuai kawng balance : 1) Concrete Pavement. | 36.28 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
185 | 2) Const. of Slab Culvert. At chainage between 0.00-0.503km | 43.71 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
186 | Const. of Hmunte road at Muthi 1) Formation Cutting | 36.57 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 50% |  |  |  | 50% |  | Work in progress | Restricted Tender
187 | 2)Const. of Slab Culvert. Chainage between 0.00-1.00Kmp | 16.57 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
188 | 3) Const. of Retaining Wall Chainage between 0.00-2.00Kmp | 14.5 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
189 | Retaining Wall | 7.18 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
190 | Const. of Chamdur-Kawrbellui road 1) Formation Cutting | 30.5 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 50% |  | 40% |  | 90% |  | Work in progress | Restricted Tender
CONSTRUCTION OF ROAD FROM ZEMABAWK NORTH TO CWC AND MUALZEN
Const. of New Road from Zemabawk North Dinthar Veng to CWC including Protection Works & Cross Drain.
191 | Formation Cutting. | 72.46 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
192 | Const. of Slab Culvert Type - I | 8 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
193 | Const. of Slab Culvert Type - II | 12 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
194 | Const. of Slab Culvert Type - III | 16.94 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
195 | Const. of Slab Culvert Type - I | 25 | Aizawl Road North Division | 14.12.23 | 14.12.24 |  |  | 100% |  | 100% |  | Phy.Completed | Restricted Tender
Const. of New Road from Zemabawk North Thlanmual Hnuai to Mualzen including Protection Works & Cross Drain.
196 | Formation Cutting. | 60.12 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
197 | At Chainage between 0.00 to 1.50 | 28.6 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
198 | At Chainage between 1.50-3.00 | 23.28 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
CONSTRUCTION OF ROAD FROM FALKLAND TO GALILEE VIA MITLAMUAL AT ZEMABAWK, AIZAWL.
Const. of Widening & New Road from Falkland to Mitlamual including Protection Works & Cross Drain.
199 | Widening & New Cutting | 42.16 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
200 | Const. of Slab Culvert Type - I | 2.64 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
Const. of New Road from Zemabawk Galilee Vailui to Mitlamual including Protection Works and Cross Drain.
201 | Formation Cutting | 52.09 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 20% |  |  |  | 20% |  | Work in progress | Restricted Tender
202 | Const. of PCC Pavement. | 22.88 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
203 | Const. of Slab Culvert Phase-I | 14.63 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started
CONSTRUCTION OF ROAD FROM FALKLAND TO ZEMABAWK NORTH VIA THUAMPUI.
Const. of New Road from Falkland Penniel Road to Thuampui Vengthar and BS Farm to UPC Biakin at Pi Vani Lui Link Road including Protection Work & Cross Drain (1.00 Km )
204 | Widening of Road. | 29.22 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
205 | Const. of PCC Pavement on BS Farm to UPC Biakin. | 32.18 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
206 | Const. of Slab Culvert at Ch : 0.360 Kmp | 4.3 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
207 | Const. of RCC Link Drain at Ch : 0.000-0.112 Km | 25 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 70% |  |  |  | 70% |  | Work in progress | Restricted Tender
208 | Const. of RCC Link Drain with Cover at Ch : 0.000 Km | 3.72 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
209 | Const. of RCC Link Drain with Cover at Ch : 0.120 Km | 5.58 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
Const. of New Road RAY to BS Farm Falkland including Protection Works & Cross Drain (0.800 Km)
210 | Lowering and Widening | 10.14 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
211 | Const. of PCC Pavement on RAY to BS Farm Falkland | 10.48 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
212 | Const. of Retaining Wall | 8.84 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
213 | Construction of V-Shape | 4.2 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
214 | Const. of Missing Link at BCM Multipurpose Centre at Falkland | 6.34 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
215 | Const. of Step near Pu Ringdika's House | 1.4 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
216 | Repairing of Kailiana Concrete Pavement Road at Zemabawk 'N' | 10.6 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
CONSTRUCTION OF TUIRIAL AIRFIELD TO MUTHI AND ZOKHAWSANG AGRICULTURE.
Const. of New Road from Tuirial Airfield Runway to Muthi Lui Lalchhuana Leilet including Protection Works & Cross Drain.
217 | Formation Cutting | 40.94 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
218 | Const. of RCC Slab Culvert. | 66.58 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 80% |  |  |  | 80% |  | Work in progress | Restricted Tender
CONSTRUCTION OF ROAD FROM THUAMPUI TO NH-6 (Zemabawk)
219 | Const. of Link Drain near Pi Diki House at Sihphir | 10 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
220 | Pavement of AR Complex at Zokhawsang | 59 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
221 | Resurfacing of Women Polytechnic Internal Road at Durtlang | 27 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
Improvement of Dinthar Veng to Muthi Lui Road (Balance Portion ) at Zemabawk.
222 | Concrete Pavement | 31.5 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
223 | Const. of RCC Slab Culvert No.1 | 12.21 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
224 | Const. of Retaining Wall | 5 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
225 | Const. of U-Shape Side Drain. | 8.29 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
226 | Resurfacing of Sihpui to Ramhlun Vengthar Bus Turning Point at Ch : 1.052-1.357 Km. | 11 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
227 | Patch Repair of Vaivakawn to MZU via Zonuam. | 18 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
228 | Const. of Retaining Wall below Thanhrangi's House at Luangmual Complex. | 5 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
Concrete Pavement from Field Veng to Dinthar Veng at Zemabawk North
229 | Concrete Pavement | 16.72 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
230 | Rectangular Side Drain with Cover | 2.26 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
231 | V-Shape Drain | 3.36 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
232 | Const. of Step with Railing over Link Drain near Zemabawk North Play Ground. | 8 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
Const. of RCC Bridge with Link Drain & Retaining Wall bebeath Ramfangzauva's Building at AL Road Zemabawk.
233 | Const. of RCC Balcony | 3.07 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
234 | Const. of RCC Link Drain | 11.62 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
235 | Const. of Retaining Wall | 5.14 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
236 | Const. of Masonry Stone Link Drain with Retaining Wall below Gov't. Zemabawk Primary School - I | 1.92 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
237 | Concrete Pavement from NH-54 to Holy Cross School Zemabawk. | 15.6 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
238 | Const. of Masonry Stone Link Drain near F.Lalrinmawia's Residence at Dinthar Veng, Zemabawk North. | 5.61 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
239 | Const. of RCC Link Drain (Balance Portion) at Dinthar Veng. Zemabawk | 10.33 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
Const. of Road including Culvert & Retaining Wall on Thuampui to Thuampui Vengthar Road (Balance Portion.)
240 | Formation Cutting | 8.82 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
241 | Slab Culvert | 5.13 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
242 | Retaining Wall | 9.84 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
Concrete Pavement Laichhinga Street Kawn Veng-II at Zemabawk.
243 | Concrete Pavement | 12.3 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
244 | Rectangular Side Drain with Cover | 1.05 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
245 | Concrete Pavement from Hogh School to Bethel at Zemabawk | 2.62 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
246 | Const. of RCC U-Shape Side Drain Kailiana Road at Zemabawk near Pi Sawihari. | 7.81 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
247 | PCC Flooring Zemabawk North Thlanmual to Muthi Lui | 10.67 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
248 | Const. of Hand Railing at Galilee Veng Main Road, Zemabawk. | 2.48 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
249 | Laying of Chequerred Tiles at Mel Li mual (Mual khat) existing step at Zemabawk. | 4.5 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
UPGRADATION OF INTERNAL ROADS AT DURTLANG, BAWNGKAWN, CHALTLANG, ZUANGTUI, RAMHLUN & RAMTHAR.
250 | Const. of Rectangular Side Drain with Cover at Tatkawng Veng. | 1.68 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 30% |  |  |  | 30% |  | Work in progress | Restricted Tender
251 | Const. of Concrete Pavement of Durtlang tlak lam Thlanmual Road. | 20 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
252 | Const. of Concrete Pavement of Gosen Veng Kawngpui at Zuangtui | 7 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 20% |  |  |  | 20% |  | Work in progress | Restricted Tender
253 | Const. of PCC Flooring at Rivenga Road at Muanna Veng. | 10 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
254 | Const. of PCC Flooring Internal Road - Zamliana Road to K.Thankunga Road, Selesih. | 5 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
255 | Vantlang Step near K,Thankunga House at Selesih. | 5 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
256 | Const. of PCC Flooring Leitan Ramthar Biak im Lane at Leitan, Ramthar. | 10 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
257 | Const. of Concrete Pavement on Bawngkawn Thlanmual to Thuampui Road | 22.87 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 50% |  |  |  | 50% |  | Work in progress | Restricted Tender
258 | Steel Grade Cover Side Drain on PC Malsawma House to Rev. C. Vanlalhruaia House at Ramhlun 'S' | 8.04 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
259 | Const of RCC Foot Step near PC Lalzuiliana House Ramthar | 16.58 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
260 | Const. of RCC Link Drain near PC Lalzuiliana House, Ramthar | 8.42 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
261 | Const. of Breast Wall below PC. Laltanpuia House at Ramthar North | 7.37 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
262 | Const. of Breast Wall near Lalrammuana Ralte House at Ramthar North. | 5.76 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
263 | Const of RCC Foot Step near Pi Manmawii House ar Ramhlun 'S' | 6.68 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
IMPROVEMENT OF ROAD FROM DURTLANG LEITAN TO DURTLANG RAMTHAR AT DURTLANG.
Const. of Road at Selesih Aizawl (Sh: Const. of Concrete Pavement and Culvert etc.)
264 | Concrete Pavement of Pu Dinga Road | 5 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
Improvement of Road at Durtlang North, Aizawl. (Sh : Const. of Concrete Pavement etc.)
265 | Const. of Concrete Pavement & Cross Drain on Vungkhama Road including Chhingtei Road at Durtlang North. | 15 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
266 | Const. of Concrete Pavement of Durtlang North Thlanmual. | 10 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
Improvement of Road at Durtlang , Aizawl. (Sh : Const. of Concrete Pavement, Cross Drain with Cover, V-Shape Side Drain, Slab Culvert and Link Drain etc.)
267 | Const. of PCC V-Shape Side Drain at Centanary Road & Women Polytechnic approach Road at Durtlang. | 5 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
268 | Concrete Pavement of Lalnu Road at Suaka Veng, Durtlang (Balance Portion) | 5.4 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
269 | Const. of Cross Drain with Cover on Durtlang Field. | 1 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
270 | Const. of Step including Link Drain at Centenary Road, Durtlang. | 20 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
Const. & Improvement of road at Durtlang Leitan, Aizawl (Sh: Const. of Concrete Pavement, RCC frame Retaining Wall, Cross Drain with Cover, U-Shape Side Drain and Link Drain etc.)
271 | Const. of PCC V-Shape Side Drain and Retaining Wall at Gospel Thunder Team Compound, Durtlang Leitan | 20 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
272 | Const. of RCC Frame Retaining Wall at Zotui Road, Durtlang Leitan. | 3.5 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
273 | Patch repair of Durtlang Leitan SIRD Road. | 5.05 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
Improvement of Road at Durtlang Ramthar, Aizawl. (Sh: Const. of Concrete Pavement, Cross Drain and Re-Surfacing)
274 | Resurfacing of 3rd Lane at Durtlang Ramthar. | 29.5 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
275 | Concrete Pavement of approach road to Durtlang Ramthar Presby. Church including Cross Drainage. | 30.5 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
Improvement of Road at Chaltlang Lily Veng, Aizawl (Sh: Widening of Road, Concrete Pavement, RCC Retaining Wall and Re-surfacing etc)
276 | Resurfacing of Chaltlang Lily Veng Internal Road (Balance) | 3 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
277 | Re-const. of Step from State Guest House to Lily Veng Internal Road. | 6 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
278 | Const. of RCC Balcony & Masonry Step near R.Lalmanga House at Chaltlang Lily Veng. | 14 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
Improvement of Road at Chaltlang, Aizawl. (Sh: Junction Improvement, Const. of Concrete Pavement, U-Shape Side Drain, Retaining Wall & Step.)
279 | Concrete pavement of road near F. Malsawma House at Chaltlang | 2.5 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
280 | Const. of Retaining Wall & Concrete Pavement on AMC Road at Dingdi Veng, Chaltlang. | 9.7 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
Improvement of Road at Bawngkawn (Sh: Const. of Balcony, Link Drain, Retaining Wall & Concrete Pavement.)
281 | Const. of Retaining Wall near Pu Salemthara Residence at Brigade, Bawngkawn. | 2.6 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
282 | Concrete Pavement of Liansailova Road, Bawngkawn. | 10 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
283 | Concrete Pavement of Shalom Road at Bawngkawn Hmar Veng (Balance Portion) | 10 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
284 | Concrete Pavement on Upper Bawngkawn Hmar Veng. | 4.5 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
285 | Const. of Additional Protection Work at Bethel Veng. | 13 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
IMPROVEMENT OF ROAD FROM ZEMABAWK TO LUNGBIAL ROAD IN THE LOCALITY OF ZEMABAWK AT AIZAWL.
Construction of Road at Sihphir.
286 | Concrete Pavement of Approach Road to Sihphir Rescue Center at Sihphir Kawnveng. | 8.8 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
287 | Formation Cutting, Pavement & Step of Sunhlu tlang (Prayer mountain) at Sihphir Tlang Veng. | 7.9 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
288 | Const. of Step including Retaining Wall near Pu Zakhuma House at Sihphir Field Veng. | 3.66 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
289 | Const. of Link Drain with Cover near Pi Liani House at Sihphir Dinthar. | 1.74 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
290 | Const. of Link Drain near H.Lalfakzuala House, Sihphir Dinthar | 2.61 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
Construction of Concrete Pavement at Zuangtui, Aizawl.
291 | RCC Balcony Gosen Veng to 132 KV Sub-Station at Zuangtui peng. | 26.13 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
Concrete Pavement of Rivenga Road at Muanna Veng, Aizawl.
292 | Concrete Pavement of Rivenga Road at Muanna Veng, Aizawl. | 7.3 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
Construction of Road at Muthi, Aizawl.
293 | Concrete Pavement at Ch; 0.000-0.715 Kmp Muthi peng kawn. | 8.6 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
Construction of Road at Nausel.
294 | Concrete Pavement at Nausel Thlanmual kawng | 8.2 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
Improvement of Road at Sihphir Venghlun.
295 | Const. of Retaining Wall at Thuampui Selesih Road at Ch: 4.300Kmp, Durtlang. | 6.14 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
Construction of New Road from Zemabawk North Thlanmual to Thuampui Thlanmual including Protection Works & Cross Drain.
296 | Formation Cutting | 51.36 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
297 | Const. of RCC Slab Culvert. | 33.04 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 80% |  |  |  | 80% |  | Work in progress | Restricted Tender
Construction of Road at Falkland, Aizawl.
298 | Const. of PCC Pavement on Local Council Road to RAY at Falkland. | 27.79 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
299 | Const. of PCC Pavement on Rabboni Road at Falkland | 5.14 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
300 | Const. of PCC Pavement on Local Council Road Falkland | 11.33 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
301 | PCC Pavement on approach road to Vai Lui via Rev. Lalsangliana House at Falkland Veng. | 5.74 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
Sub-DIVISION - III
Construction of PCC Pavement at Sihhmui to NH-54 (Length=7.00 Kms, PCC Pavement=7.00 Kms)
302 | Widening of road from Law College to PCI road at Luangmual, Aizawl (Sh: Earth Work for Widening of existing road) | 11.95 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started
303 | Improvement & Upgradation of road at Chawlhhmun, Aizawl | 26 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted
304 | Improvement & Upgradation of road at Zotlang, Aizawl | 20.29 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started
305 | Construction of RCC pavement at Sihhmui | 15.91 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted
306 | Improvement & Upgradation of road from PCI to Anganwadi at Lungverh | 77.98 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed
307 | Rangvamual internal road | 23.27 | Aizawl Road North Division |  |  | 100% |  |  |  | 100% |  | Phy.Completed
308 | Phunchawng internal road | 19.2 | Aizawl Road North Division |  |  | 100% |  |  |  | 100% |  | Phy.Completed
Improvement of internal roads at Hunthar, Chanmari West, Rangvamual, Phunchawng & Chhinga Veng (Improvement of Roads PCC Pavement = 20.00 Kms, Pavement = 5.00 Kms, Link Drain = 100.00 M)
309 | Patch Repair and Seal Coating of Approach Road of tanhril, Aizawl | 23.08 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted
310 | Construction of PCC Pavement of Approach Road to Tawngtai Bethel Camping Centre, Sakawrtuichhun, Aizawl | 9.49 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted
311 | Rigid Pavement of Gan Sabra Road | 19.33 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted
312 | Constrcution of PCC Pavement of Road from Saikaphleia's House to Muanthanga's House at Lungverh. Length=120.00 Rm | 9.49 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted
Construction of Lunghlu Road at Chanmari West Aizawl (Length=4.00 Kms, Ew = 4.00 Kms, Pavement = 4.00 Kms, Side Drain = 4500m, R/W 30m, Culvert = 10.Nos.)
313 | Construcrtion of RCC Frame struction Retaining Wall I at Lunghlu Road, Hunthar | 14.5 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted
314 | Patch repair and Seal coat of MUP Road at Chanmari West, Aizawl | 11.55 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted
315 | Patch repair and Seal coat from BT Bakery to Protective Home via Zarkawt Thlanmual | 29.95 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted
316 | Construction of RCC Road at Methodist mual Turning Point to Edenthar Anganwadi Centre No.1 at Edenthar | 8.76 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted
317 | Rigid Pavement of Gan Sabra Road | 16.86 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted
AIZAWL ROAD SOUTH DIVISION
Construction and Rehabilitation of Samtlang - Lungleng Road Under SASCI - 2022-2023
318 | Improvement of Internal Road to Hlimen Vengchhak to Pu N Zokunga House. | 5 | Aizawl Road South Division | [8 empty] | Cannot be started due to land conflick with the Land owners. | Item rate Contract
319 | Improvement of Curves at Ch.0.00 Kmp and 0.600 on Mission Vengthlang Damphei to Tlawng Road | 72 | Aizawl Road South Division |  |  | 99.8% |  |  | 69.1 | 99.8% | 69.1 | Work in progress | Item rate Contract
320 | Widening of Approach Road to City Bus Parking at S.Hlimen (Melthum - Hlimen Road ) | 576 | Aizawl Road South Division | 7.04.23 | 7.04.24 | 37% | 142.02 |  |  | 37% | 142.02 | Work in progress | Restricted tender
321 | Widening of S.Hlimen City Bus Parking - Samtlang Road (Hlimen-Samtlang Road) | 831 | Aizawl Road South Division | 06.4.23 | 06.04.24 | 86% | 462.56 | 2% |  | 88% | 462.56 | Work in progress | Restricted tender
SASCI - 2023-2024
322 | Const. of PCC Pavement, PCC Side drain and Retaining Wall at Upper Republic to Bethlehem via College veng under SASCI Phase-I Part-1 | 387 | Aizawl Road South Division | 14.12.23 | 14.12.24 | 21.38% |  | 6.68% |  | 28.06% |  | Work in progress | Restricted Tender
323 | Improvement of Venghnuai to Salem Road under SASCI Phase-I, Part-1. | 280 | Aizawl Road South Division | 14.12.23 | 14.12.24 | 24% |  | 26.67% |  | 50.67% |  | Work in progress | Restricted Tender
324 | Overlaying of Road with PCC Pavement from Mission Veng to Khatla with Retaining Wall and Minor Bridge at Aizawl under SASCI Phase - I, Part - I | 241 | Aizawl Road South Division | 14.12.23 | 14.12.24 | 76.82% |  | 19.09% | 65.53 | 95.91% | 65.53 | Work in progress | Restricted Tender
325 | Upgradation of Internal roads at Tuikual, Venghlui and Republic veng | 200 | Aizawl Road South Division | 14.12.23 | 14.12.24 | 67.92% |  | 22.75% | 51.32 | 90.67% | 51.32 | Work in progress | Restricted Tender
326 | Improvement of Saikhamakawn to Kulikawn via Tlangnuam under SASCI Phase-I, Part-I | 248 | Aizawl Road South Division | 14.12.23 | 14.12.24 | 87.06% |  | 1.24% |  | 88.3% |  | Work in progress | Restricted Tender
327 | Const. of road from Tlawng road to Model Veng under SASCI during 2023-2024 | 350 | Aizawl Road South Division | 14.12.23 | 14.12.24 |  |  | 1.5% |  | 1.5% |  | Work in progress | Restricted Tender
328 | Const. of Roads from Nursery - Tamdo - Lawipu (2.50Kms) under SASCI during 2023-2024 Phase-II | 476 | Aizawl Road South Division | 14.12.23 | 14.12.24 | 68.33% |  | 10.23% |  | 78.56% |  | Work in progress | Restricted Tender
329 | Improvement of Roads and Infrastructtures at Aizawl City under SASCI 2023-2024 Under Aizawl Road South Division. | 180.2 | Aizawl Road South Division | 14.12.23 | 14.12.24 | 66.67% |  | 33.33% | 148.96 | 100% | 148.96 | Work in progress | Restricted Tender
CHAMPHAI DIVISION
Const./Improvement of Road from Pamchung - Tualcheng - Chhangphut Field - Keifangtlang at Champhai District. 2022-2023
330 | Const. of Road from Pamchung to Tualcheng | 60 | Champhai Division | 21.03.23 | 21.04.23 | 100% | 57.89 |  |  | 100% | 57.89 | Completed | Spot Quatation
331 | Widening of Chhangphut Field to Keifangtlang | 90 | Champhai Division | 21.03.23 | 21.04.23 | 100% | 86.41 |  |  | 100% | 86.41 | Completed | Spot Quatation
332 | Widening and Retaining Wall at Hnahlan Dawrkawn to BRTF Road | 20 | Champhai Division | 21.03.23 | 21.04.23 | 100% | 19.33 |  |  | 100% | 19.33 | Completed | Spot Quatation
333 | Const. and Widening of Champhai Vengthlang ( N.Saron) to PHE Road | 50 | Champhai Division | 21.03.23 | 21.04.23 | 100% | 48.31 |  |  | 100% | 48.31 | Completed | Spot Quatation
334 | Const. of Railing and Retaining Wall at Champhai, Awmpui Phei & IB Veng | 40 | Champhai Division | 21.03.23 | 21.04.23 | 100% | 39.15 |  |  | 100% | 39.15 | Completed | Spot Quatation
335 | Consultancy Fee | 77 | Champhai Division | 21.03.23 | 21.04.23 | 100% | 10.15 |  |  | 100% | 10.15 | Completed | Spot Quatation
Const. of Pavement Champhai Vengthar - BRTF Road - Zotlang at Champhai. 2022-2023
336 | Black Topping of Road from Champhai Vengthar to BRTF Road (Zotekai Short Cut Road) | 164.46 | Champhai Division | 30.03.23 | 31.04.23 | 100% | 162.99 |  |  | 100% | 162.99 | Completed | Spot Quatation
337 | White Topping of Khawulh Approach Road at Zotlang, Champhai (Cement Concrete Pavement ) | 30 | Champhai Division | 30.03.23 | 31.04.23 | 100% | 28.92 |  |  | 100% | 28.92 | Completed | Spot Quatation
338 | Widening of Road from Dinthar to Ramhrangkawn (7th Day Gate to LCN Filling Station ) | 45 | Champhai Division | 30.03.23 | 31.04.23 | 100% | 43.47 |  |  | 100% | 43.47 | Completed | Spot Quatation
339 | Widening of Approach Road to Kendriya Vidhyalaya School, Champhai | 10 | Champhai Division | 30.03.23 | 31.04.23 | 100% | 9.95 |  |  | 100% | 9.95 | Completed | Spot Quatation
Improvement of Road from IKK Zion Veng - Khawbung - Tuipui at Champhai District 2022-2023
340 | Widening and Flexible Pavement of Road from IKK Church to Zion Veng Boundary. | 135.54 | Champhai Division | 30.03.23 | 31.04.23 | 100% | 120.5 |  | 14.24 | 100% | 134.74 | Completed | Spot Quatation
341 | Bouldering of Road from ZBC Church to Mualnuam Road. | 15 | Champhai Division | 30.03.23 | 31.04.23 | 100% | 14.49 |  |  | 100% | 14.49 | Completed | Spot Quatation
342 | Const.and Widening of Road Zawlsei to Tuipui | 40 | Champhai Division | 30.03.23 | 31.04.23 | 100% | 39.5 |  |  | 100% | 39.5 | Completed | Spot Quatation
343 | Surfacing of Ruantlang Dawrkawn to CNV Road Via Lersia Field. | 17.3 | Champhai Division | 30.03.23 | 31.04.23 | 100% | 16.72 |  |  | 100% | 16.72 | Completed | Spot Quatation
344 | Patch Repair and Seal Coating of New Champhai to Tlangsam Road. | 25 | Champhai Division | 30.03.23 | 31.04.23 | 100% | 24.15 |  |  | 100% | 24.16 | Completed | Spot Quatation
345 | Pothole & Re-surfacing of Sasaw Road at Khawbung Internal Road (Khawbung to Tuipui Short Cut Road) | 42.28 | Champhai Division | 30.03.23 | 31.04.23 | 100% | 41.6 |  |  | 100% | 41.6 | Completed | Spot Quatation
346 | Const. of Retaining Wall on Road Formation Collapse at 22.600 Kmp on Champhai to Khawbung Road. | 6.13 | Champhai Division | 30.03.23 | 31.04.23 | 100% | 5.9 |  |  | 100% | 5.9 | Liability | Spot Quatation
347 | Completion of Champhai - Zokhawthar Road under SASCI. 2023-2024 | 1311 | Champhai Division | 06.03.23 | 06.03.24 | 53% | 841.97 | 7% |  | 60% | 841.97 | In Progress | Spot Quatation
Construction of Hruaikawn - Zokhawthar Road (8.00 Km) 2022-2023
348 | Const. of Hruaikawn-Zokhawthar | 50 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
349 | Const. of Bungzung to Tuipui Road (Biate kai) Part-I | 100 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
350 | Const. of Vaphai to Chawngtui 'East' Road | 210 | Champhai Division | 05.10.23 | 05.10.24 | 68% |  | 32% | 201.83 | 100% | 201.83 | Completed | Spot Quatation
351 | Const. of Approach Road to PHC at Bungzung | 60 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
352 | Const. of Bungzung to Zawngtetui Road | 280 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
Construction of Road from Samthang to Farkawn via Lamsial.
353 | Const. of Samthang to Farkawn via Lamsial Road | 350 | Champhai Division | 05.10.23 | 05.10.24 | 85% |  |  |  | 85% |  | On-going | Spot Quatation
354 | Const. of Road from Selam to Tuisa Lui | 24.21 | Champhai Division | 05.10.23 | 05.10.24 | 100% |  |  | 23.26 | 100% | 23.26 | Work completed | Spot Quatation
355 | Const. of Vanzau to Dungtlang (Balance work - Rocky portions)-I | 50 | Champhai Division | 05.10.23 | 05.10.24 | 90% |  | 10% | 67.25% | 100% | 67.25 | Completed | Spot Quatation
Construction of Vaphai to Tiau Road
356 | Const. of Vaphai to Tiau Road | 200 | Champhai Division | 05.10.23 | 05.10.24 | 80% |  | 2% | 130.43 | 82% | 130.43 | On-going | Spot Quatation
357 | Const. of Road from Selam to Tuisa Lui | 125 | Champhai Division | 05.10.23 | 05.10.24 | 100% |  |  | 120.19 | 100% | 120.19 | Work completed | Spot Quatation
358 | Const. of Sesih to Bulfek Road | 165 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
359 | Const. of Truck Lay by (Terminal) at Khuangleng | 10.79 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
360 | Const. of Pavillion at Farkawn (Frame Structure) | 30 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
Improvement & Widening of Road from Bungzung to R.Tuipui (Length = 5.00 Km)
361 | Improvement & Widening of Road Bungzung to Tuipui | 20 | Champhai Division | 05.10.23 | 05.10.24 | 100% |  |  | 19.2 | 100% | 19.2 | Work completed | Spot Quatation
362 | Const. of Road Leisenzo to Lianpui | 9 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
363 | Maintenance of Road Vangchhia to Lianpui | 9 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
364 | Const. of Road Khamkhanthanga's House to Bulfekzawl Road at Sesih | 4 | Champhai Division | 05.10.23 | 05.10.24 | 100% |  |  |  | 100% |  | Work completed | Spot Quatation
365 | Maintenance of Road Khankawn to Tlawva | 9.5 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
366 | Maintenance of Road Thekte to Lurh-Zo | 3.5 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
367 | Const. of Gov't. Khuangthing M/S Court Yard PCC Flooring and Fencing. | 9 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
368 | Const. of PCC Flooring Internal Roads at Farkawn. | 30 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
369 | Const. of PCC Flooring from Kapchhunga's House to Singkawnga's House at Farkawn. | 4 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
370 | Const. of PCC Flooring from Theirekawn Culvert to Rinchhana's House at Farkawn. | 4 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
371 | Const. of PCC Flooring from Vanbiakawia House to Rinliana House at Farkawn. | 4 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
372 | Const. of PCC Flooring from Zasanga House to Hriattira House at Farkawn. | 4 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
373 | Const. of PCC Flooring from Kawn veng to Sub-Centre at Khawbung. | 3 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
374 | Const. of PCC Flooring from Lalnimawia House to Main Road at Khawbung. | 3 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
375 | Const. of PCC Flooring approach road Pathian veng Thlanmual at Khawbung. | 3 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
376 | Const. of PCC Flooring approach road Vengthlang Cemetary at Vaphai. | 3 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
377 | Const. of PCC Flooring between Water Reservoir and Challiana House at Vaphai. | 3 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
378 | Const. of PCC Flooring between Tialthuama House and Sanghnuna House at Vaphai. | 3 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
379 | Const. of PCC Flooring between High School and Nginliankhupa House at Khuangleng. | 9 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
380 | Const. of PCC Flooring J.Vanlalmawia House to Vety Quarter at Khuangleng. | 3 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
381 | Const. of PCC Flooring from Lalmuansanga House to Remmawia House at Khuangthing. | 5 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
382 | Const. of PCC Flooring approach road Gov't. P/S-I at Khuangthing. | 5 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
383 | Const. of PCC Flooring from Khummanga House to Tinngaihliana House at Sesih. | 5 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
384 | Const. of PCC Flooring & Step near Liandothanga House at Sesih. | 5 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
385 | Const. of PCC Flooring from Lalnunpuia House to Lalthlana House at Bungzung. | 7 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
386 | Const. of PCC Flooring approach road Cemetary at Samthang. | 3 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
387 | Const. of PCC Flooring near Lalhmunmawia House at Samthang. | 3 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
388 | Const. of PCC Flooring Lane chung road at Dungtlang. | 4 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
389 | Const. of PCC Flooring from Liandawnga House to Playground at Leisenzo. | 5 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
390 | Const. of PCC Flooring approach road Cemetary at Leisenzo. | 3 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
391 | Const. of PCC Flooring approach road Health Clinic Centre at Vangchhia. | 4 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
392 | Const. of PCC Flooring approach road Gov't. M/S at Vanzau. | 3 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
393 | Const. of PCC Flooring Sub-Centre approach road at Khankawn. | 4 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
394 | Const. of PCC Flooring Internal Road Lane hnuai at Lianpui. | 3 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
395 | Const. of PCC Flooring approach road Cemetary at Thekte. | 3 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
396 | Const. of PCC Flooring approach road Presby. Church at Leithum. | 3 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
397 | Const. of PCC Flooring Internal Road near Laldinmawia House at Sazep. | 3 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
398 | Const. of PCC Flooring approach road Gov't. P/S at Zawlsei. | 3 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
399 | Const. of PCC Flooring near Community Hall at Buang. | 3 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
400 | Const. of PCC Flooring from T.Hranglawta House to Chhunkhuma House at Bulfekzawl. | 3 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
401 | Const. of PCC Flooring from Waiting Shed to Cemetary at Hruaikawn. | 15 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
402 | Const. of PCC Flooring approach road Gov't. P/S at Thekpui. | 3 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
403 | Const. of PCC Flooring near Biakliana House at Zawngtetui. | 2 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
404 | Const. of PCC Flooring between Thangvhuanga House to Lalsawma House at Chawngtui 'E' | 2 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
405 | Const. of PCC Flooring Tiau road at Saikhumphai. | 1.5 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
406 | Const. of Side Drain from Lallianmanga House to Lalremruata House at N.Hruaikawn. | 2 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
407 | Const. of Zalhva Link Road Culvert at Samthang. | 2.5 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
Construction of PCC Pavement from Dilkawn to Kelkang (Length = 7.00 Km)
408 | Approach road for Tuipui Village from NH-6 with 1(one) Bridge (3Kms. Approx). | 20 | Champhai Division | 05.10.23 | 05.10.24 | 100% |  |  | 19.27 | 100% | 19.27 | Completed | Spot Quatation
409 | Const. of Road Kanan veng to Jail veng with Culvert. | 20 | Champhai Division | 05.10.23 | 05.10.24 | 10% |  |  |  | 10% |  | On-going | Spot Quatation
410 | Const. of PCC Flooring from Khawulh Peng to Presby. Church at Tlangnuam ,Vengthar. | 20 | Champhai Division | 05.10.23 | 05.10.24 | 100% |  |  | 19.23 | 100% | 19.23 | Completed | Spot Quatation
411 | White-Topping of Road from KC Lalzarliana House to Chauleng Veng | 10 | Champhai Division | 05.10.23 | 05.10.24 | 50.1% |  | 49.9% | 9.62 | 100% | 9.62 | Completed | Spot Quatation
412 | Widening and Bouldering of Road from Cold Storage, New Champhai to Tlangnuam Vengthar Presbyterian Church. | 10 | Champhai Division | 05.10.23 | 05.10.24 | 50.1% |  | 29.9% |  | 80% |  | On-going | Spot Quatation
413 | Const. of Road from Zion Veng Thlanmual Peng to Emmanuel After Care Centre. | 10 | Champhai Division | 05.10.23 | 05.10.24 | 100% |  |  | 9.62 | 100% | 9.62 | Completed | Spot Quatation
414 | White-Topping of Circular road from Pauchinthanga House to Thangkhanpuma House at Helipad Veng, New Champhai. | 10 | Champhai Division | 05.10.23 | 05.10.24 |  |  | 10% |  | 10% |  | Not yet started | Spot Quatation
415 | Const. of Side Drain from PWD Road near Lianthuama Car Wash to Petrol Pump, New Champhai. | 15 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
416 | Const. of White-topping of road from Community Hall to World Bank Road with 2 Culverts. | 10 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
417 | Widening of road between Lersia Field and Vanlaltluanga House. | 10 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
418 | Const. of Retaining Wall at Dilkawn | 10 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
419 | Const. of PCC Flooring from Saitawngkawn to Thlanmual. | 10 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
420 | Const. of PCC Flooring from B.Sanga House to Ramthanzauvi House at Melbuk. | 10 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
421 | Const. of PCC Flooring from Dilkawn to Kelkang. | 30 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
422 | Const. of Road from Hausiama Lungphun to Hmingzauva Leilet. | 30 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
423 | Const. of Road from Thangzuala House to Bangla Lui. | 30 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
424 | Widening of approach road from Melbuk to New Hruaikawn. | 5 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
425 | Const. of PCC Flooring from Hlunthanga House to Genesaret Gospel Home. | 5 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
426 | Const. of PCC Flooring from Zonunsiama House to P.School. | 5 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
427 | Const. of Black-Topping of Road from Thangzuala House to F.Lalhnawla House at Zotlang. | 10 | Champhai Division | 05.10.23 | 05.10.24 |  |  | 40% |  | 40% |  | Work in progress | Spot Quatation
428 | Const. of PCC Flooring at Hranga High School Tual, Kanan Veng. | 5 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
Construction of Road from Pamchung to Tualcheng (Length = 5.00 Kms)
429 | Improvement of Pamchung to Tualcheng (5.00 Kms.) | 150 | Champhai Division | 05.10.23 | 05.10.24 | 100% |  |  | 79.5 | 100% | 79.5 | Completed | Spot Quatation
430 | Const. of Hliappui to Aiduzawl. | 30 | Champhai Division | 05.10.23 | 05.10.24 | 100% |  |  | 30 | 100% | 30 | Completed | Spot Quatation
431 | Const. of Ngaizawl to Neihdawn. | 20 | Champhai Division | 05.10.23 | 05.10.24 | 100% |  |  | 20 | 100% | 20 | Completed | Spot Quatation
432 | Const. of PCC Flooring from Methodist Church to C.Zoramlawma House at Vengthlang, Champhai. | 15 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
433 | Const. of PCC Flooring from Rengchhuani House to Nukami House at Rahsi Veng, Champhai. | 10 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
434 | Const. of Side Drain & Culvert from Lalringa House to Challiankunga House at Kahrawt, Champhai. | 7 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
435 | PCC Flooring from Hospital Veng Biak In to Joseph Paua at Vengsang, Champhai | 10 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
436 | PCC Flooring from Leitlahniam to Lumikawr at IB veng, Champhai. | 10 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
437 | Const. of PCC Flooring from Dawrkawn to MUP House at Hnahlan | 10 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
438 | Const. of PCC Flooring from Community Hall to Ramnunsanga House, N.Diltlang. | 1 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
439 | Const. of PCC Flooring of Ngur High School Road, Ngur. | 5 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
440 | Const. of PCC Flooring at PHC, Rabung. | 5 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
441 | Const. of Agriculture Link Road from Selam to Leiva River, Selam. | 24 | Champhai Division | 05.10.23 | 05.10.24 | 100% |  |  | 23.08 | 100% | 23.08 | Work .Completed | Spot Quatation
IMPROVEMENT OF ROADS WITHIN CHAMPHAI DIVISION.
442 | Patch repair and resurfacing of Diversion Road (North Side) near Tourist Lodge at Champhai (Vaihmun Diversion Road). | 8.93 | Champhai Division | 05.10.23 | 05.10.24 | 100% |  |  | 8 | 100% | 8 | Work Completed | Departmental
443 | Patch repair and Resurfacing of Sap Sakei Lamlian Bethel Boundary to Vaihmun. | 16.22 | Champhai Division | 05.10.23 | 05.10.24 | 100% |  |  | 13.6 | 100% | 13.6 | Work Completed | Departmental
444 | Patch repair and Seal Coating of Champhai District Hospital to Keifangtlang DC Office (Liability) | 10.63 | Champhai Division | 05.10.23 | 05.10.24 | 100% |  |  | 7.76 | 100% | 7.76 | Work Completed | Departmental
445 | Patch repair and Resurfacing of Approach Road to Sub-Jail (Aizawl) Road (Petrol Pump) District Jail. | 9.1 | Champhai Division | 05.10.23 | 05.10.24 | 100% |  |  | 5.34 | 100% | 5.34 | Work Completed | Departmental
446 | Patch repair and Resurfacing of Treasury Complex approach Road. Treasury Office. | 5.12 | Champhai Division | 05.10.23 | 05.10.24 | 100% |  |  | 4.11 | 100% | 4.11 | Work Completed | Departmental
IMPROVEMENT OF SAMTHANG TOWN ROAD.
447 | Const. of Flexible Pavement at Samthang (Courtyard of CM Commemorative Stone) |  | Champhai Division | 05.10.23 | 05.10.24 | 100% |  |  | 4.54 | 100% | 4.54 | Work Completed | Departmental
448 | Const. of Flexible Pavement at Samthang (Internal Road) | 19.8 | Champhai Division | 05.10.23 | 05.10.24 | 100% |  |  | 12.59 | 100% | 12.59 | Work Completed | Departmental
449 | Repair of Samthang Kawtchhuah repair by Flexible Pavement. |  | Champhai Division | 05.10.23 | 05.10.24 | 100% |  |  | 2 | 100% | 2 | Work Completed | Departmental
KOLASIB DIVISION :
Const. of Road from Kawnpui to Bukpui Road (Length = 10.00 Kms) under SASCI 2023-2024
450 | Formation Cutting of Kawnpui to Bukpui Link Road. | 112 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not under prioritised-I | Restricted Tender
451 | Formation Cutting of Lungdai Dursaleng Bamboo Link Road to Tuirial. | 50 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not under prioritised-I | Restricted Tender
452 | Formation Cutting of Chhimveng Thlanmual to Chemlui (Raichawm zau) Link Road. | 35 | Kolasib Division | 16.10.23 | 16.10.24 | 30% |  | 70% |  | 100% |  | Phy.Completed | Restricted Tender
453 | Formation Cutting of Zanlawn to Serlui Link Road | 30 | Kolasib Division | 16.10.23 | 16.10.24 | 50% |  | 20% |  | 70% |  | Work in progress | Restricted Tender
454 | Formation Cutting/Widening of Ramnghaka Huan Kawn to Rophum Kawn Link Road at Thingdawl. | 20 | Kolasib Division | 16.10.23 | 16.10.24 |  |  | 70% |  | 70% |  | Work in progress | Restricted Tender
455 | Formation Cutting of Kawnpui PHC to VC-II Field Approach Road. | 15 | Kolasib Division | 16.10.23 | 16.10.24 | 90% |  | 10% |  | 100% |  | Phy.Completed | Restricted Tender
456 | Formation Cutting of Bamboo Link Road, Lungmuat to Tuirial. | 10 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not under prioritised-I | Restricted Tender
457 | Const. of Retaining Wall at N.Chaltlang near UPC Biakin. | 8 | Kolasib Division | 16.10.23 | 16.10.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
458 | Const. of RCC Slab Extention at Kawnpui Field No-II | 35 | Kolasib Division | 16.10.23 | 16.10.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
Const.of PCC Pavementfrom Hmarveng - Venglai - Diakkawn in Kolasib Town Part "A" ( SASCI : 2023-2024 )
459 | Works within Hmarveng VC area at Different Location. | 32.93 | Kolasib Division | 16.10.23 | 16.10.24 | 16.6% |  |  |  | 16.6% |  | Under prioritised-I | Restricted Tender
460 | Works within Diakkawn VC area at Different Location. | 35.02 | Kolasib Division | 16.10.23 | 16.10.24 | 20% |  |  |  | 20% |  | Under prioritised-I | Restricted Tender
461 | Works within Khuangpuilam VC area at Different Location. | 13.8 | Kolasib Division | 16.10.23 | 16.10.24 | 33.33% |  |  |  | 33.33% |  | Not Under prioritised-I | Restricted Tender
462 | Works within New Diakkawn VC Area at Different Location. | 38.76 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not under prioritised-I | Restricted Tender
463 | Works within Project Veng VC Area at Different Location. | 45.49 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not under prioritised-I | Restricted Tender
464 | Works within Venglai East VC Area at Different Location. | 24.39 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not under prioritised-I | Restricted Tender
465 | Works within College Veng VC Area at Different Location. | 23.62 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not under prioritised-I | Restricted Tender
466 | Works within Tumpui Veng VC Area at Different Location. | 49 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not under prioritised-I | Restricted Tender
467 | Works within Electrict Veng VC Area at Different Location. | 22.22 | Kolasib Division | 16.10.23 | 16.10.24 | 75% |  |  |  | 75% |  | Under prioritised-I | Restricted Tender
468 | Works within Saidan Veng VC Area at Different Location. | 34.29 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not under prioritised-I | Restricted Tender
469 | Works within Tuitha Veng VC Area at Different Location. | 23.59 | Kolasib Division | 16.10.23 | 16.10.24 | 33.33% |  |  |  | 33.33% |  | Under prioritised-I | Restricted Tender
Const. of Rigid Pavement from Vairengte - Bilkhawthlir - Phainuam (SASCI : 2023-2024)
470 | Const. of Cement Concrete Pavement from Approach Road to Community Hall at Saiphai. | 35 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not under prioritised-I | Restricted Tender
471 | Const. of Panelled Concrete Pavement within Saipum Town. | 35 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not under prioritised-I | Restricted Tender
472 | Const. of PCC Flooring at N.Hlimen | 20 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not under prioritised-I | Restricted Tender
473 | Const. of PCC Flooring at Thingthelh | 10 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not under prioritised-I | Restricted Tender
474 | Const. of PCC Flooring at Rengtekawn. | 35 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not under prioritised-I | Restricted Tender
475 | Const. of PCC Flooring at N.Builum | 5 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not under prioritised-I | Restricted Tender
476 | Const. of PCC Flooring at Gosen Veng. | 5 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not under prioritised-I | Restricted Tender
477 | Const. of Panelled Concrete Pavement at Saihapui 'K' | 15 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not under prioritised-I | Restricted Tender
478 | Const. of Panelled Concrete Pavement at Bukvannei. | 15 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not under prioritised-I | Restricted Tender
479 | Const. of Panelled Concrete Pavement at N.Thinglian | 5 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not under prioritised-I | Restricted Tender
480 | Const. of Panelled Concrete Pavement at Buhchangphai | 20 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not under prioritised-I | Restricted Tender
481 | Const. of Panelled Concrete Pavement at N.Chhimluang | 10 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not under prioritised-I | Restricted Tender
482 | Const. of Panelled Concrete Pavement at N.Chawnpui | 10 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not under prioritised-I | Restricted Tender
483 | Const. of Panelled Concrete Pavement at Phaisen | 10 | Kolasib Division | 16.10.23 | 16.10.24 | [6 empty] | Not under prioritised-I | Restricted Tender
484 | Const. of Panelled Concrete Pavement at Phainuam | 35 | Kolasib Division | 16.10.23 | 16.10.24 | 100% |  |  | 33.54 | 100% | 33.54 | Completed | Restricted Tender
485 | Const. of Panelled Concrete Pavement at Saihapui 'V' | 10 | Kolasib Division | 16.10.23 | 16.10.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
486 | Const. of Panelled Concrete Pavement at Bilkhawthlir | 65 | Kolasib Division | 16.10.23 | 16.10.24 | 100% |  |  | 61.84 | 100% | 61.84 | Completed | Restricted Tender
487 | Const. of Panelled Concrete Pavement at Vairengte | 80 | Kolasib Division | 16.10.23 | 16.10.24 | 100% |  |  | 76.62 | 100% | 76.62 | Phy.Completed | Restricted Tender
488 | Const. of Formation Cutting at Phainuam to Bilkhawthlir, Buarchep Link Road. | 80 | Kolasib Division | 16.10.23 | 16.10.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
Const. of PCC Pavement from Hmarveng - Venglai - Diakkawn in Kolasib Town PART "B" (SASCI : 2023-2024)
489 | Works within Hmarveng VC Area at Different Location. | 4.72 | Kolasib Division | 16.10.23 | 16.10.24 | 100% |  |  | 4.56 | 100% | 4.56 | Completed | Spot Quatation
490 | Works within Venglai VC Area at Different Location. | 13.16 | Kolasib Division | 16.10.23 | 16.10.24 | 83.33% |  |  |  | 83.33% |  | Under prioritised-I | Spot Quatation
491 | Works within Diakkawn VC Area at Different Location. | 18.43 | Kolasib Division | 16.10.23 | 16.10.24 | 100% |  |  | 17.82 | 100% | 17.82 | Completed | Spot Quatation
492 | Works within Khuangpuilam VC Area at Different Location. | 15.05 | Kolasib Division | 16.10.23 | 16.10.24 | 100% |  |  | 14.55 | 100% | 14.55 | Completed | Spot Quatation
493 | Works within New Diakkawn VC Area at Different Location. | 19.58 | Kolasib Division | 16.10.23 | 16.10.24 | 100% |  |  | 18.91 | 100% | 18.91 | Completed | Spot Quatation
494 | Works within Project Veng VC Area at Different Location. | 25.06 | Kolasib Division | 16.10.23 | 16.10.24 | 100% |  |  | 24.21 | 100% | 24.21 | Completed | Spot Quatation
495 | Works within College Veng VC Area at Different Location. | 13.04 | Kolasib Division | 16.10.23 | 16.10.24 | 100% |  |  | 12.06 | 100% | 12.06 | Completed | Spot Quatation
496 | Works within Saidan Veng VC Area at Different Location. | 25.44 | Kolasib Division | 16.10.23 | 16.10.24 | 100% |  |  | 24.58 | 100% | 24.58 | Completed | Spot Quatation
Improvement of roads and Infrastructures at District Headquarters ;( Kolasib District) (SASCI : 2023-2024)
497 | Kolasib Town Roads: Resurfacing of Diakkawn Traffic Point to Police Station. | 15 | Kolasib Division | 31.10.23 | 29.02.24 | 100% |  |  | 10.06 | 100% | 10.06 | Phy.Completed | Departmental
498 | Patch Repair of Rengtekawn (NH-54) to Bawktlang (New Builum) 132 KV Sub-Station. | 31.5 | Kolasib Division | 31.10.23 | 29.02.24 | 100% |  |  | 17.51 | 100% | 17.51 | Phy.Completed | Departmental
499 | Patch Repair Serkhan to Bagha Road. | 69.5 | Kolasib Division | 31.10.23 | 29.02.24 | [6 empty] | Under Proritised-I | Departmental
500 | Repair of SPT Bridge over R.Chepte & Sesih and Repair of Diversion Road with WBM. | 8.5 | Kolasib Division | 31.10.23 | 29.02.24 | 100% |  |  | 8.02 | 100% | 8.02 | Completed | Departmental
PROJECT DIVISION - I
501 | Extension of Community Hall at Upper Republic | 53 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 39.82 |  |  | 100% | 39.82 | Phy.Completed
502 | Construction of RCC slab Dam veng YMA Hall | 4.83 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 4.81 |  |  | 100% | 4.81 | Completed
503 | Construction of Cequered tiles Near Local Council House Bungkawn Vengthar | 1.45 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 1.45 |  |  | 100% | 1.45 | Completed
504 | Construction of Saizahawla Tuikhur near R.Lalrinchhana Field Road | 7.72 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 7.68 |  |  | 100% | 7.68 | Completed
505 | Construction of RCC Structure at Electric Sub-Station, Khatla, Tlawng Road | 4.8 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 4.81 |  |  | 100% | 4.81 | Completed
506 | Laying of Chequered Tiles Between Zonghaka and Sk Thanga's House at Nursery | 2.12 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 2.11 |  |  | 100% | 2.11 | Completed
507 | Laying of Chequered Tiles tetween UPC (Mizoram) and RC Vanlalsawma (L) House at Nursery | 2.69 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 2.69 |  |  | 100% | 2.69 | Completed
508 | Construction of Chequered tiles near Khatla South Presbyterian | 1.43 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 1.43 |  |  | 100% | 1.43 | Completed
509 | Constrcution of Chequered tiles between J.Zangena House and Rinsanga Colney (L) near Khatla's Presbyterian Church | 0.98 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 0.49 |  |  | 100% | 0.49 | Completed
510 | Construction of Step Chequered tiles with Hand Railing near Khatla Pastor Quarter to J.Lianhlira House | 2.84 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 2.84 |  |  | 100% | 2.84 | Completed
511 | Renovation and linement of new Cemetary at Maubawk | 1.24 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 1.25 |  |  | 100% | 1.25 | Completed
512 | Renovation of Kanan Multipurpose Community Hall | 14.42 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 14.21 |  |  | 100% | 14.21 | Completed
513 | Renovation & Repair of Khatla Bazar Building | 3.86 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 3.86 |  |  | 100% | 3.86 | Completed
514 | Renovation of Mission Veng Health Clinic at Mission | 1.93 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 1.93 |  |  | 100% | 1.93 | Completed
515 | Construction of Anganwadi Centre-II, Aizawl | 4.79 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 4.79 |  |  | 100% | 4.79 | Completed
516 | Construction of Basketball Court at Dinthar | 52.99 | Project Division-I | 15.3.23 | 15.2.24 | 35% | 24.43 |  |  | 35% | 24.43 | Work in progress
517 | Construction of Basketball Court at Dinthar | 43.36 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 34.72 |  |  | 100% | 34.72 | Phy.Completed
518 | Construction of Basketball Court at Dinthar | 4.82 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 4.81 |  |  | 100% | 4.81 | Completed
519 | Renovation of Futsal Ground including Side Drain at Nursery veng | 4.4 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 4.4 |  |  | 100% | 4.4 | Contingencies of works
520 | Upgradation of Chief Minister Staff Quarter ( 5 nos of Quarters Phase-I | 193 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 191.07 |  |  | 100% | 191.07 | Completed
521 | Upgradation of Chief Minister Staff Quarter(5 nos of Qtrs Phase-II) | 95 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 78.89 |  |  | 100% | 78.89 | Phy.Completed | EPC
522 | Constructuction of Gov"t Staff Qtrs ( Block-C) at DIET Complex. | 544 | Project Division - I | 10.05.2023 | 10.05.2025 | 56% | 173.66 | 1% | 0.62 | 57% | 174.28 | Work in progress | EPC
523 | C/O Food Civil Supplies & Consumer Affairs 1500MTGodown at Sairang | 921 | Project Division - I | 7.4.23 | 7.4.26 | 22% | 147.29 | 2% |  | 24% | 147.29 | Work in progress | EPC
SASCI - 2023-2024 under Project Division - I
524 | Improvement of Government Buildings, High Court, Gov't Polytechnic & E-in-C PWD Office | 272.71 | Project Division - I |  |  | 75% |  |  | 14.4 | 75% | 14.4 | Work in progress | EPC
525 | Const. of Steps, Footpath, Bazar Shed, Hall Property House, Internal Road at Zemabawk, Thuampui, Zotlang, Chawnpui, Vaivakawn, Kanan. | 115 | Project Division - I |  |  | 78% |  | 11% | 52.55 | 89% | 52.55 | Work in progress | EPC
526 | Const. & Improvement of Public Buildings, YMA Zawlbuk at Chanmari West, Improvement of Electric Veng Hall | 188.29 | Project Division - I | 16.12.23 | 16.12.24 | 25.83% |  | 44.17% | 113.3 | 70% | 113.3 | Work in progress | EPC
527 | Const. & Improvement of Public Buildings. | 200 | Project Division - I | 16.12.23 | 16.12.24 | 80% |  | 10% | 62.72 | 90% | 62.72 | Work in progress | EPC
528 | Const. of Football Field at Maubawk | 325.99 | Project Division - I | 06.12.23 | 06.12.24 | [6 empty] | Not yet started | Item rate
529 | Const. of E-in-C PHED Office Phase-II | 169.67 | Project Division - I | 16.12.23 | 16.12.24 | 75% |  | 5% |  | 80% |  | Work in progress | EPC
530 | Const. of Tuikual 'S' Mini Sport Complex | 413.16 | Project Division - I | 16.12.23 | 16.12.24 | 22% |  | 5% | 20 | 27% | 20 | Work in progress | EPC
531 | Const. of DLAO Office at MINECO | 223.52 | Project Division - I | 16.12.23 | 16.12.24 | 25% |  | 2% | 30 | 27% | 30 | Work in progress | EPC
532 | Construction of Central Medical Warehouse at ZMC, Approach Road | 150 | Project Division - I | 16.12.23 | 16.12.24 | 10% |  | 10% | 45.64 | 20% | 45.64 | Work in progress | EPC
533 | Construction of Motor Parking at Kulikawn and Bethlehem Vengthlang | 40 | Project Division - I |  |  | 95% |  | 5% | 36.52 | 100% | 36.52 | Completed
HMUIFANG DIVISION : 2022-2023
534 | Improvement & Strengthening of Aibawk-Darlung Road for 4.000-14.000 Kmp in Mizoram for the year 2022-2023 | 547 | Hmuifang Division | 21.12.22 | 31.03.23 | 100% | 546.97 |  |  | 100% | 546.97 | Completed | Departmental
535 | Construction of Agriculture Link Road for Thingzam Zau, Tuirial Lui | 269.6 | Hmuifang Division | 15.12.22 | 14.05.23 | 100% | 249.72 |  |  | 100% | 249.72 | Completed | Departmental
536 | Contsruction of Upgradation of Aizawl-Thenzawl-Lunglei Road 5.00 kmp-100.00 Kmp | 206 | Hmuifang Division | 15.02.23 | 14.05.23 | 100% | 201.83 |  |  | 100% | 201.83 | Phy.Completed | Departmental
SASCI - 2023-2024 under Hmuifang Division.
537 | Strengthening of Aizawl-Thenzawl- Lunglei Road (83.00-100.00Kmp) | 1322 | Hmuifang division | 15.08.23 | 15.08.24 | 100% |  |  | 158.05 | 100% | 158.05 | Phy.Completed
538 | Const. of Agriculture Link Road to R.Mat from Chawilung, Lungsei, Samlukhai, Sialsuk. | 173.57 | Hmuifang division | 14.12.23 | 14.12.24 | 96% |  |  |  | 96% |  | Work in progress
539 | Improvement of Roads and Infrastructure at Aizawl City. | 30 | Hmuifang division | 14.12.23 | 14.12.24 | 100% |  |  | 23.45 | 100% | 23.45 | Phy.Completed
540 | Rigid Pavement of sinking area on Hualngohmun on Aizawl-Thenzawl -Lunglei Road. | 40 | Hmuifang division | 14.12.23 | 14.12.24 | 100% |  |  | 26.29 | 100% | 26.29 | Phy.Completed
541 | Completion of Approach Road to Upper Republic Thlanmual at Hualngohmun. | 2.5 | Hmuifang division | 14.12.23 | 14.12.24 | 100% |  |  | 2.4 | 100% | 2.4 | Phy.Completed
542 | Patch Repair of Maubuang approach road & Const. of Permanent Works at essential location on Maubuang. | 30 | Hmuifang division | 14.12.23 | 14.12.24 | 100% |  |  | 21.52 | 100% | 21.52 | Phy.Completed
KHAWZAWL DIVISION- 2022-2023
543 | Construction of Kawlkulh Bypass Road | 805 | Khawzawl Division | 01.02.23 | 30.06.23 | 22% | 485.45 |  |  | 22% | 485.45 | Work in progress | Restricted Tender
SASCI - 2023-2024 Under Khawzawl Division.
544 | Improvement & Strengthening of Vengthar Bazar toVengsang Presby. Church via Taidawnkawn at Khawzawl(Length: 7.50 KM) | 128.45 | Khawzawl Division | 03.10.23 | 03.04.24 | 100% |  |  | 89.05 | 100% | 89.05 | Phy.Completed | Spot Quotation
545 | Improvement of road at Chawngtlai - Biate - Ngopa- Khawhai & Pawlrang to Luangpawn | 166.5 | Khawzawl Division | 03.10.23 | 03.04.24 | 100% |  |  | 160.73 | 100% | 160.73 | Phy.Completed | Spot Quotation
546 | Const. of Agricultural Link road to Keltan Zau, Sihphai, Dawlzang, Lamzawl. (Length-8 Kms) | 101.1 | Khawzawl Division | 05.10.23 | 05.10.24 | 100% |  |  |  | 100% |  | Phy.Completed | Spot Quotation
547 | Improvement of roads and Infrastructures at District Headquarters ; Saiha, Lawngtlai, Lunglei, Hnahthial, Serchhip, Champhai, Khawzawl, Saitual, Kolasib and Mamit. | 168.7 | Khawzawl Division |  |  | 100% |  |  | 33.41 | 100% | 33.41% | Phy.Completed | Spot Quotation
548 | Const. of Pamchung to Tualcheng Road. Hliappui to Aiduzawl | 30 | Khawzawl Division | 05.10.23 | 05.10.24 |  |  | 100% |  | 100% |  | Phy.Completed | Restricted Tender
549 | Const. of Pamchung to Tualcheng Road. Ngaizawl to Neihdawn. | 20 | Khawzawl Division | 05.10.23 | 05.10.24 |  |  | 100% | 19.23 | 100% | 0.1923 | Completed | Restricted Tender
SAITUAL DIVISION : Under SASCI : 2023-2024
550 | Improvement of Khawlek - Ratu Road (Length = 6.00 Km) | 130 | Saitual Division |  |  | 35% |  |  | 43.45 | 35% | 43.45 | Work in progress
551 | Widening, Pavement & Const. of Culverts on 3rd Road from Sedaikawn to PWD Kawn, Saitual L=4.00Kms, Widening= 4.00Kms, Pavement=4.00Kms, Side Drain=1500mt, R/Wall= 15mt, Culvert= 6 Nos. | 137.52 | Saitual Division |  |  | 50% |  | 50% | 106.03 | 100% | 106.03 | Phy.Completed
552 | Rigid Pavement of Sakeibangla to ZMC via Thingsulthliah Road, PCC Pavement = 3.00Km, Side Drain = 2000mt, R/Wall = 10mt, Culvert = 2Nos. | 152.43 | Saitual Division |  |  | 66.6% |  |  | 51.24 | 66.6% | 51.24 | Work in progress
553 | Improvement of Roads and Infrastructures at District Headquarters, Saitual : Saitual Town Road : Pot Hole repair of Saitual - Saichal Road. | 15.5 | Saitual Division |  |  | 100% |  |  | 15.5 | 100% | 15.5 | Phy.Completed
TLABUNG DIVISION : SASCI 2023-2024
554 | Const. of PCC Pavement from Chawnpuikawn to Diplibagh Road with Additional Culverts & R/Walls Length=2Kms. | 129.77 | Tlabung Division | 14.12.23 | 14.12.24 | 10% |  |  |  | 10% |  | On going | Item Rate
555 | Const. of Agriculture Link Road from Sihphirtlang to Tuichawng River | 57.2 | Tlabung Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Completed Phy.Works | Item Rate
556 | [12 empty] | Item Rate
556 | Improvement of Borapansury - I to Borapansury- II Road upto Bangadesh Boundary. | 168.34 | Tlabung Division | 14.12.23 | 14.12.24 | 30% |  |  | 17.9 | 30% | 17.9 | On going | Item Rate
557 | Construction of RCC Pier for strenthening of Bailey Bridge over R.De on Phairuang to Bunghmun Road | 77 | Tlabung Division | 24.3.24 | 8.5.24 | 25% |  | 25% | 40.14 | 50% | 40.14 | Work in progress | Departmental
558 | Strengthening of Chawngte to Borapansury Road | 391.3 | Tlabung Division | 22.07.23 | 22.07.24 |  |  | 17.8% | 65.2 | 17.8% | 65.2 | Work in progress | Item rates
PROJECT DIVISION - II : 2022-2023
559 | Construction of Public Playground at Thenzawl (Sh: Const.of Public Playgound Galley of length 120 metre (6 block of 20 metre each including 3 (three) steps for sitting at Thenzawl | 25 | Project Division-II | 26.02.23 | 26.08.23 | 100% | 25 |  |  | 100% | 25 | Completed | Item Rate
560 | Construction of Community Hall at Chawilung (Sh: Construcytion of Steel Truss with dyna roofing) | 6 | Project Division-II | 24.02.23 | 24.04.23 | 100% | 6 |  |  | 100% | 6 | Completed | Item Rate
561 | Construction of Community Hall at Hualngohmun (Sh: Construction of Steel Truss with dyna roofing) | 8 | Project Division-II | 24.02.23 | 24.04.23 | 100% | 8 |  |  | 100% | 8 | Completed | Item Rate
562 | Construction of MUP House at Zamuang, Mamit District | 15 | Project Division-II | 26.02.23 | 26.06.23 | 100% | 15 |  |  | 100% | 15 | Completed | Item Rate
563 | Construction of Urinal Sheds (sh: Near Rambeiseia In, BBEC Pastor Qtrs, Pu Lalzama House, Lalaithai's House, C.Laltanpuia House, Darlak Peng at Tuidam, Urinal Sheds at Vengthar, W.Bunghmun, H/S Veng at Bunghmun, Near Baptist Church at New Eden, near Presbyterian Church at New Eden) | 5 | Project Division-II | 24.02.23 | 24.04.23 | 100% | 5 |  |  | 100% | 5 | Completed | Item Rate
564 | Construction of waiting Sheds (Sh: Const.of Waiting shed at Dilpeng, Kawrtethawveng 2. Repair of Waiting Shed at New Kawnpui Village 3. Construction of Buhfai Semna/Dahna Teireikam at Kananthar). | 7.5 | Project Division-II | 24.02.23 | 24.04.23 | 100% | 7.5 |  |  | 100% | 7.5 | Completed | Item Rate
565 | Construction of Pavement of Chequered Tiles (Sh: Near Pi Duhkungi House to Kawnghnuai at Tuidam 2. Ramrikawn to Pi Rinngaii In Kawng at Kawrtethawveng 3. Mualzawl (Hmarveng) to Arm Veng 4. KDZKT Road to Internal Road near Pi Nuntluangi In at Kawrtethawveng 5. Chequered Tile phah, step Repair approach to Tuikhuah tuikhur panna at Kawrtethawveng) | 9.5 | Project Division-II | 24.02.23 | 24.04.23 | 100% | 9.5 |  |  | 100% | 9.5 | Completed | Item Rate
566 | Construction of Tourist Lodge at Kawnpui | 50 | Project Division-II | 26.02.23 | 26.10.23 | 100% | 50 |  |  | 100% | 50 | Completed | Item Rate
567 | Construction of Futsal Ground at Kawnpui Chhimveng | 25 | Project Division-II | 25.02.23 | 25.06.23 | 88% | 12.5 |  | 12.5 | 100% | 25 | Completed | Item Rate
568 | Continuation of Public Playground at Serkhan | 15 | Project Division-II | 25.03.23 | 25.05.23 | 100% | 15 |  |  | 100% | 15 | Completed | Item Rate
569 | Construction of Community Hall at Hortoki | 70 | Project Division-II | 26.02.23 | 26.10.23 | 100% | 70 |  |  | 100% | 70 | Completed | Item Rate
570 | Continuation of Public Playground at Zanlawn | 15 | Project Division-II | 25.02.23 | 25.05.23 | 100% | 15 |  |  | 100% | 15 | Completed | Item Rate
571 | Continuation of Public Playground at Bualpui | 15 | Project Division-II | 25.02.23 | 25.05.23 | 100% | 15 |  |  | 100% | 15 | Completed | Item Rate
572 | Construction of Bazar Shed at Nisapui | 15 | Project Division-II | 25.02.23 | 25.05.23 | 100% | 15 |  |  | 100% | 15 | Completed | Item Rate
573 | Continuation of Futsal Ground at Lungdai | 25 | Project Division-II | 25.02.23 | 25.06.23 | 100% | 25 |  |  | 100% | 25 | Completed | Item Rate
SASCI : 2023-2024 Under Project Division - II
574 | Const. of Public Buildings: Const. of Community Hall at Melthum, Saikhamakawn, Chamring. | 104.5 | Project Division-II | 13.03.24 | 15.10.24 |  |  | 15.71% |  | 15.71% |  | Work in progress | Item Rate
575 | Const. of Public Playground at Thingdawl, Bukpui, N.Chaltlang, Hortoki, Serkhan and Lungmuat. | 185 | Project Division-II | 13.03.24 | 15.10.24 | 37.76% |  | 3.08% |  | 40.84% |  | Work in progress | Item Rate
576 | Retainoing wall ar various Places | 67.6 | Project Division-II | 13.03.24 | 15.10.24 | 20% |  |  |  | 20% |  | Work in progress | Item Rate
577 | Const. of Playground at Tuipuibari, Tuirum, Dapchhuah, New Mamit, Rajivnagar-I | 245 | Project Division-II | 13.03.24 | 15.10.24 | 58.12% |  |  |  | 58.12% |  | Work in progress | Item Rate
PROJECT DIVISION - III : (2023-2024 )
578 | Construction of Govt.Serchhip College (Sh: Adninistrative Block) | 650 | Project Division-III | 27.02.23 | 27.02.25 | 36% | 91.04 | 7% |  | 43% | 91.04 | work in progress | PWD Form-8
579 | Const. of Football ground and Volleyball court at Vapar, Selam, Tualcheng, Hnahlan, Hmunhmeltha | 203 | Project Division-III | 13.10.23 | 13.10.24 | 78% |  | 2% | 69.3 | 80% | 69.3 | work in progress | PWD Form-8
580 | Const. of Khawbung Futsal ground, Gallery, Roofing, Lighting & Laying of Artificial Turf | 255.5 | Project Division-III | 14.10.23 | 14.10.24 | 20% |  | 5% | 10 | 25% | 10 | work in progress | PWD Form-8
581 | Const. of Community Hall at Dulte & Chhawrtui | 271 | Project Division-III | 13.10.23 | 13.10.24 | 7% |  | 1% |  | 8% |  | work in progress | PWD Form-8
582 | Development of Community Centre at Zotlang, Champhai (Sh: Const. of Market Building cum Community Hall & Futsal Ground) | 215 | Project Division-III | 14.10.23 | 14.10.24 | 40% |  | 20% | 17 | 60% | 17 | work in progress | PWD Form-8
583 | Additional works for Const. of General Nursing Midwifery (GNM) hostel and Nursing Hostel at Champhai | 438 | Project Division-III | 13.10.23 | 13.10.24 | 60% |  | 20% | 82.59 | 80% | 82.59 | work in progress | PWD Form-8
584 | Const. of Public Playground at Keitum, Lungchhuan. | 250 | Project Division-III | 13.10.23 | 13.10.24 | 98% |  |  | 91.84 | 98% | 91.84 | work in progress | PWD Form-8
585 | Const. of Gov't. Building at Serchhip District (Sh: PWD Staff Quarters, Extension of Gov't. Serchhip Cillege and Kitchen Cum Dining at PTS, Thenzawl, Mizoram) | 362 | Project Division-III | 13.10.23 | 13.10.24 | 40% |  | 5% | 133.39 | 45% | 133.39 | work in progress | PWD Form-8
586 | Const. of Community Resource Center at Baktawng and Chhuanthar | 350 | Project Division-III | 13.10.23 | 13.10.24 | 80% |  | 20% | 114.74 | 100% | 114.74 | Phy.Completed | PWD Form-8
587 | Const. of Community Hall at Khawzawl Vengthar, Arro Village, khawzawl Dinthar and Khawhai South | 209 | Project Division-III | 13.10.23 | 13.10.24 | 75% |  | 10% | 71 | 85% | 71 | work in progress | PWD Form-8
LUNGLEI ROAD DIVISION -I, SASCI : 2022-2023
588 | Construction of pavement on Approach Road to Pialthleng at Lunglei District | 724.85 | Lunglei Road Division -I | 24.03.23 | 24.03.24 | 95% | 395.94 | 3% | 230.56 | 98% | 626.5 | Work in Progress | Restricted Tender
589 | Aizawl- Thenawl- Lunglei Road between Kanghmun 'S' and Kikawn, Lunglei Phase - I, (Sh: Group - A Between 100.00-120.00 Kmp) | 647.09 | Lunglei Road Division -I | 03.07.23 | 03.07.24 | 38% |  | 10% | 269.7 | 48% | 269.7 | Work in progress | Restricted Tender
590 | Aizawl- Thenawl- Lunglei Road between Kanghmun 'S' and Kikawn, Lunglei Phase - I, (Sh: Group - B Between 120.00-143.00 Kmp) | 658.16 | Lunglei Road Division -I | 26.06.23 | 26.06.24 | 94% |  |  | 503.34 | 94% | 503.34 | Work in progress | Restricted Tender
SASCI : 2023-2024 under Lunglei Road Division- I
591 | Improvement of Bazar Veng - College Veng - Venghlun at Lunglei District. | 130.05 | Lunglei Road Division -I | 24.12.23 | 23.12.24 | 79% |  |  | 52.61 | 79% | 52.61 | Work in progress
592 | Const. of Bamboo Link Road Phunchawngzau at Pukpui. | 165 | Lunglei Road Division -I | 24.12.23 | 23.12.24 | 7% |  | 2% |  | 9% |  | Work in progress
593 | Const. of Link Road from Vaisam Tlang - Zawlte - Phunchawng at Bunghmun. | 95.08 | Lunglei Road Division -I | 24.12.23 | 23.12.24 | 43% |  | 34% |  | 77% |  | Work in progress
594 | Improvement of Roads and Infrastructures at District Headquarters, Saiha, Lawngtlai, Lunglei, Hnahthial, Serchhip, Champhai, Khawzawl, Saitual, Kolasib and Mamit. | 14.13 | Lunglei Road Division -I |  |  |  |  | 100% | 11.01 | 100% | 11.01 | Phy.Completed
LUNGLEI ROAD DIVISION - II 2023-2024
595 | Const. of PCC Road to Public Playground at Zobawk South. | 71 | Lunglei Road Division-II |  |  | 14% |  | 29% |  | 43% |  | Work in progress
596 | Const. of Bamboo Link Road at Phunchawngzau, Pukpui (Group-B) | 85 | Lunglei Road Division-II |  |  | 75% |  |  |  | 75% |  | Work in progress
597 | Improvement of Hnahthial to Takam Tiau Road. | 198.34 | Lunglei Road Division-II |  |  | 83% |  |  |  | 83% |  | Work in progress
598 | Const. of Agriculture Link Road between Tuikhurhlu to Batluang at Pangzawl. | 97.09 | Lunglei Road Division-II |  |  | 100% |  |  |  | 100% |  | Phy.Completed
SIAHA DIVISION : 2022-2023
599 | Strengthening and Improvement of Kawlchaw to Serkawr Road | 318 | Siaha Division | 21.03.23 | 21.03.24 | 100% | 315.23 |  |  | 100% | 315.23 | Completed | Item rate Contract
600 | Improvement and Upgradation of Siaha to Thingsen Road upto NH 54B Junction (7.00km) | 778.53 | Siaha Division | 21.03.23 | 18.09.24 | 59.8% | 284.22 |  |  | 59.8% | 284.22 | Work in progress. | Item rate Contract
601 | Widening Road at Cheural - Lungzarhtum - Vartekkai - Sangau (11.50Km) in Mizoram for the year 2022-23 under SASCI Group-1. Widening of Road from BCM Church to BRTF Road via Middle School at Cheural Town Extension (L=1.800km) | 43.12 | Siaha Division | 09.04.23 | 30.9.23 | 87.15% | 32.75 |  |  | 87.15% | 32.75 | Work in progress | Item rate Contract
602 | Wifening Road at Cheural - Lungzarhtum - Vartekkai - Sangau (11.50Km) in Mizoram for the year 2022-23 under SASCI Group-2. Widening of Road from LIKBK Pastor Qtr to Pu H.Lalhranga House at Lungzarhtum (L=1.500km) | 44.54 | Siaha Division | 09.04.23 | 31.8.23 | 82.73% | 35.26 |  |  | 82.73% | 35.26 | Work in progress. | Item rate Contract
603 | Wifening Road at Cheural - Lungzarhtum - Vartekkai - Sangau (11.50Km) in Mizoram for the year 2022-23 under SASCI Group-3 Widening of Road from NEC road Junction to Vartekkai with construction of minor bridge (L=7.000km) | 207.27 | Siaha Division | 09.04.23 | 08.04.24 | 99.98% | 168.35 | 0.02% | 19.93 | 100% | 188.28 | Work in progress. | Item rate Contract
604 | Wifening Road at Cheural - Lungzarhtum - Vartekkai - Sangau (11.50Km) in Mizoram for the year 2022-23 under SASCI Group-4 Widening of Road from Tourist Lodge to Vengthar Field via SDO (C) Complex at Sangau (L=0.860km) | 20.07 | Siaha Division | 09.04.23 | 31.08.23 | 53.27% | 14.41 | 41.21% | 1.1 | 94.48% | 15.51 | Work in progress. | Item rate Contract
605 | Formation Cutting of Road to Sand Quarry at Bualpui 'NG' -Archhuang-Sangau-Lungpher (15.46Km) in Mizoram for the year 2022-23 under SASCI | 61.85 | Siaha Division | 09.04.23 | 31.8.23 | 97% | 57.88 |  |  | 97% | 57.88 | Work in progress. | Item rate Contract
606 | Formation Cutting of Road to Sand Quarry at Bualpui 'NG' -Archhuang-Sangau-Lungpher (15.46Km) in Mizoram for the year 2022-23 under SASCI | 49.63 | Siaha Division | 09.04.23 | 31.8.23 | 96.04% | 43.86 |  |  | 96.04% | 43.86 | Work in progress. | Item rate Contract
607 | Formation Cutting of Road to Sand Quarry at Bualpui 'NG' -Archhuang-Sangau-Lungpher (15.46Km) in Mizoram for the year 2022-23 under SASCI | 38.68 | Siaha Division | 09.04.26 | 8.7.23 | 90.05% | 26.72 |  |  | 90.05% | 26.72 | Work in progress. | Item rate Contract
608 | Formation Cutting of Road to Sand Quarry at Bualpui 'NG' -Archhuang-Sangau-Lungpher (15.46Km) in Mizoram for the year 2022-23 under SASCI | 125.86 | Siaha Division | 09.04.23 | 08.04.23 | 99.41% | 118.37 |  |  | 99.41% | 118.37 | Work in progress. | Item rate Contract
SASCI : 2023-2024 Under Siaha Division.
609 | Const. of Thiahra to Tuipui with Bridge Over River Tuisumpui (Phase-1) | 144.24 | Siaha Division | 20.10.23 | 31.03.25 | 13.75% |  | 25.42% | 55.6 | 39.17% | 55.6 | Work in progress. | Item rate Contract
610 | Improvement & Widening of Balu Road between BRTF Road at River Tuipui (Lopu) | 19.23 | Siaha Division | 20.10.23 | 31.03.25 | 100% |  |  | 18.24 | 100% | 18.24 | Phy.Completed | Item rate Contract
611 | Improvement & Widening of Balu Road between BRTF Road at River Tuipui (Chakhei) | 24.04 | Siaha Division | 20.10.23 | 31.03.25 | 100% |  |  | 22.19 | 100% | 22.19 | Phy.Completed | Item rate Contract
612 | Improvement & Widening of Balu Road between BRTF Road at River Tuipui (Iana and Tuipui) | 14.42 | Siaha Division | 20.10.23 | 31.03.25 | 100% |  |  | 12.34 | 100% | 12.34 | Phy.Completed | Item rate Contract
613 | Improvement of Siaha Town from Meisatla to Tlangkawn via College Veng (7.50 kms) | 269.23 | Siaha Division | 20.10.23 | 31.03.25 | 92.97% |  | 1.48% | 173.74 | 94.45% | 173.74 | Work in progress | Item rate Contract
614 | Improvement of Siaha Town from Meisatla to Tlangkawn via College Veng (7.50 kms) Tisopi-CC pavement. | 14.42 | Siaha Division | 20.10.23 | 31.03.25 | 100% |  |  | 14.4 | 100% | 14.4 | Work Phy.Completed | Item rate Contract
615 | Improvement of Siaha Town from Meisatla to Tlangkawn via College Veng (7.50 kms) College vaih-II and New Siaha East-II. | 28.85 | Siaha Division | 20.10.23 | 31.03.25 | 70.67% |  | 2.31% | 19.9 | 72.98% | 19.9 | Work in progress. | Item rate Contract
616 | Improvement of Siaha Town from Meisatla to Tlangkawn via College Veng (7.50 kms) Between Elim School and AR Ground.. | 19.23 | Siaha Division | 20.10.23 | 31.03.25 | 80.15% |  | 19.85% | 19.14 | 100% | 19.14 | Work in progress | Item rate Contract
617 | Improvement of Siaha Town from Meisatla to Tlangkawn via College Veng (7.50 kms) Between J.Vialu House to Siaha Vaihpi | 14.43 | Siaha Division | 20.10.23 | 31.03.25 | 100% |  |  | 14.4 | 100% | 14.4 | Work Phy.Completed | Item rate Contract
618 | Improvement of Siaha Town from Meisatla to Tlangkawn via College Veng (7.50 kms) Council vaih Cemetary. | 28.85 | Siaha Division | 20.10.23 | 31.03.25 | 100% |  |  | 16.7 | 100% | 16.7 | Work Phy.Completed | Item rate Contract
619 | Improvement of Siaha Town from Meisatla to Tlangkawn via College Veng (7.50 kms) K.Paichho House to Gilgal Church. | 11.54 | Siaha Division | 20.10.23 | 31.03.25 | 100% |  |  | 11.36 | 100% | 11.36 | Work Phy.Completed | Item rate Contract
620 | Improvement of Siaha Town from Meisatla to Tlangkawn via College Veng (7.50 kms) Horti Link Road. | 12.5 | Siaha Division | 20.10.23 | 31.03.25 | 100% |  |  | 8.66 | 100% | 8.66 | Work Phy.Completed | Item rate Contract
621 | Improvement of Siaha Town from Meisatla to Tlangkawn via College Veng (7.50 kms) Agri. Link Road. | 28.85 | Siaha Division | 20.10.23 | 31.03.25 | 100% |  |  | 22.25 | 100% | 22.25 | Work Phy.Completed | Item rate Contract
622 | Improvement of Siaha Town from Meisatla to Tlangkawn via College Veng (7.50 kms) Chhaolo.. | 19.23 | Siaha Division | 20.10.23 | 31.03.25 | 100% |  |  | 15.94 | 100% | 15.94 | Work Phy.Completed | Item rate Contract
623 | Improvement of Siaha Town from Meisatla to Tlangkawn via College Veng (7.50 kms) Noaotla | 24.04 | Siaha Division | 20.10.23 | 31.03.25 | 100% |  |  | 16.33 | 100% | 16.33 | Work Phy.Completed | Item rate Contract
624 | Improvement of Siaha Town from Meisatla to Tlangkawn via College Veng (7.50 kms) Thanngerh Agri. Link Road Thaltlang. | 28.85 | Siaha Division | 20.10.23 | 31.03.25 | 43.75% |  |  |  | 43.75% |  | Work in progress. | Item rate Contract
625 | Improvement of Siaha Town from Meisatla to Tlangkawn via College Veng (7.50 kms) Rawlbuk. | 9.62 | Siaha Division | 20.10.23 | 31.03.25 | 100% |  |  | 6.71 | 100% | 6.71 | Work Phy.Completed | Item rate Contract
626 | Improvement of Siaha Town from Meisatla to Tlangkawn via College Veng (7.50 kms) S.Lungpher | 9.62 | Siaha Division | 20.10.23 | 31.03.25 | 100% |  |  | 2.76 | 100% | 2.76 | Work Phy.Completed | Item rate Contract
627 | Improvement of Siaha Town from Meisatla to Tlangkawn via College Veng (7.50 kms) Lungtian-II | 9.62 | Siaha Division | 20.10.23 | 31.03.25 | 100% |  |  | 8.91 | 100% | 8.91 | Work Phy.Completed | Item rate Contract
628 | Improvement of Siaha Town from Meisatla to Tlangkawn via College Veng (7.50 kms) Vawmbuk | 9.62 | Siaha Division | 20.10.23 | 31.03.25 | 100% |  |  |  | 100% |  | Work Phy.Completed | Item rate Contract
629 | Improvement And Widening of Balu Road between BRTF Road at River Tuipui (8.50 kms) | 197.12 | Siaha Division | 20.10.23 | 31.03.25 | 91.54% |  | 8.46% | 155.53 | 100% | 155.53 | Phy.Completed | Item rate Contract
630 | Improvement And Widening of Balu Road between BRTF Road at River Tuipui (8.50 kms) Supha and Miepu | 24.04 | Siaha Division | 20.10.23 | 31.03.25 | 53.88% |  | 46.12% |  | 100% |  | Phy.Completed | Item rate Contract
631 | Improvement And Widening of Balu Road between BRTF Road at River Tuipui (8.50 kms) New Laty. | 19.23 | Siaha Division | 20.10.23 | 31.03.25 | 70% |  | 30% | 17.23 | 100% | 17.23 | Phy.Completed | Item rate Contract
632 | Improvement And Widening of Balu Road between BRTF Road at River Tuipui (8.50 kms) | 38.46 | Siaha Division | 20.10.23 | 31.03.25 | 100% |  |  | 34.41 | 100% | 34.41 | Phy.Completed | Item rate Contract
633 | Improvement And Widening of Balu Road between BRTF Road at River Tuipui (8.50 kms) Laki | 19.23 | Siaha Division | 20.10.23 | 31.03.25 | 100% |  |  | 17.47 | 100% | 17.47 | Phy.Completed | Item rate Contract
634 | Improvement And Widening of Balu Road between BRTF Road at River Tuipui (8.50 kms) Tisi | 19.23 | Siaha Division | 20.10.23 | 31.03.25 | 100% |  |  | 18.19 | 100% | 18.19 | Completed | Item rate Contract
635 | Improvement And Widening of Balu Road between BRTF Road at River Tuipui (8.50 kms) New Ahmypi & Old Ahmypi | 19.23 | Siaha Division | 20.10.23 | 31.03.25 | 100% |  |  | 19.23 | 100% | 19.23 | Completed | Item rate Contract
KAWRTHAH DIVISION : 2023-2024
636 | Strengthening of Hriphaw - Kolalian - Dulupcherra Road (14.00Kms) | 500 | Kawrthah Division | 16.12.23 | 15.12.24 | 70% |  | 1% | 308.91 | 71% | 308.9 | Work in progress | Restricted Tender
637 | Const. of W.Mualthuam - Belkhai Road (3.100 Kms) | 360 | Kawrthah Division | 16.12.23 | 15.12.24 | 100% |  |  | 81 | 100% | 81 | Phy.Completed | Restricted Tender
638 | Strengthening of Zamuang - Hriphaw - Kolalian - Dulupcherra (KDZKT) Road (28.00 Kmp) | 500 | Kawrthah Division | 16.12.23 | 15.12.24 | 75% |  |  | 154.48 | 75% | 154.48 | Work in progress | Restricted Tender
639 | Additional Works and Completion of Double Lane Bridge Over R.Teirei on Bairabi - Zamuang. | 1400 | Kawrthah Division | 16.12.23 | 15.12.24 | 25% |  |  | 51.81 | 25% | 51.81 | Work in progress | Restricted Tender
640 | Improvement of Roads & Infrastructure at District Headquarter : Saiha. | 10 | Kawrthah Division | 15.02.24 | 15.04.24 | 100% |  |  | 10 | 100% | 10 | Phy.Completed | Depart- mental
MAMIT DIVISION : 2023-2024
641 | Const. of Agri. Link Road from New W.Phaileng, Hnahva, Marpara North & Silsury East. (Length=7.00Kms) | 100 | Mamit Division | 06.12.23 | 06.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Item rate Contract
642 | Const. of Road from Parvatui to Zopui (Length=6.00Kms) | 135 | Mamit Division | 06.12.23 | 06.12.24 | 78.32% |  |  |  | 78.32% |  | Work in progress | Item rate Contract
643 | Const. of Link Road between Tuirum to Daifim to Khanthuam (Length= 7.00Kms) | 122.2 | Mamit Division | 06.12.23 | 06.12.24 | 66.07% |  |  |  | 66.07% |  | Work in progress | Item rate Contract
644 | Const. of Link Road Tuirum-Daifim - Nghalchawm, Damdiai - Damansora | 107.71 | Mamit Division | 06.12.23 | 06.12.24 | 91.75% |  |  |  | 91.75% |  | Work in progress | Item rate Contract
645 | Improvement of Road and Infrastuctures at District Headquarter Mamit. | 35 | Mamit Division | 06.12.23 | 06.12.24 | 60% |  |  |  | 60% |  | Work in progress | Depart- mental
SERCHHIP DIVISION :
646 | Improvement of roadsInfrastucture at District Headquarters Saiha, Lawngtlai, Lunglei, Hnahthial, Serchhip, Champhai, Khawzawl, Saitual, Kolasib, Mamit. | 85 | Serchhip Division | 7.10.23 | 30.10.23 | 100% |  |  | 85 | 100% | 85 | Completed | Item rate
647 | Construction of DS.Chawngtui-N.Vanlaiphai Road (0.00-14.800Kmp) Phase-II (Parmanent Works) | 295 | Serchhip Division | 15.2.23 | 27.10.24 | 80% | 155.73 |  | 71.79 | 80% | 227.52 | Work in progress | Item rate
648 | Construction of Strengthening of double lane BUGS Bridge Over R.Tuichang at 6.00Kmp on Keitum-Artahkawn Road (40R-70R) | 343 | Serchhip Division | 15.2.23 | 31.3.23 | 100% | 299.74 |  |  | 100% | 299.74 | Phy.Completed | Item rate
649 | Widening, Strengthening & Improvement of Sports Complex Approach Road at Serchhip (Length =1.50Kms) Widening= 1.500Kms Retaining Wall = 80.00 mP.C.C. Pavement = 1.500 Km Side Drain = 1500.00 m Culvert = 8 nos. | 380 | Serchhip Division | 05.10.23 | 05.10.24 | 50% |  |  | 69.99 | 50% | 69.99 | Phy.Completed | Item rate
650 | Additional works for Compietion of Strengthening of Chekawn - Artahkawn Road | 205 | Serchhip Division | 07.10.23 | 06.10.24 | 100% |  |  | 111.99 | 100% | 111.99 | Phy.Completed | Item rate
651 | Const. of Agriculturre Link road to River Lungva from Hriangtlang, Sialsir, Hlaizawl. | 351.5 | Serchhip Division | 05.10.23 | 05.10.24 | 37.59% |  |  |  | 37.59% |  | Work in progress | Item rate
LAWNGTLAI DIVISION :
Improvement of Thlengang to river Chhimtuipui Road : 2022-2023
652 | Construction of RCC Dock along with approach Slab | 23.31 | Lawngtlai Division | 11.05.23 | 10.4.24 | 100% | 23.31 |  |  | 100% | 23.31 | Completed | Spot Quotation
653 | Widening of Lawngtlai to Sahriluichhuah (Kalodyne River) Balu Road | 94.8 | Lawngtlai Division | 11.05.23 | 10.4.24 | 100% | 94.8 |  |  | 100% | 94.8 | Completed | Spot Quotation
654 | Improvement of Bethel veng to Chengkawllui road at College veng, Lawngtlai | 90.84 | Lawngtlai Division | 11.05.23 | 10.4.24 | 100% | 90.83 |  |  | 100% | 90.83 | Completed | Spot Quotation
Improvement of Thlengang to river Chhimtuipui Road :
655 | Formation cutting of Vathuampui to Mautlang Road | 70.47 | Lawngtlai Division | 11.05.23 | 10.4.24 | 100% | 70.42 |  |  | 100% | 70.42 | Completed | Spot Quotation
656 | Widening of Bungtlang 'S' to Saikhawthlir Road | 56.15 | Lawngtlai Division | 11.05.23 | 10.4.24 | 100% | 50.13 |  |  | 100% | 50.13 | Completed | Spot Quotation
657 | Widening of Hmawngbu to Kakichhuah Road | 61.99 | Lawngtlai Division | 11.05.23 | 10.4.24 | 100% | 61.97 |  |  | 100% | 61.97 | Completed | Spot Quotation
IMPROVEMENT OF DILTLANG TO CHAWNGTELUI ROAD
658 | Construction of Retaining Wall at Certain Location | 25.07 | Lawngtlai Division | 11.05.23 | 10.4.24 | 100% | 17.19 |  |  | 100% | 17.19 | Phy Completed | Mode of Contract
659 | Resurfacing of NH-54 to DTO Office (including courtyard) at Chanmari, Lawngtlai | 6.99 | Lawngtlai Division | 11.05.23 | 10.4.24 | 100% | 6.99 |  |  | 100% | 6.99 | Completed | Mode of Contract
660 | Construction of Minor Bridge between Khawmawi Bazar Veng to Khawmawi Vengthar | 34.48 | Lawngtlai Division | 11.05.23 | 10.4.24 | 100% | 34.47 |  |  | 100% | 34.47 | Completed | Mode of Contract
661 | Black topping of internal road at Lawngpuighat | 81.65 | Lawngtlai Division | 11.05.23 | 10.4.24 | 100% | 81.63 |  |  | 100% | 81.63 | Completed | Mode of Contract
662 | Construction of Playground approach road at Thingfal Mamte Veng | 19.49 | Lawngtlai Division | 11.05.23 | 10.4.24 | 100% | 19.49 |  |  | 100% | 19.49 | Completed | Mode of Contract
663 | Consultancy fee for Roads | 66.55 | Lawngtlai Division | 11.05.23 | 10.4.24 | 15% | 9.98 |  |  | 15% | 9.98 | Work in progress
664 | Consultancy Fee for Bridges | 106.39 | Lawngtlai Division | 11.05.23 | 10.4.24 | 70% | 74.68 |  |  | 70% | 74.68 | Work progress
SASCI : 2023-2024 Under Lawngtlai Division.
665 | Improvement of Approach Road to Kawrthindeng WRC Area. | 121.77 | Lawngtlai Division | 26.02.24 | 31.12.24 | 70% |  | 0.9% |  | 70.9% |  | Work progress | Restricted Tender
666 | Const. of Mautlang to Borogusuri | 117 | Lawngtlai Division | 26.02.24 | 31.12.24 | 90% |  | 0.38% |  | 90.38% |  | Work progress | Restricted Tender
National Highway Division - I (SASCI 2023 - 2024)
Improvement of Road from HN - 44A to Mamit and Rawpuichhip within Mamit in Mizoram for the year 2022-2023 under SASCI (Length=8.45 Km)
667 | Const. of Rigid/Concrete Pavement for New Approach road to Rawpuichhip from NH-44A | 56.89 | National Highway Division - I | 21.02.23 | 21.03.23 | 30% |  |  |  | 30% |  | Work in progress | Spot Quotation
668 | Const. of Humepipe Culvert at Ch:4.300kmp on NH-44A diverted road at Rawpuichhip Area (L=6.25, H=5m) | 9 | National Highway Division - I | 22.02.23 | 22.03.23 | 100% |  |  |  | 100% |  | Phy.Completed | Spot Quotation
Const. of Bamboo Link Road from Hmunpui to Mauhaklui & Tuidam approach Road in Mizoram. SASCI : 2023-2024
669 | Repair and Maintenance of Tuidam Approach Road. | 103 | National Highway Division - I | 15.12.23 | 15.12.24 | 100% |  |  | 103 | 100% | 103 | Completed | Restricted Tender
670 | Hmunpui Bamboo Link Road (Length = 8.00 Km) | 150 | National Highway Division - I | 15.12.23 | 15.12.24 | 97% |  | 3% | 150 | 100% | 150 | Completed | Restricted Tender
671 | Const. of Lengpui Advantist Road (Length = 60m) | 10 | National Highway Division - I | 15.12.23 | 15.12.24 |  |  | 100% | 10 | 100% | 10 | Completed | Restricted Tender
672 | Const. of Saiphai to Hortoki Road (13.800 Km) | 600 | National Highway Division - I | 15.12.23 | 15.12.25 |  |  | 10% |  | 10% |  | Amount deducted to Rs. 600 lakhs. New alignment being surveyed | Restricted Tender
673 | Improvement of Roads and Infrastructure at District Headquarters; Saiha, Lawngtlai, Lunglei, Hnahthial, Serchhip, Champhai, Khawzawl, Saitual, Kolasib, Mamit ; (Sh: Tuidam Approach Road) | 10 | National Highway Division - I | 31.03.23 | 31.03.24 | 100% |  |  | 10 | 100% | 10 | Completed | Depart- mental
674 | Improvement of Roads and Infrastructure at District Headquarters; Saiha, Lawngtlai, Lunglei, Hnahthial, Serchhip, Champhai, Khawzawl, Saitual, Kolasib, Mamit ; (Sh: Strengthening of Bailey Bridge over R. Teirei (Darlak) on NH-44A | 70 | National Highway Division - I | 31.03.23 | 31.03.24 | 100% |  |  | 70 | 100% | 70 | Completed | Depart- mental
675 | Improvement of Roads and Infrastructure at District Headquarters; Saiha, Lawngtlai, Lunglei, Hnahthial, Serchhip, Champhai, Khawzawl, Saitual, Kolasib, Mamit ; (Sh:Mamit to Bairabi Road) | 16 | National Highway Division - I | 31.03.23 | 31.03.24 | 100% |  |  | 16 | 100% | 16 | Completed | Depart- mental
676 | Improvement of Roads and Infrastructure at District Headquarters; Saiha, Lawngtlai, Lunglei, Hnahthial, Serchhip, Champhai, Khawzawl, Saitual, Kolasib, Mamit ; (Sh:Dampui Approach Road from NH-44A | 5 | National Highway Division - I | 31.03.23 | 31.03.24 |  |  | 100% | 5 | 100% | 5 | Completed | Depart- mental
677 | Improvement of Roads and Infrastructure at Aizawl City (Sh: Clearing, Grubbing of Roads Land and Jungle clearance of Saiphai Bamboo Plantation in Mizoram | 45 | National Highway Division - I | 31.03.23 | 31.03.24 | [6 empty] | Not yet started | Depart- mental
678 | Improvement of Roads and Infrastructure at Aizawl City (Sh: Work under National Highway Division-I) | 30 | National Highway Division - I | 31.03.23 | 31.03.24 |  |  | 100% | 30 | 100% | 30 | Completed | Depart- mental
679 | Improvement of Roads and Infrastructure at Aizawl City (Sh: Estimate for Const. of Lengpui Catholic School Road PCC) | 15 | National Highway Division - I | 31.03.23 | 31.03.24 | 100% |  |  | 15 | 100% | 15 | Completed | Depart- mental
NATIONAL HIGHWAY DIVISION - III SASCI : 2023-2024
680 | Const. of Rigid Pavement at essential places between 133.00Kmp to 147.00Kmp on NH-54 (Total Length =400.00 m) | 267 | National Highway Division - III | 25.7.23 | 13.11.23 | 100% |  |  | 261.21 | 100% | 261.21 | Completed | Departmental
681 | Upgradation of Saiphai, Zophai and Berhvakawn to Mualkhang Road. | 220 | National Highway Division - III | [8 empty] | Not yet started
682 | Improvement of Roads and Infrastructures at Aizawl City (Sh: Pot Hole filling and patches repair of NH-54(NH-6) for regular flow of traffic (Kawnpui - Sairang ) | 20 | National Highway Division - III | 18.9.23 | 15.11.23 | 100% |  |  | 19.99 | 100% | 19.99 | Completed | Departmental
QUALITY CONTROL RESEARCH & DEVELOPMENT DIVISION, ZUANGTUI : AIZAWL.
683 | Improvement of Government Building, High Court, Government Polytechnic & E-in-C, PWD Office (Sh: Const. of Barbet Wire fencing of PWD Complex at Zuangtui. | 23.3 | Quality Control Research & Development Division. |  |  | 100% |  |  |  | 100% |  | Phy.Completed | Spot Quotation
684 | Improvement of Government Building, High Court, Government Polytechnic & E-in-C, PWD Office (Sh: Const. ofBeily Bridge PartsGodown at PWD Complex, Zuangtui | 20 | Quality Control Research & Development Division. |  |  | 70% |  | 30% |  | 100% |  | Phy.Completed | Departmental
AIZAWL BUILDING DIVISION SASCI : 2023-2024
685 | Improvement of Roads and Infrastructures at Aizawl City under Aizawl Road South Division (Electrification of Refugee Relief Camp BSUP) | 5 | Aizawl Building Division | 18.10.23 | 11.11.23 | 100% |  |  | 5 | 100% | 5 | Completed | Departmental