## NABARD
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding: NABARD | [8 empty] | Month : February 2025
Sl. no | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Const.of BUSG Composite Bridges over R.Chepte on Bilkhawthlar to Saiphai Road | 508.45 | Kolasib Division | 24.6.19 | 24.12.20 | 45% | 128.5 |  |  | 45% | 128.5
2 | Const.of BUSG Composite Bridges over R.Sesih on Bilkhawthlar to Saiphai Road | 281.12 | Kolasib Division | 24.6.19 | 24.12.20 | 95% | 208.54 |  |  | 95% | 208.54
3 | Design & Construction of T-Beam Bridge Package-II at Bulung River (CH:10.20 KMP) | 1015.92 | Kolasib Division | 24.12.21 | 24.06.23 | 11% | 42.42 |  |  | 11% | 42.42 |  | Restricted tender
4 | Design & Construction of T-Beam Bridge Package-II at Damdiai River (CH:23.50 KMP) |  | Kolasib Division | 24.12.21 | 24.06.23 | 30.5% | 39.66 |  |  | 30.5% | 39.66 |  | Restricted tender
5 | Design & Construction of T-Beam Bridge Package-II at Chhimluangte River (CH:0.450 KMP) | 969.01 | Kolasib Division | 18.12.21 | 18.06.23 | 75% | 337 | 10% |  | 85% | 337 | Work in progress departmentally | Restricted Tender and Departmental
6 | Design & Construction of T-Beam Bridge Package-I at Dumkhel River (CH:5.50 KMP) |  | Kolasib Division | 18.12.21 | 18.06.23 | 27% | 115.75 |  |  | 27% | 115.75 | Work in progress | Restricted Tender and Departmental
7 | Const.of Meidum to Hortoki Road Phase -II (Km 9.100 to Km 26.000) SH: Earthworks and Permanent works from Km 9.100-Km 13.325) Package -I | 1087.32 | Kolasib Division | 24.12.21 | 24.06.23 | 100% | 1035.62 |  |  | 100% | 1035.62
8 | Const.of Meidum to Hortoki Road Phase -II (Km 13.325 to Km 17.500 SH: Earthworks and Permanent works from Km 13.325 to Km 17.500) Package -II | 1171 | Kolasib Division | 25.12.21 | 25.06.23 | 85.9% | 652.14 |  |  | 85.9% | 652.14
9 | Const.of Meidum to Hortoki Road Phase -II (Km 17.500 to Km 21.725 SH: Earthworks and Permanent works from Km 15.690 to Km 19.005) Package -III | 1422 | Kolasib Division | 18.12.21 | 18.06.23 | 88% | 1097.89 |  |  | 88% | 1097.89
10 | Const.of Meidum to Hortoki Road Phase -II (Km 21.725 to Km 26.000 SH: Earthworks and Permanent works from Km 19.005 to Km 22.360) Package -IV | 958.99 | Kolasib Division | 08.12.21 | 8.06.23 | 99.54% | 806.11 |  |  | 99.54% | 806.11
11 | Construction of Meidum to Hortoki Road Phase - II (Km 9.100 to 26.000): SH: Construction of Rigid pavement: Package-I (Km 9.100-Km 15.730) | 2390.08 | Kolasib Division | 03.08.22 | 03.08.23 | 15.71% | 549.95 | 6.29% |  | 22% | 549.95
12 | Construction of Meidum to Hortoki Road Phase - II (Km 9.100 to 26.000): SH: Construction of Rigid pavement: Package-II (Km 15.73-Km 22.36) | 2390.08 | Kolasib Division | 03.08.22 | 03.08.23 | 8% | 416.38 | 2% |  | 10% | 416.38
13 | Construction of link Road from NH-306 (PHE pump House) to R.Aitlang Lui Basin Crop Land : Length = 9.22 Kms | 447.75 | Kolasib Division | 12.08.22 | 12.08.23 | 100% | 431.65 |  |  | 100% | 431.65 | Works completed 16.96 lakh have been kept in D-III | Restricted Tender
14 | Construction of link Road from NH-306 (Vairengte) to Sabual Mual Arable Crop Land = 3.720 Kms | 402.78 | Kolasib Division | 13.08.22 | 13.08.23 | 95.92% | 364.32 |  |  | 95.92% | 364.32 |  | Restricted Tender
15 | Construction of Agriculture Link Road from NH-306 A to Buarchep Arable Crop Land : Length = 1.720 Kms | 168.3 | Kolasib Division | 27.08.22 | 27.08.23 | 100% | 168.32 |  |  | 100% | 168.32 | Work physically completed | Restricted Tender
16 | Construction of 24 Warehouses with associated Infrstructure in 23 locations in Mizoram under NABARD (Group-II Zuangtui/Sairang) | 440.97 | Project Division-I | 17.7.23 | 31.3.25 | 73% | 77.25 | 2% |  | 75% | 77.25 |  | Item Rate
17 | Construction of 24 Warehouses with associated Infrastructure in 23 locations in Mizoram Group-I (Scheme-NABARD) i) Construction of Warehouse and other amenities at Bairabi | 316.55 | Project Division-II | 17.07.23 | 31.03.25 | 90% | 78.74 | 2% | 16.9 | 92% | 95.64 | Work in progress | Item Rate
| ii) Construction of Warehouse and other amenities at Marpara | 235.73 | Project Division-II | 17.07.23 | 31.03.25 | 60% | 100.11 | 3% | 0.3 | 63% | 100.41 | Work in progress | Item Rate
| iii) Construction of Warehouse and other amenities at Sialsuk SC | 171.09 | Project Division-II | 17.07.23 | 31.03.25 | 49% | 54.25 | 3% |  | 52% | 54.25 | Work in progress | Item Rate
| iv) Construction of Warehouse and other amenities at Zawlnuam | 176 | Project Division-II | 17.07.23 | 31.03.25 | 50% | 86.47 | 3% |  | 53% | 86.47 | Work in progress | Item Rate
| v) Construction of Warehouse and other amenities at Kanhmun | 175.8 | Project Division-II | 17.07.23 | 31.03.25 | 53% | 56.17 | 2% | 33.96 | 55% | 90.13 | Work in progress | Item Rate
18 | Construction of 24 Warehouses with associated Infrastructure in 23 lacations in Mizoram Group-IX (Scheme-NABARD) i) Construction of Warehouse and other amenities at Phuldungsei | 175.81 | Project Division-II | 17.07.23 | 31.03.25 | 58% | 62.49 | 3% | 33.8 | 61% | 96.29 | Work in progress | Item Rate
19 | Construction of 24 Warehouses with associated Infrastructure in 23 locations in Mizoram under NABARD (Group-VII: Teikhang, Rabung & Dungtlang) | 336.53 | Project Division-III | 17.7.23 | 31.3.25 | 85% | 70 | 3% |  | 88% | 70 | Work in progress | PWD Form-8
20 | Construction of 24 Warehouses with associated infrastructure in 23 locations in Mizoram under NABARD (Group-V) Zohmun) | 170.99 | Project Division-IV | 17.07.23 | 17.07.25 | 46% | 36.91 | 2% | 11.59 | 48% | 48.5 | Work in progress. | Item Rate
21 | Improvement & Strengthening of Nalkawn - Chamdur Valley | 2616.41 | Lawngtlai Division | 09.08.19 | 31.12.24 | 68.69% | 1765.07 | 2.35% |  | 71.04% | 1765.07 | Work in progress. | Item Rate
22 | Const.of double lane built up Steel Girden Bridge over R.Teirei (Span -102m) at Ch.7.00 Kmp on Bairabi Zamuang Road | 1365.6 | Kawrthah Division | 5.8.17 | 30.6.24 | 100% | 1213.31 |  | 152.3 | 100% | 1365.61 | Work completed Upto sanctioned by NABARD. Work continued from SASCI funding | Contract after call of Restricted Tender
23 | Const.of double lane built up Steel Girden Bridge (Span-81m) over R.Langkaih on Mizoram-Tripura Border at Kanhmun | 2231.91 | Kawrthah Division | 6.4.18 | 30.11.24 | 44% | 932.03 | 5% |  | 49% | 932.03 |  | Contract after call of Restricted Tender
24 | Construction of Agriculture Link Road in Nothern Mizoram (Sh: Construction of Link Road from Saikhawthlir to R.Hnanglui Arable crop land, Length = 3.50 kms) | 362.02 | Kawrthah Division | 20.08.22 | 20.3.24 | 75% | 225.45 | 25% | 136.58 | 100% | 362.03 | Work completed | Contract after call of Restricted Tender
25 | Construction of Agriculture Link Road in Nothern Mizoram (Sh: Construction of Link Road from Chuhvel to R.Hnanglui Arable crop land, Length = 2.35 kms) | 284.76 | Kawrthah Division | 18.08.22 | 30.4.24 | 95% | 224.39 | 5% | 60.37 | 100% | 284.76 | Work completed | Contract after call of Restricted Tender
26 | Construction of Agriculture Link Road in Northern Mizoram (Sh: Construction of Link Road from from Thinghlun to Hriphaw through permanent crop length=9.570 kmp) | 385.61 | Kawrthah Division | 20.08.22 | 31.5.24 | 85% | 295.97 | 15% | 89.64 | 100% | 385.61 | Work completed | Contract after call of Restricted Tender
27 | Upgradation of Meidum to Hortoki Phase-I (0.0-9.10) | 4445 | NHD-III | 26.5.20 | 26.11.21 1st EOT=211 days (21.11.21-20.6.22) 2nd EOT=375 days (21.6.22-30.6.23) 3rd EOT =243 days (30.6.23-28.2.24) | 99% | 4094.91 |  |  | 99% | 4094.91 |  | Item Rate
28 | Construction of River Training Works for Protection of Tlawng River Bank at Bairabi Phase-I (Group-I) | 1111 | NHD-III | 17.10.22 | 17.10.23 1st EOT=166 days 18.10.23-31.3.24 | 100% | 279.17 |  |  | 100% | 279.17 |  | Item Rate
| Phase-I (Group-II) |  |  | 17.10.22 | 17.10.23 1st EOT=166 days 18.10.23-31.3.25 | 100% | 279.09 |  |  | 100% | 279.09 |  | Item Rate
| Phase-I (Group-III) |  |  | 17.10.22 | 17.10.23 | 100% | 216.65 |  |  | 100% | 216.65 |  | Item Rate
| Phase-I (Group-IV) |  |  | 17.10.22 | 17.10.23 | 100% | 246.7 |  |  | 100% | 246.7 |  | Item Rate
| Construction of river training works for protection of Tlawng river bank at Bairabi Phase-I |  |  | Departmental |  |  | 29.75 |  | 2.15 |  | 31.9 | Contingency
29 | Construction of MDR from Khamrang (Dilsei) to Selesih (Sh: Construction of approach road to Mualkhang Village) | 14529.27 | NHD-III | 08.02.21 | 08.08.22 | 100% | 122.25 |  |  | 100% | 122.25 |  | Item Rate
30 | Construction of Road from Khamrang to Selesih Phase-II Group-1 (11/00 to 22/00Km) |  |  | 8.11.21 | 8.5.23 1st EOT=210 days (wef 09.05.23- 04.12.23 | 32.31% | 664.75 |  |  | 32.31% | 664.75 |  | Item Rate
31 | Construction of Road from Khamrang to Selesih Phase-II Group-2 (22/00 to 25/00Km) |  |  | 22.11.21 | 22.11.22 1st EOT=90days (upto -20.02.23) 2nd EOT=90 days (wef 21.2.23-21.5.23) 3rd EOT = 90 days(22.5.23-19.8.23) | 30.25% | 244.82 |  | 116.45 | 30.25% | 361.27 |  | Item Rate
32 | Construction of Road from Khamrang to Selesih Phase-II Group-3 (25/00 to 28/00Km) |  |  | 11.11.21 | 11.11.22 1st EOT=104 days (upto -24.02.23) 2nd EOT=90 days (wef 10.2.23-11.5.23) 3rd EOT = 90 days(wef 12.5.23-9.8.23) | 16.87% | 262.85 |  |  | 16.87% | 262.85 |  | Item Rate
33 | Construction of Road from Khamrang to Selesih Phase-II (Sh: Construction of Rigid Pavement from 11/00 to 19/00 Kmp=8.00 Kms) Group A |  |  | 26.8.23 | 26.8.25 | [7 empty] | Item Rate
34 | Construction of Road from Khamrang to Selesih Phase-II (Sh: Construction of Rigid Pavement from 19/00 to 28/00 Kmp=9.00Kms) Group B |  |  | 26.8.23 | 26.8.25 | [7 empty] | Item Rate
35 | Construction of road from Khamrang to Selesih Phase-II |  |  | Departmental |  |  | 1.18 |  |  |  | 1.18 | Contingency
36 | Construction of MDR from Khamrang-Dilsei to Selesih (Phase-I) (Length = 11.00 Kms) Group-A (0/00 to 3/600Km) | 6583.18 | NHD-III | 8.02.21 | 8.8.22 1st EOT=184 days (upto 08.02.23, 2nd EOT=150 days (upto 08.07.23) | 65.35% | 388.92 |  |  | 65.35% | 388.92 |  | Item Rate
37 | Construction of road from Khamrang to Selesih Phase-I (Length = 11.00 Kms) Group-B (3/60 to 7/200Km) |  | NHD-III | 8.02.21 | 8.8.22 1st EOT=184 days (upto 08.02.23, 2nd EOT=150 days (wef 09.02.23-08.07.23) | 55.75% | 434.62 |  |  | 55.75% | 434.62 |  | Item Rate
38 | Construction of road from Khamrang to Selesih Phase-I (Length = 11.00 Kms) Group-C (7/200 to 11/00Km) |  | NHD-III | 8.02.21 | 8.8.22 1st EOT=184 days (upto 08.02.23, 2nd EOT=150 days (wef 09.02.23-08.07.23) | 47.78% | 299.51 |  |  | 47.78% | 299.51 |  | Item Rate
39 | Construction of road from Khamrang to Selesih Phase-I (Sh: Construction of Rigid Pavement from 7/00 to 11/00 Kmp = 4.00 Kms) |  | NHD-III | 16.8.22 | 16.02.24 | 3.8% | 152.36 |  |  | 3.8% | 152.36 |  | Item Rate
40 | Constuction of road from Khamrang to Selesih Phase-I |  | NHD-III | Departmental |  |  | 189.75 |  | 0.52 |  | 190.27 | Contingency
41 | Const.of Double Storied PHC at Lungsen | 267.15 | Lunglei Building Project Division | 10.2.22 | 10.2.24 | 100% | 267.15 |  |  | 100% | 267.15 | Civil & I/E works completed handover in process | Restricted Tender
42 | Const.of Infrastructure Support fro School of Agricultural Science at Hnahthial: Phase-II | 685 | Lunglei Building Project Division | 08.04.23 | 08.04.25 | [5 empty] | 198.7 | Work in progress | Restricted Tender
| i) Boys Hostel |  | Lunglei Building Project Division | 08.04.23 | 08.04.25 | 53% | 142.44 | 10% | 56.26 | 63% |  |  | Restricted Tender
| ii) Staff Quarter Type-III |  | Lunglei Building Project Division | 08.04.23 | 08.04.25 | 34% |  | 10% |  | 44%
| iii) Staff Quarter Type-II |  | Lunglei Building Project Division | 08.04.23 | 08.04.25 | 52% |  | 10% |  | 62%
| iv) Guest House |  | Lunglei Building Project Division | 08.04.23 | 08.04.25 | 53% |  | 10% |  | 63%
43 | 1. Construction of 24 Warehouses with associated Infrastructure in 23 localities in Mizoram under NABARD Gr-III: Siaha, Chapui, Bungtlang South
| 1) Siaha SDC | 509.86 | Lunglei Building Project Division | 17.07.23 | 31.3.25 | 43% | 80.76 | 7% |  | 80% | 80.76 | Work in progress | Restricted Tender
| 2) Chapui | 217.02 | Lunglei Building Project Division | 17.07.23 | 31.3.25 | 42% | 71.03 | 3% |  | 45% | 71.03 | Work in progress
| 3) Bungtlang South | 180.45 | Lunglei Building Project Division | 17.07.23 | 31.3.25 | 80% | 59.84 | 5% |  | 85% | 59.84 | Work in progress
| 2. Gr-IV: Lungpher | 216.98 | Lunglei Building Project Division | 17.07.23 | 31.3.25 | 92% | 116.58 | 8% |  | 100% | 116.58 | Work in progress | Restricted Tender
3. Gr-VI: South Vanlaiphai and Vawmbuk
| 1) South Vanlaiphai | 206.2 | Lunglei Building Project Division | 17.07.23 | 31.3.25 | 50% | 63.98 | 5% |  | 55% | 63.98 | Work in progress | Restricted Tender
| 2) Vawmbuk | 217.1 | Lunglei Building Project Division | 17.07.23 | 31.3.25 | 60% | 51.83 | 10% |  | 70% | 51.83 | Work in progress
4. Gr-VIII: Hnahthial, Thingsai. Cherhlun and Siata
| 1) Hnahthial | 217.1 | Lunglei Building Project Division | 17.07.23 | [7 empty] | Work cannot be started till today as the proposed new site which was donated by Thiltlang VC was covered with teak plantation by Forest Department as Thiltlang VC lends these areas to Forest Department long time back. Clearance of these areas from this plantation needs to be work out following Government procedures so that construction of this building | Restricted Tender
| 2) Thingsai | 177.51 | Lunglei Building Project Division | 17.07.23 | 31.3.25 | 37% | 41.18 | 5% | 1.16 | 42% | 42.34 | Work in progress
| 3) Cherhlun | 93.26 | Lunglei Building Project Division | 17.07.23 | 31.3.25 | 40% |  | 8% |  | 48% |  | Work in progress
| 4) Siata | 217.09 | Lunglei Building Project Division | 17.07.23 | 31.3.25 | 73% | 27.26 | 12% | 74.43 | 85% | 101.69 | Work in progress
5. Gr-X: Vaseikai and Tlabung
| 1) Vaseikai | 260.81 | Lunglei Building Project Division | 17.07.23 | 31.3.25 | 60% | 70.31 | 5% |  | 65% | 70.31 | Work in progress | Restricted Tender
| 2) Tlabung | 102.29 | Lunglei Building Project Division | 17.07.23 | 31.3.25 | 32% | 22.36% | 5% |  | 37% | 22.36 | Work in progress
44 | Strengthening & Improvement of W.Phaileng to Marpara Road (00.00-30.00Kmp) Package-I | 1854.59 | Mamit Division | 15.03.23 | 15.03.25 | 29% | 616.84 | 34.5% |  | 63.5% | 616.84
45 | Strengthening & Improvement of W.Phaileng to Marpara Road (30.00-80.00Kmp) Package-II | 4778.8 | Mamit Division | 15.03.23 | 15.03.25 | 30% | 983.16 | 14.51% |  | 44.51% | 983.16
46 | Improvement of Chawngte to Borapansuri Road (0.00-30.00Kmp) | 3987 | Tlabung Division | 15.3.23 | 15.3.25 | 18% | 174.82 | 1.9% | 201.15 | 19.9% | 375.97 | Work in progress | Item rate
47 | Construction of Galvanised steel concrete composite Bridge over Borapansuri Road | 635.69 | Tlabung Division | 31.5.24 | 31.5.26 | 1% |  |  |  | 1% |  |  | Item rate
48 | Improvement of Ramrikawn to NH-54 via Sakawrtuichhun Road (3.00 Kmp-7.50 Kmp = 4.50 Km) | 432.65 | Aizawl Road North Division |  |  | 100% | 115.72 |  | 60.82 | 100% | 176.54 | Phy. Completed | Dept.
49 | Construction of Galvanised Steel Truss Bridge over Mat-River on Hnahthial to Haulawng Road via Zotui (Span-70.00m) | 1447.93 | Lunglei Road Division - II | 01.04.24 | 01.04.26 | 1.5% |  | 3.5% |  | 5% |  |  | Open Tender
50 | Upgradation of Laki to Vahai Road from Ch.0.00 Km to Ch.15.56Km | 1809.44 | Siaha Division | 28.06.24 | 27.06.26 | 17.88% |  | 11.65% | 294.92 | 29.53% | 294.92 | Work in progress | Item rate contract

## NEC
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding: NEC | [8 empty] | Month : February 2025
Sl. no | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the Month |  | Overall cumulative achievement |  | Remarks | Mode of Contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Lunglei Market and Trade Centre at Electric/Chanmari Veng, Lunglei (NEC) | 1403.4 | Lunglei Building Project Division | 25.08.22 | 30.09.25 | 70% | 562.61 | 2% |  | 72% | 562.61 | Work in progress | Restricted Tender
2 | Construction of Mara Handloom & Weaving Centre at Council Vaih, Saiha | 439.41 | Lunglei Building Project Division | 13.04.22 | 13.04.24 | 97% | 348.26 | 3% | 47.2 | 100% | 395.46 | Work in progress | Restricted Tender
3 | Improvement & Upgradation of KDZKT Road (0.00 - 88.400Kmp) | 18327.42 | Kawrthah Division | 27.4.15 | 4.6.18 | 100% | 18290 | - |  | 100% | 18290 | Work Phy.Completed on 31.12.21 SMS of R.Revised estimate is being awaited for financial closure | Contract after call of Tender
4 | Const.of Patient Lodging at Mawdiangdiang near NEIGHRIMS, Shillong | 419.67 | Project Division-I | 9.9.21 | 31.7.24 | 72% | 167.87 | 3% |  | 75% | 167.87 | Revised Target date of completion 9.9.25 | EPC
5 | Infrastructure Development of Biotechnology Cell in Mizoram (C/O Building at MINECO) | 188.66 | Project Division-I | 10.7.23 | 10.1.25 | 42% | 69.55 | 2% |  | 44% | 69.55 | Work in progress | Item rate
6 | Establishment of Central Medical Warehouse at Aizawl, Mizoram | 1101.11 | Project Division-I | 14.8.23 | 14.8.25 | 33% | 140.19 | 2% |  | 35% | 140.19 | Extended to 22.10.25 | Item rate
7 | Construction of Aizawl Institute of Arts & Music for the NER, Tuivamit Tlang, Aizawl | 590.23 | Project Division-I | 4.9.23 | 4.9.25 | 65% | 230.1 |  |  | 65% | 230.1 |  | Item rate
8 | Construction of Veterinary Information and Resource Centre at Aizawl | 339.25 | Project Division-I | 25.9.23 | 25.9.25 | 58% | 124.1 |  |  | 58% | 124.1 |  | Item rate
9 | Construction of 60 Bedded Intern Hostel at ZMC, Falkawn | 679 | Project Division-II | 01.09.22 | 01.05.24 | 80% | 509.25 | 5% |  | 85% | 509.25 | Work in progress. EOT awaited. Expenditure has been booked in PFMS. However, due to Technical issue expensiture couldnot be finished | Item Rate
10 | Construction of Market Building at West Phaileng, Mamit District | 278.25 | Project Division-II | 22.08.23 | 22.08.25 | 39% | 60 | 4% |  | 43% | 60 | Work in progress | Item Rate
11 | Creation of Passion fruit Processing unit at Cold Storage, New Champhai Mizoram | 185.36 | Project Division-III | 23.09.22 | 24.3.24 | 100% | 185.39 |  |  | 100% | 185.39 | As per revised sanction by NEC, only civil construction work is under PWD Work completed | PWD Form-8
12 | Construction of Zomi cultural Centre and preservation of historical sites at Champhai | 478.69 | Project Division-III | 26.09.22 | 26.09.24 | 100% | 225.84 |  |  | 100% | 225.84 | Work completed | PWD Form-8
13 | Construction of Biate Tea Tourism Circuit & Nature Camp in Mizoram | 369.62 | Project Division-III | 9.10.23 | 9.10.25 | 93% | 143.52 | 0.5% |  | 93.5% | 143.52 | Work in progress | PWD Form-8
14 | Forstering Industry, Innovation, Infrastructure and Livelihood Oppurtunities (SDG 9) at Lunglen-1 and Sialhawk, Mizoram and strengthening of Food Testing Laboratory (Sh: Construction of Pineapple precessing plant building at Sialhawk) | 65.7 | Project Division-III | 12.10.23 | 12.10.25 | 99% |  | 1% |  | 100% |  | Work in progress | PWD Form-8
15 | Establishing Mizo cultural heritage centre for protecting the historical and natural heritage of Mizo at Kawlri, Serchhip | 486.47 | Project Division-III | 16.2.24 | 16.2.26 | 22% |  | 3% |  | 25% |  | Work in progress | PWD Form-8
16 | Construction of Community Hall at Bethel Veng Champhai | 1443.75 | Project Division-III | 16.2.24 | 16.2.26 | 18% |  | 5% |  | 23% |  | Work in progress | PWD Form-8
17 | Upgradation od Sports Infrastructure of Ngopa Playground at Saitual District Mizoram | 394.15 | Project Division-III | [8 empty] | Newly sanctioned. Under tender | PWD Form-9
18 | Construction of AYUSH Development Centre at MINECO Aizawl | 264.16 | Project Division-IV | 7.12.22 | 17.08.24 | 70% | 198.12 | 5% |  | 75% | 198.12 | Work in progress. EOT application in progress | Item Rate
19 | Etablishment of Sinlung Hills Council Administrative Complex (Const.of Sinlung Hills Administrative Building at Sakawrdai) | 381.99 | Project Division-IV | 8.11.21 | 31.07.24 | 89% | 210.4 | 1% |  | 90% | 210.4 | Work in progress. Bill withheld amount Rs.5.00 lakh. EOT application in progress. Materials supply hindered due to adverse road conditions | Item Rate

## PMGSY
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding: PMGSY | [8 empty] | Month : February 2025
Sl. no | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Diblibagh to Chengkawllui Road (0.000-19.520)Kmp | 2798.82 | Tlabung Division | 17.6.19 | 17.6.20 | 84% | 1509.2 | 3.9% |  | 87.9% | 1509.2 |  | Item Rate
2 | Diblibagh to Sugarbasora Road (0.000-2.000)Kmp | 305.81 | Tlabung Division | 28.9.18 | 28.9.19 | 75.4% | 211.07 | 24.6% |  | 100% | 211.07 | Completed Phy.Works Extension granted up to Dt.31.03.23 | Item Rate
3 | Diblibagh to Sugarbasora Road Group B (2.000-4.760)Kmp | 373.19 | Tlabung Division | 22.9.18 | 22.9.19 | 100% | 210.96 |  |  | 100% | 210.96 | Completed Phy.Works Extension granted up to Dt.31.03.23 | Item Rate
4 | Upgradation & Maintenance of Phairuang - Thenhlum (Upto Bolia) Road (0.00 - 48.770 Kmp) | 5440.31 | Tlabung Division | 30.8.24 | 02.03.26 | 12% |  |  |  | 12% |  |  | Item Rate
5 | Upgradation & Maintenance of Phairuang to Thenhlum (Bolia to Thenhlum) Road (Ch:0.00-16.23 Km) | 1169.62 | Tlabung Division | 29.8.24 | 01.03.26 | 13% |  | 0.2% |  | 13.2% |  |  | Item Rate
6 | Construction & Maintenance of Sairang - Lengte-Nghalchawm (PMGSY) Road | 991.9 | NHD-I | 19.12.20 | 31.3.24 | 100% | 961.71 |  |  | 100% | 961.71 | Completed | Item rate contract
7 | Construction and Maintenance of E.Phaileng-Suangpuilawn Road Gr.A(0.000-6.000Kmp) (Sh: Widening, Culvert & R/Wall and Construction of road using flexible pavement) | 877.11 | Saitual Division | 19.12.20 | 19.12.22 | 100% | 600.18 |  | 15.13 | 100% | 615.31 | EoT Dt.15.10.23
8 | Construction and Maintenance of E.Phaileng-Suangpuilawn Road Gr-B (6.000-11.000Kmp) (Sh: Widening, Culverts & R/Wall and Construction of Road using flexible pavement) | 916.53 | Saitual Division | 19.12.20 | 19.12.22 | 100% | 211.36 |  |  | 100% | 211.36 | EoT Dt.31.3.24
9 | Construction and Maintenance of E.Phaileng-Suangpuilawn Road Gr-C (11.000-16.000Kmp) (Sh: Widening, Culverts & R/Wall and Construction of Road using flexible pavement) | 807.85 | Saitual Division | 15.8.20 | 15.8.22 | 100% | 807.24 | - |  | 100% | 807.24 | EoT Dt.31.03.24
10 | Construction and Maintenance of E.Phaileng-Suangpuilawn Road Gr-D (16.000-22.000Kmp) (Sh: Widening, Culverts & R/Wall and Construction of Road using flexible pavement) | 852.8 | Saitual Division | 01.01.21 | 01.01.23 | 100% | 787.09 |  |  | 100% | 787.09 | EoT Dt.28.10.23
11 | Construction and Maintenance of E.Phaileng-Suangpuilawn Road Gr-E (22.000-28.000Kmp) (Sh: Widening, Culverts & R/Wall and Construction of Road using flexible pavement) | 830.41 | Saitual Division | 01.01.21 | 01.01.23 | 100% | 632.27 | - | - | 100% | 632.27 | EoT Dt.30.3.24
12 | Construction and Maintenance of E.Phaileng-Suangpuilawn Road Gr-F (28.000-34.000Kmp) (Sh: Widening, Culverts & R/Wall and Construction of Road using flexible pavement) | 1133.61 | Saitual Division | 10.02.20 | 10.02.22 | 100% | 1128.61 | - |  | 100% | 1128.61 | EoT Dt.31.12.22
13 | Construction and Maintenance of E.Phaileng-Suangpuilawn Road Gr-G 34.000-40.000Kmp) (Sh: Widening, Culverts & R/Wall and Construction of Road using flexible pavement) | 1160.95 | Saitual Division | 6.01.20 | 6.01.22 | 100% | 657.03 |  | 86.84 | 100% | 743.87 | EoT Dt.4.11.23
14 | Construction and Maintenance of E.Phaileng-Suangpuilawn Road Gr-H 40.000-46.000Kmp) (Sh: Widening, Culverts & R/Wall and Construction of Road using flexible pavement) | 1099.24 | Saitual Division | 6.01.20 | 6.01.22 | 100% | 619.07 |  |  | 100% | 619.07 | EoT Dt.18.7.23
15 | PMGSY-III
16 | Upgradation & Maintenance of Saitual to Phullen Road (0.000 - 18.130 Kmp) | 1830.83 | Saitual Division | 05.09.24 | 05.03.26 | 3.05% |  | 0.25% |  | 3.3% |  | Ongoing
17 | Construction and Maintenance of Bunghmun-W.Mualthuam Road (Sh: Cell filled Concrete Road) (0.00-13.500 Kmp) | 955.77 | Kawrthah Division | 27.11.17 | 16.9.22 | 100% | 918.23 | - | - | 100% | 918.23 | Works under maintenance from 16.9.22 | Contract after call of Tender
18 | Construction and Maintenance of Bunghmun to Thaidawr Road (0.00 Kmp-8.90 Kmp) | 745.77 | Kawrthah Division | 17.6.19 | 16.9.22 | 100% | 720.72 | - | - | 100% | 720.72 | Works under maintenance from 16.9.22 | Contract after call of Tender
19 | Construction of Upgradation and Maintenance of Moroicherre to Lushaicherre (0.00-9.84Kmp) | 669.69 | Kawrthah Division | 30.8.24 | 2.3.26 | 10% |  |  |  | 10% |  | Contract after call of Tender | Contract after call of Tender
20 | Upgradation & Maintenance of Bairabi to Zamuang Road (Ch:0.00 to 24.20Kmp) | 2312.39 | Kawrthah Division | 29.08.24 | 1.03.26 | 10% |  |  |  | 10% |  | Contract after call of Tender | Contract call of Tender
21 | Construction & Maintenance of Khawzawl to Biate Road (0.00 kmp-6.00Km) Group-A | 780.49 | Khawzawl Division | 31.12.20 | 31.12.22 | 100% | 732.3 |  |  | 100% | 732.3 | Work completed | Item Rate Contract
22 | Construction & Maintenance of Khawzawl to Biate Road (6.00 kmp-12.00Km) Group-B | 760.98 | Khawzawl Division | 31.12.20 | 31.12.22 | 100% | 704.47 |  |  | 100% | 704.47 | Work completed | Item Rate Contract
23 | Construction & Maintenance of Khawzawl to Biate Road (12.00 kmp-18.00Km) Group-C | 817.47 | Khawzawl Division | 2.1.21 | 2.1.23 | 100% | 764.53 |  |  | 100% | 764.53 | Work completed | Item Rate Contract
24 | Construction & Maintenance of Khawzawl to Biate Road (18.00 kmp-24.00Km) Group-D | 750.94 | Khawzawl Division | 10.6.20 | 10.6.22 | 100% | 691.87 |  |  | 100% | 691.87 | Work completed | Item rate contract
25 | Construction & Maintenance of Khawzawl to Biate Road (24.00 kmp-30.00Km) Group-E | 754.41 | Khawzawl Division | 29.4.21 | 29.4.22 | 100% | 671.58 |  |  | 100% | 671.58 | Work completed | Item Rate Contract
26 | Construction & Maintenance of Khawzawl to Biate Road (30.00 kmp-36.00Km) Group-F | 1148.93 | Khawzawl Division | 7.2.20 | 7.2.22 | 100% | 988.06 |  |  | 100% | 988.06 | Work completed | Item Rate Contract
27 | Construction & Maintenance of Khawzawl to Biate Road (36.00 kmp-42.00Km) Group-G | 818.99 | Khawzawl Division | 1.1.21 | 1.1.23 | 100% | 792.78 |  |  | 100% | 792.78 | Completed on 23.02.24 | Item Rate Contract
28 | Construction & Maintenance of Khawzawl to Biate Road (42.00 kmp-48.00Km) Group-H | 1430.82 | Khawzawl Division | 6.1.20 | 6.1.22 | 100% | 1324.75 |  |  | 100% | 1324.75 | Work completed | Item rate contract
29 | Construction & Maintenance of Khawzawl to Biate Road (48.00 kmp-54.00Km) Group-I | 1108.01 | Khawzawl Division | 24.3.21 | 24.3.22 | 100% | 985.77 |  |  | 100% | 985.77 | Work completed | Item Rate Contract
30 | Construction & Maintenance of Khawzawl to Biate Road (54.00 kmp-60.00Km) Group-J | 937.99 | Khawzawl Division | 4.1.21 | 4.1.23 | 100% | 892.15 |  |  | 100% | 892.15 | Work completed | Item Rate Contract
31 | Construction & Maintenance of Khawzawl-Ngaizawl Road | 853.85 | Khawzawl Division | 13.11.17 | 13.11.19 | 100% | 843.15 |  |  | 100% | 843.15 | Work completed | Item Rate Contract
32 | Construction & Maintenance of Khawhai - Tlangpuilian Road | 962.79 | Khawzawl Division | 13.11.17 | 31.12.19 | 100% | 909.22 |  |  | 100% | 909.22 | Work completed on 01.03.24 | Item Rate Contract
33 | Construction & Maintenance of Khawzawl - Vankal Road | 1997.33 | Khawzawl Division | 13.12.18 | 13.12.19 | 88% | 1821.89 | 12% |  | 100% | 1821.89 | Work physically completed | Item rate contract
34 | Construction & Maintenance of Khawzawl - Hmuncheng Road | 668.08 | Khawzawl Division | 23.05.22 | 30.09.22 | 100% | 566.56 |  |  | 100% | 566.56 | Completed on 31.3.24 | Item rate contract
35 | Upgradation & Maintenance of Kawlkulh to N.E Bualpui Road (Ch.0.00 - 24.00 Kmp) | 2718.95 | Khawzawl Division | 05.09.24 | 05.03.26 | 15% |  | 1% |  | 16% |  | Work in progress | Item rate contract
36 | Upgradation & Maintenance of Kawlkulh to Lungpho to Ngentiang Road (Ch.0.00 - 11.840 Kmp) | 1057.86 | Khawzawl Division | 29.08.24 | 01.03.26 | 6% |  | 1% |  | 7% |  | Work in progress | Item rate contract
37 | Upgradation & Maintenance of Kawlkulh to Lungpho upto Rullam Road (Ch.0.00 - 39.50 Kmp) | 3061.94 | Khawzawl Division | 23.08.24 | 23.02.26 | 9% |  | 3% |  | 12% |  | Work in progress | Item rate contract
38 | Construction & Maintenance of Phuldungsei to Parvatui Road (0.00 Kmp - 17.30 Kmp) | 3695.52 | Mamit Division | 13.12.18 |  | 100% | 3812.65 |  |  | 100% | 3812.65 |  | Item rate
39 | Construction & Maintenance of Tuipuibari to Andermanik Road (0.00 Kmp - 2.760 km) | 430.18 | Mamit Division | 17.9.18 | 17.9.19 | 100% | 428.43 |  |  | 100% | 428.43 |  | Item rate
40 | Construction & Maintenance of Andermanik to N.Belkhai Road (0.00 Kmp - 6.00 km) | 1016.7 | Mamit Division | 10.6.19 | 10.6.20 | 65.5% | 575.36 | 3.5% |  | 69% | 575.36 | Revised Target date of completion= 31.03.2024 | Item rate
41 | Construction and Maintenance of Sachan to Sumasumi Road (0.00 - 24.09 Kmp) | 4005.26 | Lunglei Road Division-I | 10.06.19 | 31.03.25 | 84% | 3431.7 |  |  | 84% | 3431.7 | Work in progress
42 | Construction and Maintenance of Sumasumi - Tuikawi Road (0.00 - 19.22 Kmp) | 2882.21 | Lunglei Road Division-I | 14.06.19 | 31.03.25 | 59% | 1407.58 | 3% |  | 62% | 1407.58 | Work in progress
43 | Const. & Maint.of Bunghmun to Sachan Road (0.00-9.07Kmp) | 1325.06 | Lunglei Road Division-I | 13.12.18 | 31.03.25 | 74% | 899.05 | 4% |  | 78% | 899.05
44 | Lunglei-Kawlhawk-Buarpui Road (0.000-66.500Kmp) | 5572.22 | Lunglei Road Division-I | 8.9.24 | 8.3.26
45 | Const. & Maint.of Khawhri to Chawngtui Road (0.00-17.81 Kmp) | 1280.59 | Lunglei Road Division-II | 8.10.18 | 31.3.24 | 100% | 1280.16 |  |  | 100% | 1280.16 | Phy. Completed | Open Tender
46 | Const. & Maint.of Luangmual to Vaisam Road (0.00-26.700 Kmp) | 4711.5 | Lunglei Road Division-II | 10.06.19 | 31.3.24 | 89.52% | 4176.83 |  |  | 89.52% | 4176.83 | 1) EOT Granted upto 25/02/25 2) Deviation Sanction No.B-15028/240/2023/Ph-II/28/EC/PWD/PMGSY/8 of 9.10.23 | Open Tender
47 | Const. & Maint.of Haulawng to Dawn Road (0.00-6.00 Kmp) | 766.65 | Lunglei Road Division-II | 10.06.20 | 31.3.24 | 100% | 766.36 |  |  | 100% | 766.36 | Phy. Completed | Open Tender
48 | Const. & Maint.of Haulawng to Dawn Road (6.00-12.000 Kmp) | 632.64 | Lunglei Road Division-II | 01.01.21 | 31.3.24 | 100% | 632.64 |  |  | 100% | 632.64 | Phy. Completed | Open Tender
49 | Const. & Maint.of Haulawng to Dawn Road (12.00-18.000 Kmp) | 730.72 | Lunglei Road Division-II | 01.01.21 | 31.3.24 | 100% | 730.58 |  |  | 100% | 730.58 | Phy. Completed | Open Tender
50 | Const. & Maint.of Haulawng to Dawn Road (18.00-24.000 Kmp) | 850.56 | Lunglei Road Division-II | 01.01.21 | 31.3.24 | 100% | 841.71 |  |  | 100% | 841.71 | Phy. Completed | Open Tender
51 | Const. & Maint.of Haulawng to Dawn Road (24.00-30.500 Kmp) | 883.22 | Lunglei Road Division-II | 01.01.21 | 31.3.24 | 100% | 883.22 |  |  | 100% | 883.22 | Phy. Completed | Open Tender
52 | Construction of Nghalimlui to Bolisora (0.00-3.00)Kmp (Sh: FC, Culvert, R.Wall) | 158.33 | Lawngtlai Division | 27.10.17 | 30.04.20 | 100% | 158.33 | - | - | 100% | 158.33 | Completed | NIT
53 | Construction of Nghalimlui to Bolisora (3.00-5.00)Kmp (Sh: FC, Culvert, R.Wall) | 249.17 | Lawngtlai Division | 27.10.17 | 23.03.20 | 100% | 247.3 | - | - | 100% | 247.3 | Completed | NIT
54 | Construction of Nghalimlui to Bolisora (5.00-8.00)Kmp (Sh: FC, Culvert, R.Wall) | 206.24 | Lawngtlai Division | 27.10.17 | 10.08.20 | 100% | 206.24 | - | - | 100% | 206.24 | Completed | NIT
55 | Construction of Nghalimlui to Bolisora (8.00-12.65)Kmp (Sh: FC, Culvert, R.Wall) | 266.55 | Lawngtlai Division | 27.10.17 | 16.08.20 | 100% | 246.66 | - | - | 100% | 246.66 | Completed | NIT
56 | Construction of Karlui to Damlui (0.00-2.00)Kmp (Sh: FC, Culvert, R.Wall) | 207.84 | Lawngtlai Division | 27.10.17 | 28.2.20 | 100% | 207.66 | - | - | 100% | 207.66 | Completed | NIT
57 | Construction of Karlui to Damlui (2.00-6.00)Kmp (Sh: FC, Culvert, R.Wall) | 227.53 | Lawngtlai Division | 27.10.17 | 30.10.19 | 100% | 216.35 | - | - | 100% | 216.35 | Completed | NIT
58 | Construction of Karlui to Damlui (6.00-8.800)Kmp (Sh: FC, Culvert, R.Wall) | 147.71 | Lawngtlai Division | 13.11.17 | 25.10.19 | 100% | 147.69 | - | - | 100% | 147.69 | Completed | NIT
59 | Construction of Bolisora to Chamdurtlang (0.00 - 2.00) Kmp (Sh: FC, Culvert. R.Wall) | 155.5 | Lawngtlai Division | 27.10.17 | 20.05.20 | 100% | 155.49 | - | - | 100% | 155.49 | Completed | NIT
60 | Construction of Bolisora to Chamdurtlang(2.00-5.00)Kmp (Sh: FC, Culvert, R.Wall) | 229.32 | Lawngtlai Division | 27.10.17 | 16.03.20 | 100% | 229.32 | - | - | 100% | 229.32 | Completed | NIT
61 | Construction of Bolisora to Chamdurtlang(5.00-9.00)Kmp (Sh: FC, Culvert, R.Wall) | 359.96 | Lawngtlai Division | 01.04.19 | 29.09.21 | 100% | 359.95 | - | - | 100% | 359.95 | Completed | NIT
62 | Construction of Bolisora to Chamdurtlang(9.00-11.650)Kmp (Sh: FC, Culvert, R.Wall) | 251.92 | Lawngtlai Division | 27.10.17 | 16.03.20 | 100% | 251.9 | - | - | 100% | 251.9 | Completed | NIT
63 | Construction of Ajasora to Longpuighat (0.00-10.900)Kmp (Sh: Const.of road using Flexible Pavement Technology) | 934 | Lawngtlai Division | 13.11.17 | 19.12.21 | 100% | 857.32 | - | - | 100% | 857.32 | Ongoing | NIT
64 | Construction of Jognasury - Karlui Road (0.000-12.100)Kmp (Sh: Formation Cutting, Culvert & R.Walls & Const.of of Road Using Flexible Pavement) | 888.27 | Lawngtlai Division | 13.12.18 | 30.09.22 | 100% | 760.65 |  | - | 100% | 760.65 | Completed | NIT
65 | Construction of Maniababsora-I to Maniababsora-II Road (0.000-1.520)Kmp (Sh: FC, Culvert & R.Wall & Const.of road using Panelled Concrete Technology) | 212.32 | Lawngtlai Division | 27.12.18 | 22.11.20 | 100% | 212.32 | - | - | 100% | 212.32 | Completed | NIT
66 | Construction of Boroituli to Jaruldubasora Road (0.000-2.100)Kmp (Sh: FC, Culvert & R.Wall & Const.of road using Panelled Concrete Technology) | 257.02 | Lawngtlai Division | 17.09.18 | 10.02.22 | 100% | 257 | - | - | 100% | 257 | Completed | NIT
67 | Construction of Boroituli to Jaruldubasora Road (2.000-3.700)Kmp (Sh: FC, Culvert & R.Wall & Const.of road using Panelled Concrete Technology) | 269.85 | Lawngtlai Division | 28.09.18 | 30.09.22 | 100% | 268.54 | - | - | 100% | 268.54 | Completed | NIT
68 | Construction of Vaseitlang to Lokhisury Road(0.00-9.560)Kmp (Sh: FC, Culvert, R.Wall & Const.of road using Panelled Concrete Technology) | 1366.7 | Lawngtlai Division | 28.09.18 | 30.09.22 | 84.23% | 844.7 |  |  | 84.23% | 844.7 | Ongoing | NIT
69 | Construction of Vathuampui to Tuisentlang Road(0.000-9.600)Kmp (Sh: FC, Culvert, R.Wall & Const.of Road Using panelled Concrete) | 1320.64 | Lawngtlai Division | 03.01.18 | 30.09.22 | 95.54% | 988.46 | 2.46% | 86.52 | 98% | 1074.98 | Ongoing | NIT
70 | Construction of Vathuampui to Chamdur P-I Road(0.000-1.720)Kmp (Sh: FC, Culvert, R.Wall & Const.of Road Using panelled Concrete) | 263.08 | Lawngtlai Division | 15.10.18 | 30.09.22 | 100% | 261.11 | - | - | 100% | 261.11 | Completed | NIT
71 | Construction of Vathuampui to Chamdurtlang (0.000-1.720)Kmp (Sh: FC, Culvert, R.Wall & Const.of Road Using panelled Concrete) | 274.17 | Lawngtlai Division | 13.12.18 | 30.09.22 | 71.15% | 206.45 |  |  | 71.15% | 206.45 | Ongoing | NIT
72 | Construction of Vathuampui to Chamdurtlang (2.000-3.800)Kmp (Sh: FC, Culvert, R.Wall & Const.of Road Using panelled Concrete) | 360.89 | Lawngtlai Division | 22.09.18 | 30.09.22 | 100% | 356.27 | - |  | 100% | 356.27 | Completed | NIT
73 | Construction of Chamdurtlang to Mualtlang Road(0.000-7.970)Kmp (Sh: FC, Culvert, R.Wall & Const.of Road Using panelled Concrete) | 1152.2 | Lawngtlai Division | 13.12.18 | 30.09.22 | 100% | 1089.09 | - | - | 100% | 1089.1 | Completed | NIT
74 | Construction of Parva II to Zochachhuah Road(0.000-29.720)Kmp (Sh: FC, Culvert, R.Wall & Const.of Road Using panelled Concrete) | 5432.38 | Lawngtlai Division | 05.04.19 | 30.09.23 | 100% | 4804.07 | - |  | 100% | 4804.07 | Completed | NIT
75 | Construction of Parva II to Bondukbanga Road(0.000-2.000)Kmp (Sh: FC, Culvert, R.Wall & Const.of Road Using Flexible Pavement) | 269.72 | Lawngtlai Division | 28.09.18 | 12.01.22 | 100% | 269.14 | - | - | 100% | 269.14 | Completed | NIT
76 | Construction of Parva II to Bondukbanga Road(2.000-4.120)Kmp (Sh: FC, Culvert, R.Wall & Const.of Road Using Flexible Pavement) | 294.1 | Lawngtlai Division | 13.12.18 | 31.12.22 | 100% | 281.42 |  |  | 100% | 281.42 | Completed | NIT
77 | Construction &Maintenance of Parva-II - Kamtuli Road (0.000-25.550)Kmp (Sh: FC, Culvert, R.Wall & Const.of Road Using panelled Concrete) | 4139.88 | Lawngtlai Division | 17.06.19 | 30.09.22 | 97.14% | 2727.3 | 0.5% |  | 97.64% | 2727.3 | Ongoing | NIT
78 | Construction & Maintenance of Vaseitlang to Maniababsora Road (0.000-13.500)Kmp (Sh: FC, Culvert, R.Wall & Const.of Road Using panelled Concrete) | 2361.15 | Lawngtlai Division | 14.06.19 | 30.04.22 | 100% | 2358.27 | - | - | 100% | 2358.27 | Completed | NIT
79 | Construction & Maintenance of Sedailui to Tuikhurlui Road (0.000-1.720)Kmp (Sh: FC, Culvert, R.Wall & Const.of Road Using panelled Concrete Techonology) | 204.33 | Lawngtlai Division | 17.06.19 | 08.05.22 | 92.06% | 159.96 | 7.94% | - | 100% | 159.96 | Completed | NIT
80 | Construction &Maintenance of M.Kawnpui to Vathuampui Road (0.000-20.000)Kmp (Sh: FC, Culvert, R.Wall & Const.of Road Using panelled Concrete Technology) | 1976.47 | Lawngtlai Division | 14.06.19 | 30.09.22 | 98.63% | 1286.99 | 0.5% |  | 99.13% | 1286.99 | Ongoing | NIT
81 | Construction &Maintenance of Sumsului Road to Jognasury (0.000-15.44)Kmp (Sh: Const.of Road Using panelled Concrete Technology) | 1278.38 | Lawngtlai Division | 14.06.19 | 30.09.22 | 97.21% | 1065.69 | 1.79% |  | 99% | 1065.69 | Ongoing | NIT
82 | Construction &Maintenance of Chawngthe 'P to Sumsului Road (0.000 - 4.570) Kmp | 313.29 | Lawngtlai Division | 1.07.19 | 31.03.22 | 100% | 302.97 |  |  | 100% | 302.97 | Completed | NIT
83 | Construction of Niawhtlang - Chakhang Road Package No.MZ0761(0.000-23.260Kmp) | 870.43 | Siaha Division | 14.10.23 | 14.03.24 | 68% | 431.48 | 18.78% | 168.07 | 86.78% | 599.55 | 1. Work in progress 2. Analysis for 4 km | Item rate contract
84 | Construction of Niawhtlang-Chakhang Road Package No.MZ 0771(0.000-20.790Kmp) | 890.59 | Siaha Division | 15.10.23 | 15.03.24 | 73% | 442.67 | 2.9% |  | 75.9% | 442.67 | Work in progress | Item rate contract
85 | Construction of Phura - Vahai Road (0.000 - 17.000) Kmp | 761.54 | Siaha Division | 30.01.25 | 31.03.25 |  |  | 18.26% |  | 18.26% |  | Work in progress | Item rate contract
86 | Const.& Maintenance of Mualcheng-N.Vanlaiphai Road Group 'A' (0.000-8.000 Kmp) | 515.65 | Serchhip Division | 31.12.20 | 31.12.22 | 100% | 303.31 | - | - | 100% | 303.13 | Physically completed | Item rate contract
87 | Const.& Maintenance of Mualcheng-N.Vanlaiphai Road Group 'B' (8.000-16.000 Kmp) | 586.35 | Serchhip Division | 31.12.20 | 31.12.22 | 100% | 586.34 | - |  | 100% | 586.34 | Physically completed | Item rate contract
88 | Upgradation & Maintenance of Khawlailung to Hmunzawl to Lungpho Road (0.00-39.04Kmp) | 3362.33 | Serchhip Division | [8 empty] | Progress on mobilization | Item rate contract
89 | Construction of Tuithumhnar to Lunghauka (0.00 - 5.00) Kmp (Sh: FC, Culvert, R.Wall) | 189.03 | Multi Modal Project Division | 27.10.17 | 31.07.19 | 100% | 189.03 | - | - | 100% | 189.03 | Completed on 05/07/2019
90 | Construction of Tuithumhnar to Lunghauka (5.00 - 7.00) Kmp (Sh: FC, Culvert, R.Wall) | 196.98 | Multi Modal Project Division | 27.10.17 | 31.03.21 | 100% | 193.28 | - | - | 100% | 193.28 | Completed on 30/03/2021
91 | Construction of Tuithumhnar to Lunghauka (7.00 - 10.00) Kmp (Sh: FC, Culvert, R.Wall) | 247.04 | Multi Modal Project Division | 27.10.17 | 16.07.20 | 100% | 247.04 | - | - | 100% | 247.04 | Completed on 20/07/2020
92 | Construction of Tuithumhnar to Lunghauka (10.00 - 13.00) Kmp (Sh: FC, Culvert, R.Wall) | 184.6 | Multi Modal Project Division | 27.10.17 | 29.06.20 | 100% | 184.6 | - | - | 100% | 184.6 | Completed on 29/06/2020
93 | Construction of Tuithumhnar to Lunghauka (13.00 - 15.480) Kmp (Sh: FC, Culvert, R.Wall) | 198.08 | Multi Modal Project Division | 27.10.17 | 16.07.20 | 100% | 198.08 | - | - | 100% | 198.08 | Completed on 26/06/2020
94 | Construction & Maintenance of Ngenpuitlng to Darnamtlang (0.00 - 4.00) Kmp (Sh: FC, Culvert, R.Wall) | 233.08 | Multi Modal Project Division | 27.10.17 | 31.01.20 | 100% | 193.78 | - | - | 100% | 193.78 | Physically completed on 01/05/2020
95 | Construction & Maintenance of Ngenpuitlng to Darnamtlang (4.00 - 6.20) Kmp (Sh: FC, Culvert, R.Wall) | 161.44 | Multi Modal Project Division | 27.10.17 | 31.08.21 | 100% | 224.53 | - | - | 100% | 224.53 | Completed on 30/08/2021
96 | Construction & Maintenance of Tuithumhnar to Hmawngbu (0.00 - 6.720) Kmp (Sh: Construction of road using Grove Concrete Pavement) | 442.51 | Multi Modal Project Division | 12.11.17 | 1.10.21 | 100% | 441.76 | - |  | 100% | 441.76 | Completed on 16/06/2021
97 | Construction of Sabualtlang to Hmawngbuchhuah Road (0.00 - 1.760) Kmp (Sh:Formation Cutting, Culvert & Retaining Walls & Construction of Road Using Flexible Pavement) | 244.22 | Multi Modal Project Division | 17.12.18 | 24.10.21 | 100% | 244.22 | - |  | 100% | 244.22 | Completed on 23/10/2021
98 | Construction & Maintenance of Nalkawn to Rulkual Road (0.000-16.000) Kmp Group A (Sh: Const.of Road using Cold Mix Technology | 1078.79 | Multi Modal Project Division | 04.01.21 | 04.01.23 | 100% | 1194.51 | - | - | 100% | 1194.51 | Completed on 29.9.22
99 | Construction & Maintenance of Nalkawn to Rulkual Road (16.000-32.000) Kmp Group B (Sh: Const.of Road using Cold Mix Technology | 1315.37 | Multi Modal Project Division | 12.12.23 | 30.3.24 | 81.32% | 921.06 | 4.37% |  | 85.69% | 921.06 | The work was retendered and newly awarded to the new contractor. the work is progress
100 | Construction & Maintenance of Rawmibawk to Phalrang Road (0.000-10.200) Kmp (Sh: Const.of Road usinggroove concrete Technology | 759.92 | Multi Modal Project Division | 13.12.18 | 30.09.22 | 100% | 758 | - |  | 100% | 758 | Completed on 29.9.22
101 | Construction & Maintenance of Saiha to Rawmibawk Road (0.000-22.30) Kmp (Sh: Const.of Road using groove concrete Technology | 1941.19 | Multi Modal Project Division | 17.06.19 | 30.09.22 | 100% | 1938.8 |  |  | 100% | 1938.8 | Phy. Completed on 29.03.23
102 | Upgradation & Maintenance of Sateek to Samlukhai to Sialsuk Road | 1994.15 | Hmuifang Division | 23.08.24 | 28.02.26 | [7 empty] | Item rate
103 | Upgradation & Maintenance of Khamrang - Mualkhang Road (0.000 - 6.120Kmp) | 281.18 | Kolasib Division | 26.08.24 | 26.02.26 | 13.92% |  | 28.92% |  | 42.84% |  | In progress | Item rate

## SEDP
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding: SEDP | [8 empty] | Month : February 2025
Sl. no | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Const. of Approach Road to Aizawl College at Mualpui | 415 | Aizawl Road South Division | 26.07.21 | 26.04.22 | 73% | 300 | - | - | 73% | 300 | Work in progress | Item Rate Contract
2 | Re-Construction of Concrete Pavement on Approach Road to Mission Vengthlang Cemetry, L=150M | 8.51 | Aizawl Road South Division | 17.03.23 | 28.11.24 |  |  | 100% |  | 100% |  | Completed (work cannot completed as scheduled due to land issues with land owner, so extension was granted 532 days from 18.06.23 to 30.11.24) | Item Rate Contract
3 | Construction of High Court Parking Building at MINECO | 1960 | Project Division-I | 2.7.20 | 29.8.24 | 98% | 1312.54 | 0.5% | 145.78 | 98.5% | 1458.32 | EOT 15.12.24 | Item Rate
4 | Const.of MBSE New Building and renovation of existing main Building | 1000 | Project Division-III | 22.2.21 | 6.7.24 | 99.8% | 836.2 | 0.2% | 48.06 | 100% | 884.26 | Work in progress | PWD Form-8
5 | Improvement of Khanpui - Tualbung Road Phase-II | 2936.68 | Saitual Division | 25.03.18 | 15.6.22 | 83.61% | 2821.96 |  | 45.15 | 83.61% | 2867.11
6 | Strenthening of Saitual - Phullen Road (28.300Km)(Tuivawl-Phullen) (28.700-57.000) | 1259.71 | Saitual Division | 18.12.19 | 18.04.21 | 100% | 800.01 |  |  | 100% | 800.01 | Phy. Completed
7 | Construction of Khanpui - Tualbung Road Phase-II (0.000-16.330Kmp) | 1576 | Saitual Division | 15.01.20 | 15.07.22 | 100% | 1485.05 |  |  | 100% | 1485.05 | Phy. Completed
8 | Resurfacing of Aizawl-Thenzawl-Lunglei Road (30.00 Kmp - 51.00 Kmp) | 1271.17 | Hmuifang Division | 20.02.23 | 20.07.23 | 100% | 1267.48 |  |  | 100% | 1267.48 | Phy. Completed | Item rate

## SEDP 4 (hidden)
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding: SEDP | [8 empty] | Month : May 2022
Sl. no | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the Month |  | Overall cumulative achievement |  | Remarks
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
25 | Widening of Road infront of CE, PWD Building at Tuikhuahtlang | 46.5 | Aizawl Road South Division |  |  | 100% | 46.5
26 | Const. of Approach Road to Aizawl College at Mualpui | 415 | Aizawl Road South Division |  |  | 35% | 120.12
27 | Const. of Approach Road to T.Romana College from ITI to Mualpui Road | 464.9 | Aizawl Road South Division |  |  | 49% | 171.33
28 | Wideing of Curve near Zokhuma's House on Bethlehem Vengthlang to College Road | 38.5 | Aizawl Road South Division |  |  | 100% | 38.5
29 | Const.of Approach Road to Zopar Vaipuanpho | 50 |  |  |  | 100% | 50
30 | Improvement at 0.50 Kmp on Hridaikawn to Power Sub Station at Tlangnuam | 12.3 | Aizawl Road South Division |  |  | 100% | 12.3
31 | Concrete pavement from Kohhran Thianghlim Biak In to PHE Pump House road within Maubawk | 30.5 | Aizawl Road South Division |  |  | 100% | 30.5
32 | Const.of Composite Retaining Wall at Kawilun Republic Veng | 7 | Aizawl Road South Division |  |  | 100% | 7
33 | Re-Construcrion of Retaining Wall near T.Lalhmuntiama's house on Nursery to Mission Veng Road via Kawltheihuan | 2.19 | Aizawl Road South Division |  |  | 100% | 2.19
34 | Const.of Bridge on Chhinga Vengthar to Tuithiang Road | 586.36 | Aizawl Road South Division |  |  | 59% | 60
35 | Widening of Approach road with rigid pavement from Thlanmual to Dam veng at Tlangnuam | 55 | Aizawl Road South Division |  |  | 100% | -

## CSS
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding: CSS | [8 empty] | Month : February 2025
Sl. no | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Polytechnic at Lawngtlai (Const.of Administrative cum Academic Block) | 800 | Lunglei Building Project Division | 18.3.13 | 14.10.15 | 100% | 768.27 (Corrected value) | - | - | 100% | 768.27 | Civil Work Completed & I/E Works not yet executed | Open Tender
2 | Construction of Judicial Quarter at Lawngtlai Grade-I Qtr. | 110.58 | Lunglei Building Project Division | 8.6.20 | 7.12.21 | 100% | 100.64 |  |  | 100% | 100.64 | Handovered | Restricted Tender
3 | Construction of Judicial Quarter at Lawngtlai Type-I & II Qtr. | 138.67 | Lunglei Building Project Division | 22.6.20 | 30.08.23 (Revised) | 100% | 126.27 |  |  | 100% | 126.27 | Handovered | Restricted Tender
4 | Const.of Administrative cum Academic Block for Polytechnic Thingsen Saiha | 501.08 | Lunglei Building Project Division | 15.03.16 | 11.7.17 | 60% | 167.64 | - |  | 60% | 167.64 | The contractor has stopped Work till date due to non-release of Fund from Central Government. However, fresh LOC have been allocated and payments being made for contractors of Sl.No (i) & (iii) | Open Tender
5 | Const.of Hostel building for Polytechnic at Thingsen saiha | 191.83 | Lunglei Building Project Division | 15.3.16 | 11.04.17 | 80% | 110.41 | - |  | 80% | 110.41
6 | Construction of Staff Qtr Type I, II & III for Polytechnic at Thingsen Saiha | 77.1 | Lunglei Building Project Division | 06.10.15 | 20.4.17 | 100% | 67.14 |  |  | 100% | 67.14
7 | Const.of Type-IV Qtr for Polytechnic at Thingsen Saiha | 29.99 | Lunglei Building Project Division | 15.03.16 | 11.01.17 | 76.5% | 24.79 | - | - | 76.5% | 24.79
8 | Construction of District Court Building at Saiha. | 1803.39 | Lunglei Building Project Division | 10.9.18 | 31.10.23 (Revised) | 100% | 1803.395 |  |  | 100% | 1803.395 | Works completed on dt.28.4.23 and handovered | Restricted Tender
9 | Construction of Academic Building for Nursing School at Lunglei (Upgradation) | 500 | Lunglei Building Project Division | 19.8.24 | 19.8.26 | 14% |  | 5% |  | 19% |  | Works in progress | Open Tender
10 | Construction of fast truck Court at Kolasib | 1799.85 | Project Division II | 20.09.22 | (O)20.09.24 (R) 18.02.25 | 83.5% | 845.81 | 1.5% |  | 85% | 845.81 | Work in progress. EOT under process | Item Rate
11 | Const.of Tourist Logde at Champhai | 328.73 | Project Division-III | 09.12.10 | 30.11.20 | 100% | 300 | - | - | 100% | 300 | Taken over by the Deptt.on Dt.3.8.2021 LOC amounting to Rs.30.00 lakh submitted for clearing liability.Hence, release of LOC awaited for financial closure.
12 | Const.of Polytechnic at Chhiahtlang i) Approach Road | 800 | Project Division-III | 3.3.16 | 2.8.16 | 100% | 103.67 | - | - | 100% | 103.67 | As desired by H&TE Department revised estimate amounting to Rs.1669.26 lakh is submitted in February 2024
ii) Administrative & Academic Block iii) Hostel Block iv) Staff Quarters
13 | Construction of General Nursing Midwifery Hostel at Champhai | 250 | Project Division-III | 13.07.22 | 13.07.24 | 100% | 150.51 |  |  | 100% | 150.51 | Only Rs.150.75 lakh is transferred from Health & Medical Education Department. Work with this fund is completed. Remianing sanctioned work is continued under SASCI 2023-2024. Civil work completed | PWD Form-8
14 | Construction of Hostel for S.T Girls at Champhai | 462.75 | Project Division-III | 18.9.23 | 28.9.25 | 85% | 162.77 | 1% |  | 86% | 162.77 | Work in progress | PWD Form-8
15 | 10-Bedded Intergrated AYUSH Hospital at Keifang, Saitual District | 750 | Project Division-III | 13.10.23 | 13.10.25 | 28% | 67.78 | 2% |  | 30% | 67.78 | Work in progress | PWD Form-8
16 | Construction of District Court Complex at Vengsang, Champhai | 4915.35 | Project Division-III | 17.10.23 | 17.10.26 | 43% | 555.53 | 2% | 684.39 | 43% | 1239.92 | Work in progress | PWD Form-8
17 | Renovation of Mizoram Secretariat Building at MINECO (Revised Estimate Rs.10097000) | 300.97 | Aizawl Building Division | 13.11.23 | 31.03.24 | 100% | 300.97 |  |  | 100% | 300.97 |  | Departmental
18 | Improvement of Mizoram Secretariat Building at MINECO | 168.49 | Aizawl Building Division | 13.11.23 | 31.03.24 | 100% | 98.67 |  | 1.49 | 100% | 100.16 |  | Departmental
19 | Improvement of Mizoram Secretariat Building at MINECO | 45.65 | Aizawl Building Division | 13.11.23 | 31.03.24 | 100% | 45.65 |  |  | 100% | 45.65 |  | Departmental

## MoRTH
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : NH(O) - MoRTH | [9 empty] | Month : Febuary 2025
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummutive Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Steel Arch (Semi Through) Bridge with concrete Deck 90m Arch Span over River Tlawng at Km 5.200 on NH-44A In the State of Mizoram of EPC Mode (NHO) | 4244 | NHD-I | 30.01.21 | 26.3.24 | 82.5% | 3154.24 |  |  | 82.5% | 3154.24 | On going | EPC Mode
2 | Periodical Renewal between Ch.183/00 Kmp to Ch.190/00 Kmp on NH-54A during 2022-23 in the state of Mizoram (Length=7.00Km) | 563.17 | NHD-I | 24.01.24 | 24.09.24 | 100% | 400.08 |  |  | 100% | 400.08 | Phy. completed | EPC Mode
3 | Periodical Renewal between Ch.183/00 Kmp to Ch.190/00 Kmp on NH-54A during 2022-23 in the state of Mizoram (Length=7.00Km) | 443.5 | NHD-I | 19.08.23 | 19.04.24 | 100% | 421.85 |  |  | 100% | 421.85 | Phy. completed | EPC Mode
4 | Short Term Maintenance Contract on Km 0/00 to Km 38/80 on NH-6 (Spur) in the state of Mizoram | 433.21 | NHD-I | 09.03.24 | 08.03.25 | 85.15% | 279.39 | 7.43% |  | 92.58% | 279.39 | On going | Item Rate
5 | Performance Based Maintenance Contract (PBMC) under National Highway Division-I during 2023-24 on NH-6/54 in the state of Mizoram. (Between km 159.00 to km 178.00Km) | 1891.98 | NHD-I | 29.08.24 | 28.08.29 | 20% |  | 10% |  | 30% |  | On going | Item Rate
6 | Short Term Maintenance Contract on NH-44A/108 Rockfall Bypass between km 0.000 to km 5.135 in the state of Mizoram (Job.No.RW/GHT/NH-44A/MZ/STMC/2024-25/2) | 20.26 | NHD-I | 28.11.24 | 27.11.25 | 35.3% |  | 34.7% |  | 70% | 0 | On going | Item Rate
7 | Short Term Maintenance Contract on NH-44A/108 between km 16.670 to km 114.618 in the state of Mizoram (Job.No.RW/GHT/NH-44A/MZ/STMC/2024-25/1) | 385.6 | NHD-I | 28.11.24 | 27.11.25 | 25.3% |  | 5.89% |  | 31.19% | 0 | On going | Item Rate
8 | Ordinary Repair (DPP) for short term maintenance from Km 0.00 to Km 42.80 and from Km 60.30 to km 130.00 on NH-150 in the state of Mizoram | 327.82 | NHD-II | 05.11.21 | 02.02.22 | 100% | 325.68 | - | - | 100% | 325.68 | Payment pending for RA-IV Rs.80,705.70 and witheld amount from RA-III Rs.20,35,155 Total Rs.21,15,861 | Item Rate
9 | Construction of 2 laning with paved shoulder flexible pavement from Km 42.80 to Km 60.30 of NH-150 road during 2016-17 within Mizoram State under NH(O) Scheme. (Job No. & Dtae of Sac Original/Revised : 150/MZ/2016-17/107) | 20594.82 | NHD-II | 29.11.17 | 22.05.21 | 100% | 14000 | - |  | 100% | 14000 | Works under maintenance | EPC Mode
10 | Reconstruction of single pavement from Km 130.00 to Km 140.00 on NH-150 in the State of Mizoram on EPC Mode (Job No.150/MZ/2019-20.119) | 3440.95 | NHD-II | 23.11.20 | 26.05.23 | 100% | 2441.16 | - | - | 100% | 2441.16 | Work under Defect Liability period | EPC Mode
11 | Consultancy Services for Project Management including prparation of Feasibility Study/Detailed {roject report fro laning with Paved Shoulders of stretches from Km 0/00 to Km 42/80 and from Km 60/00 to Km 140/00 on NH-150 NH (O) Package No. DPR/MZ/NER/2015/13 | 166.04 | NHD-II | 24.06.17 | 20.05.18 | 80% | 39.18 |  |  | 80% | 39.18 |  | MoRTH
12 | Short term Maintenance Contract for NH-150(60/30 to 130/000kmp) i.e 69.70Km Length for the year 2023-2024 under national Highway Division-II, Aizawl in the state of Mizoram (Job: RW/GHT/STMC/MZ/23-24/3) | 265.15 | NHD-II | 09.03.24 | 08.03.25 | 95% | 207.39 |  | 50.01 | 95% | 257.4 | On going | Item rate
13 | Short Term Maintenance Contract to NH-150 for the year 2023-2024 for chaninage Km 63/300 Km) under National Highway Division-II, Aizawl in the state of Mizoram | 166.8 | NHD-II | 09.03.24 | 08.03.25 | 100% | 158.07 |  | 2.43 | 100% | 160.5 | On going | Item rate
14 | Short Term Maintenance Contractor for NH-6 (150 to 180/000 Kmp) i.e 30 length for the year 2024-2025 under National Highway Division-II, Aizawl in the state of Mizoram (Job No.RW/GHT/NH-6/MZ/STMC/MZ/2024-25/3) | 116.03 | NHD-II | 20.12.24 | 19.12.25 |  |  |  | 8.56 |  | 8.56 | On going | Item rate
15 | Reconstruction of Bailey Bridge over R.Tuivai on NH-2 (old NH-150) at ch.262/00 Kmp | 500 | NHD-II |  |  | 66.35% | 352.05 | 1.81% | 102.89 | 68.16% | 454.94 | On going | Item rate
16 | Periodical Renewal of NH-54 in the state of Mizoram under ARP for the year 2019-2020 between Km 118/00-133/00 Km (15.00Km) | 1477 | NHD-III | 20.04.21 | 20.04.22 1st Extension of Time = 96 day as (19.4.22-14.6.22) | 100% | 1178 |  |  | 100% | 1178 | Completed | EPC
17 | Strengthening of Km 10.00 to Km 33.00 (Length 23.00 Km) on NH-306A including Strengthening & Construction of Retaining Walls and Culverts and Strenthening of 3 Nos.of Bailey Bridges in the State of Mizoram | 6523 | NHD-III | 07.02.22 | 07.08.23 | 100% | 4178.05 |  |  | 100% | 4178.05 | Completed | EPC
18 | Strengthening/Construction/Widening to 2-lane from km 89/00 to km 105/00 of NH-154 (New NH-6) under NH Division III in the state of Mizoram for the year 2022-23 (Length=16Km) | 8681 | NHD-III | 04.09.23 | 04.03.25 | 59.14% | 2362.09 | 18.89% | 744.68 | 78.03% | 3106.77 | Work in progress | EPC
19 | Short term Maintenance Contract on KM0/00 to 10/00 and Km 33/00 to 45/00 (22km) on Nh 306A in the state of Mizoram (Job No.RE/GHT/STMC/MZ/23-24/7) | 458 | NHD-III | 17.2.24 | 31.3.25 | 95.86% | 300.66 |  |  | 95.86% | 300.66 | Work in progress | EPC
20 | PR of NH-54 in the state of Mizoram under Annual Renewal Programme for the year 2019-20 from Km 70/00 to Km 98/00 (25.00Km) on EPC mode (job No.154/MZ/2020-212/120) | 1961 | NHD-III | 28.9.20 | 28.9.21 | 100% | 1771 |  |  | 100% | 1771 | Completed | EPC
21 | Strengthening between Km 119/00 to Km 147/00 on NH-154 including construction of retaining walls at essential places in the state of Mizoram on EPC mode (Job No.154/MZ/2020-212/120) | 2407 | NHD-III | 23.12.20 | 23.06.22 | 100% | 2407.2 |  |  | 100% | 2407.2 | Completed | EPC

## Article 275
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : Article 275(1) of the Constitution | [9 empty] | Month : February 2025
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummutive Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Tribal Hostel at Suangpuilawn, Mizoram | 320 | Project Division-IV | 12.08.23 | 12.02.25 | 64% | 130.57 | 6% |  | 70% | 130.57 | Work in progress. | Item Rate
2 | Construction of Multipurpose Community Hall at Darlawn, Mizoram | 720 | Project Division-IV | 12.08.23 | 12.08.25 | 56% | 144.15 | 2% | 2.21 | 58% | 146.36 | Work in progress. Bill withheld amount Rs.14.90 lakh | Item Rate

## ECRP-II
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : ECRP-II (Emergency Covid Response Package-II) | [9 empty] | Month : February 2025
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummutive Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of 50 Bedded critical care block at Champhai District Hospital Mizoram | 1346.4 | Project Division-III | 4.8.23 | 4.2.26 | 48% | 320.99 | 2% | 34.36 | 50% | 355.35 | Work in progress | PWD Form-8

## PM DeVINE
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : PM-DeVINE | [9 empty] | Month : February 2025
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummutive Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of Contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Bamboo Link Road from Lengpui to Saiphal Bamboo Plantation (41 Km) under PM-DeVINE | 6642 | NHD-I | 21.07.23 | 19.01.25 | 38.5% | 1648.36 | 11.01% | 312.07 | 49.51% | 1960.43 | Work is going on in full swing
2 | Construction of Bamboo Link Road from Tuirial Airfield to North Chaltlang (18Km) under PM-DevINE | 3358 | Aizawl Road North Division | 1.08.23 | 31.01.25 | 31.54% |  |  | 6.3% | 31.54% | 6.3 | Work in progress

## ICMR
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : DIPHR (ICMR) | [9 empty] | Month : February 2025
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummutive Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of Contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Model Rural Health Research Units at Lungtian Ram, Aibawk | 207.5 | Project Division-II | 21.09.23 | 21.03.25 | 67% | 130.06 | 3% |  | 70% | 130.06 | Work in progress | Item Rate

## NLCPR
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : NLCPR | [9 empty] | Month : February 2025
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Community Hall at Various places in Mizoram (Sh: Construction of Community Hall at Saitual, Thingsulthliah, Maite, Tualbung, Lungpher, Buhban, Lenchim, Chawrtui and Puilo) | 206.49 | Project Division-III | 22.2.12 | 30.11.19 | 100% | 186.01 | - | - | 100% | 186.01 | Completed and balance fund of Rs.20.48 (Rs.16.35 lakhs NLCPR + Rs.4.13 lakhs SMS) a waited for clearing liabilities

## NEDP
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : NEDP | [9 empty] | Month: February 2025
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Officers & Staff Quarter Type-IV, 2 Units and Type-III 4 Units for Taxation Department Lunglei | 330 | Lunglei Building Project Division | 3.7.20 | 30.10.23 (Revised) | 100% | 293.8 |  |  | 100% | 293.8 | Handovered | Restricted Tender
2 | Construction of DC Bangalow Type-VI at Saiha | 110.9 | Lunglei Building Division | 26.11.08 | 23.05.24 (Revised) | 98.3% | 92.01 |  | - | 98.3% | 92.01 | Allocation of Fund of amount Rs.243.50 lakh have been made in accordance with Revised estimate 2024-2025, for completion of the project and works expected to be completed on July, 2025 | Restricted Tender
3 | Construction of DC Office Building at Saiha | 610.11 | Lunglei Building Division | 31.10.18 | 31.10.20 Revised 28.11.23 | 90% | 414.49 |  |  | 90% | 414.49 |  | Restricted Tender
4 | Improvement of Buarpui - Bunghmun - via Thenhlum Road (65.000-79.00) Kmp during 2016-2017 | 170.467 | Lunglei Road Division-I | 4.3.24 | 4.3.25 | 100% | 143.66 |  |  | 100% | 143.66 | Completed
5 | Const.of Bridge on Chhinga Vengthar to Tuithiang Road | 586.36 | Aizawl Road South Division | 19.04.21 | 31.10.22 | 100% | 200 | - |  | 100% | 200 | Phy.Work completed | Item Rate Contract

## SPP
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : SPP | [9 empty] | Month : February 2025
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Circuit House at Serchhip | 358.18 | Project Division-III |  |  | - | - | - | - | - | - | Estimate amounting to Rs.3.58 Cr submitted as per new drawing. Waiting for approval for tender.
2 | Construction of Truckable Road between Tlangpui and Lungva | 480 | Khawzawl Division | 5.7.18 | 5.7.19 | 63% | 327.23 | - | - | 63% | 327.23 | EOT granted upto 7.10.2020 | Item rate contract

## DONER
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : One Time Special Assistance under Ministry of DONER | [9 empty] | Month : February 2025
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Re-Construction of safe House at Tlabung | 114.9 | Lunglei Building Project Division | 18.11.21 | 18.11.22 | 100% | 113.8 | - |  | 100% | 113.8 | Civil Works and IE Works completed. Handover paper submitted | Restricted Tender
2 | Re-Construction of safe shelter at Sairang | 115 | Project Division-II | 13.11.21 | 13.11.22 | 100% | 114.4 |  |  | 100% | 114.4 | Work physically completed | Item Rate

## NERSDS
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : NERSDS | [9 empty] | Month : February 2025
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Upgradation of Saiha-Lungbun-Tluangram-Haka Road in the State of Mizoram | 5021 | Saiha Division | 29.10.21 | 31.03.24 | 67.18% | 1994 | 7.13% |  | 74.31% | 1994 | Work in progress | EPC Mode
2 | Upgradation of Hnahlan-Hmunhlui-Tuimang-Singngei Road (Length = 12.000 Kms) | 4417 | Champhai Division | 29.11.21 | 31.3.24 (as per4 EoT-01) | 98.38% | 3001.45 | 1.62% |  | 100% | 3001.45 |  | EPC
3 | Upgradation of Zote-Fartlang-Buanli-Tuipui-Tawnzang Road in the state of Mizoram under NERSDS (Length = 8.00 Kms) | 2926 | Champhai Division | 12.12.21 | 31.3.24 (as per4 EoT-01) | 100% | 2217.32 |  |  | 100% | 2217.32 |  | EPC

## ISC Scheme
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : ISC Scheme & EI | [9 empty] | Month : January 2025
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of Contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Improvement of Tuipuibari - W.Kawnpui Road and ISC (0.00-9.00 Kmp) | 4870 | Mamit Division | 20.3.20 | 20.3.22 | 99% | 3978.3 |  |  | 99% | 3978.3 |  | EPC

## CRF
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : CRF | [9 empty] | Month : February 2025
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Two Lane from Sihhmui-Ramrikawn Road (Stage-I) | 8000 | Aizawl Road North Division | 1.10.18 | 1.10.20 | 87.57% | 6111.68 |  | 263.38 | 87.57% | 6375.06 | In progress | Item rate
2 | Widening and Improvement of Road from Durtlang Leitan to Sihphir Section (Length 10.25 Km) of Aizawl - Durtlang - Lungdai -Kawnpui Road in the State of Mizoram | 3553 | Aizawl Road North Division | 14.7.23 | 31.1.25 | 50.19% | 1330.34 |  | 133.04 | 50.19% | 1463.38 | In progress | EPC
3 | Construction of BUG Bridge over Tlawng on Aizawl-Reiek-W.Lungdar Road at 14.800 Kmp | 757.56 | Aizawl Road South Division | 10.10.18 | 31.10.24 | 100% | 750.57 |  |  | 100% | 750.57 | Completed | EPC Mode
4 | Construction of Muallungthu-Lungphun Road | 5996 | Hmuifang Division | 23.11.17 | 23.11.19 | 33.39% | 2347.14 | - |  | 33.39% | 2347.14 | Work in progress | Item rate contract
5 | Widening to single lane with geometric imprivement & Upgradation of Chhiahtlang-Lamchhip Road | 6668.18 | Hmuifang Division | 23.6.17 | 23.06.19 | 100% | 6282.93 | - |  | 100% | 6282.93 | Phy. Completed | Item rate contract
6 | Construction of Road from Chakkhei to Siasi Road (Length =20Km) under CRF: Group B (Sh: Permanent Works) | 1216.88 | Saiha Division | 8.7.19 | 14.09.24 | 100% | 956.84 |  |  | 100% | 956.84 | 1.Work is physically completed 2. Deviation under process. 3. Fresh EOT is being applied | Item rate contract
7 | Construction of Chakkhei to Siasi Road (Length =20Km) under CRF: Group A (Sh: FC & Pavement Works) | 3630.73 | Saiha Division | 8.7.19 | 20.12.24 | 99.03% | 2969.68 |  |  | 99.03% | 2969.68 | 1. Work in progress 2. Extension of time being appiled | Item rate contract

## NESIDS
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : NESIDS | [9 empty] | Month : February 2025
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of 2 Residential Hostel at ZMC (Boys) | 1000 | Project Division-II | 14.10.21 | 29.10.23 | 100% | 1000 |  |  | 100% | 1000 | Work Completed | EPC
2 | Construction of 2 Residential Hotel at ZMC (Girls) | 1000 | Project Division-II | (O)14.10.21 | (O)14.10.23 (R)15.04.24 (R2)15.07.24 | 100% | 937.28 |  |  | 100% | 937.28 | Work phy. completed | EPC
3 | Construction of 100 Bedded Distict Hospital at Kolasib | 2200 | Project Division-II | 23.09.22 | (O) 23.09.24 (R) 13.10.25 | 63.5% | 883.92 | 1.5% | 400 | 65% | 1283.92 | Work in progress | EPC
4 | Construction of State Resource Centre for HIV/AIDS at Aizawl | 400 | Project Division-II | 22.09.22 | 22.09.24 | 88% | 270.38 | 6% |  | 94% | 270.38 | Work in progress EOT awaited | EPC
5 | Improvement /Upgradation of Operational/Non-operational facilities of Lengpui Aiport (elevated Road with connected components of Terminal Building) | 1959 | Project Division-III | 30.9.21 | 30.11.24 | 98.3% | 1450.31 | 0.2% | 378.36 | 98.5% | 1828.67 | Work in progress | Turnkey
6 | Improvement /Upgradation of Operational/Non-operational facilities of Lengpui Aiport (elevated Road with connected components of Terminal Building) | 1775 | Project Division-III | 11.6.24 | 11.12.26 | 35% | 330.37 | 5% |  | 40% | 330.37 | Work in progress | PWD Form-8
7 | Improvement /Upgradation of Operational/Non-operational facilities of Lengpui Aiport (Elevated Road with connected components of Terminal Building) | 1696 | Project Division-III | 10.6.24 | 10.12.26 | 13% |  | 2% |  | 15% |  | The local NGO's wanted to shift the layout of the hospital main building towards the backside and loweing of the courtyard which will involve additional fund. The matter is brought to Health Department and decision is awaited. Work for quarters only in progress. | PWD Form-8
8 | Improvement & Upgradation of Lawngtlai-Tuipui ferry Road under NESIDS | 2897.8 | Lawngtlai Division | 08.08.19 | 30.06.23 | 100% | 2666.68 |  |  | 100% | 2666.68 | Phy. Completed | Item rate
9 | Improvement & Upgradation of Daido to Vawngkawt-Buangpuilawn (manipur) Road (Daido to Vawngkawt: Mizoram Area, Length 5.639 kms) | 3319 | Saitual Division | 14.03.24 | 14.09.25 | 28.59% |  | 6.7% | 713 | 35.29% | 713 |  | EPC
10 | Construction of 50 Bedded District Hospital Complex and Procurement of Equipment at Hnahthial, Mizoram | 1378.86 | Lunglei Building Project Division | 25.06.24 | 25.12.26 | 11% |  | 6% |  | 17% |  | Work in progress | Open Tender

## SCA
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : S.C.A | [9 empty] | Month : February 2025
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummutive Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of Contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Improvement of MPSC Office Building at MINECO | 394 | Project Division-I | 29.10.22 | 29.10.24 | 100% | 385.56 |  |  | 100% | 385.56 | Works completed
2 | Construction of DIG (NR) Office Building at PHQ Complex, Aizawl | 320 | Project Division-I | 21.7.22 | 21.1.25 | 100% | 275.99 |  |  | 100% | 275.99 |  | Item Rate
3 | Construction of Govt.Staff Qtrs.(Block-B) at DIET Complex | 386.6 | Project Division-I | 28.8.22 | 28.8.24 | 98.6% | 274.51 | 1.4% |  | 100% | 274.51 |  | Item Rate
4 | Strenthening of Infrastructure in 3 newly created Districts (Const.of DC Office Saitual) | 1000 | Project Division-III | 20.1.21 | 20.4.24 | 99.5% | 983.13 |  |  | 99.5% | 983.13 | Work completed and handed over to DC Saitual | PWD Form-8
5 | Construction of District Research Officers Quarters and Staff Cum Chowkider Quarters at Keifang, Saitual District | 70 | Project Division-III | 9.9.22 | 24.2.24 | 100% | 25 |  | 37.51 | 100% | 62.51 | Civil work completed | PWD Form-8
6 | Improvement & Upgradation of Operational/Non Operational facilities of Lengpui (Sh: Renovation of Terminal building) | 2124 | Project Division-III | 10.3.21 | 31.12.24 | 98.4% | 1773.36 | 0.1% |  | 98.5% | 1773.36 | Work in progress | PWD Form-8
7 | Construction of 100 Bedded Dist Hospital at Saitual (Sh: Construction of OPD building at District Hospital, Saitual | 200 | Project Division-III | 13.10.23 | 13.10.25 | 78% | 91.33 | 4% |  | 82% | 91.33 | Work in progress | PWD Form-8

## SARDPNE
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : SARDP-NE | [9 empty] | Month : February 2025
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Widening to two laning/Re-alignment and geometric improvement from km.11+000 to 114+618 of NH-44 'A' in the state of Mizoram | 1,10,988.00 | NHD-I | 17.3.11 | 31.12.22 | 96.04% | 102146 |  |  | 96.04% | 102146 | Contract was terminated on 24.08.2023 Tender be re-floated as soon as sanction of balance work estimate is obtained | Item rate contract
2 | Construction of a new 2-lane Highway from km 0/00kmp to 38/00 in Mizoram to support Kaladan Multi Modal Transit Transport project in Phase-'A of SARDP-NE package-I | 43465 | Multi Modal Project Division |  |  | 100% | 42978 |  |  | 100% | 42978 | 1. Financial progress is based on RW/GHT/MZ/SARDP/(161)/2010/957 Dt.12.01.24 2. Work completed on 22.6.2023
3 | Construction of a new 2-lane Highway from km 38.00 to km 71.00 in Mizoram to support Kaladan Multi Modal Transit Transport project in Phase-'A of SARDP-NE package-II | 32224 | Multi Modal Project Division |  |  | 100% | 30977 |  | - | 100% | 30977 | 1. Financial progress is based on bill submitted by the Contractor after verifying at the spot by the Department. 2. Work completed on 30.04.22
4 | Construction of a new 2-lane Highway from km 71.00 to km 99.83 in Mizoram to support Kaladan Multi Modal Transit Transport project in Phase-'A of SARDP-NE package-III | 37459 | Multi Modal Project Division |  |  | 100% | 36468 |  |  | 100% | 36468 | 1. Financial progress is based on tRW/GHT/MZ/SARDP/(161)/2010/957 Dt.12.01.24 2. Work completed on 23.06.23

## MAJOR
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : Major & Minor Works and Deposit woks 8443-108, D-III | [9 empty] | Month : February 2025
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | I/E to Additional Court Room with Chamber at Kolasib | 4.26 | Electrical Division Aizawl |  |  | 100% | 4.26 | - | - | 100% | 4.26 | Completed
2 | I/E to Arrival & Departure Passenger Lobby at Lengpui Airport | 25.27 | Electrical Division Aizawl | 19.12.20 |  | 90% | 25.27 | - | - | 90% | 25.27 | Room for installation Panel Board not yet installed
3 | SITC 13 Passenger Lift-2 nos, 2-opening, 900mm centre opening Stainless Steel cable with Automatic Rescue Device (ARD) for Hydraulic Lift with Minor Civil Works at Lengpui Airport Mizoram | 77.91 | Electrical Division Aizawl | 08.09.21 | 01.04.24 | 50% | 38.33 |  |  | 50% | 38.33 | Hydroulic lift 1 No.completed
4 | Street Light Parking light at Lengpui Airport | 37.32 | Electrical Division Aizawl | 06.07.22 |  | 95% | 37.32 |  | - | 95% | 37.32 | Departure conopy const. awaited
5 | Laying of XLPE Cable from Power House to Glide Path control at Lengpui Airport, Mizoram | 39.53 | Electrical Division Aizawl | 09.05.23 | 04.08.23 | 100% | 39.52 |  |  | 100% | 39.52 | Completed
6 | Estimate for I/E of Energy Meter for Terminal Building at Lengpui Airport | 7.99 | Electrical Division Aizawl | 06.07.22 |  | 90% | 7.99 |  | - | 90% | 7.99 | On going works
7 | Parking for District Court building at New Secretariat Complex | 32.48 | Electrical Division Aizawl |  |  | 60% | 16.99 | - | - | 60% | 16.99 | Completed
8 | Addl.Estimate for SITC of MRV/VRF Centralizes Air Conditioner Airport Fist Floor Departure Hall, Mizoram | 247.74 | Electrical Division Aizawl | 12.03.22 | 04.03.24 | 80% | 220.1 | 15% | 24.34 | 95% | 244.44 | On going works
9 | SITC of EPABX System for Lengpui Airport Terminal Building | 24.64 | Electrical Division Aizawl | 06.07.22 | 29.06.24 | 80% | 19.46 |  |  | 80% | 19.46 | On going works
10 | SITC of PA System at Lengpui Airport Terminal Building | 36.36 | Electrical Division Aizawl | 06.07.22 | 29.06.24 | 80% | 28.82 |  |  | 80% | 28.82 | Const.of ceiling structure awaited for cabling works
11 | Supply & Installation of Integrated Fire Hydrant System (Wise Riser) & SiTC of Alarm System for Lengpui Airport Terminal building | 119.96 | Electrical Division Aizawl | 06.07.22 | 29.06.24 | 80% | 94.72 |  |  | 80% | 94.72 | On going works
12 | SITC of AVTRON IP Surveillance System for Lengpui Airport Terminal Building | 94.76 | Electrical Division Aizawl | 06.07.22 | 29.06.24 | 85% | 67.61 |  |  | 85% | 67.61 | Control/CCTV room was not yet ready
13 | SITC of LAN SETUP at Lengpui Airport Terminal Building | 20.05 | Electrical Division Aizawl | 06.07.22 | 29.06.24 | 80% | 15.76 |  |  | 80% | 15.76 | Const.of ceiling structure awaited
14 | Estimate for XLPE Cable for Lengpui Airport | 27.23 | Electrical Division Aizawl |  |  | 100% | 27.23 |  | - | 100% | 27.23 | Completed
15 | Additional Estimate fo SITC of Air Conditioner Departer Pssenger Lobby at Lengpui Airport | 24.67 | Electrical Division Aizawl |  |  | 100% | 24.67 | - | - | 100% | 24.67 | Completed
16 | I/E works for Const. of MBSE Office | 59.77 | Electrical Division Aizawl |  |  | 100% | 57.37 |  |  | 100% | 57.37 | Completed
17 | I/E for DC Office at Saitual | 70 | Electrical Division Aizawl |  |  | 100% | 70 | - | - | 100% | 70 | Completed
18 | I/E to High Court Parking at MINECO | 109.5 | Electrical Division Aizawl | 07.03.23 | 30.03.25 | 40% | 65.73 | 35% | - | 75% | 65.73 | On going works
19 | I/E to PHC at Bungzung | 18.18 | Electrical Division Aizawl |  |  | 100% | 18.18 |  | - | 100% | 18.18 | Completed
20 | Const.of DIG(NR) Office at Aizawl under SCA during 2022-23 (Sh:I/E) | 43.84 | Electrical Division Aizawl | 23.01.23 | 10.05.24 | 100% | 43.84 |  |  | 100% | 43.84 | Completed
| Sh: Computer Conduiting |  |  |  | 10.05.24 | 100% |  | 100% |  | 100% |  | Completed
| Sh: Telephone Conduiting |  |  |  | 10.05.24 | 100% |  | 100% |  | 100% |  | Completed
| Sh: Fire Hydrant (Wet Riser) |  |  | 23.01.23 | 10.05.24 | 100% |  |  |  | 100% |  | Completed
| Sh: Automatic Fire Alarm System |  |  | 23.01.23 | 10.05.24 | 100% |  |  |  | 100% |  | Completed
21 | Construction of DC Office at Khawzawl (Sh: Lift & I/E) | 105.73 | Electrical Division Aizawl |  |  | 100% | 105.68 |  |  | 100% | 105.68 | Completed
22 | Impvt/Revamping of Lengpui Airport runway Lighting -Isolation Bay-DGCA Observation Reg. | 347.05 | Electrical Division Aizawl |  |  | 100% | 218.94 |  |  | 100% | 218.94 | Completed
23 | Impvt/Revamping of Lengpui Airport runway Lighting -Isolation Bay-DGCA Observation Reg. | 10.91 | Electrical Division Aizawl |  |  | 100% |  |  |  | 100% |  | Completed
24 | Impvt/Revamping of Lengpui Airport runway Lighting -Isolation Bay-DGCA Observation Reg. | 14.6 | Electrical Division Aizawl |  |  | 100% |  |  |  | 100% |  | Completed
25 | Renovation/Revamping of Internal Electrification to Polytechnic at Thingdawl (Sh: Automobile Engineering Block) | 18.65 | Electrical Division Aizawl | 04.10.23 | 18.11.23 | 90% |  |  |  | 90% |  | I/E completed, Service connection left
26 | Renovation/Revamping of Internal Electrification to Polytechnic at Thingdawl (Sh: Textile Technology Block) | 18.71 | Electrical Division Aizawl | 04.10.23 | 18.11.23 | 90% | 5.77 |  |  | 90% | 5.77 | I/E completed, Service connection left
27 | Renovation/Revamping of Internal Electrification to Polytechnic at Thingdawl (Sh: Administrative Block) | 9.52 | Electrical Division Aizawl | 04.10.23 | 18.11.23 | 90% |  |  |  | 90% |  | I/E completed, Service connection left
28 | Renovation/Revamping of Internal Electrification to Polytechnic at Thingdawl (Sh: Common facility Block) | 11.05 | Electrical Division Aizawl | 04.10.23 | 18.11.23 | 90% |  |  |  | 90% |  | I/E completed, Service connection left
29 | Renovation of I/E to BSUP 17 block @ 16 rooms at Durtlang | 40 | Electrical Division Aizawl |  |  | 100% | 40 |  |  | 100% | 40 | Completed
30 | SITC of 5 passenger Lift at E-in-C Office Building | 44.96 | Electrical Division Aizawl | 14.11.23 | 28.03.24 | 100% | 44.96 |  |  | 100% | 44.96 | Completed
31 | SITC of 5 passenger Lift for Fast Track Court Building at Kolasib | 3.9 | Electrical Division Aizawl | 26.12.23 | 20.06.24 | 20% |  |  |  | 20% |  | Building not yet ready for I/E
32 | SITC of 13 passenger Lift for Fast Track Court Building at Kolasib | 49.85 | Electrical Division Aizawl | 26.12.23 | 20.06.24 | 20% |  |  |  | 20% |  | Building not yet ready for I/E
33 | I/E Provision for Main Gate at MINECO | 0.76 | Electrical Division Aizawl | 22.04.24 | 30.04.24 | 100% | 0.76 |  |  | 100% | 0.76 | Completed
34 | Additional I/E to Mizoram Public Service Commission (MPSC) Building Aizawl | 7.22 | Electrical Division Aizawl | 07.05.24 | 07.06.24 | 100% | 7.22 |  |  | 100% | 7.22 | Completed
35 | Renovation of I/E to Central Laboratory building PWD & Office of the SDO PWD Quality Control Sub- Division I, II, & IV at Zuangtui, Aizawl | 11.14 | Electrical Division Aizawl |  |  | 100% | 11.14 |  |  | 100% | 11.14 | Completed
36 | Impvt/Upgradation of Operational/Non-Operational facilities of Lengpui Airport (Sh: Northern Side Baggage conveyor belt) | 192.5 | Electrical Division Aizawl | 22.07.24 | 18.12.24 | 100% | 238.24 |  |  | 100% | 234.24 | Completed
37 | Impvt/Upgradation of Operational/Non-Operational facilities of Lengpui Airport (Sh: Southern Side Baggage conveyor belt) | 192.5 | Electrical Division Aizawl | 22.07.24 | 18.12.24 | 100% |  |  |  | 100% |  | Completed
38 | I/E to Mizoram Legislator Home at Tuikhuahtlang | 28.5 | Electrical Division Aizawl | 20.11.24 | 28.3.25 | 45% |  | 10% | 9.83 | 55% | 9.83 | On going works
39 | I.E to Fast Track Court, Kolasib | 136.73 | Electrical Division Aizawl | 02.05.24 |  | 20% |  |  |  | 20% |  | Building not yet ready for I/E
40 | Construction of New Ward Building (Renovation & Upgradation of Central Jail) at Aizawl, Mizoram | 100 | Project Division-I | 23.3.23 | 23.3.24 (8.10.24 EOT) | 100% |  |  |  | 100% |  | Phy. Completed | Item Rate

## SASCE
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : SASCE | [9 empty] | Month : February 2025
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummutive Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Multi Utility Centre at Zemabawk, Aizawl, Mizoram. | 800 | Project Division-IV | 19.12.22 | 16.8.25 | 75% | 299.75 | 2% |  | 77% | 299.75 | Work in progress. | Item Rate
2 | Construction of Solid Waste Management Centre at Hualngohmun, Mizoram (Phase-I) | 1664 | Project Division-IV | 07.04.23 | 07.04.25 | 40% | 201.12 | 2% |  | 42% | 201.12 | Work in progress. | Item Rate
3 | Construction of DC Office, Aizawl District | 2000 | Project Division-IV | NA | NA | [6 empty] | To be tendered
4 | Const.of Road from IR Camp to Ramri Lui, Zophai, Bairabi (Sh: Group A-Formation Cutting, Permanent works and side drain) | 498 | NHD-III | 27.07.23 | 27.01.24 | 100% | 240.23 |  |  | 100% | 240.23 | Completed | Item Rate
| Group B-Pavement. Traffic Sign and Road Safety |  | NHD-III | 11.09.23 | 11.03.24 | [6 empty] | Work cancelled due non-available of Fund | Item Rate

## SPF
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : State Plan Fund | [9 empty] | Month : February 2025
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummutive Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of Contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | 4202 Co-On Education etc. a) I/E to boys & girls Hostel for Govt.Saiha College bldg at Siaha | 2 | Electrical Division, Lunglei |  |  | 40% | - | - | - | 40% | - | Materials received, building not yet ready for I/E Works | Departmental
2 | 8443-108-PWD Deposit-III a) I/E to DC Bungalow (Type-IV) at Siaha | 8.2 | Electrical Division, Lunglei |  |  | 40% | - |  | - | 40% | - | Materials received, building not yet ready for I/E Works | Departmental
| b) I/E to Safe House at Tlabung | 8 | Electrical Division, Lunglei |  |  | 100% |  |  |  | 100% |  | Completed | Departmental
| c) I/E to PHC Building at Lungsen | 19 | Electrical Division, Lunglei |  |  | 100% |  |  |  | 100% |  | Completed | Departmental
| d) I/E to Judicial Quarter Grade-I at Lawngtlai | 10 | Electrical Division, Lunglei |  |  | 100% |  |  |  | 100% |  | Completed | Departmental
| e) I/E to Judicial Quarter Type-I & Type-II at Lawngtlai | 13 | Electrical Division, Lunglei |  |  | 100% |  |  |  | 100% |  | Completed | Departmental
| f) I/E to Taxation Staff Quarter Type-III 4 units at Lunglei | 17 | Electrical Division, Lunglei |  |  | 100% |  |  |  | 100% |  | Completed | Departmental
| g) I/E to Taxation Officers Quarter Type-IV 2 Units at Lunglei | 9 | Electrical Division, Lunglei |  |  | 100% |  |  |  | 100% |  | Completed | Departmental
3 | 4059-Co on Public Works (Plan) SITC of 8 (Eight) Passenger Auto Elevator for District Court Building at Siaha | 42 | Electrical Division, Lunglei | 14.12.21 | 18.5.24 | 100% | 41.7 |  |  | 100% | 41.7 | Completed | Contractor

## Aspirational
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
| Source of funding : Aspirational District Programme, Window-I | [8 empty] | Month : February 2025
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Link Road from W.Mualthuam to Sothapa Road (Length=7.300Kms) | 200 | Kawrthah Division | 15.10.23 | 14.4.24 | 100% | 100 |  |  | 100% | 100 | Phy.completed on 14.4.24 | Contract after call of Restricted Tender

## Ministry
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : Ministry of Tribal Affairs | [9 empty] | Month : February 2025
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummutive Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of Contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Auditorium at Pukpui Lunglei | 523 | Lunglei Building Project Division | 16.9.23 | 16.01.25 | [6 empty] | Work not yet started till date due to objection of site from Education Dept. Relocation of Site for Construction is being awaited from Client Dept. | Retsricted Tender

## MAP
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : MAP | [9 empty] | Month : February 2025
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Resurfacing of Approach Road to High School Bairabi (Bairabi (NH-154) to High school Bairabi) | 5.12 | National Highway Division-III | Departmental |  | 20% |  |  |  | 20% |  |  | Depart mental
2 | YMA Field Approach Road (Field veng) Vairengte | 10.21 | National Highway Division-III | Departmental |  | 70% |  | 30% |  | 100% |  | Completed | Depart mental
3 | Construction of Wing wall Foundation collapsed at Ch.91.30 Kmp. On NH 54/6 within Kolasib | 7.61 | National Highway Division-III | Departmental |  | 100% | 7.61 |  |  | 100% | 7.61 | Completed | Depart mental
4 | Re-construction of Retaining Wall at Chainage 92.45 Kmp. On NH54/6 wihtin Kolasib | 4.05 | National Highway Division-III | Departmental |  | 100% | 4.05 |  |  | 100% | 4.05 | Completed | Depart mental
5 | Resurfacing of Approach Road to Jeep Road from NH-54 at Thingdawl part 2. | 2.44 | National Highway Division-III | Departmental |  | 20% |  | 80% |  | 100% |  | Completed | Depart mental
6 | Resurfacing of Approavh Toad to Middle School at Thingdawl | 4.05 | National Highway Division-III | Departmental |  |  |  | 50% |  | 50% |  | Work in progress | Depart mental
7 | Resurfacing of Sihkhurtui to Bethlehem Vengthlang Kawn | 15.16 | Aizawl Road South Division | 9.9.24 | 8.10.24 | 100% | 15.16 |  |  | 100% | 15.16 | Completed | Departmental
8 | Patch repair & Resurfacing of Kulikawn to Saikhamakawn via Hridaikawn (CP Road) (Section : 1.784 - 2.710 Km) | 24.19 | Aizawl Road South Division | 19.7.24 | 13.8.24 | 100% | 24.19 |  |  | 100% | 24.19 | Completed | Departmental
9 | Resurfacing of ITI Mualmawi Ring Road-II at Ch 0.280 - 0.550 Kmp | 8.19 | Aizawl Road South Division | 17.9.24 | 10.10.24 | 100% | 8.19 |  |  | 100% | 8.19 | Completed | Departmental
10 | Pot hole filling and Patch Repair of Shivaji to Bungkawn Oresbyterian Church Road | 1.2 | Aizawl Road South Division | 23.07.24 | 7.8.24 | 70% | 1.2 | 30% |  | 100% | 1.2 | Completed | Departmental
11 | Resurfacing of College Vengthlang Approach Road (PUC to Collage Vengthlang Road) | 4.96 | Aizawl Road South Division | 9.9.24 | 8.10.24 | 100% | 4.96 |  |  | 100% | 4.96 | Completed | Departmental
12 | Restoration of Road Formation by Construction of Retaining Wall near Pu H.Lalnuntluanga's House on ITI Ring Road-II | 2.9 | Aizawl Road South Division | 11.9.24 | 27.9.24 | 100% | 2.9 |  |  | 100% | 2.9 | Completed | Departmental
13 | Resurfacing of Venghlui to Bethlehem (Upper) | 8.47 | Aizawl Road South Division | 10.9.24 | 9.10.24 | 100% | 8.47 |  |  | 100% | 8.47 | Completed | Departmental
14 | Pothole Filling and Resurfacing of Maubawk Baptist Church to Kawngveng 0.000-0.250 kmp | 5.76 | Aizawl Road South Division | 8.7.24 | 27.7.23 | 100% | 5.76 |  |  | 100% | 5.76 | Completed | Departmental
15 | Resurfacing of Approach Road to Tlangnuam Playfield (0.000 - 0.166 Kmp) | 3.91 | Aizawl Road South Division | 18.7.24 | 30.7.24 | 100% | 3.91 |  |  | 100% | 3.91 | Completed | Departmental
16 | Patch repair & Resurfacing of Approach Road to ICDS Complex at Tlangnuam (0.000 - 0.240 Kmp) | 5.89 | Aizawl Road South Division | 18.7.24 | 5.8.24 | 100% | 5.89 |  |  | 100% | 5.89 | Completed | Departmental
17 | Seal Coating of AOC to PWD Circle Office Road | 2.48 | Aizawl Road South Division | 23.7.24 | 7.8.24 | 60% | 2.48 | 40% |  | 100% | 2.48 | Completed | Departmental
18 | Additional work for completion of R/Wall below CEO's Quarter, MINECO | 4.7 | Aizawl Road South Division | 23.7.24 | 1.8.24 | 100% | 4.7 |  |  | 100% | 4.7 | Completed | Departmental
19 | Pothole Filling andPatch Repair with full seal coat of Mualmawi Hunction to Mualmawi Ringroad-III (Entry point at ITI) | 1.5 | Aizawl Road South Division | 23.7.25 | 9.10.24 | 100% | 1.5 |  |  | 100% | 1.5 | Completed | Departmental
20 | Reconstruction of RCC Slab Culvert on Venghlui to Bethlehem upper | 0.97 | Aizawl Road South Division | 16.7.24 | 27.8.24 | 100% | 0.97 |  |  | 100% | 0.97 | Completed | Departmental
21 | Construction of Luangpawl Helipad and Approach road repair in connection to Union Defence Minister's visit at Mamit | 70.23 | Mamit Division | 16.7.24 |  | 51.44% | 67.59 |  |  | 51.44% | 67.59 | Completed | Departmental
Annual Maintenance Operation Plan 2024 - 2025
22 | Resurfacing of Approach Road to Civil Hospital Complex, Venglai | 59.26 | Kolasib Division | 19.09.24 | 19.03.24 | 100% | 55.764 |  |  | 100% | 55.764
23 | Pothole filling and Resurfacing of baktawng Internal Road (NH54-Baktawng Kawn) | 20.25 | Serchhip Division |  | 31.3.24 | 100% | 18.32 |  | 1 | 100% | 19.32 | Work completed
24 | Patch Repair of Serchhip to Zawlpui Road | 5.13 | Serchhip Division |  | 31.3.24 | 100% | 2.82 |  | 2.07 | 100% | 4.89 | Completed
25 | Resurfacing of Vaiveng Kawn to Govt.High School at N.Vanlaiphai | 9.21 | Serchhip Division |  | 31.3.24 | 100% | 8.29 |  |  | 100% | 8.29 | Work completed
26 | Repair of H/P Culvert nera Pu Zoramsima's House at E.Lungdar | 1.13 | Serchhip Division |  | 31.3.24 | 100% | 1.02 |  | 0.06 | 100% | 1.08 | Completed
27 | Resurfacing of Vengthar Bazar to Taidawnkawn at Khawzawl | 99.63 | Khawzawl Division | 20.09.24 |  | 100% | 99.63 |  |  | 100% | 99.63 | Work completed
28 | SM&BT pf Approach road to Agriculture Complex from PWD Gate at Khawzawl | 14.68 | Khawzawl Division | 23.09.24 |  | 100% | 14.68 |  |  | 100% | 14.68 | Work completed
29 | Pot hole repair & resurfacing of Chawngtlai-Tualte road | 72.85 | Khawzawl Division | 23.09.24 | [7 empty] | Materials being procured at site
30 | Resurfacing of KST Road by providing WBM, Open Graded Premix Carpet surfacing and Sand Seal Coat wherever necessary from 5.00 to 10.00 Kmp | 129.87 | Khawzawl Division | 21.10.24 |  | 100% | 129.87 |  |  | 100% | 129.87 | Work completed
31 | PCC of BCM Vengsang Church to Mualvawm Field at Drangawn | 25.44 | Khawzawl Division | 13.09.24 |  | 100% |  |  | 24.17 | 100% | 24.17 | Work in progress
32 | PCC of Muallungthu road to Hermon 2nd Lane at Hermon Veng, Khawzawl | 17.23 | Khawzawl Division | 13.09.24 |  | 100% | 16.37 |  |  | 100% | 16.37 | Work completed
33 | PCC of Approach road to NH-6(Agri Complex to FK Picnic Spot ) at Khawzawl | 21.14 | Khawzawl Division | 13.09.24 |  | 100% | 20.08 |  |  | 100% | 20.08 | Work completed
34 | Construction of RCC frame structure Bridge at Ch: 45.500Kmp on KST Road due to cyclone remal | 38.53 | Khawzawl Division | 27.09.24 |  | 100% | 38.53 |  |  | 100% | 38.53 | Work completed
35 | Pot hole repair & Resurfacing of Ngopa-Kawlbem Road | 99.4 | Khawzawl Division | 20.09.24 |  | 100% | 99.4 |  |  | 100% | 99.4 | Work completed
36 | Reconstruction of Collapsed Culvert at Ch 45.300Kmp on KST Road by Construction of RCC Slab Culvert and Masonry Retaining Wall | 26.4 | Khawzawl Division | 04.10.24 |  | 100% | 26.4 |  |  | 100% | 26.4 | Work completed
37 | Resurfacing of Approach Road to Vengthar Prebyterian Church at Khawzawl | 8.02 | Khawzawl Division | 28.10.24 |  | 100% | 8.01 |  |  | 100% | 8.01 | Work completed
38 | Construction of Collapsed Culvert at Dinthar to Kawnzar Road at Khawzawl | 9.08 | Khawzawl Division | 28.10.24 |  | 100% | 9.07 |  |  | 100% | 9.07 | Work completed
39 | Improvement of Blind Curve on BRTF to Artlangpeng Road | 6.9 | Khawzawl Division | 07.01.25 |  | 100% | 6.9 |  |  | 100% | 6.9 | Work completed
40 | Resurfacing of approach roads to Staff Lodge, SDO Office Quarters & Courtyard | 11.54 | Khawzawl Division | 07.01.25 |  | 100% | 11.54 |  |  | 100% | 11.54 | Work completed
41 | Improvement of safety provision on accident prone zone at New Champhai to Zotlang Road with Crash Barrier and other | 72.5 | Champhai Division |  |  | 79.68% | 72.4 | 20.32% |  | 100% | 72.4 | Work completed
42 | Annual Maintenance Opreation Plan 2024-2025 (3054) under Kawrthah Division | 58.18 | Kawrthah Division | 2.10.24 | 31.2.25 | 19.52% |  | 27.26% |  | 46.78% |  | Work in progress | Departmental
43 | Patch repair and resurfacing of Zohnuai H/S approach Road from YMA Hall, Zohnuai to Science Centre | 67.4 | Lunglei Road Division-I |  |  |  | 10.39 | 28% |  | 28% | 10.39
44 | Resurfacing of Approach Road to Graveyard No.II High School Road | 11.89 | Lunglei Road Division-II |  |  |  |  | 70% | 8.32 | 70% | 8.32 | Work in progress

## Annual Plan
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : Annual Plan | [9 empty] | Month : February 2025
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummutive Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of Contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Pothole filling and Resurfacing of IOC to Treasury at Serchhip (0.850-2.63) | 33.89 | Serchhip Division |  | 31.3.25 |  |  |  |  | 100% | 33.56 | Completed
2 | Pothole filling and Resurfacing of IOC to Quarry Road upto Juditial Office | 24.83 | Serchhip Division |  | 31.3.25 |  |  |  |  | 100% | 24.32 | Completed
3 | Pothole filling and Resurfacing of Juditial to Insaktanpuina lane | 19.52 | Serchhip Division |  | 31.3.25 |  |  |  |  | 100% | 19.33 | Completed
4 | Resurfacing of District Jail road and SMBT of Jail Staff Quarter Internal Road | 35.15 | Serchhip Division |  | 31.3.25 |  |  |  |  | 100% | 34.46 | Completed
5 | Resurfacing of NH54 to Dinthar Thlanmual Serchhip | 9.09 | Serchhip Division |  | 31.3.25 |  |  |  |  | 100% | 8.91 | Completed
6 | Resurfacing of IOC to Helipad via PCR H/S and Form IB peng peng at New Serchhip | 8.62 | Serchhip Division |  | 31.3.25 |  |  |  |  | 100% | 5.47 | Completed
7 | Pothole, Path repair with Premix carpet & Full surface sealcoating of NH54 to Khawtetlang, New Serchhip | 22.91 | Serchhip Division |  | 31.3.25 |  |  |  |  | 100% | 22.68 | Completed
8 | Resurfacing of Godown to Vengthar Road at New Serchhip | 39.69 | Serchhip Division |  | 31.3.25 |  |  |  |  | 100% | 39.31 | Completed
9 | Resurfacing of Godown to IB Peng via Chalzika House at New Serchhip | 13.32 | Serchhip Division |  | 31.3.25 |  |  |  |  | 100% | 13.19 | Completed
10 | Resurfacing of Godown to Baptis Biakin hnuai Road at New Serchhip | 2.47 | Serchhip Division |  | 31.3.25 |  |  |  |  | 100% | 2.42 | Completed
11 | Pothole filling and Resurfacing of approach road to PWD IB including courtyard at New Serchhip | 6.06 | Serchhip Division |  | 31.3.25 |  |  |  |  | 100% | 6.01 | Completed
12 | Resurfacing of NH 54 (Bazar) to Sport Complex at Serchhip | 28.76 | Serchhip Division |  | 31.3.25 |  |  |  |  | 100% | 28.76 | Completed
13 | SMBT of Leisang to Sport Complex, Serchhip | 30.2 | Serchhip Division |  | 31.3.25 |  |  |  |  | 100% | 30.2 | Completed
14 | Resurfacing of Approach Road from NH-54 (Bazar) Nanaua Workshop Leisang Veng) via YMA Hall Hraveng from 90.58-0.74Kmp) | 2.68 | Serchhip Division |  | 31.3.25 |  |  |  |  | 100% | 2.68 | Completed
15 | SMBT of Approach Road to Primary School II at Chhiahtlang | 11.58 | Serchhip Division |  | 31.3.25 |  |  |  |  | 100% | 11.58 | Completed
16 | Pothole filling and resurfacing of approach road to Sarawn veng Serchhip | 2.75 | Serchhip Division |  | 31.3.25 |  |  |  |  | 100% | 2.72 | Completed
17 | Pothole filling and resurfacing of approach road to Little Flower convent Primary School at Serchhip | 3.62 | Serchhip Division |  | 31.3.25 |  |  |  |  | 100% | 3.59 | Completed
18 | Resurfacing of Dinga In to Kapchawla In Venglai, Serchhip | 4.95 | Serchhip Division |  | 31.3.25 |  |  |  |  | 100% | 4.85 | Completed
19 | Pothole filling and Resurfacing of Horti Office to tarpi tlang (SIRD Office) Serchhip | 5.43 | Serchhip Division |  | 31.3.25 |  |  |  |  | 100% | 5.33 | Completed
20 | Path repair with premix carpet and full surface sealcoating on Mualpuikawn to Vankeukawn at Chhingchhip | 22.39 | Serchhip Division |  | 31.3.25 |  |  |  |  | 100% | 21.95 | Completed
21 | Pothole filling and resurfacing on Parmawii road at Tlungvel | 16.35 | Serchhip Division |  | 31.3.25 |  |  |  |  | 100% | 16.03 | Completed
22 | Repair of Cement Concrete Portion on Zozam Veng to Eklavya's Road at Serchhip | 5.63 | Serchhip Division |  | 31.3.25 |  |  |  |  | 100% | 5.52 | Completed
23 | Blacktopping of Approach Road to Vengchung Cementary Serchhip | 12.21 | Serchhip Division |  | 31.3.25 |  |  |  |  | 100% | 11.97 | Completed
24 | Resurfacing of Kawn Veng to Hmarveng Roads at Chhiahtlang | 21.4 | Serchhip Division |  | 31.3.25 |  |  |  |  | 100% | 21.19 | Completed
25 | Pothole filling and resurfacing of kawnveng to venghlun Volleyball court via ramlai hall at Chhiahtlang | 6.7 | Serchhip Division |  | 31.3.25 |  |  |  |  | 100% | 6.63 | Completed
26 | Pothole filling and path repair of KA road upto Chekawn (PartI, 0.00-14.00Kmp) | 153.72 | Serchhip Division |  | 31.3.25 |  |  |  |  | 100% | 150.7 | Completed
27 | Pothole filling and Path repair of Artahkawn - E.Lungdar (Chhura Lung to Vengthar) 9.00 Kmp - 14.00 Kmp | 42.39 | Serchhip Division |  | 31.3.25 |  |  |  |  | 100% | 41.56 | Completed
28 | Resurfacing of P&E Office and EE Quarter (From Panghmun zawl) at N.Vanlaiphai | 13.48 | Serchhip Division |  | 31.3.25 |  |  |  |  | 100% | 13.2 | Completed
29 | Resurfacing of Zawngte lukhaikawn - Ralkahkawn Road at Khawlailung | 11.13 | Serchhip Division |  | 31.3.25 |  |  |  |  | 100% | 10.9 | Completed
30 | Resurfacing of Bazar to Sihpui Road at E.Lungdar | 11.93 | Serchhip Division |  | 31.3.25 |  |  |  |  | 100% | 11.81 | Completed
31 | Construction of RCC Slap culvert on Kikawn to IOC (petrol pump) road at Serchhip | 9.27 | Serchhip Division |  | 31.3.25 |  |  |  |  | 100% | 9 | Completed
32 | Construction of Retaining wall on Approach road to Sport Complex via Thlanmual at Serchhip | 9.27 | Serchhip Division |  | 31.3.25 |  |  |  |  | 100% | 9 | Completed
33 | Repair of RCC slap Culvert near Lalrivela House at E.Lungdar | 3.4 | Serchhip Division |  | 31.3.25 |  |  |  |  | 100% | 3.3 | Completed
34 | Patch repair & Pot hole filling, Resurfacing of Sethlun to Theiriat VC House at 1.300 Kmp | 36.32 | Lunglei Road Division-I | 1.11.24 | 31.03.25 | 23% | 30.75 | 5% |  | 28% | 30.75 | Only pothole filling is in progress ie 90% Pothole filling completed Resurfacing will be started soon
35 | Patch repair & Pot hole filling, Resurfacing of Tlabung peng to PWD Colony (Tlabung peng, PWD Colony) | 47.17 | Lunglei Road Division-I | 1.11.24 | 31.03.25 | [6 empty] | 1 Labour gang from Jharkhand state is coming for this particular work. Work will be started on second week of january
36 | Patch repair & Pot hole filling, Resurfacing of Theiriat Approach Road from Bus Stand NH-54A | 16.9 | Lunglei Road Division-I | 1.11.25 | 31.03.25 | 32% | 16.89 | 60% |  | 92% | 16.89 | Only pothole filling is100% completed. Resurfacing will be started soon
37 | Patch repair & Pot hole filling, Resurfacing of Nursing School Approach Road at Ramthar (District Road Nursing School Approach Road) | 14.98 | Lunglei Road Division-I | 1.11.24 | 31.03.25 | 25% |  | 3% |  | 28% |  | Only pothole filling is in progress ie 80% Pothole filling completed Resurfacing will be started soon
38 | Patch repair & Pot hole filling, Resurfacing of soil complex Approach road (Soil complex Office District Road) | 18.88 | Lunglei Road Division-I | 1.11.24 | 31.03.25 | 20% | 15.36 | 15% |  | 35% | 15.36 | 100m Blacktopping completed. 80% Pothole filling is completed also.
39 | Resurfacing of Nursing School Approach Road to Mini Sport Complex at AP Tlang (V.L Thansanga's Traffic point Mini Sport Complex) | 12.65 | Lunglei Road Division-I | 1.11.24 | 31.03.25 |  |  | 30% |  | 30% |  | Not started at this road is proposed BC for three District under Different head
40 | Patch repair & Pot hole filling, Resurfacing of Approach Road to Electrci Cementry Road from Mualpui Road Electric veng (Sangchem Road Electric Veng) | 20.97 | Lunglei Road Division-I | 1.11.24 | 31.03.25 | 40% | 17.97 |  |  | 40% | 17.97 | 250m Resurfacing completed
41 | Patch repair & Pot hole filling, Resurfacing of District Road (from 2/200 to 4/900Kmp) | 73.02 | Lunglei Road Division-I | 1.11.24 | 31.03.25 | 10% |  |  |  | 10% |  | Pothole filling completed but not continued as this road is proposed fro BC for three District under different head
42 | Patch repair & Pot hole filling, Resurfacing of VC House Theiriat to Pu Biaksanga's House | 29.31 | Lunglei Road Division-I | 1.11.24 | 31.03.25 | 95% | 29.31 | 5% |  | 100% | 29.31 | Completed
43 | Patch repair & Pot hole filling, Resurfacing of Approach Road to DIG Office with Courtyard | 3.46 | Lunglei Road Division-I | 1.11.24 | 31.03.25 |  |  | 100% |  | 100% |  | Completed
44 | Resurfacing of Main Road to Haka from Samsons Building (ATL Main Road Samson's Building) | 1.4 | Lunglei Road Division-I | 1.11.24 | 31.03.25 |  | 1.02 | 100% |  | 100% | 1.02
45 | Resurfacing of Approach Road to Thuamluia Mual near Police Qtrs (Thuamluia Mual Police Qtrs) | 6.96 | Lunglei Road Division-I | 1.11.24 | 31.03.25 | [6 empty] | Not yet started
46 | Resurfacing of Chanmari BCM to Haka Road (BCM Church Chanmari Haka Main Road) | 3.13 | Lunglei Road Division-I | 1.11.24 | 31.03.25 |  | 2.53 | 100% |  | 100% | 2.53 | Completed
47 | Construction of Tourist Lodge Zotlang approach road | 16.95 | Lunglei Road Division-I | 1.11.24 | 31.03.25
48 | Restoration of rain cuts and reconstruction of WBM layer at Essential places on Buarpui to Bunghmun Road | 85.79 | Lunglei Road Division-I | 1.11.24 | 31.03.25 | [6 empty] | Material collected
49 | Aizawl-Thenzawl-Lunglei Road Group B (100.00 - 120.00Kmp) (WBM) | 83.01 | Lunglei Road Division-I | 1.11.24 | 31.03.25 |  |  | 81% |  | 81% |  | In progress
50 | Aizawl-Thenzawl-Lunglei Road Group B (120.00 - 143.000Kmp) (WBM, OPC, Seal Coat) | 263.16 | Lunglei Road Division-I | 1.11.24 | 31.03.25 |  |  | 85% |  | 85% |  | In progress
| Grand Total | 285.15 |  |  |  | 19% |  | 34% |  | 55% | 113.83

## 5054 (R&B)
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : 5054 (R & B) | [9 empty] | Month : February 2025
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummutive Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of Contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Strengthening and Improvement of State Highways & Other State Roads under Mizoram | 523 | Kolasib Division | 25.10.24 | 20.03.25 |  |  | 24.25% | 38.87 | 24.25% | 38.87 |  | Retsricted Tender
2 | Strengthening /Reconstruction of abutment & per (Mizoram side) | 500 | Kolasib Division |  |  | 10% | 454.95 | 5% | 19.46 | 15% | 474.41 | 50% Advabnce payment for launching and erection charge | Retsricted Tender
3 | Strengthening and Improvement of State Highways & Other State Roads under Mizoram under Kolasib Division | 206.04 | Kolasib Division |  |  | 60.57% | 124.08 | 39.43% | 72.36 | 100% | 124.08 | 196.44
4 | Strengthening and Improvement of State Highways & Other State Roads under Mizoram under Kolasib Division (Sh: Construction of Lined Side Drain on Approach Road to Rengtekawn Middle School, Rengtekawn) | 20.7 | Kolasib Division | 1.11.24 | 31.01.25 | 100% | 10.02 |  | 9.61 | 100% | 19.63 |  | Open Tender
5 | Strengthening and Improvement of State Highways & Other State Roads under Mizoram under Kolasib Division (Sh: Rehabilitation of Serkhan to Bagha Road - Construction of Rigid Pavement at Selected stretches) | 142.4 | Kolasib Division | 1.11.24 | 31.01.25 | 65% | 58.58 | 35% | 83.82 | 100% | 142.4 |  | Open Tender
6 | Strengthening and Improvement of State Highways & Other State Roads under Mizoram under Kolasib Division (Sh: Rehabilitation of Serkhan to Bagha Road - Resurfacibg between 90.700 Kmp to 94.30 Kmp Saipum to NH-306A intersection point) | 49.88 | Kolasib Division | 1.11.24 | 29.02.25 | 52.2% | 30.76 |  |  | 52.2% | 30.76 |  | Open Tender
7 | Strengthening and Improvement of State Highways & Other State Roads under Mizoram under Kolasib Division (Sh: Improvement of works within Kawnpui Town) | 246.67 | Kolasib Division | 25.10.24 | 20.03.25 | [5 empty] | 205.45 |  | Open Tender
8 | Strengthening and Improvement of State Highways & Other State Roads under Mizoram under Kolasib Division (Sh: Restoration of Damaged Pavement and Hume Pipe Culvertunderneath on Buhchang to Phasisen Road at 1.25Kmp) | 25.99 | Kolasib Division | 1.11.24 | 31.01.25 | 100% | 20.41 |  | 0.82 | 100% | 21.23 |  | Open Tender
9 | Strengthening and Improvement of State Highways & Other State Roads under Mizoram under Mamit Division | 264.88 | Mamit Division | 1.10.24 |  | 82% | 60.63 | 4% |  | 86% | 60.63 | Work in progress | Open Tender
10 | Strengthening and Improvement of State Highways & Other State Roads under Mizoram under Mamit Division | 301.71 | Mamit Division | 1.10.24 |  |  | 229.03 |  | 59.94 |  | 288.97 | Work in progress | Open Tender
Strengthening and Improvement of State Highways & Other Roads under Mizoram under Central Circle
11 | Construction of Rigid Pavement on Sihpui Tuikhur to Aizawl By-Pass road at Kulikawn | 40.39 | Aizawl Road South Division | 13.12.24 | 13.6.25 | 15% |  | 15% | 7.12 | 30% | 7.12 | Work in progress | Open Tender
12 | Construction of Side drain cover on Approach Road to SAI at Mission Vengthlang | 17.19 | Aizawl Road South Division | 13.12.24 | 13.6.25 |  |  | 40% |  | 40% |  | Work in progress | Departmental
13 | Resurfacing of Aizawl - Thenzawl- Lunglei (ATL) Road between 0.000-1.000 Kmp (Rigid pavement 1.00-1.344 = 0.334 Km) including improvement of Bus Terminal (RW=13.8m, H=1.0 | 52.34 | Aizawl Road South Division | 13.12.24 | 13.6.25 | 5% |  | 90% |  | 95% |  | Work in progress | Departmental
14 | Construction of Cement Concrete Pavement on Bethlehem Vengthlang to Thingdawl Ruam | 18.65 | Aizawl Road South Division | 21.2.25 | 13.6.25 | 60% |  | 40% | 9.72 | 100% | 9.72 | Work in progress | Departmental
15 | Construction of Rigid Pavement on Approach Road to Tlangnuam new Cemetary | 17.85 | Aizawl Road South Division | 13.12.24 | 13.6.25 | 5% |  | 3% |  | 8% |  | Work in progress | Departmental
16 | Resurfacing of ITI Junction to Mualpui Zeri point | 37.56 | Aizawl Road South Division | 14.10.24 | 12.11.24 | 100% | 37.56 |  |  | 100% | 37.56 | Completed | Departmental
17 | Construction of Rtaining Wall and U-Shaped Side Drain near Pi Vanrammawii's at ITI Veng on Aizawl Bypass Road at Ch.3.900 | 3.26 | Aizawl Road South Division | 14.10.24 | 30.10.24 | 100% | 3.26 |  |  | 100% | 3.26 | Completed | Departmental
18 | Resurfacing of Venghlui Approach Road | 21.36 | Aizawl Road South Division | 14.10.24 | 12.11.24 | 100% | 21.36 |  |  | 100% | 21.36 | Completed | Departmental
19 | Reconstruction of Side Drain on Aizawl Bypass Road at Ch.1.600 - 2.00 Kmp | 1.86 | Aizawl Road South Division | 04.11.24 | 15.11.24 | 100% | 1.86 |  |  | 100% | 1.86 | Completed | Departmental
20 | Extenstion of Causeway at Ch.4.850 Kmp on Aizawl Bypass Road | 10.5 | Aizawl Road South Division | 16.10.24 | 7.11.24 | 100% | 10.5 |  |  | 100% | 10.5 | Completed | Departmental
21 | Re-Construction of RCC Slab Culvert on Sihlui to Bethlehem Vengthlang kawn at Ch.0.085 Kmp | 4.47 | Aizawl Road South Division | 17.10.24 | 7.11.24 | 100% | 4.47 |  |  | 100% | 4.47 | Completed | Departmental
22 | Patch Repair & Full Seal Coating of Sikulpuikawn to Mission Veng Bazar | 9.68 | Aizawl Road South Division | 15.10.24 | 7.11.24 | 100% | 9.68 |  |  | 100% | 9.68 | Completed | Departmental
23 | Link Drain near Pi B.Zoramthangi House, Kulikawn | 7.07 | Aizawl Road South Division | 14.10.24 | 08.11.24 | 100% | 7.07 |  |  | 100% | 7.07 | Completed | Departmental
24 | Improvement of Aizawl-Reiek-W.Lungdar Road | 124.05 | Aizawl Road South Division | 14.10.24 |  | 77% | 70.17 | 5% | 21.21 | 82% | 91.38 | Work in progress | Departmental
25 | Repair of Culvert Abutment Wall at Ch.1.200 kmp on Mission Vengthlang to Pika Road | 0.92 | Aizawl Road South Division | 4.12.24 | 13.12.24 | 100% | 0.92 |  |  | 100% | 0.92 | Completed | Departmental
26 | Restoration of Road Formation: Construction of Retaining Wall at Lawipu | 7.63 | Aizawl Road South Division | 04.11.24 | 03.12.24 | 100% | 7.63 |  |  | 100% | 7.63 | Completed | Departmental
27 | Pothole filling, Patch Repair and Profile Correction of Bazar Bungkawn to Sikulpuikawn via MG Road | 19.63 | Aizawl Road South Division | 11.10.24 | 19.11.24 | 100% | 19.63 |  |  | 100% | 19.63 | Completed | Departmental
28 | Pothole filling, Patch Repair and Profile Correction of Sikulpuikawn to canteen Kual via Khatla kawn | 38.68 | Aizawl Road South Division | 11.10.24 | 19.11.24 | 100% | 38.68 |  |  | 100% | 38.68 | Completed | Departmental
29 | Pothole filling, Patch Repair and Profile Correction of Approach road to new Secretariat Complex (Khatla to New Secretariat Complex) | 18.42 | Aizawl Road South Division | 11.10.24 | 26.10.24 | 100% | 18.42 |  |  | 100% | 18.42 | Completed | Departmental
30 | Pothole filling, Patch Repair and Resurfacing of khatla Ring Road (Chawnga Road) | 19.14 | Aizawl Road South Division | 11.10.24 | 26.10.24 | 100% | 19.14 |  |  | 100% | 19.14 | Completed | Departmental
31 | Pothole filling and Patch Repair of Khatla kawn to Vety Hospital via Bethel Veng | 3.84 | Aizawl Road South Division | 14.10.24 | 18.11.24 | 100% | 3.84 |  |  | 100% | 3.84 | Completed | Departmental
32 | Pothole filling and Patch Repair of MHNL Section-III | 4.16 | Aizawl Road South Division | 14.10.24 | 18.11.24 | 100% | 4.16 |  |  | 100% | 4.16 | Completed | Departmental
33 | Pothole filling and Patch Repair of Khatla South Presbyterian Church to Bungkawn High School Road | 4.98 | Aizawl Road South Division | 14.10.24 | 23.11.24 | 100% | 4.98 |  |  | 100% | 4.98 | Completed | Departmental
34 | Grade improvement of Approach to MZP Pisa pui at Aizawl | 3.98 | Aizawl Road South Division | 14.10.24 | 8.11.27 | 100% | 3.98 |  |  | 100% | 3.98 | Completed | Departmental
35 | Patch Repair and Resurfacing of Melthum to Hlimen road (0.000-1.400 Kmp) of Khatla kawn to Vety Hospital via Bethel Veng | 24.13 | Aizawl Road South Division | 06.11.24 | 29.11.24 | 100% | 24.13 |  |  | 100% | 24.13 | Completed | Departmental
36 | Construction of Retaing Wall at Ch.4.300 Kmp on Hlimen to Samtlang road) | 10.61 | Aizawl Road South Division | 14.10.24 | 4.11.24 | 100% | 10.6 |  |  | 100% | 10.6 | Completed | Departmental
37 | Construction of PCC Flooring between Pu Thanpara's House and Pi Lalzuimawii's House at Lungleng-I | 3.42 | Aizawl Road South Division | 14.10.24 | 4.11.24 | 100% | 3.38 |  |  | 100% | 3.38 | Completed | Departmental
Additional (5054)
38 | Improvement of Pangi Peng Junction to PU College (Sh: Construction of Retaing Wall at Ch.0.850 Kmp) | 8.8 | Aizawl Road South Division | 14.10.24 | 8.11.24 | 100% | 8.8 |  |  | 100% | 8.8 | Completed | Departmental
39 | Improvement of maubawk to reformation & Camping Centre Road via BSUP, Lawipu Resurfacing with OPC 20mm with Construction of Side Drain | 92.58 | Aizawl Road South Division | 11.11.24 | 28.2.25 | 53% |  | 47% | 83.16 | 100% | 83.16 | Completed | Departmental
40 | Construction of Gabion Wall at Ch.32.550Kmp on Aizawl-Reiek-W.Lungdar Road | 16.49 | Aizawl Road South Division | 04.11.24 | 3.12.24 | 90% | 12.02 | 10% |  | 100% | 12.02 | Completed | Departmental
41 | Imrpovement of Reiek to West Lungdar Road (Sh: Construction of Masonry Retaining Wall at Ch.8.500, 18.900 & 34.250 Kmps) | 31.53 | Aizawl Road South Division | 11.11.24 | 11.2.25 | 75% |  | 25% |  | 100% |  | Completed | Departmental
42 | Blacktopping of the Round about in Mizoram Secretariat No.1 | 2.68 | Aizawl Road South Division | 5.11.24 | 12.11.24 | 100% | 2.68 |  |  | 100% | 2.68 | Completed | Departmental
43 | Coonstruction of Breast Wall below Pu Neihkunga (L) Building at Nursery Veng | 5 | Aizawl Road South Division | 6.11.24 | 19.11.24 | 100% | 5 |  |  | 100% | 5 | Completed | Departmental
44 | Widening of Approcah Road to Zion Veng at Melthum | 2.93 | Aizawl Road South Division | 28.10.24 | 8.11.24 | 100% | 2.93 |  |  | 100% | 2.93 | Completed | Departmental
45 | Rigid Pavement on approach road to Zion Veng at melthum | 2.69 | Aizawl Road South Division | 28.10.24 | 8.11.24 | 100% | 2.69 |  |  | 100% | 2.69 | Completed | Departmental
46 | Improvement of Hlimen to Lungleng Road (Sh: Construction of Link Drain near Zoheri House at Hlimen) | 6.7 | Aizawl Road South Division | 28.10.24 | 8.11.24 | 100% | 6.7 |  |  | 100% | 6.7 | Completed | Departmental
Strenthening and Improvement of State Highways & Other Roads under Mizoram (Improvement of various works in Mizoram under Aizawl Road South Division)
47 | Patch Repair from Pip Pangi Peng via PU College gate to ITI Traffic Point Road including ITI Bazar Ring Road | 38.08 | Aizawl Road South Division | 13.01.25 | 11.20.25 | 70% |  | 30% | 37.36 | 100% | 37.39 | Completed | Departmental
48 | Patch Repairs from PU College Gate-Bethlehem Vengthlang | 17 | Aizawl Road South Division | 14.01.25 | 13.02.25 | 65% |  | 35% | 16.67 | 100% | 16.67 | Completed | Departmental
49 | 47 | 5 | Aizawl Road South Division | 20.01.25 | 11.20.25 | 40% |  | 60% | 4.91 | 100% | 4.91 | Completed | Departmental
50 | Patch Repairs from Venghlui-Vety Qtrs | 2 | Aizawl Road South Division | 21.01.25 | 5.02.25 | 50% |  | 50% | 1.95 | 100% | 1.95 | Completed | Departmental
51 | Patch Repairs from Chhinga Veng - College Veng | 5 | Aizawl Road South Division | 20.01.25 | 7.02.25 | 40% |  | 60% | 4.9 | 100% | 4.9 | Completed | Departmental
52 | Patch Repairs from Republic Veng - Venghnuai Playfield | 8 | Aizawl Road South Division | 16.01.25 | 11.20.25 | 60% |  | 40% | 8.68 | 100% | 8.68 | Completed | Departmental
53 | Patch Repairs from ITI Vengthar Road | 20 | Aizawl Road South Division | 14.01.25 | 13.02.25 | 55% |  | 45% | 19.62 | 100% | 19.62 | Completed | Departmental
54 | Patch Repairs from Treasury Square - Sikulpuikawn via Upper Republic | 8.85 | Aizawl Road South Division | 22.01.25 | 18.02.25 | 60% |  | 40% | 8.68 | 60% | 8.68 | Completed | Departmental
55 | Patch Repairs from Kulikawn - Tlangnuam | 3 | Aizawl Road South Division | 14.01.25 | 28.01.25 |  |  | 100% | 2.94 | 100% | 2.94 | Completed
PMGSY-III
56 | Upgradation & Maintenance of Hlimen to samtlang to Lungleng Road | 1132.5 | Aizawl Road South Division | 23.10.24 | 23.04.26 | 2% |  | 1% |  | 3% |  | On going | Open Tender
57 | Reconstruction of Bailey Brideg over R.Tuivai on NH-2 (old NH-150) at ch.262/00kmp | 500 | National Highway Division-II | 31.3.24 |  | 85.66% | 474.42 | 14.34% | 2.7 | 100% | 477.12 | Work physically completed. Essen Fabricators Pvt.Ltd did not submit a bill worth Rs.19,46,588.00 | Depart mental
58 | Resurfacing of bairabi to Zophai Road (Bairabi (NH-154) Zophai Police Camp) (0.00 - 3.700Kmp) | 36.19 | National Highway Division-III |  |  | 30% | 1.72 | 45% | 28.74 | 75% | 30.46 | Work in progress | Depart mental
59 | Resurfacing of Approach Road to Govt.Middle School Bairabi (Bairabi Govt.Middle School Bairabi) | 6.58 | National Highway Division-III |  |  | 100% | 6.32 |  |  | 100% | 6.32 | Completed | Depart mental
60 | Construction of retaining Wall at Ch.1.200 Kmp on Zophai Road | 8.14 | National Highway Division-III |  |  | 100% | 6.1 |  |  | 100% | 6.1 | Completed | Depart mental
61 | Resurfacing of Approach Road to Bairabi Bazar from NH-154 (Muantea's House-Bairabi Bazar) | 1.38 | National Highway Division-III |  |  | 100% | 1.32 |  |  | 100% | 1.32 | Completed | Depart mental
62 | Resurfacing of Vety Office to Approach Road to FCI Godown Bairabi (Vety Office to FCI Godown) | 9.76 | National Highway Division-III |  |  | 100% | 9.38 |  |  | 100% | 9.38 | Work in progress | Depart mental
63 | Resurfacing of Approach Road to Tourist Lodge Bairabi (Bairabi (NH-154) to Tourist Lodge Bairabi) | 4.45 | National Highway Division-III |  |  | 100% | 4.27 |  |  | 100% | 4.27 | Completed | Depart mental
64 | Re-Construction of Retaining Wall at Ch.0.500 Kmp (Upstream and Downstream) on Approach Road to Forest Complex at Bairabi | 5.45 | National Highway Division-III |  |  | 100% | 5.23 |  |  | 100% | 5.23 | Completed | Depart mental
65 | Patch Repair and Resurfacing of NH-54 to PWD Complex and PWD IB (Tlangnuam) Vairengte | 17.18 | National Highway Division-III |  |  | 100% | 16.51 |  |  | 100% | 16.51 | Completed | Depart mental
66 | Resurfacing of Approach Road to Highway Restaurant, Thingdawl (Thingdawl NH-54) | 4.15 | National Highway Division-III |  |  | 100% | 3.1 |  | 1.04 | 100% | 4.14 | Completed | Depart mental
67 | Patches Repair of Approach Road from NH-54 to NHD-III Office at Thingdawl | 5.3 | National Highway Division-III |  |  | 100% | 4.37 |  | 0.93 | 100% | 5.3 | Completed | Depart mental
68 | Resurfacing of Approach Road to District Park Thingdawl (Thingdawl NH-54) Part 2 | 0.84 | National Highway Division-III |  |  | 100% | 0.36 |  | 0.48 | 100% | 0.84 | Completed | Depart mental
69 | Resurfacing of Approach Road to High School Bairabi (Bairabi (NH-154) to High School Bairabi | 5.12 | National Highway Division-III |  |  | 100% | 12.78 |  |  | 100% | 12.78 | Completed | Depart mental
70 | YMA Field Approach Road (Field Veng) Vairengte | 10.21 | National Highway Division-III |  |  | 100% |  |  |  | 100% |  | Completed | Depart mental
71 | Reconstruction of Wing wall Foundation collapsed at Ch.91.30 Kmp on NH54/6 within Kolasib | 7.61 | National Highway Division-III |  |  | 100% |  |  |  | 100% |  | Completed | Depart mental
72 | Reconstruction of Retaining wall at Chainage 92.45 Kmp on NH54/6 within Kolasib | 4.05 | National Highway Division-III |  |  | 100% |  |  |  | 100% |  | Completed | Depart mental
73 | Resurfacing of Approach Road to Jeep Road from NH-54 at Thingdawl part 2 | 2.44 | National Highway Division-III |  |  | 100% |  |  |  | 100% |  | Completed | Depart mental
74 | Resurfacing of Approach Road to Middle School at Thingdawl | 4.05 | National Highway Division-III |  |  | 100% |  |  |  | 100% |  | Completed | Depart mental
75 | Annual Plan (5054) for 2024-2025 | 258.73 | Champhai Division |  |  | 39.16% | 26.58 | 13.34% | 20.09 | 52.5% | 46.67 | Work in progress
76 | Strengthening and Improvement of the state Highways and other state Roads under Mizoram | 218.6 | Kawrthah Division |  |  |  |  | 57.76% |  | 57.76% |  | Work in progress | Depart mental
77 | Improvement and Strengthening of Roads under 5054 (R&B) | 201.19 | Lunglei Road Division-II |  |  | 30.73% | 48.71 |  | 47.55 | 30.73% | 96.26 | Work in progress
78 | Pothole filling and Resurfacing of Er.VL.Khuma Residence to council veng via Council Veng Hall Road | 17.09 | Siaha Division | 30.11.24 | 31.12.24 | 100% | 16.43 |  |  | 100% | 16.43 | Work completed
79 | Pothole filling and resurfacing of approach road to College vaih Cemetary fro College vaih-I (Govt | 16.73 | Siaha Division | 08.01.25 | 31.03.25 | 100% | 16.08 |  |  | 100% | 16.08 | Work completed
80 | Resurfacing of approach road to SP Office Siaha (Police Station Main Gate to SP Office Siaha) | 9.02 | Siaha Division | 16.10.24 | 30.10.24 | 100% | 8.67 |  |  | 100% | 8.67 | Work completed
81 | Pothole filling and Resurfacing of DC Office to DCSO Office via Irrigation Office at Siaha Vengpui | 6.8 | Siaha Division | 27.10.25 | 31.03.25 | 100% | 6.54 |  |  | 100% | 6.54 | Work completed
82 | Construction of Masonry Retaining Eall at 0.210Km on AOC, College Veng to Siaha Tlangkawn Road | 9.42 | Siaha Division | 06.11.24 | 12.12.24 | 100% | 9.05 |  |  | 100% | 9.05 | Work completed
83 | Pothole filling and Resurfacing of MADC Office Civil Hospital via GMDIC Qtr (MADC Office to Thanakawn) | 15.57 | Siaha Division | 22.10.24 | 31.11.24 | 100% | 14.97 |  |  | 100% | 14.97 | Work completed
84 | Resurfacing to Vetykawn to Saihatlangkawn via IB road | 6.78 | Siaha Division | 07.10.24 | 31.10.24 | 100% | 6.52 |  |  | 100% | 6.52 | Work completed
85 | Pothole filling and Resurfacing of Meisatla to NH54B via ECM Meisatla (New Excise Office Meisatla School-II) | 21.18 | Siaha Division | 09.11.24 | 31.11.24 | 100% | 20.36 |  |  | 100% | 20.36 | Work completed
86 | Re-Construction of RCC Slab Culvert at 0.400Km on New Saiha Vetykawn to Siahatlangkawn via AR | 5 | Siaha Division | 05.11.24 | 31.12.24 | 100% | 4.81 |  |  | 100% | 4.81 | Work phy. completed
87 | Loweing of Culvert bed and RCC side drains at 0.800Km on N.Colony Saiha to Meisatla via Meisavaih road (N.Colony to Meisatla) | 1.14 | Siaha Division |  |  | 50% |  | 50% | 1.09 | 100% | 1.09 | Work completed
88 | Strengthening of Tuipang 'V'-Tuipang 'L' Road (Tuipang Lal Veng Peng Thuam-Waiting shed Tuipang 'V') | 31.28 | Siaha Division | 20.11.24 | 31.03.25 | 70% | 17 | 30% | 12.77 | 100% | 29.77 | Work phy. completed
89 | Patch Repair and Pot hole filling, Resurfacing and Seal coat of PWD Complex to NH54 at Tipa (PWD Complex-Waiting Shed NH-54) (0.000Km - 0.905 Km) | 22 | Siaha Division | 15.01.25 | 30.03.25 |  |  | 100% | 20.94 | 100% | 20.94 | Work phy. completed
90 | Strengthening of Chheihlu-Chakhang Road (0.00-12.00 Km) | 14.54 | Siaha Division | 05.02.25 | 31.03.25 | [6 empty] | Material collection
91 | Repair of Slab Culvert Collapsed on Kawlchaw - Serkawr Road (0.00 - 9.10 Km) at Ch: 0.120Km | 4.09 | Siaha Division | 14.10.24 | 31.11.24 | 100% |  |  | 3.89 | 100% | 3.89 | Work phy. completed
92 | Repair of RCC Slab Culvert Wingwall Collapsed on Theiri-Tuisih Road (0.00 -7.50 Km at Chainage 5.600 Km | 7.07 | Siaha Division | 20.11.24 | 10.12.24 | 100% | 0.6 |  | 6.13 | 100% | 6.73 | Work phy. completed
93 | Repair of RCC Slab Culvert Wingwall Collapsed on Chheihlu-Chakhang Road (0.00-12.00Km) at Chainage 1.300 Km | 7.5 | Siaha Division | 22.11.24 | 10.12.24 | 100% | 7.2 |  |  | 100% | 7.2 | Work completed
94 | Repair of RCC Slab Culvert Wingwall Collapsed on Chheihlu-Chakhang Road (0.00-12.00Km) at Chainage 7.000 Km | 7.49 | Siaha Division | 22.11.25 | 15.12.25 | 100% | 7.12 |  |  | 100% | 7.12 | Work completed
95 | Pothole filling, Patch Repair & Resurfacing of Siaha - Niawhtlang Road (Tlangpui to Niawhtlang) (7.00 - 14.000) Kmp, Phase - I | 26.83 | Siaha Division | 15.01.24 | 31.03.25 |  |  | 75% |  | 75% |  | Work in progress
96 | Pothole filling, Patch Repair & Resurfacing of Siachangkawn - Vawmbuk Road (0.000-6.000) Kmp, Phase - I | 23.9 | Siaha Division | 02.02.24 | 31.03.25 | 75% | 14 | 25% | 8.97 | 100% | 22.97 | Work phy. completed
97 | Construction of RCC Slab Culvert on Siachangkawn - Vawmbuk Road at 3.250 Kmp | 13.23 | Siaha Division | 02.02.24 | 31.03.25 | 80% |  | 20% | 12.7 | 100% | 12.7 | Work phy. completed
98 | Construction of RCC Slab Culvert on Siaha to Tuisumpui Road at Ch 12.05Kmp | 19.22 | Siaha Division | 03.12.24 | 03.06.25 |  |  | 60% |  | 60% |  | Work in progress
99 | Construction of Gabion wall on Siaha to Tuisumpui Road at Ch.12.08Km | 28.49 | Siaha Division | 03.12.24 | 03.06.25 |  |  | 60% |  | 60% |  | Work in progress
100 | Restoration of collapsed retaining wall on Chhuarlung-Ainak Road (0.00-10.90)Kmp at Ch.4.70 Kmp (Ht.-4.8m) | 15.83 | Siaha Division | 03.12.24 | 03.06.25 | 70% |  | 30% |  | 100% |  | Work phy. completed
101 | Restoration of collapsed retaining wall on Siaha - Niawhtlang Road (0.00-14.00) Kmp at Ch.4.300 Kmp (Ht.=3.0m) | 4.39 | Siaha Division | 03.12.24 | 03.06.25 | 50% |  | 25% |  | 75% |  | Work in progress
| TOTAL | 334.59 | [8 empty] | 215.84
102 | Strengthening and Improvement of State Highways and other State Roads under Mizoram under Central Circle (Sh: Improvement of Road Infrastructure under Hmuifang Division, PWD for the year 2024-25) | 408.1 | Hmuifang Division | 10.10.24 | 10.03.25 |  |  |  | 78.78 |  | 78.78 | Work in progress | Item Rate
103 | Improvement of Thenzawl to Zote Road (Sh: Construction of PCC Pavement & HP Culvert) | 30.51 | Hmuifang Division | 16.12.24 | 16.06.25 |  |  | 93% |  | 93% |  | Work in progress | Item Rate
Strengthening and Improvement of State Highways and other State Roads under Mizoram under Central Circle
SUB-DIVISION-I
104 | Resurfacing of Magazine Kawn Armed Veng South Cemetary | 620 | Aizawl Road North Division | 2.12.24 | 14.12.24 | 100% | 13.92 |  |  | 100% | 13.92 | Phy. Completed | Departmental
105 | Patch repair and full seal coating of Ramthar Tlang Veng to St.Lorence School | 340 | Aizawl Road North Division | 4.12.24 | 17.12.24 | 100% | 6.15 |  |  | 100% | 6.15 | Phy. Completed | Departmental
SUB-DIVISION-II
106 | Patch Repair and Full Seal coating of Bawngkawn to Chanmari via Chaltlang | 53.38 | Aizawl Road North Division | 14.10.24 | 01.03.25 | 70% | 36.6 |  | 7.37 | 70% | 43.97 | On going | Departmental
107 | Patch Repair and Full Seal coating DIET Complex and approach road to Laikunga's House | 19.83 | Aizawl Road North Division | 14.11.24 | 01.03.25 | 100% | 16.64 |  |  | 100% | 16.64 | Phy. Completed | Departmental
108 | Patch Repair and Full Seal Coating of Thuampui to Selesih Road | 51.33 | Aizawl Road North Division | 28.10.24 | 01.03.25 | 50% | 31.82 |  | 10.65 | 50% | 42.47 | On going | Departmental
109 | Patch Repair and Full Seal Coating of Approach road to ATC at Durtlang | 27.77 | Aizawl Road North Division | 15.10.24 | 01.03.25 | 100% | 22.9 |  |  | 100% | 22.9 | Phy. Completed | Departmental
110 | Patch Repair and Full Seal Coating of Approach road to MKVI at Zemabawk | 5.21 | Aizawl Road North Division | 11.10.24 | 01.03.25 | 100% | 4.37 |  |  | 100% | 4.37 | Phy. Completed | Departmental
111 | Patch Repair and Full Seal Coating of Approach road to Jeriko Khualbuk at Durtlang | 13.5 | Aizawl Road North Division | 18.10.24 | 01.03.25 | 100% | 11.25 |  |  | 100% | 11.25 | Phy. Completed | Departmental
112 | Patch Repair and Full Seal Coating of Upper Hermon Road at Durtlang | 2.57 | Aizawl Road North Division | 16.11.24 | 01.03.25 | 100% | 2.13 |  |  | 100% | 2.13 | Phy. Completed | Departmental
113 | Patch Repair and Full Seal Coating of Centenary Road at Durtlang | 15.5 | Aizawl Road North Division | 28.10.24 | 01.03.25 | 70% | 9.91 | 30% |  | 100% | 9.91 | On going | Departmental
114 | Patch Repair and Full Seal Coating of Durtlang Dawrkawn to Thuampui Selesih Road | 7.38 | Aizawl Road North Division | 16.10.24 | 01.03.25 | 100% | 6.08 |  |  | 100% | 6.08 | Phy. Completed | Departmental
115 | Improvement of Y-Road Junction and Seal Coating of Left Side of Y-Road | 12 | Aizawl Road North Division | 14.10.24 | 01.03.25 |  | 10.48 | 100% |  | 100% | 10.48 | Phy. Completed | Departmental
116 | Construction of concrete Pavement & patch Repair Seal Coating of Durtlang Leitan to Muthi Road | 40.61 | Aizawl Road North Division | 23.11.24 | 01.03.25 | 50% |  | 50% | 20.34 | 100% | 20.34 | Phy. Completed | Departmental
117 | Construction of concrete Pavement of Durtlang Leitan Thlanmual Road | 45 | Aizawl Road North Division | 23.11.24 | 01.03.25 | 50% |  | 50% | 31.81 | 100% | 31.81 | Phy. Completed | Departmental
SUB DIVISION-III
118 | Patch Repair and Seal Coating of Ropaiabawk to Tuithum via PWD Camp | 36.27 | Aizawl Road North Division | 14.10.24 | 01.03.25 | 100% | 36.26 |  |  | 100% | 36.26 | Phy. Completed | Departmental
119 | Improvement of Roads between Chhangurkawn to Pu Thansanga's House at Luangmual (Drain with cover) | 5.69 | Aizawl Road North Division | 14.10.24 | 01.03.25 | 60% |  | 10% | 3.79 | 70% | 3.79 | Work in progress | Departmental
120 | Construction of RCC Side Drain with Cover near Lala Khawbung house at Luangmual | 3.21 | Aizawl Road North Division | 14.10.24 | 01.03.25 | 100% | 3.2 |  |  | 100% | 3.2 | Phy. Completed | Departmental
121 | Construction of RCC Side Drain and clearance of Choked between Chhangurkawn to Ainawn Road | 2.39 | Aizawl Road North Division | 14.10.24 | 01.03.25 | 100% | 2.39 |  |  | 100% | 2.39 | Phy. Completed | Departmental
122 | Patch Repair and full seal coating of Chhangurkawn to Ainawn & Zonuam Outpost to Ainawn | 44.09 | Aizawl Road North Division | 14.10.24 | 01.03.25 | 80% | 44.09 | 10% |  | 90% | 44.09 | Work in progress | Departmental
123 | Patch Repair and full seal coating of Approach Road to Zotlang and Zotlang Internal Road | 30.21 | Aizawl Road North Division | 14.10.24 | 01.03.25 | 90% | 27.19 | 10% |  | 100% | 27.19 | Work in progress | Departmental
124 | Widening of road from Pu PC Lalremsiama House's to Ropaiabawk below Pu Lalduhawma's House | 35.02 | Aizawl Road North Division | 14.10.24 | 01.03.25 | 90% | 35.01 | 10% |  | 100% | 35.01 | Work in progress | Departmental
ADDITIONAL
125 | Construction of Retaining wall below Pu Thansanga's House at Luangmual | 7.82 | Aizawl Road North Division | 14.10.24 | 01.03.25 | 100% | 7.82 |  |  | 100% | 7.82 | Phy. Completed | Departmental
126 | Construction of Retaining wall below Pi Thanhrangi's House at Ainawn | 4.72 | Aizawl Road North Division | 14.10.24 | 01.03.25 | 100% | 4.71 |  |  | 100% | 4.71 | Phy. Completed | Departmental
127 | Construction of Retaining wall at Chanmari Edenthar Road under Aizawl Road North Sub-Division-III | 3.4 | Aizawl Road North Division | 14.10.24 | 01.03.25 | 100% | 3.4 |  |  | 100% | 3.4 | Phy. Completed | Departmental
128 | Patch Repair of Zoological Park to PTC Main Gate | 18 | Aizawl Road North Division | 11.11.24 | 03.12.24 |  |  | 100% | 18 | 100% | 18 | Phy. Completed | Departmental
129 | Patch Repair and Seal Coating of approach road to Tanhril, Aizawl | 20 | Aizawl Road North Division | 17.12.24 | 12.01.25 |  |  | 100% | 18.82 | 100% | 18.82 | Phy. Completed | Departmental
130 | Resurfacing of Zonuam Internal Road (Zonuam - Ramrikawn Road) | 17.5 | Aizawl Road North Division | 20.01.25 | 27.02.25 |  |  | 10% | 16.5 | 10% | 16.5 | Work in progress | Departmental
131 | Resurfacing of approach road to Circuit House | 194.95 | Tlabung division |  |  | 100% | 189.98 |  |  | 100% | 189.95 | Completed
132 | Construction of Bailey Bridge (TS) over R.Tlawngte lui at Ch.2.840 Kmp on Thinghlun to Hriphaw | 71 | Kawrthah Division | 21.10.24 | 31.1.25 | 75% | 53.99 | 20% | 13.5 | 95% | 67.49 | 99% of supply bill has been paid and it is expected to deliver the bridge components by the supplier i.e Essen by February, 2025 | Deprtmental
133 | Construction of Bailey Bridge (DS) over R.Tlawngte lui at Ch.0.800 Kmp on Thinghlun to Hriphaw Road | 48 | Kawrthah Division | 21.10.24 | 31.1.25 | 75% | 36.87 | 20% | 9.22 | 95% | 46.09
134 | Construction of Bailey Bridge (DS) over R.Tlawngte lui at Ch.0.900 Kmp on Thinghlun to Hriphaw Road | 48 | Kawrthah Division | 21.10.24 | 13.1.25 | 75% | 36.87 | 20% | 9.22 | 95% | 46.09
135 | Construction of Bailey Bridge (DS) over R.Hnang lui on Chuhvel to BOP Road | 48 | Kawrthah Division | 22.10.24 | 13.1.25 | 75% | 36.87 | 20% | 9.22 | 95% | 46.09
136 | Construction of Auto Rickshaw Plyable Suspension Bridge (Span=50.00m) over River Langkaih on Mizoram to tripura Border at Kanhmun | 50 | Kawrthah Division | 4.10.24 | 31.12.24 | 100% |  |  |  | 100% |  | Completed
137 | Construction of Gabion wall near BUSG Bridge over R.Bawrai lui on Kawrthah side at Bawrai | 15.55 | Kawrthah Division | 1.11.24 | 31.1.2025 | 100% |  |  | 15.55 | 100% | 15.55 | Completed | Contract after call of open Tender
138 | Resurfacing of NH54 to Ramhlun via Auditorium, Serchhip | 21.91 | Serchhip Division |  | 31.3.25 | [6 empty] | Material collection Work in progress
139 | Construction of R/W below R.Chhuanthang House on Venghlun-Chanmari Road Chhiahtlang | 4.42 | Serchhip Division |  | 31.3.25 | [6 empty] | Material collection Work in progress
140 | Pothole filling and Resurfacing on Ramliaa(L) house- Thumbawk (NH), Serchhip | 13.82 | Serchhip Division |  | 31.3.25 | [6 empty] | Material collection Work in progress

## 3054
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
| Source of funding : (3054) Maintenance Action Plane During 2024-2025 | [8 empty] | Month : February 2025
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Resurfacing pf Approach Road to Helipad | 52.82 | Tlabung Division |  |  | 100% | 52.82 |  |  | 100% | 52.82 | Completed
2 | Annual Maintenance Operation Plan 2024-25 (3054) | 58.18 | Kawrthah Division | 18.10.24 | 31.3.25 |  |  | 67% | 31.82 | 67% | 31.82 | Completed
3 | Annual Maintenance Operation Plan 2024-25 (3054) 1) Resurfacing of Hriphaw Town Road (Lal veng - Chhimveng) at Hriphaw | 218.6 | Kawrthah Division | 18.10.24 | 31.3.25 |  |  | 75% | 58.88 | 75% | 58.88 | Work in progress | Departmental
3 | Restoration of Damaged wing wall of Assam Road Tuikhuah Bridge at Ch.1.300 Kmp on KDZKT Road. (Sh: Construction of Gabion structure Reatining wall/Wing wall) | 8.5 | Kawrthah Division | 18.10.24 | 15.12.24 | 100% |  |  |  | 100% |  | Completed | Departmental
4 | Restoration of Wing wall of slab culvert at Ch/1.500 Kmp pn KDZKT Road | 6.07 | Kawrthah Division | 3.10.24 | 5.12.24 | 100% | 6.07 |  |  | 100% | 6.07 | Completed | Departmental
5 | Painting of RCC Bridge over River Goboilui on KDZKT Road | 1 | Kawrthah Division | 3.10.25 | 5.12.25 | 100% | 1 |  |  | 100% | 1 | Completed | Departmental
6 | Resurfacing of Approach Road to Graveyard No/II High School Road | 57.59 | Lunglei Road Division-II |  |  |  |  | 62% | 11.89 | 62% | 11.89 | Work in progress
Annual Maintenance Operation Plan 2024-2025
7 | Resurfacing of Sihtuikhur to Bethlehem Vengthlang Kawn | 15.16 | Aizawl Road South Division | 9.9.24 | 8.10.24 | 100% | 15.16 |  |  | 100% | 15.16 | Completed | Departmental
8 | Patch Repair & Resurfacing of Kulikawn to Saikhamkawn via Hridaikawn (CP Road) Road (Section : 1.784 -2.710 Km) | 24.19 | Aizawl Road South Division | 19.7.24 | 13.8.24 | 100% | 24.19 |  |  | 100% | 24.19 | Completed | Departmental
9 | Resurfacing of ITI Mualmawi Ring Road-II at Ch 0.280-0.550 Kmp | 8.19 | Aizawl Road South Division | 17.9.24 | 10.10.24 | 100% | 8.19 |  |  | 100% | 8.19 | Completed | Departmental
10 | Pot hole filling and Patch Repair of Shivaji to Bungkawn | 1.2 | Aizawl Road South Division | 23.7.24 | 7.8.24 | 100% | 1.2 |  |  | 100% | 1.2 | Completed | Departmental
11 | Resurfacing of College Vengthlang Approach Road (PUC to College Vengthlang Road) | 4.96 | Aizawl Road South Division | 9.9.24 | 8.10.24 | 100% | 4.96 |  |  | 100% | 4.96 | Completed | Departmental
12 | Restoration of Road Formation by Construction of Retaining Wall near Pu H.Lalnuntluanga's House on ITI Ring Road-II | 2.9 | Aizawl Road South Division | 11.9.24 | 27.9.24 | 100% | 2.9 |  |  | 100% | 2.9 | Completed | Departmental
13 | Resurfacing of Venghlui to Bethlehem (Upper) | 8.47 | Aizawl Road South Division | 10.9.24 | 9.10.24 | 100% | 8.47 |  |  | 100% | 8.47 | Completed | Departmental
14 | Pothole Filling and Resurfacing of Maubawk Baptist Church to Kawnveng 0.000-0.250Kmp | 8.76 | Aizawl Road South Division | 8.7.24 | 27.7.24 | 100% | 5.76 |  |  | 100% | 5.76 | Completed | Departmental
15 | Resurfacing of Approach Road to to Tlangnuam PlayField | 3.91 | Aizawl Road South Division | 18.7.24 | 30.7.24 | 100% | 3.91 |  |  | 100% | 3.91 | Completed | Departmental
16 | Oatch Repair and Resurfacing of Approach Road to ICDS Complex at Tlangnuam (0.000-0.240Kmp) | 5.89 | Aizawl Road South Division | 18.7.24 | 5.8.24 | 100% | 5.89 |  |  | 100% | 5.89 | Completed | Departmental
17 | Seal Coating of AOC to PWD Circle Office Road | 2.48 | Aizawl Road South Division | 23.7.24 | 7.8.24 | 100% | 2.48 |  |  | 100% | 2.48 | Completed | Departmental
18 | Additional work of completion of R/Wall below CEO's Qrts, MINECO | 4.7 | Aizawl Road South Division | 23.7.24 | 1.8.24 | 100% | 4.7 |  |  | 100% | 4.7 | Completed | Departmental
19 | Pothole Filling and patch repair with full seal coat of Mualmawi Junction to Mualmawi Ringroad -III (Entry point at ITI) | 1.5 | Aizawl Road South Division | 1.10.24 | 9.10.24 | 100% | 1.5 |  |  | 100% | 1.5 | Completed | Departmental
20 | Re-construction of RCC Slab Culvert on venghlui to Bethlehem upper | 0.97 | Aizawl Road South Division | 16.7.24 | 27.8.24 | 100% | 0.97 |  |  | 100% | 0.97 | Completed | Departmental

## SASCI
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
| Source of funding : SPECIAL ASSISTANT TO STATE FOR CAPITAL INVESTMENT | [7 empty] | Month : FEBRUARY, 2025
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
LUNGLEI BUILDING PROJECT DIVISION : 2022-2023
1 | Construction of Circuit House at Hnahthial 'A' | 304 | Lunglei Building Project Division | 13.04.23 | 13.10.24 | 73% |  | 10% | 107.28 | 83% | 107.28 | Work in progress | Restricted Tender
2 | Construction of Circuit House at Hnahthial 'B' | 200 | Lunglei Building Project Division
3 | (a) Const. of Laboratory Building at Civil Hospital Lunglei (Ground floor) | 192 | Lunglei Building Project Division | 28.10.21 | 28.10.22 | 100% | 192.98 |  |  | 100% | 192.98 | Completed | Restricted Tender
4 | (b) Const. of Laboratory Building at Civil Hospital, Lunglei (1st & 2nd floor) Supplementary Works | 396 | Lunglei Building Project Division | 28.10.22 | 28.04.24 | 100% | 290.45 |  | 40.25 | 100% | 330.7 | Civil work completed and I/E workamount to Rs 21.5 lakhs transfer to EE(elect) LLI & not yet started | Suplementary Works to the above
5 | Construction of Sangau SDO© Office building at Sangau | 77 | Lunglei Building Project Division | 20.03.23 | 20.03.24 | 100% | 76.81 |  |  | 100% | 76.81 | Completed | Spot Quotation
6 | Construction of SDO© Quarter at Sangau | 80 | Lunglei Building Project Division | 20.03.23 | 20.03.24 | 100% | 79.87 |  |  | 100% | 79.87 | Completed | Spot Quotation
7 | Construction of Staff Quarter(2 Units) at Sangau | 50.45 | Lunglei Building Project Division | 20.03.23 | 20.03.24 | 100% | 50.37 |  |  | 100% | 50.37 | Completed | Spot Quotation
8 | Construction of Meisatla Futsal Ground at Siaha | 34.79 | Lunglei Building Project Division | 20.03.23 | 20.09.23 | 49% | 21.84 |  |  | 49% | 21.84 | Work in progress | Spot Quotation
9 | Construction of Community Hall at Lungrang 'S' | 40 | Lunglei Building Project Division | 20.03.23 | 20.03.24 | 80% | 15.25 | 13% | 10.48 | 93% | 25.73 | Work in progress | Spot Quotation
10 | Construction of Community Hall at New Sachan | 27.47 | Lunglei Building Project Division | 20.03.23 | 20.09.23 | 100% | 27.46 |  |  | 100% | 27.46 | Completed | Spot Quotation
A. Construction of Government Building at Hnahthial, PWD EE Quarters, Circuit House & DC office under SASCI 2023-2024
11 | Const. of PWD EE Quarters at Hnahthial. | 150 | Lunglei Building Project Division | 23.03.23 | 23.03.26 | 15% | 269.86 | 10% | 0 | 25% | 269.86 | Work in progress | Works alloted to C Lalfakzuala Aizawl through Restricted tender
12 | Hnahthial Circuit House. | 200 | Lunglei Building Project Division | 23.03.23 | 23.03.26 | 73% |  | 5% |  | 78% |  | Work in progress
B. Construction of Community Hall at Siasi, Phurai, Tawngkawlong, Tipa B, Meisavaih, Amotlah.
13 | Const. and Completion of MTP(H) Office. | 10 | Lunglei Building Project Division | 23.03.24 | 23.07.25 | 100% | 101.65 |  |  | 100% | 101.65 | Completed | Works alloted to S. Paaw, Siaha through Restrictred tender
14 | Const. of MTP Information Office | 15 | Lunglei Building Project Division | 23.03.24 | 23.07.25 | 100% |  |  |  | 100% |  | Completed
15 | Const. of Bazar Shed at New Siaha East-II | 17 | Lunglei Building Project Division | 23.03.24 | 23.07.25 | 100% |  |  |  | 100% |  | Completed
16 | Continuation of MYA Hall at New Siaha East-I | 20 | Lunglei Building Project Division | 23.03.24 | 23.07.25 | 100% |  |  | 0 | 100% |  | Completed
17 | Const. of MTP Hall and Retaining Wall at Amotlah. | 20 | Lunglei Building Project Division | 23.03.24 | 23.07.25 | 100% |  |  |  | 100% |  | Completed
18 | Const. of Model Middle School Ground and Retaining Wall at New Siaha West-I | 15 | Lunglei Building Project Division | 23.03.24 | 23.07.25 | 100% |  |  |  | 100% |  | Completed
19 | Const. of Retaining Wall at Futsal Ground at Tuipui Ferry. | 10 | Lunglei Building Project Division | 23.03.24 | 23.07.25 | 100% |  |  |  | 100% |  | Phy.Completed
C. Construction of Playground with Pavillion at Lungtian, Sangau, Bualpui(NG), Tuichawngtlang, Ngunlingkhua, T.Dumzau.
20 | Renovation of Community Hall Ramhlun Veng, Sangau. | 30 | Lunglei Building Project Division | 23.03.24 | 23.07.25 | 100% |  |  |  | 100% |  | Completed | Works alloted to F. Lalkaisanga, Lawngtlai through Restrictred tender
21 | Const. of Community Hall at Council Veng, Lawngtlai. | 30 | Lunglei Building Project Division | 23.03.24 | 23.07.25 | 80% |  | 5% |  | 85% |  | Work in progress
22 | Vertical Extention of Central Young Lai Association Office, Lawngtlai. | 10 | Lunglei Building Project Division | 23.03.24 | 23.07.25 | 100% |  |  |  | 100% |  | Completed
23 | Const. of Futsal Ground at Lungtian-I | 30 | Lunglei Building Project Division | 23.03.24 | 23.07.25 | 100% | 146.21 |  | 0 | 100% | 146.21 | Completed
24 | Const. of Futsal Ground at Bualpui (NG) | 30 | Lunglei Building Project Division | 23.03.24 | 23.07.25 | 100% |  |  |  | 100% |  | Completed
25 | Const. of Futsal Ground at Sangau. | 30 | Lunglei Building Project Division | 23.03.24 | 23.07.25 | 100% |  |  |  | 100% |  | Completed
26 | Const. of Volleyball Court at Lungzalhtum. | 10 | Lunglei Building Project Division | 23.03.24 | 23.07.25 | 100% |  |  |  | 100% |  | Completed
D. Construction of Community Hall Cum Market Building at Luangmual, Lunglei.
27 | Const. of DM High School Building (Theiriat) | 35 | Lunglei Building Project Division | 23.03.24 | 23.07.25 | 100% |  |  |  | 100% |  | Completed | Works alloted to Lalnghinga Serkawn through Restrictred tender
28 | Const. of Luangmual Market Building, Lunglei | 80 | Lunglei Building Project Division | 23.03.24 | 23.07.25 | 100% | 132.21 |  | 0 | 100% | 132.21 | Completed
29 | Const. of Sairep Community Hall | 20 | Lunglei Building Project Division | 23.03.24 | 23.07.25 | 100% |  |  |  | 100% |  | Completed
E. Vertical Extention of Market Building at Kamalanagar.
30 | Vertical Extention of Existing Bazar Building at Kamalanagar-I with Tin Roofing. | 50 | Lunglei Building Project Division | 23.03.24 | 23.07.25 | 37% | 10.02 | 3% | 12.9 | 40% | 22.9 | Work in progress | Works alloted to Lalrovi Hunthar through Restrictred tender
31 | Const. of Additional Bazar Building by Demolishing the existing dilapidated building that was constructed under BADP | 50 | Lunglei Building Project Division | 23.03.24 | 23.07.25 | 37% |  | 3% |  | 40% |  | Work in progress
32 | 2.Const. of Rest House at PWD Complex Bunghmun. | 24.52 | Lunglei Building Project Division | 23.03.24 | 23.07.25 | 37% |  | 3% |  | 40% |  | Work in progress
F. Construction of Community Hall Cum Health Clinic Center at Kawlhawk, Bungtlang West, South Lungdai and Serte.
33 | Const. of Higher Secondary School Building, Buarpui. | 30 | Lunglei Building Project Division | 23.03.24 | 23.07.25 | 100% | 86.25 |  | 16.79 | 100% | 103.04 | Completed | Works alloted to Samson Zoramthanga, Chanmari, Lunglei through Restricted tender
34 | Const. of Community Hall, Kawlhawk | 30 | Lunglei Building Project Division | 23.03.24 | 23.07.25 | 100% |  |  |  | 100% |  | Completed
35 | Const. of Health Clinic Bungtlang West. | 10 | Lunglei Building Project Division | 23.03.24 | 23.07.25 | 100% |  |  |  | 100% |  | Completed
36 | PWD IB repair, Sertlangpui | 5 | Lunglei Building Project Division | 23.03.24 | 23.07.25 | 100% |  |  |  | 100% |  | Completed
37 | Const. of Badminton Hall at Chhipphir. | 5 | Lunglei Building Project Division | 23.03.24 | 23.07.25 | 95% |  |  |  | 95% |  | Work in progress
38 | Completion of Badminton Hall at Chhipphir | 5 | Lunglei Building Project Division | 23.03.24 | 23.07.25 | 95% |  |  |  | 95% |  | Work in progress
39 | Anganwadi Centre-I, Sertlangpui | 5 | Lunglei Building Project Division | 23.03.24 | 23.07.25 | 100% |  |  |  | 100% |  | Completed
40 | Anganwadi Centre-I New Const. Serte. | 5 | Lunglei Building Project Division | 23.03.24 | 23.07.25 | 100% |  |  |  | 100% |  | Phy.Completed
41 | Health and Wellness Officer Quarter new const. Serte | 5 | Lunglei Building Project Division | 23.03.24 | 23.07.25 | 100% |  |  |  | 100% |  | Phy.Completed
42 | Health Clinic Office, South Lungdai | 10 | Lunglei Building Project Division | 23.03.24 | 23.07.25 | 100% |  |  |  | 100% |  | Phy.Completed
43 | Const. of Futsal Ground Flooring at Lalveng, Haulawng. | 5 | Lunglei Building Project Division | 23.03.24 | 23.07.25 | 100% |  | 0% |  | 100% |  | Phy.Completed
44 | Constn of Meisatla Futsal Ground at Siaha | 34.79 | Lunglei Building Project Division | 20.03.23 | 20.09.23 | 49% | 21.84 | 0% | 0 | 49% | 21.84 | work not completed due to site disputed
45 | Constn of Community Hall at Lungrang S | 40 | Lunglei Building Project Division | 20.03.23 | 20.03.24 | 80% | 15.25 | 18% | 10.48 | 98% | 25.73 | Work in progress
| Total of Lunglei Building Project Division | 2403.23 |  |  |  |  | 1501.23 |  | 187.7 |  | 1688.91
AIZAWL ROAD NORTH DIVISION
2. CONSTRUCTION AND UPGRADATION OF ROAD FROM RAMTHAR - RAMTHAR NORTH - ZARKAWT -SARON, AIZAWL: 2022-23
44 | Construction of Ahimsa to Jail Veng road at Zarkawt. | 77.98 | Aizawl Road North Division | 02.05.23 | 30.11.23 | 70% | 250.02 | 10% | 0.4 | 80% | 250.42 | Completed | Spot Quotation
45 | Counterfort Retaining Wall at Armed Veng. | 41.22 | Aizawl Road North Division |  |  | 100% |  |  |  | 100% |  | Completed | Spot Quotation
46 | Toe Walls at Armed Veng Side | 31.44 | Aizawl Road North Division |  |  | 100% |  |  |  | 100% |  | Completed | Spot Quotation
47 | Retaining Wall at Ramthar Side | 30.21 | Aizawl Road North Division |  |  | 100% |  |  |  | 100% |  | Completed | Spot Quotation
48 | Const. of RCC Link Drain near Rallianzuala Land. | 50.65 | Aizawl Road North Division |  |  | 100% |  |  |  | 100% |  | Completed | Spot Quotation
SUB-DIVISION - I
CONSTRUCTION OF RCC DRAIN AND RCC PAVEMENT AT CHHINGA VENG AND ELECTRIC VENG. SASCI 2023-2024
49 | Resurfacing of Armed Veng South to Bethlehem Vengthlang Road at Ch : 0.677 - 1.230 Km. | 10.91 | Aizawl Road North Division | 06.12.23 | 15.12.23 | 100% |  |  |  | 100% |  | Completed | Restricted Tender
50 | Re-const. of Collapsed RCC Slab Culvert on Armed Veng South to Bethlehem Vengthlang (Old Zoo Road ) near Rawra chhutna. | 1.2 | Aizawl Road North Division |  |  | 100% |  |  |  | 100% |  | Completed | Restricted Tender
51 | Balance Work of Const. of RCC Pavement on District Jail to Lower Armed Veng Road (Service Road) | 1.84 | Aizawl Road North Division | 10.04.23 | 11.04.23 | 100% |  |  |  | 100% |  | Completed | Restricted Tender
52 | Const. of New Road from Lalhmingliana Sailo House to Siamphunga Lei at Tuithiang Phase-II | 30.14 | Aizawl Road North Division | 11.03.24 |  | 100% | 148.09 |  | 0 | 100% | 148.09 | Completed | Restricted Tender
53 | Const. of Drainage System at Aizawl Civil Hospital, Dawrpui West Area | 14.52 | Aizawl Road North Division | 18.03.23 |  | 100% |  |  |  | 100% |  | Completed | Restricted Tender
54 | Const. of Retaining Wall on Dawrpui Thlanmual Plot - 3. | 6.03 | Aizawl Road North Division | 24.04.24 |  | 100% |  |  |  | 100% |  | Completed | Restricted Tender
55 | Const. of RCC Pavement on Hostel Square at Armed Veng South. | 4.17 | Aizawl Road North Division |  |  | 100% |  |  |  | 100% |  | Completed | Restricted Tender
56 | Const. of RCC Pavement between Thansanga House to Ronghakliana House on Armed Veng South Local Council Road. | 2.17 | Aizawl Road North Division |  |  | 100% |  |  |  | 100% |  | Completed | Restricted Tender
57 | Const. of PCC Pavement near Larry Lalrava House Saron Veng. | 4.24 | Aizawl Road North Division | 08.04.24 | 13.04.24 | 100% |  |  |  | 100% |  | Completed | Restricted Tender
58 | Const. of V-Shape Side Drain near Rawra chhutna. | 0.12 | Aizawl Road North Division |  |  | 100% |  |  |  | 100% |  | Completed | Restricted Tender
59 | Const. of Retaining Wall on Dawrpui Thlanmual Plot - 1 | 10.95 | Aizawl Road North Division |  |  | 100% |  |  |  | 100% |  | Completed | Restricted Tender
60 | Const. of Retaining Wall on Dawrpui Thlanmual Plot - 2. | 8.11 | Aizawl Road North Division |  |  | 100% |  |  |  | 100% |  | Completed | Restricted Tender
61 | Const. of Breast Wall on Armed Veng South Local Council Road near Lalnghakliana House. | 5.94 | Aizawl Road North Division | 15.04.24 | 20.04.24 | 100% |  |  |  | 100% |  | Completed | Restricted Tender
62 | Const. of Breast Wall between Chawngneihkunga House to Khupneihvunga House. | 6.41 | Aizawl Road North Division |  |  | 100% |  |  |  | 100% |  | Completed | Restricted Tender
63 | Widening of Road between Chawngneihkunga House to Khupneihvunga House. | 86 | Aizawl Road North Division | 22.04.24 |  | 100% |  |  |  | 100% |  | Completed | Restricted Tender
64 | Const. of Retaining Wall below Chhinga Veng Thlanmual. | 46 | Aizawl Road North Division | 26.02.24 |  | 100% |  |  |  | 100% |  | Completed | Restricted Tender
IMPROVEMENT OF ROAD FROM RAMHLUN VENGTHAR TO RAMHLUN SPORT COMPLEX, AIZAWL.
65 | Const. of RCC Balcony on Ramhlun South Cemetary at Ramhlun South. | 42.94 | Aizawl Road North Division | 08.03.24 |  | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
66 | Const. of RCC Frame Structure Breast Wall near Ramhlun South Cemetary | 25.61 | Aizawl Road North Division | 08.02.24 |  | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
67 | Const. of Retaining Wall below Presbyterian Church, Laipuitlang. | 3.93 | Aizawl Road North Division | 16.01.24 | 13.02.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
68 | Const. of RCC Pavement & Lowering on Jubilee Road at Ramhlun Vengthar. | 58.59 | Aizawl Road North Division | 04.03.24 |  | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
69 | Const. of RCC Rectangular Side Drain with Cover near Jubilee Road at Ramhlun Vengthar. | 3.65 | Aizawl Road North Division | 03.04.24 |  | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
70 | Const. of Steel Grate Cover Side Drain near Jubilee Road at Ramhlun Vengthar. | 1.49 | Aizawl Road North Division | 03.04.24 |  | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
71 | Const. of Breast Wall on Turning Point at Tetea Road Ramthar North. | 5.65 | Aizawl Road North Division | 06.02.24 | 23.02.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
72 | Const. of RCC Pavement on Tetea Road (Below Dawngliana House) at Ramthar North. | 7.89 | Aizawl Road North Division | 02.04.24 | 26.04.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
73 | Const. of Retaining Wall on Tetea Road Block-I at Ramthar North. | 6.63 | Aizawl Road North Division |  |  | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
74 | Const. of Retaining Wall on Tetea Road Block-II at Ramthar North. | 1.83 | Aizawl Road North Division | 13.01.24 | 12.02.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
75 | Const. of Breast Wall below step at NHC Ramhlun Venglai. | 3.33 | Aizawl Road North Division | 15.01.24 | 16.02.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
76 | Const. of Breast Wall Vertical Extension NHC at Ramhlun Venglai. | 5.6 | Aizawl Road North Division | 01.02.24 | 19.02.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
77 | Const. of RCC Rectangular Side Drain with Cover NHC at Ramhlun Venglai | 0.97 | Aizawl Road North Division | 02.02.24 | 20.02.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
78 | Const. of RCC Rectangular Side Drain with Cover on Rokhuma Colney to PC. Lalzuiliana House (Bishop Road) at Ramthar. | 2.98 | Aizawl Road North Division | 12.03.24 | 25.04.24 | 100% | 213.97 |  | 8.97 | 100% | 222.94 | Phy.Completed | Restricted Tender
79 | Const. of Breast Wall below St.Lawrence School at Ramthar. | 6.56 | Aizawl Road North Division | 06.03.24 | 22.03.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
80 | Const. of Breast Wall near Boxing Hall at Ramhlun Venglai. | 9.38 | Aizawl Road North Division | 26.03.24 |  | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
81 | Const. of Retaining Wall on Sihpui to Tlaklui road at Pu C,.Lalnunmawia House. | 8.81 | Aizawl Road North Division | 05.03.24 | 21.03.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
82 | Const. of PCC Pavement on ICI road Complex Vengthlang at Ramhlun Sport Complex. | 3.51 | Aizawl Road North Division | 08.03.24 | 20.03.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
83 | Const. of Retaining Wall near Rosangpuia House at Ramhlun Sport Complex. | 4.22 | Aizawl Road North Division | 05.03.24 | 24.04.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
84 | Const. of Breast Wall on LC Road near Lianhnuna Road at Ramhlun Sport Complex. | 3.09 | Aizawl Road North Division | 04.03.24 | 25.03.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
85 | Const. of RCC Side Drain near Pu Para House at Ramhlun Sport Complex. | 0.49 | Aizawl Road North Division | 05.03.24 | 20.03.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
86 | Const. of RCC Footpath on LC Road near HC. Thangvela House to B.Zanghinglova House. | 16.85 | Aizawl Road North Division | 12.03.24 |  | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
CONSTRUCTION OF LUNGHLU ROAD AT CHANMARI WEST, AIZAWL.
87 | Const. of RCC Link Drain near Hotel Platinum at Zarkawt. | 0.85 | Aizawl Road North Division | 06.12.23 | 09.12.23 | 100% | 97.6 |  | 0.85 | 100% | 98.45 | Phy.Completed | Restricted Tender
88 | Improvement of Zarkawt Valley Approach Road Phase-II | 47 | Aizawl Road North Division | 19.02.24 |  | 68% |  | 7% |  | 75% |  | Phy.Completed | Restricted Tender
89 | Const. of Retaining Wall near Babula's House at Chanmari. | 13.27 | Aizawl Road North Division | 05.02.24 |  | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
90 | Repair of Link Drain with Cover near J.Thangdailova House at Electric Veng. | 9.64 | Aizawl Road North Division | 08.02.24 |  | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
91 | Const. of New Cemetary Road at Electric Veng. | 28 | Aizawl Road North Division | 02.02.24 |  | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
UPGRADATION OF INTERNAL ROADS AT DURTLANG, BAWNGKAWN, CHALTLANG, ZUANGTUI, RAMHLUN & RAMTHAR.
92 | Steel Grade Cover Side Drain on PC Malsawma House to Rev. C. Vanlalhruaia House at Ramhlun 'S' | 8.04 | Aizawl Road North Division | 20.03.24 |  | 100% | 129.02 |  | 3.87 | 100% | 132.89 | Phy Completed | Restricted Tender
93 | Const. of RCC Foot Step near PC. Lalzuiliana House, Ramthar. | 16.58 | Aizawl Road North Division | 06.03.24 |  | 100% |  |  |  | 100% |  | Phy Completed | Restricted Tender
94 | Const. of RCC Link Drain near PC. Lalzuiliana House at Ramthar. | 8.42 | Aizawl Road North Division | 06.03.24 |  | 100% |  |  |  | 100% |  | Phy Completed | Restricted Tender
95 | Const. of Breast Wall below PC. Laltanpuia House at Ramthar North | 7.37 | Aizawl Road North Division | 28.03.24 | 24.04.24 | 100% |  |  |  | 100% |  | Phy Completed | Restricted Tender
96 | Const. of Breast Wall near Lalrammuana Ralte House at Ramthar North. | 5.76 | Aizawl Road North Division | 05.03.24 | 27.03.24 | 100% |  |  |  | 100% |  | Phy Completed | Restricted Tender
97 | Const. of RCC Foot Step near Pi Manmawii House at Ramhlun 'S' | 6.68 | Aizawl Road North Division | 04.03.24 |  | 100% |  |  |  | 100% |  | Phy Completed | Restricted Tender
WORK IMPLEMENTATION OF ARTICLE 275(1) PHASE - II
98 | Const. of Bethany Road at Chhinga Veng, Aizawl. | 70 | Aizawl Road North Division | 07.10.23 |  | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
SUB-DIVISION - II
UPGRADATION OF BETHEL VENG ROAD AT ZEMABAWK WITH APPROACH ROAD TO ZOKHAWSANG BYPASS ROAD.
99 | PCC Pavement at Ch: 0.000 - 0.580 Kmp. | 57.53 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% | 148.74 |  | 4.46 | 100% | 153.2 | Phy Completed | Restricted Tender
100 | Const. of PCC V-Shape Side Drain at Ch: 0.000 Kmp | 1.57 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy Completed | Restricted Tender
101 | Clearance of Landslip | 20.83 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy Completed | Restricted Tender
102 | Earth Work for Widening (Additional ) | 69.54 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy Completed | Restricted Tender
103 | RCC Frame Retaining Walls No.1 | 5.2 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy Completed | Restricted Tender
IMPROVEMENT OF MUTHI - TUIRIAL LINK ROAD.
104 | Widening & Curve Improvement. | 134.74 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 90% | 121.23 | 10% |  | 100% | 121.23 | On going | Restricted Tender
105 | Slab Culvert Type - I | 11.5 | Aizawl Road North Division | 14.12.23 | 14.12.24 |  |  | 10% |  | 10% |  | On going | Restricted Tender
106 | Retaining Wall Type - I | 10 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 40% |  |  |  | 40% |  | Work in progress | Restricted Tender
107 | Retaining Wall Type - II | 14 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
CONSTRUCTION OF BAMBOO LINK ROAD FROM NAUSEL, CHAMDUR, LUNGSANG, PUMPELHSEI, KAWRBEL.
108 | Const. of Nausel - Tuirial Bamboo Link Road. | [5 empty] | 182.94 |  |  |  | 182.94
| 1) Formation Cutting | 36.01 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 65% |  |  |  | 65% |  | Phy Completed | Restricted Tender
| 2) Const. of Slab Culvert. | 26.63 | Aizawl Road North Division |  |  | 10% |  | 50% |  | 60% |  | Phy Completed
109 | Chainage between 0.000-3.500Kmp | 59.39 | Aizawl Road North Division | 14.12.23 | 14.12.24 |  |  | 10% |  | 10% |  | Not yet started | Restricted Tender
110 | Retaining Wall | 30.93 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
111 | Concrete Pavement of Sihphir Neihbawih khawhnuai kawng balance : 1) Concrete Pavement. | 36.28 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
112 | 2) Const. of Slab Culvert. At chainage between 0.00-0.503km | 43.71 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
113 | Const. of Hmunte road at Muthi 1) Formation Cutting | 36.57 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 50% |  | 20% |  | 70% |  | Phy.Completed | Restricted Tender
114 | 2)Const. of Slab Culvert. Chainage between 0.00-1.00Kmp | 16.57 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
115 | 3) Const. of Retaining Wall Chainage between 0.00-2.00Kmp | 14.5 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
116 | Retaining Wall | 7.18 | Aizawl Road North Division | 14.12.23 | 14.12.24 |  |  | 30% |  | 30% |  | Phy.Completed | Restricted Tender
117 | Const. of Chamdur-Kawrbellui road 1) Formation Cutting | 30.5 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
Const. of New Road from Zemabawk North Dinthar Veng to CWC including Protection Works & Cross Drain.
118 | Formation Cutting. | 72.46 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% | 224.68 |  | 15.23 | 100% | 239.91 | Phy Completed | Restricted Tender
119 | Const. of Slab Culvert Type - I | 8 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy Completed | Restricted Tender
120 | Const. of Slab Culvert Type - II | 12 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy Completed | Restricted Tender
121 | Const. of Slab Culvert Type - III | 16.94 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy Completed | Restricted Tender
122 | Const. of Slab Culvert Type - I | 25 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy Completed | Restricted Tender
123 | Formation Cutting. | 60.12 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy Completed | Restricted Tender
124 | At Chainage between 0.00 to 1.50 | 28.6 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy Completed | Restricted Tender
125 | At Chainage between 1.50-3.00 | 23.28 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy Completed | Restricted Tender
CONSTRUCTION OF ROAD FROM FALKLAND TO GALILEE VIA MITLAMUAL AT ZEMABAWK, AIZAWL.
126 | Widening & New Cutting | 42.16 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% | 107.94 |  | 0 | 100% | 107.94 | Phy.Completed | Restricted Tender
127 | Const. of Slab Culvert Type - I | 2.64 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
128 | Formation Cutting | 52.09 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
129 | Const. of PCC Pavement. | 22.88 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
130 | Const. of Slab Culvert Phase-I | 14.63 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Phy.Completed | Restricted Tender
CONSTRUCTION OF ROAD FROM FALKLAND TO ZEMABAWK NORTH VIA THUAMPUI.
131 | Widening of Road. | 29.22 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% | 132.85 |  | 18.33 | 100% | 151.18 | Phy.Completed | Restricted Tender
132 | Const. of PCC Pavement on BS Farm to UPC Biakin. | 32.18 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
133 | Const. of Slab Culvert at Ch : 0.360 Kmp | 4.3 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
134 | Const. of RCC Link Drain at Ch : 0.000-0.112 Km | 25 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
135 | Const. of RCC Link Drain with Cover at Ch : 0.000 Km | 3.72 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
136 | Const. of RCC Link Drain with Cover at Ch : 0.120 Km | 5.58 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
137 | Lowering and Widening | 10.14 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% | 132.85 |  | 0 | 100% | 132.85 | Phy.Completed | Restricted Tender
138 | Const. of PCC Pavement on RAY to BS Farm Falkland | 10.48 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
139 | Const. of Retaining Wall | 8.84 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
140 | Construction of V-Shape | 4.2 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
141 | Const. of Missing Link at BCM Multipurpose Centre at Falkland | 6.34 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
142 | Const. of Step near Pu Ringdika's House | 1.4 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
143 | Repairing of Kailiana Concrete Pavement Road at Zemabawk 'N' | 10.6 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted Tender
CONSTRUCTION OF TUIRIAL AIRFIELD TO MUTHI AND ZOKHAWSANG AGRICULTURE.
144 | Formation Cutting | 40.94 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% | 103.19 |  |  | 100% | 103.19 | Phy Completed | Restricted Tender
145 | Const. of RCC Slab Culvert. | 66.58 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy Completed | Restricted Tender
CONSTRUCTION OF ROAD FROM THUAMPUI TO NH-6 (Zemabawk)
146 | Const. of Link Drain near Pi Diki House at Sihphir | 10 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% | 174.71 |  | 0 | 100% | 174.71 | Phy Completed | Restricted Tender
147 | Pavement of AR Complex at Zokhawsang | 59 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy Completed | Restricted Tender
148 | Resurfacing of Women Polytechnic Internal Road at Durtlang | 27 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy Completed | Restricted Tender
149 | Concrete Pavement | 31.5 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy Completed | Restricted Tender
150 | Const. of RCC Slab Culvert No.1 | 12.21 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy Completed | Restricted Tender
151 | Const. of Retaining Wall | 5 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy Completed | Restricted Tender
152 | Const. of U-Shape Side Drain. | 8.29 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy Completed | Restricted Tender
153 | Resurfacing of Sihpui to Ramhlun Vengthar Bus Turning Point at Ch : 1.052-1.357 Km. | 11 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy Completed | Restricted Tender
154 | Patch Repair of Vaivakawn to MZU via Zonuam. | 18 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy Completed | Restricted Tender
155 | Const. of Retaining Wall below Thanhrangi's House at Luangmual Complex. | 5 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy Completed | Restricted Tender
156 | Concrete Pavement | 16.72 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy Completed | Restricted Tender
157 | Rectangular Side Drain with Cover | 2.26 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy Completed | Restricted Tender
158 | V-Shape Drain | 3.36 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy Completed | Restricted Tender
159 | Const. of Step with Railing over Link Drain near Zemabawk North Play Ground. | 8 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy Completed | Restricted Tender
160 | Const. of RCC Balcony | 3.07 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy Completed | Restricted Tender
161 | Const. of RCC Link Drain | 11.62 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy Completed | Restricted Tender
162 | Const. of Retaining Wall | 5.14 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy Completed | Restricted Tender
163 | Const. of Masonry Stone Link Drain with Retaining Wall below Gov't. Zemabawk Primary School - I | 1.92 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
164 | Concrete Pavement from NH-54 to Holy Cross School Zemabawk. | 15.6 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
165 | Const. of Masonry Stone Link Drain near F.Lalrinmawia's Residence at Dinthar Veng, Zemabawk North. | 5.61 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
166 | Const. of RCC Link Drain (Balance Portion) at Dinthar Veng. Zemabawk | 10.33 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
167 | Formation Cutting | 8.82 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
168 | Slab Culvert | 5.13 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
169 | Retaining Wall | 9.84 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
170 | Concrete Pavement | 12.3 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
171 | Rectangular Side Drain with Cover | 1.05 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
172 | Concrete Pavement from Hogh School to Bethel at Zemabawk | 2.62 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
173 | Const. of RCC U-Shape Side Drain Kailiana Road at Zemabawk near Pi Sawihari. | 7.81 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
174 | PCC Flooring Zemabawk North Thlanmual to Muthi Lui | 10.67 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
175 | Const. of Hand Railing at Galilee Veng Main Road, Zemabawk. | 2.48 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
176 | Laying of Chequerred Tiles at Mel Li mual (Mual khat) existing step at Zemabawk. | 4.5 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
UPGRADATION OF INTERNAL ROADS AT DURTLANG, BAWNGKAWN, CHALTLANG, ZUANGTUI, RAMHLUN & RAMTHAR.
177 | Const. of Rectangular Side Drain with Cover at Tatkawng Veng. | 1.68 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% | 129.02 |  | 3.87 | 100% | 132.89 | Phy Completed | Restricted Tender
178 | Const. of Concrete Pavement of Durtlang tlak lam Thlanmual Road. | 20 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
179 | Const. of Concrete Pavement of Gosen Veng Kawngpui at Zuangtui | 7 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy Completed | Restricted Tender
180 | Const. of PCC Flooring at Rivenga Road at Muanna Veng. | 10 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy Completed | Restricted Tender
181 | Const. of PCC Flooring Internal Road - Zamliana Road to K.Thankunga Road, Selesih. | 5 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy Completed | Restricted Tender
182 | Vantlang Step near K,Thankunga House at Selesih. | 5 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy Completed | Restricted Tender
183 | Const. of PCC Flooring Leitan Ramthar Biak im Lane at Leitan, Ramthar. | 10 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy Completed | Restricted Tender
184 | Const. of Concrete Pavement on Bawngkawn Thlanmual to Thuampui Road | 22.87 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 17% |  |  |  | 17% |  | On Going | Restricted Tender
185 | Steel Grade Cover Side Drain on PC Malsawma House to Rev. C. Vanlalhruaia House at Ramhlun 'S' | 8.04 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
186 | Const of RCC Foot Step near PC Lalzuiliana House Ramthar | 16.58 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
187 | Const. of RCC Link Drain near PC Lalzuiliana House, Ramthar | 8.42 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
188 | Const. of Breast Wall below PC. Laltanpuia House at Ramthar North | 7.37 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy Completed | Restricted Tender
189 | Const. of Breast Wall near Lalrammuana Ralte House at Ramthar North. | 5.76 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
190 | Const of RCC Foot Step near Pi Manmawii House ar Ramhlun 'S' | 6.68 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
IMPROVEMENT OF ROAD FROM DURTLANG LEITAN TO DURTLANG RAMTHAR AT DURTLANG.
191 | Concrete Pavement of Pu Dinga Road | 5 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% | 216.23 |  | 0 | 100% | 216.23 | Phy Completed | Restricted Tender
192 | Const. of Concrete Pavement & Cross Drain on Vungkhama Road including Chhingtei Road at Durtlang North. | 15 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy Completed | Restricted Tender
193 | Const. of Concrete Pavement of Durtlang North Thlanmual. | 10 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy Completed | Restricted Tender
194 | Const. of PCC V-Shape Side Drain at Centanary Road & Women Polytechnic approach Road at Durtlang. | 5 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
195 | Concrete Pavement of Lalnu Road at Suaka Veng, Durtlang (Balance Portion) | 5.4 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy Completed | Restricted Tender
196 | Const. of Cross Drain with Cover on Durtlang Field. | 1 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy Completed | Restricted Tender
197 | Const. of Step including Link Drain at Centenary Road, Durtlang. | 20 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy Completed | Restricted Tender
198 | Const. of PCC V-Shape Side Drain and Retaining Wall at Gospel Thunder Team Compound, Durtlang Leitan | 20 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy Completed | Restricted Tender
199 | Const. of RCC Frame Retaining Wall at Zotui Road, Durtlang Leitan. | 3.5 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy Completed | Restricted Tender
200 | Patch repair of Durtlang Leitan SIRD Road. | 5.05 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy Completed | Restricted Tender
201 | Resurfacing of 3rd Lane at Durtlang Ramthar. | 29.5 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy Completed | Restricted Tender
202 | Concrete Pavement of approach road to Durtlang Ramthar Presby. Church including Cross Drainage. | 30.5 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy Completed | Restricted Tender
203 | Resurfacing of Chaltlang Lily Veng Internal Road (Balance) | 3 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy Completed | Restricted Tender
204 | Re-const. of Step from State Guest House to Lily Veng Internal Road. | 6 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy Completed | Restricted Tender
205 | Const. of RCC Balcony & Masonry Step near R.Lalmanga House at Chaltlang Lily Veng. | 14 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy Completed | Restricted Tender
206 | Concrete pavement of road near F. Malsawma House at Chaltlang | 2.5 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy Completed | Restricted Tender
207 | Const. of Retaining Wall & Concrete Pavement on AMC Road at Dingdi Veng, Chaltlang. | 9.7 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy Completed | Restricted Tender
208 | Const. of Retaining Wall near Pu Salemthara Residence at Brigade, Bawngkawn. | 2.6 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy Completed | Restricted Tender
209 | Concrete Pavement of Liansailova Road, Bawngkawn. | 10 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy Completed | Restricted Tender
210 | Concrete Pavement of Shalom Road at Bawngkawn Hmar Veng (Balance Portion) | 10 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy Completed | Restricted Tender
211 | Concrete Pavement on Upper Bawngkawn Hmar Veng. | 4.5 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy Completed | Restricted Tender
212 | Const. of Additional Protection Work at Bethel Veng. | 13 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy Completed | Restricted Tender
IMPROVEMENT OF ROAD FROM ZEMABAWK TO LUNGBIAL ROAD IN THE LOCALITY OF ZEMABAWK AT AIZAWL.
213 | Concrete Pavement of Approach Road to Sihphir Rescue Center at Sihphir Kawnveng. | 8.8 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% | 190.61 |  | 22.8 | 100% | 213.41 | Phy Completed | Restricted Tender
214 | Formation Cutting, Pavement & Step of Sunhlu tlang (Prayer mountain) at Sihphir Tlang Veng. | 7.9 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy Completed | Restricted Tender
215 | Const. of Step including Retaining Wall near Pu Zakhuma House at Sihphir Field Veng. | 3.66 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy Completed | Restricted Tender
216 | Const. of Link Drain with Cover near Pi Liani House at Sihphir Dinthar. | 1.74 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy Completed | Restricted Tender
217 | Const. of Link Drain near H.Lalfakzuala House, Sihphir Dinthar | 2.61 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy Completed | Restricted Tender
218 | RCC Balcony Gosen Veng to 132 KV Sub-Station at Zuangtui peng. | 26.13 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy Completed | Restricted Tender
219 | Concrete Pavement of Rivenga Road at Muanna Veng, Aizawl. | 7.3 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy Completed | Restricted Tender
220 | Concrete Pavement at Ch; 0.000-0.715 Kmp Muthi peng kawn. | 8.6 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy Completed | Restricted Tender
221 | Concrete Pavement at Nausel Thlanmual kawng | 8.2 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy Completed | Restricted Tender
222 | Const. of Retaining Wall at Thuampui Selesih Road at Ch: 4.300Kmp, Durtlang. | 6.14 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy Completed | Restricted Tender
223 | Formation Cutting | 51.36 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy Completed | Restricted Tender
224 | Const. of RCC Slab Culvert. | 33.04 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy Completed | Restricted Tender
225 | Const. of PCC Pavement on Local Council Road to RAY at Falkland. | 27.79 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
226 | Const. of PCC Pavement on Rabboni Road at Falkland | 5.14 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
227 | Const. of PCC Pavement on Local Council Road Falkland | 11.33 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
228 | PCC Pavement on approach road to Vai Lui via Rev. Lalsangliana House at Falkland Veng. | 5.74 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started | Restricted Tender
Sub-DIVISION - III
229 | Widening of road from Law College to PCI road at Luangmual, Aizawl (Sh: Earth Work for Widening of existing road) | 11.95 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% | 13.09 |  | 178.06 | 100% | 191.15 | Phy.Completed
230 | Improvement & Upgradation of road at Chawlhhmun, Aizawl | 26 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted
231 | Improvement & Upgradation of road at Zotlang, Aizawl | 20.29 | Aizawl Road North Division | 14.12.23 | 14.12.24 | [6 empty] | Not yet started
232 | Construction of RCC pavement at Sihhmui | 15.91 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted
233 | Improvement & Upgradation of road from PCI to Anganwadi at Lungverh | 77.98 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed
234 | Rangvamual internal road | 23.27 | Aizawl Road North Division |  |  | 100% |  |  |  | 100% |  | Phy.Completed
235 | Phunchawng internal road | 19.2 | Aizawl Road North Division |  |  | 100% |  |  |  | 100% |  | Phy.Completed
236 | Patch Repair and Seal Coating of Approach Road of tanhril, Aizawl | 23.08 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% | 59.03 |  |  | 100% | 59.03 | Phy.Completed | Restricted
237 | Construction of PCC Pavement of Approach Road to Tawngtai Bethel Camping Centre, Sakawrtuichhun, Aizawl | 9.49 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted
238 | Rigid Pavement of Gan Sabra Road | 19.33 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted
239 | Constrcution of PCC Pavement of Road from Saikaphleia's House to Muanthanga's House at Lungverh. Length=120.00 Rm | 9.49 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted
Construction of Lunghlu Road at Chanmari West Aizawl (Length=4.00 Kms, Ew = 4.00 Kms, Pavement = 4.00 Kms, Side Drain = 4500m, R/W 30m, Culvert = 10.Nos.)
240 | Construcrtion of RCC Frame struction Retaining Wall I at Lunghlu Road, Hunthar | 14.5 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% | 97.6 |  | 1.09 | 100% | 98.69 | Phy.Completed | Restricted
241 | Patch repair and Seal coat of MUP Road at Chanmari West, Aizawl | 11.55 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted
242 | Patch repair and Seal coat from BT Bakery to Protective Home via Zarkawt Thlanmual | 29.95 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted
243 | Construction of RCC Road at Methodist mual Turning Point to Edenthar Anganwadi Centre No.1 at Edenthar | 8.76 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Phy.Completed | Restricted
244 | Rigid Pavement of Gan Sabra Road | 16.86 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Completed | Restricted
245 | Const. of PCC Pavement of Road from Saikaphleia House to Muanthanga House at Lungverh. | 10.06 | Aizawl Road North Division | 14.12.23 | 14.12.24 | 100% |  |  |  | 100% |  | Completed | Restricted
| TOTAL AIZAWL ROAD NORTH DIVISION | 3478.01 |  |  |  |  | 2873.41 |  | 257.93 |  | 3131.34 | 0 | 0
AIZAWL ROAD SOUTH DIVISION
Construction and Rehabilitation of Samtlang - Lungleng Road Under SASCI - 2022-2023
246 | Improvement of Internal Road to Hlimen Vengchhak to Pu N Zokunga House. | 5 | Aizawl Road South Division |  |  |  |  | 100% |  | 100% |  | Phy.Completed | Item rate Contract
247 | Widening of Approach Road to City Bus Parking at S.Hlimen (Melthum - Hlimen Road ) | 576 | Aizawl Road South Division | 7.04.23 | 7.04.24 | 75% | 172.25 | 15% |  | 90% | 172.25 | Work in progress | Restricted tender
248 | Widening of S.Hlimen City Bus Parking - Samtlang Road (Hlimen-Samtlang Road) | 831 | Aizawl Road South Division | 06.4.23 | 06.04.24 | 95% | 531.49 | 2% |  | 97% | 531.49 | Work in progress | Restricted tender
249 | Const. of PCC Pavement, PCC Side drain and Retaining Wall at Upper Republic to Bethlehem via College veng under SASCI Phase-I Part-1 | 387 | Aizawl Road South Division | 14.12.23 | 14.12.24 | 100% | 91.42 |  | 0 | 100% | 91.42 | Works Completed | Restricted Tender
250 | Improvement of Venghnuai to Salem Road under SASCI Phase-I, Part-1. | 280 | Aizawl Road South Division | 14.12.23 | 14.12.24 | 100% | 113.03 |  | 0 | 100% | 113.03 | Completed | Restricted Tender
251 | Overlaying of Road with PCC Pavement from Mission Veng to Khatla with Retaining Wall and Minor Bridge at Aizawl under SASCI Phase - I, Part - I | 241 | Aizawl Road South Division | 14.12.23 | 14.12.24 | 100% | 93.13 |  |  | 100% | 93.13 | Works Completed | Restricted Tender
252 | Upgradation of Internal roads at Tuikual, Venghlui and Republic veng | 200 | Aizawl Road South Division | 14.12.23 | 14.12.24 | 91.67% | 102.11 |  |  | 91.67% | 102.11 | Work in progress | Restricted Tender
253 | Improvement of Saikhamakawn to Kulikawn via Tlangnuam under SASCI Phase-I, Part-I | 248 | Aizawl Road South Division | 14.12.23 | 14.12.24 | 100% | 96.14 | % | 0 | 100% | 96.14 | Phy.Completed | Restricted Tender
254 | Const. of road from Tlawng road to Model Veng under SASCI during 2023-2024 | 350 | Aizawl Road South Division | 14.12.23 | 14.12.24 | 65% | 2.97 | 25% |  | 90% | 2.97 | work halt due to land issue | Restricted Tender
255 | Const. of Roads from Nursery - Tamdo - Lawipu (2.50Kms) under SASCI during 2023-2024 Phase-II | 476 | Aizawl Road South Division | 14.12.23 | 14.12.24 | 89.44% | 138.68 |  | 0 | 89.44% | 138.68 | Work in progress | Restricted Tender
256 | Improvement of Roads and Infrastructtures at Aizawl City under SASCI 2023-2024 Under Aizawl Road South Division. | 180.2 | Aizawl Road South Division | 14.12.23 | 14.12.24 | 100% | 151.05 |  |  | 100% | 151.05 | Completed | Restricted Tender
| Total for Aizawl Road South Division | 3774.2 | 0 | 0 | 0 | 9.1611 | 1492.27 | 1.42 | 0 | 10.5811 | 1492.27 | 0 | 0
CHAMPHAI DIVISION
Const./Improvement of Road from Pamchung - Tualcheng - Chhangphut Field - Keifangtlang at Champhai District. 2022-2023
257 | Const. of Road from Pamchung to Tualcheng | 60 | Champhai Division | 21.03.23 | 21.04.23 | 100% | 57.89 |  |  | 100% | 57.89 | Completed | Spot Quatation
258 | Widening of Chhangphut Field to Keifangtlang | 90 | Champhai Division | 21.03.23 | 21.04.23 | 100% | 86.41 |  |  | 100% | 86.41 | Completed | Spot Quatation
259 | Widening and Retaining Wall at Hnahlan Dawrkawn to BRTF Road | 20 | Champhai Division | 21.03.23 | 21.04.23 | 100% | 19.33 |  |  | 100% | 19.33 | Completed | Spot Quatation
260 | Const. and Widening of Champhai Vengthlang ( N.Saron) to PHE Road | 50 | Champhai Division | 21.03.23 | 21.04.23 | 100% | 48.31 |  |  | 100% | 48.31 | Completed | Spot Quatation
261 | Const. of Railing and Retaining Wall at Champhai, Awmpui Phei & IB Veng | 40 | Champhai Division | 21.03.23 | 21.04.23 | 100% | 39.15 |  |  | 100% | 39.15 | Completed | Spot Quatation
262 | Consultancy Fee | 77 | Champhai Division | 21.03.23 | 21.04.23 | 100% | 10.15 |  |  | 100% | 10.15 | Completed | Spot Quatation
Const. of Pavement Champhai Vengthar - BRTF Road - Zotlang at Champhai. 2022-2023
263 | Black Topping of Road from Champhai Vengthar to BRTF Road (Zotekai Short Cut Road) | 164.46 | Champhai Division | 30.03.23 | 31.04.23 | 100% | 163.69 |  |  | 100% | 163.69 | Completed | Spot Quatation
264 | White Topping of Khawulh Approach Road at Zotlang, Champhai (Cement Concrete Pavement ) | 30 | Champhai Division | 30.03.23 | 31.04.23 | 100% | 29.62 |  |  | 100% | 29.62 | Completed | Spot Quatation
265 | Widening of Road from Dinthar to Ramhrangkawn (7th Day Gate to LCN Filling Station ) | 45 | Champhai Division | 30.03.23 | 31.04.23 | 100% | 44.23 |  |  | 100% | 44.23 | Completed | Spot Quatation
266 | Widening of Approach Road to Kendriya Vidhyalaya School, Champhai | 10 | Champhai Division | 30.03.23 | 31.04.23 | 100% | 9.95 |  |  | 100% | 9.95 | Completed | Spot Quatation
Improvement of Road from IKK Zion Veng - Khawbung - Tuipui at Champhai District 2022-2023
267 | Widening and Flexible Pavement of Road from IKK Church to Zion Veng Boundary. | 135.54 | Champhai Division | 30.03.23 | 31.04.23 | 100% | 134.74 |  |  | 100% | 134.74 | Completed | Spot Quatation
268 | Bouldering of Road from ZBC Church to Mualnuam Road. | 15 | Champhai Division | 30.03.23 | 31.04.23 | 100% | 14.49 |  |  | 100% | 14.49 | Completed | Spot Quatation
269 | Const.and Widening of Road Zawlsei to Tuipui | 40 | Champhai Division | 30.03.23 | 31.04.23 | 100% | 39.5 |  |  | 100% | 39.5 | Completed | Spot Quatation
270 | Surfacing of Ruantlang Dawrkawn to CNV Road Via Lersia Field. | 17.3 | Champhai Division | 30.03.23 | 31.04.23 | 100% | 16.72 |  |  | 100% | 16.72 | Completed | Spot Quatation
271 | Patch Repair and Seal Coating of New Champhai to Tlangsam Road. | 25 | Champhai Division | 30.03.23 | 31.04.23 | 100% | 24.16 |  |  | 100% | 24.16 | Completed | Spot Quatation
272 | Pothole & Re-surfacing of Sasaw Road at Khawbung Internal Road (Khawbung to Tuipui Short Cut Road) | 42.28 | Champhai Division | 30.03.23 | 31.04.23 | 100% | 41.6 |  |  | 100% | 41.6 | Completed | Spot Quatation
273 | Const. of Retaining Wall on Road Formation Collapse at 22.600 Kmp on Champhai to Khawbung Road. | 6.13 | Champhai Division | 30.03.23 | 31.04.23 | 100% | 5.9 |  |  | 100% | 5.9 | Liability | Spot Quatation
274 | Completion of Champhai - Zokhawthar Road under SASCI. 2023-2024 | 1311 | Champhai Division | 06.03.23 | 06.03.24 | 100% | 950.64 |  | 360.36 | 100% | 1311 | Completed | Spot Quatation
Construction of Hruaikawn - Zokhawthar Road (8.00 Km) 2022-2023
275 | Const. of Hruaikawn-Zokhawthar Road | 50 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
276 | Const. of Bungzung to Tuipui Road (Biate kai) Part-I | 100 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
277 | Const. of Vaphai to Chawngtui 'East' Road | 210 | Champhai Division | 05.10.23 | 05.10.24 | 100% | 201.83 |  |  | 100% | 201.83 | Completed | Spot Quatation
278 | Const. of Approach Road to PHC at Bungzung | 60 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
279 | Const. of Bungzung to Zawngtetui Road | 280 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
Construction of Road from Samthang to Farkawn via Lamsial.
280 | Const. of Samthang to Farkawn via Lamsial Road | 350 | Champhai Division | 05.10.23 | 05.10.24 | 100% |  |  |  | 100% |  | Works Completed | Spot Quatation
281 | Const. of Khawbung to TuipuiShort cut road balance portion | 24.21 | Champhai Division | 05.10.23 | 05.10.24 | 100% | 23.26 |  |  | 100% | 23.26 | Work completed | Spot Quatation
282 | Const. of Vanzau to Dungtlang (Balance work - Rocky portions)-I | 50 | Champhai Division | 05.10.23 | 05.10.24 | 100% | 67.25 |  |  | 100% | 67.25 | Completed | Spot Quatation
Construction of Vaphai to Tiau Road
283 | Const. of Vaphai to Tiau Road | 200 | Champhai Division | 05.10.23 | 05.10.24 | 100% | 130.43 |  |  | 100% | 130.43 | Phy.Completed | Spot Quatation
284 | Const. of Road from Selam to Tuisa Lui | 125 | Champhai Division | 05.10.23 | 05.10.24 | 100% | 120.19 |  |  | 100% | 120.19 | Work completed | Spot Quatation
285 | Const. of Sesih to Bulfek Road | 165 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
286 | Const. of Truck Lay by (Terminal) at Khuangleng | 10.79 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
287 | Const. of Pavillion at Farkawn (Frame Structure) | 30 | Champhai Division | 05.10.23 | 05.10.24 | [7 empty] | Spot Quatation
Improvement & Widening of Road from Bungzung to R.Tuipui (Length = 5.00 Km)
288 | Improvement & Widening of Road Bungzung to Tuipui | 20 | Champhai Division | 05.10.23 | 05.10.24 | 100% | 19.2 |  |  | 100% | 19.2 | Work completed | Spot Quatation
289 | Const. of Road Leisenzo to Lianpui | 9 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
290 | Maintenance of Road Vangchhia to Lianpui | 9 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
291 | Const. of Road Khamkhanthanga's House to Bulfekzawl Road at Sesih | 4 | Champhai Division | 05.10.23 | 05.10.24 | 100% | 3.83 |  |  | 100% | 3.83 | Phy.Completed | Spot Quatation
292 | Maintenance of Road Khankawn to Tlawva | 9.5 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
293 | Maintenance of Road Thekte to Lurh-Zo | 3.5 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
294 | Const. of Gov't. Khuangthing M/S Court Yard PCC Flooring and Fencing. | 9 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
295 | Const. of PCC Flooring Internal Roads at Farkawn. | 30 | Champhai Division | 05.10.23 | 05.10.24 | 100% | 28.84 |  |  | 100% | 28.84 | Works Completed | Spot Quatation
296 | Const. of PCC Flooring from Kapchhunga's House to Singkawnga's House at Farkawn. | 4 | Champhai Division | 05.10.23 | 05.10.24 | 100% | 3.84 |  |  | 100% | 3.84 | Works Completed | Spot Quatation
297 | Const. of PCC Flooring from Theirekawn Culvert to Rinchhana's House at Farkawn. | 4 | Champhai Division | 05.10.23 | 05.10.24 | 100% | 3.84 |  |  | 100% | 3.84 | Works Completed | Spot Quatation
298 | Const. of PCC Flooring from Vanbiakawia House to Rinliana House at Farkawn. | 4 | Champhai Division | 05.10.23 | 05.10.24 | 100% | 3.84 |  |  | 100% | 3.84 | Works Completed | Spot Quatation
299 | Const. of PCC Flooring from Zasanga House to Hriattira House at Farkawn. | 4 | Champhai Division | 05.10.23 | 05.10.24 | 100% | 3.84 |  |  | 100% | 3.84 | Works Completed | Spot Quatation
300 | Const. of PCC Flooring from Kawn veng to Sub-Centre at Khawbung. | 3 | Champhai Division | 05.10.23 | 05.10.24 | 100% | 2.88 |  |  | 100% | 2.88 | Works Completed | Spot Quatation
301 | Const. of PCC Flooring from Lalnimawia House to Main Road at Khawbung. | 3 | Champhai Division | 05.10.23 | 05.10.24 | 100% | 2.88 |  |  | 100% | 2.88 | Works Completed | Spot Quatation
302 | Const. of PCC Flooring approach road Pathian veng Thlanmual at Khawbung. | 3 | Champhai Division | 05.10.23 | 05.10.24 | 100% | 2.88 |  |  | 100% | 2.88 | Works Completed | Spot Quatation
303 | Const. of PCC Flooring approach road Vengthlang Cemetary at Vaphai. | 3 | Champhai Division | 05.10.23 | 05.10.24 | 100% | 2.88 |  |  | 100% | 2.88 | Works Completed | Spot Quatation
304 | Const. of PCC Flooring between Water Reservoir and Challiana House at Vaphai. | 3 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
305 | Const. of PCC Flooring between Tialthuama House and Sanghnuna House at Vaphai. | 3 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
306 | Const. of PCC Flooring between High School and Nginliankhupa House at Khuangleng. | 9 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
307 | Const. of PCC Flooring J.Vanlalmawia House to Vety Quarter at Khuangleng. | 3 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
308 | Const. of PCC Flooring from Lalmuansanga House to Remmawia House at Khuangthing. | 5 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
309 | Const. of PCC Flooring approach road Gov't. P/S-I at Khuangthing. | 5 | Champhai Division | 05.10.23 | 05.10.24 | 100% | 4.8 |  |  | 100% | 4.8 | Completed | Spot Quatation
310 | Const. of PCC Flooring from Khummanga House to Tinngaihliana House at Sesih. | 5 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
311 | Const. of PCC Flooring & Step near Liandothanga House at Sesih. | 5 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
312 | Const. of PCC Flooring from Lalnunpuia House to Lalthlana House at Bungzung. | 7 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
313 | Const. of PCC Flooring approach road Cemetary at Samthang. | 3 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
314 | Const. of PCC Flooring near Lalhmunmawia House at Samthang. | 3 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
315 | Const. of PCC Flooring Lane chung road at Dungtlang. | 4 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
316 | Const. of PCC Flooring from Liandawnga House to Playground at Leisenzo. | 5 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
317 | Const. of PCC Flooring approach road Cemetary at Leisenzo. | 3 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
318 | Const. of PCC Flooring approach road Health Clinic Centre at Vangchhia. | 4 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
319 | Const. of PCC Flooring approach road Gov't. M/S at Vanzau. | 3 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
320 | Const. of PCC Flooring Sub-Centre approach road at Khankawn. | 4 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
321 | Const. of PCC Flooring Internal Road Lane hnuai at Lianpui. | 3 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
322 | Const. of PCC Flooring approach road Cemetary at Thekte. | 3 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
323 | Const. of PCC Flooring approach road Presby. Church at Leithum. | 3 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
324 | Const. of PCC Flooring Internal Road near Laldinmawia House at Sazep. | 3 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
325 | Const. of PCC Flooring approach road Gov't. P/S at Zawlsei. | 3 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
326 | Const. of PCC Flooring near Community Hall at Buang. | 3 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
327 | Const. of PCC Flooring from T.Hranglawta House to Chhunkhuma House at Bulfekzawl. | 3 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
328 | Const. of PCC Flooring from Waiting Shed to Cemetary at Hruaikawn. | 15 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
329 | Const. of PCC Flooring approach road Gov't. P/S at Thekpui. | 3 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
330 | Const. of PCC Flooring near Biakliana House at Zawngtetui. | 2 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
331 | Const. of PCC Flooring between Thangvhuanga House to Lalsawma House at Chawngtui 'E' | 2 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
332 | Const. of PCC Flooring Tiau road at Saikhumphai. | 1.5 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
333 | Const. of Side Drain from Lallianmanga House to Lalremruata House at N.Hruaikawn. | 2 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
334 | Const. of Zalhva Link Road Culvert at Samthang. | 2.5 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
Construction of PCC Pavement from Dilkawn to Kelkang (Length = 7.00 Km)
335 | Approach road for Tuipui Village from NH-6 with 1(one) Bridge (3Kms. Approx). | 20 | Champhai Division | 05.10.23 | 05.10.24 | 100% | 19.27 |  |  | 100% | 19.27 | Work Completed | Spot Quatation
336 | Const. of Road Kanan veng to Jail veng with Culvert. | 20 | Champhai Division | 05.10.23 | 05.10.24 | 100% |  |  |  | 100% |  | Work Completed | Spot Quatation
337 | Const. of PCC Flooring from Khawulh Peng to Presby. Church at Tlangnuam ,Vengthar. | 20 | Champhai Division | 05.10.23 | 05.10.24 | 100% | 19.23 |  |  | 100% | 19.23 | Work Completed | Spot Quatation
338 | White-Topping of Road from KC Lalzarliana House to Chauleng Veng | 10 | Champhai Division | 05.10.23 | 05.10.24 | 100% | 9.62 |  |  | 100% | 9.62 | Work Completed | Spot Quatation
339 | Widening and Bouldering of Road from Cold Storage, New Champhai to Tlangnuam Vengthar Presbyterian Church. | 10 | Champhai Division | 05.10.23 | 05.10.24 | 100% | 9.62 |  |  | 100% | 9.62 | Work Completed | Spot Quatation
340 | Const. of Road from Zion Veng Thlanmual Peng to Emmanuel After Care Centre. | 10 | Champhai Division | 05.10.23 | 05.10.24 | 100% | 9.62 |  |  | 100% | 9.62 | Work Completed | Spot Quatation
341 | White-Topping of Circular road from Pauchinthanga House to Thangkhanpuma House at Helipad Veng, New Champhai. | 10 | Champhai Division | 05.10.23 | 05.10.24 | 100% |  |  | 4 | 100% | 4 | Work Completed | Spot Quatation
342 | Const. of Side Drain from PWD Road near Lianthuama Car Wash to Petrol Pump, New Champhai. | 15 | Champhai Division | 05.10.23 | 05.10.24 | 100% |  |  |  | 100% |  | Work Completed | Spot Quatation
343 | Const. of White-topping of road from Community Hall to World Bank Road with 2 Culverts. | 10 | Champhai Division | 05.10.23 | 05.10.24 | 100% |  |  |  | 100% |  | Work Completed | Spot Quatation
344 | Widening of road between Lersia Field and Vanlaltluanga House. | 10 | Champhai Division | 05.10.23 | 05.10.24 | 100% |  |  |  | 100% |  | Work Completed | Spot Quatation
345 | Const. of Retaining Wall at Dilkawn | 10 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
346 | Const. of PCC Flooring from Saitawngkawn to Thlanmual. | 10 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
347 | Const. of PCC Flooring from B.Sanga House to Ramthanzauvi House at Melbuk. | 10 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
348 | Const. of PCC Flooring from Dilkawn to Kelkang. | 30 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
349 | Const. of Road from Hausiama Lungphun to Hmingzauva Leilet. | 30 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
350 | Const. of Road from Thangzuala House to Bangla Lui. | 30 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
351 | Widening of approach road from Melbuk to New Hruaikawn. | 5 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
352 | Const. of PCC Flooring from Hlunthanga House to Genesaret Gospel Home. | 5 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
353 | Const. of PCC Flooring from Zonunsiama House to P.School. | 5 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
354 | Const. of Black-Topping of Road from Thangzuala House to F.Lalhnawla House at Zotlang. | 10 | Champhai Division | 05.10.23 | 05.10.24 | 100% | 9.62 |  |  | 100% | 9.62 | Completed | Spot Quatation
355 | Const. of PCC Flooring at Hranga High School Tual, Kanan Veng. | 5 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
Construction of Road from Pamchung to Tualcheng (Length = 5.00 Kms)
356 | Improvement of Pamchung to Tualcheng (5.00 Kms.) | 150 | Champhai Division | 05.10.23 | 05.10.24 | 100% | 79.5 |  |  | 100% | 79.5 | Completed | Spot Quatation
357 | Const. of Hliappui to Aiduzawl. | 30 | Champhai Division | 05.10.23 | 05.10.24 | 100% | 30 |  |  | 100% | 30 | Completed | Spot Quatation
358 | Const. of Ngaizawl to Neihdawn. | 20 | Champhai Division | 05.10.23 | 05.10.24 | 100% | 20 |  |  | 100% | 20 | Completed | Spot Quatation
359 | Const. of PCC Flooring from Methodist Church to C.Zoramlawma House at Vengthlang, Champhai. | 15 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
360 | Const. of PCC Flooring from Rengchhuani House to Nukami House at Rahsi Veng, Champhai. | 10 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
361 | Const. of Side Drain & Culvert from Lalringa House to Challiankunga House at Kahrawt, Champhai. | 7 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
362 | PCC Flooring from Hospital Veng Biak In to Joseph Paua at Vengsang, Champhai | 10 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
363 | PCC Flooring from Leitlahniam to Lumikawr at IB veng, Champhai. | 10 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
364 | Const. of PCC Flooring from Dawrkawn to MUP House at Hnahlan | 10 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
365 | Const. of PCC Flooring from Community Hall to Ramnunsanga House, N.Diltlang. | 1 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
366 | Const. of PCC Flooring of Ngur High School Road, Ngur. | 5 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
367 | Const. of PCC Flooring at PHC, Rabung. | 5 | Champhai Division | 05.10.23 | 05.10.24 | [6 empty] | Not yet started | Spot Quatation
368 | Const. of Agriculture Link Road from Selam to Leiva River, Selam. | 24 | Champhai Division | 05.10.23 | 05.10.24 | 100% | 23.08 |  |  | 100% | 23.08 | Work .Completed | Spot Quatation
IMPROVEMENT OF ROADS WITHIN CHAMPHAI DIVISION.
369 | Patch repair and resurfacing of Diversion Road (North Side) near Tourist Lodge at Champhai (Vaihmun Diversion Road). | 8.93 | Champhai Division | 05.10.23 | 05.10.24 | 100% | 8 |  |  | 100% | 8 | Work Completed | Departmental
370 | Patch repair and Resurfacing of Sap Sakei Lamlian Bethel Boundary to Vaihmun. | 16.22 | Champhai Division | 05.10.23 | 05.10.24 | 100% | 13.6 |  |  | 100% | 13.6 | Work Completed | Departmental
371 | Patch repair and Seal Coating of Champhai District Hospital to Keifangtlang DC Office (Liability) | 10.63 | Champhai Division | 05.10.23 | 05.10.24 | 100% | 7.76 |  |  | 100% | 7.76 | Work Completed | Departmental
372 | Patch repair and Resurfacing of Approach Road to Sub-Jail (Aizawl) Road (Petrol Pump) District Jail. | 9.1 | Champhai Division | 05.10.23 | 05.10.24 | 100% | 5.34 |  | 2 | 100% | 7.34 | Work Completed | Departmental
373 | Patch repair and Resurfacing of Treasury Complex approach Road. Treasury Office. | 5.12 | Champhai Division | 05.10.23 | 05.10.24 | 100% | 4.11 |  |  | 100% | 4.11 | Work Completed | Departmental
IMPROVEMENT OF SAMTHANG TOWN ROAD.
374 | Const. of Flexible Pavement at Samthang (Courtyard of CM Commemorative Stone) |  | Champhai Division | 05.10.23 | 05.10.24 | 100% | 4.54 |  |  | 100% | 4.54 | Work Completed | Departmental
375 | Const. of Flexible Pavement at Samthang (Internal Road) | 19.8 | Champhai Division | 05.10.23 | 05.10.24 | 100% | 12.59 |  |  | 100% | 12.59 | Work Completed | Departmental
376 | Repair of Samthang Kawtchhuah repair by Flexible Pavement. |  | Champhai Division | 05.10.23 | 05.10.24 | 100% | 2 |  |  | 100% | 2 | Work Completed | Departmental
| TOTAL for Champhai Division | 4730.51 | 0 | 0 | 0 | 59 | 2650.49 | 12 | 366.36 | 59 | 3016.85 | 0 | 0
KOLASIB DIVISION :
377 | Const. of PCC Pavement from Hmar veng- Venglai - Diakkawn in Kolasib Town.(10Km) PART-B | 134.58 | Kolasib Division | 16.10.23 | 16.10.24 | 100% | 134.58 | 0% |  | 100% | 134.58 | Completed | Spot Quatation
378 | Const. of PCC Pavement from Hmar veng- Venglai - Diakkawn in Kolasib Town.(10Km) PART-A | 47.5 | Kolasib Division | 16.10.23 | 16.10.24 | 100% | 47.5 |  |  | 100% | 47.5 | Completed | Restricted Tender
379 | Const. of Rigid Pavement from Vairengte - Bilkhawthlir - Phainuam (SASCI : 2023-2024) | 500 | Kolasib Division | 16.10.23 | 16.10.24 | 100% | 260 | 0% |  | 100% | 260 | Phy.Completed | Restricted Tender
380 | Const. of Road from Kawnpui to Bukpui Road (10 Km). | 152 | Kolasib Division | 16.10.23 | 16.10.24 | 100% | 75.31 | 0% | 70.82 | 100% | 146.13 | Work in progress | Restricted Tender
381 | Improvement of Roads and Infrastructure at District Headquarters under Kolasib. | 124.5 | Kolasib Division | 31.10.23 | 29.02.24 | 92.5% | 106.02 | 6.25% | 14.46 | 100% | 120.48 | Work in progress | Departmental
| TOTAL FOR KOLASIB DIVISION | 958.58 |  |  |  |  | 623.41 |  | 85.28 |  | 708.69
PROJECT DIVISION - I
382 | Extension of Community Hall at Upper Republic | 55 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 55 |  | 0 | 100% | 55 | Phy.Completed
383 | Construction of RCC slab Dam veng YMA Hall | 5 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 4.81 |  | 0.19 | 100% | 5 | Completed
384 | Construction of Cequered tiles Near Local Council House Bungkawn Vengthar | 1.5 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 1.44 |  | 0.06 | 100% | 1.5 | Completed
385 | Construction of Saizahawla Tuikhur near R.Lalrinchhana Field Road | 8 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 7.68 |  | 0.32 | 100% | 8 | Completed
386 | Construction of RCC Structure at Electric Sub-Station, Khatla, Tlawng Road | 5 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 4.81 |  | 0.19 | 100% | 5 | Completed
387 | Laying of Chequered Tiles Between Zonghaka and Sk Thanga's House at Nursery | 2.15 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 2.12 |  | 0.03 | 100% | 2.15 | Completed
388 | Laying of Chequered Tiles tetween UPC (Mizoram) and RC Vanlalsawma (L) House at Nursery | 2.7 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 2.69 |  | 0.01 | 100% | 2.7 | Completed
389 | Construction of Chequered tiles near Khatla South Presbyterian | 1.5 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 1.43 |  | 0.07 | 100% | 1.5 | Completed
390 | Constrcution of Chequered tiles between J.Zangena House and Rinsanga Colney (L) near Khatla's Presbyterian Church | 1 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 0.98 |  | 0.02 | 100% | 1 | Completed
391 | Construction of Step Chequered tiles with Hand Railing near Khatla Pastor Quarter to J.Lianhlira House | 3 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 2.84 |  | 0.16 | 100% | 3 | Completed
392 | Renovation and linement of new Cemetary at Maubawk | 1.25 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 1.25 |  |  | 100% | 1.25 | Completed
393 | Renovation of Kanan Multipurpose Community Hall | 15 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 14.21 |  | 0.79 | 100% | 15 | Completed
394 | Renovation & Repair of Khatla Bazar Building | 4 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 3.86 |  | 0.14 | 100% | 4 | Completed
395 | Renovation of Mission Veng Health Clinic at Mission | 2 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 1.93 |  | 0.07 | 100% | 2 | Completed
396 | Construction of Anganwadi Centre-II, Aizawl | 5 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 4.79 |  | 0.21 | 100% | 5 | Completed
397 | Construction of Basketball Court at Dinthar | 55 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 52.92 |  | 0 | 100% | 52.92 | Work in progress
398 | Construction of Basketball Court at Kulikawn | 45 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 45 |  | 0 | 100% | 45 | Phy.Completed
399 | Construction of Basketball Court at ITI Veng | 5 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 5 |  | 0 | 100% | 5 | Completed
400 | Renovation of Futsal Ground including Side Drain at Nursery veng | 4.4 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 4.4 |  |  | 100% | 4.4 | Contingencies of works
401 | Upgradation of Chief Minister Staff Quarter ( 5 nos of Quarters Phase-I | 193 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 193 |  | 0 | 100% | 193 | Completed
402 | Upgradation of Chief Minister Staff Quarter(5 nos of Qtrs Phase-II) | 95 | Project Division-I | 15.3.23 | 15.2.24 | 100% | 95 |  | 0 | 100% | 95 | Phy.Completed | EPC
403 | Constructuction of Gov"t Staff Qtrs ( Block-C) at DIET Complex. | 544 | Project Division - I | 10.05.2023 | 10.05.2025 | 69% | 176.76 | 4% | 75.06 | 73% | 251.82 | Work in progress | EPC
404 | C/O Food Civil Supplies & Consumer Affairs 1500MTGodown at Sairang | 921 | Project Division - I | 7.4.23 | 7.4.26 | 45% | 147.29 | 5% | 0.49 | 50% | 147.78 | Work in progress | EPC
SASCI - 2023-2024 under Project Division - I
405 | Improvement of Government Buildings, High Court, Gov't Polytechnic & E-in-C PWD Office | 165.71 | Project Division - I |  |  | 100% | 48.95 |  | 2.01 | 100% | 50.96 | Work in progress | EPC
406 | Const. of Steps, Footpath, Bazar Shed, Hall Property House, Internal Road at Zemabawk, Thuampui, Zotlang, Chawnpui, Vaivakawn, Kanan. | 115 | Project Division - I |  |  | 100% | 80.4 |  | 23.9 | 100% | 104.3 | Work in progress | EPC
407 | Const. & Improvement of Public Buildings, YMA Zawlbuk at Chanmari West, Improvement of Electric Veng Hall | 148.29 | Project Division - I | 16.12.23 | 16.12.24 | 100% | 143.15 |  | 0 | 100% | 143.15 | Work in progress | EPC
408 | Const. & Improvement of Public Buildings. | 200 | Project Division - I | 16.12.23 | 16.12.24 | 100% | 191.58 |  | 0 | 100% | 191.58 | Phy.Completed | EPC
409 | Const. of Football Field at Maubawk | 325.99 | Project Division - I | 06.12.23 | 06.12.24 | 100% | 72.74 |  | 72.74 | 100% | 72.74 | Work in progress | Item rate
410 | Const. of E-in-C PHED Office Phase-II | 169.67 | Project Division - I | 16.12.23 | 16.12.24 | 100% | 169.67 |  |  | 100% | 169.67 | Completed | EPC
411 | Const. of Tuikual 'S' Mini Sport Complex | 413.16 | Project Division - I | 16.12.23 | 16.12.24 | 85% | 165.5 | 10% | 50.99 | 95% | 216.49 | Work in progress | EPC
412 | Const. of DLAO Office at MINECO | 223.52 | Project Division - I | 16.12.23 | 16.12.24 | 100% | 150 |  |  | 100% | 150 | Work in progress | EPC
413 | Construction of Central Medical Warehouse at ZMC, Approach Road | 150 | Project Division - I | 16.12.23 | 16.12.24 | 60% | 47.43 |  |  | 60% | 47.43 | Work in progress | EPC
414 | Construction of Motor Parking at Kulikawn and Bethlehem Vengthlang | 40 | Project Division - I |  |  | 100% | 38.85 | 0% |  | 100% | 38.85 | Completed
| TOTAL FOR PROJECT DIVISION | 3925.84 |  |  |  |  | 1937.48 |  | 227.45 |  | 2092.19 | 0 | 0
HMUIFANG DIVISION : 2022-2023
415 | Improvement & Strengthening of Aibawk-Darlung Road for 4.000-14.000 Kmp in Mizoram for the year 2022-2023 | 547 | Hmuifang Division | 21.12.22 | 31.03.23 | 100% | 546.97 |  |  | 100% | 546.97 | Completed | Departmental
416 | Construction of Agriculture Link Road for Thingzam Zau, Tuirial Lui | 269.6 | Hmuifang Division | 15.12.22 | 14.05.23 | 100% | 249.72 |  |  | 100% | 249.72 | Phy.Completed | Departmental
417 | Contsruction of Upgradation of Aizawl-Thenzawl-Lunglei Road 5.00 kmp-100.00 Kmp | 206 | Hmuifang Division | 15.02.23 | 14.05.23 | 100% | 201.83 |  |  | 100% | 201.83 | Phy.Completed | Departmental
SASCI - 2023-2024 under Hmuifang Division.
418 | Strengthening of Aizawl-Thenzawl- Lunglei Road (83.00-100.00Kmp) | 1322 | Hmuifang division | 15.08.23 | 15.08.24 | 100% | 1307.28 |  | 9.51 | 100% | 1316.79 | Phy.Completed | Item rate
419 | Const. of Agriculture Link Road to R.Mat from Chawilung, Lungsei, Samlukhai, Sialsuk. | 173.57 | Hmuifang division | 14.12.23 | 14.12.24 | 100% | 166.87 |  | 0 | 100% | 166.87 | Phy. Completed | Item rate
420 | Improvement of Roads and Infrastructure at Aizawl City. | 30 | Hmuifang division | 14.12.23 | 14.12.24 | 100% | 28.84 |  |  | 100% | 28.84 | Phy.Completed
421 | Rigid Pavement of sinking area on Hualngohmun on Aizawl-Thenzawl -Lunglei Road. | 40 | Hmuifang division | 14.12.23 | 14.12.24 | 100% | 38.46 |  |  | 100% | 38.46 | Phy.Completed
422 | Completion of Approach Road to Upper Republic Thlanmual at Hualngohmun. | 2.5 | Hmuifang division | 14.12.23 | 14.12.24 | 100% | 2.4 |  |  | 100% | 2.4 | Phy.Completed
423 | Patch Repair of Maubuang approach road & Const. of Permanent Works at essential location on Maubuang. | 30 | Hmuifang division | 14.12.23 | 14.12.24 | 100% | 28.84 |  |  | 100% | 28.84 | Phy.Completed
| TOTAL FOR HMUIFANG DIVISION | 2620.67 |  |  |  | 9 | 2571.21 |  | 9.51 |  | 2580.72 | 0
KHAWZAWL DIVISION- 2022-2023
424 | Construction of Kawlkulh Bypass Road | 805 | Khawzawl Division | 01.02.23 | 30.06.23 | 22% | 615.95 |  |  | 22% | 615.95 | Work in progress | Restricted Tender
SASCI - 2023-2024 Under Khawzawl Division.
425 | Improvement & Strengthening of Vengthar Bazar toVengsang Presby. Church via Taidawnkawn at Khawzawl(Length: 7.50 KM) | 128.45 | Khawzawl Division | 03.10.23 | 03.04.24 | 100% | 119.72 |  |  | 100% | 119.72 | Completed | Spot Quotation
426 | Improvement of road at Chawngtlai - Biate - Ngopa- Khawhai & Pawlrang to Luangpawn | 166.5 | Khawzawl Division | 03.10.23 | 03.04.24 | 100% | 160.73 |  |  | 100% | 160.73 | Completed | Spot Quotation
427 | Const. of Agricultural Link road to Keltan Zau, Sihphai, Dawlzang, Lamzawl. (Length-8 Kms) | 70 | Khawzawl Division | 05.10.23 | 05.10.24 | 100% | 65.97 |  |  | 100% | 65.97 | Completed | Restricted Tender
428 | Const. of Agricultural Link road to Keltan Zau, Sihphai, Dawlzang, Lamzawl. (Length-8 Kms) | 101.1 | Khawzawl Division | 05.10.23 | 05.10.24 | 100% | 95.65 |  |  | 100% | 95.65 | Completed | Spot Quotation
429 | Improvement of roads and Infrastructures at District Headquarters ; Saiha, Lawngtlai, Lunglei, Hnahthial, Serchhip, Champhai, Khawzawl, Saitual, Kolasib and Mamit. | 168.7 | Khawzawl Division |  |  | 100% | 166.29 |  |  | 100% | 166.29 | Completed | Spot Quotation
430 | Const. of Pamchung to Tualcheng Road. Hliappui to Aiduzawl | 30 | Khawzawl Division | 05.10.23 | 05.10.24 | 100% | 30 |  |  | 100% | 30 | Completed | Restricted Tender
431 | Const. of Pamchung to Tualcheng Road. Ngaizawl to Neihdawn. | 20 | Khawzawl Division | 05.10.23 | 05.10.24 | 100% | 19.23 |  |  | 100% | 19.23 | Completed | Restricted Tender
| TOTAL FOR KHAWZAWL DIVISION | 1489.75 |  |  |  |  | 1273.54 |  | 0 |  | 1273.54 | 0 | 0
SAITUAL DIVISION : Under SASCI : 2023-2024
432 | Improvement of Khawlek - Ratu Road (Length = 6.00 Km) | 130 | Saitual Division |  |  | 100% | 102.98 |  | 0.62 | 100% | 103.6 | Phy.Completed
433 | Widening, Pavement & Const. of Culverts on 3rd Road from Sedaikawn to PWD Kawn, Saitual L=4.00Kms, Widening= 4.00Kms, Pavement=4.00Kms, Side Drain=1500mt, R/Wall= 15mt, Culvert= 6 Nos. | 137.52 | Saitual Division |  |  | 100% | 137.52 |  |  | 100% | 137.52 | works Completed
434 | Rigid Pavement of Sakeibangla to ZMC via Thingsulthliah Road, PCC Pavement = 3.00Km, Side Drain = 2000mt, R/Wall = 10mt, Culvert = 2Nos. | 55.78 | Saitual Division |  |  | 100% | 55.78 |  |  | 100% | 55.78 | works Completed
435 | Improvement of Roads and Infrastructures at District Headquarters, Saitual : Saitual Town Road : Pot Hole repair of Saitual - Saichal Road. | 15.5 | Saitual Division |  |  | 100% | 15.5 |  |  | 100% | 15.5 | works Completed
| TOTAL FOR SAITUAL DIVISION | 338.8 |  |  |  |  | 311.78 |  | 0.62 |  | 312.4
TLABUNG DIVISION : SASCI 2023-2024
436d | Const. of PCC Pavement from Chawnpuikawn to Diplibagh Road with Additional Culverts & R/Walls Length=2Kms. | 129.77 | Tlabung Division | 14.12.23 | 14.12.24 | 100% | 127.06 |  |  | 100% | 127.06 | Completed | Item Rate
437d | Const. of Agriculture Link Road from Sihphirtlang to Tuichawng River | 57.2 | Tlabung Division | 14.12.23 | 14.12.24 | 100% | 57.13 |  |  | 100% | 57.13 | Completed Phy.Works | Item Rate
438 | Improvement of Borapansury - I to Borapansury- II Road upto Bangadesh Boundary. | 168.34 | Tlabung Division | 14.12.23 | 14.12.24 | 47.3% | 17.9 | 50.7% |  | 98% | 17.9 | work in progress | Item Rate
439 | Construction of RCC Pier for strenthening of Bailey Bridge over R.De on Phairuang to Bunghmun Road | 77 | Tlabung Division | 24.3.24 | 8.5.24 | 50% | 54.36 | 30% | 0 | 80% | 54.36 | Work in progress | Departmental
440 | Strengthening of Chawngte to Borapansury Road | 391.3 | Tlabung Division | 22.07.23 | 22.07.24 | 50% | 126.38 | 24% |  | 74% | 126.38 | On going | Item rates
| TOTAL FOR TLABUNG DIVISION | 823.61 |  |  |  |  | 382.83 |  | 0 |  | 382.83
PROJECT DIVISION - II
SASCI : 2023-2024
441 | Const. of Public Buildings: Const. of Community Hall at Melthum, Saikhamakawn, Chamring. | 203.5 | Project Division-II | 13.03.24 | 15.10.24 | 26.5% | 67.31 | 3.5% | 31.69 | 30.5% | 99 | Not yet started | Item Rate
442 | Const. of Public Playground at Thingdawl, Bukpui, N.Chaltlang, Hortoki, Serkhan and Lungmuat. | 185 | Project Division-II | 13.03.24 | 15.10.24 | 43.07% | 75 | 3.08% | 10 | 46.15% | 85 | Not yet started | Item Rate
443 | Retaining wall ar various Places | 67.6 | Project Division-II | 13.03.24 | 15.10.24 | 100% | 60.54 |  | 0 | 100% | 60.54 | Work physically completed | Item Rate
444 | Const. of Playground at Tuipuibari, Tuirum, Dapchhuah, New Mamit, Rajivnagar-I | 245 | Project Division-II | 13.03.24 | 15.10.24 | 100% |  | 0% | 125.9 | 100% | 125.9 | Work physically completed | Item Rate
| TOTAL FOR PROJECT DIVISION II | 701.1 |  |  |  |  | 202.85 |  | 167.59 |  | 370.44
PROJECT DIVISION - III : (2023-2024 )
445 | Construction of Govt.Serchhip College (Sh: Adninistrative Block) | 650 | Project Division-III | 27.02.23 | 27.02.25 | 55% | 204.77 | 10% | 0 | 60% | 204.77 | work in progress | PWD Form-8
446 | Const. of Football ground and Volleyball court at Vapar, Selam, Tualcheng, Hnahlan, Hmunhmeltha | 203 | Project Division-III | 13.10.23 | 13.10.24 | 100% | 95.47 |  | 3.83 | 100% | 99.3 | 100% of 1st proity work completed | PWD Form-8
447 | Const. of Khawbung Futsal ground, Gallery, Roofing, Lighting & Laying of Artificial Turf | 255.5 | Project Division-III | 14.10.23 | 14.10.24 | 100% | 74.75 |  | 36.6 | 100% | 111.35 | work in progress | PWD Form-8
448 | Const. of Community Hall at Dulte & Chhawrtui | 271 | Project Division-III | 13.10.23 | 13.10.24 | 53% | 28 | 7% | 21.81 | 60% | 49.81 | work in progress | PWD Form-8
449 | Development of Community Centre at Zotlang, Champhai (Sh: Const. of Market Building cum Community Hall & Futsal Ground) | 215 | Project Division-III | 14.10.23 | 14.10.24 | 100% | 65 |  | 21.49 | 100% | 86.49 | 100% of Ist priority work complete | PWD Form-8
450 | Additional works for Const. of General Nursing Midwifery (GNM) hostel and Nursing Hostel at Champhai | 438 | Project Division-III | 13.10.23 | 13.10.24 | 96% | 160.44 | 2% | 8.81 | 98% | 169.25 | work in progress | PWD Form-8
451 | Const. of Public Playground at Keitum, Lungchhuan. | 250 | Project Division-III | 13.10.23 | 13.10.24 | 100% | 96.96 |  | 0 | 100% | 96.96 | 100%of 1st priority work completed | PWD Form-8
452 | Const. of Gov't. Building at Serchhip District (Sh: PWD Staff Quarters, Extension of Gov't. Serchhip Cillege and Kitchen Cum Dining at PTS, Thenzawl, Mizoram) | 362 | Project Division-III | 13.10.23 | 13.10.24 | 85% | 133.39 | 3% |  | 88% | 133.39 | work in progress | PWD Form-8
453 | Const. of Community Resource Center at Baktawng and Chhuanthar | 350 | Project Division-III | 13.10.23 | 13.10.24 | 100% | 136.54 |  | 3.36 | 100% | 139.9 | 100%of 1st priority work completed | PWD Form-8
454 | Const. of Community Hall at Khawzawl Vengthar, Arro Village, khawzawl Dinthar and Khawhai South | 209 | Project Division-III | 13.10.23 | 13.10.24 | 97% | 79.25 | 3% |  | 100% | 79.25 | 100%of 1st priority work completed | PWD Form-8
| TOTAL FOR PROJECT DIVISION III | 3203.5 |  |  |  |  | 1074.57 |  | 95.9 |  | 1170.47
LUNGLEI ROAD DIVISION -I, SASCI : 2022-2023
455 | Construction of pavement on Approach Road to Pialthleng at Lunglei District | 724.85 | Lunglei Road Division -I | 24.03.23 | 24.03.24 | 100% | 700.08 |  | 0 | 100% | 700.08 | Completed | Restricted Tender
456 | Aizawl- Thenawl- Lunglei Road between Kanghmun 'S' and Kikawn, Lunglei Phase - I, (Sh: Group - A Between 100.00-120.00 Kmp) | 647.09 | Lunglei Road Division -I | 03.07.23 | 03.07.24 | 65% | 608.25 | 10% | 0 | 75% | 608.25 | Work in progress | Restricted Tender
457 | Aizawl- Thenawl- Lunglei Road between Kanghmun 'S' and Kikawn, Lunglei Phase - I, (Sh: Group - B Between 120.00-143.00 Kmp) | 658.16 | Lunglei Road Division -I | 26.06.23 | 26.06.24 | 90% | 532.93 | 10% | 0 | 100% | 532.93 | Completed | Restricted Tender
SASCI : 2023-2024 under Lunglei Road Division- I
458 | Improvement of Bazar Veng - College Veng - Venghlun at Lunglei District. | 130.05 | Lunglei Road Division -I | 24.12.23 | 23.12.24 | 100% | 63.61 |  |  | 100% | 63.61 | Completed
459 | Const. of Bamboo Link Road Phunchawngzau at Pukpui. | 165 | Lunglei Road Division -I | 24.12.23 | 23.12.24 | 100% | 83.99 |  |  | 100% | 83.99 | Completed
460 | Const. of Link Road from Vaisam Tlang - Zawlte - Phunchawng at Bunghmun. | 95.08 | Lunglei Road Division -I | 24.12.23 | 23.12.24 | 100% | 40.47 |  |  | 100% | 40.47 | Completed
461d | Improvement of Roads and infrastructure at District Headquater | 14.3 | Lunglei Road Division -I |  |  | 100% | 14.13 |  |  | 100% | 14.13 | Completed
| Total for Lunglei Road Division -I | 2434.53 |  |  |  |  | 2043.46 |  | 0 |  | 2043.46
LUNGLEI ROAD DIVISION - II 2023-2024
461 | Const. of PCC Road to Public Playground at Zobawk South. | 71 | Lunglei Road Division-II |  |  | 81% | 9.9 | 1% |  | 82% | 9.9 | Work in progress
462 | Const. of Bamboo Link Road at Phunchawngzau, Pukpui (Group-B) | 85 | Lunglei Road Division-II |  |  | 78% | 60 | 5% |  | 83% | 60 | Work in progress
463 | Improvement of Hnahthial to Takam Tiau Road. | 188.34 | Lunglei Road Division-II |  |  | 99% | 127.21 | 1% | 0 | 100% | 127.21 | Phy.Completed
464 | Const. of Agriculture Link Road between Tuikhurhlu to Batluang at Pangzawl. | 100.5 | Lunglei Road Division-II |  |  | 100% | 100.5 |  | 0 | 100% | 100.5 | Completed
| Total for Lunglei Road Division II | 444.84 |  |  |  |  | 297.61 |  | 0 |  | 297.61
SIAHA DIVISION : 2022-2023
465 | Strengthening and Improvement of Kawlchaw to Serkawr Road | 318 | Siaha Division | 21.03.23 | 21.03.24 | 100% | 315.23 |  |  | 100% | 315.23 | Completed | Item rate Contract
466 | Improvement and Upgradation of Siaha to Thingsen Road upto NH 54B Junction (7.00km) | 778.53 | Siaha Division | 21.03.23 | 18.09.24 | 92% | 542.62 | 7% | 35.72 | 99% | 578.34 | Work in progress. | Item rate Contract
467 | Widening Road at Cheural - Lungzarhtum - Vartekkai - Sangau (11.50Km) in Mizoram for the year 2022-23 under SASCI Group-1. Widening of Road from BCM Church to BRTF Road via Middle School at Cheural Town Extension (L=1.800km) | 43.12 | Siaha Division | 09.04.23 | 30.9.23 | 87.15% | 32.75 |  |  | 87.15% | 32.75 | Workphysically completed, actual length of road less than sanction length | Item rate Contract
468 | Wifening Road at Cheural - Lungzarhtum - Vartekkai - Sangau (11.50Km) in Mizoram for the year 2022-23 under SASCI Group-2. Widening of Road from LIKBK Pastor Qtr to Pu H.Lalhranga House at Lungzarhtum (L=1.500km) | 44.54 | Siaha Division | 09.04.23 | 31.8.23 | 100% | 35.26 |  |  | 100% | 35.26 | Workphysically completed, actual length of road less than sanction length | Item rate Contract
469 | Widening Road at Cheural - Lungzarhtum - Vartekkai - Sangau (11.50Km) in Mizoram for the year 2022-23 under SASCI Group-3 Widening of Road from NEC road Junction to Vartekkai with construction of minor bridge (L=7.000km) | 207.27 | Siaha Division | 09.04.23 | 08.04.24 | 100% | 188.28 |  |  | 100% | 188.28 | Work Completed | Item rate Contract
470 | Wifening Road at Cheural - Lungzarhtum - Vartekkai - Sangau (11.50Km) in Mizoram for the year 2022-23 under SASCI Group-4 Widening of Road from Tourist Lodge to Vengthar Field via SDO (C) Complex at Sangau (L=0.860km) | 20.07 | Siaha Division | 09.04.23 | 31.08.23 | 94.48% | 15.51 | 5.52% |  | 100% | 15.51 | Workphysically completed, actual length of road less than sanction length | Item rate Contract
471 | Formation Cutting of Road to Sand Quarry at Bualpui 'NG' -Archhuang-Sangau-Lungpher (15.46Km) in Mizoram for the year 2022-23 under SASCI | 61.85 | Siaha Division | 09.04.23 | 31.8.23 | 97% | 57.88 |  |  | 97% | 57.88 | Work Phy.Completed | Item rate Contract
472 | Formation Cutting of Road to Sand Quarry at Bualpui 'NG' -Archhuang-Sangau-Lungpher (15.46Km) in Mizoram for the year 2022-23 under SASCI | 49.63 | Siaha Division | 09.04.23 | 31.8.23 | 96.04% | 43.86 | 3.96% |  | 100% | 43.86 | Workphysically completed, actual length of road less than sanction length | Item rate Contract
473 | Formation Cutting of Road to Sand Quarry at Bualpui 'NG' -Archhuang-Sangau-Lungpher (15.46Km) in Mizoram for the year 2022-23 under SASCI | 38.68 | Siaha Division | 09.04.26 | 8.7.23 | 90.05% | 26.72 |  |  | 90.05% | 26.72 | Workphysically completed, actual length of road less than sanction length | Item rate Contract
474 | Formation Cutting of Road to Sand Quarry at Bualpui 'NG' -Archhuang-Sangau-Lungpher (15.46Km) in Mizoram for the year 2022-23 under SASCI | 125.86 | Siaha Division | 09.04.23 | 08.04.23 | 99.41% | 118.37 |  |  | 100% | 118.37 | Workphysically completed, actual length of road less than sanction length | Item rate Contract
475 | Improvement of Roads & Infrastructure at District Headquarter : Saiha. Tuipui L Junction. | 15 | Siaha Division | 05.04.23 | 05.05.23 |  |  | 100% |  | 100% |  | Phy.Completed | Item rate Contract
SASCI : 2023-2024 Under Siaha Division.
476 | Improvement of Siaha Town from Meisatla to Tlangkawn via College veng (7.50Kms) | 269.23 | Siaha Division | 20.10.23 | 31.03.25 | 95.62% | 177.51 | 0.77% |  | 96.39% | 177.51 | Work in progress | Item rate Contract
477 | Const. of Thiahra to Tuipui with Bridge Over River Tuisumpui (Phase-1) | 144.24 | Siaha Division | 20.10.23 | 31.03.25 | 47.07% | 58 | 10.93% | 78.26 | 58% | 136.26 | Work in progress. | Item rate Contract
478 | Constn.of PCC of internal road at (Lopu) | 19.23 | Siaha Division | 20.10.23 | 31.03.25 | 100% | 18.24 |  |  | 100% | 18.24 | Phy.Completed | Item rate Contract
479 | Improvement & Widening of Balu Road between BRTF Road at River Tuipui (Chakhei) | 24.04 | Siaha Division | 20.10.23 | 31.03.25 | 100% | 22.19 |  |  | 100% | 22.19 | Phy.Completed | Item rate Contract
480 | Improvement & Widening of Balu Road between BRTF Road at River Tuipui (Iana and Tuipui) | 14.42 | Siaha Division | 20.10.23 | 31.03.25 | 100% | 12.34 |  | 0.75 | 100% | 13.09 | Phy.Completed | Item rate Contract
481 | Improvement of Siaha Town from Meisatla to Tlangkawn via College Veng (7.50 kms) Tisopi-CC pavement. | 14.43 | Siaha Division | 20.10.23 | 31.03.25 | 100% | 14.4 |  |  | 100% | 14.4 | Work Phy.Completed | Item rate Contract
482 | Improvement of Siaha Town from Meisatla to Tlangkawn via College Veng (7.50 kms) College vaih-II and New Siaha East-II. | 28.85 | Siaha Division | 20.10.23 | 31.03.25 | 73.91% | 21.39 |  |  | 73.91% | 21.39 | Work in progress. | Item rate Contract
483 | Improvement of Siaha Town from Meisatla to Tlangkawn via College Veng (7.50 kms) Between Elim School and AR Ground.. | 19.23 | Siaha Division | 20.10.23 | 31.03.25 | 100% | 19.14 |  |  | 100% | 19.14 | Works Completed | Item rate Contract
484 | Improvement of Siaha Town from Meisatla to Tlangkawn via College Veng (7.50 kms) Between J.Vialu House to Siaha Vaihpi | 14.43 | Siaha Division | 20.10.23 | 31.03.25 | 100% | 14.4 |  |  | 100% | 14.4 | Work Phy.Completed | Item rate Contract
485 | Improvement of Siaha Town from Meisatla to Tlangkawn via College Veng (7.50 kms) Council vaih Cemetary. | 28.85 | Siaha Division | 20.10.23 | 31.03.25 | 100% | 16.7 |  | 5.55 | 100% | 22.25 | Work Phy.Completed | Item rate Contract
486 | Improvement of Siaha Town from Meisatla to Tlangkawn via College Veng (7.50 kms) K.Paichho House to Gilgal Church. | 11.54 | Siaha Division | 20.10.23 | 31.03.25 | 100% | 11.36 |  |  | 100% | 11.36 | Work Completed | Item rate Contract
487 | Horti Link Road between Km 10 and Lalsiama Farm. | 12.5 | Siaha Division | 20.10.23 | 31.03.25 | 100% | 8.66 |  |  | 100% | 8.66 | Work Phy.Completed | Item rate Contract
488 | Improvement of Siaha Town from Meisatla to Tlangkawn via College Veng (7.50 kms) Agri. Link Road. Pangkhua to Pangkhawchhuah. | 28.85 | Siaha Division | 20.10.23 | 31.03.25 | 100% | 22.25 |  |  | 100% | 22.25 | Work Phy.Completed | Item rate Contract
489 | Improvement of Siaha Town from Meisatla to Tlangkawn via College Veng (7.50 kms) Chhaolo.. | 19.23 | Siaha Division | 20.10.23 | 31.03.25 | 100% | 15.94 |  |  | 100% | 15.94 | Work Phy.Completed | Item rate Contract
490 | Improvement of Siaha Town from Meisatla to Tlangkawn via College Veng (7.50 kms) Noaotla | 24.04 | Siaha Division | 20.10.23 | 31.03.25 | 100% | 16.33 |  |  | 100% | 16.33 | Work Phy.Completed | Item rate Contract
491 | Improvement of Siaha Town from Meisatla to Tlangkawn via College Veng (7.50 kms) Thanngerh Agri. Link Road Thaltlang. | 28.85 | Siaha Division | 20.10.23 | 31.03.25 | 43.75% | 1.37 |  | 1.37 | 43.75% | 1.37 | Work in progress. | Item rate Contract
492 | Improvement of Siaha Town from Meisatla to Tlangkawn via College Veng (7.50 kms) Rawlbuk. | 9.62 | Siaha Division | 20.10.23 | 31.03.25 | 100% | 6.71 |  |  | 100% | 6.71 | Work Phy.Completed | Item rate Contract
493 | Improvement of Siaha Town from Meisatla to Tlangkawn via College Veng (7.50 kms) S.Lungpher | 9.62 | Siaha Division | 20.10.23 | 31.03.25 | 100% | 2.76 |  |  | 100% | 2.76 | Work Phy.Completed | Item rate Contract
494 | Improvement of Siaha Town from Meisatla to Tlangkawn via College Veng (7.50 kms) Lungtian-II | 9.62 | Siaha Division | 20.10.23 | 31.03.25 | 100% | 8.91 |  |  | 100% | 8.91 | Work Phy.Completed | Item rate Contract
495 | Improvement of Siaha Town from Meisatla to Tlangkawn via College Veng (7.50 kms) Vawmbuk | 9.62 | Siaha Division | 20.10.23 | 31.03.25 | 100% |  |  |  | 100% |  | Work Phy.Completed | Item rate Contract
496 | Const. of Semi RCC Bridge over Pala River between Supha and Miepu. | 24.04 | Siaha Division | 20.10.23 | 31.03.25 | 100% |  |  |  | 100% |  | Phy.Completed | Item rate Contract
497 | Improvement And Widening of Balu Road between BRTF Road at River Tuipui (8.50 kms) New Laty. | 19.23 | Siaha Division | 20.10.23 | 31.03.25 | 100% | 17.23 |  |  | 100% | 17.23 | Phy.Completed | Item rate Contract
498 | Improvement And Widening of Balu Road between BRTF Road at River Tuipui (8.50 kms) | 38.46 | Siaha Division | 20.10.23 | 31.03.25 | 100% | 34.41 |  |  | 100% | 34.41 | Phy.Completed | Item rate Contract
499 | Improvement And Widening of Balu Road between BRTF Road at River Tuipui (8.50 kms) Laki | 19.23 | Siaha Division | 20.10.23 | 31.03.25 | 100% | 17.47 |  |  | 100% | 17.47 | Phy.Completed | Item rate Contract
500 | Improvement And Widening of Balu Road between BRTF Road at River Tuipui (8.50 kms) Tisi | 19.23 | Siaha Division | 20.10.23 | 31.03.25 | 100% | 18.19 |  |  | 100% | 18.19 | Completed | Item rate Contract
501 | Improvement And Widening of Balu Road between BRTF Road at River Tuipui (8.50 kms) New Ahmypi & Old Ahmypi | 19.23 | Siaha Division | 20.10.23 | 31.03.25 | 100% | 19.23 |  |  | 100% | 19.23 | Completed | Item rate Contract
| TOTAL FOR SIAHA DIVISION | 2582.41 |  |  |  |  | 1951.61 |  | 121.65 |  | 2071.89 | 0 | 0
KAWRTHAH DIVISION : 2023-2024
502 | Strengthening of Hriphaw - Kolalian - Dulupcherra Road (14.00Kms) | 500 | Kawrthah Division | 16.12.23 | 15.12.24 | 77% | 308.91 | % |  | 77% | 308.91 | Work in progress | Restricted Tender
503 | Const. of W.Mualthuam - Belkhai Road (3.100 Kms) | 360 | Kawrthah Division | 16.12.23 | 15.12.24 | 100% | 81 |  |  | 100% | 81 | Works completed as per revise E/S | Restricted Tender
504 | Strengthening of Zamuang - Hriphaw - Kolalian - Dulupcherra (KDZKT) Road (28.00 Kmp) | 500 | Kawrthah Division | 16.12.23 | 15.12.24 | 95% | 154.48 | 3% |  | 98% | 154.48 | Work in progress | Restricted Tender
505 | Additional Works and Completion of Double Lane Bridge Over R.Teirei on Bairabi - Zamuang. | 1400 | Kawrthah Division | 16.12.23 | 15.12.24 | 40% | 277.7 |  | 61.19 | 40% | 338.89 | Work in progress | Restricted Tender
506 | Improvement of Roads & Infrastructure at District Headquarter : Saiha. | 10 | Kawrthah Division | 15.02.24 | 15.04.24 | 100% | 10 |  |  | 100% | 10 | Completed | Depart- mental
| TOTAL FOR KAWRTHAH DIVISION | 2770 |  |  |  |  | 832.09 |  | 61.19 |  | 893.28
MAMIT DIVISION : 2023-2024
507 | Const. of Agri. Link Road from New W.Phaileng, Hnahva, Marpara North & Silsury East. (Length=7.00Kms) | 100 | Mamit Division | 06.12.23 | 06.12.24 | 100% | 98.04 |  |  | 100% | 98.04 | Work phy Completed | Item rate Contract
508 | Const. of Road from Parvatui to Zopui (Length=6.00Kms) | 135 | Mamit Division | 06.12.23 | 06.12.24 | 97.5% | 2.3 | 2.5% | 132.54 | 100% | 134.84 | Work phy Completed | Item rate Contract
509 | Const. of Link Road between Tuirum to Daifim to Khanthuam (Length= 7.00Kms) | 122.2 | Mamit Division | 06.12.23 | 06.12.24 | 85.8% | 86.19 | 14.2% | 1.59 | 100% | 87.39 | Work phy Completed | Item rate Contract
510 | Const. of Link Road Tuirum-Daifim - Nghalchawm, Damdiai - Damansora | 107.71 | Mamit Division | 06.12.23 | 06.12.24 | 100% | 94.99 |  |  | 100% | 94.99 | Work phy Completed | Item rate Contract
511 | Improvement of Road and Infrastuctures at District Headquarter Mamit. | 35 | Mamit Division | 06.12.23 | 06.12.24 | 60% | 19.99 | 40% | 14.29 | 100% | 34.28 | Work phy Completed | Depart- mental
| TOTAL FOR MAMIT DIVISION | 499.91 |  |  |  |  | 301.51 |  | 148.42 |  | 449.54
SERCHHIP DIVISION :
512d | Improvement of roadsInfrastucture at District Headquarters Saiha, Lawngtlai, Lunglei, Hnahthial, Serchhip, Champhai, Khawzawl, Saitual, Kolasib, Mamit. | 85 | Serchhip Division | 7.10.23 | 30.10.23 | 100% | 85 |  |  | 100% | 85 | Completed | Item rate
513d | Construction of DS.Chawngtui-N.Vanlaiphai Road (0.00-14.800Kmp) Phase-II (Parmanent Works) | 295 | Serchhip Division | 15.2.23 | 27.10.24 | 86% | 227.52 | 14% | 62.43 | 100% | 289.95 | Completed | Item rate
514 | Construction of Strengthening of double lane BUGS Bridge Over R.Tuichang at 6.00Kmp on Keitum-Artahkawn Road (40R-70R) | 343 | Serchhip Division | 15.2.23 | 31.3.23 | 100% | 299.74 |  | 11.99 | 100% | 311.73 | Phy.Completed | Item rate
515 | Widening, Strengthening & Improvement of Sports Complex Approach Road at Serchhip (Length =1.50Kms) Widening= 1.500Kms Retaining Wall = 80.00 mP.C.C. Pavement = 1.500 Km Side Drain = 1500.00 m Culvert = 8 nos. | 380 | Serchhip Division | 05.10.23 | 05.10.24 | 50% | 69.99 | 50% |  | 100% | 69.99 | Completed | Item rate
516d | Additional works for Compietion of Strengthening of Chekawn - Artahkawn Road | 205 | Serchhip Division | 07.10.23 | 06.10.24 | 100% | 111.99 |  |  | 100% | 111.99 | work is already completed | Item rate
517 | Const. of Agriculturre Link road to River Lungva from Hriangtlang, Sialsir, Hlaizawl. | 351.5 | Serchhip Division | 05.10.23 | 05.10.24 | 37.59% | 120.64 |  |  | 37.59% | 120.64 | Working completed | Item rate
| TOTAL FOR SERCHHIP DIVISION | 1659.5 |  |  |  |  | 914.88 |  | 74.42 |  | 989.3
LAWNGTLAI DIVISION :
IMPROVEMENT OF DILTLANG TO CHAWNGTELUI ROAD
518 | Construction of Retaining Wall at Certain Location | 25.07 | Lawngtlai Division | 11.05.23 | 10.4.24 | 100% | 25.07 |  |  | 100% | 25.07 | Completed | Mode of Contract
519 | Resurfacing of NH-54 to DTO Office (including courtyard) at Chanmari, Lawngtlai | 6.99 | Lawngtlai Division | 11.05.23 | 10.4.24 | 100% | 6.99 |  |  | 100% | 6.99 | Completed | Mode of Contract
520 | Construction of Minor Bridge between Khawmawi Bazar Veng to Khawmawi Vengthar | 34.48 | Lawngtlai Division | 11.05.23 | 10.4.24 | 100% | 34.47 |  |  | 100% | 34.47 | Completed | Mode of Contract
521 | Black topping of internal road at Lawngpuighat | 81.65 | Lawngtlai Division | 11.05.23 | 10.4.24 | 100% | 81.63 |  |  | 100% | 81.63 | Completed | Mode of Contract
522 | Construction of Playground approach road at Thingfal Mamte Veng | 19.49 | Lawngtlai Division | 11.05.23 | 10.4.24 | 100% | 19.49 |  |  | 100% | 19.49 | Completed | Mode of Contract
523 | Consultancy fee for Roads | 66.55 | Lawngtlai Division | 11.05.23 | 10.4.24 | 15% | 9.98 |  |  | 15% | 9.98 | Work in progress
524 | Consultancy Fee for Bridges | 106.39 | Lawngtlai Division | 11.05.23 | 10.4.24 | 70% | 74.68 |  |  | 70% | 74.68 | Work progress
SASCI : 2023-2024 Under Lawngtlai Division.
525 | Improvement of Approach Road to Kawrthindeng WRC Area. | 121.77 | Lawngtlai Division | 26.02.24 | 31.12.24 | 88.63% | 91.08 |  | 7.07 | 100% | 98.15 | Work progress | Restricted Tender
526 | Const. of Mautlang to Borogusuri | 117 | Lawngtlai Division | 26.02.24 | 31.12.24 | 99.15% | 93.07 |  | 19.39 | 100% | 112.46 | Work progress | Restricted Tender
| Improvement of Thlengang to River Chhimtuipui road | 208.95 | Lawngtlai Division | 11.05.23 | 31.05.24 |  |  |  |  | 100% | 208.94 | Works Completed
| TOTAL FOR LAWNGTLAI DIVISION | 579.39 |  |  |  |  | 436.46 |  | 26.46 |  | 462.92
National Highway Division - I (SASCI 2023 - 2024)
Improvement of Road from HN - 44A to Mamit and Rawpuichhip within Mamit in Mizoram for the year 2022-2023 under SASCI (Length=8.45 Km)
527 | Const. of Rigid/Concrete Pavement for New Approach road to Rawpuichhip from NH-44A | 56.89 | National Highway Division - I | 21.02.23 | 21.03.23 | 30% |  |  |  | 30% |  | Work in progress | Spot Quotation
528 | Const. of Humepipe Culvert at Ch:4.300kmp on NH-44A diverted road at Rawpuichhip Area (L=6.25, H=5m) | 9 | National Highway Division - I | 22.02.23 | 22.03.23 | 100% |  |  |  | 100% |  | Phy.Completed | Spot Quotation
Const. of Bamboo Link Road from Hmunpui to Mauhaklui & Tuidam approach Road in Mizoram. SASCI : 2023-2024
529 | Repair and Maintenance of Tuidam Approach Road. | 103 | National Highway Division - I | 15.12.23 | 15.12.24 | 100% | 103 |  |  | 100% | 103 | Completed | Restricted Tender
530 | Hmunpui Bamboo Link Road (Length = 8.00 Km) | 150 | National Highway Division - I | 15.12.23 | 15.12.24 | 100% | 150 |  |  | 100% | 150 | Completed | Restricted Tender
531 | Const. of Lengpui Advantist Road (Length = 60m) | 10 | National Highway Division - I | 15.12.23 | 15.12.24 | 100% | 10 |  |  | 100% | 10 | Completed | Restricted Tender
532 | Const. of Saiphai to Hortoki Road (13.800 Km) | 600 | National Highway Division - I | 15.12.23 | 15.12.25 | 1% |  |  | 25 |  | 25 | work in progress | Restricted Tender
533 | Improvement of Roads and Infrastructure at District Headquarters; Saiha, Lawngtlai, Lunglei, Hnahthial, Serchhip, Champhai, Khawzawl, Saitual, Kolasib, Mamit ; (Sh: Tuidam Approach Road) | 10 | National Highway Division - I | 31.03.23 | 31.03.24 | 100% | 10 |  |  | 100% | 10 | Completed | Depart- mental
534 | Improvement of Roads and Infrastructure at District Headquarters; Saiha, Lawngtlai, Lunglei, Hnahthial, Serchhip, Champhai, Khawzawl, Saitual, Kolasib, Mamit ; (Sh: Strengthening of Bailey Bridge over R. Teirei (Darlak) on NH-44A | 70 | National Highway Division - I | 31.03.23 | 31.03.24 | 100% | 70 |  |  | 100% | 70 | Completed | Depart- mental
535 | Improvement of Roads and Infrastructure at District Headquarters; Saiha, Lawngtlai, Lunglei, Hnahthial, Serchhip, Champhai, Khawzawl, Saitual, Kolasib, Mamit ; (Sh:Mamit to Bairabi Road) | 16 | National Highway Division - I | 31.03.23 | 31.03.24 | 100% | 16 |  |  | 100% | 16 | Completed | Depart- mental
536 | Improvement of Roads and Infrastructure at District Headquarters; Saiha, Lawngtlai, Lunglei, Hnahthial, Serchhip, Champhai, Khawzawl, Saitual, Kolasib, Mamit ; (Sh:Dampui Approach Road from NH-44A | 5 | National Highway Division - I | 31.03.23 | 31.03.24 | 100% | 5 |  |  | 100% | 5 | Completed | Depart- mental
537 | Improvement of Roads and Infrastructure at Aizawl City (Sh: Clearing, Grubbing of Roads Land and Jungle clearance of Saiphai Bamboo Plantation in Mizoram | 45 | National Highway Division - I | 31.03.23 | 31.03.24 |  |  | 30% |  | 30% |  | work in progress | Depart- mental
538 | Improvement of Roads and Infrastructure at Aizawl City (Sh: Work under National Highway Division-I) | 30 | National Highway Division - I | 31.03.23 | 31.03.24 | 100% | 30 |  |  | 100% | 30 | Completed | Depart- mental
539 | Improvement of Roads and Infrastructure at Aizawl City (Sh: Estimate for Const. of Lengpui Catholic School Road PCC) | 15 | National Highway Division - I | 31.03.23 | 31.03.24 | 100% | 15 |  |  | 100% | 15 | Completed | Depart- mental
| TOTAL FOR NATIONAL HIGHWAY DIVISION I | 1119.89 |  |  |  |  | 409 |  |  |  | 434
NATIONAL HIGHWAY DIVISION - II SASCI : 2.23-2.24
540 | Const. of Agri. Link Road from Sailutar, Mauchar, Sunhluchhip to R.Tuirial Agri. Potential Area. | 265 | National Highway Division - II |  |  | 100% | 238 |  |  | 100% | 238 | Priority I
541 | PCC Flooring of Thlanmual kawng Sesawng | 15 | National Highway Division - II |  |  | 100% |  |  |  | 100% |  | Priority I
542 | Widening & PCC Flooring of Kalvari Tlang Chhuah kawng, Khawruhlian. | 20 | National Highway Division - II |  |  | 100% |  |  |  | 100% |  | Priority I
543 | PCC Flooring of Hmunnghak Vengchung panna ( Lalsangluaia Sailo Road ) Hmunnghak. | 10 | National Highway Division - II |  |  | 100% |  |  |  | 100% |  | Priority I
544 | Const. of Khawruhlian Bypass Road with connectivity to N.Khawdungsei, Zirtuichhuah, Sunhluchhip & Khawlwk (Part-II) | 220 | National Highway Division - II |  |  | 90% | 184 | 10% | 0 | 100% | 184 | Priority I
| TOTAL FOR NATIONAL HIGHWAY DIVISION II | 530 |  |  |  |  | 422 |  | 0 |  | 422
NATIONAL HIGHWAY DIVISION - III SASCI : 2023-2024
545 | Const. of Rigid Pavement at essential places between 133.00Kmp to 147.00Kmp on NH-54 (Total Length =400.00 m) | 267 | National Highway Division - III | 25.7.23 | 13.11.23 | 100% | 261.21 |  | 5.79 | 100% | 267 | Completed | Departmental
546 | Improvement of Roads and Infrastructures at Aizawl City (Sh: Pot Hole filling and patches repair of NH-54(NH-6) for regular flow of traffic (Kawnpui - Sairang ) | 20 | National Highway Division - III | 18.9.23 | 15.11.23 | 100% | 19.99 |  | 0.01 | 100% | 20 | Completed | Departmental
| TOTAL FOR NATIONAL HIGHWAY DIVISION III | 287 |  |  |  |  | 281.2 |  | 5.8 |  | 287
QUALITY CONTROL RESEARCH & DEVELOPMENT DIVISION, ZUANGTUI : AIZAWL.
547 | Improvement of Government Building, High Court, Government Polytechnic & E-in-C, PWD Office (Sh: Const. of Barbet Wire fencing of PWD Complex at Zuangtui. | 23.3 | Quality Control Research & Development Division. |  |  | 100% | 23.3 |  |  | 100% | 23.3 | Phy.Completed | Spot Quotation
548 | Improvement of Government Building, High Court, Government Polytechnic & E-in-C, PWD Office (Sh: Const. ofBeily Bridge PartsGodown at PWD Complex, Zuangtui | 20 | Quality Control Research & Development Division. |  |  | 100% |  |  | 20 | 100% | 20 | .Completed | Departmental
| TOTAL FOR QUALITY CONTROL DIVISION | 43.3 |  |  |  |  | 23.3 |  | 20 |  | 43.3
AIZAWL BUILDING DIVISION SASCI : 2023-2024
549 | Improvement of Roads and Infrastructures at Aizawl City under Aizawl Road South Division (Electrification of Refugee Relief Camp BSUP) | 5 | Aizawl Building Division | 18.10.23 | 11.11.23 | 100% | 5 |  |  | 100% | 5 | Completed | Departmental
550 | Improvement of Gov't Buildings, High Court, Gov't. Polytechnic and E - in - C Office (Sh: Furnishing of Hon'ble Chief Minister's Bungalow. | 7.71 | Aizawl Building Division | 05.10.23 | 06.11.23 | 100% | 7.71 |  |  | 100% | 7.71 | Completed | Departmental
| TOTAL FOR AIZAWL BIULDING DIVISION | 12.71 |  |  |  |  | 12.71 |  | 0 |  | 12.71

## AMOP
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD
Source of funding : AMOP | [9 empty] | Month : February 2025
Sl. No | Name of Work/Project | Approved Cost (Rs.in lakh) | Name of Division | Date of Commence ment | Target date of Completion | Cummutive Progress at the end of last month |  | Achievement of woks during the Month |  | Overall cumulative achievement |  | Remarks | Mode of Contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Luangpawl Helipad and Approach Road repair in connection to Union Defence Minister's visit at Mamit | 9.25 | Mamit Division |  |  | 100% | 8.8 |  |  | 100% | 8.8 | Work Completed
2 | Pothole filling & Resurfacing of Khawrihnim Internal Road (0.00-0.390Kmp) | 4.5 | Mamit Division |  |  | 100% | 4.27 |  |  | 100% | 4.27 | Work Completed
3 | Re-Construction of Paved Shoulder with V-Shaped Side Drain on PWD Complex - Payground Road at Mamit | 9.54 | Mamit Division |  |  | 42% | 9.08 | 10% |  | 52% | 9.08 | Work in progress
4 | Re-Construction of PWD Complex - Playground via Ngharpet (0.00-1.37 Kmp) at Mamit | 19.7 | Mamit Division |  |  | 36% | 18.75 | 28% |  | 64% | 18.75 | Work in progress
5 | Resurfacing of Charkawn - Vengthar via PES (YMA Road) (0.00 - 0.460 Kmp) at Mait | 8 | Mamit Division |  |  | 100% | 7.6 |  |  | 100% | 7.6 | Work Completed
6 | Seal coating of DC Complex - Bairabi Road via Revenue Office at Mamit (0.00 - 0.310 Kmp) | 2.31 | Mamit Division |  |  | 100% | 2.19 |  |  | 100% | 2.19 | Work Completed
7 | Resurfacinf of Belleikawn to Helipad at W.Phaileng | 9.02 | Mamit Division | 16.7.24 |  | 100% | 9.01 |  |  | 100% | 9.01 | Completed
8 | Resurfacing of Approach Road to Playground (HS Veng to W Phaileng Playground) | 2.91 | Mamit Division | 16.7.24 |  | 100% | 2.9 |  |  | 100% | 2.9 | Completed
9 | Maintenance of W Phaileng to Tuirum Road | 5 | Mamit Division | 16.7.24 |  | 100% | 4.99 |  |  | 100% | 4.99 | Completed
| GRAND TOTAL | 70.23 |  |  |  | 90.64% | 67.59 |  |  | 90.64% | 67.59
10 | Construction of RCC Side Drain on Bazar Traffic point to Meisatla Forest Check gate Road | 79.63 | Siaha Division | 01.11.24 | 31.03.25 |  |  |  |  | 100% |  | Work physically completed
11 | Annual Maintenance Operation Plan 2024-2025 | 68.17 | Kolasib Division | 19.09.24 | 19.03.25 | 86.6% | 59.26 |  |  | 86.6% | 59.26 | Work in progress