## ARND
MONTHLY PROGRESS REPORT FOR THE MONTH OF JUNE, 2025
Name of Work : Resurfacing of road within Aizawl city under Aizawl Road North Division
Name of Scheme : State Funding
Tender Amount : Rs. 2145.56 lakh
Agreement Amount : Rs. 2145.56 lakh
Name of Contractor : Nidhi Creative infrastructure Pvt.Ltd.
Name of Division : Aizawl Road North Division
Sl. No. | Name of works | Unit | Qnty | Approved Cost (in lakh) | Date of Commencement | Target Date of Completion | Commulative Progress at the end of Last Month |  | Achievement of Works during the Month |  | Overall cumulative achievement |  | Remarks | Mode of Contract
[7 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Non Bituminous Base Course | sqm | 8495 | 1699.8 | 2025-04-17 | 2026-10-17 | 14.95% | - | 0% | - | 14.95% | - | Works in progress | EPC
2 | Construction of Flexible Pavement | km | 44.63 | 1699.8 |  |  | 15.69% | - | 0.35% | - | 16.04% | -
3 | Construction of Rigid Pavement | km | 1.5 | 397.57 |  |  | - | - | - | - | - | -
4 | Construction of Hume Pipe Culvert | No. | 1 | 6.14 |  |  | - | - | 100% | - | 100% | -
5 | Widening of Tlaklui to Sihpui road Junction | Rm | 60 | 42.05 |  |  | - | - | - | - | - | -
| Total = |  |  | 2145.56 |  |  | 12.41% |  | 0.56% |  | 12.97%
MONTHLY PROGRESS REPORT FOR THE MONTH OF JUNE, 2025
Name of Work : Widening and Improvement of Road from Durtlang Leitan To Sihphir Section (Length 10.25 Km) of Aizawl - Durtlang - Lungdai - Kawnpui Road in the State Of Mizoram | [7 empty] | Name of Contractor : M/s SLT Infracon Private Limited
Name of Scheme : CRF | [7 empty] | Date of Commencement : 14/07/2023
Tender Amount : Rs. 46.57 Crore | [7 empty] | Target date of Completion : 31/01/2025
Agreement Amount : Rs. 35.53 Crore | [7 empty] | Revised Target date of Completion : NIL
Name of Division : Aizawl Road North Division | [7 empty] | D-III Balance :
OVERALL ACHIEVEMENT (PHY) - |  | 56.78% | [8 empty] | (Rs. in lakh)
Sl. No. | Name of Works | Unit | Cost (in lakh) | Date of commencement | Target date of completion | Cumulative Progress at the end of last month |  | Achievement works during the month |  | Overall cumulative achievement |  | Remarks | Mode of Contract | Previous achievement |  | 7.98
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 |  |  |  |  | 2926.76
1 | Scarifying | m3 | 8.61 | 14.7.23 | 31.1.25 | 64% | 1463.38 | - | - | 64% | 1463.38 | In Progress | EPC | 50.05% | 0.28% | 0.1792% | 86.58%
2 | Earthwork | m3 | 93.82 |  |  | - |  | - |  | 100% |  |  |  | 101.8% | 3.05% | 3.05%
3 | Granular Sub-Base (GSB) | m3 | 37.84 |  |  | 92% |  | - |  | 92% |  |  |  | 67.45% | 1.23% | 1.132%
4 | Dry Lean Concrete (DLC) | m3 | 611.55 |  |  | 40% |  | 0.39% |  | 40.39% |  |  |  | 14.17% | 19.88% | 8.03%
5 | Pavement Quality Concrete (PQC) | m3 | 2120.72 |  |  | 43% |  | 4.8% |  | 47.8% |  |  |  | 14.11% | 68.94% | 32.95%
6 | Hume Pipe Culvert | No. | 55.37 |  |  | - |  | - |  | 100% |  |  |  | 100% | 1.8% | 1.8%
7 | RCC Slab Culvert | No. | 148.27 |  |  | 88.98% |  | - |  | 88.98% |  |  |  | 88.98% | 4.82% | 4.289% | 51.43% | 44.53%
8 | Lined Side Drain | No. | 5.39 |  |  | - |  | - |  | 100% |  |  |  | 414.3% | 1.13% | 1.13% | 13.42%
9 | Retaining Wall | Rm | 450.68 |  |  | - |  | - |  | 100% |  |  |  | 92.02% | 94.52% | 94.52%
10 | Traffic Signboard | Rm | 3.91 |  |  | - |  | - |  | - |  |  |  | 0% | 0.82% | #VALUE!
11 | Road Marking | Rm | 7.92 |  |  | - |  | - |  | - |  |  |  | 0% | 1.66% | #VALUE!
12 | Km Stone | Nos. | 0.38 |  |  | - |  | - |  | - |  |  |  | 0% | 0.08% | #VALUE!
13 | Crash barrier | - | 8.54 |  |  | - |  | - |  | - |  |  |  | 471.1% | 1.79% | #VALUE! | #VALUE! | #VALUE!
|  |  | 3553 | [7 empty] | 1463.38 | [6 empty] | #VALUE!
3553
MONTHLY PROGRESS REPORT FOR THE MONTH OF JUNE, 2025 (ROAD WORKS)
Name of Work : Construction of Two Lane from Sihhmui to Ramrikawn Road (Stage-I) | [7 empty] | Name of Contractor : F. Kapsanga, Tuikual
Name of Scheme : CRF | [7 empty] | Revised Target date of Completion : 03.05.2022
Sanction Amount : Rs. 80.00 Crore | [7 empty] | D-III Balance :
Tender Amount : Rs. 71.37 Crore
Name of Division : Aizawl Road North Division
OVERALL ACHIEVEMENT (PHYSICAL) - 87.66% | [10 empty] | (Rs. in lakh)
Sl. No. | Name of Works | Unit | Cost (in lakh) | Date of commencement | Target date of completion | Cumulative Progress at the end of last month |  | Achievement works during the month |  | Overall cumulative achievement |  | Remarks | Mode of Contract |  | 0.82
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Formation Works | Km | 5464.63 | 1.10.2018 | 1.10.2020 | 97% | 6375.06 | - | - | 97% | 6375.06 | In progress | Item Rate
2 | Protection Works
| a) Retaining Wall | Rm | 540.88 |  |  | 91% |  | - |  | 91%
3 | Cross Drainage Works
| a) Hume Pipe Culvert | Nos. | 188.63 |  |  | 48% |  | 2% |  | 50%
| b) Box Culvert | Nos. | 818.03 |  |  | 98% |  | 1% |  | 99% |  |  |  | #VALUE!
4 | Lined Side Drain
| a) Lined Drain | Km | 44.32 |  |  | 8% |  | - |  | 8%
| b) Unlined Drain | Km | 8.31 |  |  | 96% |  | - |  | 96% |  |  |  | 0.10387 | 0.15581
5 | Box Culvert and Retaining Structure | [13 empty] | 150
| a) Box Culvert | Nos. | 493.84 |  |  | - |  | - |  | -
| b) Retaining Wall | Nos. | 96.86 |  |  | 12% |  | - |  | 12%
6 | Contingencies etc. | LS | 344.5 |  |  | - |  | - |  | -
| GRAND TOTAL |  | 8000 | [7 empty] | 6375.06 |  |  |  | 26338243
MONTHLY PROGRESS REPORT FOR THE MONTH OF JUNE, 2025 UNDER NABARD
OVERALL ACHIEVEMENT (PHY) - 91.55%
Sl. No. | Name of Project | Unit | Approved Cost (Rs. in lakh) | Date of Commencement | Target date of completion | Cumulative Progress at the end of last month |  | Achievement works during the month |  | Overall cummulative achievement |  | Remarks | Mode of contract
[6 empty] | Phy. | Fin. | Phy. | Fin. | Phy. | Fin.
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
IMPROVEMENT OF RAMRIKAWN TO NH-54 VIA SAKAWRTUICHHUN ROAD (3.00 Kmp - 7.50 Kmp = 4.50 Km)
1 | Rigid Pavement of Ramrikawn to Sakawrtuichhun | Rm | 432.65 | - | - | 85% | 216.33 | 5% | - | 90% | 216.33 | Work in Progress | Departmental
2 | Resurfacing of Ramrikawn to Zihnghalkawn 980 Rms | Rm |  | - | - | - |  | - |  | 100% |  | Phy Completed
3 | Constn. of R/Wall at Ch 4.230 Kmp at Sakawrtuichhun | Rm |  | - | - | - |  | - |  | 100% |  | Phy Completed
4 | Constn. of R/Wall at Ch 3.420 Kmp at Sakawrtuichhun | Rm |  | - | - | - |  | - |  | 100% |  | Phy Completed
5 | Constn. of R/Wall at Ch 6.340 Kmp at Sakawrtuichhun | Rm |  | - | - | - |  | - |  | 100% |  | Phy Completed
6 | Constn of Slab Culvert at 5.900 kmp at Sakawrtuichhun | Rm |  | - | - | - |  | - |  | 100% |  | Phy Completed
MONTHLY PROGRESS REPORT FOR THE MONTH OF JUNE, 2025
PM - DevINE
A. Physical Report
(Rs. in lakhs)
Sl No | Name of the project, location and State | Name of the Implementing Agency/Deptt. | Approved cost by MDoNER/NEC & Date of Approval |  | Date of actual commencement of work/scheme | Target date of completion of work/scheme | Scope of the work/scheme in physical terms (eg. Kms etc) | Physical Achievement |  | Remarks
|  |  | Cost | Date |  |  |  | Percentage(during the month) | Percentage till the reporting period
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
1 | Construction of Bamboo Link Road from Tuirial Airfield to North Chaltlang (18 Kms) under PM - DevINE | Sadguru Engineers & Allied Services Private Ltd | 3358 | 17.4.23 | 1.08.2023 | 20.10.2025 | Concrete Pavement from 0.00 - 18.00 Kmp | - | 47.13% | Work in progress
MONTHLY PROGRESS REPORT FOR THE MONTH OF JUNE, 2025
PM - DevINE
B. Financial Report
(Rs. in lakhs)
Sl No | Name of the project, location and State | Name of the Implementing Agency/Deptt. | Approved cost by MDoNER/NEC & Date of Approval |  | Fund released by MDoNER/NEC |  | Expenditure made |  | Unspent balance out of the fund released | Status of submission of U/Cs | Remarks
|  |  | Original Cost | Revised Cost | During 2024 - 2025 | Since inception (cumulative) | During the month vis-à-vis target | Since inception (cumulative)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Construction of Bamboo Link Road from Tuirial Airfield to North Chaltlang (18 Kms) under PM - DevINE | Sadguru Engineers & Allied Services Private Ltd | 3358 | - | - | 845.89 | - | 845.89 | - | - | -
| Name of Officer - LALBIAKNUNGA | [5 empty] | Chief Engineer, PWD
| Designation - Sr. Executive Engineer | [5 empty] | Highways
| Date with seal - 2.07.2025 | [5 empty] | Mizoram: Aizawl
MONTHLY PROGRESS REPORT FOR THE MONTH OF JUNE, 2025 ( ROAD WORKS)
SPECIAL ASSISTANCE TO THE STATES FOR CAPITAL INVESTMENT (SASCI - I) UNDER AIZAWL ROAD NORTH DIVISION
Sl. No. | Name of works | Unit | Cost (in lakh) | Date of commencement | Target date of completion | Cumulative Progress at the end of last month |  | Achievement works during the month |  | Overall cumulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
SUB - DIVISION - I
1. CONSTRUCTION AND UPGRADATION OF ROAD FROM RAMTHAR-RAMTHAR NORTH- ZARKAWT-SARON, AIZAWL
ZARKAWT
1 | Construction of Ahimsa to Jail Veng road at Zarkawt | Rm | 77.98 | 2.5.23 | 30.11.23 | 100% | - | - | - | 100% | 250.42 | Phy Completed | Spot Quotation
2. CONSTRUCTION OF CHECK DAM AT THEIHAI LUI,ARMED VENG
1 | Counterfort Retaining Wall at Armed Veng | Rm | 41.2174 | - | - | - | - | - | - | 100% |  | Phy Completed | Spot Quotation |  | 85248
2 | Toe Walls at Armed Veng side | Rm | 31.4446 | - | - | - |  | - |  | 100% |  | Phy Completed | Spot Quotation
3 | Retaining Wall at Ramthar side | Rm | 30.2092 | - | - | - |  | - |  | 100% |  | Phy Completed | Spot Quotation
4 | Construction of RCC Link Drain near Pu Rallianzuala's Land | Rm | 50.6527 | - | - | - |  | - |  | 100% |  | Phy Completed | Spot Quotation
MONTHLY PROGRESS REPORT FOR THE MONTH OF JUNE, 2025 UNDER SASCI - II
Sl. No. | Name of works | Unit | Approved Cost (in lakh) | Date of Comment | Target Date of Completion | Commulative Progress at the end of Last Month |  | Achievement of Works during the Month |  | Overall cumulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
SUB - DIVISION - I
1.CONSTRUCTION OF RCC DRAIN AND PCC PAVEMENT AT CHHINGA VENG AND ELECTRIC VENG
1 | Resurfacing of Armed Veng South to Bethlehem Vengthlang Road at Ch : 0.677 - 1.230 km | Rm | 10.91 | 6.12.2023 | 15.12.2023 | - | - | - | - | 100% | 148.1 | Phy Completed | Restricted
2 | Reconstruction of Collapsed RCC Slab Culvert on Armed Veng South to Bethlehem Vengthlang (Old Zoo Road) near Rawra Chhutna | No | 1.2 |  |  | - | - | - |  | 100% |  | Phy Completed | Restricted
3 | Balance Work of Construction of RCC Pavement on District Jail to Lower Armed Veng Road (Service Road) | Rm | 1.84 | 10.4.2023 | 11.4.2023 | - | - | - |  | 100% |  | Phy Completed | Restricted |  | #VALUE!
4 | Construction of New Road from Lalhmingliana Sailo House to Siamphunga Lei at Tuithiang Phase-II | Rm | 30.14 | 11.3.2024 |  | - | - | - |  | 100% |  | Phy Completed | Restricted
5 | Construction of Drainage System at Aizawl Civil Hospital, Dawrpui West Area | Rm | 14.52 | 18.3.2023 |  | - | - | - |  | 100% |  | Phy Completed | Restricted
6 | Construction of Retaining Wall on Dawrpui Thlanmual Plot-3 | Rm | 6.03 | 24.4.2024 |  | - | - | - |  | 100% |  | Phy Completed | Restricted | asd
7 | Construction of RCC Pavement on Hostel Square at Armed Veng South | Rm | 4.17 |  |  | - | - | - |  | 100% |  | Phy Completed | Restricted
8 | Construction of RCC Pavement between Pu Thansanga's House to Pu Ronghakliana's House on Armed Veng South Local Council Road | Rm | 2.17 |  |  | - | - | - |  | 100% |  | Phy Completed | Restricted
9 | Construction of PCC Pavement near Pu Larry Lalrova's House Saron Veng | Rm | 4.24 | 8.4.2024 | 13.4.2024 | - | - | - | - | 100% | 148.09 | Phy Completed | Restricted
10 | Construction of V-Shape Side drain near Rawra Chhutna | Rm | 0.11923 |  |  | - | - | - |  | 100% |  | Phy Completed | Restricted
11 | Construction of Retaining Wall on Dawrpui Thlanmual Plot - 1 | Rm | 10.95 |  |  | - | - | - |  | 100% |  | Phy Completed | Restricted
12 | Construction of Retaining Wall on Dawrpui Thlanmual Plot - 2 | Rm | 8.11 |  |  | - | - | - |  | 100% |  | Phy Completed | Restricted |  | #VALUE!
13 | Construction of Breast Wall on Armed Veng South Local Council Road near Pu Lalnghakliana's House | Rm | 5.94 | 15.4.2024 | 20.4.2024 | - | - | - |  | 100% |  | Phy Completed | Restricted
14 | Construction of Breast Wall between Chawngneihkunga's House to Khupneihvunga's House | Rm | 6.41 |  |  | - | - | - |  | 100% |  | Phy Completed | Restricted
15 | Widening of Road between Chawngneihkunga's House to Khupneihvunga's House | 86 | Rm | 22.4.2024 |  | - | - | - |  | 100% |  | Phy Completed | Restricted
16 | Construction of Retaining Wall below Chhinga Veng Thlanmual | Rm | 46 | 26.2.2024 |  | - | - | - |  | 100% |  | Phy Completed | Restricted
2. IMPROVEMENT OF ROAD FROM RAMHLUN VENGTHAR TO RAMHLUN SPORT COMPLEX, AIZAWL.
17 | Construction of RCC Balcony on Ramhlun South Cemetery at Ramhlun South | Rm | 42.94 | 8.3.2024 |  | - | - | - | - | 100% | 211.87 | Phy Completed | Restricted
18 | Construction of RCC Frame Structure Breast Wall near Ramhlun South Cemetary | Rm | 25.61 | 8.2.2024 |  | - | - | - |  | 100% |  | Phy Completed | Restricted
19 | Construction of Retaining Wall below Presbyterian Church, Laipuitlang | Rm | 3.93 | 16.1.2024 | 13.2.2024 |  | - | - |  | 100% |  | Phy Completed | Restricted
20 | Construction of RCC Pavement & Lowering on Jubilee road at Ramhlun Vengthar | Rm | 58.59 | 4.3.2024 |  | - | - | - | - | 100% | 222.94 | Phy Completed | Restricted
21 | Construction of RCC Rectangular side drain with cover near Jubilee road at Ramhlun Vengthar | Rm | 3.65 | 3.4.2024 |  | - | - | - |  | 100% |  | Phy Completed | Restricted
22 | Construction of Steel Grate Cover Side Drain near Jubilee road at Ramhlun Vengthar | No | 1.49 | 3.4.2024 |  | - | - | - |  | 100% |  | Phy Completed | Restricted
23 | Construction of Breast wall on Turning Point at Tetea Road Ramthar North | Rm | 5.65 | 6.2.2024 | 23.2.2024 | - | - | - |  | 100% |  | Phy Completed | Restricted
24 | Construction of RCC Pavement on Tetea Road (Below Pu Dawngliana House) at Ramthar North | Rm | 7.89 | 2.4.2024 | 26.4.2024 | - | - | - |  | 100% |  | Phy Completed | Restricted
25 | Construction of Retaining wall on Tetea Road Block-I at Ramthar North | Rm | 6.63 |  |  | - | - | - |  | 100% |  | Phy Completed | Restricted
26 | Construction of Retaining wall on Tetea Road Block-II at Ramthar North | Rm | 1.83 | 13.1.2024 | 12.2.2024 | - | - | - |  | 100% |  | Phy Completed | Restricted | 211.87
27 | Construction of Breast Wall Below Step at NHC Ramhlun Venglai | Rm | 3.33 | 15.1.2024 | 16.2.2024 | - | - | - |  | 100% |  | Phy Completed | Restricted | 2.1
28 | Construction of Breast Wall Vertical Extension NHC at Ramhlun Venglai | Rm | 5.6 | 1.2.2024 | 19.2.2024 | - | - | - |  | 100% |  | Phy Completed | Restricted | 213.97
29 | Construction of RCC Rectangular side drain with cover NHC at Ramhlun Venglai | Rm | 0.97 | 2.2.2024 | 20.2.2024 | - | - | - |  | 100% |  | Phy Completed | Restricted
30 | Construction of RCC Rectangular side drain with cover on Rokhuma Colney to PC.Lalzuiliana House(Bishop Road) at Ramthar | Rm | 2.98 | 12.3.2024 | 25.4.2024 | - | - | - |  | 100% |  | Phy Completed | Restricted
31 | Construction of Breast Wall Below St.Lawrence School at Ramthar | Rm | 6.56 | 6.3.2024 | 22.3.2024 | - | - | - |  | 100% |  | Phy Completed | Restricted
32 | Construction of Breast Wall near Boxing hall at Ramhlun Venglai | Rm | 9.38 | 26.3.2024 |  | - | - | - | - | 100% | - | Phy Completed | Restricted
33 | Construction of Retaining Wall on Sihpui to Tlaklui road at Pu C Lalnunmawia's House | Rm | 8.81 | 5.3.2024 | 21.3.2024 | - | - | - |  | 100% |  | Phy Completed | Restricted
34 | Construction of PCC Pavement on ICI road Complex Vengthlang at Ramhlun Sport Complex | Rm | 3.51 | 8.3.2024 | 20.3.2024 | - | - | - |  | 100% |  | Phy Completed | Restricted
35 | Construction of Retaining wall near Pu.Rosangpuia House at Ramhlun Sport Complex | Rm | 4.22 | 5.3.2024 | 24.4.2024 | - | - | - |  | 100% |  | Phy Completed | Restricted
36 | Construction of Breast wall on LC Road near Lianhnuna Road at Ramhlun Sport Complex | Rm | 3.09 | 4.3.2024 | 25.3.2024 | - | - | - |  | 100% |  | Phy Completed | Restricted
37 | Construction of RCC Side drain near Pu.Para House at Ramhlun Sport Complex | Rm | 0.49 | 5.3.2024 | 20.3.2024 | - | - | - |  | 100% |  | Phy Completed | Restricted
38 | Construction of RCC Footpath on LC Road near Pu HC Thangvela's House to Pu B Zanghinglova's House | Rm | 16.85 | 12.3.2024 |  | - | - | - |  | 100% |  | Phy Completed | Restricted
3. CONSTRUCTION OF LUNGHLU ROAD AT CHANMARI WEST AIZAWL
39 | Construction of RCC Link drain near Hotel Platinum at Zarkawt | Rm | 0.84926 | 6.12.2023 | 9.12.2023 | - | - | - | - | 100% | 139.99 | Phy Completed | Restricted
40 | Improvement of Zarkawt Valley Approach Road Phase-II | Rm | 47.0033 | 19.2.2024 |  | - | - | - |  | 100% |  | Phy Completed | Restricted
41 | Construction of Retaining wall near Babula's House at Chanmari | Rm | 13.2659 | 5.2.2024 |  | - | - | - | - | 100% | - | Phy Completed | Restricted | #VALUE!
42 | Repair of Link Drain with Cover near J.Thangdailova House at Electric Veng | Rm | 9.6394 | 8.2.2024 |  | - | - | - |  | 100% |  | Phy Completed | Restricted
43 | Construction of New Cemetery Road at Electric Veng | Rm | 28 | 2.2.2024 |  | - | - | - |  | 100% |  | Phy Completed | Restricted
4. UPGRADATION OF INTERNAL ROADS AT DURTLANG, BAWNGKAWN, CHALTLANG, ZUANGTUI, RAMHLUN & RAMTHAR
44 | Steel Grate Cover Side Drain on PC Malsawma House to Rev. C.Vanlalhruaia House at Ramhlun South | Rm | 8.04 | 20.3.2024 |  | - | - |  | - | 100% | 132.89 | Phy Completed | Restricted
45 | Construction of RCC Foot Step near PC.Lalzuiliana House Ramthar | Rm | 16.58 | 6.3.2024 |  | - | - |  |  | 100% |  | Phy Completed | Restricted
46 | Construction of RCC Link Drain near PC.Lalzuiliana House at Ramthar | Rm | 8.42 | 6.3.2024 |  | - | - |  |  | 100% |  | Phy Completed | Restricted
47 | Construction of Breast Wall Below PC.Laltanpuia House at Ramthar North | Rm | 7.3657 | 28.3.2024 | 24.4.2024 | - | - |  |  | 100% |  | Phy Completed | Restricted
48 | Construction of Breast Wall near Pu.Lalrammuana Ralte House at Ramthar North | Rm | 5.76 | 5.3.2024 | 27.3.2024 | - | - |  |  | 100% |  | Phy Completed | Restricted
49 | Construction of RCC Foot Step near Pi.Manmawii House at Ramhlun South | Rm | 6.68 | 4.3.2024 |  | - | - |  |  | 100% |  | Phy Completed | Restricted
WORK UNDER IMPLEMENTATION OF ARTICLE 275 (1) PHASE - II
50 | Construction of Bethany Road at Chhinga Veng | Rm | 70 | 7.10.2023 |  | - | - | - |  | 100% |  | Phy Completed | Restricted
SUB - DIVISION - II
UPAGRADATION OF BETHEL VENG ROAD AT ZEMABAWK, AIZAWL WITH APPROACH ROAD TO ZOKHAWSANG BYPASSS ROAD
51 | Upagradation of Bethel Veng Road at Zemabawk, Aizawl with approach road to Zokhawsang Bypass Road
| 1. PCC Pavement at Ch: 0.000 - 0.580kmp | Rm | 57.8 | 14.12.23 | 14.12.24 | - | - | - | - | 100% | 153.2 | Phy Completed | Restricted
| 2. Construction of PCC V shape side drain at Ch: 0.000kmp | Rm | 1.57 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | Phy Completed | Restricted
| 3. Clearance of Landslip | Nos | 20.83 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | Phy Completed | Restricted
52 | Additional requirement for Upgradation of Bethel Veng road at Zemabawk
| 1. Earthwork for Widening (Additional) | Km | 69.54 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | Phy Completed | Restricted
| 2. RCC Frame Retaining Walls no1 | Rm | 5.2 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | Phy Completed | Restricted
IMPROVEMENT OF MUTHI - TUIRIAL LINK ROAD
53 | 1. Widening & Curve Improvement | Km | 134.74 | 14.12.23 | 14.12.24 | - | - | - | - | 100% | 121.23 | On-Going | Restricted
2. Construction of Slab Culvert
| i. Slab Culvert Type-I | Nos | 11.5 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | On-Going | Restricted
3. Construction of Retaining Wall
| i. Retaining Wall Type - I | Rm | 10 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | Work in Progress | Restricted
| ii. Retaining Wall Type - II | Rm | 14 | 14.12.23 | 14.12.24 | - | - | - |  | - |  | Not yet started
CONSTRUCTION OF BAMBOO LINK ROAD FROM NAUSEL, CHAMDUR, LUNGSANG, PUMPELHSEI, KAWRBEL
54 | Construction of Nausel - Tuirial Bamboo Link Road | [5 empty] | - |  | - |  | 187.92
| 1. Formation Cutting | Km | 36.01 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 2. Construction of Slab Culvert | Nos | 26.63 |  |  | - |  | - |  | 100% |  | Phy Completed | Restricted
| At chainage between 0.000 to 3.500 Kmp | Nos | 59.39 | 14.12.23 | 14.12.24 | - |  | - |  | - |  | Not yet started
| 3. Construction of Retaining Wall |  |  |  |  | - |  | - |  | 100% |  | Phy Completed | Restricted
At chainage between 0.000 to 3.500 Kmp
| Retaining Wall | Nos | 30.93 | 14.12.23 | 14.12.24 | - |  | - |  | - |  | Not yet started
55 | Concrete Pavement of Sihphir Neibawih khawhnuai kawng balance
| 1. Concrete Pavement | Rm | 36.28 | 14.12.23 | 14.12.24 | - |  | - |  | 100% |  | Phy Completed | Restricted
2. Construction of Slab Culvert
| At chainage between 0.000 to 0.503 Kmp | Nos | 43.71 | 14.12.23 | 14.12.24 | - |  | - |  | - |  | Not yet started
56 | Construction of Hmunte Road at Muthi
| 1. Formation Cutting | Km | 36.57 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | Phy completed | Restricted
| 2. Construction of Slab Culvert |  |  |  |  | - | - | - |  | 100% |  | Phy completed | Restricted
| At chainage between 0.000 to 1.000 Kmp | Nos | 16.57 | 14.12.23 | 14.12.24 | - | - | - |  | - |  | Not yet started
| At chainage between 1.000 to 2.000 Kmp | Nos | 14.5 | 14.12.23 | 14.12.24 | - | - | - |  | - |  | Not yet started
| 3. Construction of Retaining Wall |  |  |  |  | - | -
At chainage between 0.000 to 2.000 Kmp
| Retaining Wall | Rm | 7.18 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | Phy completed | Restricted
57 | Construction of Chamdur - Kawrbellui Road
| 1. Formation Cutting | Km | 30.5 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | Phy Completed | Restricted
CONSTUCTION OF ROAD FROM ZEMABAWK NORTH TO CWC AND MUALZEN
58 | Construction of New Road from Zemabawk North Dinthar Veng to CWC including Protetion Works & Cross Drain | [7 empty] | - |  | 239.91
| 1. Formation Cutting | Km | 72.46 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | Phy Completed | Restricted
| 2. Construction of Slab Culvert Type-I | Nos | 8 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | Phy Completed | Restricted
| 3. Construction of Slab Culvert Type-II | Nos | 12 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | Phy Completed | Restricted
| 4. Construction of Slab Culvert Type-III | Nos | 16.94 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | Phy Completed | Restricted
| 5. Construction of Retaining Wall Type-I | Rm | 25 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | Phy Completed | Restricted
59 | Construction of New Road from Zemabawk North Thlanmual Hnuai to Mualzen including Protetion Works & Cross Drain
| 1. Formation Cutting | Km | 60.12 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | Phy Completed | Restricted
2. Construction of Slab Culvert
| At chainage between 0.000 to 1.500 Kmp | Nos | 28.6 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | Phy Completed | Restricted
| At chainage between 1.500 to 3.000 Kmp | Nos | 23.28 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | Phy Completed | Restricted
CONSTRUCTION OF ROAD FROM FALKLAND TO GALILEE VIA MITLAMUAL AT ZEMABAWK, AIZAWL
60 | Construction of Widening & New Road from Falkland to Mitlamual including protection Works & Cross Drain | [7 empty] | - |  | 107.94
| 1. Widening and New Cutting | Km | 42.16 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | Phy Completed | Restricted
| 2. Construction of Slab Culvert Type-I | Nos | 2.64 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | Phy Completed | Restricted
61 | Construction of New Road from Zemabawk Galile Vailui to Mitlamual including Protection Works and Cross Drain | [7 empty] | - |  | 107.94
| 1. Formation Cutting | Km | 52.09 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | Phy Completed | Restricted
| 2. Construction of PCC Pavement | Rm | 22.88 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | Phy Completed | Restricted
| 3. Construction of Slab Culvert Type-I | Nos | 14.63 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | Phy Completed | Restricted
CONSTRUCTION OF ROAD FROM FALKLAND TO ZEMABAWK NORTH VIA THUAMPUI
62 | Construction of New Road from Falkland Penniel Road to Thuampui Vengthar and BS Farm to UPC BiakIn at Pi Vani Lui Link Road including Protection Work & Cross Drain (1.00 Km) | [7 empty] | - |  | 151.18
| 1. Widening of Road | Rm | 29.22 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | Phy Completed | Restricted
| 2. Construction of PCC Pavement on BS Farm to UPC BiakIn | Rm | 32.18 | 14.12.23 | 14.12.24 | - | - | - |  | - |  | Not yet started
| 3. Construction of Slab Culvert at Ch : 0.360 Kmp | No | 4.3 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | Phy Completed | Restricted
| 4. Construction of RCC Link Drain at Ch 0.000-0.112 km | Rm | 25 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | Phy Completed | Restricted
| 5. Construction of RCC Link Drain With Cover at Ch 0.000 km | Rm | 3.72 | 14.12.23 | 14.12.24 | - | - | - |  | - |  | Not yet started
| 6. Construction of RCC Link Drain With Cover at Ch 0.120 km | Rm | 5.58 | 14.12.23 | 14.12.24 | - | - | - |  | - |  | Not yet started
63 | Construction of New Road RAY to BS Farm Falkland including Protection Works and Cross Drain (0.800Km) | [7 empty] | - |  | 132.85
| 1. Lowering and Widening | Rm | 10.14 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | Phy Completed | Restricted
| 2. Construction of PCC Pavement on RAY to BS Farm Falkland | Rm | 10.48 | 14.12.23 | 14.12.24 | - | - | - |  | - |  | Not yet started
| 3. Construction of Retaining Wall | Rm | 8.84 | 14.12.23 | 14.12.24 | - | - | - |  | - |  | Not yet started
| 4. Construction of V-Shape | Rm | 4.2 | 14.12.23 | 14.12.24 | - | - | - |  | - |  | Not yet started
| 5. Construction of missing Link at BCM Multipurepose Centre at Falkland Veng | Rm | 6.34 | 14.12.23 | 14.12.24 | - | - | - |  | - |  | Not yet started
64 | Construction of Step near Pu Ringdika's House | Rm | 1.4 | 14.12.23 | 14.12.24 | - | - | - |  | - |  | Not yet started
65 | Repairing of Kailiana Concrete Pavement Road at Zemabawk North | Rm | 10.6 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | Phy Completed | Restricted
CONSTRUCTION OF TUIRIAL AIRFIELD TO MUTHI AND ZOKHAWSANG AGRICULTURE
66 | Construction of New Road from Tuirial Airfield Runway to Muthi lui Lalchhuana Leilet including Protetion Works & Cross Drain | [7 empty] | - |  | 103.19
| 1. Formation Cutting | Km | 40.94 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | Phy Completed | Restricted
| 2. Construction of RCC Slab Culvert | No | 66.58 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | Phy Completed | Restricted
CONSTRUCTION OF ROAD FROM THUAMPUI TO NH - 6 (ZEMABAWK)
67 | Construction of Link Drain near Pi Diki House at Sihphir | Rm | 10 | 14.12.23 | 14.12.24 | - | - | - | - | 100% | 179.18 | Phy Completed | Restricted
68 | Pavement of AR Complex at Zokhawsang | Km | 59 | 14.12.23 | 14.12.24 | - |  | - |  | 100% |  | Phy Completed | Restricted
69 | Resurfacing of Women Polytechnic Internal road at Durtlang | Km | 27 | 14.12.23 | 14.12.24 | - |  | - |  | 100% |  | Phy Completed | Restricted
70 | Improvement of Dinthar Veng to Muthi Lui Road (Balance Portion) at Zemabawk
| 1. Concrete Pavement | Rm | 31.5 | 14.12.23 | 14.12.24 | - |  | - |  | 100% |  | Phy Completed | Restricted
| 2. Construction of RCC Slab Culvert No.1 | No | 12.21 | 14.12.23 | 14.12.24 | - |  | - |  | 100% |  | Phy Completed | Restricted
| 3. Construction of Retaining Wall | Rm | 5 | 14.12.23 | 14.12.24 | - |  | - |  | 100% |  | Phy Completed | Restricted
| 4. Construction of U shape Side Drain | Rm | 8.29 | 14.12.23 | 14.12.24 | - | - | - | - | 100% | 174.71 | Phy Completed | Restricted
71 | Resurfacing of Sihpui to Ramhlun Vengthar Bus Turning Point at Ch : 1.052 - 1.357 km | m² | 11 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | Phy Completed | Restricted
72 | Patch repair of Vaivakawn to MZU via Zonuam. | m² | 18 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | Phy Completed | Restricted
73 | Construction of Retaining Wall below Thanhrangi's House at Luangmual Complex | Rm | 5 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | Phy Completed | Restricted
74 | Concrete Pavement from Field veng to Dinthar Veng at Zemabawk North |  |  |  |  | -
| 1. Concrete Pavement | Rm | 16.72 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | Phy Completed | Restricted
| 2. Rectangular Side Drain with cover | Rm | 2.26 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | Phy Completed | Restricted
| 3. V-Shape Drain | Rm | 3.36 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | Phy Completed | Restricted
75 | Construction of Step with Railing over Link drain near Zemabawk North Play Ground | Rm | 8 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | Phy Completed | Restricted
76 | Construction of RCC Bridge with Link Drain & R/Wall beneath Pu Ramfangzauva's Building at AL road Zemabawk | [7 empty] | - |  | 174.71
| 1. Construction of RCC Balcony | Rm | 3.07 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | Phy Completed | Restricted
| 2. Construction of RCC Link Drain | Rm | 11.67 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | Phy Completed | Restricted
| 3. Construction of Retaining Wall | Rm | 5.14 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | Phy Completed | Restricted
77 | Construction of Masony Stone Link Drain with R/Wall below Govt. Zemabawk PS-I | Rm | 1.92 | 14.12.23 | 14.12.24 | - | - | - | - | - | 174.71 | Not yet started
78 | Concrete Pavement from NH-54 to Holy Cross School Zemabawk | Rm | 15.6 | 14.12.23 | 14.12.24 | - | - | - |  | - |  | Not yet started
79 | Construction of Masony Stone Link Drain near F.Lalrinmawia's Residence at Dinthar Veng Zemabawk North | Rm | 5.61 | 14.12.23 | 14.12.24 | - | - | - |  | - |  | Not yet started
80 | Construction of RCC Link Drain (Balance Portion) at Dinthar Veng | Rm | 10.33 | 14.12.23 | 14.12.24 | - | - | - |  | - |  | Not yet started
81 | Construction of Road including Culvert & R/wall on Thuampui to Thuampui Vengthar Road (Balance Portion)
| 1. Formation Cutting | Km | 8.82 | 14.12.23 | 14.12.24 | - | - | - |  | - |  | Not yet started
| 2. Slab Culvert | No | 5.13 | 14.12.23 | 14.12.24 | - | - | - |  | - |  | Not yet started
| 3. Retaining Wall | Rm | 9.84 | 14.12.23 | 14.12.24 | - | - | - |  | - |  | Not yet started
82 | Concrete Pavement Laichhinga Street Kawn Veng-II at Zemabawk
| 1. Concrete Pavement | Rm | 12.3 | 14.12.23 | 14.12.24 | - | - | - |  | - |  | Not yet started
| 2. Rectangular Side Drain with cover | Rm | 1.15 | 14.12.23 | 14.12.24 | - | - | - |  | - |  | Not yet started
83 | Concrete Pavement from High School to Bethel at Zemabawk | Rm | 2.62 | 14.12.23 | 14.12.24 | - | - | - |  | - |  | Not yet started
84 | Construction of RCC U Shape Side Drain Kailiana Road at Zemabawk near Pi Sawihari | Rm | 7.81 | 14.12.23 | 14.12.24 | - | - | - |  | - |  | Not yet started
85 | PCC flooring Zemabawk North Thlanmual to Muthi lui | Rm | 10.67 | 14.12.23 | 14.12.24 | - | - | - |  | - |  | Not yet started
86 | Construction of hand Railing at Galilee Veng Main Road Zemabawk | No | 2.48 | 14.12.23 | 14.12.24 | - | - | - |  | - |  | Not yet started
87 | Laying of Chequerred Tiles at Melimual (Mual khat) existing steps at Zemabawk | No | 4.5 | 14.12.23 | 14.12.24 | - | - | - |  | - |  | Not yet started
UPGRADATION OF INTERNAL ROADS AT DURTLANG, BAWNGKAWN, CHALTLANG, ZUANGTUI, RAMHLUN & RAMTHAR
88 | Construction of Rectangular Side Drain with cover at Tatkawng Veng | Rm | 1.68 | 14.12.23 | 14.12.24 | - | - | - | - | 100% | 132.89 | Phy Completed | Restricted
89 | Construction of Concrete Pavement of Durtlang tlak lam Thlanmual Road | Rm | 20 | 14.12.23 | 14.12.24 | - | - | - |  | - |  | Not yet started
90 | Construction of Concrete Pavement of Gosen Veng Kawngpui at Zuangtui | Rm | 7 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | Phy Completed | Restricted
91 | Construction of PCC Flooring at Rivenga Road at Muanna Veng | Rm | 10 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | Phy Completed | Restricted
92 | Construction of PCC Flooring Internal Road - Zamliana Road to K.Thankunga Road at Selesih | Rm | 5 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | Phy Completed | Restricted
93 | Vantlang Step near K.Thankunga House at Selesih | Rm | 5 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | Phy Completed | Restricted
94 | Construction of PCC Flooring Laitan Ramthar Biak In lane at Leitan Ramthar | Rm | 10 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | Phy Completed | Restricted
95 | Construction of Concrete Pavement on Bawngkawn Thlanmual to Thuampui Road | Rm | 22.87 | 14.12.23 | 14.12.24 | 17% | - | 83% |  | 100% |  | Phy Completed | Restricted
96 | Steel Grate Cover Side Drain on PC.Malsawma House to Rev.C.Vanlalhruaia House at Ramhlun South | Rm | 2.2727 | 14.12.23 | 14.12.24 | - | - |  |  |  |  | On-Going
97 | Construction of RCC Foot Step near PC.Lalzuiliana House Ramthar | Rm | 14.6908 | 14.12.23 | 14.12.24 | - | - | 0% |  | 0% |  | Not yet started
98 | Construction of RCC Link Drain near PC.Lalzuiliana House at Ramthar | Rm | 8.3752 | 14.12.23 | 14.12.24 | - | - | 0% |  | 0% |  | Not yet started
99 | Construction of Breast Wall Below PC.Laltanpuia House at Ramthar North | Rm | 7.3314 | 14.12.23 | 14.12.24 | - | - | 0% |  | 0% |  | Not yet started
100 | Steel Grate Cover Side Drain on PC Malsawma House to Rev. C.Vanlalhruaia House at Ramhlun South | Rm | 8.04 | 14.12.23 | 14.12.24 | - | - | - |  | - |  | Not yet started
101 | Construction of RCC Foot Step near PC.Lalzuiliana House Ramthar | Rm | 16.58 | 14.12.23 | 14.12.24 | - | - | - |  | - |  | Not yet started
102 | Construction of RCC Link Drain near PC.Lalzuiliana House at Ramthar | Rm | 8.42 | 14.12.23 | 14.12.24 | - | - | - |  | - |  | Not yet started
103 | Construction of Breast Wall Below PC.Laltanpuia House at Ramthar North | Rm | 7.37 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | Phy Completed | Restricted
104 | Construction of Breast Wall near Pu.Lalrammuana Ralte House at Ramthar North | Rm | 5.76 | 14.12.23 | 14.12.24 | - | - | - | - | - | - | Not yet started
105 | Construction of RCC Foot Step near Pi.Manmawii House at Ramhlun South | Rm | 6.68 | 14.12.23 | 14.12.24 | - | - | - |  | - |  | Not yet started
IMPROVEMENT OF ROAD FROM DURTLANG LEITAN TO DURTLANG RAMTHAR AT DURTLANG
106 | Construction of Road at Selesih. Aizawl (Sh: Construction of Concrete Pavement and Culvert etc) | [7 empty] | - |  | 221.01
| 1. Concrete Pavement of Pu Dinga Road | Rm | 5 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | Phy Completed | Restricted
107 | Improvement of road at Durtlang North, Aizawl. (Sh: Construction of Concrete Pavement etc)
| 1. Construction of Concrete Pavement & Cross Drain on Vungkhama road inlcuding Chhingtei Road at Durtlang North | Rm | 15 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | Phy Completed | Restricted
| 2. Construction of Concrete Pavement of Durtlang North Thlanmual | Rm | 10 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | Phy Completed | Restricted
108 | Improvement of road at Durtlang, Aizawl. (Sh : Construction of Concrete Pavement, Cross Drain with cover, V Shape Side Drain, slab culvert and link Drain etc)
| 1. Construction of PCC V shape Side Drain at Centenary Road & Women Polytechnic approach road at Durtlang | Rm | 5 | 14.12.23 | 14.12.24 | - | - | - |  | - |  | Not yet started
| 2. Concrete Pavement of Lalnu road at Suaka Veng, Durtlang (Balance Portion) | Rm | 5.4 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | Phy Completed | Restricted
| 3. Construction of Cross Drain with cover on Durtlang Field | Rm | 0.99516 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | Phy Completed | Restricted
| 4. Construction of Step including Link Drain at Centenary Road, Durtlang | Rm | 20 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | Phy Completed | Restricted
109 | Construction and Improvement of road at Durtlang Leitan, Aizawl.(Sh : Construction of Concrete Pavement, RCC frame Retaining Wall, Cross Drain with cover, U Shape Side Drain and link Drain etc) | [7 empty] | - |  | 216.23
| 1. Construction of PCC V Shape Side and Retaining Wall at Gospel Thunder Team compound, Durtlang Leitan | Rm | 20 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | Phy Completed | Restricted
| 2. Construction of RCC Frame RW at Zotui Road, Durtlang Leitan | Rm | 3.5 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | Phy Completed | Restricted
| 3. Patch repair of Durtlang Leitan SIRD Road | Km | 5.05 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | Phy Completed | Restricted
110 | Improvement of Road at Durtlang Ramthar, Aizawl (Sh : Construction of Concrete Pavement, Cross Drain and Re-Surfacing)
| 1. Resurfacing of 3rd Lane at Durtlang Ramthar | Rm | 29.5 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | Phy Completed | Restricted
| 2. Concrete pavement of approach road to Durtlang Ramthar Prebyterian Church including cross drainage | Km | 30.5 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | Phy Completed | Restricted
111 | Improvement of Road at Chaltlang Lily veng, AizawL (Sh : Widening . of road, Construction of Concrete Pavement, RCC R/Wall and Re-Surfacing etc) | [7 empty] | - |  | 216.23
| 1. Resurfacing of Chaltlang Lily Veng internal road (Balance) | Km | 3 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | Phy Completed | Restricted
| 2. Reconstruction of step from State Guest House to Lily Veng internal road | Rm | 6 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | Phy Completed | Restricted
| 3. Construction of RCC Balcony & Masonry Step near R.lalmanga House at Chaltlang Lily Veng | Rm | 14 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | Phy Completed | Restricted
112 | Improvement of Road at Chaltlang, Aizawl. (Sh: Junction improvement. Construction of Concrete Pavement, U Shape drain, Retainning Wall & Step)
| 1. Concrete Pavement of Road near F.Malsawma Residence at Chaltlang | Rm | 2.5 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | Phy Completed | Restricted
| 2. Construction of Retaining Wall & Concrete pavement on AMC Road at Dingdi Veng, Chaltlang | Rm | 9.7 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | Phy Completed | Restricted
113 | Improvement of Road at Bawngkawn, Aizawl. (Sh : Construction of Balcony, Link Drain, Retaing Wall & Concrete Pavement)
| 1. Construction of retaining Wall near Pu. Salemthara Residence at Brigade, Bawngkawn | Rm | 2.6 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | Phy Completed | Restricted
| 2. Concrete Pavement of Liansailova road, Bawngkawn | Rm | 10 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | Phy Completed | Restricted
| 3. Concrete Pavement of Shalom Road at Bawngkawn Hmar Veng (Balance Portion) | Rm | 10 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | Phy Completed | Restricted
| 4. Concrete Pavement on Upper Bawngkawn Hmar Veng | Rm | 4.5 | 14.12.23 | 14.12.24 | - | - | - | - | 100% | - | Phy Completed | Restricted
114 | Construction of additional protection work at Bethel Veng | Rm | 13 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | Phy Completed | Restricted
IMPROVEMENT OF ROAD FROM ZEMABAWK TO LUNGBIAL ROAD IN THE LOCALITY OF ZEMABAWK AT AIZAWL
115 | CONSTRUCTION OF ROAD AT SIHPHIR | [7 empty] | - |  | 213.41
| i.Concrete pavement of approach road to Sihphir Rescue Center road at Sihphir Kawnveng | Rm | 8.8 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | Phy Completed | Restricted
| ii.Formation Cutting , Concrete Pavement & Step of Sunhlu tlang (Prayer Mountain) at Sihphir Tlang Veng | Rm | 7.9 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | Phy Completed | Restricted
| iii.Construction of Step including retaining wall near Pu Zakhuma House at Sihphir field veng | Rm | 3.66 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | Phy Completed | Restricted
| iv.Construction of link Drain with cover near Pi Liani House at Sihphir Dinthar | Rm | 1.74 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | Phy Completed | Restricted
| v.Construction of Link drain near Pu H.Lalfakzuala, Sihphir Dinthar | Rm | 2.61 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | Phy Completed | Restricted
116 | CONSTRUCTION OF CONCRETE PAVEMENT AT ZUANGTUI, AIZAWL
| i.RCC Balcony Gosen Veng to 132 KV substation at Zuangtui | Rm | 26.13 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | Phy Completed | Restricted
117 | CONCRETE PAVEMENT RIVENGA ROAD AT MUANNA VENG, AIZAWL
| i.Concrete Pavement of Rivenga Road at Muanna Veng | Rm | 7.3 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | Phy Completed | Restricted
118 | CONSTRUCTION OF ROAD AT MUTHI, AIZAWL | [7 empty] | - |  | -
| i.Concrete Pavement at ch:0.000 - 0.715kmp Muthi peng to kawn | Rm | 8.6 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | Phy Completed | Restricted
119 | CONSTRUCTION OF ROAD AT NAUSEL
| i.Concrete Pavement at Nausel Thlanmual kawng | Rm | 8.2 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | Phy Completed | Restricted
120 | IMPROVEMENT OF ROAD AT SIHPHIR VENGHLUN
| i.Construction of Retaining Wall at Thuampui Selesih road at Ch:4.300Kmp, Durtlang | Rm | 6.14 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | Phy Completed | Restricted
121 | Construction of New Road from Zemabawk North Thlanmual to Thuampui Thlanmual including Protetion Works & Cross Drain
| i. Formation Cutting | Km | 51.36 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | Phy Completed | Restricted
| ii. Construction of RCC Slab Culvert | No | 33.04 | 14.12.23 | 14.12.24 | - | - | - |  | 100% |  | Phy Completed | Restricted
122 | CONSTRUCTION OF ROAD AT FALKLAND, AIZAWL
| i.Construction of PCC Pavement on Local Council Road to RAY at Falkland | Rm | 27.79 | 14.12.23 | 14.12.24 | - | - | - |  | - |  | Not yet started
| ii.Construction of PCC Pavement on Rabboni Road at Falkland | Rm | 5.1404 | 14.12.23 | 14.12.24 | - | - | - |  | - |  | Not yet started
| iii.Construction of PCC Pavement on Local Council Road Falkland | Rm | 11.332 | 14.12.23 | 14.12.24 | - | - | - |  | - |  | Not yet started
| iv.PCC Pavement on Approach Road to Vai Lui via Rev Lalsangliana's House at Falkland Veng | Rm | 5.7395 | 14.12.23 | 14.12.24 | - | - | - |  | - |  | Not yet started
SUB - DIVISION - III
CONSTRUCTION OF PCC PAVEMENT AT SIHHMUI TO NH-54. (LENGTH = 7.00Kms, PCC PAVEMENT = 7.00Kms) | [13 empty] | 417.6 | 2023-12-14 | 2024-12-14
123 | Widening of road from Law college to PCI road at Luangmual, Aizawl (Sh: Earth Work for Widening of existing road) | Rm. | 11.95 | 2023-12-14 | 2024-12-14 | - | - | - | - | 100% | 191.15 | Phy Completed | Restricted
124 | Improvement & Upgradation of road at Chawlhhmun, Aizawl |  | 26 | 2023-12-14 | 2024-12-14
| Sh: 1. Construction of PCC Pavement of Pu Muantea's road at Chawlhhmun | Rm. |  |  |  | - | - | - |  | 100% |  | Phy Completed | Restricted
| 2. Construction of PCC Pavement near Pu Fabiana's house at Chawlhhmun | Rm. |  |  |  | - |  | - |  | 100% |  | Phy Completed | Restricted
125 | Improvement & Upgradation of road at Zotlang, Aizawl |  | 20.29 | 2023-12-14 | 2024-12-14
| Sh: 1. Construction of RCC Pavement at Zotlang to Zohnuai | Rm. |  |  |  | - | - | - |  | 100% |  | Phy Completed | Restricted
| 2. Construction of Retaining Wall for Pi Romawii Approach Road at Zotlang | Rm. |  |  |  | - | - | - |  | 100% |  | Phy Completed | Restricted
| 3. Construction of RCC Pavement at Zotlang to Zohnuai Biak In | Rm. |  |  |  | - | - | - |  | 100% |  | Phy Completed | Restricted
126 | Construction of approach road (RCC Pavement) to Community Hall (NH 44A) at Sihhmui | Rm. | 15.91 | 2023-12-14 | 2024-12-14 | - | - | - |  | 100% |  | Phy. Completed | Restricted
127 | Improvement & Upgradation of road from PCI to Anganwadi at Lungverh |  | 77.98 | 2023-12-14 | 2024-12-14
| Sh: 1. Construction of RCC Pavement from PCI to Anganwadi at Lungverh | Rm. |  |  |  | - | - | - |  | 100% |  | Phy. Completed | Restricted
| 2. Construction of RCC Slab Culvert at Thlanmual kawr | Rm. |  |  |  | - | - | - |  | 100% |  | Phy. Completed | Restricted
| 3. Construction of RCC Slab Culvert at Pu Rinnunga kawmthlang | Rm. |  |  |  | - | - | - |  | 100% |  | Phy. Completed | Restricted
| 4. Retaining wall at F Suakliana Kawmchhak | Rm. |  |  |  | - | - | - | - | 100% | - | Phy. Completed | Restricted
128 | Rangvamual internal road | Rm | 23.27 |  |  | - | - | - |  | 100% |  | Phy. Completed | Restricted
129 | Phunchawng internal road | Rm | 19.2 |  |  | - | - | - |  | 100% |  | Phy. Completed | Restricted | 194.6
IMPROVEMENT OF INTERNAL ROADS AT HUNTHAR, CHANMARI WEST, RANGVAMUAL, PHUNCHAWNG & CHHINGA VENG. (IMPROVEMENT OF ROADS PCC PAVEMENT = 20.00 KMS, PAVEMENT = 5.00 KMS, LINK DRAIN = 100.00M) | [13 empty] | 288 | 2023-12-14 | 2024-12-14
130 | Patch Repair and Seal Coating of Approach Road to Tanhril, Aizawl | Rm | 23.08 | 2023-12-14 | 2024-12-14 | - | - | - | - | 100% | 59.03 | Phy. Completed | Restricted
131 | Construction of PCC Pavement of Approach Road to Tawngtai Bethel Camping Centre, Sakawrtuichhun, Aizawl | Rm. | 9.49 | 2023-12-14 | 2024-12-14 | - | - | - |  | 100% |  | Phy. Completed | Restricted
132 | Rigid Pavement of Gan Sabra Road | Rm. | 19.33 | 2023-12-14 | 2024-12-14 | - | - | - |  | 100% |  | Phy. Completed | Restricted
133 | Construction of PCC Pavement of Road from Saikaphleia' House to Muanthanga's House at Lungverh. Length = 120.00Rm. | Rm. | 9.49 | 2023-12-14 | 2024-12-14 | - | - | - |  | 100% |  | Phy. Completed | Restricted | 61.39
CONSTRUCTION OF LUNGHLU ROAD AT CHANMARI WEST AIZAWL (Length = 4.00Kms, Ew = 4.00Kms, Pavement = 4.00Kms, Side Drain = 4500m, R/W 30m, Culvert = 10.Nos)
134 | Construction of RCC Frame structure Retaining Wall I at Lunghlu Road, Hunthar | Rm | 14.49 | 2023-12-14 | 2024-12-14 | - | - | - | - | 100% | 98.69 | Phy. Completed | Restricted
135 | Patch repair and Seal coat of MUP Road at Chanmari West, Aizawl | Rm | 11.5532 | 2023-12-14 | 2024-12-14 | - | - | - |  | 100% |  | Phy. Completed | Restricted
136 | Patch repair and Seal Coat from BT Bakery to Protective Home Via Zarkawt Thlanmual | Rm | 29.9487 | 2023-12-14 | 2024-12-14 | - | - | - |  | 100% |  | Phy. Completed | Restricted
137 | Construction of RCC Road at Methodist mual Turning Point to Edenthar Anganwadi Centre No. 1 at Edenthar | Rm | 8.76 | 2023-12-14 | 2024-12-14 | - | - | - |  | 100% |  | Phy. Completed | Restricted | 64.7519
138 | Rigid Pavement of Gan Sabra Road | Rm. | 16.86 | 2023-12-14 | 2024-12-14 | - | - | - |  | 100% |  | Phy. Completed | Restricted
139 | Construction of PCC Pavement of Road from Saikaphleia' House to Muanthanga's House at Lungverh. Length = 120.00Rm. | Rm. | 10.06 | 2023-12-14 | 2024-12-14 | - | - | - |  | 100% |  | Phy. Completed | Restricted
CONSTRUCTION OF LUNGHLU ROAD AT CHANMARI WEST AIZAWL (Length = 4.00Kms, Ew = 4.00Kms, Pavement = 4.00Kms, Side Drain = 4500m, R/W 30m, Culvert = 10.Nos)
140 | Construction of RCC Frame structure Retaining Wall I at Lunghlu Road, Hunthar | Rm | 14.5 | - | - | - | - | - | - | 100% | 98.69 | Phy Completed
141 | Patch repair and Seal coat of MUP Road at Chanmari West, Aizawl | Rm | 11.5532 | - | - | - | - | - |  | 100% |  | Phy. Completed | Restricted
142 | Patch repair and Seal Coat from BT Bakery to Protective Home Via Zarkawt Thlanmual | Rm | 29.9487 | - | - | - | - | - |  | 100% |  | Phy Completed
143 | Construction of RCC Road at Methodist mual Turning Point to Edenthar Anganwadi Centre No. 1 at Edenthar | Rm | 8.76 | - | - | - | - | - |  | 100% |  | Phy. Completed | Restricted
Sr. Executive Engineer, PWD.,
Aizawl Road North Division,
Aizawl : Mizoram

## ARSD
MONTHLY PROGRESS REPORT UNDER AIZAWL ROAD SOUTH DIVISION, PWD
FOR THE MONTH OF JUNE 2025
Sl. No. | Name of Schemes | Unit | Approved Cost (Rs in Lakh) | Date of Commencement | Target Date of Comple-tion | Cumulative Progress at the end of last month |  | Achievement of works during the month |  | Overall Cumulative achievement |  | Remarks | Mode of Tender
| Name of Works / Project |  |  |  |  | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | SEDP (2019-2020)
1 | Const.of Approach Road to Aizawl College at Mualpui | Rm | 415 | 2021-07-26 | 2022-04-26 | 73% | 300 | 0% | 0 | 73% | 300 | On Going ES was accorded vide No.B.12031/17/2019-PWD(T) Dt.26.3.2020 (Rs.100 lakhs); No.G.20016/3/2021-FBT Dt.7.10.2021 (Rs.100 lakhs) and No. B.12031/29/2021-PWD(T) dt. 01.03.2023 respectively, which totalled Rs.300 out of Rs. 415.00. The remaining balance/ ES was asked for Approval vide No.B.16012/6/22/T(ARS)/I/5 Dt.29th Sept,2022. It was regretted due to Financial Constraint as the year has been declared as year of consolidation vide No. B. 12031/17/2019-PWD(T) dt. 23rd July, 2024. Since balance fund is not expected in the near future, fore-closure of the contract is in the process. | Item Rate Contract
2 | NEDP (2018-2019)
1 | Construction of Bridge on Chhinga Vengthar to Tuithiang road | Rm | 586.36 | 2021-04-19 | 2022-10-31 | 100% | 200 | - | - | 100% | 200 | Physical Works Completed according to Working Estimate E/S Amount of Rs.200.00 Lakh. The remaining ES was asked for Allocation vide No.B.16011/69-C/15/T(ARS)/28 dated: 23rd Jan, 2023 in which balance ES from Higher Authority is awaited. However balance fund is not expected in the near future, fore-closure of the contract is in the process. | Restricted tender
3 | Central Road Fund
1 | Construction of BUG Bridge over R.Tlawng on Aizawl - Reiek - W.Lungdar Road at 14.800 Kmp | Rm | 757.56 | 10.10. 2018 | 31.10.2024 | 100% | 750.57 | 0% | 0 | 100% | 750.57 | Work Completed | EPC mode
4 | SASCI (2022-2023)
i) | Widening of Approach Road to City Bus Parking at S.Hlimen, Aizawl (Melthum - Hlimen Road) under SASCI 2022-2023. | Rm | 576 | 2023-04-07 | 2024-04-07 | 98% | 419.43 | 2% | 48.96 | 100% | 468.39 | EOT Approval is awaited. | Restricted tender
ii) | Widening of S.Hlimen City Bus Parking - Samtlang Road (Hlimen - Samtlang Road) under SASCI 2022-2023. | Rm | 831 | 2023-04-06 | 2024-04-06 | 100% | 716.07 | 0% | 94.69 | 100% | 810.76 | Completed | Restricted tender
5 | SASCI (2023-2024)
i) | Overlaying of road with PCC Pavement From Mission Veng to Khatla with Retaining wall and Minor bridge at Aizawl under SASCI Phase - I, Part - I | Rm | 241 | 2023-12-14 | 2024-12-14 | 100% | 93.13 | 0% | 0 | 100% | 93.13 | Work Completed (Sanction reviewed and the fund was cut down to Rs. 94.54 lakh) | Restricted tender
ii) | Improvement of Saikhamakawn to Kulikawn Via Tlangnuam under SASCI Phase-I, Part-I for 2023 - 2024 | Rm | 248 | 2023-12-14 | 2024-12-14 | 100% | 96.15 | 0% | 0 | 100% | 96.15 | Work Completed (Sanction reviewed and the fund was cut down to Rs. 97.01 lakh) | Restricted tender
iii) | Construction of PCC pavement, PCC Side drain and R/Wall at Upper Republic to Bethlehem Via College Veng under SASCI Phase-I, Part-I | Rm | 387 | 2023-12-14 | 2024-12-14 | 100% | 171.69 | 0% | 0 | 100% | 171.69 | Work Completed (Sanction reviewed and the fund was cut down to Rs. 173.16 lakh) | Restricted tender
iv) | Improvement of Venghnuai to Salem Road under SASCI Phase-I, Part-I | Rm | 280 | 2023-12-14 | 2024-12-14 | 100% | 113.03 | 0% | 0 | 100% | 113.03 | Work Completed (Sanction reviewed and the fund was cut down to Rs. 114.01 lakh) | Restricted tender
v) | Construction of Road from Nursery -Tamdo -Lawipu (2.50Kms) under SASCI During 2023-2024 Phase-II | Rm | 467 | 2023-12-14 | 2024-12-14 | 97.72% | 138.68 | 1% | 0 | 98.72% | 138.68 | Work in Progress (Sanction reviewed and the fund was cut down to Rs. 202.26 lakh) | Restricted tender |  | finan chiah a ngai
vi) | Construction of Road from Tlawng Road to Model Veng under SASCI During 2023-2024 | Rm | 350 | 2023-12-14 | 2024-12-14 | 100% | 2.97 | 0% | 116.64 | 100% | 119.61 | Work Completed (Sanction reviewed and the fund was cut down to Rs. 120.74 lakh) | Restricted tender
vii) | Upgradation of internal Roads at Tuikual, Venghlui and Republic Veng | Rm | 200 | 2023-12-14 | 2024-12-14 | 91.67% | 102.11 | 8.33% | 0 | 100% | 102.11 | Work Completed (Sanction reviewed and the fund was cut down to Rs. 104.58 lakh) | Restricted tender | physicalPui Hmiungtea nghah a ngai
viii) | Improvement of Roads and Infrastructures at Aizawl City under SASCI 2023-2024. Under Aizawl Road South Division | Rm | 180.2 | 2023-12-14 | 2024-12-14 | 100% | 151.05 | 0% | 0 | 100% | 151.05 | Completed (Sanction reviewed and the fund was cut down to Rs. 152.06 lakh) | Deparmental mode B.E. released to PD-I & Aizawl Electrical Div. & Aizawl Building Div., PWD
6 | Strengthening and Improvement of State Highways & Other Roads under Mizoram under Central Circle
1 | Construction of Rigid pavement on Sihpui tuikhur to Aizawl By-Pass road at Kulikawn | Rm | 40.39 | 2024-12-13 | 2025-05-09 | 100% | 7.12 | 0% | 16.56 | 100% | 23.68 | Work Completed | Open tender
2 | Construction of Side Drain Cover on Approach Road to SAI at Mission Vengthlang | Rm | 17.19 | 2024-12-13 | 2025-06-13 | 100% | 0 | 0% | 15.55 | 100% | 15.55 | Work Completed | Open tender
3 | Resurfacing of Aizawl - Thenzawl - Lunglei (ATL) Road between 0.000 - 1.000 Kmp. (Rigid pavement 1.00- 1.344=0.334km) including improvement of Bus Terminal (RW=13.8m, H=1.0 | Rm | 52.34 | 2024-12-13 | 2025-06-13 | 100% | 0 | 0% | 52.34 | 100% | 52.34 | Work Completed | Open tender
4 | Construction of Cement concrete Pavement on Bethlehem Vengthlang to Thingdawl Ruam | Rm | 18.65 | 21.2.2025 | 2025-06-13 | 100% | 9.72 | 0% | 8.93 | 100% | 18.65 | Work Completed | Open tender
5 | Construction of Rigid Pavement on Approach road to Tlangnuam new Cemetery | Rm | 17.85 | 2024-12-13 | 2025-06-13 | 100% | 0 | 0% | 16.15 | 100% | 16.15 | Work Completed | Open tender
14 | Improvement of Aizawl-Reiek-W.Lungdar road | Rm | 124.05 | 2024-11-04 | 2025-03-22 | 100% | 91.38 | 0% | 0 | 100% | 91.38 | Work Completed | Departmental
| Improvement of Sinking Area on Bypass Road at Ch.0+800kmp (Sh. Widening) | Rm | 6.82 | 19:03 | 21:03 | 100% | 0 | 0% | 0 | 100% | 0 | Work Completed | Departmental
7 | PMGSY
1 | Upgradation & Maintenance of Hlimen to Samtlang to Lungleng Road | Rm | 1132.5 | 2024-10-23 | 2026-04-23 | 11% | 0 | 0.3% | 0 | 11.3% | 0 | On going | Open tender
8 | Cyclone Remal Fund
1 | Pothole repairs on Bethlehem Kawn to Aizawl Bypass Road |  | 11.2 | 23:04 | 16:05 | 100% | 0 | 0% | 0 | 100% | 0 | Work Completed | Departmental
2 | Pothole repairs on Falkland Internal Road at ITI (Falkland Street) |  | 0.6 | 1:05 | 7:05 | 100% | 0 | 0% | 0 | 100% | 0 | Work Completed | Departmental
3 | Pothole repairs on Tuikhuahtlang Taxi Stand to Pu R. Lalawia's House |  | 0.6 | 8:05 | 14:05 | 100% | 0 | 0% | 0 | 100% | 0 | Work Completed | Departmental
4 | Pothole repairs on Approach Road to T. Romana College |  | 3 | 5:05 | 21:05 | 100% | 0 | 0% | 0 | 100% | 0 | Work Completed | Departmental
5 | Pothole repairs on Sihtuikhur to Tuithiang |  | 4.3 | 15:05 | 30:05 | 100% | 0 | 0% | 0 | 100% | 0 | Work Completed | Departmental
9 | Maintenance Action Plan 2025-2026 (3054)
1 | Reconstruction of Pavement near Pu Lalmuanpuia Punte, MLA Quarter | Sqm | 1.21 | 17:04 | 23:04 | 100% | 0 | 0% | 0 | 100% | 0 | Work Completed | Departmental
2 | Pothole repair of Aizawl City Roads within Aizawl Road South Division
a) | Pot hole Repair of MHNL Section - I | Sqm | 2.37 | 12:05 | 20:05 | 100% | 0 | 0% | 0 | 100% | 0 | Work Completed | Departmental
b) | Pot hole Repair of MHNL Section - II | Sqm | 1.48 | 14:05 | 17:05 | 100% | 0 | 0% | 0 | 100% | 0 | Work Completed | Departmental
c) | Pot hole Repair of Nursery to Maubawkkawn | Sqm | 5.1 | 16:05 | 21:05 | 100% | 0 | 0% | 0 | 100% | 0 | Work Completed | Departmental
d) | Pot hole Repair of Secretariat Internal Roads | Sqm | 4.41 | 19:05 | 23:05 | 100% | 0 | 0% | 0 | 100% | 0 | Work Completed | Departmental
e) | Pot hole Repair of Tennis Court to Dinthar (Kaisara Road) | Sqm | 4.12 | 21:05 | 26:05 | 100% | 0 | 0% | 0 | 100% | 0 | Work Completed | Departmental
f) | Pot hole Repair of Tuikual South Lower Lane Road | Sqm | 3.23 | 22:05 | 28:05 | 100% | 0 | 0% | 0 | 100% | 0 | Work Completed | Departmental
g) | Pot hole Repair of Zuangtuikhur to SA Hall Road | Sqm | 0.78 | 22:05 | 24:05 | 100% | 0 | 0% | 0 | 100% | 0 | Work Completed | Departmental
h) | Pot hole Repair of Assam Rifle Internal Roads at Khatla | Sqm | 2.3 | 14:03 | 14:03 | 100% | 0 | 0% | 0 | 100% | 0 | Work Completed | Departmental
P

## AZL BUI DIV
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2025
Name of Division: Aizawl Building Division
Source of Funding : CSS
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of completion | Cummulative Progress at the end of last month |  | Acievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Improvement of Mizoram Secretariat Building at MINECO | Percen tage | 168.49 | 13.11.2023 | 31.03.2024 | 100% | 138.13 |  | 30.36 | 100% | 168.49 |  | Departmental
Sr.Executive Engineer, P.W.D.,
Aizawl Building Division,
Aizawl:Mizoram.

## AZL ELEC DIV
MONTHLY PROGRESS REPORT UNDER AVIATION WING FOR THE MONTH OF JUNE/2025
Name Of Division : PWD, Electrical Division, Aizawl
Head of Account : Major & Minor Works and Deposit works 8443-108, D-III
Sl. No | Name of Works / Scheme | Unit | Approved Cost Amount (in Lakhs.) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month. |  | Achievement of works during the Month |  | Overall cummulative achievement |  | Remarks
[6 empty] | Phy (%) | Fin(Rs) | Phy (%) | Fin(Rs) | Phy (%) | Fin(Rs)
1 | 2 |  | 3 | 6 |  | 10 | 11 | 12 | 13 | 14 | 15 | 18
1 | SITC of 13 Passenger Lift - 1 no., 2-opening, 900mm centre opening Stainless Steel Cable with Automatic Rescue Device (ARD) for Hydraulic Lift with Minor Civil Works at Lengpui Airport Mizoram | % | 39.24 | 08.09.2021 | 01.04.2024 | 100% | 39.24 | 0% |  | 100% | 39.24 | Completed
2 | I/E to Arrival & Departure Passenger Lobby at Lengpui Airport | % | 25.27 | 19.12.2020 | 1.4.2024 | 95% | 25.27 | 0% |  | 95% | 25.27 | On going works
3 | Street Light Parking light at Lengpui Airport | % | 37.32 | 06.07.2022 | 1.4.2024 | 98% | 37.32 | 0% |  | 98% | 37.32 | departure conopy constn. awaited
4 | Addl. Estimate for SITC of MRV/VRF Centralizes Air Conditioner Airport First Floor Departure Hall, Mizoram. | % | 247.74 | 12.03.2022 | 04.03.2024 | 97.5% | 244.44 | 0.5% | - | 98% | 244.44 | Completion stage, Testing and Comissioning left.
5 | SITC of EPABX System for Lengpui Airport Terminal Building. | % | 24.64 | 06.07.2022 | 29.06.2024 | 96% | 19.46 | 0% | - | 96% | 19.46 | Control room ceiling works not yet ready Telephones stocked at site, ready be fixed in the rooms when occupied
6 | SITC of PA System at Lengpui Airport Terminal Building. | % | 36.36 | 06.07.2022 | 29.06.2024 | 96% | 28.82 | 3% | - | 99% | 28.82 | On going works
Sl. No | Name of Works / Scheme | Unit | Approved Cost Amount (in Lakhs.) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month. |  | Achievement of works during the Month |  | Overall cummulative achievement |  | Remarks
[6 empty] | Phy (%) | Fin(Rs) | Phy (%) | Fin(Rs) | Phy (%) | Fin(Rs)
1 | 2 |  | 3 | 6 |  | 10 | 11 | 12 | 13 | 14 | 15 | 18
7 | Supply & Installation of Integrated Fire Hydrant System (Wise Riser)&SITC of Alarm System for Lengpui Airport Terminal Building. | % | 119.96 | 06.07.2022 | 29.06.2024 | 97% | 94.72 | 0% | - | 97% | 94.72 | On going works
8 | SITC of AVTRON IP Surveillance System for Lengpui Airport Terminal Building. | % | 94.76 | 06.07.2022 | 29.06.2024 | 96% | 67.61 | 2% | - | 98% | 67.61 | Civil works (Ceiling) not yet ready at Ground floor
9 | SITC of LAN SETUP at Lengpui Airport Terminal Building. | % | 20.05 | 06.07.2022 | 29.06.2024 | 99% | 15.76 | 0% | - | 99% | 15.76 | On going works
10 | Estimate for I/E of Energy Meter for Terminal Building at Lengpui Airport | % | 7.99 | 06.07.2022 |  | 100% | 7.99 | 0% | - | 100% | 7.99 | Completed
11 | Impvt/Upgradation of Operational/Non-Operational facilities of Lengpui Airport(SH:Northern Side Baggage conveyor belt) | % | 192.5 | 22.07.2024 | 18.12.2024 | 100% | 370.86 | 0% | - | 100% | 373.6 | Completed
12 | Impvt/Upgradation of Operational/Non-Operational facilities of Lengpui Airport(SH:Northern Side Baggage conveyor belt) | % | 192.5 | 22.07.2024 | 18.12.2024 | 100% |  | 0% |  | 100% |  | Completed
13 | Estimate for XLPE Cable for Lengpui Airport. | % | 27.23 |  |  | 100% | 27.23 | - | - | 100% | 27.23 | Completed
Sl. No | Name of Works / Scheme | Unit | Approved Cost Amount (in Lakhs.) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month. |  | Achievement of works during the Month |  | Overall cummulative achievement |  | Remarks
[6 empty] | Phy (%) | Fin(Rs) | Phy (%) | Fin(Rs) | Phy (%) | Fin(Rs)
1 | 2 |  | 3 | 6 |  | 10 | 11 | 12 | 13 | 14 | 15 | 18
14 | Additional Estimate for SITC of Air Conditioner Departure Passenger Lobby at Lengpui Airport. | % | 24.67 |  |  | 100% | 24.67 | - | - | 100% | 24.67 | Completed
15 | Laying of XLPE Cable from Power House to Glide Path control at Lengpui Airport, Mizoram | % | 39.53 | 09.05.2023 | 04.08.2023 | 100% | 39.52 | - | - | 100% | 39.52 | Completed
16 | Impvt/Revamping of Lengpui Airport runway Lighting-DGCA Observation Reg. | % | 347.05 |  |  | 100% | 360.78 |  | - | 100% | 370.38 | Completed
17 | Impvt/Revamping of Lengpui Airport runway Lighting-Isolation Bay-DGCA Observation Reg. | % | 10.91 |  |  | 100% |  |  |  | 100% |  | Completed
18 | Impvt/Revamping of Lengpui Airport runway Lighting-Isolation Bay-DGCA Apron Extension Observation Reg. | % | 14.6 |  |  | 100% |  |  |  | 100% |  | Completed
Sr. Executive Engineer, PWD.,
Electrical Division, Aizawl.

## Champhai Div
MONTHLY PROSGESS REPORT OF WORKS FOR THE MONTH OF JUNE, 2025
Name of Division : PWD., Champhai
SL.No. | Name of Scheme | Unit | Approved Cost (in lakhs) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of Works during the month |  | Overall Cumulative Achievement |  | Remarks | Mode of Tender
| Name of Work/Project |  |  |  |  | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
I | ANNUAL PLAN (5054)
1 | Upgradation of Approach road to Tuipui Village from NH-6 (new Eden) Length - 1.625 Km | Km | 128.28 | 6.12.2024 | 6.12.2025 | 80% | _ | 2% | _ | 82% | _ | On-going | Open Tender
2 | Construction of Bailey Bridge (60 ft span) over R. Tuimuk on approach road to Tuipui Village from NH-6 (New Eden) | Ft. | 53.06 | 22.8.2024 |  | 75% | _ | 3% | _ | 78% | 53.06 | On-going | Deptt.
II | SASCI
1 | Khankawn P/S to Kanan Junction | Km | 600 | _ | _ | _ | _ | _ | _ | _ | _ | Mobilisation Started | Restricted Tender
Sr. Executive Engineer, PWD.,
Champhai Division:Champhai

## Hmuifang Div
MONTHLY PROGRESS REPORT FOR THE MONTH OF JUNE, 2025
Name of Division: Hmuifang Division, Aibawk
Rs. in Lakh
Sl. no | Name of Scheme | Unit | Approved Cost (Rs.in lakh) | Date of Commencement | Target Date of Completion : | Commulative Progress at the end of last month |  | Achievement of Works during the month |  | Overall Commulative Achievement |  | Remarks | Mode of Tender
| Name of Work/Project |  |  |  |  | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
CRF
1 | Widening to Single Lane with Geometric Improvement & Up-Gradation of Chhiahtlang to Lamchhip road in Mizoram |  | 6668.18 | 23.06.2017 | 23.06.2019 | 100% | 6282.93 |  |  | 100% | 6282.93 | Physically Completed | Restricted Tender
2 | Construction of Muallungthu to Lungphun Road |  | 5996 | 23.11.2017 | 23.11.2019 | [7 empty] | Restricted Tender
| i) Formation Cutting |  |  |  |  | 100% | 2460 |  | 0 | 100% | 2460 | Physically Completed
| ii) Permanent Works |  |  |  |  | 24.51% |  | 0% |  | 24.51% |  | Work in progress
| iii) Pavement | [10 empty] | not yet started
SASCI-II
1 | Construction of Agiculture Link Road to R. Mat from Chawilung, Lungsei, Samlukhai, Sialsuk |  | 173.57 | 14.12.2023 | 14.12.2024 | 100% | 166.87 |  | 0 | 100% | 166.87 | Physically Completed | Restricted Tender
5054
1 | Widening and Repair of Vantawng Approach Road | Km | 104.49 | 10.10.2024 | 10.03.2025 | 100% | 39.48 | 0% | 65.01 | 100% | 104.49 | Physically & Financially Completed | Departmental
Sr. Executive Engineer, PWD.,
Hmuifang Division, Aibawk

## Kol Div
MONTHLY PROGRESS REPORT UNDER KOLASIB DIVISION
FOR THE MONTH OF JUNE, 2025
KOLASIB DIVISION
Sl. No. | Name of Schemes | Quantity | Unit | Approved Cost (Rs in Lakh) | Date of Commencement | Target Date of Comple-tion | Cumulative Progress at the end of last month |  | Achievement of works during the month |  | Overall Cumulative achievement |  | Remarks | Mode of Tender
| Name of Works / Project | [5 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 |  | 3 | 4 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | NABARD
1 | Construction of Meidum to Hortoki Phase-II
i | Earthwork and Permanent Work from Km 13.325 to Km 17.500 Package-I | 3.305 | Km | 13336 | 24.12.2021 | 29.04.2024 | 100% | 1035.621 |  |  | 100% | 1035.621 | Completed | Restricted Tender
ii | Earthwork and Permanent Work from Km 13.325 to Km 17.500 Package-II | 3.275 | Km |  | 25.12.2021 | 23.07.2025 | 97% | 831.292 | 0% | 102.173 | 97% | 933.465 |  | Restricted Tender
iii | Earthwork and Permanent Works from Km 17.500 to Km 21.725 Package-III | 3.315 | Km |  | 18.12.2021 | 16.11.2025 | 98% | 1186.121 | 0% |  | 98% | 1163.122 | Mobilisation & Machinery Advance Recovery Balance= Rs.23.00 lakh | Restricted Tender
iv | Earthwork and Permanent Works from Km 21.725 to Km 26.00 Package-IV | 3.355 | Km |  | 08.12.2021 | 19.05.2025 | 99% | 806.117 | 0% |  | 99% | 726.528 | Mobilisation & Machinery Advance Recovery Balance=Rs.79.589 lakh | Restricted Tender
v | Construction of Rigid Pavement : Package -I (Km 9.100-Km 15.730) | 5.58 | Km |  | 03.08.2022 | 10.12.2025 | 38% | 858.939 | 0% |  | 38% | 667.978 | Mobilisation & Machinery Advance Recovery Balance= Rs.190.965 lakh | Restricted Tender
vi | Construction of Rigid Pavement : Package -II (Km 15.730-Km 22.36) | 5.58 | Km |  | 03.08.2022 | 05.09.2025 | 14% | 486.431 | 0% |  | 14% | 188.463 | Mobilisation & Equipment Advance Recovery Balance= Rs.297.974 lakh | Restricted Tender
vii | Design & Construction of T-Beam Bridge package-I at Chhimluangte (CH : 0.450 Kmp) | 24 | m |  | 18.12.2021 |  | 100% | 469.321 |  | 13.298 | 100% | 482.621 | Completed | Departmental
viii | Design & Construction of T-Beam Bridge package-I at Dumkhel (CH : 5.500 Kmp) | 20 | m |  | 30.12.2024 | 30.06.2026 | 27% | 115.75 | 0% |  | 27% | 115.75 | Secured Advance Rs.62.24 lakh | Restricted Tender
ix | Design & Construction of T-Beam Bridge package-II at Bulung (CH : 10.200 Kmp) | 28 | m |  | 24.12.2021 | 02.10.2025 | 16% |  | 0% |  | 16% | 0 | Secured Advance Rs.82.080 lakh | Restricted Tender
x | Design & Construction of T-Beam Bridge package-II at Damdiai (CH : 23.50 Kmp) | 20 | 3: m; 8: 30%; 10: 0%; 12: 30%; 13: 0; 15: Restricted Tender
2 | Construction of BUSG Composite Bridge (Span=22.00m, Revised span=34.00m) over R. Chepte on Bilkhawthlir to Saiphai road under NABARD | 34 | m | 508.45 | 24.06.2019 | 30.11.2025 | 45% | 124.782 | 0% |  | 45% | 124.782 | Rs. 291.35 lakh from NABARD Rs.217.10 lakh from SASCE Expenditure includes centages Equipment Advance Recovery balance=Rs.8.037 lakh | Restricted Tender
3 | Construction of BUSG Composite Bridge (Span=22.00m) over R. Sesih on Bilkhawthlir to Saiphai road under NABARD | 22 | m | 291.35 | 24.06.2019 | 16.07.2025 | 92% | 248.894 | 0% |  | 92% | 248.894 | Expenditure includes centages Equipment Advance Recovery balance=Rs.25.298 lakh | Restricted Tender
4 | Construction of Link Road from NH-306 (Vairengte) to Sabual Mual Arable Crop Land : length=3.720 Kms | 3.72 | Km | 417.58 | 13.08.2022 | 28.02.2025 | 100% | 390.842 |  | 15.461 | 100% | 406.303 | Physically Completed Expenditure includes centages | Restricted Tender

## Kawrthah Div
MONTHLY PROGRESS REPORT FOR THE MONTH OF JUNE 2025
Name of Division |  | : KAWRTHAH
Source of Funding |  | : SASCI
Sl. No | Name of Works/Project | Unit |  | Approved Cost (in lakhs) | Date of Commencement | Target Date of Completion | Achievement upto previous month |  | Achievement for the month |  | Overall Cummulative achievement |  | Remarks | Mode of Contract
[7 empty] | Phy | Fin | Phy | Fin | Phy | Fin (actual)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Strengthening of Hriphaw - Kolalian - Dulupcherra Road (14.00 Kms) |  |  | 482.98 | 16.12.2023 | 14.2.2025 | [6 empty] | Work completed | Contract after call of Restricted Tender
| WBM | Cum | 819.05 |  |  |  | 819.05 | 482.98 |  |  | 819.05 | 482.98
| OPC | Km | 16.72 |  |  |  | 16.72 |  |  |  | 16.72
| Seal Coat | Km | 16.72 |  |  |  | 16.72 |  |  |  | 16.72
| Side Drain (Unlined) | Km | 14.7 |  |  |  | 14.7 |  |  |  | 14.7
| Retaining Wall | Rm | 14.2 |  |  |  | 14.2 |  |  |  | 14.2
| Wing wall repair/Reconstruction | Rm | 7 |  |  |  | 7 |  |  |  | 7
| Total of Work Component : |  |  | 482.98 |  |  |  | 482.98 |  |  |  | 482.98
| Add 3% Contingencies : |  |  | 12.7 | [5 empty] | 2.97 |  | 2.97
| Add 1% Quality Control : |  |  | 4.235
| Grand Total : |  |  | 500 |  |  |  | 482.98 |  | 2.97 |  | 485.95
| Overall Physical Progress | : | 100%
MONTHLY PROGRESS REPORT FOR THE MONTH OF JUNE 2025
Name of Division |  | : KAWRTHAH
Source of Funding |  | : SASCI
Sl. No | Name of Works/Project | Unit |  | Approved Cost (in lakhs) | Date of Commencement | Target Date of Completion | Achievement upto previous month |  | Achievement for the month |  | Overall Cummulative achievement |  | Remarks | Mode of Contract
[7 empty] | Phy | Fin | Phy | Fin | Phy | Fin (actual)
1 | 2 | 3 |  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Additional works and Completion of Double Lane Bridge over River Teirei on Bairabi - Zamuang Road. |  |  | 5: 29.2.2024; 6: 30.06.2025; 9: -; 13: Work in progress; 14: Continued by the existing contractor i.e Sadguru Engineers & Allied Services Pvt.Ltd. For Bridge work & piling of Bank protection & Departmentally for Bank protection (Balanced work) and approach road.
| Bridge Work (Super Structure) | Nos | 1 | 4: 546.91; 7: 92%; 8: 631.12; 9: 0.5%; 11: 92.5%; 12: 631.12
| River Banks Protection | Nos | 2 | 4: 475.69; 7: 91%; 11: 91%
| Approach Road | Nos | 2 | 4: 298.46; 7: 46%; 9: 4%; 11: 50%
| Road Signages |  |  | 4: 25.6
| Total of Work Component : |  |  | 4: 1346.66; 8: 631.12; 12: 631.12
| Provision for Contingencies : |  |  | 4: 26.76
| Provision for Quality Control : |  |  | 4: 26.6
| Grand Total : |  |  | 4: 1400.02; 8: 631.12; 12: 631.12
| Overall physical Progress : | 81%
MONTHLY PROGRESS REPORT FOR THE MONTH OF JUNE 2025
Name of Division |  | : KAWRTHAH
Source of Funding |  | : SASCI
Sl. No | Name of Works/Project | Unit |  | Approved Cost (in lakhs) | Date of Commencement | Target Date of Completion | Achievement upto previous month |  | Achievement for the month |  | Overall Cummulative achievement |  | Remarks | Mode of Contract
[7 empty] | Phy | Fin | Phy | Fin (in lakhs) | Phy | Fin (in lakhs)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Strengthen ing of Zamuang - Hriphaw - Kolalian - Dulupcherra (ZHKD) Road (28.00 Kmp) | Km | 28 | 225 | 16.12.2023 | 30.6.2025 | 99.2% | 192.28 |  |  | 99.2% | 192.28 | Work in progress | Contract after call of restricted tender
| Grand Total : |  |  | 4: 225; 7: 99.2%; 8: 192.28; 11: 99.2%; 12: 192.28
| Overall Physical Progress | : | 99.2%
MONTHLY PROGRESS REPORT FOR THE MONTH OF JUNE 2025
Name of Division |  | : KAWRTHAH
Source of Funding |  | : NABARD
Amount in lakhs
Sl. No | Name of Work/Project | Unit |  |  | Approved Cost (in lakh) | Date of Commencement | Target Date of Completion | Achievement upto previous month |  | Achievement for the month |  | Overall commulative achievement |  | Remarks | Mode of Contract
[8 empty] | Phy | Fin (lakh) | Phy | Fin (lakh) | Phy | Fin (actual)
1 | 2 | 3 |  |  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Double Lane BUSG Bridge (Span = 81m) over R.Langkaih on Mizoram-Tripura Border at Kanhmun | Bridge Works : |  |  | 13: Work ni progress; 14: Contract after call of Restricted Tender
|  | a) Site Investigation & Design | 7% | % | 154.23 | 6.4.2018 | 31.5.2025 | 100% | 1156.47 | - | 271.86 | 100% | 1428.33
|  | b) Construction of Subway | 20% | % | 4: 440.65; 7: 100%; 11: 100%
|  | c) Foundation & Sub-Structure | 41% | % | 4: 903.34; 7: 90%; 9: 0.5%; 11: 90.5%
|  | d) Super-Structure | 30% | % | 4: 660.98; 7: 9%; 9: 1%; 11: 10%
|  | e) Miscellaneous | 2% | % | 4: 44.06; 9: -
|  | f) Contingency |  |  | 4: 28.65; 7: -; 9: -; 11: -
|  | Grand Total : |  |  | 4: 2231.91; 8: 1156.47; 10: 271.86; 12: 1428.33
|  | Overall physical Progress :- |  |  | 4: 68%
Sr.Executive Engineer, PWD.,
Kawrthah Division, Kawrthah.

## Khawzawl Div
MONTHLY PROGRESS REPORT FOR THE MONTH OF | [7 empty] | JUNE, 2025 | [5 empty] | Page - 1
Name of Division : Khawzawl | [7 empty] | Agreement No : 7/PMGSY-III/2024-25
Source of funding : PMGSY
Sl. No. | Name of Work/Project | Unit | Approved Cost (Rs. In lakh) |  | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the Month |  | Overall cummulative achivement |  | Remarks | Mode of Contract
|  |  | Qnty | Amount |  |  | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Upgradation & Maintenace of Kawlkulh to NE.Bualpui Road (Ch. 0.00 -24.00Kmp) | [12 empty] | Work in Progress. | Item Rate Contract
1 | Formation Cutting | Km | 23 | 420.55 | 05.09.2024 | 05.03.2026 | 22 | 389.84 | 0 |  | 22 | 389.84
2 | ULSD | Rm | 22276 | 9.42 |  |  | 4500 |  | 2500 |  | 7000
3 | Permanent Work
| a) R/Wall | Rm | 100 | 18.58 |  |  | 15 |  | 0 |  | 15
| b) H/P Culvert Extension | No. | 73 | 101.44 |  |  | 86 |  | 10 |  | 96
| c) H/P Culvert Restoration | No. | 5 | 2.34
| d) H/P Culvert Type 1 | No. | 4 | 16.98
| e) LSD | Rm | 1724 | 19.84
| f) Parapet | No. | 200 | 2.03
4 | Pavement Work
| a) FDR Base Course | Km | 24 | 885.23
| b) WBM-III | Km | 24 | 339.85
| c)Wearing course (MSS) | Km | 24 | 737.95
| d) Shoulder | Km | 24 | 5.26
5 | Road signages
| 1) 5th KM Stone | No. | 6 | 0.3
| 2) Ordinary KM Stone | No. | 19 | 0.67
| 3) 200m Stone | No. | 96 | 1.44 |  |  | 96 |  |  |  | 96
| 4) Boundary pillars | No. | 240 | 3.6
| 5) Pillars Painting | sqm | 33.912 | 0.05
| 6) Speed limit | No. | 11 | 0.72
| 7) Right/Left hand curve | No. | 144 | 9.36
| 8) School | No. | 11 | 0.72
| 9) Men at work | No. | 5 | 0.33
| 10) Falling rocks | No. | 11 | 0.72
| 11) Destination sign | sqm | 1.62 | 0.16
| 12) Place identification sign | sqm | 0.75 | 0.08
| 13) Advance direction sign | sqm | 1.62 | 0.16
| 14) Direction sign | sqm | 12.96 | 1.3
| 15) Painting lines, Dashes etc. | sqm | 4800 | 24
| 16) PMGSY LOGO | 2 km | 13 | 1.3
| 17) Title information | Nos | 2 | 0.2 |  |  | 2 | 0.2 |  |  | 2 | 0.2
| 18) Citizen information | Nos | 1 | 0.15 |  |  | 1 | 0.15 |  |  | 1 | 0.15
6 | AMC 1st Year | Kms | 24 | 16.8
7 | AMC 2nd Year | Kms | 24 | 20.4
8 | AMC 3rd Year | Kms | 24 | 24
9 | AMC 4th Year | Kms | 24 | 30
10 | AMC 5th Year | Kms | 24 | 36
11 | Deduct reusable hard rock @15% |  |  | -12.9549 |  |  |  | -12.95 |  |  |  | -12.95
| Total = |  |  | 2718.95 |  |  | 19% | 377.24 | 2% |  | 21% | 377.24
MONTHLY PROGRESS REPORT FOR THE MONTH OF | [7 empty] | JUNE, 2025 | [5 empty] | Page - 2
Name of Division : Khawzawl | [7 empty] | Agreement No : 5/PMGSY-III/2024-25
Source of funding : PMGSY
Sl. No. | Name of Work/Project | Unit | Approved Cost (Rs. In lakh) |  | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the Month |  | Overall cummulative achivement |  | Remarks | Mode of Contract
|  |  | Qnty | Amount |  |  | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Upgradation & Maintenace of Kawlkulh to Lungpho upto Rullam Road (Ch. 0.00 -39.50Kmp) | [12 empty] | Work in Progress | Item rate contract
1 | Formation Cutting | Km | 39.5 | 384.99 | 23.08.2024 | 23.02.2026 | 39.5 |  |  |  | 39.5
2 | ULSD | Rm | 39500 | 46.22 |  |  | 39500 |  |  |  | 39500
3 | Permanent Work
| a) R/Wall | Rm | 820 | 217.63 |  |  | 248 |  | 35 |  | 283
| b) HP culvert Type-I | No. | 52 | 256.81 |  |  | 24 |  | 7 |  | 31
| c)RCC Slab Culvert-II | No. | 3 | 35.82
| d) LSD | Rm | 650 | 12.37
| e) Parapet | No. | 560 | 44.44
4 | Pavement Work
| a) Compacting Ground | Km | 4.85 | 6
| b) Scarifying | Km | 31.095 | 25.85
| c)WBM-II | Km | 35.945 | 384.61
| d) WBM-III | Km | 35.945 | 384.61
| e) Wearing course (MSS) | Km | 35.945 | 673.87
| f) Shoulder | Km | 35.945 | 81.48
| g) Rigid Pavement | Km | 3.555 | 319.23
5 | Road signages
| 1) 5th KM Stone | each | 9 | 0.6
| 2) Ordinary KM Stone | No. | 32 | 1.26
| 3) 200m Stone | No. | 158 | 1.11
| 4) Boundary pillars | No. | 395 | 3.43
| 5) Pillars Painting | sqm | 55.8135 | 0.12
| 6)Speed limit | No. | 55.8135 | 0.1
| 7) Right/Left hand curve | No. | 2 | 5.96
| 8) School | No. | 125 | 0.05
| 9) Men at work | No. | 1 | 0.1
| 10) Falling rocks | No. | 2 | 0.1
| 11) Destination sign | sqm | 1.62 | 0.09
| 12) Place identification sign | sqm | 0.75 | 0.04
| 13) Advance direction sign | sqm | 1.62 | 0.09
| 14) Direction sign | sqm | 0.36 | 0.02
| 15) Painting lines, Dashes etc. | sqm | 11861.85 | 25.08
| 16) PMGSY LOGO | 2 km | 20 | 4.99
| 17) Title information | Nos | 2 | 0.3 |  |  | 1 |  |  |  | 1
| 18) Citizen information | Nos | 1 | 0.18 |  |  | 1 |  |  |  | 1
6 | AMC 1st Year | kms | 39.5 | 19.75
7 | AMC 2nd Year | kms | 39.5 | 23.7
8 | AMC 3rd Year | kms | 39.5 | 29.63
9 | AMC 4th Year | kms | 39.5 | 35.55
10 | AMC 5th Year | kms | 39.5 | 47.4
11 | Deduct Reusable Hard Rock@15% |  |  | -11.6
| Total = |  |  | 3061.98 |  |  | 20% |  | 3% |  | 23%
MONTHLY PROGRESS REPORT FOR THE MONTH OF | [7 empty] | JUNE, 2025 | [5 empty] | Page - 3
Name of Division : Khawzawl | [7 empty] | Agreement No : 17/PMGSY-III/2024-25
Source of funding : PMGSY
Sl. No. | Name of Work/Project | Unit | Approved Cost (Rs. In lakh) |  | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the Month |  | Overall cummulative achivement |  | Remarks | Mode of Contract
|  |  | Qnty | Amount |  |  | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Upgradation & Maintenace of Kawlkulh to Lungpho to Ngentiang Road (Ch. 0.00 - 11.840Kmp) | [12 empty] | Work in Progress | Item Rate Contract
1 | Formation Cutting | Km | 11.84 | 79.92 | 29.08.2024 | 01.03.2026 | 11.84 |  | 0 |  | 11.84
2 | ULSD | Rm | 11840 | 13.25 |  |  | 10500 |  | 0 |  | 10500
3 | Permanent Work
| a) R/Wall | Rm | 380 | 180.37 |  |  | 213 |  | 15 |  | 228
| b) HP culvert Type-I | No. | 23 | 150.28 |  |  | 11 |  | 1 |  | 12
| c)RCC Slab Culvert-II | No. | 1 | 16.06
| d) LSD | Rm | 1900 | 53.54 |  |  | 140 |  | 0 |  | 140
| e) Parapet | No. | 560 | 17.64
4 | Pavement Work
| a) Compacting Ground | Km | 11.555 | 6.18
| b) Scarifying | Km | 11.555 | 4.15
| c) WBM-III | Km | 11.555 | 185.4
| d) Prime Coat | Km | 11.555 | 44.51
| e) Tack Coat | Km | 11.555 | 24.88
| f) Wearing course (MSS) | Km | 11.555 | 187.6
| g) Shoulder | Km | 11.555 | 24.89
| f) Rigid Pavement | Km | 0.285 | 10.34
5 | Road signages
| 1) 5th KM Stone | each | 3 | 0.19
| 2) Ordinary KM Stone | No. | 10 | 0.37
| 3) 200m Stone | No. | 47 | 0.31
| 4) Boundary pillars | No. | 118 | 0.97
| 5) Pillars painting | No. | 119 | 0.03
| 6)Speed limit | No. | 2 | 0.09
| 7) Right/Left hand curve | No. | 125 | 5.66
| 8) School | No. | 1 | 0.05
| 9) Men at work | No. | 2 | 0.09
| 10) Falling rocks | No. | 2 | 0.09
| 11) Destination sign | sqm | 1.62 | 0.08
| 12) Place identification sign | sqm | 0.75 | 0.04
| 13) Advance direction sign | sqm | 1.62 | 0.08
| 14) Direction sign | sqm | 0.36 | 0.02
| 15) Painting lines, Dashes etc. | sqm | 3813.15 | 7.66
| 16) PMGSY LOGO | 2 km | 6 | 0.52
| 17) Title information | Nos | 2 | 0.29 |  |  | 1 |  |  |  | 1
| 18) Citizen information | Nos | 1 | 0.17 |  |  | 1 |  |  |  | 1
6 | AMC 1st Year | Kms | 11.84 | 5.92
7 | AMC 2nd Year | Kms | 11.84 | 7.1
8 | AMC 3rd Year | Kms | 11.84 | 8.88
9 | AMC 4th Year | Kms | 11.84 | 10.66
10 | AMC 5th Year | Kms | 11.84 | 14.21
11 | Deduct Reusable Hard Rock@15% |  |  | -4.63
| Total = |  |  | 1057.86 |  |  | 25% |  | 3% |  | 28%

## LPBD
MONTHLY PROGRESS REPORT FOR THE MONTH OF JUNE, 2025 ( BUILDING WORKS )
Name of Division: Lunglei Building Project Division, Lunglei
Rs. in Lakh
Sl.no | Name of Scheme | Unit | Approved Cost (Rs.in lakh) | Date of Commencement | Target Date of Completion : | Commulative Progress at the end of last month |  | Achievement of Works during the month |  | Overall Commulative Achievement |  | Remarks | Mode of Tender
| Name of Work/Project |  |  |  |  | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
SASCI
1 | Construction of Laboratory Building at Civil Hospital, Lunglei (Ground floor) |  | 192.98 | 28.10.2021 | 28.10.2022 | 100% | 192.98 |  |  | 100% | 192.98 | Completed. | Restricted Tender
2 | Construction of Laboratory Building at Civil Hospital, Lunglei (1st & 2nd Floor) Supplementary Works |  | 396 | 28.10.2022 | 28.4.2024 | 100% | 330.7 |  |  | 100% | 330.7 | Civil Works completed and I/E not yet started | Supplementary Works to sl.no(a) above
3 | Construction of Futsal ground at Lungdai, Kawnpui, Ngopa, Kawlkulh, Champhai, Serchhip & Siaha (Sh: Construction of Futsal Ground at Siaha)
1 | Construction of Meisatla Futsal Ground at Siaha |  | 34.786 | 20.03.23 | 20.09.23 | 49% | 21.84 | 0% | 0 | 49% | 21.84 | Work not completed due to site dispute | Restricted Tender
4 | Construction of Government Building at Hnahthial, PWD EE Quarters, Circuit House & DC Office |  | 344.03 | 23.03.24 | 23.03.26 |  | 336.26 |  | 11.58 |  | 347.84 |  | Restricted Tender
1 | Construction of PWD EE Quarters at Hnahthial |  |  |  |  | 60% |  | 5% |  | 65% |  | Work in Progress
2 | Hnahthial Circuit House |  |  |  |  | 92% |  | 1% |  | 93% |  | Work in Progress
5 | Construction of Community Hall at Siasi, Phural, Tawngkawlong, Tipa B, Meisavaih, Amotlah |  | 305.72 | 23.03.24 | 23.07.25 |  | 103.5 |  | 0 |  | 103.5 |  | Restricted Tender
1 | Construction and Completion of MTP(H) Office |  |  |  |  | 100% |  |  |  | 100% |  | Completed
2 | Construction of MTP Information Office |  |  |  |  | 100% |  |  |  | 100% |  | Completed
3 | Construction of Bazarshed at New Siaha East-II |  |  |  |  | 100% |  |  |  | 100% |  | Completed
4 | Continuation of MYA Hall at New Siaha East-I |  |  |  |  | 100% |  |  |  | 100% |  | Completed
5 | Construction of MTP Hall and Retaining Wall at Amotlah |  |  |  |  | 100% |  |  |  | 100% |  | Completed
6 | Construction of Model Middle School Ground at Retaining Wall at New Siaha West-I |  |  |  |  | 100% |  |  |  | 100% |  | Completed
7 | Construction of Retaining Wall at Futsal Ground at Tipi Ferry |  |  |  |  | 100% |  |  |  | 100% |  | Completed
6 | Construction of Play ground with Pavillion at Lungtian, Sangau, Bualpui (NG), Tuichawngtlang, Ngunlingkhua, T. Dumzau |  | 339.41 | 23.03.24 | 23.07.25 |  | 164.53 |  | 0 |  | 164.53 |  | Restricted Tender
1 | Renovation of Community Hall Ramhlun Veng, Sangau |  |  |  |  | 100% |  |  |  | 100% |  | Completed
2 | Construction of Community Hall Council Veng, Lawngtlai |  |  |  |  | 100% |  |  |  | 100% |  | Completed
3 | Vertical Extension of Central Young Lai Association Office Lawngtlai |  |  |  |  | 100% |  |  |  | 100% |  | Completed
4 | Construction of Futsal Ground at Lungtian-I |  |  |  |  | 100% |  |  |  | 100% |  | Completed
5 | Construction of Futsal Ground at Bualpui (NG) |  | 339.41 | 23.03.24 | 23.07.25 | 100% | 164.53 |  | 0 | 100% | 164.53 | Completed | Restricted Tender
6 | Construction of Futsal Ground at Sangau |  |  |  |  | 100% |  |  |  | 100% |  | Completed
7 | Construction of Volleyball Court Lungzarhtum |  |  |  |  | 100% |  |  |  | 100% |  | Completed
7 | Construction of Community Hall Cum Market Building at Luangmual, Lunglei |  | 301.19 | 23.03.24 | 23.07.25 |  | 132.21 |  | 0 |  | 132.21 |  | Restricted Tender
1 | Construction of DM High School Building ( Theiriat ) |  |  |  |  | 100% |  |  |  | 100% |  | Completed
2 | Construction of Luangmual Market Building |  |  |  |  | 100% |  |  |  | 100% |  | Completed
3 | Construction of Sairep Community Hall |  |  |  |  | 100% |  |  |  | 100% |  | Completed
8 | Vertical Extention of Market Building at Kamalanagar |  | 237.85 | 23.03.24 | 23.07.25 |  | 23.97 |  | 0 |  | 23.97 |  | Restricted Tender
1 | Vertical Extension of existing Bazaar Building at Kamalanagar-I with Tin Roofing |  |  |  |  | 45% |  | 2% |  | 47% |  | Work in Progress
2 | Construction of additional Bazaar Building by demolishing the existing dilapidated building that was constructed under BADP |  |  |  |  | 45% |  | 2% |  | 47% |  | Work in Progress
3 | 2. Construction of Rest House at PWD Complex Bunghmun. |  |  |  |  | 42% |  | 0% |  | 42% |  | Work in Progress
9 | Construction of Community Hall cum Health Clinic Center at Kawlhawk, Bungtlang West, South Lungdai and Serte |  | 371.57 | 23.03.24 | 23.07.25 |  | 103.04 |  | 0 |  | 103.04 |  | Restricted Tender
1 | Higher Secondary School Building, Buarpui |  |  |  |  | 100% |  |  |  | 100% |  | Completed
2 | Community Hall, Kawlhawk |  |  |  |  | 100% |  |  |  | 100% |  | Completed
3 | Health Clinic, Bungtlang West |  |  |  |  | 100% |  |  |  | 100% |  | Completed
4 | PWD IB repair, Sertlangpui |  |  |  |  | 100% |  |  |  | 100% |  | Completed
5 | Construction of Badminton Hall at Chhipphir |  |  |  |  | 95% |  | 0% |  | 95% |  | Work in Progress
6 | Completion of Badminton Hall at Chhipphir |  |  |  |  | 95% |  | 0% |  | 95% |  | Work in Progress
7 | Anganwadi Centre-I, Sertlangpui |  |  |  |  | 100% |  |  |  | 100% |  | Completed
8 | Anganwadi Centre-I New Construction, Serte |  |  |  |  | 100% |  |  |  | 100% |  | Completed
9 | Health & Wellness Officer Quarter new construction, Serte |  |  |  |  | 100% |  |  |  | 100% |  | Completed
10 | Health Clinic Office, South Lungdai |  |  |  |  | 100% |  |  |  | 100% |  | Completed
11 | Construction of Futsal Ground Flooring at Lalveng, Haulawng |  |  |  |  | 100% |  |  |  | 100% |  | Completed
10 | Construction of Government Quarters (General Pool) at Venglai, Lunglei (Ramnghaka's Quarters Site) SH : Type-IV Quarters (2 units, 1 Block) |  | 214.99 | 30.04.2025 | 30.04.2026 |  |  | 3% | 0 | 3% | 0 | Work in Progress | Restricted Tender
11 | Construction of Government Quarters (General Pool) at Venglai, Lunglei (Soil Quarters Site) SH : Type-III Quarters (1 unit) Type-IV Quarters (2 units) |  | 221.37 | 30.04.2025 | 30.04.2026 |  |  | 3% | 0 | 3% | 0 | Work in Progress | Restricted Tender
12 | Construction of Government Quarters (General Pool) at Venglai, Lunglei (Zautea's Quarters Site) SH : Type-IV Quarters (1 unit, 1 Block) |  | 79.29 | 30.04.2025 | 30.04.2026 |  |  | 1% | 0 | 1% | 0 | Work in Progress | Restricted Tender
13 | Construction of GovernmentQuarters (General Pool) at Venglai, Lunglei (Numami's Quarters Site) SH : Type-IV Quarters (1 unit, 1 Block) |  | 79.29 | 30.04.2025 | 30.04.2026 |  |  | 5% | 0 | 5% | 0 | Work in Progress | Restricted Tender
14 | Construction of Government Quarters (General Pool) at Venglai, Lunglei (Quarters No. 5 Site) SH : Type-III Quarters (2 units, 1 Block) |  | 133.42 | 30.04.2025 | 30.04.2026 |  |  | 1% | 0 | 1% | 0 | Work in Progress | Restricted Tender
15 | Construction of Government Quarters (General Pool) at Venglai, Lunglei (Zorini's Quarters Site) SH : Type-III Quarters (2 units, 1 Block) |  | 137.99 | 30.04.2025 | 30.04.2026 |  |  | 2% | 0 | 2% | 0 | Work in Progress | Restricted Tender
16 | Construction of Government Quarters (General Pool) at Venglai, Lunglei (Thapa's Quarters Site) SH : Type-III Quarters (2 units, 1 Block) |  | 137.99 | 30.04.2025 | 30.04.2026 |  |  | 2% | 0 | 2% | 0 | Work in Progress | Restricted Tender
17 | Construction of Government Quarters (General Pool) at Venglai, Lunglei (Pi Marcella's Quarters Site) SH: Type - III Quarters (2 Units) |  | 120.02 | 30.04.2025 | 30.04.2026 |  |  | 5% | 0 | 5% | 0 | Work in Progress | Restricted Tender
18 | Construction of Government Quarters (General Pool) at Venglai, Lunglei (Pi Marcella's Quarters Site) SH: Type - III Quarters (1 Unit) |  | 86.52 | 30.04.2025 | 30.04.2026 |  |  | 2% | 0 | 2% | 0 | Work in Progress | Restricted Tender
19 | Construction of Working Women Hostel at Ramthar Veng, Lunglei |  | 1186.47 | 02.05.2025 | 02.05.2026 |  |  | 0% | 0 | 0% | 0 | Work not yet started | Restricted Tender
20 | Construction of District Prison/Jail,Lunglei |  | 523.87 | 16.04.2025 | 16.04.2026 |  |  | 1% | 0 | 1% | 0 | Work in Progress | Restricted Tender
21 | Construction of Government Quarters (General Pool) at Lawngtlai at Additional DC Quarter |  | 133.09 | 16.04.2025 | 16.04.2026 |  |  | 1% | 0 | 1% | 0 | Work in Progress | Restricted Tender
22 | Construction of Government Quarters (General Pool) at Lawngtlai Electric Veng (near RD Office) |  | 648.26 | 16.04.2025 | 16.04.2026 |  |  | 0% | 0 | 0% | 0 | The existing building cannot be dismantled by the contractor as the occupient and client department (DC Lawngtlai) does not settle yet | Restricted Tender
23 | Construction of Government Quarters (General Pool) at Lawngtlai Electric Veng (near BDO Office) |  | 220.73 | 23.04.2025 | 23.04.2026 |  |  | 0% | 0 | 0% | 0 | Work not yet started | Restricted Tender
24 | Construction of Government Quarters (General Pool) at Lawngtlai Electric Veng (near A&T Office) |  | 219.67 | 16.04.2025 | 16.04.2026 |  |  | 0% | 0 | 0% | 0 | Work not yet started | Restricted Tender
25 | Construction of Circuit Houses at Siaha |  | 522.13 | 16.04.2025 | 16.04.2026 |  |  | 0% | 0 | 0% | 0 | Work not yet started | Restricted Tender
26 | Construction of Government Quarters (General Pool) at New Siaha at Additional DC Quarters (Inside Gate) |  | 228.26 | 16.04.2025 | 16.04.2026 |  |  | 0% | 0 | 0% | 0 | Work not yet started | Restricted Tender
27 | Construction of Government Quarters (General Pool) at New Siaha at Additional DC Quarters (Outside Gate) |  | 239.98 | 16.04.2025 | 16.04.2026 |  |  | 0% | 0 | 0% | 0 | Work not yet started | Restricted Tender
28 | Construction of Government Quarters (General Pool) at New Siaha at Additional DC Quarters (Type III) |  | 273.97 | 16.04.2025 | 16.04.2026 |  |  | 0% | 0 | 0% | 0 | Work not yet started | Restricted Tender
29 | Construction of Government Quarters (General+B74:M92 Pool) at New Siaha at Meisavaih Site-I (Type III, 4 unit) |  | 274.93 | 16.04.2025 | 16.04.2026 |  |  | 0% | 0 | 0% | 0 | Work not yet started | Restricted Tender
30 | Construction of Government Quarters (General Pool) at New Siaha at Meisavaih Site-II (Type III, 4 unit) |  | 274.79 | 16.04.2025 | 16.04.2026 |  |  | 0% | 0 | 0% | 0 | Work not yet started | Restricted Tender
31 | Construction of District Prison/Jail, Siaha |  | 916.43 | 16.04.2025 | 16.04.2026 |  |  | 1% | 0 | 1% | 0 | Work in progress. | Restricted Tender
1 | NABARD
CONSTRUCTION OF WAREHOUSES WITH ASSOCIATED INFRASTRUCTURE IN 12 LOCATIONS UNDER NABARD
| GROUP- III: | [11 empty] | Restricted Tender
| 1) Siaha SDC |  | 444.99 | 17.07.2023 | 31.3.2025 | 54% | 210.45 | 0% |  | 54% | 210.45 | No progress since previous month
| 2) Chapui |  | 197.82 | 17.07.2023 | 31.3.2025 | 50% | 98.89 | 3% |  | 53% | 98.89 | Works in progress.
| 3) Bungtlang South |  | 162.63 | 17.07.2023 | 31.3.2025 | 92% | 74.86 | 1% |  | 93% | 74.86 | Works in progress. | Restricted Tender
| GROUP- IV: | [11 empty] | Restricted Tender
| 1) Lungpher |  | 197.12 | 17.07.2023 | 31.3.2025 | 100% | 116.58 |  |  | 100% | 116.58 | Civil Works completed and I/E not yet started
| GROUP- VI: | [11 empty] | Restricted Tender
| 1) South Vanlaiphai |  | 187.15 | 17.07.2023 | 31.3.2025 | 70% | 63.98 | 2% |  | 72% | 63.98 | Works in progress.
1 | 2) Vawmbuk |  | 197.82 | 17.07.2023 | 31.3.2025 | 74% | 51.83 | 1% |  | 75% | 51.83 | Works in progress.
| GROUP-VIII: | [11 empty] | Restricted Tender
| 1) Hnahthial |  | 197.24 | 17.07.2023 | 31.3.2025 | 0% | - | 1% | - | 1% | - | Work started
| 2) Thingsai |  | 160.32 | 17.07.2023 | 31.3.2025 | 62% | 42.34 | 4% |  | 66% | 42.34 | Works in progress
| 3) Cherhlun |  | 85.61 | 17.07.2023 | 31.3.2025 | 88% | 26.72 | 3% |  | 91% | 26.72 | Works in progress
| 4) Siata |  | 197.82 | 17.07.2023 | 31.3.2025 | 88% | 74.43 | 1% |  | 89% | 74.43 | Works in progress | Restricted Tender
| GROUP-X: | [11 empty] | Restricted Tender
| 1) Vaseikai |  | 220.35 | 17.07.2023 | 31.3.2025 | 82% | 109.75 | 3% |  | 85% | 109.75 | Works in progress
| 2) Tlabung |  | 93.84 | 17.07.2023 | 31.3.2025 | 79% | 22.366 | 5% |  | 84% | 22.366 | Works in progress
2 | Construction of Infrastructure Support for School of Agricultural Science at Hnahthial (Phase-II) | [10 empty] | Works in progress | Restricted Tender
| i) Boys Hostel |  | 659.4 | 08.04.2023 | 08.04.2025 | 81% | 293.71 | 2% |  | 83% | 293.71
| ii) Staff Quarter Type - III |  |  |  |  | 69% |  | 5% |  | 74%
| iii) Staff Quarter Type - II |  |  |  |  | 77% |  | 2% |  | 79%
| iv) Guest House |  |  |  |  | 78% |  | 5% |  | 83%
NEC
1 | Construction of Mara Handloom & Weaving Centre at Council Vaih, Siaha |  | 439.41 | 13.04.2022 | 31.03.2025 | 100% | 395.46 |  |  | 100% | 395.46 | Civil & I/E Works completed,handover in process | Restricted Tender
2 | Construction of Lunglei Market and Trade Centre at Electric/ Chanmari Veng, Lunglei |  | 1403.4 | 25.08.2022 | 30.09.2025 | 77% | 562.61 | 3% |  | 80% | 562.61 | Work in progress | Restricted Tender
CSS
1 | Construction of Academic Building for Nursing School at Lunglei (Upgradation) | - | 441.35 | 19.8.2024 | 19.8.2026 | 49% | 68.69 | 1% |  | 50% | 68.69 | Works in progress | Open Tender
NEDP
1 | Construction of DC Bungalow (Type VI) at Siaha |  | 93.86 | 26.11.2018 | 23.05.2024 (Revised) | 100% | 109 |  |  | 100% | 109 | Handover in process | Restricted Tender
2 | Construction of DC Office Building at Siaha |  | 509.08 | 31.10.2018 | 31.10.2020 Revised to Dt.28.11.2023 | 94% | 473.53 | 1% |  | 95% | 473.53 | Works in progress | Restricted Tender
NESIDS
1 | Construction of 50-Bedded District Hospital Complex and Procurement of Equipment at Hnahthial, Mizoram |  | 1378.86 | 25.6.2024 | 25.12.2026 | 22% | - | 1% |  | 23% | - | Work in progress | Open Tender
MINISTRY OF TRIBAL AFFAIRS
1 | Construction of Auditorium at Pukpui Lunglei |  | 470.088 | 16.9.2023 | 16.01.2025 | 0% | - | - | - | 0% | - | Dismantling at site is under process and construction will be started as soon as estimate is approved. | Restricted Tender
Sr. Executive Engineer, PWD.,
Lunglei Building Project Division, Lunglei

## LRD I
MONTHLY PROGRESS REPORT UNDER LUNGLEI ROAD DIVISION - I, LUNGLEI
FOR THE MONTH OF JUNE, 2025
(Rs. in lakh)
Sl. No. | Name of Schemes | Quantity | Unit | Approved Cost (Rs in Lakh) | Date of Commencement | Target Date of Comple-tion | Cumulative Progress at the end of last month |  | Achievement of works during the month |  | Overall Cumulative achievement |  | Remarks | Mode of Tender
| Name of Works / Project | [5 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | PMGSY
1 | Construction and Maintenance of Bunghmun to Sachan Road (0.00 - 9.07Kmp)
I | Formation Cutting | 5.48 | Km | 134.1 | 13.12.2018 | 12.12.2019 | 5.48 | 930.03 |  |  | 5.48 | 930.03 | Completed
II | Pavement Works
| a) Sub-Grade | 10.42 | Km | 17.76 |  |  | 10.42 |  |  |  | 10.42 |  | Completed
| b) Repair of Damages | 10.42 | Km | 2.12 |  |  | 10.42 |  |  |  | 10.42 |  | Completed
| c) GSB | 10.42 | Km | 186.5 |  |  | 10.42 |  |  |  | 10.42 |  | Completed
| d)Panel Concrete pavement | 10.42 | Km | 339.93 |  |  | 7.97 |  | 0.03 |  | 8 |  | On going |  | 7.03
III | Shoulder | 10.42 | Km | 27.33 |  |  | 7.74 |  | 0.23 |  | 7.97 |  | On going |  | -0.94
IV | Side Drainage Works :-
| a) Unline Side Drain | 10.42 | Km | 9.5 |  |  | 10.42 |  |  |  | 10.42 |  | Completed |  |  | 0.71
| b) Line Side drain | 2327 | Km | 40.52
V | Protection Works | [13 empty] | -0.23
| a) Retaining Wall | 359 | Rm | 167.97 |  |  | 310 |  |  |  | 310 |  | On going
| b) Gabion Wall | 180 | Rm | 31.23
VI | Cross Drainage Works :
| a) Minor Bridge | 2 | Nos | 132.06 |  |  | 2 |  |  |  | 2 |  | Completed
| b) Slab Culvert | 0 | Nos
| c) Hume Pipe Culvert | 31 | Nos | 225.16 |  |  | 31 |  |  |  | 31 |  | Completed
VII | Parapets | 186 | Nos | 5.45
VIII | Road Signs with fixing |  |  | 20.68
Logo & Info Board
| TOTAL = |  |  | 1340.31 |  |  | 86% | 930.03 |  |  | 87% | 930.03
PMGSY
2 | Construction and Maintenance of Sachan to Sumasumi Road (0.00 – 24.09)Km | [11 empty] | Completed
I | Formation Cutting | 24.09 | Km | 803.63 | 10.06.2019 | 10.06.2020 | 24.09 | 3431.7 |  |  | 24.09 |  | Completed
II | Unline Side Drain | 24.09 | Km | 32.77 |  |  | 24.09 |  |  |  | 24.09 |  | On going
III | Side Drain | 4950 | Rm | 103.68
IV | Cross Drainage Work | [11 empty] | Completed
| a) Minor Bridge | 1 | Nos | 41.33 |  |  | 1 | [5 empty] | Completed
| b) Slab Culvert | 76 | Nos | 910.66 |  |  | 76 |  |  |  | 76
| c) Hume Pipe Culvert | 0 | Nos
V | ProtectionWorks | [11 empty] | On going
| a) Retaining Wall | 850 | Rm | 426.38 |  |  | 610 |  |  |  | 610
| b)Gabion Wall | 195 | Rm | 36.15
VI | Pavement Works | [11 empty] | Completed
| a) Preparation of Sub-Grade | 24.09 | Km | 43.716 |  |  | 24.09 |  |  |  | 24.09 |  | Completed
| b)Repair of Damages | 24.09 | Km | 5.42 |  |  | 24.09 |  |  |  | 24.09 |  | Completed
| c) GSB | 24.09 | Km | 558 |  |  | 24.09 |  |  |  | 24.09 |  | Completed
| d) WBM Grading 2 | 24.09 | Km | 333.67 |  |  | 24.09 |  |  |  | 24.09 |  | Completed
| e) WBM Grading 3 | 24.09 | Km | 331.76 |  |  | 24.09 |  |  |  | 24.09 |  | On going
| f) Prime Coat | 24.09 | Km | 52.18 |  |  | 5 |  |  |  | 5 |  | On going
| g) Tack Coat | 24.09 | Km | 17.6 |  |  | 5 |  |  |  | 5 |  | On going
| h) 20mm thick OPC | 24.09 | Km | 226.42 |  |  | 5 |  |  |  | 5 |  | On going
| i) Seal Coat | 24.09 | Km | 69.11 |  |  | 5 |  |  |  | 5 |  | Completed
| Embankment | 18673.269 | m3 | 21.44 |  |  | 18307.789 |  |  |  | 18307.789 |  | Completed
VII | Shoulder | 24.09 | m3 | 68.38 |  |  | 24.09 |  |  |  | 24.09 |  | Completed
VIII | Parapets | 205 | Nos | 5.74 |  |  | 205 |  |  |  | 205 |  | Completed
IX | Road signs with fixing | 315 | Nos | 36.72 |  |  | 315 |  |  |  | 315
X | Logo & info board |  | Km | 1.65
| Deduction as per BOQ Sl.No 53 | 14059.115 |  | -11950247.75
| TOTAL= |  |  | 4005.26 |  |  | 89% | 3431.7 |  |  | 89%
PMGSY
3 | Construction and Maintenance of Sumasumi - Tuikawi Road (0.00-19.22)Km
I | Formation Cutting | 19.22 | Km | 508.744 | 14.06.2019 | 14.06.2020 | 18.675 | 1407.58 |  | 23.88 | 18.675 | 1431.46 | Work Completed
II | Unline Side Drain | 19.22 | Km | 22.491 |  |  | 16.5 |  |  |  | 16.5
III | Line Side Drain | 4000 | Rm | 72.321 |  |  | 1500 |  |  |  | 1500
IV | Cross Drainage Work
| a) Minor Bridge | 1 | Nos | 37.746
| b) Slab Culvert | 15 | Nos | 396.06 |  |  | 15 |  |  |  | 15
| c) Hume Pipe Culvert | 49 | Nos | 308.6 |  |  | 31 |  |  |  | 31
V | ProtectionWorks
| a) Retaining Wall | 448 | Rm | 158.219 |  |  | 318 |  |  |  | 318 |  |  |  |  | -2.6
| b)Gabion Wall | 150 | Rm | 38.21
VI | Pavement Works
| a) Preparation of Sub-Grade | 19.22 | Km | 29.85 |  |  | 13.355 |  |  |  | 13.355
| b) GSB | 19.22 | Km | 447 |  |  | 13.55 |  |  |  | 13.55
| c) PCC Pavement works | 19.22 | Km | 764.29 |  |  | 12.9 |  |  |  | 12.9 |  |  |  |  | 2.145
| d) Constn. of Road Shoulder | 19.22 | Km | 46.691 |  |  | 12.9 |  |  |  | 12.9
| e) Repair of Damages | 19.22 | Km | 3.72 |  |  | 13.355 |  |  |  | 13.355 |  |  |  | 0
VII | Traffic Sign and Road Safety Measures
| a) Km Stone | 97 | Nos | 1.149 |  |  | 97 |  |  |  | 97
| b) 60cm Equilateral Triangle Traffic Signs | 117 | Nos | 19.571 |  |  | 117 |  |  |  | 117
| c) Traffic Signs | 4.35 | m2 | 1.029 |  |  | 4.35 |  |  |  | 4.35
| d) PMGSY Logo and Informatory Board | 12 | Nos | 1.231
| Deduction as per BOQ Sl.no 51 | 12603.739 |  | -107.13
| Total= |  |  | 2882.21 |  |  | 100% | 1407.58 |  | 23.88 | 100% | 1431.46
PMGSY
4 | UPGRADATION & MAINTENANCE OF LUNGLEI TO KAWLHAWK TO BUARPUI ROAD (0.000- 66.500 KMP)
I | Formation Cutting | 66.5 | Km |  | 08.09.2024 | 08.03.2026
| (a) Clearing & Grabing of Road | 39.9 | Hect. | 35.91 |  |  | 56.5 |  |  |  | 56.5
(b) Cutting of tree.(Lead upto100m)
| (i) Girth above 300mm to 600mm. | 200 | Nos | 0.62
| (ii) Girth above 600mm to 900mm. | 400 | Nos | 1.8
| (i) Girth above 900mm to 1800mm. | 550 | Nos | 4.95
| (c) Reference Pillar | 67.5 | Km | 5.4
| (d) Back Pillar | 67.5 | Km | 20.59
| (e) Job Pillar | 2 | Each | 0.01
| (f) Excavation in Soil | 101786.354 | Cum | 85.5
| (g) Excavation in Ordinary Rock | 135778.115 | Cum | 207.74
| (h) Excavation in Hard Rock | 10749.874 | Cum | 38.16
II | Earthen Shoulder | 66.5 | Km | 63.02
III | Kilometre Stone.(M -15)
| (a) 5th Km Stone (Precast) | 14 | Nos | 0.7
| (b) Ordinary Km Stone.(Precast) | 54 | Nos | 1.62
| (c) 200m Stone.(Precast) | 266 | Nos | 1.6
IV | Boundary Pillars.(M-15) | 665 | Nos | 4.79
V | Side Drains
| (a)Unline Side Drain | 66.5 | Km | 50.79
| (b)Lined Side Drain | 0.91 | Km | 13.92
VII | Clearing of Culverts | 2652 | Nos | 13.26
VII | Cross Drainage
| a) Slab Culvert | 30 | Nos | 176.72
| b) Hume Pipe Culvert | 51 | Nos | 201.42
VIII | Protection works | 1970 | Rm | 430.89
IX | Pavement works
| (a) FDR with Flexible | 63.96 | Km | 3961.59
| b) Rigid,(PCC) | 2.54 | Km | 116.76
X | Parapet | 560 | Nos | 73.02
XI | Road Signs,(Retro-Reflectorised) | 132 | Nos | 5.33
XII | Titlle Informatin | 2 | Nos | 0.38
XIII | Citizen Informatin | 1 | Nos | 0.19
XIV | PMGSY LOGO | 33 | Each | 5.94
XV | Road Marking Paint..ect. | 21106.8 | Sqm | 49.6
| TOTAL = |  |  | 5572.22 |  |  | 0.85% |  |  |  | 0.85%
MONTHLY PROGRESS REPORT UNDER LUNGLEI ROAD DIVISION - I, LUNGLEI
FOR THE MONTH OF JUNE/ 2025
(Rs. in lakh)
Sl. No. | Name of Schemes | Quantity | Unit | Approved Cost (Rs in Lakh) | Date of Commencement | Target Date of Comple-tion | Cumulative Progress at the end of last month |  | Achievement of works during the month |  | Overall Cumulative achievement |  | Remarks | Mode of Tender
| Name of Works / Project | [5 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
SASCI
I | Aizawl-Thenzawl-Lunglei Road Between Kanghmun 'S' and Kikawn, Lunglei Phase-I, (Sh:- Group - A Between 100.00 - 120.00Kmp)
1 | Water Bound Macadam | 726.31 | Cum | 51.43 | 03.07.2023 | 06.05.2025 | 2309 | 608.25 |  |  | 2309 | 608.25 | Completed
2 | Open Graded premix | 14063.5 | Sqm | 56.25 |  |  | 15400 |  |  |  | 15400 |  | Completed
3 | Seal coating | 110000 | Sqm | 195.8 |  |  | 15400 |  |  |  | 15400 |  | Completed
4 | DLC | 660.83 | Cum | 49.63 |  |  | 99.55 |  |  |  | 99.55 |  | In progress
5 | PQC | 991.237 | Cum | 208.16 |  |  | 182.44 |  |  |  | 182.44 |  | In progress
6 | RCC Hume Pipe Culvert | 1 | No | 9.9
7 | Lined Side Drain | 360 | Rm | 8.89 |  |  | 75 | [5 empty] | In progress
8 | Side Drain Clearance | 20000 | Rm | 18 |  |  | 20000 |  |  |  | 20000 |  | Completed
9 | Clearing Road Side Jungle | 40 | Km | 4.36 |  |  | 40 |  |  |  | 40 |  | Completed
10 | Breast Wall | 23 | m | 44.67 |  |  | 20 |  |  |  | 20 |  | In progress
11 | Lined Side Drain with RCC Cover | 15 | m
12 | Substituted Item (Flexible instead of DLC + PQC) at some locations
(a) | Scarifying & Sub-Grade Prepn | 0.65 | Km |  |  |  | 0.65 |  |  |  | 0.65 |  | Work in Progress (Substituted Items as already approved by SE, Lunglei Circle).
(b) | Laying of WBM | 0.65 | Km |  |  |  | 0.65 |  |  |  | 0.65
(c) | DBM | 0.65 | Km
(d) | BC | 0.65 | Km
| TOTAL = |  |  | 647.09 |  |  | 90% | 608.25 |  |  | 90% | 608.25
MONTHLY PROGRESS REPORT UNDER LUNGLEI ROAD DIVISION - I, LUNGLEI
FOR THE MONTH OF JUNE, 2025
(Rs. in lakh)
Sl. No. | Name of Schemes | Quantity | Unit | Approved Cost (Rs in Lakh) | Date of Commencement | Target Date of Comple-tion | Cumulative Progress at the end of last month |  | Achievement of works during the month |  | Overall Cumulative achievement |  | Remarks | Mode of Tender
| Name of Works / Project | [5 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
ANNUAL PLAN (5054)
I | Construction of Bailey Bridge (SS) Over R.Sazek on Mauzam to New Sachan Road (Sh: Construction of Abutment & Wingwall)
| 1) Abutment Wall | 2 | Nos | 42.2 | 24.02.2025 | 31.03.2026 | 100% | 58.68 |  |  | 100% | 58.68 | Completed
| 2) Wing Wall | 1 | No |  |  |  | 100% |  |  |  | 100% |  | Completed
| 3) Gabian Wall | 3 | Nos |  |  |  | 100% |  |  |  | 100% |  | Completed
| 4) Steel Structure | 1 | No | 24.66 |  |  | 0% |  |  |  | 0% |  | Material Collection |  |  |  | 0.75
| TOTAL = |  |  | 66.86 |  |  | 75% | 58.68 |  |  | 75% | 58.68

## LRD II
MONTHLY PROGRESS REPORT FOR THE MONTH OF JUNE, 2025
Name of Division: Lunglei Road Division-II, Lunglei.
Source of Funding : PMGSY
Sl. No | Name of Work/Scheme | Unit | Approved Cost (Rs. In Lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last Month |  | Achievement of Works during the Month |  | Overall Cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 13
PMGSY
1 | Construction and Maintenance of Luangmual- Vaisam Road (0.00- 28.470 Kmp) |  | 4752.44 | 10.06.2019 | 31.3.2025 | 100% | 4728.45 | 0% | 0 | 100% | 4728.45 | Physically Completed | Open Tender
MONTHLY PROGRESS REPORT FOR THE MONTH OF JUNE, 2025
Name of Division: Lunglei Road Division-II, Lunglei
Sl. No | Name of Work/Scheme | Unit | Approved Cost (Rs. In Lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last Month |  | Achievement of Works during the Month |  | Overall Cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
I | SASCI
1 | Construction of Link Road 2nd Phase from Tawipui n-II to Mat Zau. | Rm | 25 | 27.12.2023 | 26.12.2024 | 100% | 0 | 0% | 0 | 100% | 0 | completed | Open Tender
2 | Improvement and Widening of Public Playground at Zobawk including Construction of Retaining wall | Rm | 35 | 27.12.2023 | 26.12.2024 | 0% | 0 | 0% | 0 | 0% | 0 | not yet started | Open Tender
Sr. Executive Engineer, PWD.,
Lunglei Road Division-II, Lunglei

## LLI Elec DIV
MONTHLY PROGRESSIVE REPORT FOR THE MONTH OF JUNE 2025
FOR WORKS UNDER STATE PLAN FUND
Name of Division : PWD Electrical Division,Lunglei.
Source of funding : State funding | [11 empty] | Rs in Lakhs
Sl No | Name of works/Project | Unit | Approval Cost(Rs in lakh) | Date of Commencement | Target Date of comp- letion | Cumulative Progress at the end of last month |  | Achievement of works during the Month |  | Overall Cumulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy. | Fin. | Phy. | Fin. | Phy. | Fin.
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
2 | 8443-108-PW Deposit-III
| a) I/E to DC Bungalow(Type-VI) at Siaha. |  | 8.2 |  |  | 100% |  | 0% |  | 100% |  | Completed | Departmental
| b) I/E to Laboratory Building at Civil Hospital, Lunglei. (SH: First Floor,Second Floor & Third Floor) |  | 24.5 |  |  | 75% |  | 25% |  | 100% |  | Completed | Departmental
3 | SASCI FUND ACCOUNT
| a) I/E to Szairep Community Hall at Sairep. |  | 1.273 |  |  | 0% |  | 60% |  | 60% |  | On going works | Departmental
| b) I/E to DM High School at Theiriat,Lunglei. |  | 2.194 |  |  | 70% |  | 10% |  | 80% |  | On going works | Departmental
| c) I/E to Market Building at Luangmual,Lunglei. |  | 5.034 |  |  | 80% |  | 5% |  | 85% |  | On going works | Departmental
| c) I/E to Circuit House at Hnahthial,Mizoram. |  | 31.59 |  |  | 70% |  | 0% |  | 70% |  | On going works | Departmental
FOR WORKS UNDER STATE PLAN FUND
Sl No | Name of works/Scheme | Estimated Amount | A/A or Not | Cumulative achievement as on March, 2016 |  | Target Date of comp- letion | Fund allocated during the year | Achievement during the Month |  | Cumulative achievement upto the end of the month during the year |  | Cumulative achievement since implementation of the project |  | Remarks
|  |  |  | Phy. | Fin. |  |  | Phy. | Fin. | Phy. | Fin. | Phy. | Fin.
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
2 | 4202 Co-On Education etc.
| b) Boys' Hostel for Govt. Lunglei College at Lunglei | 2.00 lacs | Yes | 20% |  |  | 2 | 20% |  | 40% |  | 40% |  | Completed
| c) Girls' Hostel for Govt. Lunglei College at Lunglei | 2.00 lacs | Yes | 20% |  |  | 2 | 20% |  | 40% |  | 40% |  | Completed
| d) I/E to Govt.Hnahthial College at Hnahthial | 10.56 lacs | Yes | 20% |  |  | 10.56 |  |  |  |  | 20% |  | On going works
| e) I/E to DIET Bldg at Saiha (Sangau Road) | 27.00 lacs | Yes | 20% |  |  | 27 |  |  | 40% |  | 40% |  | Completed
| f) I/E to DIET Bldg at Thingkah (Lawngtlai Dist.) | 27.00 lacs | Yes | 20% |  |  | 27 | 55% |  | 95% |  | 95% |  | Completed
| g) I/E to Indoor stadium at Chanmari, Lunglei | 15.00 lacs | Yes | Nil |  |  | 15 | 20% |  | 20% |  | 20% |  | On going works
| h) I/E to boys & girls Hostel for Govt.Saiha College bldg at Siaha | 2.00 lacs | Yes | 20% |  |  | 2 | 20% |  | 20% |  | 20% |  | On going works
| i) I/E to Infrastructure development of Lawngtlai College at Lawngtlai | 5.00 lacs | Yes | 20% |  |  | 5.00 lacs | 20% |  | 20% |  | 20% |  | On going works
3 | 4055 Co-On Police (P)
| d) I/E to Police Station at Vaseitlang | 8.00 lacs | Yes | Nil |  |  | 8 |  |  | 100% |  | 100% | 8.00 lacs | Completed
4 | 4408 Co-0n Food Storage and Warehousing
| a) I/E to Storage Godown at Kawlchaw | 3.00 lacs | Yes | Nil |  |  | 3 |  |  | 100% |  | 100% | 3.00 lacs | Completed
| b) I/E to Storage Godown at Vaseikai | 3.00 lacs | Yes | Nil |  |  | 3 |  |  | 100% |  | 100% | 3.00 lacs | Completed
| c) I/E Storage Godown at Hnahthial | 3.00 lacs | Yes | Nil |  |  | 3 | 5% |  | 100% |  | 100% | 3.00 lacs | Completed
| d) I/E Storage Godown at Sangau | 3.00 lacs | Yes | Nil |  |  | 3 | 5% |  | 100% |  | 100% | 3.00 lacs | Completed
| e) I/E Storage Godown at Lungsen | 3.00 lacs | Yes | Nil |  |  | 3 |  |  | 100% |  | 100% | 3.00 lacs | Completed
| f) I/E Storage Godown at Tlabung | 3.00 lacs | Yes | Nil |  |  | 3 |  |  | 100% |  | 100% | 3.00 lacs | Completed
5 | 4059 Co-On Public Works(P)
| a) I/E to Treasury Office at Saiha | 13.00 lacs | Yes | Nil |  |  | 13 |  |  | 100% |  | 100% | 13.00 lacs | Completed
6 | 8443-108-PW Deposit-III
| a) I/E to Govt Staff Qtrs (PWD), Type-II 4 units at Lunglei | 8.00 lacs | Yes | Nil |  |  | 8 | 10% |  | 100% |  | 100% | 8.00 lacs | Completed
| b) I/E to PHC at Haulawng | 10.00 lacs | Yes | Nil |  |  | 10 |  |  | 100% |  | 100% | 8.00 lacs | Completed
| c) I/E to PHC at Bunghmun | 10.00 lacs | Yes | Nil |  |  | 10 |  |  | 100% |  | 100% | 10.00 lacs | Completed
| d) I/E to PHC at Zobawk | 12.00 lacs | Yes | Nil |  |  | 12 | 40% |  | 90% |  | 90% |  | On going works
| e) I/E to PHC at Longpuighat | 11.00 lacs | Yes | Nil |  |  | 11 | 10% |  | 30% |  | 30% |  | On going works
7 | 4210 Co-On Medical
Construction of 100 Bedded Civil Hospital at Siaha
| (a) Power Distribution & Bed Lift | 114.83 lacs | Yes | 40% |  |  |  | 40% |  | 40% |  | 40% |  | On going works
(i) Power Distribution
(ii) SITC of 20 Passengers cum Stretcher Auto elevator
| (b) Solar Power | 146.00 lacs | Yes | 30% |  |  |  | 40% |  | 40% |  | 40% |  | On going works
(i) SITC of Solar Heating System (SHS)
(ii) SITC of 1X40 KWp SPV Power Plant
| (c) Fire fighting & VRF AC | 28.41 lacs | Yes | Nil |  |  |  | 10% |  | 10% |  | 10% |  | On going works
(i) SITC of fire detection/fighting system
(ii) SITC of 8 Tonnes (2+2+2+2) with 10 HP pure inverter out door unit with R410A Refrigerator AC VRF system
| (d) Internal Electrification main building | 61.40 lacs | Yes | Nil |  |  | 61.4 | 30% |  | 30% |  | 30% | 30 | On going works
| (e) I/E to Type-IV Quarter 3 units | 12.67 lacs | Yes | Nil |  |  |  | 10% |  | 10% |  | 10% |  | On going works
Executive Engineer, P.W.D.,
Electrical Division, Lunglei.

## LTI Div
Monthly Progressive Report for the Month of JUNE 2025
Name of Division |  | : | Lawngtlai Division
Slno | Name of Work/Project | Unit (km) | Approved Cost (Rs.in lakh) | Date of Commencement | Target Date of Completion | Cumulative Progress at the end of last month |  | Achievement of Work During the Month |  | Overall Cumulative Achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
NESIDS
1 | Improvement & Upgradation of Lawngtlai to Tuipui Ferry Road in the State of Mizoram under North East Special Infrastructure Developmant Scheme (NESIDS) | 10 | 2897.87 | 08.08.2019 | 30.06.2023 | 100% | 2666.68 |  |  | 100% | 2666.68 | Physically Completed | NIT
NABARD
2 | NABARD/ Improvement and Strengthening of Nalkawn - Chamdur Valley (NCV) (Section I & II) Road Under NABARD | 88.5 | 2616.41 | 09.08.2019 | 31.12.2024 | 71.04% | 1824.89 |  |  | 71.04% | 1824.89 | Work in progress | Item Rate
SASCI
1 | Improvement of Thlengang to River Chhimtuipui Road ( Construction of RCC Dock Along with Approach Slab) | 2Nos | 23.31 | 11.05.2023 | 31.05.2024 | 100% | 23.31 |  |  | 100% | 23.31 | Completed | Item Rate
2 | Widening of Lawngtlai to Sahrilui chhuah (Kolodyne River) Balu road | 7.5 km | 94.8 | 11.05.2023 | 31.05.2024 | 100% | 40.49 |  |  | 100% | 94.8 | Completed | Item Rate
3 | Improvement of Bethel veng to Chengkawllui Road at College veng, Lawngtlai | 1.6 Km | 90.84 | 11.05.2023 | 31.05.2024 | 100% | 90.83 |  |  | 100% | 90.83 | Completed | Item Rate
4 | Formation cutting of Vathuampui to Mautlang Road | 8.00Km | 70.47 | 11.05.2023 | 31.05.2024 | 100% | 70.42 |  |  | 100% | 70.42 | Completed | Item Rate
5 | Widening of Bungtlang 'S' to Saikhawthlir Road | 5.00Km | 56.15 | 11.05.2023 | 31.05.2024 | 100% | 50.13 |  |  | 100% | 50.13 | Completed | Item Rate
6 | Widening of Hmawngbu to Kakichhuah Road | 7.50Km | 61.99 | 11.05.2023 | 31.05.2024 | 100% | 61.97 |  |  | 100% | 61.97 | Completed | Item Rate
7 | Improvement of Diltlang to Chawngtelui road (Construction of Retaining wall at certain locations) | 51.50Km | 25.07 | 11.5.2023 | 31.05.2024 | 51.5 | 25.07 |  |  | 51.5 | 25.07 | Completed | Item Rate
8 | Resurfacing of NH-54 to DTO Office (including courtyard) at Chanmari, Lawngtlai | 50.00m | 6.997 | 11.5.2023 | 31.05.2024 | 50 | 6.997 |  |  | 50 | 6.997 | Completed | Item Rate
9 | Construction of Minor Bridge between Khawmawi Bazar veng to Khawmawi vengthar | 1No | 34.48 | 11.5.2023 | 31.05.2024 | 1 No | 34.47 |  |  | 1 No | 34.47 | Completed | Item Rate
10 | Blacktopping of Internal road at Lawngpuighat | 0.8Km | 81.65 | 11.5.2023 | 31.05.2024 | 0.8 | 81.63 |  |  | 0.8 | 81.63 | Completed | Item Rate
11 | Construction of Playground approach road at Thingfal Mamte veng | 420.00m | 19.49 | 11.5.2023 | 31.05.2024 | 420 | 19.49 |  |  | 420 | 19.49 | Completed | Item Rate
12 | Town extension Road at Electric Veng, Lawngtlai | 280Rm | 22.81 | 26.02.2024 | 31.12.2024 | 100% | 21.13 |  |  | 100% | 21.13 | Completed | Item Rate
13 | Construction of RDC road to Roliana Tuikhur at Lawngtlai | 122.00Rm | 9.96 | 26.02.2024 | 31.12.2024 | 100% | 9.45 |  |  | 100% | 9.45 | Completed | Item Rate
14 | Construction of Retaining Wall with steps at Bazar Thlanmual Road, Lawngtlai | 60.00Rm | 20 | 26.02.2024 | 31.12.2024 | 100% | 19.23 |  |  | 100% | 19.23 | Completed | Item Rate
15 | PCC Pavement of Internal Village Road at Lawngtlai L-IV | 150.00Rm | 10 | 26.02.2024 | 31.12.2024 | 100% | 9.6 |  |  | 100% | 9.6 | Completed | Item Rate
16 | Town extension Road at Lawngtlai L-III | 110.00Rm | 7.2 | 26.02.2024 | 31.12.2024 | 100% | 6.86 |  |  | 100% | 6.86 | Completed | Item Rate
17 | Construction of Culvert at Council veng to Bazar Road, Lawngtlai | 1No | 20 | 26.02.2024 | 31.12.2024 | 100% | 19.25 |  |  | 100% | 19.25 | Completed | Item Rate
18 | Village extension Road at Vaivakawn, Vawmbuk | 1.6 Km | 10 | 26.02.2024 | 31.12.2024 | 100% | 9.53 |  |  | 100% | 9.53 | Completed | Item Rate
19 | Internal Road Pavement (Approach road to PWD Rest House at Chawnhu) | 200.00Rm | 6.7 | 26.02.2024 | 31.12.2024 | 100% | 6.43 |  |  | 100% | 6.43 | Completed | Item Rate
20 | Construction of Side Drain near Piangliana Residence at Mualbu 'L' | 165.00Rm | 3.2 | 26.02.2024 | 31.12.2024 | 100% | 3.04 |  |  | 100% | 3.04 | Completed | Item Rate
21 | Approach Road Between PMGSY Road to Kawnkhua | 930.00Rm | 7.4 | 26.02.2024 | 31.12.2024 | 100% | 7.07 |  |  | 100% | 7.07 | Completed | Item Rate
22 | Construction of PCC Pavement from Nimaichondro House to Primary School at Ngunling khua | 80.00Rm | 4.5 | 26.02.2024 | 31.12.2024 | 100% | 3.96% |  |  | 100% | 3.96 | Completed | Item Rate
5054 Co under Road & Bridge
1 | Construction of Slab Culverts on chawnhu 132/33 Kv Power Station Road & Approach Road to Chengkawltlang at Council Veng, Lawngtlai under 5054 | 6 Nos | 24.76 | 28.11.2024 | 03.06.2025 | 6 Nos | 24.76 |  |  | 6 Nos | 24.76 | Completed | Item Rate
Sr. Executive Engineer, PWD,
Lawngtlai Division, Lawngtlai

## MMPD
MONTHLY PROGRESS REPORT UNDER MULTI MODAL PROJECT DIVISION FOR THE MONTH OF JUNE, 2025
SlNo | Name of Scheme | Unit | Approved Cost (in lakhs) | Date of Commencement | Target date of completion | Cumulative progress at the end of last month |  | Achievement of works during the month |  | Overall Cumulative achievement |  | Remarks | Mode of Tender
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
SASCI
Work under SASCI
NABARD
Work under NABARD
NEC
Work under NEC
PMGSY
Work under PMGSY
1 | Construction & Maintenance of Nalkawn to Rulkual Road (16.00-32.00) Kmp Group B (Sh: Construction of Road using Cold Mix Technology) | Km | 1088.47 | 12.12.2023 | 30.03.2025 | 100% | 791.94 | 0 | 0% | 100% | 791.94 | Work Physically completed on 27.03.2025. Original amount=1034.60 Deviation= 55.87
SEDP
Work under SEDP
CSS
Work under CSS
MoRTH
Work under MoRTH
1 | Construction of 2 Nos Reinforced Earth wall for restoration of road formation collapse at km 11.000 & km 11.050 and re-construction of Box culvert at km 11.000 on NH-502A in the state of Mizoram | mtr | 594.66 | 10.02.2025 | 30.11.2025 | 172 | 0 | 100 | 0 | 272 | 0 | On-going | EPC Mode
2 | STMC on NH 502A (KMMTTP) between Km 0.00 to Km 34.92 in the State of Mizoram | cum | 133.29 | 13.12.2024 | 12.12.2025 | 58400 | 0 | 5000 |  | 63400 | 0 | On-going | Item Rate. .
3 | STMC on NH 502A (KMMTTP) between Km 34.92 to Km 60.700 in the State of Mizoram | sqm | 99.38 | 13.12.2024 | 12.12.2025 | 154872.49 | 0 | 192.49 |  | 155064.98 | 0 | On-going | Item Rate
4 | STMC on NH 502A (KMMTTP) between Km 60.700 to Km 87.51 in the State of Mizoram | sqm | 106.31 | 13.12.2024 | 12.12.2025 | 161060.18 | 0 | 200.18 |  | 161260.36 | 0 | On-going | Item Rate
5 | Construction of new 2-lane Highway from Km 0.00-km 38.00 on NH 54 near Lawngtlai in Mizoram to support Kaladan Multi Modal Transit Transport Project in Phase A of SARDP-NE (pacakge-I) | Km | 43465 | 12.10.2010 | 12.10.2014 | 100% | 42680 |  |  | 100% | 42680 | Work physically Completed on 22.06.2023 | Item Rate
6 | Construction of new 2-lane Highway from km 38.00 to Km 70/00 in Mizoram to support Kaladan Multi Modal Transit Transport Project in Phase A of SARDP-NE (pacakge-II) | Km | 32224 | 12.10.2010 | 30.09.2014 | 100% | 30977 |  |  | 100% | 30977 | Work physically Completed on 30.04.2022 | Item Rate
7 | Construction of new 2-lane Highway from Km 70/00 to Km 99/00 in Mizoram to support Kaladan Multi Modal Transit Transport Project in Phase A of SARDP-NE (pacakge-III) | Km | 37459 | 12.10.2010 | 30.09.2014 | 100% | 36468 |  |  | 100% | 36468 | Work physically Completed on 23.06.2023 | Item Rate
Sr.Executive Engineer, PWD
Multi Modal Project Division
Lawngtlai: Mizoram

## NH I
Montly Progress Report under National Highway Division-I, PWD., June 2025
Sl. No | Name of Scheme | Unit | Approved Cost (in lakhs) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall Cummulative achievement |  | Remarks | Mode of Tender
| Name of Work/Project |  |  |  |  | Phy. | Fin. | Phy. | Fin. | Phy. | Fin.
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
SASCI
1 | Construction of Saiphal - Hortoki Road (13.800 km) | Phy in % Fin in lakh | 600 | 15.12.2023 | 15.12.2025 | 55% |  | 2% | 0 | 57% | 0 | On Going | Restricted tender
MoRTH
2 | Short Term Maintenance Contract on NH-44A/108 Rockfall Bypass Between km 0.000 to km 5.135 in the state of Mizoram. (Job No. RW/GHT/NH-44A/MZ/STMC/2024-25/2) | Phy in % Fin in lakh | 20.26 | 28.11.2024 | 27.11.2025 | 81.89% | 0 | 1.11% | 0 | 83% | 0 | On Going | Open Tender
3 | Short Term Maintenance Contract on NH-44A/108 Between km 16.670 to km 114.618 in the state of Mizoram. (Job No. RW/GHT/NH-44A/MZ/STMC/2024-25/1) | Phy in % Fin in lakh | 385.6 | 28.11.2024 | 27.11.2025 | 57.89% | 0 | 1.88% | 0 | 59.77% | 0 | On Going | Open Tender
4 | Performance Based Maintenance Contract (PBMC) under National Highway Division-I during 2023-24 on NH-6/54 between km 159/00 to km 178/00 (Length = 19.00 km) in the State of Mizoram. (Job No. 6/54-MZ-2023-24/124) | Phy in % Fin in lakh | 1891.98 | 29.08.2024 | 28.08.2029 | 73% | 850.13 | 1% | 0 | 74% | 850.13 | On Going | Open Tender
5 | Construction of Steel Arch (Semi Through) Bridge with Concrete Deck 90m Span Over River Tlawng at km 5.200 on NH-44A in the State of Mizoram on EPC Mode | Phy in % Fin in lakh | 4244 | 30.01.2021 | 26.3.2024 | 85.5% | 3163.92 | 1.5% | 474.5 | 87% | 3638.42 | On Going | Open Tender
PM-DevINE
6 | Construction of Bamboo Link Road from Lengpui to Saiphal Baboo Plantation (41 km) under PM-DevINE | Phy in % Fin in lakh | 6642 | 21.07.2024 | 19.01.2025 | 72.41% | 2847.58 | 2% | 0 | 74.41% | 2847.58 | On Going | Open Tender
Sr. Executive Engneer, PWD., National Highway Division-I Aizawl : Mizoram

## NH II
MONTHLY PROGRESS REPORT OF NH-150 FOR THE MONTH OF JULY 2025
Name of Division : National Highway Division -II | [10 empty] | Rupees in lakh
Source of funding : MoRTH Name of Contractor : M/S Ratna Infrastructure Projects Pvt.Ltd
Sl No | Name of Work/Project | Item Description | Unit | Approved Cost (Rs in Lakh) | Date of Commencement | Target of Completion | Cummulative Progress at the end of last Month |  | Achievement of works during the Month |  | Overall cummulative achievement upto 31.03.2023 |  | Remarks | Mode of Contract
[7 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Ordinary Repair (DPP) for short term maintenance from Km 0.00 to Km 42.80 and from Km 60.30 to Km 130.00 on NH-150 in the state of Mizoram. | Clearing pucca drains | Rm | ` 327.82 | 05.11.2021 | 02.02.2022 | 163149 | ` 325.68 | - | `0.00 | 163149 | ` 325.68 | Payment pending for RA-IV ` 80,705.70 and witheld amount from RA-III ` 20,35,155 Total ` 21,15,861 | Item rate
|  | Removal of Rank Vegetation | Sqm. |  |  |  | 1169920 |  | - |  | 1169920
|  | Scarifying Existing Granular Surface | Sqm. |  |  |  | 6789.35 |  | - |  | 6789.35
|  | WBM | Cum |  |  |  | 613.51 |  | - |  | 613.51
|  | Prime Coat | Sqm. |  |  |  | 4090.05 |  | - |  | 4090.05
|  | Tack Coat | Sqm. |  |  |  | 10879.4 |  | - |  | 10879.4
|  | Bituminous Macadam | Cum |  |  |  | 204.5 |  | - |  | 204.5
|  | Bituminous Concrete | Cum |  |  |  | 203.68 |  | - |  | 203.68
1 | Construction of 2 laning with paved shoulder flexible Pavement from Km 42.80 to Km 60.30 of NH- 150 road during 2016-17 within Mizoram State under NH(O) Scheme. (Job No. & Date of Sanc Original / Revised : 150/MZ/2016-17/107) | Earthwork up to top of the subgrade | Km | `20594.82 | 29.11.2017 | 22.05.2021 | 17.5 | `14000.00 | - | `0.00 | 17.5 | `14000.00 | Works under maintenance | EPC Mode
|  | Granular work(WMM) | Km |  |  |  | 17.5 |  | - |  | 17.5
|  | Granular work(GSB) | Km |  |  |  | 17.5 |  | - |  | 17.5
|  | Dense Bituminous Macadam (DBM) | Km |  |  |  | 17.5 |  | - |  | 17.5
|  | Bituminous Concrete | Km |  |  |  | 17.35 |  | - |  | 17.35
|  | Pipe Culvert | Nos. |  |  |  | 36 |  | - |  | 36
|  | RCC Box Culvert | Nos. |  |  |  | 72 |  | - |  | 72
|  | Road side drains. | m |  |  |  | 17189 |  | - |  | 17189
|  | Crash barrier/ "w" Metal Beam Crash Barrier | m |  |  |  | 1000 |  | - |  | 1000
|  | Km stone, 5th km stone, & hectometre stones | Km |  |  |  | 17.5 |  | - |  | 17.5
|  | Traffic sign | Km |  |  |  | 17.5 |  | - |  | 17.5
|  | Direction and Place identification signs upto 0.9 sqm size signboard | Km |  |  |  | 17.5 |  | - |  | 17.5
|  | Boundary stone, | Km |  |  |  | 17.5 |  | - |  | 17.5
|  | Chute drain | m |  |  |  | 664 |  | - |  | 664
|  | Breast wall | m |  |  |  | 650 |  | - |  | 650
|  | Retaining wall | m |  |  |  | 1894 |  | - |  | 1894
|  | Gabion wall | m |  |  |  | 150 |  | - |  | 150
|  | Toe wall | m |  |  |  | 680 |  | - |  | 680
|  | Trafic Divertion | Km |  |  |  | 17.5 |  | - |  | 17.5
|  | Pavement marking | Km |  |  |  | 17.5 |  | - |  | 17.5
1 | Reconstruction of single lane pavement from Km 130.00 to Km 140.00 on NH-150 in the State of Mizoram on EPC Mode (Job No. 150/MZ/2019-20/119) | Widening | Km | `3440.95 | 23.11.2020 | 26.05.2023 | 0.98 | `2441.16 | - | `0.00 | 0.98 | `2441.16 | Work under Defect Liability period | EPC Mode
|  | Earthwork & subgrade | Km |  |  |  | 9.965 |  | - |  | 9.965
|  | GSB | Km |  |  |  | 9.965 |  | - |  | 9.965
|  | WBM 1s Layer | Rm |  |  |  | 9965 |  | - |  | 9965
|  | WBM 2nd Layer | Rm |  |  |  | 9965 |  | - |  | 9965
|  | BM | Rm |  |  |  | 9965 |  | - |  | 9965
|  | MSS | Rm |  |  |  | 9965 |  | - |  | 9965
|  | Road Safety | [6 empty] | -
|  | (1) Installation of Crash Barrier | Rm |  |  |  | 505 |  | - |  | 505
|  | (2) Erection of KM Stone | Nos. |  |  |  | 10 |  | - |  | 10
|  | (3) Road Marking | sqm. |  |  |  | 2182.4 |  | - |  | 2182.4
|  | (4) Road Sign board | Nos. |  |  |  | 24 |  | - |  | 24
|  | Slab Culvert | No |  |  |  | 5 |  | - |  | 5
|  | Side Drain | Km |  |  |  | 9.335 |  | - |  | 9.335
|  | R/Wall | Rm |  |  |  | 91 |  | - |  | 91
|  | G/Wall | Rm |  |  |  | 36 |  | - |  | 36
1 | Consultancy Services for Project Management including Preparation of Feasibility Study/Detailed Project report for two laning with Paved Shoulders of stretches from Km 0/00 to Km 42/80 and from Km 60/00 to Km 140/00 on NH-150 NH(O) Package No. DPR/MZ/NER/2015/13 |  | 166.03 | 24.06.2017 | 20.05.2018 | 80% | 3918485 | 0% | 0 | 80% | 3918485 |  | MoRTH
1 | Short Term Maintenance Contractfor NH-6 (150 ti 180/000 Kmp) i.e : 30 length for the year 2024-25 under National Highway Division- II, Aizawl in the state of Mizoram. (Job No.RW/GHT/NH-6/MZ/STMC/MZ/2024-25/3) | Clearing, cleaning, deepening and reshaping of road side unlined/kaccha drains ..etc | sqm | 11603496 | 20.12.2024 | 19.12.2025 | 30000 | 2250000 | 0 | 0 | 30000 | 2250000 | Ongoing | Item Rate
|  | Clearing slab/box type culverts and pipe culverts including clearing, cleaning and reshaping of upstream and down stream faces of these culverts within right of way. | m |  |  |  | 15 | 244485 | 0 | 0 | 15 | 244485
|  | Removal of rank vegetation/weeds..etc | Rm |  |  |  | 90000 | 106200 | 0 | 0 | 90000 | 106200
|  | Providing Random Rubble mansory in cement mortar 1:3 for drains,protection walls, boundary walls etc | cum |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Providing and fixing single faced W-Beam metal crash barrier | Sqm/ month |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Amounut | [5 empty] | 2600685 |  | 0 |  | 2600685

## NH III
MONTHLY PROGRESS REPORT FOR NATIONAL HIGHWAY WORKS FOR THE MONTH OF JUNE,2025
DIVISION : NATIONAL HIGHWAY DIVISION-III, THINGDAWL
Strengthening/ Construction/widening/ to 2-lane from km 89/00 to km 105/00 of NH-154(New NH-6) under NH Division-III in the state of Mizoram for the year 2022-23 (Length=16 km)
Road | MNB | Other Works |  | Total |  |  |  | Cost of Project |  | 2025-06-25 |  | Cum Fin.Prog Rs.in lakh
431225100 | 24426000 | 75348900 |  | 531000000 |  |  |  | 531000000
Description of Works |  | Weightage Cost (%) | Item weightage (%) | Item Amount | Qty | unit | Unit Rate | Phy Prog (Km) | Phy Prog % | Value of Phy Prog (Cr.) | Phy Prog (%)
|  |  | A- Widening and strengthening of existing road | [8 empty] | 4646.43
1.Scarifying |  | 81.21% | 0.03% | 129367.53 | 1.68 | Km | 77004.4821 | 1.68 | 0.03% | 129367.53 | 0.02436%
2.Earthwork upto top of subgrade |  |  | 22.06% | 95128257.06 | 6.28 | Km | 15147811.6338 | 6.28 | 22.06% | 95128257.06 | 17.91%
3.Sub-Base course |  |  | 16.93% | 73006409.43 | 6.28 | Km | 11625224.4315 | 6.015 | 16.22% | 69925724.9556 | 13.17%
3.Non-Bituminous Base Course(WMM for Km 89.00 - Km 99.500) |  |  | 12.29% | 52997564.79 | 6.28 | Km | 8439102.6736 | 6 | 11.74% | 50634616.0414 | 9.536%
4.Non-Bituminous Base Course (WBM for Km 99.500 to Km 105.00) |  |  | 0.64% | 2759840.64 | 5.5 | Km | 501789.2073 | 5.5 | 0.64% | 2759840.64 | 0.5197%
5.Bituminous Base Course |  |  | 23.52% | 101424143.52 | 11.78 | Km | 8609859.382 | 11.376 | 22.71% | 97945760.3297 | 18.45%
6.Wearing Coat |  |  | 17.37% | 74903799.87 | 16 | Km | 4681487.4919 | 15.3 | 16.61% | 71626758.6257 | 13.49%
Extension of HP Culvert |  |  | 0.52% | 2242370.52 | 3 | Nos. | 747456.84 | 3 | 0.52% | 2242370.52 | 0.4223%
RCC Box cell culverts |  |  | 4.25% | 18327066.75 | 14 | Nos. | 1309076.1964 | 14 | 4.25% | 18327066.75 | 3.451%
Repair of existing culvert @ 93.250 km by construction of wing wall |  |  | 2.39% | 10306279.89 | 1 | Nos. | 10306279.89 | 1 | 2.39% | 10306279.89 | 1.941%
[7 empty] | A2-New Minor Bridge |  |  |  | 0%
Widening and Repair of Minor Bridge |  | 4.6% | [5 empty] | 0 |  |  | 0%
Repair of Minor bridge by construction of wing wall |  |  | 13.87% | 3387886.2 | 1 | Nos. | 3387886.2 | 1 | 13.87% | 3387886.2 | 0.638%
New Minor Bridge | [10 empty] | 0%
(i) Foundation & Sub-Structure |  |  | 41.2% | 10063512 | 1 | Nos. | 10063512 | 1 | 41.2% | 10063512 | 1.895%
(ii) Super-Strcuture |  |  | 32.97% | 8053252.2 | 1 | Nos. | 8053252.2 |  |  |  | 0%
(iii) Approaches |  |  | 11.96% | 2921349.6 | 1 | Nos. | 2921349.6 |  |  |  | 0%
[7 empty] | Other Works |  |  |  | 0%
CRM Retaining wall |  | 14.19% | 24.45% | 18422806.05 | 433 | Rm | 42546.8962 | 433 | 24.45% | 18422806.05 | 3.469%
RRM Retaining wall |  |  | 39.64% | 29868303.96 | 390 | Rm | 76585.3948 | 390 | 39.64% | 29868303.96 | 5.625%
Lined side drain |  |  | 24.7% | 18611178.3 | 5000 | Rm | 3722.2357 | 4000 | 19.76% | 14888942.64 | 2.804%
RCC Crash barrier |  |  | 6.52% | 4912748.28 | 720 | Rm | 6823.2615
Traffic Signages |  |  | 2.1% | 1582326.9 | 16 | Km | 98895.4313
Road Markings |  |  | 1.54% | 1160373.06 | 16 | Km | 72523.3163 | 15 | 1.444% | 1087849.7438 | 0.2049%
Km Stones |  |  | 0.08% | 60279.12 | 16 | Km | 3767.445
Boundary Pillar |  |  | 0.69% | 519907.41 | 16 | Km | 32494.2131
Road Delineators |  |  | 0.28% | 210976.92 | 16 | Km | 13186.0575
93.55%
CHANGE OF SCOPE
Junction Improvement |  |  |  | 1918225.9055 | 1 | Nos. | 1918225.9055 | 1 | 100% | 1918225.9055
Restoration of MNB at km:89+170 |  |  |  | 0
Construction of Toe wall |  |  |  | 339837.3984 | 12 | RM | 28319.7832 | 0 | 0%
Construction of wing wall |  |  |  | 1372694.1246 | 20 | RM | 68634.7062 | 0
Sub-Surface Drain |  |  |  | 10927494.1592 | 410 | RM | 26652.4248 | 410 | 100% | 10927494.1592
Hume Pipe Culvert |  |  |  | 5264439.8276 | 4 | Nos | 1316109.9569 | 4 | 100% | 5264439.8276
Breast Wall |  |  |  | 6655631.0908 | 90 | RM | 73951.4566 | 90 | 100% | 6655631.0908
|  |  | Total: | 26478322.5062 | [5 empty] | 24765790.9832
Strengthening of Km 10.00 to Km 33.00 (Length 23.00Km) on NH-306A including Strengthening & Construction of Retaining Walls and culverts and Strengthening of 3 Nos. of Bailey Bridges in the State of Mizoram
Road | MNB | Other Works |  | Total |  |  |  | Cost of Project |  | 2025-05-01 |  | Cum Fin.Prog Rs.in lakh
381352370 | 3735900 | 30011730 |  | 415100000 |  |  |  | 531000000
Description of Works |  | Weightage Cost (%) | Item weightage (%) | Item Amount (Cr.) | Quantity | unit | Unit Rate | Phy Prog (Km) | Phy Prog % | Value of Physical Progress (Cr.) | Phy Prog (%)
|  |  | A- Widening and strengthening of existing road | [8 empty] | Completed and DLP is going on
1.Earthwork upto top of subgrade |  | 91.87% | 1.9% | 7245695.03 | 7 | Km | 1035099.29 | 7 | 1.9% | 7245695.03 | 1.9%
2.Sub-Base course |  |  | 11.44% | 43626711.128 | 7 | Km | 6232387.304 | 7 | 11.44% | 43626711.128 | 11.44%
3.Non-Bituminous Base Course(WMM for Km10.00 - Km17.00) |  |  | 14.76% | 56287609.812 | 7 | Km | 8041087.116 | 7 | 14.76% | 56287609.812 | 14.76%
4.Non-Bituminous Base Course (WBM for Km 17.00 to Km 33.00) |  |  | 17.83% | 67995127.571 | 16 | Km | 4249695.4732 | 16 | 17.83% | 67995127.571 | 17.83%
5.Bituminous Base Course |  |  | 28.91% | 110248970.167 | 23 | Km | 4793433.4855 | 23 | 28.91% | 110248970.167 | 28.91%
6.Wearing Course |  |  | 17.59% | 67079881.883 | 23 | Km | 2916516.6036 | 23 | 17.59% | 67079881.883 | 17.59%
7. Earthen Shoulder |  |  | 0.67% | 2555060.879 | 23 | Nos. | 111089.6034 | 23 | 0.67% | 2555060.879 | 0.67%
RCC Box cell culverts |  |  | 6.9% | 26313313.53 | 36 | Nos. | 730925.3758 | 36 | 6.9% | 26313313.53 | 6.9%
Repair of Minor Bridge
Repair of Minor bridge |  | 0.9% | 100% | 3735900 | 3 | Nos. | 1245300 | 3 | 100% | 3735900 | 100%
Other Works
Retaining wall |  | 7.23% | 86.16% | 25858106.568 | 575 | Rm | 44970.6201 | 575 | 86.16% | 25858106.568 | 86.16%
Unlined side drain |  |  | 6.34% | 1902743.682 | 23000 | Rm | 82.728 | 23000 | 6.34% | 1902743.682 | 6.34%
Road Markings |  |  | 4.39% | 1317514.947 | 23 | km | 57283.2586 | 23 | 4.39% | 1317514.947 | 4.39%
Traffic Signages |  |  | 2.92% | 876342.516 | 108 | Km | 8114.2826 | 108 | 2.92% | 876342.516 | 2.92%
Km Stone |  |  | 0.19% | 57022.287 | 16 | Km | 3563.8929 | 16 | 19% | 57022.287 | 19%
| Total: |  | 415100000 | [5 empty] | 415100000
Short term Maintenance Contract on KM 0/00 to 10/00 and Km 33/00 to 45/00 (22Km) on NH 306A in the state of Mizoram (Job No.RE/GHT/STMC/MZ/23-24/7).
Road | MNB | Other Works |  | Total |  |  |  | Cost of Project |  | 2025-06-25 |  | Cum Fin.Prog Rs.in lakh
34343701 |  |  |  | 34343701 |  |  |  | 34343701
Description of Works |  | Weightage Cost (%) | Item weightage (%) | Item Amount (Cr.) | Quantity | unit | Unit Rate | Phy Prog (Km) | Phy Prog % | Value of Physical Progress (Cr.) | Phy Prog (%)
|  |  | A- Widening and strengthening of existing road | [8 empty] | 300.66
1. Providing spot reconditioning, reconstruction etc |  |  | 0.02913% | 10005 | 500.25 | m3 | 20 | 500.25 | 0.02913% | 2500 | 0.02913%
2.Removal of rank vegetation/weds and undesireable vegetation from shoulder etc. |  |  | 8.251% | 2833696 | 354212 | m2 | 8 | 354212 | 8.251% | 708424 | 8.251%
3.Clearing, cleaning, deepening and reshaping etc. |  |  | 2.562% | 880000 | 44000 | m | 20 | 44000 | 2.562% | 135384.8 | 2.562%
4.Providing and marking of hot applied thermoplastic compound 2.50mm thick |  |  | 15.9% | 5460000 | 4200 | m2 | 1300 | 4200 | 15.9% | 5460000 | 15.9%
5.Providing and fixing single faced W-beam metal crash barrier |  |  | 69.18% | 23760000 | 3300 | Rm | 7200 | 3300 | 69.18% | 23760000 | 69.18%
6.Providing treatmnet and repair of pot holes/ruts of any depth etc. |  |  | 4.076% | 1400000 | 7 | sqm/m | 200000 | 0.1 | 0.05823% |  | 0.05823%
| Total: |  | 100% | 34343701 | [5 empty] | 30066308.8 | 95.98%
Sr.Executive Engineer,PWD.,
National Highway Division-III,
Thingdawl, Mizoram

## PD I
MONTHLY PROGRESS REPORT UNDER EXECUTIVE ENGINEER, PROJECT DIVISION- I, PWD FOR JUNE 2025
Sl. No. | Name of Scheme | Unit | Approved Cost (in lakhs) | Date of Commencement | Target date of completion | Cummulative progress at the end of last month |  | Achievement of work during the month |  | Overall cummulative achievement |  | Remarks | Mode of Tender
| Name of Work/Project |  |  |  |  | Phy (%) | Fin (₹) | Phy (%) | Fin (₹) | Phy (%) | Fin (₹)
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) | (10) | (11) | (12) | (13) | (14)
A. NEC
1 | C/o of Patient Lodging at Mawdiangdiang near NEIGRIMS, Shillong | 1 | 419.67 | 9.9.21 | 31.7.24 | 85% | 167.87 | 0.5% | 0 | 85.5% | 167.87 | EOT upto 9.9.25 | Item rate
2 | Co/ Veterinary Information and Resource Centre at Aizawl | 1 | 339.25 | 25.9.23 | 25.9.25 | 67% | 124.1031 | 4% | 0 | 71% | 124.1031 |  | Item rate
3 | C/o Aizawl Institute of Arts & Music for the NER, Tuivamit Tlang, Aizawl | 1 | 590.23 | 4.9.23 | 4.9.25 | 82% | 230.1064 | 2% | 0 | 84% | 230.1064 |  | Item rate
4 | Establishment of Central Medical Warehouse at Aizawl, Mizoram | 1 | 1101.11 | 14.8.23 | 14.8.25 | 38% | 140.1864 | 1% | 0 | 39% | 140.1864 |  | Item rate
5 | Infrastructure Development of Biotechnology Cell in Mizoram (C/O Building at MINECO | 1 | 188.66 | 10.7.23 | 10.1.25 | 44.6% | 69.55 | 0.2% | 0 | 44.8% | 69.55 | EOT upto 22.10.25 | Item rate
B. SASCI
6 | C/o Central Medical Warehouse at ZMC, Approach Road SH: Approach Road | 1 | 150 | 16.12.23 | 16.12.24 | 65% | 47.428 | 1% | 0 | 66% | 47.428 |  | Item rate
7 | C/o Tuikual 'S' Mini Sport Complex | 2 | 413.16 | 16.12.23 | 16.12.24 | 99.5% | 184.78 | 0.5% | 0 | 100% | 184.78 | EOT upto 16.3.2025 | Item rate
8 | C/o FCS&CA 1500MT Capacity Godown at Sairang | 1 | 921.07 | 7.4.23 | 7.4.26 | 60% | 147.7812 | 2% | 0 | 62% | 147.7812 |  | Item rate
9 | Constn. of Govt. Staff Qtrs. (Block-C) at DIET Complex, Chaltlang. | 1 | 544 | 29.4.23 | 29.10.25 | 74.8% | 271.5559 | 4.4% | 0 | 79.2% | 271.5559 |  | Item rate
10 | Re-construction of Central Jail, Aizawl | 1 | 1329 | 16.5.25 | 16.5.26 | 0% | 0 | 0.5% | 0 | 0.5% | 0 |  | Item rate
12 | Construction of Working Women Hostel, Khatla | 1 | 2972 | 24.4.25 | 24.4.26 | 0% | 0 | 5% | 0 | 5% | 0 |  | Item rate
13 | Construction of New Campus for Govt. Aizawl West College Building |  |  |  |  | 0% | 0 | 3% | 0 | 3% | 0 |  | Item rate
| a. Administrative Building | 1 | 572.97 | 9.5.25 | 9.5.26
| b. Academic Building | 1 | 201.36 | 9.5.25 | 9.5.26
C. SEDP
13 | Construction of High Court Parking Building at MINECO | 1 | 1960 | 2.7.20 | 29.8.24 | 100% | 1573.4952 | 0% | 1.7081 | 100% | 1575.2033 | EOT upto 17.5.2025 | Item rate
D. NABARD
14 | C/O 24 Warehouses with associated Infrastructure in 23 locations in Mizoram under NABARD (Group-II Zuangtui/ Sairang) | 1 | 440.97 | 17.7.23 | 31.3.25 | 85% | 152.9176 | 5% | 0 | 90% | 152.9176 |  | Item rate
Executive Engineer, PWD
Project Division-I
Aizawl, Mizoram

## PD II
MONTHLY PROGRESS REPORT FOR THE MONTH OF JUNE, 2025
Name of Division: Project Division-II, P.W.D
Source of Funding: SASCI
1 | Contruction of Civil SDO Qrts Type - IV at Kawnpui | % | 78.08 | 15.05.2025 | 15.5.2026 | 0% | 0 | 1% | 0 | 1% | 0 | Procurement Starts | Item Rate
2 | Contruction of Civil SDO Qrts Type - IV at Bairabi | % | 82.32 | 15.05.2025 | 15.5.2026 | 0% | 0 | 2% | 0 | 2% | 0 | Procurement Starts | Item Rate
3 | Re-Construction of District Prison at Mamit | % | 453.37 | 23.04.2025 | 23.04.2026 | 0% | 0 | 0.5% | 0 | 0.5% | 0 | Work in Progress | Item Rate
4 | Re-Construction of District Prison at Kolasib | % | 647.64 | 15.05.2025 | 15.05.2026 | 0% | 0 | 3% | 0 | 3% | 0 | Work in Progress | Item Rate
5 | Contruction of Working Women Hostel at ZMC / H Falkawn, Mizoram | % | 2634.06 | 14.05.2025 | 14.5.2026 | 0% | 0 | 1.5% | 0 | 1.5% | 0 | Work in Progress | Item Rate
6 | Contruction of Working Women Hostel at Thenzawl | % | 1100 | 15.05.2025 | 15.05.2026 | 0% | 0 | 1% | 0 | 1% | 0 | Work in Progress | Item Rate
7 | Contruction of Directorate of Economics & Statistics Office at MINECO, Aizawl | % | 207 | 30.04.2025 | 30.04.2026 | 0% | 0 | 0.5% | 0 | 0.5% | 0 | Work in Progress | Item Rate
Sr. Executive Engineer, PWD.,
Project Division-II, Aizawl

## PD III
MONTHLY PROGRESS REPORT FOR THE MONTH OF JUNE 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Gov't Serchhip College ( Sh: Administrative Block) | % | 650 | 27.2.2023 | 27.2.2025 | 73% | 207.57 | 5% | 0 | 78% | 207.57 | Work in Progress | PWD Form - 8
Sr.Executive Engineer, PWD., Project Division - III Aizawl, Mizoram
MONTHLY PROGRESS REPORT FOR THE MONTH OF JUNE 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Const. of Football ground and volleyball court at Vapar, Selam, tualcheng, Hnahla. Hmunhmeltha | % | 203 | 13.10.2023 | 13.10.2024 | 100% | 99.3 | 0% | 0 | 100% | 99.3 | 100% of 1st priority work completed. | PWD Form - 8
Sr.Executive Engineer, PWD., Project Division - III Aizawl, Mizoram
MONTHLY PROGRESS REPORT FOR THE MONTH OF JUNE 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Const. of Khawbung futsal ground, gallery, Roofing, Lighting & Laying of Artificial Turf | % | 255.5 | 14.10.2023 | 7.2.2025 | 100% | 111.35 | 0% | 0 | 100% | 111.35 | 100% of 1st priority work completed. | PWD Form - 8
Sr.Executive Engineer, PWD., Project Division - III Aizawl, Mizoram
MONTHLY PROGRESS REPORT FOR THE MONTH OF JUNE 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Const. of Community Hall at Dulte & Chhawrtui | % | 271 | 13.10.2023 | 13.10.2024 | 70% | 72.85 | 3% | 0 | 73% | 72.85 | Work in progress | PWD Form - 8
Sr.Executive Engineer, PWD., Project Division - III Aizawl, Mizoram
MONTHLY PROGRESS REPORT FOR THE MONTH OF JUNE 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Development of Community Centre at Zotlang, Champhai (Sh: Cons of Market Building cum community Hall & Futsal Ground) | % | 215 | 14.10.2023 | 7.2.2025 | 99.8% | 86.49 | 0% | 0 | 99.8% | 86.49 | 100% of 1st priority work completed. | PWD Form - 8
Sr.Executive Engineer, PWD., Project Division - III Aizawl, Mizoram
MONTHLY PROGRESS REPORT FOR THE MONTH OF JUNE 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Additional works for const. of General Nursing Midwifery (GNM) hostel and Nursing Hostel at champhai | % | 438 | 13.10.2023 | 7.2.2025 | 100% | 264.07 | 0% | 0 | 100% | 264.07 | Work in progress | PWD Form - 8
Sr.Executive Engineer, PWD., Project Division - III Aizawl, Mizoram
MONTHLY PROGRESS REPORT FOR THE MONTH OF JUNE 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Const of Public Playground at Keitum, Lungchhuan | % | 250 | 13.10.2023 | 13.10.2024 | 100% | 96.96 | 0% | 0 | 100% | 96.96 | 100% of 1st priority work completed. | PWD Form - 8
Sr.Executive Engineer, PWD., Project Division - III Aizawl, Mizoram
MONTHLY PROGRESS REPORT FOR THE MONTH OF JUNE 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Const. of Gov't Building at Serchhip District (Sh: PWD staff qtrs, Extension of Gov't Serchhip College and Kitchen cum Dining at PTS, Thenzawl, Mizoram) | % | 362 | 13.10.2023 | 13.10.2024 | 97% | 182.51 | 2% | 0 | 99% | 182.51 | Work in progress | PWD Form - 8
Sr.Executive Engineer, PWD., Project Division - III Aizawl, Mizoram
MONTHLY PROGRESS REPORT FOR THE MONTH OF JUNE 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Const of Community Resource Center at Baktawng and Chhuanthar | % | 350 | 13.10.2023 | 13.10.2024 | 100% | 139.9 | 0% | 0 | 100% | 139.9 | 100% of 1st priority work completed. | PWD Form - 8
Sr.Executive Engineer, PWD., Project Division - III Aizawl, Mizoram
MONTHLY PROGRESS REPORT FOR THE MONTH OF JUNE 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Const of Community Hall at Khawzawl Vengthar, Arro Village, Khawzawl Dinthar and Khawhai South | % | 209 | 13.10.2023 | 13.10.2024 | 100% | 79.25 | 0% | 0 | 100% | 79.25 | 100% of 1st priority work completed. | PWD Form - 8
| ` | [8 empty] | Sr.Executive Engineer, PWD., Project Division - III Aizawl, Mizoram
MONTHLY PROGRESS REPORT FOR THE MONTH OF JUNE 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Gov't Quarters (General pool) under SASCI 2024 - 2025 at Serchhip | % | 1300 | 24.4.2025 | 24.4.2026 | 0% | - | 5% | - | 5% | - | Work in progress | -
| a) Type - IV & III Quarters (Design - A) at P & E Veng (Treasury Department Site) |  | 344.74 |  |  | 0% | - | 5% | - | 5% | -
| ` | [8 empty] | Sr.Executive Engineer, PWD., Project Division - III Aizawl, Mizoram
MONTHLY PROGRESS REPORT FOR THE MONTH OF JUNE 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Gov't Quarters (General pool) under SASCI 2024 - 2025 at Serchhip | % | 1300 | 24.4.2025 | 24.4.2026 | 0% | - | 5% | - | 5% | - | Work in progress | -
| b) Type - IV & III Quarters (Design - B) at P & E Veng ( Treasury Department Site) |  | 296.54 |  |  | 0% | - | 5% | - | 5% | -
| ` | [8 empty] | Sr.Executive Engineer, PWD., Project Division - III Aizawl, Mizoram
MONTHLY PROGRESS REPORT FOR THE MONTH OF JUNE 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Gov't Quarters (General pool) under SASCI 2024 - 2025 at Serchhip | % | 1300 | 24.4.2025 | 24.4.2026 | 0% | - | 5% | - | 5% | - | Work in progress | -
| c) Type - IV & III Quarters (Design - A) at P & E Veng ( Soil & Water Conservation Department Site) |  | 351.94 |  |  | 0% | - | 5% | - | 5% | -
| ` | [8 empty] | Sr.Executive Engineer, PWD., Project Division - III Aizawl, Mizoram
MONTHLY PROGRESS REPORT FOR THE MONTH OF JUNE 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Gov't Quarters (General pool) under SASCI 2024 - 2025 at Serchhip | % | 1300 | 24.4.2025 | 24.4203 | 0% | - | 5% | - | 5% | - | Work in progress | -
| d) Type - IV Quarters ( 3 Units) at Hospital Complex, Serchhip, Mizoram |  | 306.46 |  |  | 0% | - | 5% | - | 5% | -
| ` | [8 empty] | Sr.Executive Engineer, PWD., Project Division - III Aizawl, Mizoram
MONTHLY PROGRESS REPORT FOR THE MONTH OF JUNE 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Circuit House at under DC Office (SH: Construction of Circuit House at Serchhip) | % | 652 | 16.4.2025 | 16.4.2026 | 0% | - | 5% | - | 5% | - | Work in progress | -
| ` | [8 empty] | Sr.Executive Engineer, PWD., Project Division - III Aizawl, Mizoram
MONTHLY PROGRESS REPORT FOR THE MONTH OF JUNE 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Re-construction of District Jail, Serchhip | % | 372.4 | 8.5.2025 | 8.5.2026 | 0% | - | 1% | - | 1% | - | Work in progress | -
| ` | [8 empty] | Sr.Executive Engineer, PWD., Project Division - III Aizawl, Mizoram
MONTHLY PROGRESS REPORT FOR THE MONTH OF JUNE 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Re-construction of District Jail, Champhai | % | 826.88 | 16.4.2025 | 16.4.2026 | 0% | - | 2% | - | 2% | - | Work in progress | -
| ` | [8 empty] | Sr.Executive Engineer, PWD., Project Division - III Aizawl, Mizoram
MONTHLY PROGRESS REPORT FOR THE MONTH OF JUNE 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Re-construction of District Jail, Saitual | % | 45.43 | 29.4.2025 | 29.4.2026 | 0% | - | 1% | - | 1% | - | Work in progress | -
| ` | [8 empty] | Sr.Executive Engineer, PWD., Project Division - III Aizawl, Mizoram
MONTHLY PROGRESS REPORT FOR THE MONTH OF JUNE 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Working Women Hostels(Champhai), Mizoram. | % | 1366 | - | - | - | - | - | - | - | - | Work Order issued. Site not yet finalised. | -
| ` | [8 empty] | Sr.Executive Engineer, PWD., Project Division - III Aizawl, Mizoram
MONTHLY PROGRESS REPORT FOR THE MONTH OF JUNE 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Circuit House at under DC Office (SH: Construction of Circuit House at Saitual) | % | 640 | 16.4.2025 | 16.4.2026 | 0% | - | 3% | - | 3% | - | Work in progress | -
| ` | [8 empty] | Sr.Executive Engineer, PWD., Project Division - III Aizawl, Mizoram
MONTHLY PROGRESS REPORT FOR THE MONTH OF JUNE 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | NLCPR
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Name of work : Construction of Community Hall at various places in Mizoram ( Sh: Const. Of Community Hall at Saitual, Thingsulthliah, Maite, Tualbung, Lungpher, Buhban, Lenchim, Chawrtui and Puilo). | % | 206.49 | 22.2.2012 | 30.11.2019 |  |  |  |  | 100% | 186.01 | Completed and balance fund of Rs.20.48 (Rs. 16.35 Lakhs NLCPR + Rs. 4.13 Lakhs SMS) awaited for clearing liabilities.
Sr.Executive Engineer, PWD., Project Division - III Aizawl, Mizoram
MONTHLY PROGRESS REPORT FOR THE MONTH OF JUNE 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | SPP
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Circuit House at Serchhip | % | 358.18 | - | - | - | - | - | - | - | - | Work not executed due to various reasons. Fund received Rs. 358.18 lakhs is kept at D-III
Sr.Executive Engineer, PWD., Project Division - III Aizawl, Mizoram
MONTHLY PROGRESS REPORT FOR THE MONTH OF JUNE 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | SCA/SASCE
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Improvement/Upgradation of Operational/Non-operational facilitiies of Lengpui Airport, (Sh: Renovation of terminal building). | % | 2124 | 10.3.2021 | 31.12.2024 | 98.8% | 1773.36 | 0.1% | 0 | 98.9% | 1773.36 | Work in progress | PWD Form - 8
Sr.Executive Engineer, PWD., Project Division - III Aizawl, Mizoram
MONTHLY PROGRESS REPORT FOR THE MONTH OF JUNE 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | ECRP - II
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of 50 Bedded critical care block at Champhai District Hospital, Mizoram | % | 1346.4 | 4.8.2023 | 4.2.2026 | 60% | 494.58 | 5% | 0 | 65% | 494.58 | Work in Progress | PWD Form - 8
Sr.Executive Engineer, PWD., Project Division - III Aizawl, Mizoram
MONTHLY PROGRESS REPORT FOR THE MONTH OF JUNE 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | NABARD - WIF
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of 24 Warehouses with associated infrastructure in 23 locations in Mizoram under NABARD (Group VII : Teikhang ,Rabung & Dungtlang). | % | 336.53 | 17.7.2023 | 31.3.2025 | [6 empty] | Work in Progress | PWD Form - 8
| i) Construction of 200 MT warehouse at Teikhang |  |  |  |  | 100% | 39.82 | 0% | 0 | 100% | 39.82
| ii) Construction of 200 MT warehouse at Rabung |  |  |  |  | 98% | 38.65 | 2% | 0 | 100% | 38.65
| iii) Construction of 200 MT warehouse at Dungtlang |  |  |  |  | 95% | 74.53 | 5% | 0 | 100% | 74.53
| iv) Construction of staff quarters at Dungtlang |  |  |  |  | 92% | 0 | 8% | 0 | 95% | 0
| Overall | [5 empty] | 153 |  |  | 98% | 153
| ` | [8 empty] | Sr.Executive Engineer, PWD., Project Division - III Aizawl, Mizoram
MONTHLY PROGRESS REPORT FOR THE MONTH OF JUNE 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | SCA to TSS/CSS
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Const of 100 Bedded Dist hospital at Saitual ( Sh: Cons of OPD building at district hospital, Saitual) | % | 200 | 13.10.2023 | 13.10.2025 | 91% | 125.22 | 0.5% | 0 | 91.5% | 125.22 | Work in progress | PWD Form - 8
Sr.Executive Engineer, PWD., Project Division - III Aizawl, Mizoram
MONTHLY PROGRESS REPORT FOR THE MONTH OF JUNE 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | NEC
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Creation of Passion fruit Processing unit at Cold Storage , New Champhai Mizoram. | % | 185.39 | 23.9.2022 | 24.3.2024 | 100% | 185.39 | 0% | 0 | 100% | 185.39 | Building work completed. Procurement of plants and machineries being taken up by D.C. Champhai. | PWD Form - 8
Sr.Executive Engineer, PWD., Project Division - III Aizawl, Mizoram
MONTHLY PROGRESS REPORT FOR THE MONTH OF JUNE 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | NEC
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Zomi cultural Centre and preservation of historical sites at Champhai | % | 478.69 | 26.9.2022 | 7.2.2025 | 100% | 425.84 | 0% | 0 | 100% | 425.84 | Work completed | PWD Form - 8
Sr.Executive Engineer, PWD., Project Division - III Aizawl, Mizoram
MONTHLY PROGRESS REPORT FOR THE MONTH OF JUNE 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | NEC
Sl no | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Biate Tea Tourism Circuit & Nature camp in Mizoram | % | 369.62 | 9.10.2023 | 9.10.2025 | 95% | 342.62 | 0.5% | 0 | 95.5% | 342.62 | Work in progress | PWD Form - 8
Sr.Executive Engineer, PWD., Project Division - III Aizawl, Mizoram
MONTHLY PROGRESS REPORT FOR THE MONTH OF JUNE 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | NEC
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Establishing Mizo cultural heritage centre for protecting the historical and natural heritage of Mizo at Kawlri, Serchhip | % | 486.47 | 16.2.2024 | 16.2.2026 | 40% | 121.61 | 3% | 0 | 43% | 121.61 | Work in progress | PWD Form - 8
Sr.Executive Engineer, PWD., Project Division - III Aizawl, Mizoram
MONTHLY PROGRESS REPORT FOR THE MONTH OF JUNE 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | NEC
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Auditorium at Bethel Veng Champhai | % | 1443.75 | 16.2.2024 | 16.2.2026 | 35% | 176.88 | 2% | 0 | 37% | 176.88 | Work in progress | PWD Form - 8
Sr.Executive Engineer, PWD., Project Division - III Aizawl, Mizoram
MONTHLY PROGRESS REPORT FOR THE MONTH OF JUNE 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | NESIDS - OTRI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of 50 Bedded District Hospital Complex and Procurement of equipment at Khawzawl, Khawzawl District, Mizoram | % | 1775 | 11.6.2024 | 11.12.2026 | 51% | 330.37 | 2% | 0 | 53% | 330.37 | Work in progress | PWD Form - 8
Sr.Executive Engineer, PWD., Project Division - III Aizawl, Mizoram
MONTHLY PROGRESS REPORT FOR THE MONTH OF JUNE 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | NESIDS-OTRI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of 50 Bedded District Hospital Complex and Procurement of equipment at Saitual, Saitual District, Mizoram | % | 1696 | 10.6.2024 | 10.12.2026 | 20% | 0 | 1% | 89.55 | 21% | 89.55 | The local NGO's wanted to shift the layout of the hospital main building towards the backside and lowering of the courtyard which will involve additional fund. The matter is brought to Health Department and decision is awaited. Work for quarters only in progress. | PWD Form - 8
Sr.Executive Engineer, PWD., Project Division - III Aizawl, Mizoram
MONTHLY PROGRESS REPORT FOR THE MONTH OF JUNE 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | NEC
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Upgradation of Sports Infrastructure of Ngopa Playground at Saitual District, Mizoram. | % | 394.15 | 15.3.2025 | 15.9.2027 | 2.5% | _ | 2.5% | _ | 5% | _ | Work in progress | _
Sr.Executive Engineer, PWD., Project Division - III Aizawl, Mizoram
MONTHLY PROGRESS REPORT FOR THE MONTH OF JUNE 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | NESIDS
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Improvement/Upgradation of Operational/Non-operational facilities of Lengpui Airport, (Sh: Elevated road with connected components of Terminal Building). | % | 1959 | 30.9.2021 | 30.11.2024 | 100% | 1959 | 0% | 0 | 100% | 1959 | Completed | Turnkey
Sr.Executive Engineer, PWD., Project Division - III Aizawl, Mizoram
MONTHLY PROGRESS REPORT FOR THE MONTH OF JUNE 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | CSS
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Tourist Lodge at Champhai | % | 328.73 | 9.12.2010 | 30.11.2020 |  |  |  |  | 100% | 300 | Taken over by the Department on Dt.3.8.2021 . LOC amounting to Rs. 30.00 lakh submitted for clearing liaibility. Hence, release of LOC awaited for financial closure.
Sr.Executive Engineer, PWD., Project Division - III Aizawl, Mizoram
MONTHLY PROGRESS REPORT FOR THE MONTH OF JUNE 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | CSS
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Polytechnic at Chhiahtlang | % | 800 | [8 empty] | Only approach road is executed. Out of fund received amount Rs. 300.00 lakhs balance amount of Rs. 196.34 lakhs is kept at D-III
| i) Approach road |  |  | 3.3.2016 | 2.8.2016 |  |  |  |  | 100% | 103.67
ii) Administrative & Academic Block
iii) Hostel Block
iv) Staff Quarter
Sr.Executive Engineer, PWD., Project Division - III Aizawl, Mizoram
MONTHLY PROGRESS REPORT FOR THE MONTH OF JUNE 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | CSS
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Hostel for S.T Girls at Champhai | % | 462.75 | 18.9.2023 | 28.9.2025 | 87.5% | 162.77 | 0% | 0 | 87.5% | 162.77 | Work in progress | PWD Form - 8
Sr.Executive Engineer, PWD., Project Division - III Aizawl, Mizoram
MONTHLY PROGRESS REPORT FOR THE MONTH OF JUNE 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | CSS
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | 10 - Bedded Integrated AYUSH Hospital at Keifang, Saitual District | % | 750 | 13.10.2023 | 13.10.2025 | 35% | 119.81 | 5% | 59.05 | 40% | 178.86 | Work in progress | PWD Form - 8
Sr.Executive Engineer, PWD., Project Division - III Aizawl, Mizoram
MONTHLY PROGRESS REPORT FOR THE MONTH OF JUNE 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | CSS
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Const of District Court Complex at Vengsang, Champhai. ( Sh: Main Building, phase- I) | % | 4915.35 | 17.10.2023 | 17.10.2026 | 51% | 1307.19 | 2% | 0 | 53% | 1307.19 | Work in progress | PWD Form - 8
Sr.Executive Engineer, PWD., Project Division - III Aizawl, Mizoram
MONTHLY PROGRESS REPORT UNDER SPECIAL ASSISTANCE TO STATES FOR CAPITAL EXPENDITURE FOR THE MONTH OF JUNE 2025
Sl. No. | Name of Project with brief description | Approved Cost (Rs. lakh) | First Installment |  | Second Installment |  | Component-wise break up of the Project | Component-wise Project milestones (Target date of completion) | Financial Progress (component wise in Rs.lakh | Physical Progress (component wise in %age) | Remarks, including Reason for non-achievement of milestone (If applicable)
|  |  | Date of Sanction | Amount (Rs.lakh) | Date of Sanction | Amount (Rs.lakh)
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Name of the Implementing Department : PWD, Project Division-III
1 | Improvement/ Upgradation of Operational/ Non-operational Facilities of Lengpui Airport. (SH : Renovation of Terminal Building) | 2124 | 16.03.2021 | 1577.66 | 19.10.2022 |  | A. Renovation of Terminal Building | 21.10.2023 Extended upto 31.12.2024 | 1773.36 | 98.9% | Work in Progress.
1. Earth Works
2.Dismantling Item
3.PCC works
4.RCC works
5.Brick walling
6.Plastering
7.Tile Flooring
8.Ceiling & Column Panneling with ACP Board
[6 empty] | 537 | 9.Painting with POP
10.Railing (Stainless Steel with Tuffen Glass)
11.Doors & Windows Fittings
12.Temporary Laminated Board Partition
13.Roof Treatment
14.Sanitary fittings
B.Sub-Surface Cable Channel
C.Roof Extension (LS)
Sr.Executive Engineer, PWD. Project Division - III Aizawl, Mizoram
MONTHLY PROGRESS REPORT UNDER SPECIAL ASSISTANCE TO STATES FOR CAPITAL EXPENDITURE FOR THE MONTH OF JUNE 2025
Sl. No. | Name of Project with brief description | Approved Cost (Rs. lakh) | First Installment |  | Second Installment |  | Component-wise break up of the Project | Component-wise Project milestones (Target date of completion) | Financial Progress (component wise in Rs.lakh | Physical Progress (component wise in %age) | Remarks, including Reason for non-achievement of milestone (If applicable)
|  |  | Date of Sanction | Amount (Rs.lakh) | Date of Sanction | Amount (Rs.lakh)
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Name of the Implementing Department : PWD, Project Division-III
1 | Const of 100 Bedded Dist hospital at Saitual ( Sh: Cons of OPD building at district hospital, Saitual) | 200 | 22.3.2022 | 200 |  |  | 1 Building portion with water supply & sanitary fittings. 2. Underground Sump (20,000 ltrs capacity) | 13.10.2025 | 125.22 | 91.5% | Work in progress
Sr.Executive Engineer, PWD.
Project Division-III
Aizawl ; Mizoram

## PD IV
MONTHLY PROGRESS REPORT FOR THE MONTH OF JUNE, 2025
Name of Division |  | : Project Division - IV
Source of funding |  | : SASCI
Sl. No. | Name of work/project | Unit | Approved cost (Rs. in lakh) | Date of commencement | Target date of completion | Cummulative progress at the end of last month |  | Achievement of works during the month |  | Overall Cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin |  |  | COPY 4
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Working Women Hostel (50 Bedded) at Ramhlun Sports Complex, Aizawl. | % | 1400 | 2025-05-14 | 2026-05-14 | 1% | 0 | 9.2% | 0 | 10.2% | 0 | Work in progress. | Item rate.
MONTHLY PROGRESS REPORT FOR THE MONTH OF JUNE, 2025
Name of Division |  | : Project Division - IV
Source of funding |  | : SASCE
Sl. No. | Name of work/project | Unit | Approved cost (Rs. in lakh) | Date of commencement | Target date of completion | Cummulative progress at the end of last month |  | Achievement of works during the month |  | Overall Cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | copy 4
1 | Construction of Multi Utility Centre at Zemabawk, Aizawl, Mizoram | % | 800 | 2022-12-19 | 2025-08-16 | 83% | 348.882 | 2.5% | 0 | 85.5% | 348.882 | Work in progress. | Item rate.
2 | Construction of Solid Waste Management Centre at Hualngohmun, Mizoram (Phase-I) | % | 1664 | 2023-04-07 | 2025-04-07 | 47% | 374.86 | 1.5% | 0 | 48.5% | 388.12 | Work in progress. | Item rate. | 76.51
3 | Restoration/renovation of DC Office at Aizawl. | % | 2000 | 2025-04-08 | 2026-04-08 | 1% | 0 | 3% | 0 | 4% | 0 | Work in progress. | Item rate. | 451.37
COPY 4
MONTHLY PROGRESS REPORT FOR THE MONTH OF JUNE, 2025
Name of Division |  | : Project Division - IV
Source of funding |  | : NEC
Sl. No. | Name of work/project | Unit | Approved cost (Rs. in lakh) | Date of commencement | Target date of completion | Cummulative progress at the end of last month |  | Achievement of works during the month |  | Overall Cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of AYUSH Development Centre at MINECO Aizawl, Mizoram | % | 264.16 | 2022-12-07 | 17-08-2024 17.04.2025 (1st EOT) | 82% | 198.12 | 3% | 0 | 85% | 198.12 | Work in progress. EOT application in process. | Item rate.
2 | Establishment of Sinlung Hills Council Administrative Complex, Mizoram (Sh : Construction of Sinlung Hills Council Administrative Building at Sakawrdai) | % | 381.99 | 2021-11-08 | 31-07-2024 )1st EOT) 28.02.2025 (2nd EOT) | 92.5% | 210.4039 | 0.5% | 0 | 93% | 210.4039 | Work in progress. Bill withheld amount - Rs. 5.00 lakhs. EOT application in progress. | Item rate. |  | 153.0003
MONTHLY PROGRESS REPORT FOR THE MONTH OF JUNE, 2025
Name of Division |  | : Project Division - IV
Source of funding |  | : Article 275 (1)
Sl. No. | Name of work/project | Unit | Approved cost (Rs. in lakh) | Date of commencement | Target date of completion | Cummulative progress at the end of last month |  | Achievement of works during the month |  | Overall Cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Tribal Hostel at Suangpuilawn, Mizoram. | % | 320 | 2023-08-12 | 2025-07-22 | 76% | 130.5738 | 0% | 0 | 76% | 131.5738 | Work progress hindered due to irregularity in release of fund from Ministry. | Item rate. | COPY 5
2 | Construction of Multipurpose Community Hall at Darlawn, Mizoram. | % | 720 | 2023-08-12 | 2025-08-12 | 63% | 146.3635 | 0% | 0 | 63% | 149.8635 | Work progress hindered due to irregularity in release of fund from Ministry. Bill withheld amount Rs. 14.90 lakh. | Item rate.
MONTHLY PROGRESS REPORT FOR THE MONTH OF JUNE, 2025
Name of Division |  | : Project Division - IV
Source of funding |  | : NABARD
Sl. No. | Name of work/project | Unit | Approved cost (Rs. in lakh) | Date of commencement | Target date of completion | Cummulative progress at the end of last month |  | Achievement of works during the month |  | Overall Cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of 24 warehouses with associated infrastructure in 23 locations in Mizoram under NABARD (Group V : Zohmun) | % | 170.99 | 2023-07-17 | 2025-07-17 | 54% | 48.5032 | 2.5% | 0 | 56.5% | 51.4928 | Work in progress. Const. of Staff quarter started. | Item rate. | COPY 5

## Serchhip Div
NAME OF DIVISION : Serchhip Division
MONTHLY PROGRESS FOR THE MONTH Of JUNE 2025
Sl. No | Name of Schemet | Unit | Approved Cost (in lakhs) | Date of Commence- ment | Target date of Completion | Cummulative Progress at the end of last Month |  | Achievement of works during the month |  | Overall Cumulative achievement |  | Remarks | Mode of Tender
| Name of Work/ Project |  |  |  |  | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
PMGSY
1 | Construction and Maintenance of Mualcheng to N. Vanlaiphai Road Group - A (0.00- 8.00 Kmp) |  | 515.65 | 31.12.2020 | 01.09.2022 |  |  |  |  | 100% | 303.13 | Physically Completed | Item rate
2 | Upgradation and Maintenance of Khawlailung to Hmunzawl to Lungpho Road (0.000 - 39.04 Kmp) |  | 3516.65 | 31.08.2024 | 2.03.2026 | 13.01% |  | 0.1% |  | 13.11% |  | Machinery Advance = Rs 270 lakh
NABARD
3 | Approach Road to Paragliding Ground |  | 345.63 | 08.05.2025 | 08.03.2027 | 5% |  |  |  | 5% |  | Mobilisation in progress
4 | Improvement of Kikawn to Hmar veng Serchhip |  | 1551.98 | 14.05.2025 | 14.03.2027
5 | Construction of Link Road and Land Improvement at Zawlpui, Serchhip |  | 963.3 | 03.05.2025 | 03.03.2027 | 30% |  | 5% | 57.66 | 35% | 57.66 | Work in Progress
6 | Improvement of Serchhip (Chawmkai) to Zote South Serchhip |  | 2180.93 | 14.05.2025 | 14.03.2027 | [6 empty] | Mobilisation in progress
Sr. Executive Engineer
Serchhip Division: Serchhip

## Saitual Div
NAME OF DIVISION : PWD Saitual Division
MONTHLY PROGRESS FOR THE MONTH OF : JUNE 2025
[6 empty] | Physical in % |  |  |  | Financial is Rs in lakh
Sl. No | Name of Scheme | Unit | Approved Cost (in lakhs) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last Month |  | Achievement of works during the month |  | Overall Cumulative achievement |  | Remarks | Mode of Tender
| Name of Work/ Project |  |  |  |  | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
PMGSY
1 | Upgradation & Maintenance of Saitual - Phullen Road (0.000 - 18.130 kmp) |  | 1830.83 | 05.09.2024 | 02.03.2026 | 13.9% | 253.8871 | 2.55% |  | 16.45% | 253.8871 |  | Open Tender
NESIDS
1 | Improvement & Upgradation of Daido to Vawngkawt- Buangpuilawn (Manipur) Road |  | 2404 | 14.03.2024 | 14.09.2025 | 73.21% | 813 | 5.73% |  | 78.94% | 813 | Security Deposit amounting to Rs. 0.93 Cr. Is lying in CNA Account | Open Tender
SASCI-II
1 | Improvement of Khawlek - Ratu Road (Length = 6Km) |  | 130 | 05.10.23 | 05.10.24 | 100% | 126.14 |  |  | 100% | 126.14 |  | Restricted Tender
2 | Widening and reconstruction of culverts on 3rd Road from Sedaikawn to PWD Kawn, Saitual (Length = 2.220Kms) |  | 137.52 | 05.10.23 | 05.10.24 | 100% | 137.52 |  |  | 100% | 137.52 |  | Restricted Tender
3 | Rigid pavement of Sakeibangla to ZMC via Thingsulthliah Road Thingsulthliah, PCC Pavement = 3.00km, Side drain = 2000m,R/Wall = 10m, Culvert = 2 Nos |  | 55.78 | 05.10.23 | 05.10.24 | 100% | 55.78 |  |  | 100% | 55.78 |  | Restricted Tender
4 | Pothole & Patch repair on Saitual to Phullen Road. ( 2.00 km ) |  | 15.5 | 05.10.23 | 05.10.24 | 100% | 15.5 |  |  | 100% | 15.5
SEDP
1 | Construction of Khanpui - Tualbung Road Phase-II |  | 1576.01 | 15.01.20 | 15.06.22 | 100% | 1575.73 |  |  | 100% | 1575.73
Sr. Executive Engineer, PWD.,
Saitual Division, Saitual.

## Siaha Div
PWD Siaha Division.
Sl.No. | Name of Scheme | Unit | Approved Cost (in lakhs) | Date of Commencement | Target date of Completion | Commulative Progress at the end of last Month |  | Achievement of work during the month |  | Overall Cummulative achievement |  | Remarks | Mode of Tender
| Name of Work/Project |  |  |  |  | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | SASCI
| Improvement of Saiha Town from Meisatla to Tlangkawn Via College Veng (7.50kms) (SH: Thanngerh Agriculture Link road Thaltlang) | % | 28.8465 | 20.10.23 | 31.03.25 | 100% | 8.32 |  |  | 100% | 8.32 | Deviation from formation Widening to Formation cutting has been approved. Therefore, 1.600 l,ength has been shortened to 0.530 km | Item rate Contract
2 | NABARD
Work under NABARD
| Up-gradation of Laki to Vahai Road From Ch. 0.00 km to Ch. 15.56 km | % | 1809.4429 | 28.06.2024 | 27.06.2026 | 57.05% | 625.78 | 3.41% | 420.2614 | 60.46% | 1046.0414 | Work in progress | Item rate Contract
3 | NEC
Work under NEC
4 | PMGSY
Work under PMGSY
5 | SEDP
Work under SEDP
6 | CSS
Work under CSS
7 | MoRTH
Work under MoRTH
8 | 5054
| Annual Plan 2024 - 2025 Strengthening and Improvement of Bridge under Mizoram | % | 247.61 | 02.12.2024 |  | 75% | 7.04 |  |  | 75% | 7.04 | Work in progress | Item rate Contract
9 | CRF
| Construction of Road from Chakhei to Siasi road (Length = 20 km) under CRF: Group-A (SH: FC & Pavement Works) | % | 3630.73 | 08.07.19 | 20.12.2024 | 99.98% | 2969.6779 |  |  | 99.98% | 2969.6779 | Work in progress | Item rate Contract
Sr. Executive Engineer, PWD
Siaha Division

## Tlabung Div
MONTHLY PROGRESS REPORT FOR THE MONTH OF JUNE / 2025 UNDER PWD, TLABUNG DIVISION.
[10 empty] | Physical in % |  | Financial in lakh
Sl No | Name of Scheme | Unit | Approved cost (in lakh) | Date of Commencement | Target date of completion | Cummulative progress at the end of last mont |  | Achievement of works during the month |  | Overall Cummulative achievement |  | Remarks | Mode of Contract
| Name of works / Project |  |  |  |  | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
A | SASCI
1 | Strengthening of Chawngte and Borapansury road | km | 391.3 | 22.06.2023 | 22.06.2024 | 50% | 194.02 |  |  | 50% | 194.02 | On-going Extension granted upto Dt.31.05.2025 | Item Rate
2 | Improvement of Borapansury-I to Borapansury-II Road upto Bangladesh Boundary | Km | 168.34 | 14.12.2023 | 14.12.2024 | 98% | 81.33 |  |  | 98% | 81.33 | On-going | Item Rate
B | NABARD
1 | Improvement of Chawngte - Borapansury Road (0.000-30.00)KMP | Km | 3987 | 15.03.2023 | 15.03.2025 | 23% | 621 | 4% | 200 | 27% | 821 | On-going Extension granted upto Dt.13.07.2026 | Item Rate
2 | Const of Galvanised Steel Concrete Composit Bridge over Borapansury River on Chawngte to Borapansury road | Nos | 635.69 | 13.05.2024 | 13.05.2026 | 1% | 0 |  |  | 1% | 0 | On-going | Item Rate
(R.LALRINMAWIA)
Sr. Executive Engineer, PWD..
Tlabung Division, Tlabung