## AZL ELEC DIV
A

## LAWNGTLAI DIV
LTI

## PIU
MONTHLY PROGRESS REPORT FOR THE MONTH OF SEPTEMBER 2025 - PROJECT IMPLEMENTATION UNIT, PWD
Source of Funding : PM DevINE
SL. No. | Name of work /Project. | Approved Cost (Rs) | Name of Implementing agency/Dept. | Date of Commencement | Target Date of Completion | Cummulative progress at the end of last month |  | Achievement of works during the month |  |  | Overall cumulative achievement |  | Remarks | Mode of Contract
[6 empty] | Physical | Financial | Physical | Financial |  | Physical | Financial
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 11 | 12 | 13 | 14
1 | Construction of Aizawl Bypass on Western Side under PM DevINE Scheme Location : Mizoram State : Aizawl | 451.85 Cr | Project Implementation Unit, PWD | 23.12.2024 | 23.12.2027 | 8.82% | 8.9% | 0.091% | 0% |  | 8.91% | 8.9% |  | EPC
Note: | Based on the site verification, quantity of earthwork is reduced from 22.50km to 13.10km and the overall physical progress is also changed from 15.01% to 8.91%.
MONTHLY PROGRESS REPORT FOR THE MONTH OF SEPTEMBER 2025 - PROJECT IMPLEMENTATION UNIT, PWD
FINANCIAL REPORT
Sl. No. | Name of project Location and state | Name of Implementing agency/Dept. |  | Approved Cost |  | Fund Released by MDoNER |  | Expenditure Made |  | Unspent balance out of the fund released | Status of submission U/Cs | Remarks
|  |  |  | Orignal cost INR in Crore | Revised cost INR in Crore | During 2024-25 INR in Crore | Since inception (cummulative) | During the month vis-à-vis target | Since inception ( cummulative)
1 | 2 | 3 |  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Construction of Aizawl Bypass on Western Side under PM DevINE Scheme Location : Mizoram State : Aizawl | Project Implementation Unit, PWD |  | 500.00 Cr | Nil | 112.95 | 112.95 | 0 | 61.09 | 51.86 |  | Out of the ₹112.95 Crore sanctioned, a total amount of ₹ 61.09 Cr was utilised, details as follows: i) DPR preparation = ₹ 0.507 crore ii) Tech. appraisal cost = ₹ 0.05 cr iii) EIA/EMP = ₹ 1.119 cr iv) Mobilisation Advance = ₹ 19.203 cr v) SPS-01 = ₹ 40.211 cr Grand Total = ₹ 61.09 cr
| Bill paid to the Contractor | Rs. 40.21 Cr
| Financial Progress of the Contractor | 8.9%
MONTHLY PROGRESS REPORT FOR THE MONTH OF SEPTEMBER 2025 - PROJECT IMPLEMENTATION UNIT, PWD
PHYSICAL ABSTRACT
Sl. No. | Name of the project Location and state | Name of the implementing Agency/ Deptt. | Approved cost & date | 5: Date of commencement of work /scheme; 6: Target date of completion of work/scheme; 7: Scope of work /scheme physical terms (e.g.Kms etc); 11: Physical Achievement |  |  | Remark
|  |  | Cost (lakhs) | 4: Date; 11: Achievement; 12: Percentage upto date progress | Percentage during last month | Percentage during the report
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |  |  |  | 9 | 10 | 11 | 12 | 13
1 | Construction of Aizawl Bypass on Western Side under PM DevINE Scheme Location : Mizoram State : Aizawl | Project Implementation Unit, PWD | 4510 | 23.12.2024 | 23.12.2024 | 23.12.2027 | 1 | Earthwork up to top of sub-grade | Km | 45 | 13.1 | 29.11% | 50% | -20.89% | Based on the site verification, quantity of earthwork is changed/ reduced.
|  |  |  | 7: 2; 8: Sub Base Course (SSB); 9: Km; 10: 45; 12: 0% |  | 0%
|  |  |  | 7: 3; 8: Seperation Layer (SAMI); 9: Km; 10: 45; 12: 0% |  | 0%
|  |  |  | 7: 4; 8: Bituminous Work; 9: Km; 10: 45; 12: 0% |  | 0%
|  |  |  | 7: 5; 8: Wearing Course; 9: Km; 10: 45; 12: 0% |  | 0%
[7 empty] | 6 | Reconstruction and New Culverts on Existing road/realignmnet bypass - Hume Pipe Culvert | nos | 205 | 5 | 2.439% | 1.46% | 0.979%
|  |  |  | 7: 7; 8: Reconstruction and New Culverts on Existing road/realignmnet bypass - RCC Box Culvert; 9: nos; 10: 12; 12: 0% |  | 0%
|  |  |  | 7: 8; 8: Reconstruction and New Culverts on Existing road/realignmnet bypass - chutes; 9: nos; 10: 1278; 12: 0% |  | 0%
[7 empty] | A | A-Widening and repairs of minor bridges
[7 empty] | 1 | Repair of minor bridge by construction of wing wall
[7 empty] | B | B-New Minor Bridges
|  |  |  | 7: 1; 8: Foundation + Substructure; 9: Nos; 10: 8; 12: 0% |  | 0%
|  |  |  | 7: 2; 8: Super-structure; 9: Nos; 10: 8; 12: 0% |  | 0%
|  |  |  | 7: 3; 8: Approaches; 9: Nos; 10: 8; 12: 0% |  | 0%
|  |  |  | 7: 4; 8: Protection Work; 9: Nos; 10: 8; 12: 0% |  | 0%
|  |  |  | 7: i; 8: Counterfort retaining wall; 9: RMT; 10: 2140; 12: 0% |  | 0%
|  |  |  | 7: ii; 8: Plumb Concrete Retaining Wall; 9: Nos; 10: 1722; 12: 0% |  | 0%
|  |  |  | 7: iii; 8: Breast Wall; 9: RMT; 10: 946; 12: 0% |  | 0%
|  |  |  | 7: iv; 8: Toe Wall; 9: RMT; 10: 946; 12: 0% |  | 0%
[7 empty] | v | Gabion Breast Wall | RMT | 1355 | 150.5 | 11.11% | 9.59% | 1.517%
|  |  |  | 7: vi; 8: Lined Side Drain; 9: MTR; 10: 5000; 12: 0% |  | 0%
|  |  |  | 7: vii; 8: Crash Barrier; 9: RMT; 10: 2560; 12: 0% |  | 0%
|  |  |  | 7: viii; 8: Traffic Signages; 9: Nos; 10: 225; 12: 0% |  | 0%
|  |  |  | 7: ix; 8: Road Markings; 10: 13050; 12: 0% |  | 0%
|  |  |  | 7: x; 8: Km Stones; 10: 220; 12: 0% |  | 0%
|  |  |  | 7: xi; 8: Boundary Pillar; 10: 600; 12: 0% |  | 0%
|  |  |  | 7: xii; 8: Direction and Place identification; 10: 35; 12: 0% |  | 0%

## TLABUNG DIV
TLABUNG DIV