## ARND
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER, 2025
Name of Work : Improvement & Maintenance of City Roads under Annual Maintenance Operation Plan (AMOP) 2025-26
Name of Scheme : State funding (3054)
Approved Amount : Rs. 75.17 lakh
Name of Sub-Division : Aizawl Road North Sub-Division-I
Sl. No. | Sub-Head of works | Unit | Approved Cost (in lakh) | Date of Commencement | Target Date of Completion | Commulative Progress at the end of Last Month |  | Achievement of Works during the Month |  | Overall cumulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
SUB - DIVISION - I
1 | Patch repair of Aizawl City roads within Aizawl Road North Division | Nos | 66 | 2025-08-01 | 2026-03-31 | - | - | 100% | 64.05 | 100% | 64.05 | Phy Completed | Departmental
2 | Patch Repair and Seal Coating of Electric 3rd row Road | km | 5.15 |  |  | - | - | 40% | 5 | 40% | 5 | Work in progress
3 | Patch Repair and Seal Coating of Electric 2nd row road upto Zirtiri College | km | 9.61 |  |  | - | - | 50% | 9.33 | 50% | 9.33 | Work in progress
4 | Patch Repair and Seal Coating of Darnam lui to chite (new complex) | km | 8.19 |  |  | - | - | 0% | - | 0% | - | Not yet started
5 | Patch Repair and Seal Coating of Armed veng to Electric veng Cemetry Road | km | 10.58 |  |  | - | - | 0% | - | 0% | - | Not yet started
6 | Patch Repair and Seal Coating of Armed veng to Armed Veng 'S' to Bethlehem Vengthlang Zoo Road | km | 7.13 |  |  | - | - | 30% | 6.92 | 30% | 6.92 | Work in progress
7 | Improvement of Riding Quality on Bazar Bungkawn to Chite Road | km | 15.74 |  |  | - | - | 20% | - | 20% | - | Work in progress
8 | Construction of R/Wall infront of Zohmingliani's House near RSC field, Ramhlun North | Rm | 3 |  |  | - | - | 100% | - | 100% | - | Phy Completed
SUB - DIVISION - II
1 | Patch Repair and Seal Coating of Sihphir Lower Lane ) Indoor stadium) | Km | 2.94 |  |  | 0% | - | 0% | - | 0% | - | Not yet started | Departmental
2 | Patch Repair and Seal Coating of CRPF Camp to Kailiana road at Thuampui (BRTF Complex Kailiana road) | Km | 1 |  |  | 0% | - | 0% | - | 0% | - | Not yet started
3 | Patch Repair and Full Seal Coating of approach road to Lower Zotui veng at Durtlang Leitan (Zotui kawng Pu Dokhuma's house) | Km | 0.6 |  |  | 0% | - | 0% | - | 0% | - | Not yet started
4 | Patch Repair and Full Seal Coating of Approach Road to Thuampui Cemetry (BRTF Complex Thuampui cemetry) | Km | 1.41 |  |  | 0% | - | 0% | - | 0% | - | Not yet started
5 | Patch Repair and Full Seal Coating of Zemabawk vengthar road (Anganwadi centre RIPANS road) | Km | 0.78 |  |  | 0% | - | 0% | - | 0% | - | Not yet started
6 | Patch Repair and Full Seal Coating of Approach Road to TV centre at Durtlang (DDK) | Km | 0.72 |  |  | 0% | - | 0% | - | 0% | - | Not yet started
7 | Patch Repair and Full Seal Coating of Upper Hermon road at Durtlang | Km | 8.8 |  |  | 0% | - | 0% | - | 0% | - | Not yet started
8 | Patch Repair and Full Seal Coating of Upper Hermon road Lane-4 at Durtlang | Km | 2.93 |  |  | 0% | - | 0% | - | 0% | - | Not yet started
9 | Resurfacing with Mix seal surfacing of bawngkawn Hmar veng to Thuampui road | Km | 30.53 |  |  | 0% | - | 0% | - | 0% | - | Not yet started | Departmental
10 | Patch Repair and Full Seal Coating of approach road to Bawngkawn cemetry | Km | 1.89 |  |  | 0% | - | 0% | - | 0% | - | Not yet started
11 | Patch Repair and Full Seal Coating of AMC road at bawngkawn | Km | 6 |  |  | 0% | - | 0% | - | 0% | - | Not yet started
12 | Patch Repair and Full Seal Coating of approach road to Sobji bazar road at bawngkawn | Km | 2.02 |  |  | 0% | - | 0% | - | 0% | - | Not yet started
13 | Patch Repair and Full Seal Coating of approach road to Sobji bazar road at bawngkawn | Km | 3.02 |  |  | 0% | - | 0% | - | 0% | - | Not yet started
14 | Resurfacing of Chhingtei road at Durtlang | Km | 16 |  |  | 0% | - | 0% | - | 0% | - | Not yet started
15 | Construction of V-Shaped Side drain ai Leitan Ramthar Lane-II | Km | 15.49 | 23.8.2025 | 2026-03-30 | 0% | - | 80% | 15.04 | 80% | 15.04 | Work in progress
16 | Construction of V-Shaped Side drain ai Leitan Ramthar Lane-I | Km | 21.48 | 4.9.2025 | 2026-03-30 | 0% | - | 60% | 20.86 | 60% | 20.86 | Work in progress
17 | Construction of Retaining wall at Upper Hermon road at Durtlang | Km | 20.34 | 22.8.2025 | 2026-03-30 | 0% | - | 100% | 14.87 | 100% | 14.87 | Phy Completed
18 | Construction of Gabion wall at Thuampui to selesih road at Ch:2.000kmp | Km | 5.61 | 20.8.2025 | 2026-03-30 | 0% | - | 100% | 5.44 | 100% | 5.44 | Phy Completed
19 | Construction of V-Shaped Side drain at ICFAI road | Km | 18.9 | 19.8.2025 | 2026-03-30 | 0% | - | 80% | 12.46 | 80% | 12.46 | Work in progress | Departmental
20 | Re-Construction of Course rubble masonry Line side drain at bawngkawn Sobji bazar road | Km | 7.95 | 17.8.2025 | 2026-03-30 | 0% | - | 100% | 7.72 | 100% | 7.72 | Phy Completed
21 | Construction of Retaining wall at Thuampui to Selesih road at Ch:8.040 kmp | Km | 7.76 | 10.9.2025 | 2026-03-30 | 0% | - | 100% | - | 100% | - | Phy Completed
SUB - DIVISION - III
1 | Patch Repair and Seal coating of Presby Church to Khamtlang via Bus Turning point & NBCC road Sakawrtuichhun | Km | 8.5915 | 2025-08-14 | 2026-03-30 | 0% | - | 0% | - | - | - | Not yet started | Departmental
2 | Patch Repair and Seal coating of Sairang Zero Point to Dawrpui Veng (Rochhing Road) (Sairang Zero Point Sairang Dawrpui) | Km | 3.356 | 2025-08-14 | 2026-03-30 | 0% | - | 0% | - | - | - | Not yet started
3 | Patch repair and Seal Coating of PTC Lungverh to Power Grid (PTC IR Bn Liando Resort Junction) | Km | 4.4839 | 2025-08-14 | 2026-03-30 | 0% | - | 100% | 4.03 | 100% | 4.03 | Phy Completed
4 | Patch repair and Seal Coating of Zotlang Internal Road, Aizawl | Km | 3.0199 | 2025-08-14 | 2026-03-30 | 0% | - | - | - | - | - | Not yet started
5 | Construction of V shape Side Drain at MZU Road at Zonuam, Aizawl | Km | 13.2376 | 2025-08-14 | 2026-03-30 | 0% | - | 100% | 11.91 | 100% | 11.91 | Phy Completed
6 | Patch repair and Seal Coating of Vaivakawn to Bazar Bungkawn road | Km | 6.55 | 2025-08-14 | 2026-03-30 | 0% | - | 15% | 5.89 | 15% | 5.89 | Work in progress
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER, 2025
Name of Work : Resurfacing of road within Aizawl city under Aizawl Road North Division
Name of Scheme : State Funding
Tender Amount : Rs. 2145.56 lakh
Agreement Amount : Rs. 2145.56 lakh
Name of Contractor : Nidhi Creative infrastructure Pvt.Ltd.
Name of Division : Aizawl Road North Division
Sl. No. | Name of works | Unit | Qnty | Approved Cost (in lakh) | Date of Commencement | Target Date of Completion | Commulative Progress at the end of Last Month |  | Achievement of Works during the Month |  | Overall cumulative achievement |  | Remarks | Mode of Contract
[7 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Non Bituminous Base Course | sqm | 8495 | 1699.8 | 2025-04-17 | 2026-10-17 | 14.95% | 246.2875 | 0% | 16.45 | 14.95% | 262.7375 | Works in progress | EPC
2 | Construction of Flexible Pavement | km | 44.63 | 1699.8 |  |  | 16.04% |  | 0% |  | 16.04%
3 | Construction of Rigid Pavement | km | 1.5 | 397.57 |  |  | - |  | - |  | -
4 | Construction of Hume Pipe Culvert | No. | 1 | 6.14 |  |  | 100% |  |  |  | 100%
5 | Widening of Tlaklui to Sihpui road Junction | Rm | 60 | 42.05 |  |  | - |  | - |  | -
| Total = |  |  | 2145.56 |  |  | 12.41% |  | 0.56% |  | 12.97%
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER, 2025 (ROAD WORKS)
Name of Work : Construction of Two Lane from Sihhmui to Ramrikawn Road (Stage-I) | [7 empty] | Name of Contractor : F. Kapsanga, Tuikual
Name of Scheme : CRF | [7 empty] | Revised Target date of Completion : 03.05.2022
Sanction Amount : Rs. 80.00 Crore | [7 empty] | D-III Balance :
Tender Amount : Rs. 71.37 Crore
Name of Division : Aizawl Road North Division
OVERALL ACHIEVEMENT (PHYSICAL) - 87.79% | [10 empty] | (Rs. in lakh)
Sl. No. | Name of Works | Unit | Cost (in lakh) | Date of commencement | Target date of completion | Cumulative Progress at the end of last month |  | Achievement works during the month |  | Overall cumulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Formation Works | Km | 5464.63 | 1.10.2018 | 1.10.2020 | 97% | 6867.09 | 0% | - | 97% | 6867.09 | Contract terminated due to death of contractor on 3.7.2025 | Item Rate
2 | Protection Works
| a) Retaining Wall | Rm | 540.88 |  |  | 91% |  | 0% |  | 91%
3 | Cross Drainage Works
| a) Hume Pipe Culvert | Nos. | 188.63 |  |  | 50% |  | 0% |  | 50%
| b) Box Culvert | Nos. | 818.03 |  |  | 99% |  | 0% |  | 99%
4 | Lined Side Drain
| a) Lined Drain | Km | 44.32 |  |  | 9% |  | 0% |  | 9%
| b) Unlined Drain | Km | 8.31 |  |  | 96% |  | 0% |  | 96%
5 | Box Culvert and Retaining Structure
| a) Box Culvert | Nos. | 493.84 |  |  | - |  | - |  | -
| b) Retaining Wall | Nos. | 96.86 |  |  | 13% |  | 0% |  | 13%
6 | Contingencies etc. | LS | 344.5 |  |  | - |  | - |  | -
| GRAND TOTAL |  | 8000 | [7 empty] | 6867.09
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER, 2025 UNDER NABARD
OVERALL ACHIEVEMENT (PHY) - 92.39%
Sl. No. | Name of Project | Unit | Approved Cost (Rs. in lakh) | Date of Commencement | Target date of completion | Cumulative Progress at the end of last month |  | Achievement works during the month |  | Overall cummulative achievement |  | Remarks | Mode of contract
[6 empty] | Phy. | Fin. | Phy. | Fin. | Phy. | Fin.
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
IMPROVEMENT OF RAMRIKAWN TO NH-54 VIA SAKAWRTUICHHUN ROAD (3.00 Kmp - 7.50 Kmp = 4.50 Km)
1 | Rigid Pavement of Ramrikawn to Sakawrtuichhun | Rm | 480.72 | - | - | 91% | 216.33 | - | - | 91% | 216.33 | Work in progress | Departmental
2 | Resurfacing of Ramrikawn to Zihnghalkawn 980Rm | Rm |  | - | - | 100% |  | - |  | 100% |  | Phy Completed
3 | Construction of approach road to Chawlhhmun from Power Grid at Tuivamit | Rm |  | - | - | - |  | - |  | - |  | Not yet started
4 | Constn. of R/Wall at Ch 4.230 Kmp at Sakawrtuichhun | Rm |  | - | - | 100% |  | - |  | 100% |  | Phy Completed
5 | Constn. of R/Wall at Ch 3.420 Kmp at Sakawrtuichhun | Rm |  | - | - | 100% |  | - |  | 100% |  | Phy Completed
6 | Constn. of R/Wall at Ch 6.340 Kmp at Sakawrtuichhun | Rm |  | - | - | 100% |  | - |  | 100% |  | Phy Completed
7 | Constn of Slab Culvert at 5.900 kmp at Sakawrtuichhun | Rm |  | - | - | 100% |  | - |  | 100% |  | Phy Completed
8 | Constn. of R/Wall at Ch 3.000 Kmp at Sakawrtuichhun | Rm |  | - | - | 100% |  | - |  | 100% |  | Phy Completed
9 | Constn. of R/Wall at Ch 3.500 Kmp at Sakawrtuichhun | Rm |  | - | - | 100% |  | - |  | 100% |  | Phy Completed
10 | Constn. of R/Wall at Ch 4.620 Kmp at Sakawrtuichhun | Rm |  | - | - | 100% |  | - |  | 100% |  | Phy Completed | Departmental
11 | Constn. of R/Wall at Ch 5.360 Kmp at Sakawrtuichhun | Rm |  | - | - | 100% |  | - |  | 100% |  | Phy Completed
12 | Constn. of R/Wall at Ch 5.200 Kmp at Sakawrtuichhun | Rm |  | - | - | 100% |  | - |  | 100% |  | Phy Completed
13 | Constn. of R/Wall at Ch 6.050 Kmp at Sakawrtuichhun |  |  | - | - | 100% |  | - |  | 100% |  | Phy Completed
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER, 2025
PM - DevINE
A. Physical Report
(Rs. in lakhs)
Sl No | Name of the project, location and State | Name of the Implementing Agency/Deptt. | Approved cost by MDoNER/NEC & Date of Approval |  | Date of actual commencement of work/scheme | Target date of completion of work/scheme | Scope of the work/scheme in physical terms (eg. Kms etc) | Physical Achievement |  | Remarks
|  |  | Cost | Date |  |  |  | Percentage(during the month) | Percentage till the reporting period
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
1 | Construction of Bamboo Link Road from Tuirial Airfield to North Chaltlang (18 Kms) under PM - DevINE | Sadguru Engineers & Allied Services Private Ltd | 3358 | 17.4.23 | 1.08.2023 | 20.10.2025 | Concrete Pavement from 0.00 - 18.00 Kmp | - | 47.13% | Work in progress
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER, 2025
PM - DevINE
B. Financial Report
(Rs. in lakhs)
Sl No | Name of the project, location and State | Name of the Implementing Agency/Deptt. | Approved cost by MDoNER/NEC & Date of Approval |  | Fund released by MDoNER/NEC |  | Expenditure made |  | Unspent balance out of the fund released | Status of submission of U/Cs | Remarks
|  |  | Original Cost | Revised Cost | During 2024 - 2025 | Since inception (cumulative) | During the month vis-à-vis target | Since inception (cumulative)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Construction of Bamboo Link Road from Tuirial Airfield to North Chaltlang (18 Kms) under PM - DevINE | Sadguru Engineers & Allied Services Private Ltd | 3358 | - | - | 1090.28 | 17.62 | 1090.28 | - | - | -
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER, 2025 ( ROAD WORKS)
SPECIAL ASSISTANCE TO THE STATES FOR CAPITAL INVESTMENT (SASCI - I) UNDER AIZAWL ROAD NORTH DIVISION
Sl. No. | Name of works | Unit | Cost (in lakh) | Date of commencement | Target date of completion | Cumulative Progress at the end of last month |  | Achievement works during the month |  | Overall cumulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
SUB - DIVISION - I
1. CONSTRUCTION AND UPGRADATION OF ROAD FROM RAMTHAR-RAMTHAR NORTH- ZARKAWT-SARON, AIZAWL
ZARKAWT
1 | Construction of Ahimsa to Jail Veng road at Zarkawt | Rm | 77.98 | 2.5.23 | 30.11.23 | 100% | - | - | - | 100% | 300.94 | Phy Completed | Spot Quotation
2. CONSTRUCTION OF CHECK DAM AT THEIHAI LUI,ARMED VENG
1 | Counterfort Retaining Wall at Armed Veng | Rm | 41.2174 | - | - | 100% | - | - | - | 100% | 299.99 | Phy Completed | Spot Quotation
2 | Toe Walls at Armed Veng side | Rm | 31.4446 | - | - | 100% |  | - |  | 100% |  | Phy Completed | Spot Quotation
3 | Retaining Wall at Ramthar side | Rm | 30.2092 | - | - | 100% |  | - |  | 100% |  | Phy Completed | Spot Quotation
4 | Construction of RCC Link Drain near Pu Rallianzuala's Land | Rm | 50.6527 | - | - | 100% |  | - |  | 100% |  | Phy Completed | Spot Quotation
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER, 2025 UNDER SASCI - II
Sl No | Name of works | Unit | Approved Cost (in lakh) | Date of Comment | Target Date of Completion | Commulative Progress at the end of Last Month |  | Achievement of Works during the Month |  | Overall cumulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
SUB - DIVISION - I
1.CONSTRUCTION OF RCC DRAIN AND PCC PAVEMENT AT CHHINGA VENG AND ELECTRIC VENG
1 | Resurfacing of Armed Veng South to Bethlehem Vengthlang Road at Ch : 0.677 - 1.230 km | Rm | 10.91 | 6.12.2023 | 15.12.2023 | 100% | 148.1 | - | - | 100% | 148.1 | Phy Completed | Restricted
2 | Reconstruction of Collapsed RCC Slab Culvert on Armed Veng South to Bethlehem Vengthlang (Old Zoo Road) near Rawra Chhutna | No | 1.2 | 6.12.2023 | 15.12.2023 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
3 | Balance Work of Construction of RCC Pavement on District Jail to Lower Armed Veng Road (Service Road) | Rm | 1.84 | 10.4.2023 | 11.4.2023 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
4 | Construction of New Road from Lalhmingliana Sailo House to Siamphunga Lei at Tuithiang Phase-II | Rm | 30.14 | 11.3.2024 | 27.3.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
5 | Construction of Drainage System at Aizawl Civil Hospital, Dawrpui West Area | Rm | 14.52 | 18.3.2023 | 24.3.2023 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
6 | Construction of Retaining Wall on Dawrpui Thlanmual Plot-3 | Rm | 6.03 | 24.4.2024 | 3.5.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
7 | Construction of RCC Pavement on Hostel Square at Armed Veng South | Rm | 4.17 | 5.2.2024 | 14.2.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
8 | Construction of RCC Pavement between Pu Thansanga's House to Pu Ronghakliana's House on Armed Veng South Local Council Road | Rm | 2.17 | 19.2.2024 | 23.2.2024 | 100% | 148.1 | - | - | 100% | 148.1 | Phy Completed | Restricted
9 | Construction of PCC Pavement near Pu Larry Lalrova's House Saron Veng | Rm | 4.24 | 8.4.2024 | 13.4.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
10 | Construction of V-Shape Side drain near Rawra Chhutna | Rm | 0.11923 | 12.3.2024 | 15.3.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
11 | Construction of Retaining Wall on Dawrpui Thlanmual Plot - 1 | Rm | 10.95 | 4.4.2024 | 15.4.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
12 | Construction of Retaining Wall on Dawrpui Thlanmual Plot - 2 | Rm | 8.11 | 3.5.2024 | 14.5.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
13 | Construction of Breast Wall on Armed Veng South Local Council Road near Pu Lalnghakliana's House | Rm | 5.94 | 15.4.2024 | 20.4.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
14 | Construction of Breast Wall between Chawngneihkunga's House to Khupneihvunga's House | Rm | 6.41 | 6.2.2024 | 23.2.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
15 | Widening of Road between Chawngneihkunga's House to Khupneihvunga's House | 86 | Rm | 22.4.2024 | 10.5.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
16 | Construction of Retaining Wall below Chhinga Veng Thlanmual | Rm | 46 | 26.2.2024 | 15.3.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
2. IMPROVEMENT OF ROAD FROM RAMHLUN VENGTHAR TO RAMHLUN SPORT COMPLEX, AIZAWL.
17 | Construction of RCC Balcony on Ramhlun South Cemetery at Ramhlun South | Rm | 42.94 | 8.3.2024 | 22.3.2024 | 100% | 222.94 | - | - | 100% | 222.94 | Phy Completed | Restricted
18 | Construction of RCC Frame Structure Breast Wall near Ramhlun South Cemetary | Rm | 25.61 | 8.2.2024 | 16.2.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
19 | Construction of Retaining Wall below Presbyterian Church, Laipuitlang | Rm | 3.93 | 16.1.2024 | 13.2.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
20 | Construction of RCC Pavement & Lowering on Jubilee road at Ramhlun Vengthar | Rm | 58.59 | 4.3.2024 | 22.3.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
21 | Construction of RCC Rectangular side drain with cover near Jubilee road at Ramhlun Vengthar | Rm | 3.65 | 3.4.2024 | 12.3.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
22 | Construction of Steel Grate Cover Side Drain near Jubilee road at Ramhlun Vengthar | No | 1.49 | 3.4.2024 | 10.4.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
23 | Construction of Breast wall on Turning Point at Tetea Road Ramthar North | Rm | 5.65 | 6.2.2024 | 23.2.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
24 | Construction of RCC Pavement on Tetea Road (Below Pu Dawngliana House) at Ramthar North | Rm | 7.89 | 2.4.2024 | 26.4.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
25 | Construction of Retaining wall on Tetea Road Block-I at Ramthar North | Rm | 6.63 | 1.2.2024 | 19.2.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
26 | Construction of Retaining wall on Tetea Road Block-II at Ramthar North | Rm | 1.83 | 13.1.2024 | 12.2.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
27 | Construction of Breast Wall Below Step at NHC Ramhlun Venglai | Rm | 3.33 | 15.1.2024 | 16.2.2024 | 100% | 222.94 | - | - | 100% | 222.94 | Phy Completed | Restricted
28 | Construction of Breast Wall Vertical Extension NHC at Ramhlun Venglai | Rm | 5.6 | 1.2.2024 | 19.2.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
29 | Construction of RCC Rectangular side drain with cover NHC at Ramhlun Venglai | Rm | 0.97 | 2.2.2024 | 20.2.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
30 | Construction of RCC Rectangular side drain with cover on Rokhuma Colney to PC.Lalzuiliana House(Bishop Road) at Ramthar | Rm | 2.98 | 12.3.2024 | 25.4.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
31 | Construction of Breast Wall Below St.Lawrence School at Ramthar | Rm | 6.56 | 6.3.2024 | 22.3.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
32 | Construction of Breast Wall near Boxing hall at Ramhlun Venglai | Rm | 9.38 | 26.3.2024 | 4.4.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
33 | Construction of Retaining Wall on Sihpui to Tlaklui road at Pu C Lalnunmawia's House | Rm | 8.81 | 5.3.2024 | 21.3.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
34 | Construction of PCC Pavement on ICI road Complex Vengthlang at Ramhlun Sport Complex | Rm | 3.51 | 8.3.2024 | 20.3.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
35 | Construction of Retaining wall near Pu.Rosangpuia House at Ramhlun Sport Complex | Rm | 4.22 | 5.3.2024 | 24.4.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
36 | Construction of Breast wall on LC Road near Lianhnuna Road at Ramhlun Sport Complex | Rm | 3.09 | 4.3.2024 | 25.3.2024 | 100% | - | - | - | 100% | - | Phy Completed | Restricted
37 | Construction of RCC Side drain near Pu.Para House at Ramhlun Sport Complex | Rm | 0.49 | 5.3.2024 | 20.3.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
38 | Construction of RCC Footpath on LC Road near Pu HC Thangvela's House to Pu B Zanghinglova's House | Rm | 16.85 | 12.3.2024 | 25.3.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
3. CONSTRUCTION OF LUNGHLU ROAD AT CHANMARI WEST AIZAWL
39 | Construction of RCC Link drain near Hotel Platinum at Zarkawt | Rm | 0.84926 | 6.12.2023 | 9.12.2023 | 100% | 140.02 | - | 21.15 | 100% | 161.17 | Phy Completed | Restricted
40 | Improvement of Zarkawt Valley Approach Road Phase-II | Rm | 47.0033 | 19.2.2024 | 29.2.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
41 | Construction of Retaining wall near Babula's House at Chanmari | Rm | 13.2659 | 5.2.2024 | 14.2.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
42 | Repair of Link Drain with Cover near J.Thangdailova House at Electric Veng | Rm | 9.6394 | 8.2.2024 | 16.2.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
43 | Construction of New Cemetery Road at Electric Veng | Rm | 28 | 2.2.2024 | 15.2.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
4. UPGRADATION OF INTERNAL ROADS AT DURTLANG, BAWNGKAWN, CHALTLANG, ZUANGTUI, RAMHLUN & RAMTHAR
44 | Steel Grate Cover Side Drain on PC Malsawma House to Rev. C.Vanlalhruaia House at Ramhlun South | Rm | 8.04 | 20.3.2024 | 29.3.2024 | 100% | 132.89 |  | - | 100% | 132.89 | Phy Completed | Restricted
45 | Construction of RCC Foot Step near PC.Lalzuiliana House Ramthar | Rm | 16.58 | 6.3.2024 | 20.3.2024 | 100% |  |  |  | 100% |  | Phy Completed | Restricted
46 | Construction of RCC Link Drain near PC.Lalzuiliana House at Ramthar | Rm | 8.42 | 6.3.2024 | 13.3.2024 | 100% |  |  |  | 100% |  | Phy Completed | Restricted
47 | Construction of Breast Wall Below PC.Laltanpuia House at Ramthar North | Rm | 7.3657 | 28.3.2024 | 24.4.2024 | 100% |  |  |  | 100% |  | Phy Completed | Restricted
48 | Construction of Breast Wall near Pu.Lalrammuana Ralte House at Ramthar North | Rm | 5.76 | 5.3.2024 | 27.3.2024 | 100% |  |  |  | 100% |  | Phy Completed | Restricted
49 | Construction of RCC Foot Step near Pi.Manmawii House at Ramhlun South | Rm | 6.68 | 4.3.2024 | 15.3.2024 | 100% |  |  |  | 100% |  | Phy Completed | Restricted
WORK UNDER IMPLEMENTATION OF ARTICLE 275 (1) PHASE - II
50 | Construction of Bethany Road at Chhinga Veng | Rm | 70 | 7.10.2023 | 30.11.2023 | 100% | - | - |  | 100% |  | Phy Completed | Restricted
SUB - DIVISION - II
UPAGRADATION OF BETHEL VENG ROAD AT ZEMABAWK, AIZAWL WITH APPROACH ROAD TO ZOKHAWSANG BYPASSS ROAD
51 | Upagradation of Bethel Veng Road at Zemabawk, Aizawl with approach road to Zokhawsang Bypass Road
| 1. PCC Pavement at Ch: 0.000 - 0.580kmp | Rm | 57.8 | 14.12.23 | 14.12.24 | 100% | 153.2 | - | - | 100% | 153.2 | Phy Completed | Restricted
| 2. Construction of PCC V shape side drain at Ch: 0.000kmp | Rm | 1.57 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 3. Clearance of Landslip | Nos | 20.83 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
52 | Additional requirement for Upgradation of Bethel Veng road at Zemabawk
| 1. Earthwork for Widening (Additional) | Km | 69.54 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 2. RCC Frame Retaining Walls no1 | Rm | 5.2 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
IMPROVEMENT OF MUTHI - TUIRIAL LINK ROAD
53 | 1. Widening & Curve Improvement | Km | 134.74 | 14.12.23 | 14.12.24 | 100% | 163.41 | - | - | 100% | 163.41 | On-Going | Restricted
2. Construction of Slab Culvert
| i. Slab Culvert Type-I | Nos | 11.5 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | On-Going | Restricted
3. Construction of Retaining Wall
| i. Retaining Wall Type - I | Rm | 10 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Work in Progress | Restricted
| ii. Retaining Wall Type - II | Rm | 14 | 14.12.23 | 14.12.24 | - |  | - |  | - |  | Not yet started
CONSTRUCTION OF BAMBOO LINK ROAD FROM NAUSEL, CHAMDUR, LUNGSANG, PUMPELHSEI, KAWRBEL
54 | Construction of Nausel - Tuirial Bamboo Link Road | [5 empty] | 261.48 |  | - |  | 261.48
| 1. Formation Cutting | Km | 36.01 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 2. Construction of Slab Culvert | Nos | 26.63 |  |  | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| At chainage between 0.000 to 3.500 Kmp | Nos | 59.39 | 14.12.23 | 14.12.24 | - |  | - |  | - |  | Not yet started
| 3. Construction of Retaining Wall |  |  |  |  | 100% |  | - |  | 100% |  | Phy Completed | Restricted
At chainage between 0.000 to 3.500 Kmp
| Retaining Wall | Nos | 30.93 | 14.12.23 | 14.12.24 | - |  | - |  | - |  | Not yet started
55 | Concrete Pavement of Sihphir Neibawih khawhnuai kawng balance | [5 empty] | 261.48 |  | - |  | 261.48
| 1. Concrete Pavement | Rm | 36.28 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
2. Construction of Slab Culvert
| At chainage between 0.000 to 0.503 Kmp | Nos | 43.71 | 14.12.23 | 14.12.24 | - |  | - |  | - |  | Not yet started
56 | Construction of Hmunte Road at Muthi
| 1. Formation Cutting | Km | 36.57 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy completed | Restricted
| 2. Construction of Slab Culvert |  |  |  |  | 100% |  | - |  | 100% |  | Phy completed | Restricted
| At chainage between 0.000 to 1.000 Kmp | Nos | 16.57 | 14.12.23 | 14.12.24 | - |  | - |  | - |  | Not yet started
| At chainage between 1.000 to 2.000 Kmp | Nos | 14.5 | 14.12.23 | 14.12.24 | - |  | - |  | - |  | Not yet started
3. Construction of Retaining Wall
At chainage between 0.000 to 2.000 Kmp
| Retaining Wall | Rm | 7.18 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy completed | Restricted
57 | Construction of Chamdur - Kawrbellui Road
| 1. Formation Cutting | Km | 30.5 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
CONSTUCTION OF ROAD FROM ZEMABAWK NORTH TO CWC AND MUALZEN
58 | Construction of New Road from Zemabawk North Dinthar Veng to CWC including Protetion Works & Cross Drain | [5 empty] | 239.91 |  | - |  | 239.91
| 1. Formation Cutting | Km | 72.46 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 2. Construction of Slab Culvert Type-I | Nos | 8 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 3. Construction of Slab Culvert Type-II | Nos | 12 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 4. Construction of Slab Culvert Type-III | Nos | 16.94 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 5. Construction of Retaining Wall Type-I | Rm | 25 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
59 | Construction of New Road from Zemabawk North Thlanmual Hnuai to Mualzen including Protetion Works & Cross Drain
| 1. Formation Cutting | Km | 60.12 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
2. Construction of Slab Culvert
| At chainage between 0.000 to 1.500 Kmp | Nos | 28.6 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| At chainage between 1.500 to 3.000 Kmp | Nos | 23.28 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
CONSTRUCTION OF ROAD FROM FALKLAND TO GALILEE VIA MITLAMUAL AT ZEMABAWK, AIZAWL
60 | Construction of Widening & New Road from Falkland to Mitlamual including protection Works & Cross Drain | [5 empty] | 132.94 |  | - |  | 132.94
| 1. Widening and New Cutting | Km | 42.16 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 2. Construction of Slab Culvert Type-I | Nos | 2.64 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
61 | Construction of New Road from Zemabawk Galile Vailui to Mitlamual including Protection Works and Cross Drain
| 1. Formation Cutting | Km | 52.09 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 2. Construction of PCC Pavement | Rm | 22.88 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 3. Construction of Slab Culvert Type-I | Nos | 14.63 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
CONSTRUCTION OF ROAD FROM FALKLAND TO ZEMABAWK NORTH VIA THUAMPUI
62 | Construction of New Road from Falkland Penniel Road to Thuampui Vengthar and BS Farm to UPC BiakIn at Pi Vani Lui Link Road including Protection Work & Cross Drain (1.00 Km) | [5 empty] | 151.18 |  | - |  | 151.18
| 1. Widening of Road | Rm | 29.22 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 2. Construction of PCC Pavement on BS Farm to UPC BiakIn | Rm | 32.18 | 14.12.23 | 14.12.24 | - |  | - |  | - |  | Not yet started
| 3. Construction of Slab Culvert at Ch : 0.360 Kmp | No | 4.3 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 4. Construction of RCC Link Drain at Ch 0.000-0.112 km | Rm | 25 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 5. Construction of RCC Link Drain With Cover at Ch 0.000 km | Rm | 3.72 | 14.12.23 | 14.12.24 | - |  | - |  | - |  | Not yet started
| 6. Construction of RCC Link Drain With Cover at Ch 0.120 km | Rm | 5.58 | 14.12.23 | 14.12.24 | - |  | - |  | - |  | Not yet started
63 | Construction of New Road RAY to BS Farm Falkland including Protection Works and Cross Drain (0.800Km) | [7 empty] | -
| 1. Lowering and Widening | Rm | 10.14 | 14.12.23 | 14.12.24 | 100% | - | - |  | 100% |  | Phy Completed | Restricted
| 2. Construction of PCC Pavement on RAY to BS Farm Falkland | Rm | 10.48 | 14.12.23 | 14.12.24 | - |  | - |  | - |  | Not yet started
| 3. Construction of Retaining Wall | Rm | 8.84 | 14.12.23 | 14.12.24 | - |  | - |  | - |  | Not yet started
| 4. Construction of V-Shape | Rm | 4.2 | 14.12.23 | 14.12.24 | - |  | - |  | - |  | Not yet started
| 5. Construction of missing Link at BCM Multipurepose Centre at Falkland Veng | Rm | 6.34 | 14.12.23 | 14.12.24 | - |  | - |  | - |  | Not yet started
64 | Construction of Step near Pu Ringdika's House | Rm | 1.4 | 14.12.23 | 14.12.24 | - |  | - |  | - |  | Not yet started
65 | Repairing of Kailiana Concrete Pavement Road at Zemabawk North | Rm | 10.6 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
CONSTRUCTION OF TUIRIAL AIRFIELD TO MUTHI AND ZOKHAWSANG AGRICULTURE
66 | Construction of New Road from Tuirial Airfield Runway to Muthi lui Lalchhuana Leilet including Protetion Works & Cross Drain | [5 empty] | 103.19 |  | - |  | 103.19
| 1. Formation Cutting | Km | 40.94 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 2. Construction of RCC Slab Culvert | No | 66.58 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
CONSTRUCTION OF ROAD FROM THUAMPUI TO NH - 6 (ZEMABAWK)
67 | Construction of Link Drain near Pi Diki House at Sihphir | Rm | 10 | 14.12.23 | 14.12.24 | 100% | 179.18 | - | - | 100% | 179.18 | Phy Completed | Restricted
68 | Pavement of AR Complex at Zokhawsang | Km | 59 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
69 | Resurfacing of Women Polytechnic Internal road at Durtlang | Km | 27 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
70 | Improvement of Dinthar Veng to Muthi Lui Road (Balance Portion) at Zemabawk
| 1. Concrete Pavement | Rm | 31.5 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 2. Construction of RCC Slab Culvert No.1 | No | 12.21 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 3. Construction of Retaining Wall | Rm | 5 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 4. Construction of U shape Side Drain | Rm | 8.29 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
71 | Resurfacing of Sihpui to Ramhlun Vengthar Bus Turning Point at Ch : 1.052 - 1.357 km | m² | 11 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
72 | Patch repair of Vaivakawn to MZU via Zonuam. | m² | 18 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
73 | Construction of Retaining Wall below Thanhrangi's House at Luangmual Complex | Rm | 5 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
74 | Concrete Pavement from Field veng to Dinthar Veng at Zemabawk North |  |  |  |  | - | - |  | -
| 1. Concrete Pavement | Rm | 16.72 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 2. Rectangular Side Drain with cover | Rm | 2.26 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 3. V-Shape Drain | Rm | 3.36 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
75 | Construction of Step with Railing over Link drain near Zemabawk North Play Ground | Rm | 8 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
76 | Construction of RCC Bridge with Link Drain & R/Wall beneath Pu Ramfangzauva's Building at AL road Zemabawk
| 1. Construction of RCC Balcony | Rm | 3.07 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 2. Construction of RCC Link Drain | Rm | 11.67 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 3. Construction of Retaining Wall | Rm | 5.14 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
77 | Construction of Masony Stone Link Drain with R/Wall below Govt. Zemabawk PS-I | Rm | 1.92 | 14.12.23 | 14.12.24 | - |  | - |  | - |  | Not yet started
78 | Concrete Pavement from NH-54 to Holy Cross School Zemabawk | Rm | 15.6 | 14.12.23 | 14.12.24 | - | - | - |  | - |  | Not yet started
79 | Construction of Masony Stone Link Drain near F.Lalrinmawia's Residence at Dinthar Veng Zemabawk North | Rm | 5.61 | 14.12.23 | 14.12.24 | - |  | - |  | - |  | Not yet started
80 | Construction of RCC Link Drain (Balance Portion) at Dinthar Veng | Rm | 10.33 | 14.12.23 | 14.12.24 | - |  | - |  | - |  | Not yet started
81 | Construction of Road including Culvert & R/wall on Thuampui to Thuampui Vengthar Road (Balance Portion)
| 1. Formation Cutting | Km | 8.82 | 14.12.23 | 14.12.24 | - |  | - |  | - |  | Not yet started
| 2. Slab Culvert | No | 5.13 | 14.12.23 | 14.12.24 | - |  | - |  | - |  | Not yet started
| 3. Retaining Wall | Rm | 9.84 | 14.12.23 | 14.12.24 | - |  | - |  | - |  | Not yet started
82 | Concrete Pavement Laichhinga Street Kawn Veng-II at Zemabawk
| 1. Concrete Pavement | Rm | 12.3 | 14.12.23 | 14.12.24 | - |  | - |  | - |  | Not yet started
| 2. Rectangular Side Drain with cover | Rm | 1.15 | 14.12.23 | 14.12.24 | - |  | - |  | - |  | Not yet started
83 | Concrete Pavement from High School to Bethel at Zemabawk | Rm | 2.62 | 14.12.23 | 14.12.24 | - |  | - |  | - |  | Not yet started
84 | Construction of RCC U Shape Side Drain Kailiana Road at Zemabawk near Pi Sawihari | Rm | 7.81 | 14.12.23 | 14.12.24 | - | - | - |  | - |  | Not yet started
85 | PCC flooring Zemabawk North Thlanmual to Muthi lui | Rm | 10.67 | 14.12.23 | 14.12.24 | - |  | - |  | - |  | Not yet started
86 | Construction of hand Railing at Galilee Veng Main Road Zemabawk | No | 2.48 | 14.12.23 | 14.12.24 | - |  | - |  | - |  | Not yet started
87 | Laying of Chequerred Tiles at Melimual (Mual khat) existing steps at Zemabawk | No | 4.5 | 14.12.23 | 14.12.24 | - |  | - |  | - |  | Not yet started
UPGRADATION OF INTERNAL ROADS AT DURTLANG, BAWNGKAWN, CHALTLANG, ZUANGTUI, RAMHLUN & RAMTHAR
88 | Construction of Rectangular Side Drain with cover at Tatkawng Veng | Rm | 1.68 | 14.12.23 | 14.12.24 | 100% | 132.89 | - | - | 100% | 132.89 | Phy Completed | Restricted
89 | Construction of Concrete Pavement of Durtlang tlak lam Thlanmual Road | Rm | 20 | 14.12.23 | 14.12.24 | - |  | - |  | - |  | Not yet started
90 | Construction of Concrete Pavement of Gosen Veng Kawngpui at Zuangtui | Rm | 7 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
91 | Construction of PCC Flooring at Rivenga Road at Muanna Veng | Rm | 10 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
92 | Construction of PCC Flooring Internal Road - Zamliana Road to K.Thankunga Road at Selesih | Rm | 5 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
93 | Vantlang Step near K.Thankunga House at Selesih | Rm | 5 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
94 | Construction of PCC Flooring Laitan Ramthar Biak In lane at Leitan Ramthar | Rm | 10 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
95 | Construction of Concrete Pavement on Bawngkawn Thlanmual to Thuampui Road | Rm | 22.87 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
96 | Steel Grate Cover Side Drain on PC.Malsawma House to Rev.C.Vanlalhruaia House at Ramhlun South | Rm | 2.2727 | 14.12.23 | 14.12.24 | - | - |  |  |  |  | On-Going
97 | Construction of RCC Foot Step near PC.Lalzuiliana House Ramthar | Rm | 14.6908 | 14.12.23 | 14.12.24 | - | - | 0% |  | 0% |  | Not yet started
98 | Construction of RCC Link Drain near PC.Lalzuiliana House at Ramthar | Rm | 8.3752 | 14.12.23 | 14.12.24 | - | - | 0% |  | 0% |  | Not yet started
99 | Construction of Breast Wall Below PC.Laltanpuia House at Ramthar North | Rm | 7.3314 | 14.12.23 | 14.12.24 | - | - | 0% |  | 0% |  | Not yet started
100 | Steel Grate Cover Side Drain on PC Malsawma House to Rev. C.Vanlalhruaia House at Ramhlun South | Rm | 8.04 | 14.12.23 | 14.12.24 | - | - | - | - | - | - | Not yet started
101 | Construction of RCC Foot Step near PC.Lalzuiliana House Ramthar | Rm | 16.58 | 14.12.23 | 14.12.24 | - |  | - |  | - |  | Not yet started
102 | Construction of RCC Link Drain near PC.Lalzuiliana House at Ramthar | Rm | 8.42 | 14.12.23 | 14.12.24 | - |  | - |  | - |  | Not yet started
103 | Construction of Breast Wall Below PC.Laltanpuia House at Ramthar North | Rm | 7.37 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
104 | Construction of Breast Wall near Pu.Lalrammuana Ralte House at Ramthar North | Rm | 5.76 | 14.12.23 | 14.12.24 | - |  | - |  | - |  | Not yet started
105 | Construction of RCC Foot Step near Pi.Manmawii House at Ramhlun South | Rm | 6.68 | 14.12.23 | 14.12.24 | - |  | - |  | - |  | Not yet started
IMPROVEMENT OF ROAD FROM DURTLANG LEITAN TO DURTLANG RAMTHAR AT DURTLANG
106 | Construction of Road at Selesih. Aizawl (Sh: Construction of Concrete Pavement and Culvert etc) | [5 empty] | 221.01 |  | - |  | 221.01
| 1. Concrete Pavement of Pu Dinga Road | Rm | 5 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
107 | Improvement of road at Durtlang North, Aizawl. (Sh: Construction of Concrete Pavement etc)
| 1. Construction of Concrete Pavement & Cross Drain on Vungkhama road inlcuding Chhingtei Road at Durtlang North | Rm | 15 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 2. Construction of Concrete Pavement of Durtlang North Thlanmual | Rm | 10 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
108 | Improvement of road at Durtlang, Aizawl. (Sh : Construction of Concrete Pavement, Cross Drain with cover, V Shape Side Drain, slab culvert and link Drain etc) | [5 empty] | - |  | -
| 1. Construction of PCC V shape Side Drain at Centenary Road & Women Polytechnic approach road at Durtlang | Rm | 5 | 14.12.23 | 14.12.24 | - |  | - |  | - |  | Not yet started
| 2. Concrete Pavement of Lalnu road at Suaka Veng, Durtlang (Balance Portion) | Rm | 5.4 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 3. Construction of Cross Drain with cover on Durtlang Field | Rm | 0.99516 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 4. Construction of Step including Link Drain at Centenary Road, Durtlang | Rm | 20 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
109 | Construction and Improvement of road at Durtlang Leitan, Aizawl.(Sh : Construction of Concrete Pavement, RCC frame Retaining Wall, Cross Drain with cover, U Shape Side Drain and link Drain etc)
| 1. Construction of PCC V Shape Side and Retaining Wall at Gospel Thunder Team compound, Durtlang Leitan | Rm | 20 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 2. Construction of RCC Frame RW at Zotui Road, Durtlang Leitan | Rm | 3.5 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 3. Patch repair of Durtlang Leitan SIRD Road | Km | 5.05 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
110 | Improvement of Road at Durtlang Ramthar, Aizawl (Sh : Construction of Concrete Pavement, Cross Drain and Re-Surfacing) | [5 empty] | - |  | -
| 1. Resurfacing of 3rd Lane at Durtlang Ramthar | Rm | 29.5 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 2. Concrete pavement of approach road to Durtlang Ramthar Prebyterian Church including cross drainage | Km | 30.5 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
111 | Improvement of Road at Chaltlang Lily veng, AizawL (Sh : Widening . of road, Construction of Concrete Pavement, RCC R/Wall and Re-Surfacing etc)
| 1. Resurfacing of Chaltlang Lily Veng internal road (Balance) | Km | 3 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 2. Reconstruction of step from State Guest House to Lily Veng internal road | Rm | 6 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 3. Construction of RCC Balcony & Masonry Step near R.lalmanga House at Chaltlang Lily Veng | Rm | 14 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
112 | Improvement of Road at Chaltlang, Aizawl. (Sh: Junction improvement. Construction of Concrete Pavement, U Shape drain, Retainning Wall & Step) | [5 empty] | - |  | - |  | -
| 1. Concrete Pavement of Road near F.Malsawma Residence at Chaltlang | Rm | 2.5 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 2. Construction of Retaining Wall & Concrete pavement on AMC Road at Dingdi Veng, Chaltlang | Rm | 9.7 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
113 | Improvement of Road at Bawngkawn, Aizawl. (Sh : Construction of Balcony, Link Drain, Retaing Wall & Concrete Pavement)
| 1. Construction of retaining Wall near Pu. Salemthara Residence at Brigade, Bawngkawn | Rm | 2.6 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 2. Concrete Pavement of Liansailova road, Bawngkawn | Rm | 10 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 3. Concrete Pavement of Shalom Road at Bawngkawn Hmar Veng (Balance Portion) | Rm | 10 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 4. Concrete Pavement on Upper Bawngkawn Hmar Veng | Rm | 4.5 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
114 | Construction of additional protection work at Bethel Veng | Rm | 13 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
IMPROVEMENT OF ROAD FROM ZEMABAWK TO LUNGBIAL ROAD IN THE LOCALITY OF ZEMABAWK AT AIZAWL
115 | CONSTRUCTION OF ROAD AT SIHPHIR | [5 empty] | 213.41 |  | - |  | 213.41
| i.Concrete pavement of approach road to Sihphir Rescue Center road at Sihphir Kawnveng | Rm | 8.8 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| ii.Formation Cutting , Concrete Pavement & Step of Sunhlu tlang (Prayer Mountain) at Sihphir Tlang Veng | Rm | 7.9 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| iii.Construction of Step including retaining wall near Pu Zakhuma House at Sihphir field veng | Rm | 3.66 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| iv.Construction of link Drain with cover near Pi Liani House at Sihphir Dinthar | Rm | 1.74 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| v.Construction of Link drain near Pu H.Lalfakzuala, Sihphir Dinthar | Rm | 2.61 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
116 | CONSTRUCTION OF CONCRETE PAVEMENT AT ZUANGTUI, AIZAWL
| i.RCC Balcony Gosen Veng to 132 KV substation at Zuangtui | Rm | 26.13 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
117 | CONCRETE PAVEMENT RIVENGA ROAD AT MUANNA VENG, AIZAWL
| i.Concrete Pavement of Rivenga Road at Muanna Veng | Rm | 7.3 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
118 | CONSTRUCTION OF ROAD AT MUTHI, AIZAWL | [7 empty] | - |  | -
| i.Concrete Pavement at ch:0.000 - 0.715kmp Muthi peng to kawn | Rm | 8.6 | 14.12.23 | 14.12.24 | 100% | - | - |  | 100% |  | Phy Completed | Restricted
119 | CONSTRUCTION OF ROAD AT NAUSEL
| i.Concrete Pavement at Nausel Thlanmual kawng | Rm | 8.2 | 14.12.23 | 14.12.24 | 100% | - | - |  | 100% |  | Phy Completed | Restricted
120 | IMPROVEMENT OF ROAD AT SIHPHIR VENGHLUN
| i.Construction of Retaining Wall at Thuampui Selesih road at Ch:4.300Kmp, Durtlang | Rm | 6.14 | 14.12.23 | 14.12.24 | 100% | - | - |  | 100% |  | Phy Completed | Restricted
121 | Construction of New Road from Zemabawk North Thlanmual to Thuampui Thlanmual including Protetion Works & Cross Drain
| i. Formation Cutting | Km | 51.36 | 14.12.23 | 14.12.24 | 100% | - | - |  | 100% |  | Phy Completed | Restricted
| ii. Construction of RCC Slab Culvert | No | 33.04 | 14.12.23 | 14.12.24 | 100% | - | - |  | 100% |  | Phy Completed | Restricted
122 | CONSTRUCTION OF ROAD AT FALKLAND, AIZAWL
| i.Construction of PCC Pavement on Local Council Road to RAY at Falkland | Rm | 27.79 | 14.12.23 | 14.12.24 | - | - | - | - | - | - | Not yet started
| ii.Construction of PCC Pavement on Rabboni Road at Falkland | Rm | 5.1404 | 14.12.23 | 14.12.24 | - | - | - | - | - | - | Not yet started
| iii.Construction of PCC Pavement on Local Council Road Falkland | Rm | 11.332 | 14.12.23 | 14.12.24 | - | - | - | - | - | - | Not yet started
| iv.PCC Pavement on Approach Road to Vai Lui via Rev Lalsangliana's House at Falkland Veng | Rm | 5.7395 | 14.12.23 | 14.12.24 | - | - | - | - | - | - | Not yet started
SUB - DIVISION - III
CONSTRUCTION OF PCC PAVEMENT AT SIHHMUI TO NH-54. (LENGTH = 7.00Kms, PCC PAVEMENT = 7.00Kms)
123 | Widening of road from Law college to PCI road at Luangmual, Aizawl (Sh: Earth Work for Widening of existing road) | Rm. | 11.95 | 2023-12-14 | 2024-12-14 | 100% | 190.85 | - | - | 100% | 190.85 | Phy Completed | Restricted
124 | Improvement & Upgradation of road at Chawlhhmun, Aizawl |  | 26 | 2023-12-14 | 2024-12-14
| Sh: 1. Construction of PCC Pavement of Pu Muantea's road at Chawlhhmun | Rm. |  |  |  | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 2. Construction of PCC Pavement near Pu Fabiana's house at Chawlhhmun | Rm. |  |  |  | 100% |  | - |  | 100% |  | Phy Completed | Restricted
125 | Improvement & Upgradation of road at Zotlang, Aizawl |  | 20.29 | 2023-12-14 | 2024-12-14 |  | - |  | - |  | -
| Sh: 1. Construction of RCC Pavement at Zotlang to Zohnuai | Rm. |  |  |  | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 2. Construction of Retaining Wall for Pi Romawii Approach Road at Zotlang | Rm. |  |  |  | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 3. Construction of RCC Pavement at Zotlang to Zohnuai Biak In | Rm. |  |  |  | 100% |  | - |  | 100% |  | Phy Completed | Restricted
126 | Construction of approach road (RCC Pavement) to Community Hall (NH 44A) at Sihhmui | Rm. | 15.91 | 2023-12-14 | 2024-12-14 | 100% |  | - |  | 100% |  | Phy. Completed | Restricted
127 | Improvement & Upgradation of road from PCI to Anganwadi at Lungverh |  | 77.98 | 2023-12-14 | 2024-12-14
| Sh: 1. Construction of RCC Pavement from PCI to Anganwadi at Lungverh | Rm. |  |  |  | 100% |  | - |  | 100% |  | Phy. Completed | Restricted
| 2. Construction of RCC Slab Culvert at Thlanmual kawr | Rm. |  |  |  | 100% |  | - |  | 100% |  | Phy. Completed | Restricted
| 3. Construction of RCC Slab Culvert at Pu Rinnunga kawmthlang | Rm. |  |  |  | 100% |  | - |  | 100% |  | Phy. Completed | Restricted
| 4. Retaining wall at F Suakliana Kawmchhak | Rm. |  |  |  | 100% |  | - |  | 100% |  | Phy. Completed | Restricted
128 | Rangvamual internal road | Rm | 23.27 |  |  | 100% |  | - |  | 100% |  | Phy. Completed | Restricted
129 | Phunchawng internal road | Rm | 19.2 |  |  | 100% |  | - |  | 100% |  | Phy. Completed | Restricted
IMPROVEMENT OF INTERNAL ROADS AT HUNTHAR, CHANMARI WEST, RANGVAMUAL, PHUNCHAWNG & CHHINGA VENG. (IMPROVEMENT OF ROADS PCC PAVEMENT = 20.00 KMS, PAVEMENT = 5.00 KMS, LINK DRAIN = 100.00M)
130 | Patch Repair and Seal Coating of Approach Road to Tanhril, Aizawl | Rm | 23.08 | 2023-12-14 | 2024-12-14 | 100% | 59.03 | - | - | 100% | 59.03 | Phy. Completed | Restricted
131 | Construction of PCC Pavement of Approach Road to Tawngtai Bethel Camping Centre, Sakawrtuichhun, Aizawl | Rm. | 9.49 | 2023-12-14 | 2024-12-14 | 100% |  | - |  | 100% |  | Phy. Completed | Restricted
132 | Rigid Pavement of Gan Sabra Road | Rm. | 19.33 | 2023-12-14 | 2024-12-14 | 100% |  | - |  | 100% |  | Phy. Completed | Restricted
133 | Construction of PCC Pavement of Road from Saikaphleia' House to Muanthanga's House at Lungverh. Length = 120.00Rm. | Rm. | 9.49 | 2023-12-14 | 2024-12-14 | 100% |  | - |  | 100% |  | Phy. Completed | Restricted
CONSTRUCTION OF LUNGHLU ROAD AT CHANMARI WEST AIZAWL (Length = 4.00Kms, Ew = 4.00Kms, Pavement = 4.00Kms, Side Drain = 4500m, R/W 30m, Culvert = 10.Nos)
134 | Construction of RCC Frame structure Retaining Wall I at Lunghlu Road, Hunthar | Rm | 14.49 | 2023-12-14 | 2024-12-14 | 100% | 140.02 | - | - | 100% | 140.02 | Phy. Completed | Restricted
135 | Patch repair and Seal coat of MUP Road at Chanmari West, Aizawl | Rm | 11.5532 | 2023-12-14 | 2024-12-14 | 100% |  | - |  | 100% |  | Phy. Completed | Restricted
136 | Patch repair and Seal Coat from BT Bakery to Protective Home Via Zarkawt Thlanmual | Rm | 29.9487 | 2023-12-14 | 2024-12-14 | 100% |  | - |  | 100% |  | Phy. Completed | Restricted
137 | Construction of RCC Road at Methodist mual Turning Point to Edenthar Anganwadi Centre No. 1 at Edenthar | Rm | 8.76 | 2023-12-14 | 2024-12-14 | 100% |  | - |  | 100% |  | Phy. Completed | Restricted
138 | Rigid Pavement of Gan Sabra Road | Rm. | 16.86 | 2023-12-14 | 2024-12-14 | 100% |  | - |  | 100% |  | Phy. Completed | Restricted
139 | Construction of PCC Pavement of Road from Saikaphleia' House to Muanthanga's House at Lungverh. Length = 120.00Rm. | Rm. | 10.06 | 2023-12-14 | 2024-12-14 | 100% |  | - |  | 100% |  | Phy. Completed | Restricted
CONSTRUCTION OF LUNGHLU ROAD AT CHANMARI WEST AIZAWL (Length = 4.00Kms, Ew = 4.00Kms, Pavement = 4.00Kms, Side Drain = 4500m, R/W 30m, Culvert = 10.Nos)
140 | Construction of RCC Frame structure Retaining Wall I at Lunghlu Road, Hunthar | Rm | 14.5 | 2023-12-14 | 2024-12-14 | 100% | 140.02 | - | - | 100% | 140.02 | Phy Completed
141 | Patch repair and Seal coat of MUP Road at Chanmari West, Aizawl | Rm | 11.5532 | 2023-12-14 | 2024-12-14 | 100% |  | - |  | 100% |  | Phy. Completed | Restricted
142 | Patch repair and Seal Coat from BT Bakery to Protective Home Via Zarkawt Thlanmual | Rm | 29.9487 | 2023-12-14 | 2024-12-14 | 100% |  | - |  | 100% |  | Phy Completed
143 | Construction of RCC Road at Methodist mual Turning Point to Edenthar Anganwadi Centre No. 1 at Edenthar | Rm | 8.76 | 2023-12-14 | 2024-12-14 | 100% |  | - |  | 100% |  | Phy. Completed | Restricted
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER, 2025 UNDER ARND
Name of Work : Construction of Approach Road to IGC Complex, Luangmual under SASCI Part V of 2024-2025 | [7 empty] | Name of Contractor: Zonunpuii, Kolasib Hmar Veng
Agreement Amount : ₹ 4,80,67,489.00 | [7 empty] | Date of Commencement: 03.07.2025
Agreement No.: AGM-2/SE-CC/PWD/2025-2026 Dt. 18.06.2025 | [7 empty] | Target date of Completion: 03.07.2026
Name of Division : Aizawl Road North Sub-Division-III
Source of funding: SASCI-V
Overall Physical Achievement : 4.14%
Sl. No. | Name of Project | Unit |  | Approved Cost (Rs. in lakh) | Date of Commencement | Target date of completion | Cumulative Progress at the end of last month |  | Achievement works during the month |  | Overall cummulative achievement |  | Remarks | Mode of contract
[7 empty] | Phy. | Fin. | Phy. | Fin. | Phy. | Fin.
1 | 3 | 3 |  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Improvement of IGC, Luangmual |  |  | 5: 2025-07-03; 6: 2026-07-03
a | Earthwork | 200 | Rm | 4: 978568
b | Flexible Pavement | 1500 | Rm | 4: 20821135
c | Re-construction of slabs culvert | 4 | No. | 4: 988218; 7: 25%; 9: 5%; 11: 30%; 13: Work in Progrees; 14: Item Rate
d | Hume Pipe Culvert | 5 | No. | 4: 1545232
e | Retaining Wall | 60 | Rm | 4: 1773085; 7: 17%; 9: 0%; 11: 17%; 13: Work in Progrees; 14: Item Rate
f | RCC Line side drain with cover | 200 | Rm | 4: 1374490
g | Trapezoidal side drain | 500 | Rm | 4: 1632485
2 | Improvement of road from Tanhril Presbyterian Church to MZU
a | Flexible Pavement | 800 | Rm | 4: 6170189
b | Hume Pipe Culvert | 2 | No. | 4: 996811; 7: 100%; 9: 0%; 11: 100%; 14: Item Rate
3 | Improvement of road from Tlana Lungdawh kawn to PWD Site |  |  | 5: 2025-07-03; 6: 2026-07-03
a | Earthwork | 980 | Rm | 4: 1456657; 7: 5%; 9: 0%; 11: 5%; 13: Work in Progrees; 14: Item Rate
b | Rigid Pavement | 1000 | Rm | 4: 7526950
c | Flexible Pavement | 800 | Rm | 4: 1308555
d | Hume Pipe Culvert | 3 | No. | 4: 1495114; 7: 25%; 9: 5%; 11: 30%; 13: Work in Progrees; 14: Item Rate
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER, 2025 UNDER ARND
Name of Work : Improvement of Road from Ainawn to Tuithum |  |  |  | 8: Name of Contractor: F. Lalmalsawma, Tuikual
Agreement Amount : ₹ 16,35,30,525.00 |  |  |  | 8: Date of Commencement: 15.07.2025
Agreement No.: AGM-3/SE-CC/PWD/2025-2026 Dt. 01.07.2025 |  |  |  | 8: Target date of Completion: 15.07.2026
Name of Division : Aizawl Road North Sub-Division-III
Source of funding: SASCI-V
Overall Physical Achievement : 1.36%
Sl. No. | Name of Project | Unit |  | Approved Cost (Rs. in lakh) | Date of Commencement | Target date of completion | Cumulative Progress at the end of last month |  | Achievement works during the month |  | Overall cummulative achievement |  | Remarks | Mode of contract
[7 empty] | Phy. | Fin. | Phy. | Fin. | Phy. | Fin.
1 | 2 | 3 |  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Earthwork | 4682 | Rm | 20371452 | 2025-07-15 | 2026-07-15 | 7% | - | 3% | - | 10% |  | Work in Progress | Item Rate
2 | RCC side drain | 2000 | Rm | 4: 7896319
3 | RCC Slab Culvert | 4 | No. | 4: 2912158
4 | Hume Pipe Culvert | 5 | No. | 2614215 |  |  | 30% | - | 0% | - | 30% |  | Work in Progress | Item Rate
5 | Retaining Wall | 200 | Rm | 9720546 |  |  | 6% | - | 1% | - | 7% |  | Work in Progress | Item Rate
6 | RCC Frame Structure Retaining Wall | 70 | Rm | 4: 3729602
7 | Minor Bridge | 4 | No. | 4: 23515882
8 | Rigid Pavement | 2380 | Rm | 4: 74239201
9 | Flexible Pavement | 2000 | Rm | 4: 18531150
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER, 2025 UNDER ARND
Name of Work : Construction of Various Earth Retaining and Drainage Structure for Mitigation of Vaivakawn Zohnuai Subsidence Areas |  |  |  | 8: Name of Contractor: Jenny Lalthansangi, Vavakawn Zohnuai
Agreement Amount : ₹ 16,35,30,525.00 |  |  |  | 8: Date of Commencement: 15.07.2025
Agreement No.: AGM-4/SE-CC/PWD/2025-2026 Dt. 01.07.2025 |  |  |  | 8: Target date of Completion: 01.03.2026
Name of Division : Aizawl Road North Sub-Division-III
Source of funding: SASCI-V
Overall Physical Achievement : 25%
Sl. No. | Name of Project | Unit |  | Approved Cost (Rs. in lakh) | Date of Commencement | Target date of completion | Cumulative Progress at the end of last month |  | Achievement works during the month |  | Overall cummulative achievement |  | Remarks | Mode of contract
[7 empty] | Phy. | Fin. | Phy. | Fin. | Phy. | Fin.
1 | 2 |  | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Breast Wall on lower side of Pu Sangthanmawia's Land. | 20 | Rm | 915550 | 2025-07-15 | 2026-03-01 | 100% |  | - |  | 100% |  | Phy Completed | Item rate
2 | Construction of Breast Wall on Uphill side of RK Road. | 30 | 3: Rm; 4: 3792520; 7: 0%; 9: 0%; 11: 0%; 13: Not yet started
3 | Construction of Composite Retaining Wall (Section 1) above NH-6 | 28 | 3: Rm; 4: 8041065; 7: 45%; 9: 0%; 11: 45%; 13: Work in Progress
4 | Construction of Composite Retaining Wall(Section 2) above NH-6 | 28 | 3: Rm; 4: 5808526; 7: 70%; 9: 0%; 11: 70%; 13: Work in Progress
5 | Construction of Breast Wall above NH-6(below RK Road) | 25 | 3: Rm; 4: 1147430; 7: 100%; 9: 0%; 11: 100%; 13: Work in Progress
6 | Construction of Breast Wall on Uphill Side of NH-6 (Near Link Drain) | 15 | 3: Rm; 4: 617879; 7: 100%; 9: 0%; 11: 100%; 13: Work in Progress
7 | Construction of RCC Line Drain below NH-6(50 m) | 50 | 3: Rm; 4: 775315; 7: 0%; 9: 0%; 11: 0%; 13: Not yet started
8 | Construction of RCC Side Drain along NH-6 (Near Culvert,20 m) | 20 | 3: Rm; 4: 259995; 7: 0%; 9: 0%; 11: 0%
9 | Construction of Retaining Wall at Nutumi Road | 35 | Rm | 2577091 | 2025-07-15 | 2026-03-01 | 20% |  | 20% |  | 40% |  | Work in Progress | Item rate
10 | Construction of Hume Pipe Culvert at MZU Road | 1 | 3: No.; 4: 366606; 7: 0%; 9: 0%; 11: 0%; 13: Not yet started
11 | Construction of side drain at Various places | 1217 | 3: Rm; 4: 5222600.48; 7: 0%; 9: 5%; 11: 5%; 13: Work in Progress
12 | Clearance of link drain at various places | 122 | 3: Rm; 4: 91500; 7: 0%; 9: 20%; 11: 20%; 13: Work in Progress
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER, 2025 UNDER ARND
Name of Work : Restoration Of Damage Due To Cyclone Remal Under Aizawl Road North Division, Aizawl Road South Division And Hmuifang Division |  |  | 7: Name of Contractor : Fredy Vanlalngila, Dinthar-I
Agreement Amount : ₹ 11,24,97,994.21 |  |  | 7: Date of Commencement : 27.06.2025
Agreement No.: 4/CE-HW/2025-2026 Dt. 01.06.2025 |  |  | 7: Target date of Completion :27.01.2026
Name of Division : Aizawl Road North Division
Source of funding: Cyclone Remal
Sl. No. | Name of Project | Unit | Approved Cost (Rs. in lakh) | Date of Commencement | Target date of completion | Cumulative Progress at the end of last month |  | Achievement works during the month |  | Overall cummulative achievement |  | Remarks | Mode of contract
[6 empty] | Phy. | Fin. | Phy. | Fin. | Phy. | Fin.
1 | 2 |  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Retaining Wall below Zoramthanga's House | Rm | 20 | 2025-07-01 | 2026-01-31 | 0% | - | 18% | - | 18% | Rs. 73.68 lakhs bill forwarded to Executive Engineer, Aizawl Road South Division for payment being the Nodal Officer for payment | Not yet started
2 | Restoration of H/P Culvert at Falkland | Nos | 5 |  |  | 100% | - | - | - | 100% |  | Phy Completed | Item Rate
3 | Restoration of Breast Wall at Armed Veng South | Rm | 6 |  |  | 100% | - | - | - | 100% |  | Phy Completed | Item Rate
4 | Restoration of Retaining Wall Collapsed at Ramthar North | Rm | 18.01 |  |  | 0% | - | 100% | - | 100% |  | Not yet started
5 | Construction of Retaining Wall at Falkland | Rm | 3 |  |  | 100% | - | - | - | 100% |  | Phy Completed | Item Rate
6 | Construction of Retaining Wall at Thuampui Vengthar | Rm | 8 |  |  | 0% | - | 80% | - | 80% |  | Work in Progress
7 | Construction of Gabion Wall on Darnamlui for Restoration of formation edge collapsed at Ramthar North, Aizawl | Rm | 90.44 |  |  | 0% | - | 9% | - | 9% |  | Work in Progress
8 | Construction of Breast wall at Berawtlang | Km | 20.58 | 1.7.2025 | 30.7.2025 | 100% | - | - | - | 100% | Rs. 73.68 lakhs bill forwarded to Executive Engineer, Aizawl Road South Division for payment being the Nodal Officer for payment | Phy Completed | Item Rate
9 | Construction of Breast wall at Thuampui to Selesih road at Ch:6.000kmp | Km | 21.08 | - | - | 0% | - | 0% | - | 0% |  | Not yet started
10 | Widening of Lungbial road for diversion of collapsed Balcony on approach road to Berawtlang | Km | 41.06 | - | - | 0% | - | 0% | - | 0% |  | Not yet started
11 | Construction of retaining wall near Pu Lalzarzoliana's house at Lungbial | Km | 2 | 1.7.2025 | 22.7.2025 | 100% | - | - | - | 100% |  | Phy Completed | Item Rate
12 | Construction of Reataining wall at Thuampui to Selesih at Ch:11.800 kmp | Km | 2.43 | 1.7.2025 | 30.7.2025 | 100% | - | - | - | 100% |  | Phy Completed | Item Rate
13 | Construction of RCC balcony at Gosen veng at Zuangtui | Km | 17.89 | - | - | 0% | - | 0% | - | 0% |  | Not yet started
14 | Construction of RCC Rectangular side drain at RIPANS at Zemabawk | Km | 22.01 | - | - | 0% | - | 100% | - | 100% |  | Phy Completed
15 | Construction of Retaining wall at Thuampui to Selesih road at Ch:2.200 kmp | Km | 7.98 | 1.7.2025 | 18.7.2025 | 100% | - | - |  | 100% |  | Phy Completed | Item Rate
16 | Repair of Culvert and Retaining Wall @ ch. 3.900 Kmp at MZU Road | Rm | 3.61 | 2025-06-27 | 2026-01-27 | 100% |  | - |  | 100% |  | Phy Completed | Item Rate
17 | Construction of Retaing Wall @ ch. 6.325 Kmp at MZU Road | Rm | 4: 4.14; 7: 100%; 9: -; 11: 100%; 13: Phy Completed; 14: Item Rate
18 | Construction of Retaing Wall at approach road to Tanhril at 0.200 Kmp | Rm | 4: 3.61; 7: 100%; 9: -; 11: 100%; 13: Phy Completed; 14: Item Rate
19 | Construction of Retaining Wall @ ch. 1.600 Kmp on NH-54 to Sakawrtuichhun Road | Rm | 4: 7.88; 7: 100%; 9: -; 11: 100%; 13: Phy Completed; 14: Item Rate
20 | Construction of Retaining Wall @ ch. 0.980 Kmp on Zohnuai to Ropaiabawk road | Rm | 11.77 | 2025-06-27 | 2026-01-27 | 50% |  | 30% |  | 80% | Rs. 73.68 lakhs bill forwarded to Executive Engineer, Aizawl Road South Division for payment being the Nodal Officer for payment | Work in Progress | Item Rate
21 | Construction of Retaining Wall @ ch. 0.200 Kmp on NH-54 to Sakawrtuichhun Road | Rm | 4: 9.44; 7: 100%; 9: -; 11: 100%; 13: Phy Completed; 14: Item Rate
22 | Construction of Retaining near Pu B. Lalhmingsanga's house at Zonuam | Rm | 4: 1.84; 7: 100%; 9: -; 11: 100%; 13: Phy Completed; 14: Item Rate
23 | Construction of Retaining Wall at MUP road, Chanmari West | Rm | 4: 6.02; 7: 100%; 9: -; 11: 100%; 13: Phy Completed; 14: Item Rate
24 | Construction of Retaining Wall @ ch. 1.550 Kmp on Zohnuai to Ropaiabawk Road | Rm | 4: 7.1; 7: 80%; 9: 20%; 11: 100%; 13: Phy Completed; 14: Item Rate
25 | Construction of Retaining Wall @ ch. 1.150 on Zohnuai to Ropaiabawk road | Rm | 4: 10.05; 7: 100%; 9: -; 11: 100%; 13: Work in Progress; 14: Item Rate
26 | Restoration of Sinking portion near Sangthanmawia's house, Vaivakawn | Rm | 4: 70.45; 7: 5%; 9: 20%; 11: 25%; 13: Work in Progress; 14: Item Rate
27 | Construction of Retaining Wall near Pi Zaihnuni's house at Chawnpui | Rm | 4: 5.88; 7: 100%; 9: -; 11: 100%; 13: Work in Progress; 14: Item Rate
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER, 2025 UNDER ARND
Name of Work : Restoration Of Damage Due To Cyclone Remal Under Aizawl Road North Division (Part-II) And National Highway Division-III |  |  | 9: Name of Contractor : Kevin Vanlaltlana, Bungkawn
Agreement Amount : ₹ 11,24,97,994.21 |  |  | 9: Date of Commencement : 13.06.2025
Agreement No.: 4/CE-HW/2025-2026 Dt. 01.06.2025 |  |  | 9: Target date of Completion :13.01.2026
Name of Division : Aizawl Road North Sub-Division-III
Source of funding: Cyclone Remal
Overall Physical Achievement : 100%
Sl No | Name of Project | Unit |  | Approved Cost (Rs. in lakh) | Date of Commencement | Target date of completion | Cumulative Progress at the end of last month |  | Achievement works during the month |  | Overall cummulative achievement |  | Remarks | Mode of contract
[7 empty] | Phy. | Fin. | Phy. | Fin. | Phy. | Fin.
1 | 2 | 3 |  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Improvement of side drain and cross drain at Zotlang internal road | 30 | Rm | 259355.69 | 2025-06-13 | 2026-01-13 | 100% | - | - | - | 100% | Rs. 16.14 lakhs bill forwarded to Executive Engineer, National Highway Division - III, for payment being the Nodal Officer for payment | Phy Completed | Item Rate
2 | Construction of V shape side drain from Lalhmingliana Hnamte house to T. Lalzapi's house at Zotlang | 100 | Rm | 4: 386896.83; 7: 100%; 9: -; 11: 100%; 13: Phy Completed; 14: Item Rate
3 | Construction of V shape side drain from C. Thanchhuma house to Rosiamliana Ralte's house at Zotlang | 40 | Rm | 4: 154811.1; 7: 100%; 9: -; 11: 100%; 13: Phy Completed; 14: Item Rate
4 | Construction of drain below Pu Lalduhawma's house at Chawlhhmun | 77 | Rm | 4: 812604.91; 7: 100%; 9: -; 11: 100%; 13: Phy Completed; 14: Item Rate

## ARSD
MONTHLY PROGRESS REPORT UNDER AIZAWL ROAD SOUTH DIVISION, PWD
FOR THE MONTH OF OCTOBER 2025
Sl. No. | Name of Schemes | Unit | Approved Cost (Rs in Lakh) | Date of Commencement | Target Date of Comple-tion | Cumulative Progress at the end of last month |  | Achievement of works during the month |  | Overall Cumulative achievement |  | Remarks | Mode of Tender
| Name of Works / Project |  |  |  |  | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
I | SEDP (2019-2020)
1 | Const.of Approach Road to Aizawl College at Mualpui | Rm | 415 | 2021-07-26 | 2022-04-26 | 73% | 300 |  |  | 73% | 300 | On Going ES was accorded vide No.B.12031/17/2019-PWD(T) Dt.26.3.2020 (Rs.100 lakhs); No.G.20016/3/2021-FBT Dt.7.10.2021 (Rs.100 lakhs) and No. B.12031/29/2021-PWD(T) dt. 01.03.2023 respectively, which totalled Rs.300 out of Rs. 415.00. The remaining balance/ ES was asked for Approval vide No.B.16012/6/22/T(ARS)/I/5 Dt.29th Sept,2022. It was regretted due to Financial Constraint as the year has been declared as year of consolidation vide No. B. 12031/17/2019-PWD(T) dt. 23rd July, 2024. | Item Rate Contract
II | NEDP (2018-2019)
1 | Construction of Bridge on Chhinga Vengthar to Tuithiang road | Rm | 586.36 | 2021-04-19 | 2022-10-31 | 100% | 200 |  |  | 100% | 200 | Physical Works Completed according to Working Estimate E/S Amount of Rs.200.00 Lakh. The remaining ES was asked for Allocation vide No.B.16011/69-C/15/T(ARS)/28 dated: 23rd Jan, 2023 in which balance ES from Higher Authority is awaited. | Restricted tender
III | Central Road Fund
1 | Construction of BUG Bridge over R.Tlawng on Aizawl - Reiek - W.Lungdar Road at 14.800 Kmp | Rm | 757.56 | 10:10 | 31.10.24 | 100% | 750.57 |  |  | 100% | 750.57 | Work Completed | EPC mode
IV | SASCI (2022-2023)
i) | Widening of Approach Road to City Bus Parking at S.Hlimen, Aizawl (Melthum - Hlimen Road) under SASCI 2022-2023. | Rm | 576 | 2023-04-07 | 28.5.25 | 100% | 468.39 |  | 102.75 | 100% | 571.14 | Work Completed | Restricted tender
V | Strengthening and Improvement of State Highways & Other Roads under Mizoram under Central Circle
1 | Construction of Rigid pavement on Sihpui tuikhur to Aizawl By-Pass road at Kulikawn | Rm | 40.39 | 2024-12-13 | 13.2.25 | 100% | 23.68 |  | 16.71 | 100% | 40.39 (100%) | Work Completed | Open tender
2 | Construction of Side Drain Cover on Approach Road to SAI at Mission Vengthlang | Rm | 17.19 | 2024-12-13 | 2025-06-13 | 100% | 15.55 |  | 1.64 | 100% | 17.19 (100%) | Work Completed | Open tender
3 | Construction of Rigid Pavement on Approach road to Tlangnuam new Cemetery | Rm | 17.85 | 2025-02-21 | 7.4.25 | 100% | 16.15 |  | 1.7 | 100% | 17.85 (100%) | Work Completed | Open tender
4 | Improvement of Aizawl-Reiek-W.Lungdar road | Rm | 124.05 | 2024-11-04 | 2025-03-22 | 100% | 91.38 |  |  | 100% | 91.38 | Work Completed | Departmental
5 | Improvement of Sinking Area on Bypass Road at Ch.0+800kmp (Sh. Widening) | Rm | 6.82 | 19:03 | 21:03 | 100% | 0 |  |  | 100% | - | Work Completed | Departmental
VI | PMGSY
1 | Upgradation & Maintenance of Hlimen to Samtlang to Lungleng Road | Rm | 1132.5 | 2024-10-23 | 2026-04-23 | 14% |  | 0% |  | 14% |  | On going | Restricted tender
VII | Cyclone Remal Fund
1 | Pothole repairs on Bethlehem Kawn to Aizawl Bypass Road | Sqm | 11.2 | 23:04 | 16:05 | 100% |  |  |  | 100% | 33.72 (100%) | Work Completed | Departmental
2 | Pothole repairs on Falkland Internal Road at ITI (Falkland Street) | Sqm | 0.6 | 1:05 | 7:05 | 100% |  |  |  | 100% |  | Work Completed | Departmental
3 | Pothole repairs on Tuikhuahtlang Taxi Stand to Pu R. Lalawia's House | Sqm | 0.6 | 8:05 | 14:05 | 100% |  |  |  | 100% |  | Work Completed | Departmental
4 | Pothole repairs on Approach Road to T. Romana College | Sqm | 3 | 5:05 | 21:05 | 100% |  |  |  | 100% |  | Work Completed | Departmental
5 | Pothole repairs on Sihtuikhur to Tuithiang | Sqm | 4.3 | 15:05 | 30:05 | 100% |  |  |  | 100% |  | Work Completed | Departmental
6 | Pothole repairs of ISPW to Khatla Thlanmual Road | Sqm | 5.94 | 2:04 | 29:04 | 100% |  |  |  | 100% |  | Work Completed | Departmental
7 | Pothole repairs of Samtlang Internal Road | Sqm | 8.08 | 19:06 | 9:07 | 100% |  |  |  | 100% |  | Work Completed | Departmental
VIII | Maintenance Action Plan 2025-2026 (3054)
1 | Patch repair of Approach Road to Health Minister Bungalow & Deputy Speaker Bungalow at Tuikhuahtlang | Sqm | 7.46 | 1:09 | 19:09 | 100% |  | - |  | 100% |  | Work Completed
2 | Resurfacing of approach road to Damdiai Veng, Tlangnuam Vengthar | Sqm | 3 | [8 empty] | Not yet started
3 | Resurfacing of approach road to Hridaikawn to Power Sub Station | Sqm | 8.94 | 4:09 | 29:09 |  |  | 100% |  | 100% |  | Work Completed
4 | Resurfacing of Saikai to Multi Farming Co-operative Society at Reiek | Sqm | 3.87 | [8 empty] | Not yet started
5 | Resurfacing of Approach road to PHC Via PWD IB at Reiek | Sqm | 4.34 | [8 empty] | Not yet started
6 | Resurfacing of Sikulpuikawn to Mission Veng Presbyterian Church (Saptawni Road) | Sqm | 4.08 | 3:11 | 8:11 |  |  | 100% |  | 100% |  | Work Completed
7 | SMBT of approach road to play field, Tlangnuam | Sqm | 5.18 | 3:09 | 15:09 |  |  | 100% |  | 100% |  | Work Completed
8 | Resurfacing of approach road to Pika road | Sqm | 7.53 | [8 empty] | Not yet started
9 | Patch Repair of Approach Road to MLA Quarter at Khatla Bethel Tlang | Sqm | 1.44 | 27:10 | 31:10 |  |  | 100% |  | 100% |  | Work Completed
10 | Patch repair of Venghlui to Bethlehem (Lower) | Sqm | 3.56 | 2:09 | 15:09 | 100% |  | - |  | 100% |  | Work Completed
11 | Construction of Pavement and RCC drain with steel cover near Pu F.Kapsanga building on Bazar Bungkawn to Sikulpuikawn road | Rm | 2.01 | 1:09 | 8:09 |  |  | 100% |  | 100% |  | Work Completed
12 | Reconstruction of Pavement near Pu Lalmuanpuia Punte, MLA Quarter | Sqm | 1.21 | 17:04 | 23:04 | 100% | 1.2 |  | 1.2 | 100% | 1.2 | Work Completed | Departmental
13 | Patch Repair of approach road to Anganwadi Centre, Tlangnuam Vengthar | Sqm | 2.13 | 8:09 | 17:09 |  |  | 100% |  | 100% |  | Work Completed
14 | Resurfacing of approach to PHC Lungleng | Sqm | 4.27 | [8 empty] | Not yet started
15 | Resurfacing of Ailawng Internal Road | Sqm | 5.85 | [8 empty] | Not yet started
16 | Resurfacing of Maubawkkawn to Maubawk Tlangveng | Sqm | 3.7 | [8 empty] | Not yet started
17 | Pavement of widened portion of road on Khatlakawn to Vety Hospital Road | Rm | 4 | 6:10 | 15:10 |  |  | 100% |  | 100% |  | Work Completed
18 | Patch repair of Venghlui to College Veng | Sqm | 1.48 | 17:09 | 23:09 | 100% |  | - |  | 100% |  | Work Completed
19 | Patch repair of Officer Training Centre internal road at Mualpui | Sqm | 2.89 | 3:09 | 16:09 | 100% |  | - |  | 100% |  | Work Completed
20 | Resufacing of approach road to Zobawm Veng Kulikawn | Sqm | 7.4 | 9:09 |  |  |  | 50% |  | 50% |  | On going
21 | Patch repair of Tuikhuahtlang Taxi Stand to DC Bungalow | Sqm | 3.04 | 3:09 | 12:09 | 100% |  | - |  | 100% |  | Work Completed
22 | Resurfacing of Nursery to Maubawkkawn | Sqm | 22.73 | 10:11 |  |  |  | 20% |  | 20% |  | Not yet started
23 | Resurfacing of approach road to Muanna in, Mualpui, Salem | Sqm | 16.12 | 8:09 |  | 25% |  | 75% |  | 100% |  | Work Completed
24 | Construction of Retaining Wall at Ch 0.250 Kimp approach road to community hall, Hlimen. | Rm | 7.03 | [8 empty] | Not yet started
25 | Construction of Cross drain at Maubawkkawn | No. | 2.46 | 9:05 | 26:05 | 100% |  | - |  | 100% |  | Work Completed | Departmental
26 | Improvement of drain at T.Romana College Junction, ITI | Rm | 1.49 | 15:08 | 2:09 | 100% |  | - |  | 100% |  | Work Completed | Departmental
27 | Extension of culvert at ITI Veng Link Road-II Turning Point | Rm | 3.17 | 1:08 | 2025-08-29 | 100% |  | - |  | 100% |  | Work Completed | Departmental
28 | Re Construction of Culvert Abutment & Cover slab at ch. 2.450 kmp on Aizawl - Reiek - W.Lungdar road | Rm | 3.71 | 22:09 | 11:11 | 30% |  | 70% |  | 100% |  | Work Completed | Departmental
29 | Construction of Breast Wall on Approach road to Mission Vengthlang Cemetry | Rm | 3.91 | 29:09 | 13:10 |  |  | 100% |  | 100% |  | Work Completed | Departmental
30 | Widening of road by dismantling water tank near Pu Khawlthanseia's House on Kaisara Road | Rm | 3.56 | [8 empty] | Not yet started | Departmental
31 | Balcony for road extension on Nursery to Mission Veng via City Hospital Road | Rm | 7.92 | 14:04 | 30:04 | 100% |  |  |  | 100% |  | Work Completed | Departmental
32 | Extension of RCC Slab Culvert at Ch: 26.700 Kmp on Aizawl-Reiek-W. Lungdar | Rm | 9.55 | 22:09 | 11:10 | 20% |  | 80% |  | 100% |  | Work Completed | Departmental
33 | Improvement of approach road to Bethlehem Vengthlang thlanmual with PCC flooring | Sqm | 6.74 | 2025-08-13 | 9:09 | 100% |  | - |  | 100% |  | Work Completed | Departmental
34 | Re-construction of RCC Balcony at approach road to Salem Chhim Veng | Rm | 25 | 2025-08-04 |  | 60% |  | 40% |  | 100% |  | Work Completed | Departmental
35 | Pothole repair of Aizawl city roads within Aizawl Road South Division
1) | Pothole Repairs on Bethlehem Vengthlang to Lower Thingdawlruam | Sqm | 1.8 | 2025-05-13 | 2025-05-21 | 100% | 1.2 | - | 0.55 | 100% | 1.75 | Work Completed | Departmental
2) | Pothole Repairs on Bethlehem Vengthlang Internal Road | Sqm | 3 | 2025-05-22 | 2025-06-03 | 100% | 1.98 | - | 0.93 | 100% | 2.91 | Work Completed | Departmental
3) | Pothole Repairs on Approach Road to Bethlehem Vengthlang High School | Sqm | 2 | 2025-06-04 | 2025-06-13 | 100% | 1.33 | - | 0.61 | 100% | 1.94 | Work Completed | Departmental
4) | Pothole Repairs on Southern Gate of Raj Bhavan to Republic 6-B | Sqm | 0.8 | 2025-04-01 | 2025-04-09 | 100% | 0.56 | - | 0.19 | 100% | 0.75 | Work Completed | Departmental
5) | YMA Lungphun to Bethlehem Vengthlang Kawn | Sqm | 2.3 | 2025-06-16 | 2025-06-26 | 100% | 1.68 | - | 0.55 | 100% | 2.23 | Work Completed | Departmental
6) | Pothole Repairs on PCCF Office to Sikulpuikawn | Sqm | 1.8 | 2025-04-07 | 2025-04-16 | 100% | 1.33 | - | 0.41 | 100% | 1.74 | Work Completed | Departmental
7) | Pothole Repairs on Approach Road to Republic Playfield South | Sqm | 1 | 2025-05-01 | 2025-05-09 | 100% | 0.65 | - | 0.32 | 100% | 0.97 | Work Completed | Departmental
8) | Pothole Repairs on ITI Junction to Vengchhak Presbyterian Church | Sqm | 1 | 2025-05-19 | 2025-05-27 | 100% | 0.66 | - | 0.31 | 100% | 0.97 | Work Completed | Departmental
9) | Pothole Repairs on ITI to Aizawl Bypass Road | Sqm | 1.5 | 2025-06-16 | 2025-06-26 | 100% | 0.99 | - | 0.46 | 100% | 1.45 | Work Completed | Departmental
10) | Pothole Repairs on Tuikhuahtlang to Sikulpuikawn Eastern Side | Sqm | 0.13 | 2025-04-01 | 2025-04-02 | 100% | 0.05 |  | 0.07 | 100% | 0.12 | Work Completed | Departmental
11) | Pothole Repairs on Venghlui Biak In to Republic Biak In | Sqm | 2.8 | 2025-04-01 | 2025-04-15 | 100% | 2.11 | - | 0.6 | 100% | 2.71 | Work Completed | Departmental
12) | Pothole Repairs on ITI to Muawlmawi Ring Road-I | Sqm | 0.7 | 2025-06-05 | 2025-06-12 | 100% | 0.31 | - | 0.37 | 100% | 0.68 | Work Completed | Departmental
13) | Pothole Repairs on Approach Road to Mualmawi Church Northern Side | Sqm | 0.7 | 2025-05-28 | 2025-06-04 | 100% | 0.47 | - | 0.21 | 100% | 0.68 | Work Completed | Departmental
14) | Pothole Repairs on Salem High School (Hrangchhunga H/S) Approach Road | Sqm | 2.19 | 2025-04-11 | 2025-04-24 | 100% | 1.43 | - | 0.69 | 100% | 2.12 | Work Completed | Departmental
15) | Pothole Repairs on Zoramthanga's house to Bethlehem Vengthlang Kawn | Sqm | 2.5 | 2025-04-24 | 2025-05-07 | 100% | 1.12 | - | 1.3 | 100% | 2.42 | Work Completed | Departmental
16) | Pothole Repairs on Approach Road to Govt. Aizawl College New Campus | Sqm | 1.03 | 2025-05-08 | 2025-05-16 | 100% | 0.7 | - | 0.29 | 100% | 0.99 | Work Completed | Departmental
17) | Pothole Repairs on Aizawl College to Salvation OTC at Mualpui | Sqm | 2.63 | 2025-04-25 | 2025-05-11 | 100% | 1.17 | - | 1.37 | 100% | 2.54 | Work Completed | Departmental
18) | Pothole Repairs on Salem Diversion Road | Sqm | 2.41 | 2025-06-02 | 2025-06-16 | 100% | 1.57 | - | 0.77 | 100% | 2.34 | Work Completed | Departmental
19) | Pothole filling and Resurfacing of Approach Road to Salem Veng to Market House | Sqm | 2.8 | 2025-05-19 | 2025-05-30 | 100% |  | - | 0.73 | 100% | 0.73 | Work Completed | Departmental
20) | Pothole Repairs on Venghnuai Junction to Venghnuai Field | Sqm | 6.5 | 2025-06-13 | 2025-07-04 | 100% | 4.64 | - | 1.67 | 100% | 6.31 | Work Completed | Departmental
21) | Patch repair on PU College internal road | Sqm | 3 | 2025-05-01 | 2025-05-16 | 100% | 2.8 | - | 0.11 | 100% | 2.91 | Work Completed | Departmental
22) | Patch repair on approach road to Republic Playfield North | Sqm | 1.3 | 2025-05-13 | 2025-05-23 | 100% | 0.86 | - | 0.4 | 100% | 1.26 | Work Completed | Departmental
23) | Patch repair on Republic Playfield to College Veng | Sqm | 2 | 2025-04-21 | 2025-04-30 | 100% | 0.089 | - | 1.84 | 100% | 1.929 | Work Completed | Departmental
24) | Pothole repair on 3rd Bn MAP internal road | Sqm | 1 | 2025-06-17 | 2025-06-25 | 100% | 0.66 | - | 0.3 | 100% | 0.96 | Work Completed | Departmental
25) | Pothole repair on Republic Kawipui to Lungli Tuikhur | Sqm | 2.2 | 2025-04-16 | 2025-04-30 | 100% | 2.1 | - | 0.02 | 100% | 2.12 | Work Completed | Departmental
26) | Pothole repair on Bethlehem Vengthlang Taxi Stand to Tuithiang | Sqm | 3.2 | 2025-04-02 | 2025-04-22 | 100% | 2.41 | - | 0.69 | 100% | 3.1 | Work Completed | Departmental
27) | Pothole repair on Republic Playfield to Republic Vengthlang | Sqm | 3.7 | 2025-05-26 | 2025-06-12 | 100% | 3.55 | - | 0.038 | 100% | 3.588 | Work Completed | Departmental
28) | Approach Road to SR Valla House, Mission Veng | Sqm | 3.67 |  |  |  |  | 100% | 3.55 | 100% | 3.55 | Work Completed | Departmental
29) | Maubawkkawn to Maubawk Tlang Veng | Sqm | 1.43 |  |  |  |  | 100% | 1.38 | 100% | 1.38 | Not yet started | Departmental
30) | Pot hole Repair of MHNL Section - I | Sqm | 2.37 | 12:05 | 20:05 | 100% | 2.22 | 0% | 0.08 | 100% | 2.3 | Work Completed | Departmental | 1428
31) | Pot hole Repair of MHNL Section - II | Sqm | 1.48 | 14:05 | 17:05 | 100% | 1.38 | 0% | 0.05 | 100% | 1.43 | Work Completed | Departmental
32) | Pot hole Repair of Nursery to Maubawkkawn | Sqm | 5.1 | 16:05 | 21:05 | 100% | 4.79 | 0% | 0.14 | 100% | 4.93 | Work Completed | Departmental
33) | Pot hole Repair of Secretariat Internal Roads | Sqm | 4.41 | 19:05 | 23:05 | 100% | 4.15 | 0% | 0.13 | 100% | 4.28 | Work Completed | Departmental
34) | Pot hole Repair of Tennis Court to Dinthar (Kaisara Road) | Sqm | 4.12 | 21:05 | 26:05 | 100% | 3.87 | 0% | 0.12 | 100% | 3.99 | Work Completed | Departmental
35) | Pot hole Repair of Tuikual South Lower Lane Road | Sqm | 3.23 | 22:05 | 28:05 | 100% | 3.04 | 0% | 0.1 | 100% | 3.14 | Work Completed | Departmental
36) | Pot hole Repair of Zuangtuikhur to SA Hall Road | Sqm | 0.78 | 22:05 | 24:05 | 100% | 0.72 | 0% | 0.007 | 100% | 0.727 | Work Completed | Departmental
37) | Pot hole Repair of Assam Rifle Internal Roads at Khatla | Sqm | 2.3 | 2025-03-04 | 14:03 | 100% | 2.16 | 0% | 0.07 | 100% | 2.23 | Work Completed | Departmental
38) | Patch Repair of Kulikawn to Saikhamakawn via Tlangnuam (1kmp - 2 kmp) | Sqm | 5.39 | 2025-03-04 | 2025-03-19 |  | 4.01 | 100% | 1.22 | 100% | 5.23 | Work Completed | Departmental
39) | Patch Repair of Critical Section along Aizawl-Thenzawl-Lunglei Road (1.300 kmp - 5.000 kmp) | Sqm | 14.04 | 2025-05-05 | 2025-05-26 |  | 10.34 | 100% | 3.29 | 100% | 13.63 | Work Completed | Departmental
40) | Patch Repair of Approach Road to Kulikawn Hospital | Sqm | 1.94 | 2025-05-05 | 2025-05-09 |  | 1.43 | 100% | 0.45 | 100% | 1.88 | Work Completed | Departmental
41) | Patch Repair of Kulikawn to Saikhamakawn via Hridaikawn (0kmp - 1 kmp) | Sqm | 2.69 | 2025-03-05 | 2025-03-17 |  | 2 | 100% | 0.61 | 100% | 2.61 | Work Completed | Departmental
42) | Patch Repair of Tlangnuam to Hridaikawn | Sqm | 1.07 | 2025-03-10 | 2025-03-17 |  | 0.8 | 100% | 0.24 | 100% | 1.04 | Work Completed | Departmental | 95.5%
36 | Seal Coating of Approach road to Maubawk Cemetry | Sqm | 3.1 | [8 empty] | Not yet started | Departmental
IX | Restoration of Damage due to Cyclone Remal under ARSD under SASCI 2024-2025
1 | Construction of Retaining Wall on ITI Ring Road-III at Ch 0.050 Kmp | Rm | 5.32 | 2025-07-31 | 2025-08-22 |  |  | 100% | 103.33 | 100% | 103.33 | Work Completed | Restricted Tender
2 | Construction of Breast Wall on Sihtuikhur to Aizawl Bypass below Pu Chhunglawma's House, Bethlehem Vengthlang | Rm | 6.8 | 2025-07-02 | 2026-02-02 | [6 empty] | Not yet started | Restricted Tender
3 | Construction of Retaining Wall on Sihtuikhur to Aizawl Bypass Road at Ch 2.500 Kmp | Rm | 5.44 | 2025-07-02 | 2026-02-02 | 80% |  | 20% |  | 100% |  | Work Completed | Restricted Tender
4 | Re-Construction of Retaining Wall at Ch. 13.300 kmp on Maubawk to Lawipu road | Rm | 4.11 | 2025-07-02 | 2026-02-02 |  |  | 100% |  | 100% |  | Work Completed | Restricted Tender
5 | Construction of Retaining Wall at Ch. 2.100 kmp on Aizawl - Reiek - W.Lungdar Road | Rm | 1.65 | 2025-07-02 | 2026-02-02 |  |  | 100% |  | 100% |  | Work Completed | Restricted Tender
6 | Re-Construction of Retaining Wall at Ch. 3.650 kmp on Aizawl - Reiek - W.Lungdar Road | Rm | 3.67 | 2025-07-02 | 2026-02-02 |  |  | 100% |  | 100% |  | Work Completed | Restricted Tender
7 | Construction of Retaining Wall at Ch. 5.200 kmp on Aizawl - Reiek - W.Lungdar Road | Rm | 2.49 | 2025-07-02 | 2026-02-02 |  |  | 100% |  | 100% |  | Work Completed | Restricted Tender
8 | Construction of Retaining Wall at Ch. 5.900 kmp on Aizawl - Reiek - W.Lungdar Road | Rm | 28.86 | 2025-07-02 | 2026-02-02 | 30% |  | 70% |  | 100% |  | Work Completed | Restricted Tender
9 | Construction of Retaining Wall at Ch. 6.900 kmp on Aizawl - Reiek -W.Lungdar Road | Rm | 8.19 | 2025-07-02 | 2026-02-02 | 80% |  | 20% |  | 100% |  | Work Completed | Restricted Tender
10 | Construction of Retaining Wall at Ch. 17.600 kmp on Aizawl - Reiek - W.Lungdar Road | Rm | 23.12 | 2025-07-02 | 2026-02-02 | 20% |  | 20% |  | 40% |  | On going | Restricted Tender
11 | Construction of Retaining Wall at Ch. 19.200 kmp on Aizawl - Reiek-W.Lungdar Road | Rm | 5.35 | 2025-07-02 | 2026-02-02 |  |  | 100% |  | 100% |  | Work Completed | Restricted Tender
12 | Re-Construction of Retaining Wall at Ch. 27.200Kmp on Aizawl - Reiek-W.Lungdar Road | Rm | 3.71 | 2025-07-02 | 2026-02-02 | 100% |  | 0% |  | 100% |  | Work Completed | Restricted Tender
13 | Construction of Retaining Wall at Ch. 0.100 kmp on Bulbulle to Tlawng Road | Rm | 6.02 | 2025-07-02 | 2026-02-02 |  |  | 100% |  | 100% |  | Work Completed | Restricted Tender
14 | Construction of Retaining Wall at Ch. 0.200 kmp on Bulbule to Tlawng Road | Rm | 2.02 | 2025-07-02 | 2026-02-02 |  |  | 100% |  | 100% |  | Work Completed | Restricted Tender
15 | Construction of Retaining Wall at Ch. 0.500 kmp on Bulbulle to Tlawng Road | Rm | 3.01 | 2025-07-02 | 2026-02-02 |  |  | 100% |  | 100% |  | Work Completed | Restricted Tender
16 | Construction of Retaining Wall at Ch. 0.590 kmp on Bulbulle to Tlawng Road | Rm | 3.63 | 2025-07-02 | 2026-02-02 |  |  | 100% |  | 100% |  | Work Completed | Restricted Tender
17 | Construction of Retaining Wall at Ch. 0.950 kmp on Lawipu to Tlawng Road | Rm | 3.05 | 2025-07-02 | 2026-02-02 |  |  | 100% |  | 100% |  | Work Completed | Restricted Tender
18 | Construction of Link drain at ch 0.650kmp on Bulbule to Tlawng road | Rm | 2.51 | 2025-07-02 | 2026-02-02 | 20% |  | 70% |  | 20% |  | On going | Restricted Tender
19 | Construction of Retaining Wall On Aizawl Bypass Road at Ch 0.450 Kmp | Rm | 2.89 | 2025-07-02 | 2026-02-02 |  |  | 100% |  | 100% |  | Work Completed | Restricted Tender
20 | Construction of Retaining Wall On Aizawl Bypass Road at Ch 11.910 Kmp | Rm | 9.4 | 2025-07-02 | 2026-02-02 |  |  | 100% |  | 100% |  | Work Completed | Restricted Tender
21 | Construction of Retainning wall on Hualngohmun-Samtlang Road | Rm | 37.32 | 2025-07-02 | 2026-02-02 |  |  | 30% |  | 30% |  | On going | Restricted Tender
22 | Construction of Humepipe Culvert on Hualngohmun-Samtlang Road | Rm | 16.46 | 2025-07-02 | 2026-02-02 |  |  | 100% |  | 100% |  | Work Completed | Restricted Tender
23 | Reconstruction of Pavement on Collapse portion of Hualngohmun to Samtlang Road at Ch. 2.150 Kmp.) | Rm | 2.23 | 2025-07-02 | 2026-02-02 | [6 empty] | Not yet started | Restricted Tender
X | Restoration of Damage due to Cyclone Remal under ARSD
1 | Clearance of landslip under Aizawl Road South Sub Division-II |  |  |  |  | 100% |  |  |  | 100% |  | Completed | Departmental
2 | Extension of Culvert at Transport Office at Hlimen | Rm | 6 | 1:09 | 29:09 | 100% |  |  |  | 100% |  | Completed | Departmental
XI. | Resurfacing of Selected Stretches on Aizawl - Reiek - W. Lungdar Road | Rm | 58.04 |  |  |  |  | 50% |  | 50% |  | On Going | Departmental
XII | SASCI (2025-2026)
| Maubawk to MINECO Bypass Road on Western Side | [11 empty] | Restricted tender
| Formation Cutting | Km | 0.397 |  |  |  |  | 100% |  | 100% |  | Completed
| Pavement Works | Km | 0.261 | [8 empty] | Not yet started
| RCC Slab Culvert | No | 4 | [8 empty] | Not yet started
Protection Work
| a) Retaining Wall | Rm | 218 |  |  |  |  | 40% |  | 40% |  | On going
| b) Breast Wall | Rm | 218 | [8 empty] | Not yet started
| Construction of RCC Balcony Roadway | Rm | 96 | [8 empty] | Not yet started
.

## PIU
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER 2025 - PROJECT IMPLEMENTATION UNIT, PWD
Source of Funding : PM DevINE
SL. No. | Name of work /Project. | Approved Cost (Rs) | Name of Implementing agency/Dept. | Date of Commencement | Target Date of Completion | Cummulative progress at the end of last month |  | Achievement of works during the month |  |  | Overall cumulative achievement |  | Remarks | Mode of Contract
[6 empty] | Physical | Financial | Physical | Financial |  | Physical | Financial
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 11 | 12 | 13 | 14
1 | Construction of Aizawl Bypass on Western Side under PM DevINE Scheme Location : Mizoram State : Aizawl | 451.85 Cr | Project Implementation Unit, PWD | 23.12.2024 | 23.12.2027 | 8.91% | 8.9% | 0.1327% | 0% |  | 9.043% | 8.9% |  | EPC
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER 2025 - PROJECT IMPLEMENTATION UNIT, PWD
FINANCIAL REPORT
Sl. No. | Name of project Location and state | Name of Implementing agency/Dept. |  | Approved Cost |  | Fund Released by MDoNER |  | Expenditure Made |  | Unspent balance out of the fund released | Status of submission U/Cs | Remarks
|  |  |  | Orignal cost INR in Crore | Revised cost INR in Crore | During 2024-25 INR in Crore | Since inception (cummulative) | During the month vis-à-vis target | Since inception ( cummulative)
1 | 2 | 3 |  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Construction of Aizawl Bypass on Western Side under PM DevINE Scheme Location : Mizoram State : Aizawl | Project Implementation Unit, PWD |  | 500.00 Cr | Nil | 112.95 | 112.95 | 0 | 61.09 | 51.86 |  | Out of the 112.95 Crore sanctioned, a total amount of Rs. 64.09 Cr was utilised which includes DPR preparation and Appraisal cost, preparation of EIA/EMP report and Mobilisation Advance as well as SPS-01 (contractor's bill)
| Bill paid to the Contractor | Rs. 40.21 Cr
| Financial Progress of the Contractor | 8.9%
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER 2025 - PROJECT IMPLEMENTATION UNIT, PWD
PHYSICAL ABSTRACT
Sl. No. | Name of the project Location and state | Name of the implementing Agency/ Deptt. | Approved cost & date | 5: Date of commencement of work /scheme; 6: Target date of completion of work/scheme; 7: Scope of work /scheme physical terms (e.g.Kms etc); 11: Physical Achievement |  |  | Remark
|  |  | Cost (lakhs) | 4: Date; 11: Achievement; 12: Percentage upto date progress | Percentage during last month | Percentage during the report
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |  |  |  | 9 | 10 | 11 | 12 | 13
1 | Construction of Aizawl Bypass on Western Side under PM DevINE Scheme Location : Mizoram State : Aizawl | Project Implementation Unit, PWD | 4510 | 23.12.2024 | 23.12.2024 | 23.12.2027 | 1 | Earthwork up to top of sub-grade | Km | 45 | 13.1 | 29.11% | 29.1% | 0% | q
|  |  |  | 7: 2; 8: Sub Base Course (SSB); 9: Km; 10: 45; 12: 0% |  | 0%
|  |  |  | 7: 3; 8: Seperation Layer (SAMI); 9: Km; 10: 45; 12: 0% |  | 0%
|  |  |  | 7: 4; 8: Bituminous Work; 9: Km; 10: 45; 12: 0% |  | 0%
|  |  |  | 7: 5; 8: Wearing Course; 9: Km; 10: 45; 12: 0% |  | 0%
[7 empty] | 6 | Reconstruction and New Culverts on Existing road/realignmnet bypass - Hume Pipe Culvert | nos | 205 | 8 | 3.902% | 2.44% | 1.462%
|  |  |  | 7: 7; 8: Reconstruction and New Culverts on Existing road/realignmnet bypass - RCC Box Culvert; 9: nos; 10: 12; 12: 0% |  | 0%
|  |  |  | 7: 8; 8: Reconstruction and New Culverts on Existing road/realignmnet bypass - chutes; 9: nos; 10: 1278; 12: 0% |  | 0%
|  |  |  | 7: A; 8: A-Widening and repairs of minor bridges |  | 0%
|  |  |  | 7: 1; 8: Repair of minor bridge by construction of wing wall; 10: 0 |  | 0%
|  |  |  | 7: B; 8: B-New Minor Bridges |  | 0%
|  |  |  | 7: 1; 8: Foundation + Substructure; 9: Nos; 10: 8; 12: 0% |  | 0%
|  |  |  | 7: 2; 8: Super-structure; 9: Nos; 10: 8; 12: 0% |  | 0%
|  |  |  | 7: 3; 8: Approaches; 9: Nos; 10: 8; 12: 0% |  | 0%
|  |  |  | 7: 4; 8: Protection Work; 9: Nos; 10: 8; 12: 0% |  | 0%
|  |  |  | 7: i; 8: Counterfort retaining wall; 9: RMT; 10: 2140; 12: 0% |  | 0%
|  |  |  | 7: ii; 8: Plumb Concrete Retaining Wall; 9: Nos; 10: 1722; 12: 0% |  | 0%
|  |  |  | 7: iii; 8: Breast Wall; 9: RMT; 10: 946; 12: 0% |  | 0%
|  |  |  | 7: iv; 8: Toe Wall; 9: RMT; 10: 946; 12: 0% |  | 0%
[7 empty] | v | Gabion Breast Wall | RMT | 1355 | 180 | 13.28% | 11.11% | 2.174%
|  |  |  | 7: vi; 8: Lined Side Drain; 9: MTR; 10: 5000; 12: 0% |  | 0%
|  |  |  | 7: vii; 8: Crash Barrier; 9: RMT; 10: 2560; 12: 0% |  | 0%
|  |  |  | 7: viii; 8: Traffic Signages; 9: Nos; 10: 225; 12: 0% |  | 0%
|  |  |  | 7: ix; 8: Road Markings; 10: 13050; 12: 0% |  | 0%
|  |  |  | 7: x; 8: Km Stones; 10: 220; 12: 0% |  | 0%
|  |  |  | 7: xi; 8: Boundary Pillar; 10: 600; 12: 0% |  | 0%
|  |  |  | 7: xii; 8: Direction and Place identification; 10: 35; 12: 0% |  | 0%

## AZL ELEC DIV
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER 2025
Name Of Division : PWD, Electrical Division, Aizawl
Head of Account : Major & Minor Works and Deposit works 8443-108, D-III
Sl. No | Name of Works / Scheme | Unit | Approved Cost Amount (in Lakhs.) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month. |  | Achievement of works during the Month |  | Overall cummulative achievement |  | Remarks
[6 empty] | Phy (%) | Fin(Rs) | Phy (%) | Fin(Rs) | Phy (%) | Fin(Rs)
1 | 2 |  | 3 | 6 |  | 10 | 11 | 12 | 13 | 14 | 15 | 18
1 | SITC of 13 Passenger Lift - 1 no., 2-opening, 900mm centre opening Stainless Steel Cable with Automatic Rescue Device (ARD) for Hydraulic Lift with Minor Civil Works at Lengpui Airport Mizoram | % | 39.24 | 08.09.2021 | 01.04.2024 | 100% | 39.24 | 0% | - | 100% | 39.24 | Completed
2 | I/E to Arrival & Departure Passenger Lobby at Lengpui Airport | % | 25.27 | 19.12.2020 | 1.4.2024 | 97% | 25.27 | 0% | - | 97% | 25.27 | Room modification (Civil Works) not yet ready
3 | Street Light Parking light at Lengpui Airport | % | 37.32 | 06.07.2022 | 1.4.2024 | 98% | 37.32 | 2% | - | 100% | 37.32 | Completed
4 | Addl. Estimate for SITC of MRV/VRF Centralizes Air Conditioner Airport First Floor Departure Hall, Mizoram. | % | 247.74 | 12.03.2022 | 04.03.2024 | 98.5% | 244.44 | 0% | - | 98.5% | 244.44 | Completion stage, Testing and Comissioning left.
5 | SITC of EPABX System for Lengpui Airport Terminal Building. | % | 24.64 | 06.07.2022 | 29.06.2024 | 97% | 19.46 | 1% | - | 98% | 19.46 | Telephones stocked at site, ready be fixed in the rooms when occupied
6 | SITC of PA System at Lengpui Airport Terminal Building. | % | 36.36 | 06.07.2022 | 29.06.2024 | 99% | 28.82 | 0% | - | 99% | 28.82 | Ready for Commision
Sl. No | Name of Works / Scheme | Unit | Approved Cost Amount (in Lakhs.) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month. |  | Achievement of works during the Month |  | Overall cummulative achievement |  | Remarks
[6 empty] | Phy (%) | Fin(Rs) | Phy (%) | Fin(Rs) | Phy (%) | Fin(Rs)
1 | 2 |  | 3 | 6 |  | 10 | 11 | 12 | 13 | 14 | 15 | 18
7 | Supply & Installation of Integrated Fire Hydrant System (Wise Riser)&SITC of Alarm System for Lengpui Airport Terminal Building. | % | 119.96 | 06.07.2022 | 29.06.2024 | 98% | 94.72 | 0% | - | 98% | 94.72 | Completion stage
8 | SITC of AVTRON IP Surveillance System for Lengpui Airport Terminal Building. | % | 94.76 | 06.07.2022 | 29.06.2024 | 98% | 67.61 | 0% | - | 98% | 67.61 | All system function and ready for Commission exept 6 nos. Camera at Ground Floor due to Civil works (Ceiling) not yet ready at Ground floor
9 | SITC of LAN SETUP at Lengpui Airport Terminal Building. | % | 20.05 | 06.07.2022 | 29.06.2024 | 99% | 15.76 | 0% | - | 99% | 15.76 | Completion stage
10 | Estimate for I/E of Energy Meter for Terminal Building at Lengpui Airport | % | 7.99 | 06.07.2022 |  | 100% | 7.99 | 0% | - | 100% | 7.99 | Completed
11 | Impvt/Upgradation of Operational/Non-Operational facilities of Lengpui Airport(SH:Northern Side Baggage conveyor belt) | % | 192.5 | 22.07.2024 | 18.12.2024 | 100% | 370.86 | 0% | - | 100% | 373.6 | Completed
12 | Impvt/Upgradation of Operational/Non-Operational facilities of Lengpui Airport(SH:Southern Side Baggage conveyor belt) | % | 192.5 | 22.07.2024 | 18.12.2024 | 100% |  | 0% |  | 100% |  | Completed
13 | Estimate for XLPE Cable for Lengpui Airport. | % | 27.23 |  |  | 100% | 27.23 | - | - | 100% | 27.23 | Completed
Sl. No | Name of Works / Scheme | Unit | Approved Cost Amount (in Lakhs.) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month. |  | Achievement of works during the Month |  | Overall cummulative achievement |  | Remarks
[6 empty] | Phy (%) | Fin(Rs) | Phy (%) | Fin(Rs) | Phy (%) | Fin(Rs)
1 | 2 |  | 3 | 6 |  | 10 | 11 | 12 | 13 | 14 | 15 | 18
14 | Additional Estimate for SITC of Air Conditioner Departure Passenger Lobby at Lengpui Airport. | % | 24.67 |  |  | 100% | 24.67 | - | - | 100% | 24.67 | Completed
15 | Laying of XLPE Cable from Power House to Glide Path control at Lengpui Airport, Mizoram | % | 39.53 | 09.05.2023 | 04.08.2023 | 100% | 39.52 | - | - | 100% | 39.52 | Completed
16 | Impvt/Revamping of Lengpui Airport runway Lighting-DGCA Observation Reg. | % | 347.05 |  |  | 100% | 360.78 |  | - | 100% | 370.38 | Completed
17 | Impvt/Revamping of Lengpui Airport runway Lighting-Isolation Bay-DGCA Observation Reg. | % | 10.91 |  |  | 100% |  |  |  | 100% |  | Completed
18 | Impvt/Revamping of Lengpui Airport runway Lighting-Isolation Bay-DGCA Apron Extension Observation Reg. | % | 14.6 |  |  | 100% |  |  |  | 100% |  | Completed
19 | Renovation/Repairing of Internal Electrification to Polytechnic at Thingdawl (SH: Automobile Engineering Block) | % | 18.65 | 4.10.2023 | 18.11.2023 | 98% | 18.65 | 0% | - | 98% | 18.65 | I/E Work completed, Service connection awaited.
20 | Renovation/Repairing of Internal Electrification to Polytechnic at Thingdawl (SH: Textile Technology Block) | % | 18.71 | 4.10.2023 | 18.11.2023 | 98% | 18.5 | 0% | - | 98% | 18.5 | I/E Work completed, Service connection awaited.
Sl. No | Name of Works / Scheme | Unit | Approved Cost Amount (in Lakhs.) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month. |  | Achievement of works during the Month |  | Overall cummulative achievement |  | Remarks
[6 empty] | Phy (%) | Fin(Rs) | Phy (%) | Fin(Rs) | Phy (%) | Fin(Rs)
1 | 2 |  | 3 | 6 |  | 10 | 11 | 12 | 13 | 14 | 15 | 18
21 | Renovation/Repairing of Internal Electrification to Polytechnic at Thingdawl (SH: Administrative Block) | % | 9.52 | 4.10.2023 | 18.11.2023 | 98% | 9.46 | 0% | - | 98% | 9.46 | I/E Work completed, Service connection awaited.
22 | Renovation/Repairing of Internal Electrification to Polytechnic at Thingdawl (SH: Common Facility Block) | % | 11.05 | 4.10.2023 | 18.11.2023 | 98% | 11 | 0% | - | 98% | 11 | I/E Work completed, Service connection awaited.
23 | SITC of 5-passenger Lift for Fast Track Court Building at Kolasib | % | 3.9 | 26.12.2024 | 31.08.2025 | 20% | - | 0% | - | 20% |  | Technical Sanction accorded,Building not yet ready for I/E
24 | SITC of 13-passenger Lift for Fast Track Court Building at Kolasib | % | 49.85 | 26.12.2024 | 31.08.2025 | 20% | - | 0% | - | 20% |  | TS accorded, Lift shaf & pit construction / modification required conveyed to PD-III
25 | I/E to Fast Track Court at Kolasib | % | 136.73 | 02.06.2024 |  | 20% | - | 0% | - | 20% |  | Technical Sanction accorded,Building not yet ready forI/E
26 | I/E to High Court Parking at MINECO | % | 109.54 | 07.03.2023 | 30.04.25 | 100% | - | 0% | - | 100% |  | Completed
27 | I/E to Mizoram Legislator Home at Tuikhuahtlang , Aizawl. | % | 28.5 | 20.11.2024 | 30.05.25 | 100% | - | 0% | - | 100% |  | Completed
28 | Repair and Maintenance of AC at Session Hall (Phase-I : Northern Side) | % | 9.04 | 14.04.2025 | 12.07.25 | 100% | 8.78 | 0% | - | 100% | 8.78 | Completed
Sl. No | Name of Works / Scheme | Unit | Approved Cost Amount (in Lakhs.) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month. |  | Achievement of works during the Month |  | Overall cummulative achievement |  | Remarks
[6 empty] | Phy (%) | Fin(Rs) | Phy (%) | Fin(Rs) | Phy (%) | Fin(Rs)
1 | 2 |  | 3 | 6 |  | 10 | 11 | 12 | 13 | 14 | 15 | 18
29 | New Electrification of MLA Staff Quarters 4 (four) Units (Qtr No. T-141/A, T-141/B, T-141/C and T-141/D) at Tuikhuahtlang, Aizawl. | % | 10.86 | 02.04.2025 | 30.05.27 | 80% | - | 20% | - | 100% | - | Completed
30 | Repair and Maintenance of AC at Session Hall (Phase-I : Southern Side) | % | 3.58 | 15.05.2025 | 13.07.25 | 100% | 3.48 | 0% | - | 100% | 3.48 | Completed
31 | I/E to PHE, E-in-C Office at MINECO | % | 30.34 | 25.08.2025 | 30.09.25 | 60% | - | 40% | - | 100% | - | Completed
32 | Complete Renovation for I/E to AYUSH Hospital at Thenzawl | % | 40 | 01.09.2025 | 31.12.27 | 20% | - | 5% | - | 25% | - | Supply order placed and few materials received
33 | I/E to Staff Quarters (Block-C) at DIET Complex, Chaltlang, Aizawl. | % | 45.98 | - | - | - | - | 70% | - | 70% | - | I/E works in progress
34 | I/E to PWD Staff Quarters (3 Unit) at Serchhip, Aizawl. | % | 5.91 | - | - | - | - | 100% | - | 100% | - | I/E works completed without S/C
Sr. Executive Engineer, PWD.,
Electrical Division, Aizawl.

## AZL BUILDING DIV
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER 2025
Name of Division: Aizawl Building Division
Source of Funding : CSS
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of completion | Cummulative Progress at the end of last month |  | Acievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Improvement of Mizoram Secretariat Building at MINECO | Percen tage | 168.49 | 13.11. 2023 | 31.03. 2024 | 100% | 168.49 |  |  | 100% | 168.49 |  | Departmental
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER 2025
Name of Division: Aizawl Building Division
Source of Funding : State
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of completion | Cummulative Progress at the end of last month |  | Acievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of RCC link drain near Chief Minister's Office at Mc Donald Hill | Percen tage | 25 | 05.04.2025 | 31.08.2025 | 90% | 67% | 8% | 31% | 98% | 98% |  | Departmental
2 | Maintenance and furnishing of General Pool Quarters | Percen tage | 85 | 15.01.2025 | 31.03.2025 | 100% | 100% |  |  | 100% | 100% |  | Departmental
Sr.Executive Engineer, P.W.D.,
Aizawl Building Division,
Aizawl:Mizoram.

## CHAMPHAI DIV
MONTHLY PROSGESS REPORT OF WORKS FOR THE MONTH OF OCTOBER, 2025
Name of Division : PWD., Champhai
SL.No. | Name of Scheme | Unit | Approved Cost (in lakhs) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of Works during the month |  | Overall Cumulative Achievement |  | Remarks | Mode of Tender
| Name of Work/Project |  |  |  |  | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
I | ANNUAL PLAN (5054)
1 | Upgradation of Approach road to Tuipui Village from NH-6 (new Eden) Length - 1.625 Km | Km | 128.28 | 6.12.2024 | 6.12.2025 | 82% | _ | _ | 74.32 | 82% | 74.32 | On-going | Open Tender
2 | Construction of Bailey Bridge (60 ft span) over R. Tuimuk on approach road to Tuipui Village from NH-6 (New Eden) | Ft. | 53.06 | 22.8.2024 |  | 78% | _ | _ | _ | 78% | 53.06 | On-going | Deptt.
II | SASCI
1 | Upgradation of Khankawn to Champhai (Phase - I) | Km | 600 | _ | 6.6.2026 | _ | _ | _ | _ | _ | _ | Mobilisation Stage | Restricted Tender
2 | Construction of Champhai Ring Road Phase-I (Khankawn - Falkawn - Hmunhmeltha - Vengthar - Zote via Keilungliah) | Km | 2000 | _ | 7.7.2026 | _ | _ | _ | _ | _ | _ | Mobilisation Stage | Restricted Tender
3 | Upgradation of Khankawn to Champhai Road Under Part-V (Stimulating of Industrial Growth) (Phase - II) | Km | 600 | _ | 21.7.2026 | _ | _ | _ | _ | _ | _ | Mobilisation Stage | Restricted Tender
III | MAINTENANCE ACTION PLAN (3054)
1 | Improvement & resurfacing of Sobji Bazar to SIB Complex via Rohnaas House(Sobji Bazar SIB Complex) | Km | 8.18 | 13.10.2025 | 31.3.2026 | _ | _ |  |  |  |  | On-going | Departmental
2 | Improvement & resurfacing of Khawhluna Point Bethel to Thangvelas House (Sihdim Road) | Km | 21.55 | 13.10.2025 | 31.3.2026 | _ | _ | 100% | 100% | 100% |  | Work Completed | Departmental
3 | Improvement & resurfacing Excise Office approach road | Km | 2.48 | 13.10.2025 | 31.3.2026 | _ | _ |  |  |  |  | On-going | Departmental
4 | Kanan Internal Road upto CNV Road via Seri(CNV Road Kanan Internal Road) | Km | 10.78 | 13.10.2025 | 31.3.2026 | _ | _ |  |  |  |  | On-going | Departmental
5 | Improvement & resurfacing of Chanem Ring Road (Chanem Building Chanem) | Km | 6.41 | 13.10.2025 | 31.3.2026 | _ | _ |  |  |  |  | On-going | Departmental
6 | Patch repair & resurfacing of Kahrawt Field to Vengsang HS via PHE Office (Kahrawt Field Vengsang High School) | Km | 9.72 | 13.10.2025 | 31.3.2026 | _ | _ |  |  |  |  | On-going | Departmental
7 | Improvement & resurfacing of Tlangsam Community Hall Approach Road | Km | 8.01 | 13.10.2025 | 31.3.2026 | _ | _ |  |  |  |  | On-going | Departmental
8 | Resurfacing of approach road to Hlakungpui mual, Khawbung (Balance portion including approach road to SA Quarter) | Km | 4.59 | 21.10.2025 | 31.3.2026 | _ | _ |  |  |  |  | On-going | Departmental
9 | Resurfacing of approach road to PHC Farkawn ( Farkawn PHC Farkawn) | Km | 10.55 | 21.10.2025 | 31.3.2026 | _ | _ |  |  |  |  | On-going | Departmental
10 | Resurfacing of approach road to Zawlsei Middle School, Zawlsei | Km | 3.01 | 21.10.2025 | 31.3.2026 | _ | _ |  |  |  |  | On-going | Departmental
11 | Resurfacing of approach road to mini Sport Complex, Khawbung | Km | 4.52 | 21.10.2025 | 31.3.2026 | _ | _ |  |  |  |  | On-going | Departmental
12 | Pothole Filling, Patch repair of Champhai - Khawbung road (Dungtlang to Khawbung) (64.000-71.000 kmp) | Km | 3.79 | 21.10.2025 | 31.3.2026 | _ | _ |  |  |  |  | On-going | Departmental
13 | Construction of Unlined Side Drain on Lianchhiari Lunglen Tlang road at Dungtlang | Km | 5 | 21.10.2025 | 31.3.2026 | _ | _ |  |  |  |  | On-going | Departmental
IV | 3054 NON-PLAN R&B
1 | Upgradation of Zotlang to Mualnuam Road | Km | 70 | 4.9.2025 | 31.3.2026 | _ | _ | 100% | 100% | 100% | _ | Work Completed | Departmental
Sr. Executive Engineer, PWD.,
Champhai Division:Champhai

## HMUIFANG DIV
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER, 2025
Name of Division: Hmuifang Division, Aibawk
Rs. in Lakh
Sl. no | Name of Scheme | Unit | Approved Cost (Rs.in lakh) | Date of Commencement | Target Date of Completion : | Commulative Progress at the end of last month |  | Achievement of Works during the month |  | Overall Commulative Achievement |  | Remarks | Mode of Tender
| Name of Work/Project |  |  |  |  | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
CRF
1 | Widening to Single Lane with Geometric Improvement & Up-Gradation of Chhiahtlang to Lamchhip road in Mizoram |  | 6668.18 | 23.06.2017 | 23.06.2019 | 100% | 6282.93 |  |  | 100% | 6282.93 | Physically Completed | Restricted Tender
2 | Construction of Muallungthu to Lungphun Road |  | 5996 | 23.11.2017 | 23.11.2019 | [7 empty] | Restricted Tender
| i) Formation Cutting |  |  |  |  | 100% | 2460 |  |  | 100% | 2460 | Physically Completed
| ii) Permanent Works |  |  |  |  | 24.51% |  |  |  | 24.51% |  | Work in progress
| iii) Pavement | [10 empty] | not yet started
SASCI-II
1 | Construction of Agiculture Link Road to R. Mat from Chawilung, Lungsei, Samlukhai, Sialsuk |  | 173.57 | 14.12.2023 | 14.12.2024 | 100% | 166.87 |  |  | 100% | 166.87 | Physically Completed | Restricted Tender
2 | Restoration of damage due to cyclone remal under Aizawl Road North, Aizawl Road South & Hmuifang Division |  | 1170 | 17.04.2025 | 17.11.2025 | 40% |  | 48.33% |  | 88.33% |  | Work in progress | Restricted Tender
3 | Restoration of damage due to cyclone remal under Hmuifang Division, Part-II |  | 1175 | 17.04.2025 | 17.11.2025 | 76% |  | 14% |  | 90% |  | Work in progress | Restricted Tender
5054
1 | Widening and Repair of Vantawng Approach Road | Km | 104.49 | 10.10.2024 | 10.03.2025 | 100% | 104.49 |  |  | 100% | 104.49 | Physically & Financially Completed | Departmental
Sr. Executive Engineer, PWD.,
Hmuifang Division, Aibawk

## KOLASIB DIV
MONTHLY PROGRESS REPORT
FOR THE MONTH OF OCTOBER, 2025
UNDER KOLASIB DIVISION
Sl. No. | Name of Schemes | Quantity | Unit | Approved Cost (Rs in Lakh) | Date of Commencement | Target Date of Comple-tion | Cumulative Progress at the end of last month |  | Achievement of works during the month |  | Overall Cumulative achievement |  | Remarks | Mode of Tender
| Name of Works / Project | [5 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 |  | 3 | 4 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | NABARD
1 | Construction of Meidum to Hortoki Phase-II
i | Earthwork and Permanent Work from 9.100 Km to 13.325 Km Package-I | 3.305 | Km | 13366 | 24.12.2021 | 29.04.2024 | 100% | 1035.621 |  |  | 100% | 1035.621 | Completed | Restricted Tender
ii | Earthwork and Permanent Work from Km 13.325 to Km 17.500 Package-II | 3.275 | Km |  | 25.12.2021 | 23.07.2025 | 97% | 933.465 | 0% |  | 97% | 933.465 |  | Restricted Tender
iii | Earthwork and Permanent Works from Km 17.500 to Km 21.725 Package-III | 3.315 | Km |  | 18.12.2021 | 16.11.2025 | 98% | 1223.502 | 0% |  | 98% | 1223.502 | Mobilisation & Machinery Advance Recovery Balance= Rs.7 lakh | Restricted Tender
iv | Earthwork and Permanent Works from Km 21.725 to Km 26.00 Package-IV | 3.355 | Km |  | 08.12.2021 | 19.05.2025 | 99% | 726.528 | 0% |  | 99% | 726.528 | Mobilisation & Machinery Advance Recovery Balance=Rs.79.589 lakh | Restricted Tender
v | Construction of Rigid Pavement : Package -I (Km 9.100-Km 15.730) | 5.58 | Km |  | 03.08.2022 | 10.12.2025 | 38% | 722.158 | 0% |  | 38% | 722.158 | Mobilisation & Machinery Advance Recovery Balance= Rs.173.459 lakh | Restricted Tender
vi | Construction of Rigid Pavement : Package -II (Km 15.730-Km 22.36) | 5.58 | Km |  | 03.08.2022 | 05.09.2025 | 9.2% | 188.463 | 0% |  | 9.2% | 188.463 | Mobilisation & Equipment Advance Recovery Balance= Rs.297.974 lakh | Restricted Tender
vii | Design & Construction of T-Beam Bridge package-I at Chhimluangte (CH : 0.450 Kmp) | 24 | m |  | 18.12.2021 |  | 100% | 482.621 |  |  | 100% | 482.621 | Completed | Departmental |  | 367.621
viii | Design & Construction of T-Beam Bridge package-I at Dumkhel (CH : 5.500 Kmp) | 20 | m |  | 30.12.2024 | 30.06.2026 | 27% | 115.75 | 0% |  | 27% | 115.75 | Secured Advance Rs.62.24 lakh | Restricted Tender
ix | Design & Construction of T-Beam Bridge package-II at Bulung (CH : 10.200 Kmp) | 28 | m |  | 24.12.2021 | 02.10.2025 | 17.5% |  | 0% |  | 17.5% | 0 | Secured Advance Rs.82.080 lakh | Restricted Tender
x | Design & Construction of T-Beam Bridge package-II at Damdiai (CH : 23.50 Kmp) | 20 | 3: m; 8: 21.5%; 10: 0%; 12: 21.5%; 13: 0; 15: Restricted Tender |  |  |  | 273.047
2 | Construction of BUSG Composite Bridge (Span=22.00m, Revised span=34.00m) over R. Chepte on Bilkhawthlir to Saiphai road under NABARD | 34 | m | 508.45 | 24.06.2019 | 30.11.2025 | 45% | 132.82 | 0% |  | 45% | 132.82 | NABARD Fund=Rs. 291.35 lakh SASCE Fund=Rs.217.10 Expenditure from NABARD=Rs.46.67 Expenditure from SASCE=Rs.86.15. Equipment Advance Recovery balance=Rs.8.037 | Restricted Tender | 26.1225 | 11.7551 |  | 244.05
3 | Construction of BUSG Composite Bridge (Span=22.00m) over R. Sesih on Bilkhawthlir to Saiphai road under NABARD | 22 | m | 291.35 | 24.06.2019 | 30.09.2025 | 94% | 248.894 | 0% |  | 94% | 248.894 | Expenditure includes centages Equipment Advance Recovery balance=Rs.25.298 lakh | Restricted Tender | 85.4278 | 80.3022 |  | 28.997
4 | Construction of Link Road from NH-306 (Vairengte) to Sabual Mual Arable Crop Land : length=3.720 Kms | 3.72 | Km | 417.58 | 13.08.2022 | 28.02.2025 | 100% | 406.303 |  |  | 100% | 406.303 | Physically Completed Expenditure includes centages | Restricted Tender
5 | Construction of approach Road to Railway Station in Mizoram (SH: Construction of Approach Road to Hortoki Railway Station | 2.51 | km | 625.97 | 18.07.2025 | 18.07.2026 | 6% |  | 4% |  | 10% |  |  | Restricted Tender
2 | SASCI | [15 empty] | 273.047
1 | Restoration of Damages due to Cyclone Remal under SASCI, 2024-2025 under Kolasib Division | [15 empty] | 24.153
i | Re-construction of Hume Pipe Culvert on Hmar Veng to Saidan Road, Kolasib | 7.5 | 3: m; 4: 17.147; 6: 16.06.2025; 7: 16.01.2026; 8: 100%; 12: 100%; 15: Restricted Tender
ii | Construction of Retaining Wall on Rengtekawn to NH 154(Zero Point) Road at 1.050 Kmp | 52 | 3: m; 4: 29.666; 6: 16.06.2025; 7: 16.01.2026 |  |  | 244.05
iii | Construction of Breast Wall on Rengtekawn to NH 154(Zero Point) Road at 1.600 Kmp | 30 | 3: m; 4: 10.756; 6: 16.06.2025; 7: 16.01.2026 |  |  | 4.844
iv | Re-construction of SPT Bridge over R.Chepte at 10.000 Kmp on Bilkhawthlir to Saiphai Road (SH: Approach Roads ) | 110 | 3: m; 4: 1.973; 6: 16.06.2025; 7: 16.01.2026; 10: 10%; 12: 10% |  |  | 248.894
v | Construction of Hume Pipe Culvert near Lalrampana House on Rengtekawn NH 54-132 KV | 1 | 3: nos; 4: 5.456; 6: 16.06.2025; 7: 16.01.2026; 8: 100%; 12: 100%
vi | Construction of SPT Bridge over Aitlanglui at Vairengte | 12 | 3: m; 4: 15; 6: 16.06.2025; 7: 16.01.2026; 10: 5%; 12: 5%
vii | Construction of Retaining Wall at Serkhan to Bagha Road at 29.100 Kmp | 1 | 3: nos; 4: 4.358; 6: 16.06.2025; 7: 16.01.2026; 10: 100%; 12: 100%
viii | Construction of Retaining Wall near Tumpui field on Main Feeder to Karkawn via Helipad | 1 | 3: nos; 4: 24.231; 6: 16.06.2025; 7: 16.01.2026
ix | Construction of Retaining Wall at Serkhan to Bagha Road at 15.100 Kmp | 1 | 3: nos; 4: 15.409; 6: 16.06.2025; 7: 16.01.2026; 8: 5%; 10: 8%; 12: 13%
x | Construction of Retaining Wall at Serkhan to Bagha Road at 32.400 Kmp | 1 | 3: nos; 4: 11.154; 6: 16.06.2025; 7: 16.01.2026; 8: 5%; 10: 60%; 12: 65%
xi | Construction of Retaining Wall on Rengtekawn-Builum Road at 8.000 KMP | 1 | 3: nos; 4: 6.118; 6: 16.06.2025; 7: 16.01.2026; 8: 100%; 12: 100%
xii | Construction of Retaining Wall on Rengtekawn-Builum Road at 5.600 KMP | 1 | 3: nos; 4: 24.108; 6: 16.06.2025; 7: 16.01.2026
xiii | Restoration of Damaged Pavement on Buhchang to Phaisen road at 7.350 Kmp | 27 | 3: m; 4: 12.677; 6: 16.06.2025; 7: 16.01.2026; 10: 10%; 12: 10%
xiv | Re-Construction of Hume Pipe Culvert at 8.160 Kmp on Bilkhawthlir to Saiphai Road | 1 | 3: nos; 4: 7.21; 6: 16.06.2025; 7: 16.01.2026; 8: 100%; 12: 100%
xv | Construction of Retaining Wall on Rengtekawn to Builum Road at 5.100 Kmp | 1 | 3: nos; 4: 11.736; 6: 16.06.2025; 7: 16.01.2026; 8: 100%; 12: 100%
xvi | Re-Construction of Hume Pipe Culvert at 9.390 on Bilkhawthlir to Saiphai Road | 2 | 3: nos; 4: 11.965; 6: 16.06.2025; 7: 16.01.2026; 10: 5%; 12: 5%
xvii | Restoration of Damaged Pavement on Buhchang to Phaisen road at 8.850 Kmp | 11 | 3: m; 4: 5.176; 6: 16.06.2025; 7: 16.01.2026; 8: 10%; 10: 2%; 12: 12%
xviii | Construction of Retaining Wall at Kawnpui to Hortoki Road at 15.100 Kmp | 1 | 3: nos; 4: 5.178; 6: 16.06.2025; 7: 16.01.2026; 8: 5%; 12: 5%
Sr.Executive Engineer, PWD
Kolasib Division.

## KAWRTHAH DIV
MONTHLY PROGRESS REPORT FOR THE MONTH OF | [9 empty] | OCTOBER, 2025
Name of Division |  | : KAWRTHAH
Source of Funding |  | : SASCI
Sl. No | Name of Works/Project | Unit |  | Approved Cost (in lakhs) | Date of Commencement | Target Date of Completion | Achievement upto previous month |  | Achievement for the month |  | Overall Cummulative achievement |  | Remarks | Mode of Contract
[7 empty] | Phy | Fin | Phy | Fin | Phy | Fin (actual)
1 | 2 | 3 |  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Additional works and Completion of Double Lane Bridge over River Teirei on Bairabi - Zamuang Road. |  |  | 5: 29.2.2024; 6: 15.11.2025; 9: -; 13: Work in progress; 14: Continued by the existing contractor i.e Sadguru Engineers & Allied Services Pvt.Ltd. For Bridge work & piling of Bank protection & Departmentally for Bank protection (Balanced work) and approach road. |  |  | 0.35
| Bridge Work (Super Structure) | Nos | 1 | 546.91 |  |  | 93.65% | 901.62 | 0.35% | 68.73 | 94% | 970.35
| River Banks Protection | Nos | 2 | 4: 475.69; 7: 92%; 11: 92%
| Approach Road | Nos | 2 | 4: 298.46; 7: 65%; 9: 5%; 11: 70%
| Road Signages |  |  | 4: 25.6
| Total of Work Component : |  |  | 4: 1346.66; 8: 901.62; 10: 68.73; 12: 970.35
| Provision for Contingencies : |  |  | 4: 26.76
| Provision for Quality Control : |  |  | 4: 26.6
| Grand Total : |  |  | 4: 1400.02; 8: 901.62; 10: 68.73; 12: 970.35
| Overall physical Progress | : |  | 4: 85.33% |  | 69.3097
429.67
MONTHLY PROGRESS REPORT FOR THE MONTH OF |  |  |  | 10: OCTOBER, 2025
Name of Division |  | : KAWRTHAH
Source of Funding |  | : SASCI
Sl. No | Name of Works/Project | Unit |  | Approved Cost (in lakhs) | Date of Commencement | Target Date of Completion | Achievement upto previous month |  | Achievement for the month |  | Overall Cummulative achievement |  | Remarks | Mode of Contract
[7 empty] | Phy | Fin | Phy | Fin (in lakhs) | Phy | Fin (in lakhs)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Strengthen ing of Zamuang - Hriphaw - Kolalian - Dulupcherra (ZHKD) Road (28.00 Kmp) | Km | 28 | 225 | 16.12.2023 | 30.6.2025 | 100% | 192.28 |  | 14.54 | 100% | 206.82 | Works completed physically | Contract after call of restricted tender
| Grand Total : |  |  | 4: 225; 7: 100%; 8: 192.28; 10: 14.54; 11: 100%; 12: 206.82
| Overall Physical Progress | : | 100%
MONTHLY PROGRESS REPORT FOR THE MONTH OF |  |  |  | 10: OCTOBER, 2025
Name of Division |  | : KAWRTHAH
Source of Funding |  | : NABARD
Amount in lakhs
Sl. No | Name of Work/Project | Unit |  |  | Approved Cost (in lakh) | Date of Commencement | Target Date of Completion | Achievement upto previous month |  | Achievement for the month |  | Overall commulative achievement |  | Remarks | Mode of Contract
[8 empty] | Phy | Fin (lakh) | Phy | Fin (lakh) | Phy | Fin (actual)
1 | 2 | 3 |  |  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Double Lane BUSG Bridge (Span = 81m) over R.Langkaih on Mizoram-Tripura Border at Kanhmun | Bridge Works : |  |  | 13: Work in progress; 14: Contract after call of Restricted Tender
|  | a) Site Investigation & Design | 7% | % | 154.23 | 6.4.2018 | 31.12.2025 | 100% | 1428.33 | - |  | 100% | 1428.33
|  | b) Construction of Subway | 20% | % | 4: 440.65; 7: 100%; 11: 100%
|  | c) Foundation & Sub-Structure | 41% | % | 4: 903.34; 7: 90.5%; 11: 90.5%
|  | d) Super-Structure | 30% | % | 4: 660.98; 7: 26%; 9: 40%; 11: 66%
|  | e) Miscellaneous | 2% | % | 4: 44.06; 9: -
|  | f) Contingency |  |  | 4: 28.65; 7: -; 9: -; 11: -
|  | Grand Total : |  |  | 4: 2231.91; 8: 1428.33; 12: 1428.33
|  | Overall physical Progress :- |  |  | 4: 85.91%
MONTHLY PROGRESS REPORT FOR THE MONTH OF |  |  |  |  | 9: OCTOBER, 2025
Name of Division |  | : KAWRTHAH
Source of Funding |  | : SASCI
Sl. No | Name of Works/Project | Unit |  | Approved Cost (in lakhs) | Date of Commencement | Target Date of Completion | Achievement upto previous month |  | Achievement for the month |  | Overall Cummulative achievement |  | Remarks | Mode of Contract
[7 empty] | Phy | Fin | Phy | Fin (in lakhs) | Phy | Fin (in lakhs)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Restoration of Damge due to Cyclone Remal under Kawrthah Division | Nos | 23 | 293.2 | 16.6.2025 | 16.1.2026 | 56.52% |  | 26.1% |  | 82.62% |  | Work in progress | Contract after call of restricted tender
| Grand Total : |  |  | 293.2 | 10: 82.62%
| Overall Physical Progress | : |  | 82.62%
MONTHLY PROGRESS REPORT FOR THE MONTH OF |  |  |  |  | 8: OCTOBER, 2025
Name of Division |  | : | Kawrthah
Source of Funding |  | : | 3054 RFB
Sl. No. | Name of Works/Project | Unit | Qnty. | Approved Cost (in lakh) | Date of commencement | Target Date of completion | Achievement upto previous month |  | Achievement for the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[7 empty] | Phy | Fin | Phy | Fin | Phy | Fin (actual)
1 | 2 | 3 | 4 |  | 6 | 7 | 8 | 9 | 8 | 10 | 11 | 12 | 13 | 14
I. | ANNUAL MAINTENANCE OPERATION PLAN 2025-26 (3054) UNDER KAWRTHAH DIVISION.
| 1) Patch Repair of Kawrthah Internal Road (Puksut kawn - HS Veng) at Kawrthah | Km | 0.446 | 75.33 | - | 31/12/2025 | - |  | - |  | - |  | Works to be started immediately | Departmental
| 2) Resurfacing of Hriphaw Town Road (Lalveng - Chhim veng) at Hriphaw Ch.0.400 - 7.395 Kmp | Km | 0.995 |  | 6: -; 7: 31/12/2025; 8: -; 8: -; 11: -
| 3) Patch repair of Chuhvel to Sihthiang Road | Km | 10.18 |  | 6: -; 7: 31/12/2025; 8: -; 8: -; 11: -
| 4) Approach road to Damcherra market (From MVI office) (MVI office - Zakamlova building) | Km | 0.133 |  | 6: -; 7: 31/12/2025; 8: -; 8: -; 11: -
| 5) Approach road to Police Quarters (Police station at KDZKT Police Quarter) | Km | 0.124 |  | 6: -; 7: 31/12/2025; 8: -; 8: -; 11: -
| 6) Re-surfacing of Approach road to VC House (Salvation Hall - VC House) Part-I at Tuidam | Km | 0.28 |  | 6: -; 7: 31/12/2025; 8: -; 8: -; 11: -
| 7) Re-surfacing of Approach road to Forest IB at Kawrtethawveng | Km | 0.2 |  | 6: -; 7: 31/12/2025; 8: -; 8: -; 11: -
| Total = |  |  | 75.33
| Overall Physical progress | : | 0%
MONTHLY PROGRESS REPORT FOR THE MONTH OF |  |  |  |  | 9: OCTOBER, 2025
Name of work/Project |  | : Construction of Up-gradation and Maintenance of Moroicherra to Lushaicherra (0.00 – 9.84 Kmp)
Name of Division |  | : Kawrthah
Date of Commencement |  | : 13.08.2024
Target Date of Completion |  | : 02.03.2026
Name of Contractor |  | : C.Vanlalruatkima, Lungdai
Sl. No | Components of Works | As per Agreement |  |  | 6: Achievement upto previous Month; 8: Achievement for the Month; 8: Overall Cummulative achievement; 11: Remarks/ Issues
|  | Qty | Unit | Item Amount (lakhs) | Phy Prog (Qty) | Fin Prog (lakh) | Phy Prog (Qty) | Fin Prog (lakh) | Phy Prog (Qty) | Fin Prog (lakh)
1 | 3 |  |  | 4 | 7 | 8 | 9 | 10 | 11 | 12 | 13
1 | A. Formation works : a) Clearing & setting | 9.84 | Km | 6.938 | 9.84 | 131.01 |  |  | 9.84 | 131.01 | Work in progress
b) New FC for curve Improvement
| Total of earthwork | 6562.8 | M3 | 4: 5.903; 7: 1478.6; 9: 5084.2; 11: 6562.8
2 | B. Side Drains : a) Unlined Side drain
| a) Unlined Side Drain | 8940 | Rm | 4: 7.161; 7: 4500; 9: 145; 11: 4645
| b) Lined Side drain | 900 | Rm | 4: 15.728
3 | C. Protection works : | 126 | Rm | 4: 57.2; 7: 126; 11: 126
4 | D. Drainage Work a) HP Culvert | 15 | Nos | 4: 88.148; 7: 2; 9: 2; 11: 4
5 | E. Minor Bridge Hand/Guard Rail | 3 | Nos | 4: 1.121
6 | F. Pavement works :
| a) Scarifying Existing Bituminous | 8.72 | Km | 4: 3.419; 7: 8; 9: 0.72; 11: 8.72
| b) WBM -II | 9.84 | Km | 4: 131.045; 7: 5.5; 9: 3.375; 11: 8.875
| c) WBM -III | 9.84 | Km | 4: 131.045
| d) Prime coat | 9.84 | Km | 4: 25.37
| e) MSS | 9.84 | Km | 4: 117.646
| f) Tack Coat | 9.84 | Km | 4: 5.744
| g) Earthern Shouder | 9.84 | Km | 4: 6.489
7 | G. Road Sign |  |  | 4: 26.467
8 | H. Title information |  |  | 4: 0.285; 7: 2; 11: 2
9 | I. Citizen information |  |  | 4: 0.166; 7: 1; 11: 1
10 | J. PMGSY LOGO |  |  | 4: 0.949; 7: 4; 11: 4
11 | K. AMC | 5 | Years | 4: 38.87
| TOTAL OF WORK COMPONENT |  |  | 4: 669.694; 8: 131.01; 12: 131.01
| Overall Physical Progress = | 33.88%
MONTHLY PROGRESS REPORT FOR THE MONTH OF |  |  |  | 9: OCTOBER, 2025
Name of work/Project |  | : Upgradation & Maintenance of Bairabi to Zamuang Road (Ch:0.00 to 24.20 Kmp)
Name of Division |  | : KAWRTHAH
Date of Commencement |  | : 29.8.2024
Target Date of Completion |  | : 1.3.2026
Name of Contractor |  | : Laltlanmawia, Kolasib
Sl. No. | Components of Works | As per Agreement |  | 7: Achievement upto previous Month; 9: Achievement for the Monthr; 11: Overall cummulative achievement; 13: Remarks/ Issues
|  | Qty | Unit | Item Amount (lakhs) | Phy Prog (Qty) | Fin Prog (lakh) | Phy Prog (Qty) | Fin Prog (lakh) | Phy Prog (Qty) | Fin Prog (lakh)
1 | 3 |  |  | 4 | 7 | 8 | 9 | 10 | 11 | 12 | 14
1 | Protection work | 77 | Rm | 4: 30.32; 14: Work in progress
2 | Side Drain
| i) LSD | 120 | Rm | 4: 4.11
| ii) ULSD | 24080 | Rm | 4: 22.35; 7: 3000; 11: 3000
3 | Pavement
| i) Subgrade | 24.2 | Km | 4: 84.63; 7: 12.2; 11: 12.2
| ii) GSB | 24.2 | Km | 4: 188.81; 7: 6.2; 11: 6.2
| iii) WBM-II | 24.2 | Km | 4: 501.1281
| iv) WBM-III | 24.2 | Km | 4: 492.4852
| v) Prime coat | 24.2 | Km | 4: 117.9918
| vi) Tack coat | 24.2 | Km | 4: 26.6613
| vii) MSS | 24.2 | Km | 4: 661.861
| viii)Shoulders | 24.2 | Km | 4: 27.08
4 | Road marking | 24.2 | Km | 4: 14.93
5 | KM Stone &Road Signs:
| i) Km Stone,Hm Stone etc. | 122 | No | 4: 11.77
| ii) Boundary pillar | 242 | No
| iii) Information & Cautionary Sign | 151 | No | 7: 2; 11: 2
6 | AMC |  |  | 4: 128.26
| GRAND TOTAL |  |  | 4: 2312.3874
| Overall Progress = | 10.1%
Sr.Executive Engineer, PWD.,
Kawrthah Division, Kawrthah.

## LBPD
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER, 2025 ( BUILDING WORKS )
Name of Division: Lunglei Building Project Division, Lunglei
Rs. in Lakh
Sl.no | Name of Scheme | Unit | Approved Cost (Rs.in lakh) | Date of Commencement | Target Date of Completion : | Commulative Progress at the end of last month |  | Achievement of Works during the month |  | Overall Commulative Achievement |  | Remarks | Mode of Tender
| Name of Work/Project |  |  |  |  | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
SASCI
1 | Construction of Laboratory Building at Civil Hospital, Lunglei (Ground floor) |  | 192.98 | 28.10.2021 | 28.10.2022 | 100% | 192.98 |  |  | 100% | 192.98 | Completed. | Restricted Tender
2 | Construction of Laboratory Building at Civil Hospital, Lunglei (1st & 2nd Floor) Supplementary Works |  | 396 | 28.10.2022 | 28.4.2024 | 100% | 330.7 |  |  | 100% | 330.7 | Civil Works completed and I/E not yet started | Supplementary Works to sl.no(a) above
3 | Construction of Futsal ground at Lungdai, Kawnpui, Ngopa, Kawlkulh, Champhai, Serchhip & Siaha (Sh: Construction of Futsal Ground at Siaha)
1 | Construction of Meisatla Futsal Ground at Siaha |  | 34.786 | 20.03.23 | 20.09.23 | 49% | 21.84 | 0% | 0 | 49% | 21.84 | Work not completed due to site dispute | Restricted Tender
4 | Construction of Government Building at Hnahthial, PWD EE Quarters, Circuit House & DC Office |  | 344.03 | 23.03.24 | 23.03.26 |  | 227.54 |  | 0 |  | 227.54 |  | Restricted Tender
1 | Construction of PWD EE Quarters at Hnahthial |  |  |  |  | 95% | [5 empty] | Work in Progress
2 | Hnahthial Circuit House |  |  |  |  | 100% |  |  |  | 100% |  | Completed
5 | Construction of Community Hall at Siasi, Phural, Tawngkawlong, Tipa B, Meisavaih, Amotlah |  | 305.72 | 23.03.24 | 23.07.25 |  | 103.5 |  | 0 |  | 103.5 |  | Restricted Tender
1 | Construction and Completion of MTP(H) Office |  |  |  |  | 100% |  |  |  | 100% |  | Completed
2 | Construction of MTP Information Office |  |  |  |  | 100% |  |  |  | 100% |  | Completed
3 | Construction of Bazarshed at New Siaha East-II |  |  |  |  | 100% |  |  |  | 100% |  | Completed
4 | Continuation of MYA Hall at New Siaha East-I |  |  |  |  | 100% |  |  |  | 100% |  | Completed
5 | Construction of MTP Hall and Retaining Wall at Amotlah |  |  |  |  | 100% |  |  |  | 100% |  | Completed
6 | Construction of Model Middle School Ground at Retaining Wall at New Siaha West-I |  |  |  |  | 100% |  |  |  | 100% |  | Completed
7 | Construction of Retaining Wall at Futsal Ground at Tipi Ferry |  |  |  |  | 100% |  |  |  | 100% |  | Completed
6 | Construction of Play ground with Pavillion at Lungtian, Sangau, Bualpui (NG), Tuichawngtlang, Ngunlingkhua, T. Dumzau |  | 339.41 | 23.03.24 | 23.07.25 |  | 164.53 |  | 0 |  | 164.53 |  | Restricted Tender
1 | Renovation of Community Hall Ramhlun Veng, Sangau |  |  |  |  | 100% |  |  |  | 100% |  | Completed
2 | Construction of Community Hall Council Veng, Lawngtlai |  |  |  |  | 100% |  |  |  | 100% |  | Completed
3 | Vertical Extension of Central Young Lai Association Office Lawngtlai |  |  |  |  | 100% |  |  |  | 100% |  | Completed
4 | Construction of Futsal Ground at Lungtian-I |  | 339.41 | 23.03.24 | 23.07.25 | 100% | 164.53 |  | 0 | 100% | 164.53 | Completed
5 | Construction of Futsal Ground at Bualpui (NG) |  |  |  |  | 100% |  |  |  | 100% |  | Completed | Restricted Tender
6 | Construction of Futsal Ground at Sangau |  |  |  |  | 100% |  |  |  | 100% |  | Completed
7 | Construction of Volleyball Court Lungzarhtum |  |  |  |  | 100% | [5 empty] | Completed
7 | Construction of Community Hall Cum Market Building at Luangmual, Lunglei |  | 301.19 | 23.03.24 | 23.07.25 |  | 132.21 |  | 0 |  | 132.21 |  | Restricted Tender
1 | Construction of DM High School Building ( Theiriat ) |  |  |  |  | 100% |  |  |  | 100% |  | Completed
2 | Construction of Luangmual Market Building |  |  |  |  | 100% |  |  |  | 100% |  | Completed
3 | Construction of Sairep Community Hall |  |  |  |  | 100% |  |  |  | 100% |  | Completed
8 | Vertical Extention of Market Building at Kamalanagar |  | 237.85 | 23.03.24 | 31.12.2025 |  | 23.97 |  | 4.74 |  | 28.71 |  | Restricted Tender
1 | Vertical Extension of existing Bazaar Building at Kamalanagar-I with Tin Roofing |  |  |  |  | 50% |  | 15% |  | 65% |  | Work in Progress
2 | Construction of additional Bazaar Building by demolishing the existing dilapidated building that was constructed under BADP |  |  |  |  | 50% |  | 20% |  | 70% |  | Work in Progress
3 | 2. Construction of Rest House at PWD Complex Bunghmun. |  |  |  |  | 60% |  | 5% |  | 65% |  | Work in Progress
9 | Construction of Community Hall cum Health Clinic Center at Kawlhawk, Bungtlang West, South Lungdai and Serte |  | 371.57 | 23.03.24 | 23.07.25 |  | 103.04 |  | 0 |  | 103.04 |  | Restricted Tender
1 | Higher Secondary School Building, Buarpui |  |  |  |  | 100% |  |  |  | 100% |  | Completed
2 | Community Hall, Kawlhawk |  |  |  |  | 100% |  |  |  | 100% |  | Completed
3 | Health Clinic, Bungtlang West |  |  |  |  | 100% |  |  |  | 100% |  | Completed
4 | PWD IB repair, Sertlangpui |  |  |  |  | 100% |  |  |  | 100% |  | Completed
5 | Construction of Badminton Hall at Chhipphir |  |  |  |  | 95% |  | 0% |  | 95% |  | No progress since june 2025
6 | Completion of Badminton Hall at Chhipphir |  |  |  |  | 95% |  | 0% |  | 95% |  | No progress since june 2025
7 | Anganwadi Centre-I, Sertlangpui |  |  |  |  | 100% |  |  |  | 100% |  | Completed
8 | Anganwadi Centre-I New Construction, Serte |  |  |  |  | 100% |  |  |  | 100% |  | Completed
9 | Health & Wellness Officer Quarter new construction, Serte |  |  |  |  | 100% |  |  |  | 100% |  | Completed
10 | Health Clinic Office, South Lungdai |  |  |  |  | 100% |  |  |  | 100% |  | Completed
11 | Construction of Futsal Ground Flooring at Lalveng, Haulawng |  |  |  |  | 100% |  |  |  | 100% |  | Completed
10 | Construction of Government Quarters (General Pool) at Venglai, Lunglei (Ramnghaka's Quarters Site) SH : Type-IV Quarters (2 units, 1 Block) |  | 214.99 | 13.05.2025 | 13.05.2026 | 27% | 0 | 6% | 43.83 | 33% | 43.83 | Work in Progress | Restricted Tender
11 | Construction of Government Quarters (General Pool) at Venglai, Lunglei (Soil Quarters Site) SH : Type-III Quarters (1 unit) Type-IV Quarters (2 units) |  | 221.37 | 14.05.2025 | 14.05.2026 | 27% | 0 | 11% | 45.74 | 38% | 45.74 | Work in Progress | Restricted Tender
12 | Construction of Government Quarters (General Pool) at Venglai, Lunglei (Zautea's Quarters Site) SH : Type-IV Quarters (1 unit, 1 Block) |  | 79.29 | 19.05.2025 | 19.05.2026 | 4% | 0 | 6% | 0 | 10% | 0 | Work in Progress | Restricted Tender
13 | Construction of GovernmentQuarters (General Pool) at Venglai, Lunglei (Numami's Quarters Site) SH : Type-IV Quarters (1 unit, 1 Block) |  | 79.29 | 13.05.2025 | 13.05.2026 | 80% | 0 | 15% | 45.36 | 95% | 45.36 | Work in Progress | Restricted Tender
14 | Construction of Government Quarters (General Pool) at Venglai, Lunglei (Quarters No. 5 Site) SH : Type-III Quarters (2 units, 1 Block) |  | 133.42 | 13.05.2025 | 13.05.2026 | 18% | 0 | 7% | 0 | 25% | 0 | Work in Progress | Restricted Tender
15 | Construction of Government Quarters (General Pool) at Venglai, Lunglei (Zorini's Quarters Site) SH : Type-III Quarters (2 units, 1 Block) |  | 137.99 | 13.05.2025 | 13.05.2026 | 27% | 0 | 23% | 34.08 | 50% | 34.08 | Work in Progress | Restricted Tender
16 | Construction of Government Quarters (General Pool) at Venglai, Lunglei (Thapa's Quarters Site) SH : Type-III Quarters (2 units, 1 Block) |  | 137.99 | 13.05.2025 | 13.05.2026 | 35% | 0 | 20% | 40 | 55% | 40 | Work in Progress | Restricted Tender
17 | Construction of Government Quarters (General Pool) at Venglai, Lunglei (Pi Marcella's Quarters Site) SH: Type - III Quarters (2 Units) |  | 120.02 | 13.05.2025 | 13.05.2026 | 26% | 0 | 12% | 30 | 38% | 30 | Work in Progress | Restricted Tender
18 | Construction of Government Quarters (General Pool) at Venglai, Lunglei (Pi Marcella's Quarters Site) SH: Type - III Quarters (1 Unit) |  | 86.52 | 13.05.2025 | 13.05.2026 | 60% | 0 | 25% | 24.94 | 85% | 24.94 | Work in Progress | Restricted Tender
19 | Construction of Working Women Hostel at Ramthar Veng, Lunglei |  | 1186.47 | 14.05.2025 | 14.05.2027 | 2% | 0 | 1% | 0 | 3% | 0 | Work in Progress | Restricted Tender
20 | Construction of District Prison/Jail,Lunglei |  | 523.87 | 28.04.2025 | 28.04.2026 | 12% | 0 | 3% | 0 | 15% | 0 | Work in Progress | Restricted Tender
21 | Construction of Fire Station at Lunglei, Mizoram |  | 178.46 | 04.08.2025 | 04.08.2026 | 1% | 0 | 1% | 0 | 2% | 0 | Work in Progress | Restricted Tender
22 | Construction of Revenue Staff Quarters at Hnahthial |  | 186.4 | 29.07.2025 | 29.07.2026 | 5% | 0 | 0% | 0 | 5% | 0 | Work in Progress | Restricted Tender
23 | Construction of DCSO Office & Disaster Management & Rehabilitation Office Associated Parking at Lunglei |  | 117.06 | 21.07.2025 | 21.07.2026 | 1% | 0 | 1% | 0 | 2% | 0 | Work in Progress | Restricted Tender
24 | Reconstruction of Thingsai PWD IB |  | 192.35 | 07.07.2025 | 07.07.2026 | 0% | 0 | 0% | 0 | 0% | 0 | Works Not Yet started | Restricted Tender
25 | Upgradation of District Research Office at Lunglei |  | 41.27 | 11.08.2025 | 11.08.2026 | 0% | 0 | 5% | 0 | 5% | 0 | Work in Progress | Restricted Tender
26 | Upgradation of District Research Office at Hnahthial |  | 24.8 | 18.08.2025 | 18.08.2026 | 0% | 0 | 0% | 0 | 0% | 0 | Works Not Yet started | Restricted Tender
27 | Construction of Government Quarters (General Pool) at Lawngtlai at Additional DC Quarter |  | 133.09 | 28.04.2025 | 28.04.2026 | 7% | 0 | 8% | 0 | 15% | 0 | Work in Progress | Restricted Tender
28 | Construction of Government Quarters (General Pool) at Lawngtlai Electric Veng (near RD Office) |  | 648.26 | 28.04.2025 | 28.04.2026 | 0% | 0 | 5% | 0 | 5% | 0 | Work in Progress | Restricted Tender
29 | Construction of Government Quarters (General Pool) at Lawngtlai Electric Veng (near BDO Office) |  | 220.73 | 05.05.2025 | 05.05.2026 | 4% | 0 | 1% | 0 | 5% | 0 | Work in progress. | Restricted Tender
30 | Construction of Government Quarters (General Pool) at Lawngtlai Electric Veng (near A&T Office) |  | 219.67 | 28.04.2025 | 28.04.2026 | 2% | 0 | 13% | 0 | 15% | 0 | Work in progress. | Restricted Tender
31 | SDO (C) Office & Quarter at Chawngte |  | 183.24 | 20.07.2025 | 20.07.2026 | 0% | 0 | 0% | 0 | 0% | 0 | Works Not Yet started | Restricted Tender
32 | Construction of Fire Station at Lawngtlai, Mizoram |  | 180.78 | 04.08.2025 | 04.08.2026 | 0% | 0 | 7% | 0 | 7% | 0 | Work in progress. | Restricted Tender
33 | Construction of Circuit House Under DC Office, Lawngtlai District |  | 765.04 | 19.07.2025 | 19.07.2026 | 0% | 0 | 1% | 0 | 1% | 0 | Work in progress. | Restricted Tender
34 | Construction of Office Building Cum Quarters at Lawngtlai (Commissioner of State Tax) |  | 296.08 | 15.07.2025 | 15.07.2026 | 0% | 0 | 1% | 0 | 1% | 0 | Work in progress. | Restricted Tender
35 | Upgradation of District Research Office at Lawngtlai |  | 23.14 | 11.08.2025 | 11.08.2026 | 60% | 0 | 40% | 0 | 100% | 0 | Completed | Restricted Tender
36 | Construction of Circuit Houses at Siaha |  | 522.13 | 28.04.2025 | 28.04.2026 | 1% | 0 | 10% | 0 | 11% | 0 | Work in progress. | Restricted Tender
37 | Construction of Government Quarters (General Pool) at New Siaha at Additional DC Quarters (Inside Gate) |  | 228.26 | 28.04.2025 | 28.04.2026 | 10% | 0 | 10% | 0 | 20% | 0 | Work in progress. | Restricted Tender
38 | Construction of Government Quarters (General Pool) at New Siaha at Additional DC Quarters (Outside Gate) |  | 239.98 | 28.04.2025 | 28.04.2026 | 15% | 0 | 40% | 0 | 55% | 0 | Work in progress. | Restricted Tender
39 | Construction of Government Quarters (General Pool) at New Siaha at Additional DC Quarters (Type III) |  | 273.97 | 28.04.2025 | 28.04.2026 | 12% | 0 | 5% | 0 | 17% | 0 | Work in progress. | Restricted Tender
40 | Construction of Government Quarters (General Pool) at New Siaha at Meisavaih Site-I (Type III, 4 unit) |  | 274.93 | 28.04.2025 | 28.04.2026 | 7% | 0 | 13% | 0 | 20% | 0 | Work in progress. | Restricted Tender
41 | Construction of Government Quarters (General Pool) at New Siaha at Meisavaih Site-II (Type III, 4 unit) |  | 274.79 | 28.05.2025 | 28.05.2026 | 12% | 0 | 33% | 0 | 45% | 0 | Work in progress. | Restricted Tender
42 | Construction of District Prison/Jail, Siaha |  | 916.43 | 28.04.2025 | 28.04.2026 | 15% | 0 | 13% | 0 | 28% | 0 | Work in progress. | Restricted Tender
43 | SDO (C) Office & Quarters at Tipa |  | 184.71 | 07.07.2025 | 07.07.2026 | 0% | 0 | 7% | 0 | 7% | 0 | Work not yet started due to site dispute | Restricted Tender
44 | Construction of Fire Station at Council Vaih, Siaha |  | 189.38 | 04.08.2025 | 04.08.2026 | 0% | 0 | 7% | 0 | 7% | 0 | Works Not Yet started | Restricted Tender
45 | Upgradation of District Research Office at Siaha |  | 22.82 | 18.08.2025 | 18.08.2026 | 0% | 0 | 45% | 0 | 45% | 0 | Works Not Yet started | Restricted Tender
1 | NABARD
CONSTRUCTION OF WAREHOUSES WITH ASSOCIATED INFRASTRUCTURE IN 12 LOCATIONS UNDER NABARD
| GROUP- III: | [11 empty] | Restricted Tender
| 1) Siaha SDC |  | 444.99 | 17.07.2023 | 31.3.2026 | 57% | 210.45 | 1% | 0 | 58% | 210.45 | No progress since previous month
| 2) Chapui |  | 197.82 | 17.07.2023 | 28.2.2026 | 65% | 98.89 | 15% | 0 | 80% | 98.89 | Works in progress.
| 3) Bungtlang South |  | 162.63 | 17.07.2023 | 31.12.2025 | 94% | 127.07 | - | 0 | 94% | 127.07 | Works in progress. | Restricted Tender
| GROUP- IV: | [11 empty] | Restricted Tender
| 1) Lungpher |  | 197.12 | 17.07.2023 | 17.7.2025 | 100% | 194.11 | 0% | 0 | 100% | 194.11 | Civil Works completed and I/E not yet started
| GROUP- VI: | [11 empty] | Restricted Tender
| 1) South Vanlaiphai |  | 187.15 | 17.07.2023 | 19.11.2025 | 76% | 107.34 | 1% | 0 | 77% | 107.34 | Works in progress.
1 | 2) Vawmbuk |  | 197.82 | 17.07.2023 | 31.12.2025 | 78% | 139.92 | 1% | 0 | 79% | 139.92 | Works in progress.
| GROUP-VIII: | [11 empty] | Restricted Tender
| 1) Hnahthial |  | 197.24 | 17.07.2023 | 19.07.2027 | 4% | 0 | 2% | 0 | 6% | 0 | Work started
| 2) Thingsai |  | 160.32 | 17.07.2023 | 13.10.2025 | 72% | 42.34 | 1% | 0 | 73% | 42.34 | Works in progress
| 3) Cherhlun |  | 85.61 | 17.07.2023 | 17.7.2025 | 94% | 26.72 | 1% | 0 | 95% | 26.72 | Works in progress
| 4) Siata |  | 197.82 | 17.07.2023 | 31.12.2025 | 92% | 74.43 | 1% | 0 | 93% | 74.43 | Works in progress | Restricted Tender
| GROUP-X: | [11 empty] | Restricted Tender
| 1) Vaseikai |  | 220.35 | 17.07.2023 | 20.12.2025 | 87% | 109.75 | 0% | 71.01 | 87% | 180.76 | Works in progress
| 2) Tlabung |  | 93.84 | 17.07.2023 | 13.12.2025 | 90% | 54.331 | 1% | 0 | 91% | 54.331 | Works in progress
2 | Construction of Infrastructure Support for School of Agricultural Science at Hnahthial (Phase-II) | [10 empty] | Works in progress | Restricted Tender
| i) Boys Hostel |  | 659.4 | 08.04.2023 | 19.12.2025 | 95% | 293.71 | 3% | 0 | 98% | 293.71
| ii) Staff Quarter Type - III |  |  |  |  | 95% |  | 3% |  | 98%
| iii) Staff Quarter Type - II |  |  |  |  | 95% |  | 3% |  | 98%
| iv) Guest House |  |  |  |  | 95% |  | 3% |  | 98%
NEC
1 | Construction of Lunglei Market and Trade Centre at Electric/ Chanmari Veng, Lunglei |  | 1403.4 | 25.08.2022 | 16.01.2026 | 83% | 1042.54 | 2% | 39.78 | 85% | 1082.32 | Work in progress | Restricted Tender
CSS
1 | Construction of Academic Building for Nursing School at Lunglei (Upgradation) | - | 441.35 | 19.8.2024 | 19.08.2026 | 57% | 0 | 3% | 39.78 | 60% | 68.69 | Works in progress | Open Tender
NEDP
1 | Construction of DC Bungalow (Type VI) at Siaha |  | 93.86 | 26.11.2018 | 23.05.2024 (Revised) | 100% | 109 | 0% | 0 | 100% | 109 | Handover in process | Restricted Tender
2 | Construction of DC Office Building at Siaha |  | 509.08 + 23.07 = 532.15 | 31.10.2018 | 31.12.2025 | 97% | 473.53 | 0.5% | 48.09 | 97.5% | 521.62 | Addl. Expenditure sanction of Rs.23.07lakhs received vide ES no. D/11021/27/2019-pwd (T) of dt: 12.03.25 | Restricted Tender
NESIDS
1 | Construction of 50-Bedded District Hospital Complex and Procurement of Equipment at Hnahthial, Mizoram |  | 1378.86 | 25.6.2024 | 25.12.2026 | 27% | 0 | 3% | 137.37 | 30% | 137.37 | Work in progress | Open Tender
MINISTRY OF TRIBAL AFFAIRS
1 | Construction of Auditorium at Pukpui Lunglei |  | 470.088 | 16.9.2023 | 16.01.2025 | 0% | 0 | 0% | 0 | 0% | 0 | Dismantling at site completed and construction will be started as soon as estimate is approved. | Restricted Tender
Sr. Executive Engineer, PWD.,
Lunglei Building Project Division, Lunglei

## LRD - I
MONTHLY PROGRESS REPORT UNDER LUNGLEI ROAD DIVISION - I, LUNGLEI
FOR THE MONTH OF OCTOBER/ 2025
(Rs. in lakh)
Sl. No. | Name of Schemes | Quantity | Unit | Approved Cost (Rs in Lakh) | Date of Commencement | Target Date of Comple-tion | Cumulative Progress at the end of last month |  | Achievement of works during the month |  | Overall Cumulative achievement |  | Remarks | Mode of Tender
| Name of Works / Project | [5 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
SASCI
I | Aizawl-Thenzawl-Lunglei Road Between Kanghmun 'S' and Kikawn, Lunglei Phase-I, (Sh:- Group - A Between 100.00 - 120.00Kmp) | [13 empty] | 0
1 | Scarifying existing bituminous | 2129.55 | Sqm | 0.92 | 03.07.2023 | 30.09.2025 | 22554.77 | 9.7 |  |  | 22554.77 | 9.7 | Work completed. Deviation approval vide No.B-17024/91/CE-R/25/PW/153 of 24.9.2025 |  | 0
2 | Water Bound Macadam | 726.31 | Cum | 40.67 |  |  | 6745.29 | 377.74 |  |  | 6745.29 | 377.74
3 | OPC + Prime Coat | 14063.5 | Sqm | 66.09 |  |  | 15533.14 | 73 |  |  | 15533.14 | 73
4 | Seal coating + Tack Coat | 110000 | Sqm | 195.8 |  |  | 15533.14 | 27.65 |  |  | 15533.14 | 27.65 |  |  | 0
5 | DLC | 660.83 | Cum | 49.63 |  |  | 185.19 | 13.91 |  |  | 185.19 | 13.91
6 | PQC | 991.237 | Cum | 208.16 |  |  | 241.35 | 50.68 |  |  | 241.35 | 50.68
7 | RCC Hume Pipe Culvert | 1 | No | 9.9 |  |  | 1 | 9.9 |  |  | 1 | 9.9
8 | Lined Side Drain | 147.34 | Cum | 8.89 |  |  | 26.33 | 0.54 |  |  | 26.33 | 0.54
9 | Side Drain Clearance | 20000 | Rm | 18 |  |  | 20000 | 18 |  |  | 20000 | 18
10 | Clearing Road Side Jungle | 40 | Km | 4.36 |  |  | 40 | 4.36 |  |  | 40 | 4.36
11 | Breast Wall + Lined Side Drain with RCC Cover | 635.96 | m | 44.67 |  |  | 677.51 | 61.59 |  |  | 677.51 | 61.59
| TOTAL = |  |  | 647.09 |  |  | 100% | 647.07 |  |  | 100% | 647.07
MONTHLY PROGRESS REPORT UNDER LUNGLEI ROAD DIVISION - I, LUNGLEI
FOR THE MONTH OF OCTOBER/2025
(Rs. in lakh)
Sl. No. | Name of Schemes | Quantity | Unit | Approved Cost (Rs in Lakh) | Date of Commencement | Target Date of Comple-tion | Cumulative Progress at the end of last month |  | Achievement of works during the month |  | Overall Cumulative achievement |  | Remarks | Mode of Tender
| Name of Works / Project | [5 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
ANNUAL PLAN (5054)
I | Construction of Bailey Bridge (SS) Over R.Sazek on Mauzam to New Sachan Road (Sh: Construction of Abutment & Wingwall)
| 1) Abutment Wall | 2 | Nos | 42.2 | 24.02.2025 | 31.03.2026 | 100% | 58.68 |  |  | 100% | 58.68 | Completed
| 2) Wing Wall | 1 | No |  |  |  | 100% |  |  |  | 100% |  | Completed
| 3) Gabian Wall | 3 | Nos |  |  |  | 100% |  |  |  | 100% |  | Completed
| 4) Steel Structure | 1 | No | 24.66 |  |  | 0% |  |  |  | 0% |  | Material Collection
| TOTAL = |  |  | 66.86 |  |  | 75% | 58.68 |  |  | 75% | 58.68

## LRD-II
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER, 2025
Name of Division: Lunglei Road Division-II, Lunglei
Source of Funding : SASCI
Sl. No | Name of Work/Scheme | Unit | Approved Cost (Rs. In Lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last Month |  | Achievement of Works during the Month |  | Overall Cummulative achievement |  | Remarks | Mode of Tender
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
I | SASCI
1 | Improvement and Widening of Public Playground at Zobawk including Construction of Retaining wall | Rm | 35 | 27.12.2023 | 26.12.2024 | 0% | 0 | 0% | 0 | 0% | 0 | Not yet started. EOT granted upto 23.10.2025 | Restricted Tender
Sr. Executive Engineer, PWD.,
Lunglei Road Division-II, Lunglei

## LAWNGTLAI DIV
Monthly Progressive Report for the Month of OCTOBER 2025
Name of Division |  | : | Lawngtlai Division
Slno | Name of Work/Project | Unit (km) | Approved Cost (Rs.in lakh) | Date of Commencement | Target Date of Completion | Cumulative Progress at the end of last month |  | Achievement of Work During the Month |  | Overall Cumulative Achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
NESIDS
1 | Improvement & Upgradation of Lawngtlai to Tuipui Ferry Road in the State of Mizoram under North East Special Infrastructure Developmant Scheme (NESIDS) | 10 | 2897.87 | 08.08.2019 | 30.06.2023 | 100% | 2666.68 |  |  | 100% | 2666.68 | Physically Completed | NIT
NABARD
2 | NABARD/ Improvement and Strengthening of Nalkawn - Chamdur Valley (NCV) (Section I & II) Road Under NABARD | 88.5 | 2616.41 | 09.08.2019 | 31.12.2024 | 71.04% | 1824.89 |  |  | 71.04% | 1824.89 | Proposed for Termination as per Review Meeting on 24.09.2025 | Item Rate
SASCI ( 2022-2023 & 2023-2024)
1 | Improvement of Thlengang to River Chhimtuipui Road ( Construction of RCC Dock Along with Approach Slab) | 2Nos | 23.31 | 11.05.2023 | 31.05.2024 | 100% | 23.31 |  |  | 100% | 23.31 | Completed | Item Rate
2 | Widening of Lawngtlai to Sahrilui chhuah (Kolodyne River) Balu road | 7.5 km | 94.8 | 11.05.2023 | 31.05.2024 | 100% | 40.49 |  |  | 100% | 94.8 | Completed | Item Rate
3 | Improvement of Bethel veng to Chengkawllui Road at College veng, Lawngtlai | 1.6 Km | 90.84 | 11.05.2023 | 31.05.2024 | 100% | 90.83 |  |  | 100% | 90.83 | Completed | Item Rate
4 | Formation cutting of Vathuampui to Mautlang Road | 8.00Km | 70.47 | 11.05.2023 | 31.05.2024 | 100% | 70.42 |  |  | 100% | 70.42 | Completed | Item Rate
5 | Widening of Bungtlang 'S' to Saikhawthlir Road | 5.00Km | 56.15 | 11.05.2023 | 31.05.2024 | 100% | 50.13 |  |  | 100% | 50.13 | Completed | Item Rate
6 | Widening of Hmawngbu to Kakichhuah Road | 7.50Km | 61.99 | 11.05.2023 | 31.05.2024 | 100% | 61.97 |  |  | 100% | 61.97 | Completed | Item Rate
7 | Improvement of Diltlang to Chawngtelui road (Construction of Retaining wall at certain locations) | 51.50Km | 25.07 | 11.5.2023 | 31.05.2024 | 51.5 | 25.07 |  |  | 100% | 25.07 | Completed | Item Rate
8 | Resurfacing of NH-54 to DTO Office (including courtyard) at Chanmari, Lawngtlai | 50.00m | 6.997 | 11.5.2023 | 31.05.2024 | 50 | 6.997 |  |  | 100% | 6.997 | Completed | Item Rate
9 | Construction of Minor Bridge between Khawmawi Bazar veng to Khawmawi vengthar | 1No | 34.48 | 11.5.2023 | 31.05.2024 | 1 No | 34.47 |  |  | 100% | 34.47 | Completed | Item Rate
10 | Blacktopping of Internal road at Lawngpuighat | 0.8Km | 81.65 | 11.5.2023 | 31.05.2024 | 0.8 | 81.63 |  |  | 100% | 81.63 | Completed | Item Rate
11 | Construction of Playground approach road at Thingfal Mamte veng | 420.00m | 19.49 | 11.5.2023 | 31.05.2024 | 420 | 19.49 |  |  | 100% | 19.49 | Completed | Item Rate
12 | Town extension Road at Electric Veng, Lawngtlai | 280Rm | 22.81 | 26.02.2024 | 31.12.2024 | 100% | 21.13 |  |  | 100% | 21.13 | Completed | Item Rate
13 | Construction of RDC road to Roliana Tuikhur at Lawngtlai | 122.00Rm | 9.96 | 26.02.2024 | 31.12.2024 | 100% | 9.45 |  |  | 100% | 9.45 | Completed | Item Rate
14 | Construction of Retaining Wall with steps at Bazar Thlanmual Road, Lawngtlai | 60.00Rm | 20 | 26.02.2024 | 31.12.2024 | 100% | 19.23 |  |  | 100% | 19.23 | Completed | Item Rate
15 | PCC Pavement of Internal Village Road at Lawngtlai L-IV | 150.00Rm | 10 | 26.02.2024 | 31.12.2024 | 100% | 9.6 |  |  | 100% | 9.6 | Completed | Item Rate
16 | Town extension Road at Lawngtlai L-III | 110.00Rm | 7.2 | 26.02.2024 | 31.12.2024 | 100% | 6.86 |  |  | 100% | 6.86 | Completed | Item Rate
17 | Construction of Culvert at Council veng to Bazar Road, Lawngtlai | 1No | 20 | 26.02.2024 | 31.12.2024 | 100% | 19.25 |  |  | 100% | 19.25 | Completed | Item Rate
18 | Village extension Road at Vaivakawn, Vawmbuk | 1.6 Km | 10 | 26.02.2024 | 31.12.2024 | 100% | 9.53 |  |  | 100% | 9.53 | Completed | Item Rate
19 | Internal Road Pavement (Approach road to PWD Rest House at Chawnhu) | 200.00Rm | 6.7 | 26.02.2024 | 31.12.2024 | 100% | 6.43 |  |  | 100% | 6.43 | Completed | Item Rate
20 | Construction of Side Drain near Piangliana Residence at Mualbu 'L' | 165.00Rm | 3.2 | 26.02.2024 | 31.12.2024 | 100% | 3.04 |  |  | 100% | 3.04 | Completed | Item Rate
21 | Approach Road Between PMGSY Road to Kawnkhua | 930.00Rm | 7.4 | 26.02.2024 | 31.12.2024 | 100% | 7.07 |  |  | 100% | 7.07 | Completed | Item Rate
22 | Construction of PCC Pavement from Nimaichondro House to Primary School at Ngunling khua | 80.00Rm | 4.5 | 26.02.2024 | 31.12.2024 | 100% | 3.96% |  |  | 100% | 3.96 | Completed | Item Rate
23 | Construction of Culvert at Berema Tuikhur to College veng road, Lawngtlai | 1 Nos | 8 | 26.02.2024 | 31.12.2024 | 100% | 7.69 |  |  | 100% | 7.69 | Completed | Item Rate
24 | Widening of Road from Paithar to Sihtlangpui | 6.90 Km | 20 | 26.02.2024 | 31.12.2024 | 100% | 19.39 |  |  | 100% | 19.39 | Completed | Item Rate
25 | Construction of Link Road from upper Saikah to Saikah 'L' | 2.20 Km | 5 | 26.02.2024 | 31.12.2024 | 100% | 4.74 |  |  | 100% | 4.74 | Completed | Item Rate
26 | Construction of Retaining Wall at College Veng, Lawngtlai | 18.00 Rm | 9 | 26.02.2024 | 31.12.2024 | 100% | 8.63 |  |  | 100% | 8.63 | Completed | Item Rate
27 | Construction of Link Road from Chawntlangpui to Khuailuichhuah | 4.80 Km | 75 | 26.02.2024 | 31.12.2024 | 100% | 72.01 |  |  | 100% | 72.01 | Completed | Item Rate
Restoration of Damage Due to Cyclone Remal under Lawngtlai Division
28 | (i) Restoration of collapsed road formation by Construction of Gabion wall at 1.400 kmp on DEO office to V.Zathanga Ground at L-IV, Lawngtlai | 17.00 Km | 20.62 | 09.07.2025 | 09.01.2026 | 0% | 0 |  |  | 0% | 0 | Civil works not yet started due to Monsoon rains, collection of Materials & Site preparation in progress | Item Rate
29 | (ii) Restoration of collapsed road formation by Construction of Retaining Wall at various locations on Thingfal-Mamte-Thlengang-Tuipui Road | 34.50 Km | 19.14 | 09.07.2025 | 09.01.2026 |  | 0 | 5% |  | 5% | 0 | Work in Progress | Item Rate
30 | (iii) Restoration of collapsed road formation by Construction of Retaining Wall at various locations on Nalkawn to Chamdur Valley Road | 41.80 Km | 26.79 | 09.07.2025 | 09.01.2026 |  | 0 | 5% |  | 5% | 0 | Work in Progress | Item Rate
31 | (iv) Restoration of collapsed road formation by Construction of Gabion wall at 3.200 kmp on Lawngtlai to Tuipui Ferry Road | 45.00 Km | 23.45 | 09.07.2025 | 09.01.2026 |  | 0 | 6% |  | 6% | 0 | Work in Progress | Item Rate
32 | (v) Restoration of collapsed road formation at 6.700 kmp on Lawngtlai to Tuipui Ferry Road (Sh: Construction of Gabion wall, re-construction of HP culvert & Repair of pavement) | 22.00 Km | 39.16 | 09.07.2025 | 09.01.2026 |  | 0 | 5% |  | 5% | 0 | Work in Progress | Item Rate
5054 Co under Road & Bridge
1 | Construction of Slab Culverts on chawnhu 132/33 Kv Power Station Road & Approach Road to Chengkawltlang at Council Veng, Lawngtlai under 5054 | 6 Nos | 24.76 | 28.11.2024 | 03.06.2025 | 6 Nos | 24.76 |  |  | 6 Nos | 24.76 | Completed | Item Rate

## LLI ELEC DIV
MONTHLY PROGRESSIVE REPORT FOR THE MONTH OF OCTOBER 2025
FOR WORKS UNDER STATE PLAN FUND
Name of Division : PWD Electrical Division,Lunglei.
Source of funding : State funding | [11 empty] | Rs in Lakhs
Sl No | Name of works/Project | Unit | Approval Cost(Rs in lakh) | Date of Commencement | Target Date of comp- letion | Cumulative Progress at the end of last month |  | Achievement of works during the Month |  | Overall Cumulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy. | Fin. | Phy. | Fin. | Phy. | Fin.
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
2 | 8443-108-PW Deposit-III
| a) I/E to DC Bungalow(Type-VI) at Siaha. |  | 8.2 |  |  | 100% |  | 0% |  | 100% |  | Completed | Departmental
| b) I/E to Laboratory Building at Civil Hospital, Lunglei. (SH: First Floor,Second Floor & Third Floor) |  | 24.5 |  |  | 100% |  | 0% |  | 100% |  | Completed | Departmental
| c) SITC of 8 Passenger Lift for (G+3) Laboratory Building at Civil Hospital, Lunglei. |  | 40 | 2025-05-29 | 25.March/2026 | 90% |  | 10% |  | 100% |  | Completed | Contractor
| d) I/E to EE (PWD) Quarter at Hnahthial. |  | 6.19 |  |  | 0% |  | 100% |  | 100% |  | Completed | Departmental
4408 C.o on Food,storage & Warehouse.
| a) I/E to Staff Quarter(2 units) at Vaseikai,Lawngtlai District. |  | 5.4 |  |  | 0% |  | 0% |  | 0% |  | Material awaited | Departmental
| b) I/E to 500MT Go-Down at Vaseikai,Lawngtlai District. |  | 5.37 |  |  | 0% |  | 0% |  | 0% |  | Material awaited | Departmental
| c) I/E to 250MT Go-Down at Tlabung,Lunglei District. |  | 4.22 |  |  | 0% |  | 0% |  | 0% |  | Material awaited | Departmental
3 | SASCI FUND ACCOUNT
| a) I/E to Szairep Community Hall at Sairep. |  | 1.273 |  |  | 60% |  | 5% |  | 65% |  | On going works | Departmental
| b) I/E to DM High School at Theiriat,Lunglei. |  | 2.194 |  |  | 100% |  | 0% |  | 100% |  | Completed | Departmental
| c) I/E to Market Building at Luangmual,Lunglei. |  | 5.034 |  |  | 95% |  | 5% |  | 100% |  | Completed | Departmental
| d) I/E to Circuit House at Hnahthial,Mizoram. |  | 31.59 |  |  | 70% |  | 30% |  | 100% |  | Completed | Departmental
FOR WORKS UNDER STATE PLAN FUND
Sl No | Name of works/Scheme | Estimated Amount | A/A or Not | Cumulative achievement as on March, 2016 |  | Target Date of comp- letion | Fund allocated during the year | Achievement during the Month |  | Cumulative achievement upto the end of the month during the year |  | Cumulative achievement since implementation of the project |  | Remarks
|  |  |  | Phy. | Fin. |  |  | Phy. | Fin. | Phy. | Fin. | Phy. | Fin.
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
2 | 4202 Co-On Education etc.
| b) Boys' Hostel for Govt. Lunglei College at Lunglei | 2.00 lacs | Yes | 20% |  |  | 2 | 20% |  | 40% |  | 40% |  | Completed
| c) Girls' Hostel for Govt. Lunglei College at Lunglei | 2.00 lacs | Yes | 20% |  |  | 2 | 20% |  | 40% |  | 40% |  | Completed
| d) I/E to Govt.Hnahthial College at Hnahthial | 10.56 lacs | Yes | 20% |  |  | 10.56 |  |  |  |  | 20% |  | On going works
| e) I/E to DIET Bldg at Saiha (Sangau Road) | 27.00 lacs | Yes | 20% |  |  | 27 |  |  | 40% |  | 40% |  | Completed
| f) I/E to DIET Bldg at Thingkah (Lawngtlai Dist.) | 27.00 lacs | Yes | 20% |  |  | 27 | 55% |  | 95% |  | 95% |  | Completed
| g) I/E to Indoor stadium at Chanmari, Lunglei | 15.00 lacs | Yes | Nil |  |  | 15 | 20% |  | 20% |  | 20% |  | On going works
| h) I/E to boys & girls Hostel for Govt.Saiha College bldg at Siaha | 2.00 lacs | Yes | 20% |  |  | 2 | 20% |  | 20% |  | 20% |  | On going works
| i) I/E to Infrastructure development of Lawngtlai College at Lawngtlai | 5.00 lacs | Yes | 20% |  |  | 5.00 lacs | 20% |  | 20% |  | 20% |  | On going works
3 | 4055 Co-On Police (P)
| d) I/E to Police Station at Vaseitlang | 8.00 lacs | Yes | Nil |  |  | 8 |  |  | 100% |  | 100% | 8.00 lacs | Completed
4 | 4408 Co-0n Food Storage and Warehousing
| a) I/E to Storage Godown at Kawlchaw | 3.00 lacs | Yes | Nil |  |  | 3 |  |  | 100% |  | 100% | 3.00 lacs | Completed
| b) I/E to Storage Godown at Vaseikai | 3.00 lacs | Yes | Nil |  |  | 3 |  |  | 100% |  | 100% | 3.00 lacs | Completed
| c) I/E Storage Godown at Hnahthial | 3.00 lacs | Yes | Nil |  |  | 3 | 5% |  | 100% |  | 100% | 3.00 lacs | Completed
| d) I/E Storage Godown at Sangau | 3.00 lacs | Yes | Nil |  |  | 3 | 5% |  | 100% |  | 100% | 3.00 lacs | Completed
| e) I/E Storage Godown at Lungsen | 3.00 lacs | Yes | Nil |  |  | 3 |  |  | 100% |  | 100% | 3.00 lacs | Completed
| f) I/E Storage Godown at Tlabung | 3.00 lacs | Yes | Nil |  |  | 3 |  |  | 100% |  | 100% | 3.00 lacs | Completed
5 | 4059 Co-On Public Works(P)
| a) I/E to Treasury Office at Saiha | 13.00 lacs | Yes | Nil |  |  | 13 |  |  | 100% |  | 100% | 13.00 lacs | Completed
6 | 8443-108-PW Deposit-III
| a) I/E to Govt Staff Qtrs (PWD), Type-II 4 units at Lunglei | 8.00 lacs | Yes | Nil |  |  | 8 | 10% |  | 100% |  | 100% | 8.00 lacs | Completed
| b) I/E to PHC at Haulawng | 10.00 lacs | Yes | Nil |  |  | 10 |  |  | 100% |  | 100% | 8.00 lacs | Completed
| c) I/E to PHC at Bunghmun | 10.00 lacs | Yes | Nil |  |  | 10 |  |  | 100% |  | 100% | 10.00 lacs | Completed
| d) I/E to PHC at Zobawk | 12.00 lacs | Yes | Nil |  |  | 12 | 40% |  | 90% |  | 90% |  | On going works
| e) I/E to PHC at Longpuighat | 11.00 lacs | Yes | Nil |  |  | 11 | 10% |  | 30% |  | 30% |  | On going works
7 | 4210 Co-On Medical
Construction of 100 Bedded Civil Hospital at Siaha
| (a) Power Distribution & Bed Lift | 114.83 lacs | Yes | 40% |  |  |  | 40% |  | 40% |  | 40% |  | On going works
(i) Power Distribution
(ii) SITC of 20 Passengers cum Stretcher Auto elevator
| (b) Solar Power | 146.00 lacs | Yes | 30% |  |  |  | 40% |  | 40% |  | 40% |  | On going works
(i) SITC of Solar Heating System (SHS)
(ii) SITC of 1X40 KWp SPV Power Plant
| (c) Fire fighting & VRF AC | 28.41 lacs | Yes | Nil |  |  |  | 10% |  | 10% |  | 10% |  | On going works
(i) SITC of fire detection/fighting system
(ii) SITC of 8 Tonnes (2+2+2+2) with 10 HP pure inverter out door unit with R410A Refrigerator AC VRF system
| (d) Internal Electrification main building | 61.40 lacs | Yes | Nil |  |  | 61.4 | 30% |  | 30% |  | 30% | 30 | On going works
| (e) I/E to Type-IV Quarter 3 units | 12.67 lacs | Yes | Nil |  |  |  | 10% |  | 10% |  | 10% |  | On going works
Executive Engineer, P.W.D.,
Electrical Division, Lunglei.

## MAMIT DIV
NAME OF DIVISION : MAMIT
MONTHLY PROGRESS FOR THE MONTH OF : OCTOBER 2025
[6 empty] | Physical in % |  |  |  | Financial is Rs in lakh
Sl. No | Name of Schemet | Unit | Approved Cost (in lakhs) | Date of Commence- ment | Target date of Completion | Cummulative Progress at the end of last Month |  | Achievement of works during the month |  | Overall Cumulative achievement |  | Remarks | Mode of Tender
| Name of Work/ Project |  |  |  |  | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
NABARD
1 | Strengthening and Improvement of W.Phaileng to Marpara Road (0.00-30.00 Kmp) Package-I |  | 1854.59 | 15.03.2023 | 15.03.2025 | 64.5% | 858.17 | 0% | 0 | 64.5% | 858.17 |  | Restricted Tender | ` | `
| Price escalation | [5 empty] | 9.61 |  |  |  | 9.61
| Total | [5 empty] | 867.78 |  |  |  | 867.78
2 | Strengthening and Improvement of W.Phaileng to Marpara Road (30.00-80.00 Kmp) Package-II |  | 4778.8 | 15.03.2023 | 15.03.2025 | 74.2% | 3527.93 | 0% | 0 | 74.2% | 3527.93 |  | Restricted Tender
| Quality Control | [5 empty] | 32.43 |  | 0 |  | 32.43
| Contingency | [5 empty] | 82.68 |  | 0 |  | 82.68
| Price escalation | [5 empty] | 12.4 |  |  |  | 12.4
| Total | [5 empty] | 3655.44 |  | 0 |  | 3655.44
Sr.Executive Engineer, P.W.D.,
Mamit Division, Mamit

## MMPD
MONTHLY PROGRESS REPORT UNDER MULTI MODAL PROJECT DIVISION FOR THE MONTH OF OCTOBER, 2025
SlNo | Name of Scheme | Unit | Approved Cost (in lakhs) | Date of Commencement | Target date of completion | Cumulative progress at the end of last month |  | Achievement of works during the month |  | Overall Cumulative achievement |  | Remarks | Mode of Tender
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
SASCI
Work under SASCI
NABARD
Work under NABARD
NEC
Work under NEC
PMGSY
Work under PMGSY
1 | Construction & Maintenance of Nalkawn to Rulkual Road (16.00-32.00) Kmp Group B (Sh: Construction of Road using Cold Mix Technology) | Km | 1088.47 | 12.12.2023 | 30.03.2025 | 100% | 791.94 | 0 | 210.09 | 100% | 1002.03 | Work Physically completed on 27.03.2025. Original amount=1034.60 Deviation= 55.87
SEDP
Work under SEDP
CSS
Work under CSS
MoRTH
Work under MoRTH
1 | Construction of 2 Nos Reinforced Earth wall for restoration of road formation collapse at km 11.000 & km 11.050 and re-construction of Box culvert at km 11.000 on NH-502A in the state of Mizoram | mtr | 594.66 | 10.02.2025 | 30.11.2025 | 272 | 554.25 | 0 | 0 | 272 | 554.25 | On-going | EPC Mode | 0
2 | STMC on NH 502A (KMMTTP) between Km 0.00 to Km 34.92 in the State of Mizoram | cum | 133.29 | 13.12.2024 | 12.12.2025 | 78400 | 81.09 | 27212.71 | 0 | 105612.71 | 81.09 | On-going | Item Rate. .
3 | STMC on NH 502A (KMMTTP) between Km 34.92 to Km 60.700 in the State of Mizoram | sqm | 99.38 | 13.12.2024 | 12.12.2025 | 155257.5 | 32.94 | 192.49 | 0 | 155449.99 | 32.94 | On-going | Item Rate
4 | STMC on NH 502A (KMMTTP) between Km 60.700 to Km 87.51 in the State of Mizoram | sqm | 106.31 | 13.12.2024 | 12.12.2025 | 161460.6 | 34.15 | 200.18 | 0 | 161660.78 | 34.15 | On-going | Item Rate
5 | Construction of new 2-lane Highway from Km 0.00-km 38.00 on NH 54 near Lawngtlai in Mizoram to support Kaladan Multi Modal Transit Transport Project in Phase A of SARDP-NE (pacakge-I) | Km | 43465 | 12.10.2010 | 12.10.2014 | 100% | 42680 |  |  | 100% | 42680 | Work physically Completed on 22.06.2023 | Item Rate
6 | Construction of new 2-lane Highway from km 38.00 to Km 70/00 in Mizoram to support Kaladan Multi Modal Transit Transport Project in Phase A of SARDP-NE (pacakge-II) | Km | 32224 | 12.10.2010 | 30.09.2014 | 100% | 30977 |  |  | 100% | 30977 | Work physically Completed on 30.04.2022 | Item Rate
7 | Construction of new 2-lane Highway from Km 70/00 to Km 99/00 in Mizoram to support Kaladan Multi Modal Transit Transport Project in Phase A of SARDP-NE (pacakge-III) | Km | 37459 | 12.10.2010 | 30.09.2014 | 100% | 36468 |  |  | 100% | 36468 | Work physically Completed on 23.06.2023 | Item Rate
Sr.Executive Engineer, PWD
Multi Modal Project Division
Lawngtlai: Mizoram

## NH - I
Montly Progress Report under National Highway Division-I, PWD., October, 2025
Sl. No | Name of Scheme | Unit | Approved Cost (in lakhs) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall Cummulative achievement |  | Remarks | Mode of Tender
| Name of Work/Project |  |  |  |  | Phy. | Fin. | Phy. | Fin. | Phy. | Fin.
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
SASCI
1 | Construction of Saiphal - Hortoki Road (13.800 km) | Phy in % Fin in lakh | 600 | 15.12.2023 | 15.12.2025 | 59.5% | 314.15 | 0% | 0 | 59.5% | 314.15 | On Going | Restricted tender
MoRTH
2 | Short Term Maintenance Contract on NH-44A/108 Rockfall Bypass Between km 0.000 to km 5.135 in the state of Mizoram. (Job No. RW/GHT/NH-44A/MZ/STMC/2024-25/2) | Phy in % Fin in lakh | 20.26 | 28.11.2024 | 27.11.2025 | 95.5% | 16.39 | 4.5% | 0 | 100% | 16.39 | On Going | Open Tender
3 | Short Term Maintenance Contract on NH-44A/108 Between km 16.670 to km 114.618 in the state of Mizoram. (Job No. RW/GHT/NH-44A/MZ/STMC/2024-25/1) | Phy in % Fin in lakh | 385.6 | 28.11.2024 | 27.11.2025 | 95.5% | 208.66 | 4.5% | 0 | 100% | 208.66 | On Going | Open Tender
4 | Performance Based Maintenance Contract (PBMC) under National Highway Division-I during 2023-24 on NH-6/54 between km 159/00 to km 178/00 (Length = 19.00 km) in the State of Mizoram. (Job No. 6/54-MZ-2023-24/124) | Phy in % Fin in lakh | 1891.98 | 29.08.2024 | 28.08.2029 | 77% | 1513.96 | 0.5% | 0 | 77.5% | 1513.96 | On Going | Open Tender
5 | Construction of Steel Arch (Semi Through) Bridge with Concrete Deck 90m Span Over River Tlawng at km 5.200 on NH-44A in the State of Mizoram on EPC Mode | Phy in % Fin in lakh | 4244 | 30.01.2021 | 26.3.2024 | 97% | 3712.68 | 3% | 0 | 100% | 3712.68 | On Going | Open Tender
PM-DevINE
6 | Construction of Bamboo Link Road from Lengpui to Saiphal Baboo Plantation (41 km) under PM-DevINE ( Note: Change of Scope approved and Supplemantary Agreement signed. Progress report re-framed as per Change of Scope.) | Phy in % Fin in lakh | 6642 | 21.07.2024 | 19.01.2025 | 76.6% | 3663.35 | 1% | 76.95 | 77.6% | 3740.3 | On Going | Open Tender
Sr. Executive Engneer, PWD., National Highway Division-I Aizawl : Mizoram

## NH - II
MONTHLY PROGRESS REPORT OF NH-150 FOR THE MONTH OF OCTOBER 2025
Sl No | Name of Scheme | Approved cost (in lakh) | Date of Comenciment | Target Date of Completion | Cummulative Progress at the end of last Month |  | Achievement of works during the Month |  | Overall cummulative achievement |  | Remarks
| Name of Project |  |  |  | Phy (in %) | Fin (in lakh) | Phy (in %) | Fin (in lakh) | Phy (in %) | Fin (in lakh)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
MoRTH
1 | Consultancy Services for Project Management including Preparation of Feasibility Study/Detailed Project report for two laning with Paved Shoulders of stretches from Km 0/00 to Km 42/80 and from Km 60/00 to Km 140/00 on NH-150 NH(O) Package No. DPR/MZ/NER/2015/13 | 166.03 | 24.06.2017 | 20.05.2018 | 80% | 39.18 | 0% | 0 | 80% | 39.18 | 3rd RA bill in Process
2 | Short Term Maintenance Contractfor NH-6 (150 ti 180/000 Kmp) i.e : 30 length for the year 2024-25 under National Highway Division- II, Aizawl in the state of Mizoram. (Job No.RW/GHT/NH-6/MZ/STMC/MZ/2024-25/3) | 116.03 | 20.12.2024 | 19.12.2025 | 22.1% | 27 | 45% | 50.55 | 67.1% | 77.55 | Work in progress
3 | One Time Improvement of Old alignment fron Km 42.80 to 60.30 of NH-2 (Old NH-150) by passed by the new alignment in the State of Mizoram | 767.5 | 04.10.2024 | 04.10.2025 | 55.39% | 382.51 | 0% | 0 | 55.39% | 382.51 | Work in progress
Sr.Executive Engineer,PWD
National Highway Division - II
Aizawl : Mizoram

## NH-III
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER, 2025.
Name of Division : National Highway Division-III, Thingdawl, Mizoram
Source of funding : MORTH/NH | [11 empty] | Rs in Lakh
Sl No | Name of Work/Project | Unit | Approved Cost (Rs in Lakh) | Date of Commencement | Target Date of Completion | Cumulative Progress at the end of last month |  | Achievement of works during the month |  | Overall Cumulative achievement |  | Remarks | Mode of Contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Strengthening/Construction/Widening to 2-lane from km 89/00 to km 105/00 of NH-154 (New NH-6) under NH Division III in the state of Mizoram for the year 2022 – 23 (Length = 16 Km ) | Km | 8681 Lakhs | 04.09.2023 | 04.03.2025 | 94.55% | 4646.43 | 1.42% | 423.03 | 95.97% | 5069.46 | Work in Progress | EPC | 0.13 | 0.8 | 5069.46
[5 empty] | Contingency = |  | 0 |  | 244.32 |  | 244.32
2 | Strengthening of Km 10.00 to Km 33.00 (Length 23.00Km) on NH-306A including Strengthening & Construction of Retaining Walls and culverts and Strengthening of 3 Nos. of Bailey Bridges in the State of Mizoram | Km | 6523 Lakhs | 07.02.2022 | 07.08.2023 | 100% | 4178.05 | 0% | 0 | 100% | 4178.05 | Completed DLP is going on | EPC
2 | Short Term Maintenance Conctract on Km 0.00 - Km10.00 and Km 33.00 - Km 45.00( 22.00km) on NH-306A in the state of Mizoram | Km | 343.44 Lakh | 17.03.2024 | 16.03.2024 | 95.98% | 300.66 | 0% | 0 | 95.98% | 300.66 |  | STMC
2 | Strengthening of NH-154( New NH-06) between km 105.00 and Km 119.00 including bridge repair in the state of Mizoram | Km | 2753.00 lakh | 30.06.2025 | 31.05.2026 | 0% | 0 | 0% | 0 | 0% | 0 |  | EPC
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER, 2025.
Name of Division : National Highway Division-III, Thingdawl, Mizoram
Source of funding : NABARD | [10 empty] | Rs in Lakh
Sl No | Name of Work/Project | Unit | Approved Cost (Rs in Lakh) | Date of Commencement | Target Date of Completion | Cumulative Progress at the end of last month |  | Achievement of works during the month . |  | Overall Cumulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Upgradation of Road from Meidum to Hortoki Phase-I (Km 0.00 to Km 9.10) | Km | 4445 Lakhs | 26.05.2020 | 26.11.2021 1st EOT=211 days (21.11.2021-20.06.2022) 2nd EOT=375 days (21.06.2022-30.06.2023) 3rd EOT=243 days (30.06.2023-28.02.2024) 4th EoT=90 days (20.2,2024-28.5.2024) | 100% | 4356.17 | 0% | 0 | 100% | 4356.17 | completed | Item Rate
2 | Construction of road from Khamrang to Selesih Phase-I (Length =11.00 Kms) Group-A (0/00 to 3/600 Km) | Km | 6583.18 | 08.02.2021 | 08.08.2022 1st EOT=184 days (upto 08.02.2023, 2nd EOT= 150 days (upto 08.07.2023) | 83.33% | 388.92 | 0% | 0 | 83.33% | 388.92 |  | Item Rate
3 | Construction of road from Khamrang to Selesih Phase-I (Length =11.00 Kms) Group-B (3/60 to7/200 Km) | Km |  | 08.02.2021 | 08.08.2022 1st EOT=184 days (upto 08.02.2023; 2nd EOT=150 days (wef 09.02.2023- 08.07.2023) | 88.89% | 704.4 | 0% | 0 | 88.89% | 704.4 |  | Item Rate
4 | Construction of road from Khamrang to Selesih Phase-I (Length =11.00 Kms) Group-C (7/200 to 11/00 Km) | Km |  | 08.02.2021 | 08.08.2022 1st EOT=184 days (upto 08.02.2023; 2nd EOT=150 days (wef 09.02.2023-08.07.2023) | 47.78% | 336.16 | 0% | 18.32 | 47.78% | 354.48 |  | Item Rate
5 | Construction of road from Khamrang to Selesih Phase-I (Sh: Construction of Rigid Pavement from 7/00 to 11/00 Kmp = 4.00 kms) | Km |  | 16.08.2022 | EoT = 336 days upto 18.02.2026 | 16.8% | 432.6 | 2% | 0 | 18.8% | 432.6 |  | Item Rate
6 | [6 empty] | 46.89 |  |  |  | 46.89 | Contingency
7 | Construction of MDR from Khamrang (Dilsei) to Selesih (Sh: Constn of approach road to Mualkhang village) | Km | 14529.29 Lakhs | 08.02.2021 | 08.08.2022 | 100% | 122.25 | 0% | 0 | 100% | 122.25 |  | Item Rate
8 | Construction of road from Khamrang to Selesih Phase-II Group-1 (11/00 to 22/00 Km) | Km |  | 08.11.2021 | 08.05.2023 1st EOT=210 days (wef 09.05.2023- 04.12.2023 | 22.15% | 664.75 | 0% | 0 | 22.15% | 664.75 |  | Item Rate
9 | Construction of road from Khamrang to Selesih Phase-II Group-2 (22/00 to 25/00 Km) | Km |  | 22.11.2021 | 22.11.2022 1st EOT=90 days (upto 20.02.2023); 2nd EOT=90 days (wef 21.02.2023-21.05.2023); 3rd EOT=90 days (22.05.2023-19.08.2023) | 62.88% | 386.28 | 0% | 0 | 62.88% | 386.28 |  | Item Rate
10 | Construction of road from Khamrang to Selesih Phase-II Group-3 (25/00 to 28/00 Km) | Km |  | 11.11.2021 | 11.11.2022 1st EOT=104 days (upto 24.02.2023); 2nd EOT=90 days (wef 10.02.2023-11.05.2023) 3rd EOT=90days (Wef 12.05.23-09.08.2023) | 42.96% | 262.85 | 0% | 0 | 42.96% | 262.85 |  | Item Rate
11 | Construction of road from Khamrang to Selesih Phase-II (Sh: - Construction of Rigid Pavement from 11/00 to 19/00 Kmp = 8.00 kms) Group A | Km |  | 26.08.2023 | 26.08.2025 | 0% | 0 | 0% | 0 | 0% | 0 |  | Item Rate
12 | Construction of road from Khamrang to Selesih Phase-II (Sh: - Construction of Rigid Pavement from 19/00 to 28/00 Kmp = 9.00 kms) Group B | Km |  | 26.08.2023 | 26.08.2025 | 0% | 0 | 0% | 0 | 0% | 0 |  | Item Rate
13 | [6 empty] | 1.67 |  | 0.5 |  | 2.17 | Contingency
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER, 2025.
Name of Division : National Highway Division-III, Thingdawl, Mizoram
Source of funding : SASCI | [10 empty] | Rs in Lakh
Sl No | Name of Work/Project | Unit | Approved Cost (Rs in Lakh) | Date of Commencement | Target Date of Completion | Cumulative Progress at the end of last month |  | Achievement of works during the month . |  | Overall Cumulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Restoration of damaged due to cyclone remal under Aizawl Road North Division (Part II) & National Highway Division III | Km | 262 | 26.05.2020 | 20.01.2026 | 36.93% | 96.76 | 0% | 0 | 36.93% | 96.76 | In progress | Item Rate

## PD -I
MONTHLY PROGRESS REPORT UNDER EXECUTIVE ENGINEER, PROJECT DIVISION- I, PWD FOR OCTOBER 2025
Sl. No. | Name of Scheme | Unit | Approved Cost (in lakhs) | Date of Commencement | Target date of completion | Cummulative progress at the end of last month |  | Achievement of work during the month |  | Overall cummulative achievement |  | Remarks | Mode of Tender
| Name of Work/Project |  |  |  |  | Phy (%) | Fin (₹) | Phy (%) | Fin (₹) | Phy (%) | Fin (₹)
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) | (10) | (11) | (12) | (13) | (14)
A. NEC
1 | C/o of Patient Lodging at Mawdiangdiang near NEIGRIMS, Shillong | 1 | 419.67 | 9.9.21 | 31.7.24 | 90% | 314.75 | 5% | 0 | 95% | 314.75 | EOT upto 9.9.25 | Item rate
2 | Co/ Veterinary Information and Resource Centre at Aizawl | 1 | 339.25 | 25.9.23 | 25.9.25 | 83% | 225.46 | 5% | 0 | 88% | 225.46 |  | Item rate
3 | C/o Aizawl Institute of Arts & Music for the NER, Tuivamit Tlang, Aizawl | 1 | 590.23 | 4.9.23 | 4.9.25 | 86.5% | 517.6842 | 1% | 0 | 87.5% | 517.6842 |  | Item rate
4 | Establishment of Central Medical Warehouse at Aizawl, Mizoram | 1 | 1101.11 | 14.8.23 | 14.8.25 | 40.5% | 177.1513 | 0.5% | 0 | 41% | 177.1513 |  | Item rate
5 | Infrastructure Development of Biotechnology Cell in Mizoram (C/O Building at MINECO | 1 | 188.66 | 10.7.23 | 10.1.25 | 44.8% | 69.55 | 0% | 0 | 44.8% | 69.55 | EOT upto 22.10.25 | Item rate
B. SASCI
6 | C/o Central Medical Warehouse at ZMC, Approach Road SH: Approach Road | 1 | 150 | 16.12.23 | 16.12.24 | 66% | 47.428 | 0% | 0 | 66% | 47.428 |  | Item rate
7 | C/o FCS&CA 1500 MT Capacity Godown at Sairang | 1 | 921.07 | 7.4.23 | 7.4.26 | 73% | 207.6424 | 2% | 0 | 75% | 207.6424 |  | Item rate
8 | Constn. of Govt. Staff Qtrs. (Block-C) at DIET Complex, Chaltlang. | 1 | 544 | 29.4.23 | 29.10.25 | 92.4% | 450.0945 | 1.8% | 0 | 94.2% | 450.0945 |  | Item rate
9 | Re-construction of Central Jail, Aizawl | 3 | 1329 | 16.5.25 | 16.5.26 |  | 0% |  |  |  | 0 |  | Item rate
| a. Vertical extension of Convict Women in Women Jail |  |  |  |  | 7.4% | 0 | 4.5% | 0 | 11.9% | 0
| b. Vertical extension of male ward |  |  |  |  | 11.5% | 0 | 8.8% | 0 | 20.3% | 0
| c. Superintendent Quarters |  |  |  |  | 13.2% | 0 | 0.8% | 0 | 14% | 0
| d.Male Kitchen & Dining Hall |  |  |  |  | 0.7% | 0 | 1% |  | 1.7% | 0
| e. Toilet at UTP Ward Duty Post (Women Prison) |  |  |  |  | 0% |  | 1.1% |  | 1.1%
10 | Construction of Working Women Hostel, Khatla | 1 | 2972 | 24.4.25 | 24.4.26 | 9.9% | 0 | 4.3% | 197.1629 | 14.2% | 197.1629 |  | Item rate
11 | Construction of Integrated Office Complex at MINECO, Aizawl | 1 | 60000 |  |  | 6.5% | 73.4647 | 0.5% | 1.5315 | 7% | 74.9962 |  | Item rate
12 | Construction of Working Women Hostel, ITI Veng, Aizawl | 1 | 1448.36 |  |  | 6% | 0 | 4% | 152.0252 | 10% | 152.0252 |  | Item rate
13 | Construction of New Campus for Govt. Aizawl West College Building (SH: Administrative Building) | 1 | 572.97 | 9.5.25 | 9.5.26 | 2% | 0 | 0% | 0 | 2% | 0 |  | Item rate
14 | Construction of New Campus for Govt. Aizawl West College Building (SH: Academic Building) | 1 | 201.36 | 9.5.25 | 9.5.26 | 4.5% | 201.2913 | 1% | 0 | 5.5% | 201.2913
15 | Construction of E-in-C, PHED Office at MINECO, Aizawl | 1 | 796 | 26.6.25 | 26.6.26 | 2.2% | 0 | 1% | 0 | 3.2% | 0 |  | Item rate
16 | Vertical Extension of Mizoram Upa pawl Hqr. Building for Community Hall & Office at Khatla, Aizawl, Mizoram | 1 | 200 | 26.6.25 | 26.6.26 | 17.7% | 0 | 1.3% | 10.9566 | 19% | 10.9566 |  | Item rate
17 | Construction of Building for Additional Classroom at J. Thankima College, Aizawl | 1 | 984 | 4.7.25 | 4.7.26 | 1% |  | 0.3% | 0 | 1.3% | 0 |  | Item rate
18 | Construction of Government Residential Quarter Type-VI (4 units) at new Secretariat Complex, Khatla | 1 | 849.66 |  |  | 5% | 41.5082 | 12% | 2.418 | 17% | 43.9262 |  | Item rate
19 | Construction of Government Residential Quarter Type-V (4 units) at new Secretariat Complex, Khatla | 1 | 692 |  |  | 5% | 38.2957 | 10% | 0 | 15% | 38.2957 |  | Item rate
20 | Construction of Examination Hall at MPSC Campus | 1 | 1092 | 26.6.25 | 26.6.26 | 1% |  | 2% |  | 3% | 0 | Column layout done | Item rate
21 | Construction of Market Building at Vaivakawn, Aizawl | 1 | 2535 | 5.6.25 | 5.6.26 | 0% |  | 0% |  | 0% | 0 | Dismantling of existing building in progress | Item rate
22 | Construction of State Emergency Operation Centre (SEOC) at MINECO | 1 | 3825 | 13.5.25 | 13.5.26 | 1.9% |  | 1.7% |  | 3.6% | 0 |  | Item rate
23 | Construction of MLA Hostel at Tuikual, Aizawl | 1 | 629.17 | 14.8.25 | 14.8.26 | 0% |  | 0.9% |  | 0.9% | 0 | Dismantling of existing column in progress | Item rate
24 | Vertical Extension of Chief Controller of Accounts Office Main & Annex Building | 1 |  | 26.8.25 | 26.8.26 | 0% |  | 0.9% |  | 0.9% | 0 | Dismantling of existing column in progress | Item rate
25 | Construction of Durbar Hall & Personal Branch of Raj Bhavan | 1 | 546.408 |  |  | 0% | 0 | 0% | 67.8784 | 0% | 67.8784 |  | Item rate
C. SEDP
26 | Construction of High Court Parking Building at MINECO | 1 | 1960 | 2.7.20 | 29.8.24 | 100% | 1859.8675 | 0% | 1.653 | 100% | 1861.5205 | EOT upto 17.5.2025 | Item rate
D. NABARD
27 | C/O 24 Warehouses with associated Infrastructure in 23 locations in Mizoram under NABARD (Group-II Zuangtui/ Sairang) | 1 | 440.97 | 17.7.23 | 31.3.25 | 95% | 238.8834 | 3% | 0 | 98% | 238.8834 |  | Item rate
E. CSS
28 | Construction of file rack inside record Room of District Court Building at MINECO | 1 | 45.1 | 8.8.25 | 8.9.25 | 63.3% | 0 | 36.7% | 45.1 | 100% | 45.1 | Works completed | Item rate
Executive Engineer, PWD
Project Division-I
Aizawl, Mizoram

## PD-II
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER, 2025
Name of Division: Project Division-II, P.W.D
Sl.No. | Name of Schemet | Unit | Approved cost (Rs.in lakh) | Date of Commence-ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Mode of Tender | Remarks
| Name of Work/Project |  |  |  |  | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | . | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 14 | 13
NABARD
1 | Construction of 24 Warehouses with associated Infrastructure in 23 lacations in Mizoram Group-I i) Construction of Warehouse and other amenities at Bairabi (1000 MT) | % | 316.55 | 17.07.2023 | (O)17.07.2025 (R)31.10.2025 | 98.5% | 179.93 | 0.5% | 0 | 99% | 179.93 | Item Rate | Work in progress
| ii) Construction of Warehouse and other amenities at Marpara (500 MT) | % | 235.73 | 17.07.2023 | (O)17.07.2025 (R)07.11.2025 | 90% | 160.61 | 2% | 0 | 92% | 160.61 | Item Rate | Work in progress
| iii) Construction of Warehouse and other amenities at Sialsuk SC (200 MT) | % | 171.09 | 17.07.2023 | (O)17.07.2025 (R)11.01.2026 | 93% | 58.93 | 2% | 0.3 | 95% | 59.23 | Item Rate | Work in progress
| iv) Construction of Warehouse and other amenities at Zawlnuam (200 MT) | % | 176 | 17.07.2023 | (O)17.07.2025 (R)30.11.2025 | 95% | 141.35 | 3% | 0 | 98% | 141.35 | Item Rate | Work in progress
| v) Construction of Warehouse and other amenities at Kanhmun (200 MT) | % | 175.8 | 17.07.2023 | (0)17.07.2025 (R)30.11.2025 | 93% | 140.06 | 2% | 0 | 95% | 140.06 | Item Rate | Work in progress
2 | Construction of 24 Warehouses with associated Infrastructure in 23 lacations in Mizoram Group-IX i) Construction of Warehouse and other amenities at Phuldungsei (200 MT) | % | 175.81 | 17.07.2023 | (O)17.07.2025 (R)10.11.2025 | 90% | 96.29 | 3% | 0 | 93% | 96.29 | Item Rate | Work in progress
NEC
1 | Construction of Market Building at West Phaileng, Mamit District. | % | 278.25 | 22.08.2023 | 22.08.2025 | 80% | 139.12 | 5% | 69.56 | 85% | 208.68 | Item Rate | Work in Progress (EOT under process)
2 | Construction of Fish Farmers Training Centre at Lengpui | % | 924.32 | 20.06.2025 | 20.06.2027 | 5% | 243 | 5% | 0 | 10% | 243 | Item Rate | Work in Progress. Secured Advance Granted
NESIDS
1 | Construction of 100 Bedded District Hospital at Kolasib. | % | 2200 | 23.09.2022 | ( O) 23.09.2024 (R) 13.10.2025 | 86% | 1583.92 | 1% | 0 | 87% | 1583.92 | EPC | Work in Progress. 2nd EOT under process
CSS
1 | Construction of Fast Track Court Building at Kolasib. | % | 1799.85 | 20.09.2022 | (O) 20.09.2024 (R1) 18.02.2025 (R2) 31.05.2025 (R3) 31.07.2025 (R4)12.12.2025 | 95% | 992.99 | 2% | 0 | 97% | 992.99 | Item Rate | Work in Progress
ICMR
1 | Construction of Model Rural Health Research Unit at Lungtian Ram, Aibawk. | % | 207.5 | 21.09.2023 | 21.03.2025 | 100% | 187.5 | 0% | 0 | 100% | 187.5 | Item Rate | Work Physically Completed. There is a liability of Rs. 20 lakh for payment of the Contractor
SASCI
Work under SASCI 2024 - 2025 Part - I (Untied)
1 | Re-Construction of District Prison at Mamit | % | 453.37 | 23.04.2025 | 23.04.2026 | 8% | 0 | 4% | 44.16 | 12% | 44.16 | Item Rate | Work in Progress
2 | Re-Construction of District Prison at Kolasib | % | 751.03 | 27.05.2025 | 27.05.2026 | 28% | 121.76 | 2% | 1.07 | 30% | 122.83 | Item Rate | Work in Progress
Work under SASCI 2024 - 2025 Part - V
1 | Contruction of Civil SDO Qrts Type - IV at Kawnpui | % | 78.08 | 15.05.2025 | 15.5.2026 | 10% | 0 | 5% | 0 | 15% | 0 | Item Rate | Work in Progress
2 | Contruction of Civil SDO Qrts Type - IV at Bairabi | % | 82.32 | 15.05.2025 | 15.5.2026 | 40% | 0 | 10% | 0 | 50% | 0 | Item Rate | Work in Progress
3 | Contruction of Directorate of Economics & Statistics Office at MINECO, Aizawl | % | 207 | 30.04.2025 | 30.04.2026 | 10% | 0 | 10% | 50 | 20% | 50 | Item Rate | Work in Progress
4 | Upgradation of District Research Office at Kolasib | % | 24.03 | 20.08.2025 | 20.08.2026 | 50% | 0 | 30% | 0 | 80% | 0 | Item Rate | Work in Progress
5 | Upgradation of District Research Office at Mamit | % | 71.37 | 20.08.2025 | 20.08.2026 | 2% | 0 | 1% | 0 | 3% | 0 | Item Rate | Work in Progress
Work under SASCI 2024 - 2025 Part - VII (A)
1 | Contruction of Revenue Staff Quarters (Type - II & III) at Kolasib | % | 192.18 | 11.08.2025 | 11.08.2026 | 3% | 0 | 2% | 0 | 5% | 0 | Item Rate | Work in Progress
2 | Construction of DC Revenue (SO) Office at Mamit | % | 450 | 11.08.2025 | 11.08.2026 | 0% | 0 | 0% | 0 | 0% | 0 | Item Rate | Work yet to be started
3 | Re- Construction of DC Office Complex at Mamit | % | 100 | 21.07.2025 | 21.07.2026 | 0% | 0 | 0% | 0 | 0% | 0 | Item Rate | Work yet to be started
Work under SASCI 2024 - 2025 Part -X
1 | Contruction of Working Women Hostel at ZMC / H Falkawn, Mizoram | % | 2634.06 | 14.05.2025 | 14.05.2026 | 10% | 0 | 2% | 0 | 12% | 213.55 | Item Rate | Work in Progress Secured Advance Granted
2 | Contruction of Working Women Hostel at Thenzawl | % | 1100 | 15.05.2025 | 15.05.2026 | 4% | 0 | 6% | 0 | 10% | 104.91 | Item Rate | Work in Progress Secured Advance Granted
Deposit Work
1 | Construction of Settlement Officer Quarters (Type-IV) at Kolasib | % | 66.87 | 1.10.2025 | 1.06.2026 | 0% | 0 | 0% | 0 | 0% | 0 | Item Rate | Work to be started, Dismantling of Existing building completed
Sr. Executive Engineer, PWD.,
Project Division-II, Aizawl

## PD- III
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Gov't Serchhip College ( Sh: Administrative Block) | % | 650 | 27.2.2023 | 27.2.2025 | 93% | 245.67 | 3% | 0 | 96% | 245.67 | Work in Progress | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Const. of Football ground and volleyball court at Vapar, Selam, tualcheng, Hnahla. Hmunhmeltha | % | 203 | 13.10.2023 | 13.10.2024 | 100% | 99.3 | 0% | 0 | 100% | 99.3 | 100% of 1st priority work completed. | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Const. of Khawbung futsal ground, gallery, Roofing, Lighting & Laying of Artificial Turf | % | 255.5 | 14.10.2023 | 7.2.2025 | 100% | 111.35 | 0% | 3.58 | 100% | 114.93 | 100% of 1st priority work completed. | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Const. of Community Hall at Dulte & Chhawrtui | % | 271 | 13.10.2023 | 13.10.2024 | 95% | 112.33 | 2% | 0 | 97% | 112.33 | Work in progress | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Development of Community Centre at Zotlang, Champhai (Sh: Cons of Market Building cum community Hall & Futsal Ground) | % | 215 | 14.10.2023 | 7.2.2025 | 99.8% | 86.49 | 0% | 3.13 | 99.8% | 89.62 | 100% of 1st priority work completed. | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Additional works for const. of General Nursing Midwifery (GNM) hostel and Nursing Hostel at champhai | % | 438 | 13.10.2023 | 7.2.2025 | 100% | 264.07 | 0% | 0 | 100% | 264.07 | Work in progress | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Const of Public Playground at Keitum, Lungchhuan | % | 250 | 13.10.2023 | 13.10.2024 | 100% | 96.96 | 0% | 0.42 | 100% | 97.38 | 100% of 1st priority work completed. | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Const. of Gov't Building at Serchhip District (Sh: PWD staff qtrs, Extension of Gov't Serchhip College and Kitchen cum Dining at PTS, Thenzawl, Mizoram) | % | 362 | 13.10.2023 | 13.10.2024 | 99% | 240.63 | 1% | 63.25 | 100% | 303.88 | Work completed | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Const of Community Resource Center at Baktawng and Chhuanthar | % | 350 | 13.10.2023 | 13.10.2024 | 100% | 139.9 | 0% | 0 | 100% | 139.9 | 100% of 1st priority work completed. | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Const of Community Hall at Khawzawl Vengthar, Arro Village, Khawzawl Dinthar and Khawhai South | % | 209 | 13.10.2023 | 13.10.2024 | 100% | 79.25 | 0% | 0 | 100% | 79.25 | 100% of 1st priority work completed. | PWD Form - 8
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Gov't Quarters (General pool) under SASCI 2024 - 2025 at Serchhip (1299.68 lakhs) | % | 344.74 | 24.4.2025 | 24.4.2026 | 23% | - | 7% | 42.11 | 30% | 42.11 | Work in progress | -
a) Type - IV & III Quarters (Design - A) at P & E Veng (Treasury Department Site)
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Gov't Quarters (General pool) under SASCI 2024 - 2025 at Serchhip (1299.68 lakhs) | % | 296.54 | 24.4.2025 | 24.4.2026 | 19% | - | 9% | 29.86 | 28% | 29.86 | Work in progress | -
b) Type - IV & III Quarters (Design - B) at P & E Veng ( Treasury Department Site)
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Gov't Quarters (General pool) under SASCI 2024 - 2025 at Serchhip (1299.68 lakhs) | % | 351.94 | 24.4.2025 | 24.4.2026 | 24% | - | 4% | 50.29 | 28% | 50.29 | Work in progress | -
c) Type - IV & III Quarters (Design - A) at P & E Veng ( Soil & Water Conservation Department Site)
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Gov't Quarters (General pool) under SASCI 2024 - 2025 at Serchhip (1299.68 lakhs) | % | 306.46 | 24.4.2025 | 24.4203 | 25% | - | 3% | 42.68 | 28% | 42.68 | Work in progress | -
d) Type - IV Quarters ( 3 Units) at Hospital Complex, Serchhip, Mizoram
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Circuit House under DC Office (SH: Construction of Circuit House at Serchhip) | % | 652 | 16.4.2025 | 16.4.2026 | 19% | - | 7% | - | 26% | - | Work in progress | -
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Circuit House under DC Office (SH: Construction of Circuit House at Khawzawl) | % | 1000 | 16.7.2025 | 16.7.2026 | 2% | - | 2% | - | 4% | - | Work in progress | -
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Re-construction of District Jail, Serchhip | % | 372.4 | 8.5.2025 | 8.5.2026 | [6 empty] | Work in progress | -
| 1. Repair & Extension of Administrative Building |  |  |  |  | - | - | - | - | - | -
| 2. Multipurpose hall & Barrack |  |  |  |  | 20% | - | 5% | - | 25% | -
| 3. Segregation Cell & Vocation Hall |  |  |  |  | 20% | - | 4% | - | 24% | -
| 4. Guard Duty Post (1 no) |  |  |  |  | - | - | - | - | - | -
| 5. Extension of MI Room |  |  |  |  | - | - | - | - | - | -
| 6. Staff Quarters Type-IV |  |  |  |  | - | - | - | - | - | -
| 7. Repair & Renovation of Male ward-2, 1st floor and Chapel |  |  |  |  | - | - | - | - | - | -
| Overall |  |  |  |  | 10% | - | 4% | - | 14% | -
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Re-construction of District Jail, Champhai | % | 826.88 | 16.4.2025 | 16.4.2026 | [6 empty] | Work in progress | -
| 1. Male Ward |  |  |  |  | - | - | - | - | - | -
| 2. Female Ward |  |  |  |  | 20% | 12.92 | 25% | 0 | 45% | 12.92
| 3. Main Wall, Separation wall & Duty post |  |  |  |  | 5% | - | 5% | - | 10% | -
| 4. Type-II Quarters Block-I |  |  |  |  | 20% | 12.6 | 24% | 0 | 44% | 12.6
| 5. Type-II Quarters Block-II) |  |  |  |  | - | - | - | - | - | -
| Overall |  |  |  |  | 10% | 25.52 | 7% | 0 | 17% | 25.52
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Re-construction of District Jail, Saitual (Sh: Separation Wall (80m)) | % | 45.43 | 29.4.2025 | 29.4.2026 | 7% | - | 13% | - | 20% | - | Work in progress | -
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Working Women Hostels(Champhai), Mizoram. | % | 1366 | - | - | - | - | - | - | - | - | Work not yet started due to site problem. | -
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Circuit House at under DC Office (SH: Construction of Circuit House at Saitual) | % | 640 | 16.4.2025 | 16.4.2026 | 14% | - | 6% | 66.19 | 20% | 66.19 | Work in progress | -
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of DC's Bungalow at Saitual DC Complex, Saitual N | % | 224 | 4.7.2025 | 4.7.2026 | 6% | - | 9% | - | 15% | - | Work in progress | Restricted Tender
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Revenue Staff Quarters at Serchhip | % | 333.81 | 16.7.2025 | 16.7.2026 | 2% | - | 3% | - | 5% | - | Work in progress | Restricted Tender
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Revenue Staff Quarters at Saitual | % | 198.12 | 23.7.2025 | 23.7.2026 | 4% | - | 2% | 0 | 6% | - | Work in progress | Restricted Tender
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Revenue Staff Quarters at Khawzawl | % | 211.19 | 23.7.2025 | 23.7.2026 | 2% | - | 1% | - | 3% | - | Work in progress | -
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of DC Revenue (SO) Office at Champhai, Mizoram | % | 468 | 24.7.2025 | 24.7.2026 | 6% | - | 9% | - | 15% | - | Work in progress | Restricted Tender
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of SDO ( C ) Office and Quarter at N. Vanlaiphai | % | 189.29 | 4.7.2025 | 4.7.2026 | 13% | - | 17% | - | 30% | - | Work in progress | Restricted Tender
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of District Drugs Control and Awareness Centre at Serchhip excluding Bypass Road | % | 200 | 13.8.2025 | 13.8.2026 | 2% | - | 4% | - | 6% | - | Work in progress | Restricted Tender
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Upgradation of District Research Office at Champhai | % | 45 | 19.8.2025 | 19.8.2026 | 5% | - | 7% | - | 12% | - | Work in progress | Restricted Tender
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Upgradation of District Research Office at Khawzawl | % | 24.16 | 13.7.2025 | 13.7.2026 | 1% | - | 2% | - | 3% | - | Work in progress | Restricted Tender
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Upgradation of District Research Office at Serchhip | % | 21.7 | 19.8.2025 | 19.8.2026 | 55% | - | 45% | - | 100% | - | Work completed | Restricted Tender
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Upgradation of District Research Office at Saitual | % | 36.9 | 21.8.2025 | 21.8.2026 | 4% | - | 26% | - | 30% | - | Work in progress | Restricted Tender
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | NLCPR
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Name of work : Construction of Community Hall at various places in Mizoram ( Sh: Const. Of Community Hall at Saitual, Thingsulthliah, Maite, Tualbung, Lungpher, Buhban, Lenchim, Chawrtui and Puilo). | % | 206.49 | 22.2.2012 | 30.11.2019 |  |  |  |  | 100% | 186.01 | Completed and balance fund of Rs.20.48 (Rs. 16.35 Lakhs NLCPR + Rs. 4.13 Lakhs SMS) awaited for clearing liabilities.
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | SPP
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Circuit House at Serchhip | % | 358.18 | - | - | - | - | - | - | - | - | Work not executed due to various reasons. Fund received Rs. 358.18 lakhs is kept at D-III
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | SCA/SASCE
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Improvement/Upgradation of Operational/Non-operational facilitiies of Lengpui Airport, (Sh: Renovation of terminal building). | % | 2124 | 10.3.2021 | 31.12.2024 | 99.1% | 1773.36 | 0.1% | 0 | 99.2% | 1773.36 | Work in progress | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | ECRP - II
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of 50 Bedded critical care block at Champhai District Hospital, Mizoram | % | 1346.4 | 4.8.2023 | 4.2.2026 | 78% | 494.58 | 4% | 87.15 | 82% | 581.73 | Work in Progress | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | NABARD - WIF
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of 24 Warehouses with associated infrastructure in 23 locations in Mizoram under NABARD (Group VII : Teikhang ,Rabung & Dungtlang). | % | 336.53 | 17.7.2023 | 31.3.2025 | [6 empty] | Work in Progress | PWD Form - 8
| i) Construction of 200 MT warehouse at Teikhang |  |  |  |  | 100% | 70.49 | 0% | 0 | 100% | 70.49
| ii) Construction of 200 MT warehouse at Rabung |  |  |  |  | 100% | 70.58 | 0% | 0 | 100% | 70.58
| iii) Construction of 200 MT warehouse at Dungtlang |  |  |  |  | 100% | 81.89 | 0% | 0 | 100% | 81.89
| iv) Construction of staff quarters at Dungtlang |  |  |  |  | 99% | 0 | 0.5% | 0 | 99.5% | 0
| Overall |  |  |  |  | 99% | 222.96 | 0.5% | 0 | 99.5% | 222.96
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | SCA to TSS/CSS
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Const of 100 Bedded Dist hospital at Saitual ( Sh: Cons of OPD building at district hospital, Saitual) | % | 200 | 13.10.2023 | 13.10.2025 | 95% | 125.22 | 5% | 0 | 100% | 125.22 | Work in progress | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | NEC
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Creation of Passion fruit Processing unit at Cold Storage , New Champhai Mizoram. | % | 185.39 | 23.9.2022 | 24.3.2024 | 100% | 185.39 | 0% | 0 | 100% | 185.39 | Building work completed. Procurement of plants and machineries being taken up by D.C. Champhai. | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | NEC
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Zomi cultural Centre and preservation of historical sites at Champhai | % | 478.69 | 26.9.2022 | 7.2.2025 | 100% | 425.84 | 0% | 0 | 100% | 425.84 | Work completed | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | NEC
Sl no | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Biate Tea Tourism Circuit & Nature camp in Mizoram | % | 369.62 | 9.10.2023 | 9.10.2025 | 95.7% | 342.62 | 0.3% | 0 | 96% | 342.62 | Work in progress | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | NEC
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Establishing Mizo cultural heritage centre for protecting the historical and natural heritage of Mizo at Kawlri, Serchhip | % | 486.47 | 16.2.2024 | 16.2.2026 | 52% | 121.61 | 4% | 0 | 56% | 121.61 | Work in progress | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | NEC
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Auditorium at Bethel Veng Champhai | % | 1443.75 | 16.2.2024 | 16.2.2026 | 48% | 265.59 | 4% | 0 | 52% | 265.59 | Work in progress | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | NESIDS - OTRI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of 50 Bedded District Hospital Complex and Procurement of equipment at Khawzawl, Khawzawl District, Mizoram | % | 1775 | 11.6.2024 | 11.12.2026 | 64% | 541.04 | 3% | 0 | 67% | 541.04 | Work in progress | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | NESIDS-OTRI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of 50 Bedded District Hospital Complex and Procurement of equipment at Saitual, Saitual District, Mizoram | % | 1696 | 10.6.2024 | 10.12.2026 | 30% | 144.64 | 5% | 0 | 35% | 144.64 | The local NGO's wanted to shift the layout of the hospital main building towards the backside and lowering of the courtyard which will involve additional fund. The matter is brought to Health Department and decision is awaited. Work for quarters only in progress. | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | NEC
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Upgradation of Sports Infrastructure of Ngopa Playground at Saitual District, Mizoram. | % | 394.15 | 15.3.2025 | 15.9.2027 | 45% | _ | 15% | _ | 60% | _ | Work in progress | _
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | NEC
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Our Heritage, Our Treasure at Vangchhia Tourist Spot, Champhai, Mizoram | % | 115.76 | 19.7.2025 | 19.7.2026 | 2% | _ | 3% | _ | 5% | _ | Work in progress | _
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | NESIDS
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Improvement/Upgradation of Operational/Non-operational facilities of Lengpui Airport, (Sh: Elevated road with connected components of Terminal Building). | % | 1959 | 30.9.2021 | 30.11.2024 | 100% | 1959 | 0% | 0 | 100% | 1959 | Completed | Turnkey
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | CSS
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Tourist Lodge at Champhai | % | 328.73 | 9.12.2010 | 30.11.2020 |  |  |  |  | 100% | 300 | Taken over by the Department on Dt.3.8.2021 . LOC amounting to Rs. 30.00 lakh submitted for clearing liaibility. Hence, release of LOC awaited for financial closure.
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | CSS
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Polytechnic at Chhiahtlang | % | 800 | [8 empty] | Only approach road is executed. Out of fund received amount Rs. 300.00 lakhs balance amount of Rs. 196.34 lakhs is kept at D-III
| i) Approach road |  |  | 3.3.2016 | 2.8.2016 |  |  |  |  | 100% | 103.67
ii) Administrative & Academic Block
iii) Hostel Block
iv) Staff Quarter
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | CSS
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Hostel for S.T Girls at Champhai | % | 462.75 | 18.9.2023 | 28.9.2025 | 87.5% | 162.77 | 0% | 0 | 87.5% | 162.77 | Work temporarily halted due to fund problem | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | CSS
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | 10 - Bedded Integrated AYUSH Hospital at Keifang, Saitual District | % | 750 | 13.10.2023 | 13.10.2025 | 50% | 178.86 | 20% | 0 | 70% | 178.86 | Work in progress | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | CSS
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Const of District Court Complex at Vengsang, Champhai. ( Sh: Main Building, phase- I) | % | 4915.35 | 17.10.2023 | 17.10.2026 | 65% | 1307.19 | 2% | 136.88 | 67% | 1444.07 | Work in progress | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER 2025
Name of Division : |  | Project Division - III
Source of Funding : |  | CSR
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of 100 Bedded District Hospital, Block A at Serchhip Mizoram under Powergrid CSR Initiative | % | 2100 | - | - | 22% | - | 3% | - | 25% | 218 | Revised DPR submitted to PGIL. Revised agreement to be signed with contractor after Revised DPR is approved by PGCIL. Only Supervision and Monitoring of work is under PWD. | -
MONTHLY PROGRESS REPORT UNDER SPECIAL ASSISTANCE TO STATES FOR CAPITAL EXPENDITURE FOR THE MONTH OF OCTOBER 2025
Sl. No. | Name of Project with brief description | Approved Cost (Rs. lakh) | First Installment |  | Second Installment |  | Component-wise break up of the Project | Component-wise Project milestones (Target date of completion) | Financial Progress (component wise in Rs.lakh | Physical Progress (component wise in %age) | Remarks, including Reason for non-achievement of milestone (If applicable)
|  |  | Date of Sanction | Amount (Rs.lakh) | Date of Sanction | Amount (Rs.lakh)
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Name of the Implementing Department : PWD, Project Division-III
1 | Improvement/ Upgradation of Operational/ Non-operational Facilities of Lengpui Airport. (SH : Renovation of Terminal Building) | 2124 | 16.03.2021 | 1577.66 | 19.10.2022 |  | A. Renovation of Terminal Building | 21.10.2023 Extended upto 31.12.2024 | 1773.36 | 99.2% | Work in Progress.
1. Earth Works
2.Dismantling Item
3.PCC works
4.RCC works
5.Brick walling
6.Plastering
7.Tile Flooring
8.Ceiling & Column Panneling with ACP Board
[6 empty] | 537 | 9.Painting with POP
10.Railing (Stainless Steel with Tuffen Glass)
11.Doors & Windows Fittings
12.Temporary Laminated Board Partition
13.Roof Treatment
14.Sanitary fittings
B.Sub-Surface Cable Channel
C.Roof Extension (LS)
MONTHLY PROGRESS REPORT UNDER SPECIAL ASSISTANCE TO STATES FOR CAPITAL EXPENDITURE FOR THE MONTH OF OCTOBER 2025
Sl. No. | Name of Project with brief description | Approved Cost (Rs. lakh) | First Installment |  | Second Installment |  | Component-wise break up of the Project | Component-wise Project milestones (Target date of completion) | Financial Progress (component wise in Rs.lakh | Physical Progress (component wise in %age) | Remarks, including Reason for non-achievement of milestone (If applicable)
|  |  | Date of Sanction | Amount (Rs.lakh) | Date of Sanction | Amount (Rs.lakh)
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Name of the Implementing Department : PWD, Project Division-III
1 | Const of 100 Bedded Dist hospital at Saitual ( Sh: Cons of OPD building at district hospital, Saitual) | 200 | 22.3.2022 | 200 |  |  | 1 Building portion with water supply & sanitary fittings. 2. Underground Sump (20,000 ltrs capacity) | 13.10.2025 | 125.22 | 100% | Work in progress
Sr.Executive Engineer, PWD. Project Division - III Aizawl, Mizoram

## PD - IV
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER, 2025
Name of Division |  | : Project Division - IV
Source of funding |  | : SASCI
Sl. No. | Name of work/project | Unit | Approved cost (Rs. in lakh) | Date of commencement | Target date of completion | Cummulative progress at the end of last month |  | Achievement of works during the month |  | Overall Cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin |  |  | COPY 4
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Working Women Hostel (50 Bedded) at Ramhlun Sports Complex, Aizawl. | % | 1400 | 2025-05-14 | 2026-05-14 | 19% | 69.9456 | 2% | 10 | 21% | 79.9456 | Work in progress. | Item rate.
2 | Upgradation of Govt. Hrangbana College, Aizawl, Mizoram. | % | 200 | 2025-07-14 | 2026-07-14 | 60% | 0 | 5% | 50.0555 | 65% | 50.0555 | Work in progress. | Item rate.
3 | Construction of Retaining Wall and Drainage System in Various Higher Educations Institutions to Mitigate Effects of Cyclonic Storm. | % | 204
| a) Government Aizawl College, Mualpui | % | 38 | 2025-09-15 | 2026-09-15 | 15% | 0 | 60% | 0 | 75% | 0 | Work in progress. | Item rate.
| b) Government Mizoram Law College, Luangmual | % | 72 | 2025-09-11 | 2026-09-11 | 0% | 0 | 20% | 0 | 20% | 0 | Work in progress. | Item rate.
| c) Mizoram Hindi Training College, Durtlang North | % | 94 | 2025-09-11 | 2026-09-11 | 15% | 0 | 30% | 0 | 45% | 0 | Work in progress. | Item rate.
4 | Construction of Revenue Staff Qtr. Complex at Aizawl. | % | 500
| a) Construction of Revenue Staff Quarters at Kawltheihuan, Aizawl | % | 298 | N.A. | N.A. | 0% | 0 | 0% | 0 | 0% | 0 | Dismantling work to be started. Mobilisation in process. | Item rate.
| b) Construction of Revenue Staff Quarters at College Veng, Aizawl | % | 202 | N.A. | N.A. | 0% | 0 | 0% | 0 | 0% | 0 | Work order allotted. However, work could not be started due to land issues. | Item rate.
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER, 2025
Name of Division |  | : Project Division - IV
Source of funding |  | : SASCE
Sl. No. | Name of work/project | Unit | Approved cost (Rs. in lakh) | Date of commencement | Target date of completion | Cummulative progress at the end of last month |  | Achievement of works during the month |  | Overall Cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Multi Utility Centre at Zemabawk, Aizawl, Mizoram | % | 800 | 2022-12-19 | 2025-12-30 | 89% | 356.14 | 1.5% | 0 | 90.5% | 356.14 | Work in progress. | Item rate.
2 | Construction of Solid Waste Management Centre at Hualngohmun, Mizoram (Phase-I) | % | 1664 | 2023-04-07 | 2026-04-15 | 52.5% | 509.6972 | 1.5% | 0 | 54% | 509.6972 | Work in progress. | Item rate.
3 | Restoration/renovation of DC Office at Aizawl. | % | 2000 | 2025-04-08 | 2026-04-08 | 21.5% | 0 | 1% | 0 | 22.5% | 0 | Work in progress. | Item rate.
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER, 2025
Name of Division |  | : Project Division - IV
Source of funding |  | : NEC
Sl. No. | Name of work/project | Unit | Approved cost (Rs. in lakh) | Date of commencement | Target date of completion | Cummulative progress at the end of last month |  | Achievement of works during the month |  | Overall Cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of AYUSH Development Centre at MINECO Aizawl, Mizoram | % | 264.16 | 2022-12-07 | 17-08-2024 17.04.2025 (1st EOT) | 82% | 198.12 | 3% | 0 | 85% | 198.12 | Work in progress. EOT application in process. | Item rate.
1 | Establishment of Sinlung Hills Council Administrative Complex, Mizoram (Sh : Construction of Sinlung Hills Council Administrative Building at Sakawrdai) | % | 381.99 | 2021-11-08 | 31-07-2024 )1st EOT) 28.02.2025 (2nd EOT) | 96% | 295.1993 | 1% | 0 | 97% | 295.1993 | Work in progress. Bill withheld amount - Rs. 5.00 lakhs. | Item rate.
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER, 2025
Name of Division |  | : Project Division - IV
Source of funding |  | : Article 275 (1)
Sl. No. | Name of work/project | Unit | Approved cost (Rs. in lakh) | Date of commencement | Target date of completion | Cummulative progress at the end of last month |  | Achievement of works during the month |  | Overall Cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Tribal Hostel at Suangpuilawn, Mizoram. | % | 320 | 2023-08-12 | 2025-07-22 | 76% | 139.9992 | 0% | 0 | 76% | 139.9992 | Work progress hindered due to irregularity in release of fund from Ministry. | Item rate.
2 | Construction of Multipurpose Community Hall at Darlawn, Mizoram. | % | 720 | 2023-08-12 | 2025-08-12 | 63% | 149.8635 | 0% | 0 | 63% | 149.8635 | Work progress hindered due to irregularity in release of fund from Ministry. Bill withheld amount Rs. 14.90 lakh. | Item rate.
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER, 2025
Name of Division |  | : Project Division - IV
Source of funding |  | : NABARD
Sl. No. | Name of work/project | Unit | Approved cost (Rs. in lakh) | Date of commencement | Target date of completion | Cummulative progress at the end of last month |  | Achievement of works during the month |  | Overall Cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of 24 warehouses with associated infrastructure in 23 locations in Mizoram under NABARD (Group V : Zohmun) | % | 170.99 | 2023-07-17 | 2025-07-17 | 62% | 60.4338 | 3% | 0 | 65% | 60.4338 | Work in progress. | Item rate.
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER, 2025
Name of Division |  | : Project Division - IV
Source of funding |  | : NEDP
Sl. No. | Name of scheme | Unit | Approved cost (Rs. in lakh) | Date of commencement | Target date of completion | Cummulative progress at the end of last month |  | Achievement of works during the month |  | Overall Cumulative achievement |  | Remarks | Mode of contract
| Name of work/project |  |  |  |  | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Agriculture Growth Centre at Tuikual South, Aizawl. | % | 4555 | 2025-02-10 | 2026-02-10 | 21.5% | 753.9847 | 1.5% | 0 | 23% | 753.9847 | Work in progress. | Item rate.
Sr. Executive Engineer, PWD
Project Division - IV
Aizawl : Mizoram

## SERCHHIP DIV
MONTHLY PROGRESS REPORT OF PMGSY FOR THE MONTH OF OCTOBER, 2025
Name of Work |  | : Construction of Mualcheng - N.Vanlaiphai RoadGroup -A
Division |  | : Serchhip
Date of Commencement |  | : Dt. 31.12.2020
Target Date of Completion |  | :Dt. 31.12.2022
Name of Contractor |  | Bhavya Construction PVt LTD | [8 empty] | (Amount/Financial Rs. in lakh)
Componence of Works |  | As per Agreement |  |  | Achievement upto the previous month |  | Achievement during the month |  | Cummulative Achievement |  | Remarks
|  | Qnt | Unit | Item Amount (Lakh) | Phy | Fin. | Phy | Fin. | Phy | Fin.
| Construction and maintenancve of Mualcheng to N.Vanlaiphai road (Group -A 0.00 -8.00kmp) | 8 |  | 535.67 | 100% |  |  |  | 100% | 303.13 | Physically Completed
MONTHLY PROGRESS REPORT OF PMGSY FOR THE MONTH OF OCTOBER, 2025
Name of Work |  | :Upgradation and Maintenace of Khawlailung to Hmunzawl to Lungpho
Division |  | : Serchhip
Date of Commencement |  | : Dt. 31.08.2024
Target Date of Completion |  | :Dt. 31.08.2026
(Amount/Financial Rs. in lakh)
Componence of Works |  | As per Agreement |  |  | Achievement upto the previous month |  | Achievement during the month |  | Cummulative Achievement |  | Remarks
|  | Qnt | Unit | Item Amount (Lakh) | Phy | Fin. | Phy | Fin. | Phy | Fin.
1 | Upgradation and Maintenace of Khawlailung to Hmunzawl upto Lungpho | 44.4 |  | 3516.65 | 13.71% |  | 1.2% | 108.85 | 14.91% | 103.75 | Machinery Advance= Rs 270 lakh
Sr,Executive Engineer,PWD
Serchhip Division: SErchhip

## SAITUAL DIV
NAME OF DIVISION : PWD Saitual Division
MONTHLY PROGRESS FOR THE MONTH OF : OCTOBER 2025
[6 empty] | Physical in % |  |  |  | Financial is Rs in lakh
Sl. No | Name of Scheme | Unit | Approved Cost (in lakhs) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last Month |  | Achievement of works during the month |  | Overall Cumulative achievement |  | Remarks | Mode of Tender
| Name of Work/ Project |  |  |  |  | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
NESIDS
1 | Improvement & Upgradation of Daido to Vawngkawt- Buangpuilawn (Manipur) Road |  | 2404 | 14.03.2024 | 14.09.2025 | 88.67% | 1626.13 | 1.82% |  | 90.49% | 1626.13 | Security Deposit amounting to Rs. 0.93 Cr. Is lying in CNA Account | Open Tender
SASCI-II
1 | Improvement of Khawlek - Ratu Road (Length = 6Km) |  | 130 | 05.10.23 | 05.10.24 | 100% | 126.14 |  |  | 100% | 126.14 |  | Restricted Tender
2 | Widening and reconstruction of culverts on 3rd Road from Sedaikawn to PWD Kawn, Saitual (Length = 2.220Kms) |  | 137.52 | 05.10.23 | 05.10.24 | 100% | 137.52 |  |  | 100% | 137.52 |  | Restricted Tender
3 | Rigid pavement of Sakeibangla to ZMC via Thingsulthliah Road Thingsulthliah, PCC Pavement = 3.00km, Side drain = 2000m,R/Wall = 10m, Culvert = 2 Nos |  | 55.78 | 05.10.23 | 05.10.24 | 100% | 55.78 |  |  | 100% | 55.78 |  | Restricted Tender
4 | Pothole & Patch repair on Saitual to Phullen Road. ( 2.00 km ) |  | 15.5 | 05.10.23 | 05.10.24 | 100% | 15.5 |  |  | 100% | 15.5
SASCI & SASCI-II
1 | Restoration of damages due to cyclone remal under Khawzawl, Saitual & Serchhip Division (Saitual Division) |  | 165.25 | 16.06.2025 | 16.01.2026 | 70.77% | 59.76 |  |  | 70.77% | 59.76 |  | Restricted Tender
2 | Restoration of damages due to cyclone remal under saitual division PART-II |  | 598.92 | 16.06.2025 | 16.01.2026 | 67.42% | 81.22 | 12.2% | 40.98 | 79.62% | 122.2 |  | Restricted Tender
SASCI-V
1 | Extension of Saitual Town Via Khiangpuizawl under part V |  | 441.35 | 23.06.2025 | 23.06.2026 | 7.5% | 0 |  |  | 7.5% | 0 |  | Restricted Tender
SEDP
1 | Construction of Khanpui - Tualbung Road Phase-II |  | 1576.01 | 15.01.20 | 15.06.22 | 100% | 1575.73 |  |  | 100% | 1575.73
Sr. Executive Engineer, PWD.,
Saitual Division, Saitual.

## SIAHA DIV
PWD Siaha Division.
Sl.No. |  | Name of Scheme | Unit | Approved Cost (in lakhs) | Date of Commencement | Target date of Completion | Commulative Progress at the end of last Month |  | Achievement of work during the month |  | Overall Cummulative achievement |  | Remarks | Mode of Tender
|  | Name of Work/Project |  |  |  |  | Phy | Fin | Phy | Fin | Phy | Fin |  |  | 0.1278
1 |  | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 |  | 2: SASCI
|  | Wedening,Blacktopping and Improvement of of Road from Saihatlangkawn Beat post-Primary School-II - District Court Complex and Magistrate Rrsidence. | % | 346.15 | 21.08.2025 | 21.12.2025 | 8.43% |  |  |  | 8.43% |  | Work in progress | Item rate Contract
2 |  | 2: NABARD
Work under NABARD
|  | Up-gradation of Laki to Vahai Road From Ch. 0.00 km to Ch. 15.56 km | % | 1809.4429 | 28.06.2024 | 27.06.2026 | 62.84% | 1051.59 | 0.41% |  | 63.25% | 1051.59 | Work in progress | Item rate Contract | 0.13%
3 |  | 2: NEC
Work under NEC
4 |  | 2: PMGSY
Work under PMGSY
5 |  | 2: SEDP
Work under SEDP
6 |  | 2: CSS
Work under CSS
7 |  | 2: MoRTH
Work under MoRTH
8 |  | 2: 5054
|  | Annual Plan 2024 - 2025 Strengthening and Improvement of Bridge under Mizoram | % | 250 | 02.12.2024 |  | 3% | 7.04 |  |  | 3% | 7.04 | Work in progress | Item rate Contract
9 |  | 2: CRF
|  | Construction of Road from Chakhei to Siasi road (Length = 20 km) under CRF: Group-A (SH: FC & Pavement Works) | % | 3630.73 | 08.07.19 | 20.12.2024 | 99.99% | 2969.6779 |  |  | 99.99% | 2969.6779 | Work in progress | Item rate Contract
10 |  | 2: 3054
Work under Annual Maintenance Action Plan (3054) During 2025-26 under PWD Siaha Division
a) |  | Maintenance and Improvement of Approach road to PHC with PCC at Sangau | % | 15.35 | 18.08.2025 | 24.10.2025 |  |  | 100% | 0 | 100% | 0 | Work completed | Item rate Contract
b) |  | Construction of Retaining Wall on Tlangpui - Niawhtlang Road (0.000 - 14.000) kmp at Ch. 7.500 km | % | 6.28 | 07.07.2025 | 08.09.2025 |  |  | 100% | 0 | 100% | 0 | Work completed | Item rate Contract
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER 2025
Name of Division: Siaha Division
Name of contractor: Tantia Constructions Ltd., DD-30, Sector -I, Salt Lake City, Kalkata
Aggrement amount : Rs.43,07,95,440.00
| A.Financial Report | 12: ANNEXURE - F
| Sl.No. | Name of the project Location and State | Name of the Implementing Agency/Deptt | Approved Cost by MDoNER |  | Fund released by MDoNER/NEC |  | Expenditure made |  | Unspent balance out of the fund released | Status of submission of U/Cs | Remark
|  |  |  | Origincal cost | Revised cost | During | Since inception (Cumulative) | During the month vis-a-vis target | Since inception (cumulative)
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
| 1 | Upgradation of Saiha - Lungbun - Tluangram - Haka Road in the State of Mizoram under North East Special Infrastructure Development Scheme(NESIDS) on EPC Mode. | PWD Siaha Division, Siaha | 50.21 Cr | Nil | NIL | 42.44 | NIL | 42.44 | 0 | Nil | Work in progress
Name of Division: Siaha Division
Name of contractor: Tantia Constructions Ltd., DD-30, Sector -I, Salt Lake City, Kalkata
Aggrement amount : Rs.43,07,95,440.00
B.Physical Report
| Sl.No. | Name of the project Location and State | Name of the Implementing Agency/Deptt | Approved Cost by MDoNER/NEC & Date of Approval |  | Date of Actual Commencement of work/Scheme | Target date of completion of work/scheme | Scope of the work/scheme in physical terms (eg. Kms, etc) |  | Physical achievemnt |  | Remark
|  |  |  | Cost | Date |  |  |  |  | Percentage weightage (previous month) | Percentage weightage (reporting month)
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |  | 9 | 10 | 11
|  | Upgradation of Saiha - Lungbun - Tluangram - Haka Road in the State of Mizoram under North East Special Infrastructure Development Scheme(NESIDS) on EPC Mode. | PWD Siaha Division, Siaha | 50.21 | 2021-01-29 | 29.10.2021 | 31.03.2024 |  |  |  |  | Work in progress.
| 1 | 2: Earthwork (Formation width=7.5m); 4: 6.04; 8: 12.66; 9: Km; 10: 0%; 11: 0%
|  | a) Site Clearance and cutting of Trees | [5 empty] | 12.66 | Km
|  | b) In Cutting | [5 empty] | 12.66 | Km
|  | i) Ordinary soil | [5 empty] | 324097.97 | Cum
|  | ii) Soft Rock | [5 empty] | 135654.24 | Cum
|  | iii) Hard Rock | [5 empty] | 20610.41 | Cum
| 2 | 2: Pavement (width=7.5m)
|  | a) Granular Sub-Base (GSB = 150 mm) |  | 3.69 |  |  |  | 12.66 | Km | 0% | 0%
|  | b) Wet Mix Macadam (WMM = 250 mm) |  | 7.43 |  |  |  | 12.66 | Km | 0% | 0%
| 3 | 2: Bituminous Courses
|  | a) DBM (60 mm) |  | 6.71 |  |  |  | 12.66 | Km | 0% | 0%
|  | b) BC (30 mm) |  | 4.45 |  |  |  | 12.66 | Km | 0% | 0%
| 4 | Side Drain |  | 2.7 | 2021-01-29 | 29.10.2021 | 31.03.2024 | 10010 | Rm | 0% | 0% | Work in progress.
|  | a) Concrete Lined Side drain | [5 empty] | 6340 | Rm
|  | b) Unlined Side Drain | [5 empty] | 3670 | Rm
| 5 | 2: Protection Work (Retaining Wall); 4: 3.46; 8: 486; 9: Rm; 10: 7.88%; 11: 0%
|  | a) Type-I (Ht.= 3m) | [5 empty] | 160 | Rm
|  | b) Type-II (Ht.= 4m) | [5 empty] | 117 | Rm
|  | c) Type-III (Ht.= 5m) | [5 empty] | 209 | Rm
| 6 | 2: Cross Drainage Works (Box Culvert); 4: 8.08; 8: 53; 9: No.; 10: 18.05%; 11: 0%
|  | a) Type-I ( 1.5mx1.5m) | [5 empty] | 38 | No.
|  | b) Type-II ( 2mx2m) | [5 empty] | 11 | No.
|  | c) Type-III ( 3mx4m) | [5 empty] | 2 | No.
|  | d) Type-IV ( 4mx5m) | [5 empty] | 2 | No.
| 7 | 2: Project Facilities
|  | a) Traffic signages & Road safety measures, Km stones, Informatory signs etc. |  | 0.25 |  |  |  | 12.66 | km | 0% | 0%
|  | b) PCC Parapet Wall |  | 0.27 |  |  |  | 360 | Rm | 0% | 0%
[10 empty] | 25.93% | 0%
[10 empty] | Total = | 25.93%
| Name of the Officer | 3: Er. K. LUAIMINTHANGA
| Designation | 3: Sr. Executive Engineer, PWD,
Siaha Division
Date with Seal

## TLABUNG DIV
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER / 2025 UNDER PWD, TLABUNG DIVISION.
[10 empty] | Physical in % |  | Financial in lakh
Sl No | Name of Scheme | Unit | Approved cost (in lakh) | Date of Commencement | Target date of completion | Cummulative progress at the end of last mont |  | Achievement of works during the month |  | Overall Cummulative achievement |  | Remarks | Mode of Contract
| Name of works / Project |  |  |  |  | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
A | SASCI
1 | Strengthening of Chawngte and Borapansury road | km | 391.3 | 22.06.2023 | 22.06.2024 | 50% | 194.02 |  |  | 50% | 194.02 | On-going Extension granted upto Dt.31.03.2026 | Item Rate
2 | Restoration of Damage Due to Cyclone Remal under Tlabung Division | Km | 800 | 16.06.2025 | 16.01.2026 | 35% | 243.6 | 5% | 59.36 | 40% | 302.96 |  | Item Rate
B | NABARD
1 | Improvement of Chawngte - Borapansury Road (0.000-30.00)KMP | Km | 3987 | 15.03.2023 | 15.03.2025 | 31% | 1023 |  |  | 31% | 1022.997 | On-going Extension granted upto Dt.13.07.2026 | Item Rate
2 | Const of Galvanised Steel Concrete Composit Bridge over Borapansury River on Chawngte to Borapansury road | Nos | 635.69 | 13.05.2024 | 13.05.2026 | 1% | 0 |  |  | 1% | 0 |  | Item Rate
MONTHLY PROGRESS REPORT FOR THE MONTH OF OCTOBER / 2025
Name of works : (3054) Maintenance Action Plane During 2025- 2026
Name of Division : Tlabung Division | [9 empty] | (Rs.in lakh)
Sl No | Name of Works | Unit | Length to be covered in meter | Amount (Rs in Lakh) | Cummulative progress at the end of last mont |  | Achievement of works during the month |  | Overall Cummulative achievement |  | Remarks
[5 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Resurfacing of Central Road | Km | 0.42 | 7.61 | 0.2 |  | 0.22 |  | 0.42 |  | Completed Physical Works
2 | Resurfacing of approach road to SDO C Office with courtyard | Km | 0.044 | 6.93 | 0.044 |  |  |  | 0.044 |  | Completed Physical Works
3 | Resurfacing of Zawlpuikawn Community Hall | Km | 0.7 | 9.73 | 0.1 |  | 0.6 |  | 0.7 |  | Completed Physical Works
4 | Resurfacing of Chawngte P-C Bridge to Bethani veng | Km | 0.812 | 22.35 |  |  | 0.812 |  | 0.812 |  | Completed Physical Works
5 | Resurfacing of Approach road to PWD IB via Police Thana and Forest Complex | Km | 0.432 | 6.81 |  |  | 0.432 |  | 0.432 |  | Completed Physical Works
6 | Resurfacing of approach road to PWD Complex Lungsen | Km | 0.4 | 8.68 |  |  | 0.4 |  | 0.4 |  | Completed Physical Works
[7 empty] | Physical % |  | 100 | %
Sr.Executive Engineer, PWD.
Tlabung Division, Tlabung.