## ARND
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY, 2026
Name of Work : Improvement & Maintenance of City Roads under Annual Maintenance Operation Plan (AMOP) 2025-26
Name of Scheme : State funding (3054)
Approved Amount : Rs. 75.17 lakh
Name of Sub-Division : Aizawl Road North Sub-Division-I
Sl. No. | Sub-Head of works | Unit | Approved Cost (in lakh) | Date of Commencement | Target Date of Completion | Commulative Progress at the end of Last Month |  | Achievement of Works during the Month |  | Overall cumulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
SUB - DIVISION - I
1 | Patch repair of Aizawl City roads within Aizawl Road North Division-I | Nos | 66 | 2025-08-01 | 2026-03-31 | 100% | - | - | - | 100% | 66 | Completed | Departmental
2 | Patch Repair and Seal Coating of Electric 3rd row Road | km | 5.15 |  |  | 100% | - | - | - | 100% | 5.15 | Completed
3 | Patch Repair and Seal Coating of Electric 2nd row road upto Zirtiri College | km | 9.61 |  |  | 100% | - | - | - | 100% | 9.61 | Completed
4 | Patch Repair and Seal Coating of Darnam lui to chite (new complex) | km | 8.19 |  |  | 35% | - | 65% | - | 100% | 1.24 | Phy Completed
5 | Patch Repair and Seal Coating of Armed veng to Electric veng Cemetry Road | km | 10.58 |  |  | 45% | - | 55% | - | 100% | 1.56 | Phy Completed
6 | Patch Repair and Seal Coating of Armed veng to Armed Veng 'S' to Bethlehem Vengthlang Zoo Road | km | 7.13 |  |  | 50% | - | 50% | - | 100% | 7.13 | Phy Completed
7 | Improvement of Riding Quality on Bazar Bungkawn to Chite Road | km | 15.74 |  |  | 20% | - | - | - | 20% | 0.47 | Work in progress
8 | Construction of R/Wall infront of Zohmingliani's House near RSC field, Ramhlun North | Rm | 3 |  |  | 100% | - | - | - | 100% | 3 | Completed
9 | Patch repair and Seal Coating of Vaivakawn to Bazar Bungkawn road | Km | 6.55 |  |  | 20% | - | - | - | 20% | 6.07 | Work in progress
SUB - DIVISION - II
1 | Patch Repair and Seal Coating of Sihphir Lower Lane ) Indoor stadium) | Km | 2.94 |  |  | 0% | - | 0% | - | 0% | - | Not yet started | Departmental
2 | Patch Repair and Seal Coating of CRPF Camp to Kailiana road at Thuampui (BRTF Complex Kailiana road) | Km | 1 |  |  | 0% | - | 0% | - | 0% | - | Not yet started
3 | Patch Repair and Full Seal Coating of approach road to Lower Zotui veng at Durtlang Leitan (Zotui kawng Pu Dokhuma's house) | Km | 0.6 |  |  | 0% | - | 0% | - | 0% | - | Not yet started
4 | Patch Repair and Full Seal Coating of Approach Road to Thuampui Cemetry (BRTF Complex Thuampui cemetry) | Km | 1.41 |  |  | 0% | - | 0% | - | 0% | - | Not yet started
5 | Patch Repair and Full Seal Coating of Zemabawk vengthar road (Anganwadi centre RIPANS road) | Km | 0.78 |  |  | 0% | - | 0% | - | 0% | - | Not yet started
6 | Patch Repair and Full Seal Coating of Approach Road to TV centre at Durtlang (DDK) | Km | 0.72 |  |  | 0% | - | 0% | - | 0% | - | Not yet started
7 | Patch Repair and Full Seal Coating of Upper Hermon road at Durtlang | Km | 8.8 |  |  | 0% | - | 0% | - | 0% | - | Not yet started
8 | Patch Repair and Full Seal Coating of Upper Hermon road Lane-4 at Durtlang | Km | 2.93 |  |  | 0% | - | 0% | - | 0% | - | Not yet started
9 | Resurfacing with Mix seal surfacing of bawngkawn Hmar veng to Thuampui road | Km | 30.53 |  |  | 0% | - | 0% | - | 0% | - | Not yet started
10 | Patch Repair and Full Seal Coating of approach road to Bawngkawn cemetry | Km | 1.89 |  |  | 0% | - | 100% | - | 100% | - | Phy Completed | Departmental
11 | Patch Repair and Full Seal Coating of AMC road at bawngkawn | Km | 6 |  |  | 0% | - | 60% | - | 60% | - | Work in progress
12 | Patch Repair and Full Seal Coating of approach road to Sobji bazar road at bawngkawn | Km | 2.02 |  |  | 0% | - | 60% | - | 60% | - | Work in progress
13 | Resurfacing of Chhingtei road at Durtlang | Km | 16 |  |  | 0% | - | 0% | - | 0% | - | Not yet started
14 | Construction of V-Shaped Side drain ai Leitan Ramthar Lane-II | Km | 15.49 | 23.8.2025 | 2026-03-30 | 100% | - | 0% | - | 100% | 15.04 | Phy Completed
15 | Construction of V-Shaped Side drain ai Leitan Ramthar Lane-I | Km | 21.48 | 4.9.2025 | 2026-03-30 | 100% | - | 0% | - | 100% | 20.86 | Phy Completed
16 | Construction of Retaining wall at Upper Hermon road at Durtlang | Km | 20.34 | 22.8.2025 | 2026-03-30 | 100% | - | 0% | - | 100% | 14.87 | Phy Completed
17 | Construction of Gabion wall at Thuampui to selesih road at Ch:2.000kmp | Km | 5.61 | 20.8.2025 | 2026-03-30 | 100% | - | 0% | - | 100% | 5.44 | Phy Completed
18 | Construction of V-Shaped Side drain at ICFAI road | Km | 18.9 | 19.8.2025 | 2026-03-30 | 100% | - | 0% | - | 100% | 12.46 | Phy Completed | Departmental
19 | Re-Construction of Course rubble masonry Line side drain at bawngkawn Sobji bazar road | Km | 7.95 | 17.8.2025 | 2026-03-30 | 100% | - | 0% | - | 100% | 7.72 | Phy Completed
20 | Construction of Retaining wall at Thuampui to Selesih road at Ch:8.040 kmp | Km | 7.76 | 10.9.2025 | 2026-03-30 | 100% | - | 0% | - | 100% | 7.53 | Phy Completed
SUB - DIVISION - III
1 | Patch Repair and Seal coating of Presby Church to Khamtlang via Bus Turning point & NBCC road Sakawrtuichhun | Km | 8.5915 | 2025-08-14 | 2026-03-30 | - | - | 100% | - | 100% | 0.24 | Phy Completed | Departmental
2 | Patch Repair and Seal coating of Sairang Zero Point to Dawrpui Veng (Rochhing Road) (Sairang Zero Point Sairang Dawrpui) | Km | 3.356 | 2025-08-14 | 2026-03-30 | 0% | - | 100% | 2.12 | 100% | 2.12 | Phy Completed
3 | Patch repair and Seal Coating of PTC Lungverh to Power Grid (PTC IR Bn Liando Resort Junction) | Km | 4.4839 | 2025-08-14 | 2026-03-30 | 100% | - | 0% | - | 100% | 4.16 | Phy Completed
4 | Patch repair and Seal Coating of Zotlang Internal Road, Aizawl | Km | 3.0199 | 2025-08-14 | 2026-03-30 | - | - | 100% | 1.86 | 100% | 1.86 | Phy Completed
5 | Construction of V shape Side Drain at MZU Road at Zonuam, Aizawl | Km | 13.2376 | 2025-08-14 | 2026-03-30 | 100% | - | 0% | - | 100% | 12.28 | Phy Completed
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY, 2026
Name of Work : Resurfacing of road within Aizawl city under Aizawl Road North Division
Name of Scheme : State Funding
Tender Amount : Rs. 2145.56 lakh
Agreement Amount : Rs. 2145.56 lakh
Name of Contractor : Nidhi Creative infrastructure Pvt.Ltd.
Name of Division : Aizawl Road North Division
Sl. No. | Name of works | Unit | Qnty | Approved Cost (in lakh) | Date of Commencement | Target Date of Completion | Commulative Progress at the end of Last Month |  | Achievement of Works during the Month |  | Overall cumulative achievement |  | Remarks | Mode of Contract
[7 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Non Bituminous Base Course | sqm | 8495 | 52.55 | 2025-04-17 | 2026-10-17 | 1.16% | 462.98 | 0.77% | 700.31 | 1.93% | 1163.29 | Works in progress | EPC
2 | Construction of Flexible Pavement | km | 44.63 | 1647.25 |  |  | 38.2% |  | 23.76% |  | 61.96%
3 | Construction of Rigid Pavement | km | 1.5 | 397.57 |  |  | 0% |  | - |  | 0%
4 | Construction of Hume Pipe Culvert | No. | 1 | 6.14 |  |  | 0.2862% |  |  |  | 0.2862%
5 | Widening of Tlaklui to Sihpui road Junction | Rm | 60 | 42.05 |  |  | - |  | - |  | -
| Total = |  |  | 2145.56 |  |  | 22.98% | 21.58% | 1.83% | 32.64% | 24.81% | 54.22%
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY, 2026
Name of Work : Widening and Improvement of Road from Durtlang Leitan To Sihphir Section (Length 10.25 Km) of Aizawl - Durtlang - Lungdai - Kawnpui Road in the State Of Mizoram | [7 empty] | Name of Contractor : M/s SLT Infracon Private Limited
Name of Scheme : CRF | [7 empty] | Date of Commencement : 14/07/2023
Tender Amount : Rs. 46.57 Crore | [7 empty] | Target date of Completion : 31/01/2025
Agreement Amount : Rs. 35.53 Crore | [7 empty] | Revised Target date of Completion : NIL
Name of Division : Aizawl Road North Division | [7 empty] | D-III Balance :
OVERALL ACHIEVEMENT (PHY) - 77.85% | [10 empty] | (Rs. in lakh)
Sl. No. | Name of Works | Unit | Cost (in lakh) | Date of commencement | Target date of completion | Cumulative Progress at the end of last month |  | Achievement works during the month |  | Overall cumulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Scarifying | Rm | 7.76 | 14.7.23 | 31.1.25 | 100% | 2572.88 | 0% | - | 100% | 2572.88 | In Progress | EPC
2 | Earthwork | Cum | 102.89 |  |  | 100% |  | 0% |  | 100%
3 | Granular Sub-Base (GSB) | m3 | 166.68 |  |  | 100% |  | 0% |  | 100%
4 | Dry Lean Concrete (DLC) | Rm | 299.22 |  |  | 100% |  | 0% |  | 100%
5 | Pavement Quality Concrete (PQC) | Rm | 1638.24 |  |  | 100% |  | 0% |  | 100%
6 | Slope Protection | Rm | 715.77 |  |  | 70% |  | 10% |  | 80%
7 | Lined Side Drain | Rm | 148.94 |  |  | 40% |  | 15% |  | 55%
8 | Hume Pipe | Nos. | 484.5 |  |  | 100% |  | 0% |  | 100%
9 | RCC Slab Culvert | Nos. | 57.66 |  |  | 100% |  | 0% |  | 100%
10 | Crash barrier | Rm | 34.56 |  |  | 0% |  | 0% |  | 0%
11 | Traffic Signages | Nos. | 3.91 |  |  | 0% |  | 0% |  | 0%
12 | Road Marking | Rm | 7.91 |  |  | 0% |  | 0% |  | 0%
13 | Km Stone | Nos. | 0.38 |  |  | 0% |  | 0% |  | 0%
14 | Flexible Pavement | Rm | 320.52 |  |  | 0% |  | 0% |  | 0%
15 | Lined Side Drain with Steel Grating | Rm | 12.54 |  |  | 0% |  | 0% |  | 0%
16 | Cable Duct | Nos. | 15.91 |  |  | 100% |  | 0% |  | 100%
17 | Zebra Crossing | Sqm | 2.06 |  |  | 0% |  | 0% |  | 0%
18 | Road Stud | Nos. | 11.35 |  |  | 0% |  | 0% |  | 0%
19 | Foothpath | Rm | 362.84 |  |  | 0% |  | 0% |  | 0%
20 | Waiting Shed | Nos. | 9.04 |  |  | 0% |  | 0% |  | 0%
4402.68
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY, 2026 (ROAD WORKS)
Name of Work : Construction of Two Lane from Sihhmui to Ramrikawn Road (Stage-I) | [7 empty] | Name of Contractor : F. Kapsanga, Tuikual
Name of Scheme : CRF | [7 empty] | Revised Target date of Completion : 03.05.2022
Sanction Amount : Rs. 80.00 Crore | [7 empty] | D-III Balance :
Tender Amount : Rs. 71.37 Crore
Name of Division : Aizawl Road North Division
OVERALL ACHIEVEMENT (PHYSICAL) - 87.79% | [10 empty] | (Rs. in lakh)
Sl. No. | Name of Works | Unit | Cost (in lakh) | Date of commencement | Target date of completion | Cumulative Progress at the end of last month |  | Achievement works during the month |  | Overall cumulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Formation Works | Km | 5464.63 | 1.10.2018 | 1.10.2020 | 97% | 6867.09 | 0% | - | 97% | 6867.09 | Contract terminated due to death of contractor on 3.7.2025 | Item Rate
2 | Protection Works
| a) Retaining Wall | Rm | 540.88 |  |  | 91% |  | 0% |  | 91%
3 | Cross Drainage Works
| a) Hume Pipe Culvert | Nos. | 188.63 |  |  | 50% |  | 0% |  | 50%
| b) Box Culvert | Nos. | 818.03 |  |  | 99% |  | 0% |  | 99%
4 | Lined Side Drain
| a) Lined Drain | Km | 44.32 |  |  | 9% |  | 0% |  | 9%
| b) Unlined Drain | Km | 8.31 |  |  | 96% |  | 0% |  | 96%
5 | Box Culvert and Retaining Structure
| a) Box Culvert | Nos. | 493.84 |  |  | - |  | - |  | -
| b) Retaining Wall | Nos. | 96.86 |  |  | 13% |  | 0% |  | 13%
6 | Contingencies etc. | LS | 344.5 |  |  | - |  | - |  | -
| GRAND TOTAL |  | 8000 | [7 empty] | 6867.09
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY, 2026 UNDER NABARD
OVERALL ACHIEVEMENT (PHY) - 89.00%
Sl. No. | Name of Project | Unit | Approved Cost (Rs. in lakh) | Date of Commencement | Target date of completion | Cumulative Progress at the end of last month |  | Achievement works during the month |  | Overall cummulative achievement |  | Remarks | Mode of contract
[6 empty] | Phy. | Fin. | Phy. | Fin. | Phy. | Fin.
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
IMPROVEMENT OF RAMRIKAWN TO NH-54 VIA SAKAWRTUICHHUN ROAD (3.00 Kmp - 7.50 Kmp = 4.50 Km)
1 | Rigid Pavement of Ramrikawn to Sakawrtuichhun | Rm | 480.72 | - | - | 92% | 316.76 | - | 17.02 | 92% | 333.78 | Work in progress | Departmental
2 | Resurfacing of Ramrikawn to Zihnghalkawn 980Rm | Rm |  | - | - | 100% |  | - |  | 100% |  | Phy Completed
3 | Construction of approach road to Chawlhhmun from Power Grid at Tuivamit | Rm |  | - | - | 45% |  | 5% |  | 50% |  | Work in progress
4 | Constn. of R/Wall at Ch 4.230 Kmp at Sakawrtuichhun | Rm |  | - | - | 100% |  | - |  | 100% |  | Phy Completed
5 | Constn. of R/Wall at Ch 3.420 Kmp at Sakawrtuichhun | Rm |  | - | - | 100% |  | - |  | 100% |  | Phy Completed
6 | Constn. of R/Wall at Ch 6.340 Kmp at Sakawrtuichhun | Rm |  | - | - | 100% |  | - |  | 100% |  | Phy Completed
7 | Constn of Slab Culvert at 5.900 kmp at Sakawrtuichhun | Rm |  | - | - | 100% |  | - |  | 100% |  | Phy Completed
8 | Constn. of R/Wall at Ch 3.000 Kmp at Sakawrtuichhun | Rm |  | - | - | 100% |  | - |  | 100% |  | Phy Completed
9 | Constn. of R/Wall at Ch 3.500 Kmp at Sakawrtuichhun | Rm |  | - | - | 100% |  | - |  | 100% |  | Phy Completed
10 | Constn. of R/Wall at Ch 4.620 Kmp at Sakawrtuichhun | Rm |  | - | - | 100% |  | - |  | 100% |  | Phy Completed | Departmental
11 | Constn. of R/Wall at Ch 5.360 Kmp at Sakawrtuichhun | Rm |  | - | - | 100% |  | - |  | 100% |  | Phy Completed
12 | Constn. of R/Wall at Ch 5.200 Kmp at Sakawrtuichhun | Rm |  | - | - | 100% |  | - |  | 100% |  | Phy Completed
13 | Constn. of R/Wall at Ch 6.050 Kmp at Sakawrtuichhun |  |  | - | - | 100% |  | - |  | 100% |  | Phy Completed
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY, 2026
PM - DevINE
A. Physical Report
(Rs. in lakhs)
Sl No | Name of the project, location and State | Name of the Implementing Agency/Deptt. | Approved cost by MDoNER/NEC & Date of Approval |  | Date of actual commencement of work/scheme | Target date of completion of work/scheme | Scope of the work/scheme in physical terms (eg. Kms etc) | Physical Achievement |  | Remarks
|  |  | Cost | Date |  |  |  | Percentage(during the month) | Percentage till the reporting period
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
1 | Construction of Bamboo Link Road from Tuirial Airfield to North Chaltlang (18 Kms) under PM - DevINE | Public Works Department | 3358 | 17.4.23 | 01.08.2023 | 20.10.2025 | Concrete Pavement from 0.00 - 18.00 Kmp | - | 47.13% | The Contractor has stop site activity since last 6 months, necessay action as per EPC contract Agreement is being taken.
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY, 2026
PM - DevINE
B. Financial Report
(Rs. in lakhs)
Sl No | Name of the project, location and State | Name of the Implementing Agency/Deptt. | Approved cost by MDoNER/NEC & Date of Approval |  | Fund released by MDoNER/NEC |  | Expenditure made |  | Unspent balance out of the fund released | Status of submission of U/Cs | Remarks
|  |  | Original Cost | Revised Cost | During 2024 - 2025 | Since inception (cumulative) | During the month vis-à-vis target | Since inception (cumulative)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Construction of Bamboo Link Road from Tuirial Airfield to North Chaltlang (18 Kms) under PM - DevINE | Public Works Department | Rs. 3358.00 on 06.02.23 | Rs. 3374.42 on 02.09.25 | - | 1090.28 | - | 1090.28 | - | - | The Contractor has stop site activity since last 6 months, necessay action as per EPC contract Agreement is being taken.
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY, 2026 UNDER SASCI - II
Sl No | Name of works | Unit | Approved Cost (in lakh) | Date of Comment | Target Date of Completion | Commulative Progress at the end of Last Month |  | Achievement of Works during the Month |  | Overall cumulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
SUB - DIVISION - I
1.CONSTRUCTION OF RCC DRAIN AND PCC PAVEMENT AT CHHINGA VENG AND ELECTRIC VENG
1 | Resurfacing of Armed Veng South to Bethlehem Vengthlang Road at Ch : 0.677 - 1.230 km | Rm | 10.91 | 6.12.2023 | 15.12.2023 | 100% | 151.5 | - | - | 100% | 151.5 | Phy Completed | Restricted
2 | Reconstruction of Collapsed RCC Slab Culvert on Armed Veng South to Bethlehem Vengthlang (Old Zoo Road) near Rawra Chhutna | No | 1.2 | 6.12.2023 | 15.12.2023 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
3 | Balance Work of Construction of RCC Pavement on District Jail to Lower Armed Veng Road (Service Road) | Rm | 1.84 | 10.4.2023 | 11.4.2023 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
4 | Construction of New Road from Lalhmingliana Sailo House to Siamphunga Lei at Tuithiang Phase-II | Rm | 30.14 | 11.3.2024 | 27.3.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
5 | Construction of Drainage System at Aizawl Civil Hospital, Dawrpui West Area | Rm | 14.52 | 18.3.2023 | 24.3.2023 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
6 | Construction of Retaining Wall on Dawrpui Thlanmual Plot-3 | Rm | 6.03 | 24.4.2024 | 3.5.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
7 | Construction of RCC Pavement on Hostel Square at Armed Veng South | Rm | 4.17 | 5.2.2024 | 14.2.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
8 | Construction of RCC Pavement between Pu Thansanga's House to Pu Ronghakliana's House on Armed Veng South Local Council Road | Rm | 2.17 | 19.2.2024 | 23.2.2024 | 100% | 151.5 | - | - | 100% | 151.5 | Phy Completed | Restricted
9 | Construction of PCC Pavement near Pu Larry Lalrova's House Saron Veng | Rm | 4.24 | 8.4.2024 | 13.4.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
10 | Construction of V-Shape Side drain near Rawra Chhutna | Rm | 0.11923 | 12.3.2024 | 15.3.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
11 | Construction of Retaining Wall on Dawrpui Thlanmual Plot - 1 | Rm | 10.95 | 4.4.2024 | 15.4.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
12 | Construction of Retaining Wall on Dawrpui Thlanmual Plot - 2 | Rm | 8.11 | 3.5.2024 | 14.5.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
13 | Construction of Breast Wall on Armed Veng South Local Council Road near Pu Lalnghakliana's House | Rm | 5.94 | 15.4.2024 | 20.4.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
14 | Construction of Breast Wall between Chawngneihkunga's House to Khupneihvunga's House | Rm | 6.41 | 6.2.2024 | 23.2.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
15 | Widening of Road between Chawngneihkunga's House to Khupneihvunga's House | Rm | 9.14 | 22.4.2024 | 10.5.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
16 | Construction of Retaining Wall below Chhinga Veng Thlanmual | Rm | 36.86 | 26.2.2024 | 15.3.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| TOTAL = |  | 152.7492
2. IMPROVEMENT OF ROAD FROM RAMHLUN VENGTHAR TO RAMHLUN SPORT COMPLEX, AIZAWL.
17 | Construction of RCC Balcony on Ramhlun South Cemetery at Ramhlun South | Rm | 42.94 | 8.3.2024 | 22.3.2024 | 100% | 222.94 | - | - | 100% | 222.94 | Phy Completed | Restricted
18 | Construction of RCC Frame Structure Breast Wall near Ramhlun South Cemetary | Rm | 25.61 | 8.2.2024 | 16.2.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
19 | Construction of Retaining Wall below Presbyterian Church, Laipuitlang | Rm | 3.93 | 16.1.2024 | 13.2.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
20 | Construction of RCC Pavement & Lowering on Jubilee road at Ramhlun Vengthar | Rm | 58.59 | 4.3.2024 | 22.3.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
21 | Construction of RCC Rectangular side drain with cover near Jubilee road at Ramhlun Vengthar | Rm | 3.65 | 3.4.2024 | 12.3.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
22 | Construction of Steel Grate Cover Side Drain near Jubilee road at Ramhlun Vengthar | No | 1.49 | 3.4.2024 | 10.4.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
23 | Construction of Breast wall on Turning Point at Tetea Road Ramthar North | Rm | 5.65 | 6.2.2024 | 23.2.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
24 | Construction of RCC Pavement on Tetea Road (Below Pu Dawngliana House) at Ramthar North | Rm | 7.89 | 2.4.2024 | 26.4.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
25 | Construction of Retaining wall on Tetea Road Block-I at Ramthar North | Rm | 6.63 | 1.2.2024 | 19.2.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
26 | Construction of Retaining wall on Tetea Road Block-II at Ramthar North | Rm | 1.83 | 13.1.2024 | 12.2.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
27 | Construction of Breast Wall Below Step at NHC Ramhlun Venglai | Rm | 3.33 | 15.1.2024 | 16.2.2024 | 100% | 222.94 | - | - | 100% | 222.94 | Phy Completed | Restricted
28 | Construction of Breast Wall Vertical Extension NHC at Ramhlun Venglai | Rm | 5.6 | 1.2.2024 | 19.2.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
29 | Construction of RCC Rectangular side drain with cover NHC at Ramhlun Venglai | Rm | 0.97 | 2.2.2024 | 20.2.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
30 | Construction of RCC Rectangular side drain with cover on Rokhuma Colney to PC.Lalzuiliana House(Bishop Road) at Ramthar | Rm | 2.98 | 12.3.2024 | 25.4.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
31 | Construction of Breast Wall Below St.Lawrence School at Ramthar | Rm | 6.56 | 6.3.2024 | 22.3.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
32 | Construction of Breast Wall near Boxing hall at Ramhlun Venglai | Rm | 9.38 | 26.3.2024 | 4.4.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
33 | Construction of Retaining Wall on Sihpui to Tlaklui road at Pu C Lalnunmawia's House | Rm | 8.81 | 5.3.2024 | 21.3.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
34 | Construction of PCC Pavement on ICI road Complex Vengthlang at Ramhlun Sport Complex | Rm | 3.51 | 8.3.2024 | 20.3.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
35 | Construction of Retaining wall near Pu.Rosangpuia House at Ramhlun Sport Complex | Rm | 4.22 | 5.3.2024 | 24.4.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
36 | Construction of Breast wall on LC Road near Lianhnuna Road at Ramhlun Sport Complex | Rm | 3.09 | 4.3.2024 | 25.3.2024 | 100% | - | - | - | 100% | - | Phy Completed | Restricted
37 | Construction of RCC Side drain near Pu.Para House at Ramhlun Sport Complex | Rm | 0.49 | 5.3.2024 | 20.3.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
38 | Construction of RCC Footpath on LC Road near Pu HC Thangvela's House to Pu B Zanghinglova's House | Rm | 16.85 | 12.3.2024 | 25.3.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| TOTAL = |  | 224
WORK UNDER IMPLEMENTATION OF ARTICLE 275 (1) PHASE - II
39 | Construction of Bethany Road at Chhinga Veng | Rm | 70 | 7.10.2023 | 30.11.2023 | 100% | - | - |  | 100% |  | Phy Completed | Restricted
SUB - DIVISION - II
UPAGRADATION OF BETHEL VENG ROAD AT ZEMABAWK, AIZAWL WITH APPROACH ROAD TO ZOKHAWSANG BYPASSS ROAD
40 | Upagradation of Bethel Veng Road at Zemabawk, Aizawl with approach road to Zokhawsang Bypass Road
| 1. PCC Pavement at Ch: 0.000 - 0.580kmp | Rm | 57.8 | 14.12.23 | 14.12.24 | 100% | 154.89 | - | - | 100% | 154.89 | Phy Completed | Restricted
| 2. Construction of PCC V shape side drain at Ch: 0.000kmp | Rm | 1.57 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 3. Clearance of Landslip | Nos | 20.83 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
41 | Additional requirement for Upgradation of Bethel Veng road at Zemabawk
| 1. Earthwork for Widening (Additional) | Km | 69.54 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 2. RCC Frame Retaining Walls no1 | Rm | 5.2 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| TOTAL = |  | 154.94
IMPROVEMENT OF MUTHI - TUIRIAL LINK ROAD
42 | 1. Widening & Curve Improvement | Km | 134.74 | 14.12.23 | 14.12.24 | 100% | 170.24 | - | - | 100% | 170.24 | On-Going | Restricted
2. Construction of Slab Culvert
| i. Slab Culvert Type-I | Nos | 11.5 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | On-Going | Restricted
3. Construction of Retaining Wall
| i. Retaining Wall Type - I | Rm | 10 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Work in Progress | Restricted
| ii. Retaining Wall Type - II | Rm | 14 | 14.12.23 | 14.12.24 | - |  | - |  | - |  | Not yet started
| TOTAL = |  | 170.24
CONSTRUCTION OF BAMBOO LINK ROAD FROM NAUSEL, CHAMDUR, LUNGSANG, PUMPELHSEI, KAWRBEL
43 | Construction of Nausel - Tuirial Bamboo Link Road | [5 empty] | 261.48 |  | - |  | 261.48
| 1. Formation Cutting | Km | 36.01 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 2. Construction of Slab Culvert | Nos | 59.39 |  |  | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| At chainage between 0.000 to 3.500 Kmp | Nos |  | 14.12.23 | 14.12.24 | - |  | - |  | - |  | Not yet started
| 3. Construction of Retaining Wall |  |  |  |  | 100% |  | - |  | 100% |  | Phy Completed | Restricted
At chainage between 0.000 to 3.500 Kmp
| Retaining Wall | Nos | 30.92 | 14.12.23 | 14.12.24 | - |  | - |  | - |  | Not yet started
44 | Concrete Pavement of Sihphir Neibawih khawhnuai kawng balance | [5 empty] | 261.48 |  |  |  | 261.48
| 1. Concrete Pavement | Rm | 36.28 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
2. Construction of Slab Culvert
| At chainage between 0.000 to 0.503 Kmp | Nos | 21.52 | 14.12.23 | 14.12.24 | - |  | - |  | - |  | Not yet started
| Retaining Wall Type - I | Nos | 13.99
| Retaining Wall Type - II | Nos | 8.2
45 | Construction of Hmunte Road at Muthi
| 1. Formation Cutting | Km | 36.57 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy completed | Restricted
| 2. Construction of Slab Culvert |  |  |  |  | 100% |  | - |  | 100% |  | Phy completed | Restricted
| At chainage between 0.000 to 1.000 Kmp | Nos | 16.57 | 14.12.23 | 14.12.24 | - |  | - |  | - |  | Not yet started
| At chainage between 1.000 to 2.000 Kmp | Nos | 14.5 | 14.12.23 | 14.12.24 | - |  | - |  | - |  | Not yet started
3. Construction of Retaining Wall
At chainage between 0.000 to 2.000 Kmp
| Retaining Wall | Rm | 7.18 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy completed | Restricted
46 | Construction of Chamdur - Kawrbellui Road
| 1. Formation Cutting | Km | 30.5 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| TOTAL = |  | 311.63
CONSTUCTION OF ROAD FROM ZEMABAWK NORTH TO CWC AND MUALZEN
47 | Construction of New Road from Zemabawk North Dinthar Veng to CWC including Protetion Works & Cross Drain | [5 empty] | 246.4 |  | - |  | 246.4
| 1. Formation Cutting | Km | 72.46 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 2. Construction of Slab Culvert Type-I | Nos | 8 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 3. Construction of Slab Culvert Type-II | Nos | 12 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 4. Construction of Slab Culvert Type-III | Nos | 16.94 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 5. Construction of Retaining Wall Type-I | Rm | 25 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
48 | Construction of New Road from Zemabawk North Thlanmual Hnuai to Mualzen including Protetion Works & Cross Drain
| 1. Formation Cutting | Km | 60.12 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
2. Construction of Slab Culvert
| At chainage between 0.000 to 1.500 Kmp | Nos | 28.6 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| At chainage between 1.500 to 3.000 Kmp | Nos | 23.28 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| TOTAL = |  | 246.4
CONSTRUCTION OF ROAD FROM FALKLAND TO GALILEE VIA MITLAMUAL AT ZEMABAWK, AIZAWL
49 | Construction of Widening & New Road from Falkland to Mitlamual including protection Works & Cross Drain | [5 empty] | 134.4 |  | - |  | 134.4
| 1. Widening and New Cutting | Km | 42.16 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 2. Construction of Slab Culvert Type-I | Nos | 2.64 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
50 | Construction of New Road from Zemabawk Galile Vailui to Mitlamual including Protection Works and Cross Drain
| 1. Formation Cutting | Km | 52.09 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 2. Construction of PCC Pavement | Rm | 22.88 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 3. Construction of Slab Culvert Type-I | Nos | 14.63 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| TOTAL = |  | 134.4
CONSTRUCTION OF ROAD FROM FALKLAND TO ZEMABAWK NORTH VIA THUAMPUI
51 | Construction of New Road from Falkland Penniel Road to Thuampui Vengthar and BS Farm to UPC BiakIn at Pi Vani Lui Link Road including Protection Work & Cross Drain (1.00 Km) | [5 empty] | 151.99 |  | - |  | 151.99
| 1. Widening of Road | Rm | 29.22 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 2. Construction of PCC Pavement on BS Farm to UPC BiakIn | Rm | 32.18 | 14.12.23 | 14.12.24 | - |  | - |  | - |  | Not yet started
| 3. Construction of Slab Culvert at Ch : 0.360 Kmp | No | 4.3 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 4. Construction of RCC Link Drain at Ch 0.000-0.112 km | Rm | 25 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 5. Construction of RCC Link Drain With Cover at Ch 0.000 km | Rm | 3.72 | 14.12.23 | 14.12.24 | - |  | - |  | - |  | Not yet started
| 6. Construction of RCC Link Drain With Cover at Ch 0.120 km | Rm | 5.58 | 14.12.23 | 14.12.24 | - |  | - |  | - |  | Not yet started
52 | Construction of New Road RAY to BS Farm Falkland including Protection Works and Cross Drain (0.800Km) | [7 empty] | -
| 1. Lowering and Widening | Rm | 10.14 | 14.12.23 | 14.12.24 | 100% | - | - |  | 100% |  | Phy Completed | Restricted
| 2. Construction of PCC Pavement on RAY to BS Farm Falkland | Rm | 10.48 | 14.12.23 | 14.12.24 | - |  | - |  | - |  | Not yet started
| 3. Construction of Retaining Wall | Rm | 8.84 | 14.12.23 | 14.12.24 | - |  | - |  | - |  | Not yet started
| 4. Construction of V-Shape | Rm | 4.2 | 14.12.23 | 14.12.24 | - |  | - |  | - |  | Not yet started
| 5. Construction of missing Link at BCM Multipurepose Centre at Falkland Veng | Rm | 6.34 | 14.12.23 | 14.12.24 | - |  | - |  | - |  | Not yet started
53 | Construction of Step near Pu Ringdika's House | Rm | 1.4 | 14.12.23 | 14.12.24 | - |  | - |  | - |  | Not yet started
54 | Repairing of Kailiana Concrete Pavement Road at Zemabawk North | Rm | 10.6 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| TOTAL = |  | 152
CONSTRUCTION OF TUIRIAL AIRFIELD TO MUTHI AND ZOKHAWSANG AGRICULTURE
55 | Construction of New Road from Tuirial Airfield Runway to Muthi lui Lalchhuana Leilet including Protetion Works & Cross Drain | [5 empty] | 107 |  | - |  | 107
| 1. Formation Cutting | Km | 40.94 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 2. Construction of RCC Slab Culvert | No | 66.58 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| TOTAL = |  | 107.52
CONSTRUCTION OF ROAD FROM THUAMPUI TO NH - 6 (ZEMABAWK)
56 | Construction of Link Drain near Pi Diki House at Sihphir | Rm | 10 | 14.12.23 | 14.12.24 | 100% | 179.18 | - | - | 100% | 179.18 | Phy Completed | Restricted
57 | Pavement of AR Complex at Zokhawsang | Km | 59 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
58 | Resurfacing of Women Polytechnic Internal road at Durtlang | Km | 27 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
59 | Improvement of Dinthar Veng to Muthi Lui Road (Balance Portion) at Zemabawk
| 1. Concrete Pavement | Rm | 31.5 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 2. Construction of RCC Slab Culvert No.1 | No | 6.3 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 2. Construction of RCC Slab Culvert No.2 | No | 5.91
| 3. Construction of Retaining Wall | Rm | 5 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 4. Construction of U shape Side Drain | Rm | 8.29 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
60 | Resurfacing of Sihpui to Ramhlun Vengthar Bus Turning Point at Ch : 1.052 - 1.357 km | m² | 11 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
61 | Patch repair of Vaivakawn to MZU via Zonuam. | m² | 18 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| TOTAL = |  | 182
UPGRADATION OF INTERNAL ROADS AT DURTLANG, BAWNGKAWN, CHALTLANG, ZUANGTUI, RAMHLUN & RAMTHAR
62 | Construction of Rectangular Side Drain with cover at Tatkawng Veng | Rm | 1.68 | 14.12.23 | 14.12.24 | 100% | 134.4 | - | - | 100% | 134.4 | Phy Completed | Restricted
63 | Construction of Concrete Pavement of Durtlang tlak lam Thlanmual Road | Rm | 20 | 14.12.23 | 14.12.24 | - |  | - |  | - |  | Not yet started
64 | Construction of Concrete Pavement of Gosen Veng Kawngpui at Zuangtui | Rm | 7 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
65 | Construction of PCC Flooring at Rivenga Road at Muanna Veng | Rm | 10 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
66 | Construction of PCC Flooring Internal Road - Zamliana Road to K.Thankunga Road at Selesih | Rm | 5 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
67 | Vantlang Step near K.Thankunga House at Selesih | Rm | 5 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
68 | Construction of PCC Flooring Laitan Ramthar Biak In lane at Leitan Ramthar | Rm | 10 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
69 | Construction of Concrete Pavement on Bawngkawn Thlanmual to Thuampui Road | Rm | 22.87 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
70 | Steel Grate Cover Side Drain on PC.Malsawma House to Rev.C.Vanlalhruaia House at Ramhlun South | Rm | 2.2727 | 14.12.23 | 14.12.24 | - | - |  |  |  |  | On-Going
71 | Construction of RCC Foot Step near PC.Lalzuiliana House Ramthar | Rm | 14.6908 | 14.12.23 | 14.12.24 | - | - | 0% |  | 0% |  | Not yet started
72 | Construction of RCC Link Drain near PC.Lalzuiliana House at Ramthar | Rm | 8.3752 | 14.12.23 | 14.12.24 | - | - | 0% |  | 0% |  | Not yet started
73 | Steel Grate Cover Side Drain on PC Malsawma House to Rev. C.Vanlalhruaia House at Ramhlun South | Rm | 8.04 | 14.12.23 | 14.12.24 | - | - | - | - | - | - | Not yet started
74 | Construction of RCC Foot Step near PC.Lalzuiliana House Ramthar | Rm | 16.58 | 14.12.23 | 14.12.24 | - |  | - |  | - |  | Not yet started
75 | Construction of RCC Link Drain near PC.Lalzuiliana House at Ramthar | Rm | 8.42 | 14.12.23 | 14.12.24 | - |  | - |  | - |  | Not yet started
76 | Construction of Breast Wall Below PC.Laltanpuia House at Ramthar North | Rm | 7.37 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
77 | Construction of Breast Wall near Pu.Lalrammuana Ralte House at Ramthar North | Rm | 5.76 | 14.12.23 | 14.12.24 | - |  | - |  | - |  | Not yet started
78 | Construction of RCC Foot Step near Pi.Manmawii House at Ramhlun South | Rm | 6.68 | 14.12.23 | 14.12.24 | - |  | - |  | - |  | Not yet started
| TOTAL = |  | 134.4
IMPROVEMENT OF ROAD FROM DURTLANG LEITAN TO DURTLANG RAMTHAR AT DURTLANG
79 | Construction of Road at Selesih. Aizawl (Sh: Construction of Concrete Pavement and Culvert etc) | [5 empty] | 224.16 |  | - |  | 224.16
| 1. Concrete Pavement of Pu Dinga Road | Rm | 5 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
80 | Improvement of road at Durtlang North, Aizawl. (Sh: Construction of Concrete Pavement etc)
| 1. Construction of Concrete Pavement & Cross Drain on Vungkhama road inlcuding Chhingtei Road at Durtlang North | Rm | 15 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 2. Construction of Concrete Pavement of Durtlang North Thlanmual | Rm | 10 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
81 | Improvement of road at Durtlang, Aizawl. (Sh : Construction of Concrete Pavement, Cross Drain with cover, V Shape Side Drain, slab culvert and link Drain etc) | [5 empty] | - |  | -
| 1. Construction of PCC V shape Side Drain at Centenary Road & Women Polytechnic approach road at Durtlang | Rm | 5 | 14.12.23 | 14.12.24 | - |  | - |  | - |  | Not yet started
| 2. Concrete Pavement of Lalnu road at Suaka Veng, Durtlang (Balance Portion) | Rm | 5.4 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 3. Construction of Cross Drain with cover on Durtlang Field | Rm | 0.99516 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 4. Construction of Step including Link Drain at Centenary Road, Durtlang | Rm | 20 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
82 | Construction and Improvement of road at Durtlang Leitan, Aizawl.(Sh : Construction of Concrete Pavement, RCC frame Retaining Wall, Cross Drain with cover, U Shape Side Drain and link Drain etc)
| 1. Construction of PCC V Shape Side and Retaining Wall at Gospel Thunder Team compound, Durtlang Leitan | Rm | 20 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 2. Construction of RCC Frame RW at Zotui Road, Durtlang Leitan | Rm | 3.5 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 3. Patch repair of Durtlang Leitan SIRD Road | Km | 5.05 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
83 | Improvement of Road at Durtlang Ramthar, Aizawl (Sh : Construction of Concrete Pavement, Cross Drain and Re-Surfacing) | [5 empty] | - |  | -
| 1. Resurfacing of 3rd Lane at Durtlang Ramthar | Rm | 29.5 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 2. Concrete pavement of approach road to Durtlang Ramthar Prebyterian Church including cross drainage | Km | 30.5 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
84 | Improvement of Road at Chaltlang Lily veng, AizawL (Sh : Widening . of road, Construction of Concrete Pavement, RCC R/Wall and Re-Surfacing etc)
| 1. Resurfacing of Chaltlang Lily Veng internal road (Balance) | Km | 3 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 2. Reconstruction of step from State Guest House to Lily Veng internal road | Rm | 6 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 3. Construction of RCC Balcony & Masonry Step near R.lalmanga House at Chaltlang Lily Veng | Rm | 14 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
85 | Improvement of Road at Chaltlang, Aizawl. (Sh: Junction improvement. Construction of Concrete Pavement, U Shape drain, Retainning Wall & Step) | [5 empty] | - |  | - |  | -
| 1. Concrete Pavement of Road near F.Malsawma Residence at Chaltlang | Rm | 2.5 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 2. Construction of Retaining Wall & Concrete pavement on AMC Road at Dingdi Veng, Chaltlang | Rm | 9.7 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
86 | Improvement of Road at Bawngkawn, Aizawl. (Sh : Construction of Balcony, Link Drain, Retaing Wall & Concrete Pavement)
| 1. Construction of retaining Wall near Pu. Salemthara Residence at Brigade, Bawngkawn | Rm | 2.6 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 2. Concrete Pavement of Liansailova road, Bawngkawn | Rm | 10 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 3. Concrete Pavement of Shalom Road at Bawngkawn Hmar Veng (Balance Portion) | Rm | 10 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 4. Concrete Pavement on Upper Bawngkawn Hmar Veng | Rm | 4.5 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
87 | Construction of additional protection work at Bethel Veng | Rm | 13 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| TOTAL = |  | 225.2452
IMPROVEMENT OF ROAD FROM ZEMABAWK TO LUNGBIAL ROAD IN THE LOCALITY OF ZEMABAWK AT AIZAWL
88 | CONSTRUCTION OF ROAD AT SIHPHIR | [5 empty] | 213.41 |  | - |  | 213.41
| i.Concrete pavement of approach road to Sihphir Rescue Center road at Sihphir Kawnveng | Rm | 8.8 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| ii.Formation Cutting , Concrete Pavement & Step of Sunhlu tlang (Prayer Mountain) at Sihphir Tlang Veng | Rm | 7.9 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| iii.Construction of Step including retaining wall near Pu Zakhuma House at Sihphir field veng | Rm | 3.66 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| iv.Construction of link Drain with cover near Pi Liani House at Sihphir Dinthar | Rm | 1.74 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| v.Construction of Link drain near Pu H.Lalfakzuala, Sihphir Dinthar | Rm | 2.61 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
89 | CONSTRUCTION OF CONCRETE PAVEMENT AT ZUANGTUI, AIZAWL
| i.RCC Balcony Gosen Veng to 132 KV substation at Zuangtui | Rm | 26.13 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
90 | CONCRETE PAVEMENT RIVENGA ROAD AT MUANNA VENG, AIZAWL
| i.Concrete Pavement of Rivenga Road at Muanna Veng | Rm | 7.3 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
91 | CONSTRUCTION OF ROAD AT MUTHI, AIZAWL | [7 empty] | - |  | -
| i.Concrete Pavement at ch:0.000 - 0.715kmp Muthi peng to kawn | Rm | 8.6 | 14.12.23 | 14.12.24 | 100% | - | - |  | 100% |  | Phy Completed | Restricted
92 | CONSTRUCTION OF ROAD AT NAUSEL
| i.Concrete Pavement at Nausel Thlanmual kawng | Rm | 8.2 | 14.12.23 | 14.12.24 | 100% | - | - |  | 100% |  | Phy Completed | Restricted
93 | IMPROVEMENT OF ROAD AT SIHPHIR VENGHLUN
| i.Construction of Retaining Wall at Thuampui Selesih road at Ch:4.300Kmp, Durtlang | Rm | 6.14 | 14.12.23 | 14.12.24 | 100% | - | - |  | 100% |  | Phy Completed | Restricted
94 | Construction of New Road from Zemabawk North Thlanmual to Thuampui Thlanmual including Protetion Works & Cross Drain
| i. Formation Cutting | Km | 51.36 | 14.12.23 | 14.12.24 | 100% | - | - |  | 100% |  | Phy Completed | Restricted
| ii. Construction of RCC Slab Culvert | No | 33.04 | 14.12.23 | 14.12.24 | 100% | - | - |  | 100% |  | Phy Completed | Restricted
95 | CONSTRUCTION OF ROAD AT FALKLAND, AIZAWL
| i.Construction of PCC Pavement on Local Council Road to RAY at Falkland | Rm | 27.79 | 14.12.23 | 14.12.24 | - | - | - | - | - | - | Not yet started
| ii.Construction of PCC Pavement on Rabboni Road at Falkland | Rm | 5.1404 | 14.12.23 | 14.12.24 | - | - | - | - | - | - | Not yet started
| iii.Construction of PCC Pavement on Local Council Road Falkland | Rm | 11.332 | 14.12.23 | 14.12.24 | - | - | - | - | - | - | Not yet started
| iv.PCC Pavement on Approach Road to Vai Lui via Rev Lalsangliana's House at Falkland Veng | Rm | 5.7395 | 14.12.23 | 14.12.24 | - | - | - | - | - | - | Not yet started
| TOTAL = |  | 215.4818
SUB - DIVISION - III
CONSTRUCTION OF PCC PAVEMENT AT SIHHMUI TO NH-54. (LENGTH = 7.00Kms, PCC PAVEMENT = 7.00Kms)
96 | Widening of road from Law college to PCI road at Luangmual, Aizawl (Sh: Earth Work for Widening of existing road) | Rm. | 11.95 | 2023-12-14 | 2024-12-14 | 100% | 194.63 | - | - | 100% | 194.63 | Phy Completed | Restricted
97 | Improvement & Upgradation of road at Chawlhhmun, Aizawl |  | 26 | 2023-12-14 | 2024-12-14
| Sh: 1. Construction of PCC Pavement of Pu Muantea's road at Chawlhhmun | Rm. |  |  |  | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 2. Construction of PCC Pavement near Pu Fabiana's house at Chawlhhmun | Rm. |  |  |  | 100% |  | - |  | 100% |  | Phy Completed | Restricted
98 | Improvement & Upgradation of road at Zotlang, Aizawl |  | 20.29 | 2023-12-14 | 2024-12-14 |  | - |  | - |  | -
| Sh: 1. Construction of RCC Pavement at Zotlang to Zohnuai | Rm. |  |  |  | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 2. Construction of Retaining Wall for Pi Romawii Approach Road at Zotlang | Rm. |  |  |  | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 3. Construction of RCC Pavement at Zotlang to Zohnuai Biak In | Rm. |  |  |  | 100% |  | - |  | 100% |  | Phy Completed | Restricted
99 | Construction of approach road (RCC Pavement) to Community Hall (NH 44A) at Sihhmui | Rm. | 15.91 | 2023-12-14 | 2024-12-14 | 100% |  | - |  | 100% |  | Phy. Completed | Restricted
100 | Improvement & Upgradation of road from PCI to Anganwadi at Lungverh |  | 77.98 | 2023-12-14 | 2024-12-14
| Sh: 1. Construction of RCC Pavement from PCI to Anganwadi at Lungverh | Rm. |  |  |  | 100% |  | - |  | 100% |  | Phy. Completed | Restricted
| 2. Construction of RCC Slab Culvert at Thlanmual kawr | Rm. |  |  |  | 100% |  | - |  | 100% |  | Phy. Completed | Restricted
| 3. Construction of RCC Slab Culvert at Pu Rinnunga kawmthlang | Rm. |  |  |  | 100% |  | - |  | 100% |  | Phy. Completed | Restricted
| 4. Retaining wall at F Suakliana Kawmchhak | Rm. |  |  |  | 100% |  | - |  | 100% |  | Phy. Completed | Restricted
101 | Rangvamual internal road | Rm | 23.27 |  |  | 100% |  | - |  | 100% |  | Phy. Completed | Restricted
102 | Phunchawng internal road | Rm | 19.23 |  |  | 100% |  | - |  | 100% |  | Phy. Completed | Restricted
| TOTAL = |  | 194.63
IMPROVEMENT OF INTERNAL ROADS AT HUNTHAR, CHANMARI WEST, RANGVAMUAL, PHUNCHAWNG & CHHINGA VENG. (IMPROVEMENT OF ROADS PCC PAVEMENT = 20.00 KMS, PAVEMENT = 5.00 KMS, LINK DRAIN = 100.00M)
103 | Patch Repair and Seal Coating of Approach Road to Tanhril, Aizawl | Rm | 23.08 | 2023-12-14 | 2024-12-14 | 100% | 59.03 | - | - | 100% | 59.03 | Phy. Completed | Restricted
104 | Construction of PCC Pavement of Approach Road to Tawngtai Bethel Camping Centre, Sakawrtuichhun, Aizawl | Rm. | 9.49 | 2023-12-14 | 2024-12-14 | 100% |  | - |  | 100% |  | Phy. Completed | Restricted
105 | Rigid Pavement of Gan Sabra Road | Rm. | 19.33 | 2023-12-14 | 2024-12-14 | 100% |  | - |  | 100% |  | Phy. Completed | Restricted
106 | Construction of PCC Pavement of Road from Saikaphleia' House to Muanthanga's House at Lungverh. Length = 120.00Rm. | Rm. | 9.51 | 2023-12-14 | 2024-12-14 | 100% |  | - |  | 100% |  | Phy. Completed | Restricted
| TOTAL = |  | 61.41
CONSTRUCTION OF LUNGHLU ROAD AT CHANMARI WEST AIZAWL (Length = 4.00Kms, Ew = 4.00Kms, Pavement = 4.00Kms, Side Drain = 4500m, R/W 30m, Culvert = 10.Nos)
107 | Construction of RCC Frame structure Retaining Wall I at Lunghlu Road, Hunthar | Rm | 14.49 | 2023-12-14 | 2024-12-14 | 100% | 162.37 | - |  | 100% | 162.37 | Phy. Completed | Restricted
108 | Patch repair and Seal coat of MUP Road at Chanmari West, Aizawl | Rm | 11.5532 | 2023-12-14 | 2024-12-14 | 100% |  | - |  | 100% |  | Phy. Completed | Restricted
109 | Patch repair and Seal Coat from BT Bakery to Protective Home Via Zarkawt Thlanmual | Rm | 29.9487 | 2023-12-14 | 2024-12-14 | 100% |  | - |  | 100% |  | Phy. Completed | Restricted
110 | Construction of RCC Road at Methodist mual Turning Point to Edenthar Anganwadi Centre No. 1 at Edenthar | Rm | 8.76 | 2023-12-14 | 2024-12-14 | 100% |  | - |  | 100% |  | Phy. Completed | Restricted
111 | Construction of RCC Link drain near Hotel Platinum at Zarkawt | Rm | 0.84926 | 6.12.2023 | 9.12.2023 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
112 | Improvement of Zarkawt Valley Approach Road Phase-II | Rm | 47.0033 | 19.2.2024 | 29.2.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
113 | Construction of Retaining wall near Babula's House at Chanmari | Rm | 13.28 | 5.2.2024 | 14.2.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
114 | Repair of Link Drain with Cover near J.Thangdailova House at Electric Veng | Rm | 9.64 | 8.2.2024 | 16.2.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
115 | Construction of New Cemetery Road at Electric Veng | Rm | 28 | 2.2.2024 | 15.2.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| TOTAL = |  | 163.5244
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY, 2026 UNDER ARND
Name of Work : Construction of Approach Road to IGC Complex, Luangmual under SASCI Part V of 2024-2025 | [7 empty] | Name of Contractor: Zonunpuii, Kolasib Hmar Veng
Agreement Amount : ₹ 4,80,67,489.00 | [7 empty] | Date of Commencement: 03.07.2025
Agreement No.: AGM-2/SE-CC/PWD/2025-2026 Dt. 18.06.2025 | [7 empty] | Target date of Completion: 03.07.2026
Name of Division : Aizawl Road North Sub-Division-III
Source of funding: SASCI-V
Overall Physical Achievement : 41.99%
Sl. No. | Name of Project | Unit |  | Approved Cost (Rs. in lakh) | Date of Commencement | Target date of completion | Cumulative Progress at the end of last month |  | Achievement works during the month |  | Overall cummulative achievement |  | Remarks | Mode of contract
[7 empty] | Phy. | Fin. | Phy. | Fin. | Phy. | Fin.
1 | 3 | 3 |  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Improvement of IGC, Luangmual |  |  | 5: 2025-07-03; 6: 2026-07-03; 8: 140.29; 10: 58.79; 12: 199.08
a | Earthwork | 200 | Rm | 4: 978568; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed; 14: Item Rate
b | Flexible Pavement | 1500 | Rm | 4: 20821135; 7: 0%; 9: 0%; 11: 0%
c | Re-construction of slabs culvert | 4 | No. | 4: 988218; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed
d | Hume Pipe Culvert | 5 | No. | 4: 1545232; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed
e | Retaining Wall | 60 | Rm | 4: 1773085; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed
f | RCC Line side drain with cover | 200 | Rm | 4: 1374490; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed
g | Trapezoidal side drain | 500 | Rm | 4: 1632485; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed
2 | Improvement of road from Tanhril Presbyterian Church to MZU
a | Flexible Pavement | 800 | Rm | 4: 6170189; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed; 14: Item Rate
b | Hume Pipe Culvert | 2 | No. | 4: 996811; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed
3 | Improvement of road from Tlana Lungdawh kawn to PWD Site |  |  | 5: 2025-07-03; 6: 2026-07-03; 8: -; 10: -; 12: -
a | Earthwork | 980 | Rm | 4: 1456657; 7: 20%; 9: 10%; 11: 30%; 13: Work in Progrees; 14: Item Rate
b | Rigid Pavement | 1000 | Rm | 4: 7526950
c | Flexible Pavement | 800 | Rm | 4: 1308555
d | Hume Pipe Culvert | 3 | No. | 4: 1495114; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed; 14: Item Rate
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY, 2026 UNDER ARND
Name of Work : Improvement of Road from Ainawn to Tuithum |  |  |  | 8: Name of Contractor: F. Lalmalsawma, Tuikual
Agreement Amount : ₹ 16,35,30,525.00 |  |  |  | 8: Date of Commencement: 15.07.2025
Agreement No.: AGM-3/SE-CC/PWD/2025-2026 Dt. 01.07.2025 |  |  |  | 8: Target date of Completion: 15.07.2026
Name of Division : Aizawl Road North Sub-Division-III
Source of funding: SASCI-V
Overall Physical Achievement : 9.00%
Sl. No. | Name of Project | Unit |  | Approved Cost (Rs. in lakh) | Date of Commencement | Target date of completion | Cumulative Progress at the end of last month |  | Achievement works during the month |  | Overall cummulative achievement |  | Remarks | Mode of contract
[7 empty] | Phy. | Fin. | Phy. | Fin. | Phy. | Fin.
1 | 2 | 3 |  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Earthwork | 4682 | Rm | 20371452 | 2025-07-15 | 2026-07-15 | 55% | 244.9 | 5% | - | 60% | 244.9 | Work in Progress | Item Rate
2 | RCC side drain | 2000 | Rm | 4: 7896319
3 | RCC Slab Culvert | 4 | No. | 4: 2912158
4 | Hume Pipe Culvert | 5 | No. | 2614215 |  |  | 35% |  | 5% | - | 40% | - | Work in Progress | Item Rate
5 | Retaining Wall | 200 | Rm | 9720546 |  |  | 15% |  | 0% | - | 15% | - | Work in Progress | Item Rate
6 | RCC Frame Structure Retaining Wall | 70 | Rm | 4: 3729602
7 | Minor Bridge | 4 | No. | 4: 23515882
8 | Rigid Pavement | 2380 | Rm | 4: 74239201
9 | Flexible Pavement | 2000 | Rm | 4: 18531150
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY, 2026 UNDER ARND
Name of Work : Construction of Various Earth Retaining and Drainage Structure for Mitigation of Vaivakawn Zohnuai Subsidence Areas |  |  |  | 8: Name of Contractor: Jenny Lalthansangi, Vavakawn Zohnuai
Agreement Amount : ₹ 2,96,11,018.00 |  |  |  | 8: Date of Commencement: 15.07.2025
Agreement No.: AGM-4/SE-CC/PWD/2025-2026 Dt. 01.07.2025 |  |  |  | 8: Target date of Completion: 01.03.2026
Name of Division : Aizawl Road North Sub-Division-III
Source of funding: SASCI-V
Overall Physical Achievement :
Sl. No. | Name of Project | Unit |  | Approved Cost (Rs. in lakh) | Date of Commencement | Target date of completion | Cumulative Progress at the end of last month |  | Achievement works during the month |  | Overall cummulative achievement |  | Remarks | Mode of contract
[7 empty] | Phy. | Fin. | Phy. | Fin. | Phy. | Fin.
1 | 2 |  | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Breast Wall on lower side of Pu Sangthanmawia's Land. | 20 | Rm | 29611018 | 2025-07-15 | 2026-03-01 | 100% | 119.98 | - | - | 100% | 119.98 | Phy Completed | Item rate
2 | Construction of Breast Wall on Uphill side of RK Road. | 30 | 3: Rm; 7: 0%; 9: 20%; 11: 20%; 13: Work in Progress
3 | Construction of Composite Retaining Wall (Section 1) above NH-6 | 28 | 3: Rm; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed
4 | Construction of Composite Retaining Wall(Section 2) above NH-6 | 28 | 3: Rm; 7: 90%; 9: 10%; 11: 100%; 13: Phy Completed
5 | Construction of Breast Wall above NH-6(below RK Road) | 25 | 3: Rm; 7: 100%; 9: 0%; 11: 100%; 13: Work in Progress
6 | Construction of Breast Wall on Uphill Side of NH-6 (Near Link Drain) | 15 | 3: Rm; 7: 100%; 9: 0%; 11: 100%; 13: Work in Progress
7 | Construction of RCC Line Drain below NH-6(50 m) | 50 | 3: Rm; 7: 90%; 9: 5%; 11: 95%; 13: Work in Progress
8 | Construction of RCC Side Drain along NH-6 (Near Culvert,20 m) | 20 | 3: Rm; 7: 90%; 9: -; 11: 90%; 13: Work in Progress
9 | Construction of Retaining Wall at Nutumi Road | 35 | Rm | 29611018 | 2025-07-15 | 2026-03-01 | 60% |  | 10% | - | 70% | - | Work in Progress | Item rate
10 | Construction of Hume Pipe Culvert at MZU Road | 1 | 3: No.; 7: 0%; 9: 0%; 11: 0%; 13: Not yet started
11 | Construction of side drain at Various places | 1217 | 3: Rm; 7: 55%; 9: 5%; 11: 60%; 13: Work in Progress
12 | Clearance of link drain at various places | 122 | 3: Rm; 7: 40%; 9: 60%; 11: 100%; 13: Phy Completed
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY, 2026 UNDER ARND
Name of Work : Restoration Of Damage Due To Cyclone Remal Under Aizawl Road North Division, Aizawl Road South Division And Hmuifang Division |  |  | 7: Name of Contractor : Fredy Vanlalngila, Dinthar-I
Agreement Amount : ₹ 11,24,97,994.21 |  |  | 7: Date of Commencement : 27.06.2025
Agreement No.: 4/CE-HW/2025-2026 Dt. 01.06.2025 |  |  | 7: Target date of Completion :27.01.2026
Name of Division : Aizawl Road North Division
Source of funding: Cyclone Remal
Sl. No. | Name of Project | Unit | Approved Cost (Rs. in lakh) | Date of Commencement | Target date of completion | Cumulative Progress at the end of last month |  | Achievement works during the month |  | Overall cummulative achievement |  | Remarks | Mode of contract
[6 empty] | Phy. | Fin. | Phy. | Fin. | Phy. | Fin.
1 | 2 |  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Retaining Wall below Zoramthanga's House | Rm | 20 | 2025-07-01 | 2026-01-31 | 75% | 193.53 | 25% | 102 | 100% | Rs. 295.53 lakhs bill forwarded to Executive Engineer, Aizawl Road South Division for payment being the Nodal Officer for payment | Phy Completed | Item Rate
2 | Restoration of H/P Culvert at Falkland | Nos | 4: 5; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed; 14: Item Rate
3 | Restoration of Breast Wall at Armed Veng South | Rm | 4: 6; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed; 14: Item Rate
4 | Restoration of Retaining Wall Collapsed at Ramthar North | Rm | 4: 18.01; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed; 14: Item Rate
5 | Construction of Retaining Wall at Falkland | Rm | 4: 3; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed; 14: Item Rate
6 | Construction of Retaining Wall at Thuampui Vengthar | Rm | 4: 8; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed; 14: Item Rate
7 | Construction of Gabion Wall on Darnamlui for Restoration of formation edge collapsed at Ramthar North, Aizawl | Rm | 4: 90.44; 7: 24%; 9: 31%; 11: 55%; 13: Work in Progress; 14: Item Rate
8 | Construction of Breast wall at Berawtlang | Km | 20.58 | 1.7.2025 | 30.7.2025 | 100% | 193.53 | 0% | 102 | 100% | Rs. 295.53 lakhs bill forwarded to Executive Engineer, Aizawl Road South Division for payment being the Nodal Officer for payment | Phy Completed | Item Rate
9 | Construction of Breast wall at Thuampui to Selesih road at Ch:6.000kmp | Km | 21.08 | - | - | 100% |  | 0% |  | 100% |  | Phy Completed | Item Rate
10 | Widening of Lungbial road for diversion of collapsed Balcony on approach road to Berawtlang | Km | 41.06 | - | - | 90% |  | 0% |  | 90% |  | Work in Progress | Item Rate
11 | Construction of retaining wall near Pu Lalzarzoliana's house at Lungbial | Km | 2 | 1.7.2025 | 22.7.2025 | 100% |  | 0% |  | 100% |  | Phy Completed | Item Rate
12 | Construction of Reataining wall at Thuampui to Selesih at Ch:11.800 kmp | Km | 2.43 | 1.7.2025 | 30.7.2025 | 100% |  | 0% |  | 100% |  | Phy Completed | Item Rate
13 | Construction of RCC balcony at Gosen veng at Zuangtui | Km | 17.89 | - | - | 100% |  | 0% |  | 100% |  | Phy Completed | Item Rate
14 | Construction of RCC Rectangular side drain at RIPANS at Zemabawk | Km | 22.01 | - | - | 100% |  | 0% |  | 100% |  | Phy Completed | Item Rate
15 | Construction of Retaining wall at Thuampui to Selesih road at Ch:2.200 kmp | Km | 7.98 | 1.7.2025 | 18.7.2025 | 100% |  | 0% |  | 100% |  | Phy Completed | Item Rate
16 | Repair of Culvert and Retaining Wall @ ch. 3.900 Kmp at MZU Road | Rm | 3.61 | 2025-06-27 | 2026-01-27 | 100% |  | 0% |  | 100% |  | Phy Completed | Item Rate
17 | Construction of Retaing Wall @ ch. 6.325 Kmp at MZU Road | Rm | 4: 4.14; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed; 14: Item Rate
18 | Construction of Retaing Wall at approach road to Tanhril at 0.200 Kmp | Rm | 4: 3.61; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed; 14: Item Rate
19 | Construction of Retaining Wall @ ch. 1.600 Kmp on NH-54 to Sakawrtuichhun Road | Rm | 4: 7.88; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed; 14: Item Rate
20 | Construction of Retaining Wall @ ch. 0.980 Kmp on Zohnuai to Ropaiabawk road | Rm | 11.77 | 2025-06-27 | 2026-01-27 | 100% | 193.53 | 0% | 102 | 100% | Rs. 295.53 lakhs bill forwarded to Executive Engineer, Aizawl Road South Division for payment being the Nodal Officer for payment | Phy Completed | Item Rate
21 | Construction of Retaining Wall @ ch. 0.200 Kmp on NH-54 to Sakawrtuichhun Road | Rm | 4: 9.44; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed; 14: Item Rate
22 | Construction of Retaining near Pu B. Lalhmingsanga's house at Zonuam | Rm | 4: 1.84; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed; 14: Item Rate
23 | Construction of Retaining Wall at MUP road, Chanmari West | Rm | 4: 6.02; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed; 14: Item Rate
24 | Construction of Retaining Wall @ ch. 1.550 Kmp on Zohnuai to Ropaiabawk Road | Rm | 4: 7.1; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed; 14: Item Rate
25 | Construction of Retaining Wall @ ch. 1.150 on Zohnuai to Ropaiabawk road | Rm | 4: 10.05; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed; 14: Item Rate
26 | Restoration of Sinking portion near Sangthanmawia's house, Vaivakawn | Rm | 4: 70.45; 7: 40%; 9: 60%; 11: 100%; 13: Phy Completed; 14: Item Rate
27 | Construction of Retaining Wall near Pi Zaihnuni's house at Chawnpui | Rm | 4: 5.88; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed; 14: Item Rate
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY, 2026 UNDER ARND
Name of Work : Restoration Of Damage Due To Cyclone Remal Under Aizawl Road North Division (Part-II) And National Highway Division-III |  |  | 9: Name of Contractor : Kevin Vanlaltlana, Bungkawn
Agreement Amount : ₹ 11,24,97,994.21 |  |  | 9: Date of Commencement : 13.06.2025
Agreement No.: 4/CE-HW/2025-2026 Dt. 01.06.2025 |  |  | 9: Target date of Completion :13.01.2026
Name of Division : Aizawl Road North Sub-Division-III
Source of funding: Cyclone Remal
Overall Physical Achievement : 100%
Sl No | Name of Project | Unit |  | Approved Cost (Rs. in lakh) | Date of Commencement | Target date of completion | Cumulative Progress at the end of last month |  | Achievement works during the month |  | Overall cummulative achievement |  | Remarks | Mode of contract
[7 empty] | Phy. | Fin. | Phy. | Fin. | Phy. | Fin.
1 | 2 | 3 |  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Improvement of side drain and cross drain at Zotlang internal road | 30 | Rm | 259355.69 | 2025-06-13 | 2026-01-13 | 100% | - | 0% | - | 100% | Rs. 16.14 lakhs bill forwarded to Executive Engineer, National Highway Division - III, for payment being the Nodal Officer for payment | Phy Completed | Item Rate
2 | Construction of V shape side drain from Lalhmingliana Hnamte house to T. Lalzapi's house at Zotlang | 100 | Rm | 4: 386896.83; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed; 14: Item Rate
3 | Construction of V shape side drain from C. Thanchhuma house to Rosiamliana Ralte's house at Zotlang | 40 | Rm | 4: 154811.1; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed; 14: Item Rate
4 | Construction of drain below Pu Lalduhawma's house at Chawlhhmun | 77 | Rm | 4: 812604.91; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed; 14: Item Rate
Sr. Executive Engineer, PWD.,
Aizawl Road North Division,
Aizawl

## ARSD
MONTHLY PROGRESS REPORT UNDER AIZAWL ROAD SOUTH DIVISION, PWD
FOR THE MONTH OF JANUARY 2026
Sl. No. | Name of Schemes | Unit | Approved Cost (Rs in Lakh) | Date of Commencement | Target Date of Comple-tion | Cumulative Progress at the end of last month |  | Achievement of works during the month |  | Overall Cumulative achievement |  | Remarks | Mode of Tender
| Name of Works / Project |  |  |  |  | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
I | SEDP (2019-2020)
1 | Const.of Approach Road to Aizawl College at Mualpui | Rm | 415 | 2021-07-26 | 2022-04-26 | 73% | 300 |  |  | 73% | 300 | On Going ES was accorded vide No.B.12031/17/2019-PWD(T) Dt.26.3.2020 (Rs.100 lakhs); No.G.20016/3/2021-FBT Dt.7.10.2021 (Rs.100 lakhs) and No. B.12031/29/2021-PWD(T) dt. 01.03.2023 (Rs. 100 lakhs) respectively, which totalled Rs.300 out of Rs. 415.00. The remaining balance/ ES was asked for Approval vide No.B.16012/6/22/T(ARS)/I/5 Dt.29th Sept,2022. It was regretted due to Financial Constraint as the year has been declared as year of consolidation vide No. B. 12031/17/2019-PWD(T) dt. 23rd July, 2024. | Item Rate Contract
II | NEDP (2018-2019)
1 | Construction of Bridge on Chhinga Vengthar to Tuithiang road | Rm | 586.36 | 2021-04-19 | 2022-10-31 | 100% | 200 |  |  | 100% | 200 | Physical Works Completed according to Working Estimate E/S Amount of Rs.200.00 Lakh. The remaining ES was asked for Allocation vide No.B.16011/69-C/15/T(ARS)/28 dated: 23rd Jan, 2023 in which balance ES from Higher Authority is awaited. | Restricted tender
III | Central Road Fund
1 | Construction of BUG Bridge over R.Tlawng on Aizawl - Reiek - W.Lungdar Road at 14.800 Kmp | Rm | 757.56 | 10:10 | 31.10.24 | 100% | 750.57 |  |  | 100% | 750.57 | Work Completed | EPC mode
IV | SASCI (2022-2023)
i) | Widening of Approach Road to City Bus Parking at S.Hlimen, Aizawl (Melthum - Hlimen Road) under SASCI 2022-2023. | Rm | 576 | 2023-04-07 | 28.5.25 | 100% | 571.14 |  | 4.86 | 100% | 576 | Work Completed | Restricted tender | 0 | -4.86
V | Strengthening and Improvement of State Highways & Other Roads under Mizoram under Central Circle
1 | Improvement of Aizawl-Reiek-W.Lungdar road | Rm | 124.05 | 2024-11-04 | 2025-03-22 | 100% | 91.38 |  |  | 100% | 91.38 | Work Completed | Departmental | 73.6638 | 73%
2 | Improvement of Sinking Area on Bypass Road at Ch.0+800kmp (Sh. Widening) | Rm | 6.82 | 19:03 | 21:03 | 100% | 0 |  |  | 100% | - | Work Completed | Departmental
VI | Maintenance Action Plan 2025-2026 (3054)
1 | Patch repair of Approach Road to Health Minister Bungalow & Deputy Speaker Bungalow at Tuikhuahtlang | Sqm | 7.46 | 1.09.25 | 19:09 | 100% | 7.03 | - | 0.08 | 100% | 7.11 | Work Completed
2 | Resurfacing of approach road to Damdiai Veng, Tlangnuam Vengthar | Sqm | 3 |  |  | 100% | 2.91 | - | - | 100% | 2.91 | Work Completed
3 | Resurfacing of approach road to Hridaikawn to Power Sub Station | Sqm | 8.94 | 4.09.25 | 29:09 | 100% | 8.74 | - |  | 100% | 8.74 | Work Completed
4 | Resurfacing of Saikai to Multi Farming Co-operative Society at Reiek | Sqm | 3.87 |  |  |  |  | 100% | 3.71 | 100% | 3.71 | Work Completed | Departmental
5 | Resurfacing of Approach road to PHC Via PWD IB at Reiek | Sqm | 4.34 |  |  |  |  | 100% | 4.17 | 100% | 4.17 | Work Completed
6 | Resurfacing of Sikulpuikawn to Mission Veng Presbyterian Church (Saptawni Road) | Sqm | 4.08 | 15.9.25 | 29.9.25 | 100% | 3.96 | - |  | 100% | 3.96 | Work Completed
7 | SMBT of approach road to play field, Tlangnuam | Sqm | 5.18 | 3:09 | 15:09 | 100% | 5.03 | - |  | 100% | 5.03 | Work Completed
8 | Resurfacing of approach road to Pika road | Sqm | 7.53 |  |  | 100% | 7.31 | - |  | 100% | 7.31 | Work Completed
9 | Patch Repair of Approach Road to MLA Quarter at Khatla Bethel Tlang | Sqm | 1.44 | 22.9.25 | 6.10.25 | 100% | 1.4 | - |  | 100% | 1.4 | Work Completed
10 | Patch repair of Venghlui to Bethlehem (Lower) | Sqm | 3.56 | 2:09 | 15:09 | 100% | 3.42 | - | 0.03 | 100% | 3.45 | Work Completed
11 | Construction of Pavement and RCC drain with steel cover near Pu F.Kapsanga building on Bazar Bungkawn to Sikulpuikawn road | Rm | 2.01 | 15.9.25 | 29.9.25 | 100% | 1.94 | - |  | 100% | 1.94 | Work Completed
12 | Reconstruction of Pavement near Pu Lalmuanpuia Punte, MLA Quarter | Sqm | 1.21 | 17:04 | 23:04 | 100% | 1.2 | - |  | 100% | 1.2 | Work Completed
13 | Patch Repair of approach road to Anganwadi Centre, Tlangnuam Vengthar | Sqm | 2.13 | 8:09 | 17:09 | 100% | 2.06 | - |  | 100% | 2.06 | Work Completed
14 | Resurfacing of approach to PHC Lungleng | Sqm | 4.27 |  |  |  | 4.14 |  |  | 100% | 4.14 | Work Completed
15 | Resurfacing of Ailawng Internal Road | Sqm | 5.85 |  |  |  |  | 100% | 5.45 | 100% | 5.45 | Work Completed
16 | Resurfacing of Maubawkkawn to Maubawk Tlangveng | Sqm | 3.7 |  |  |  |  | 30% | 3.55 | 30% | 3.55 | On going work
17 | Pavement of widened portion of road on Khatlakawn to Vety Hospital Road | Rm | 4 | 15.9.25 | 29.9.25 | 100% | 3.88 | - | - | 100% | 3.88 | Work Completed
18 | Patch repair of Venghlui to College Veng | Sqm | 1.48 | 17:09 | 23:09 | 100% | 1.42 | - | 0.01 | 100% | 1.43 | Work Completed | Departmental
19 | Patch repair of Officer Training Centre internal road at Mualpui | Sqm | 2.89 | 3:09 | 16:09 | 100% | 2.78 | - | 0.02 | 100% | 2.8 | Work Completed
20 | Resufacing of approach road to Zobawm Veng Kulikawn | Sqm | 7.4 | 9:09 |  | 100% | 7.18 | - |  | 100% | 7.18 | Work Completed
21 | Patch repair of Tuikhuahtlang Taxi Stand to DC Bungalow | Sqm | 3.04 | 3:09 | 12:09 | 100% | 2.92 | - | 0.03 | 100% | 2.95 | Work Completed
22 | Resurfacing of Nursery to Maubawkkawn | Sqm | 22.73 | 22.9.25 | 21.10.25 | 100% | 21.83 | - | 0.23 | 100% | 22.06 | Work Completed
23 | Resurfacing of approach road to Muanna in, Mualpui, Salem | Sqm | 16.12 | 8:09 |  | 100% | 15.49 |  | 0.16 | 100% | 15.65 | Work Completed
24 | Construction of Retaining Wall at Ch 0.250 Kimp approach road to community hall, Hlimen. | Rm | 7.03 |  |  | 100% | 6.82 | - |  | 100% | 6.82 | Work Completed
25 | Construction of Cross drain at Maubawkkawn | No. | 2.46 | 1.7.25 | 26.7.25 | 100% | 2.38 | - |  | 100% | 2.38 | Work Completed
26 | Improvement of drain at T.Romana College Junction, ITI | Rm | 1.49 | 15:08 | 2:09 | 100% | 1.42 | - | 0.02 | 100% | 1.44 | Work Completed
27 | Extension of culvert at ITI Veng Link Road-II Turning Point | Rm | 3.17 | 1:08 | 2025-08-29 | 100% | 3.05 | - | 0.03 | 100% | 3.08 | Work Completed
28 | Re Construction of Culvert Abutment & Cover slab at ch. 2.450 kmp on Aizawl - Reiek - W.Lungdar road | Rm | 3.71 | 22:09 | 11:10 | 100% | 3.79 | - |  | 100% | 3.79 | Work Completed |  | 0.6641
29 | Construction of Breast Wall on Approach road to Mission Vengthlang Cemetry | Rm | 3.91 | 29:09 | 13:10 | 100% | 3.79 | - |  | 100% | 3.79 | Work Completed
30 | Widening of road by dismantling water tank near Pu Khawlthanseia's House on Kaisara Road | Rm | 3.56 | 24:11 |  | 100% |  |  | 3.42 | 100% | 3.42 | Work Completed
31 | Balcony for road extension on Nursery to Mission Veng via City Hospital Road | Rm | 7.92 | 1.7.25 | 31.7.25 | 100% | 7.69 |  |  | 100% | 7.69 | Work Completed
32 | Extension of RCC Slab Culvert at Ch: 26.700 Kmp on Aizawl-Reiek-W. Lungdar | Rm | 9.55 | 22:09 | 11:10 | 100% | 9.27 | - |  | 100% | 9.27 | Work Completed
33 | Improvement of approach road to Bethlehem Vengthlang thlanmual with PCC flooring | Sqm | 6.74 | 2025-08-13 | 9:09 | 100% | 6.45 | - | 0.07 | 100% | 6.52 | Work Completed
34 | Re-construction of RCC Balcony at approach road to Salem Chhim Veng | Rm | 25 | 2025-08-04 |  | 100% | 24.01 | - | 0.25 | 100% | 24.26 | Work Completed | Departmental
35 | Pothole repair of Aizawl city roads within Aizawl Road South Division | Sqm | 106.8 | 2025-03-04 | 2025-08-30 | 100% | 104.56 |  |  | 100% | 104.56 | Work Completed
36 | Seal Coating of Approach road to Maubawk Cemetry | Sqm | 3.1 |  |  |  |  | 30% | 2.98 | 30% | 2.98 | On going work
VII | PMGSY
1 | Upgradation & Maintenance of Hlimen to Samtlang to Lungleng Road | Rm | 1132.5 | 2024-10-23 | 2026-04-23 | 17% | 0 |  | 0 | 17% | 0 | Contract terminate | Open tender
VIII | Restoration of Damage due to Cyclone Remal under ARSD under SASCI 2024-2025 | Rm | 1170 | 2025-07-02 | 2026-02-02 | 100% | 870.01 | 0% | 132.76 | 100% | 1002.77 | Work In progress
IX | Restoration of Damage due to Cyclone Remal under ARSD
2 | Extension of Culvert at Transport Office at Hlimen | Rm | 6 | 1:09 | 29:09 | 100% |  |  | 6 | 100% | 6 | Work Completed | Departmental
X | Resurfacing of Selected Stretches on Aizawl - Reiek - W. Lungdar Road | Rm | 52.32 | 8:09 | 7:10 | 70% | 50.55 | 30% | 1.77 | 100% | 52.32 | Work Completed | Departmental
XI | Maubawk to MINECO Bypass Road on Western Side under SASCI (2025-2026)
| Formation Cutting | Km | 0.397 |  |  | 100% |  | - |  | 100% |  | Completed
| Pavement Works | Km | 0.261 | [8 empty] | Not yet started
| RCC Slab Culvert | No | 4 | [8 empty] | Not yet started
| Protection Work | [7 empty] | 48.38 |  | 48.38
| a) Retaining Wall | Rm | 218 |  |  | 60% |  | 10% |  | 70% |  | On going
| b) Breast Wall | Rm | 218 |  |  |  |  | 30% |  | 30% |  | On going
| Construction of RCC Balcony Roadway | Rm | 96 | [8 empty] | Not yet started
XII | Resurfacing leh Road within Aizawl City under Aizawl Road South Division | Rm | 2231.39 |  |  |  |  | 65% |  | 65% |  | On going | Restricted Tender
.
Sr.Executive Engineer, PWD;
Aizawl Road South Division,
Aizawl, Mizoram.

## PIU
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY 2026 - PROJECT IMPLEMENTATION UNIT, PWD
Source of Funding : PM DevINE
SL. No. | Name of work /Project. | Approved Cost (Rs) | Name of Implementing agency/Dept. | Date of Commencement | Target Date of Completion | Cummulative progress at the end of last month |  | Achievement of works during the month |  | Overall cumulative achievement |  | Remarks | Mode of Contract
[6 empty] | Physical | Financial | Physical | Financial | Physical | Financial
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Aizawl Bypass on Western Side under PM DevINE Scheme Location : Mizoram State : Aizawl | 451.85 Cr | Project Implementation Unit, PWD | 23.12.2024 | 23.12.2027 | 15.06% | 16.68% | 1.893% | 3.47% | 16.95% | 20.15% |  | EPC
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY 2026 - PROJECT IMPLEMENTATION UNIT, PWD
FINANCIAL REPORT
Sl. No. | Name of project Location and state | Name of Implementing agency/Dept. |  | Approved Cost |  | Fund Released by MDoNER |  | Expenditure Made |  | Financial Progress (%) | Unspent balance out of the fund released (Crore) | Status of submission U/Cs | Remarks
|  |  |  | Orignal cost INR in Crore | Revised cost INR in Crore | During 2024-25 INR in Crore | Since inception (cummulative) | During the month vis-à-vis target Crore | Since inception (Cummulative) Crore
1 | 2 | 3 |  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
1 | Construction of Aizawl Bypass on Western Side under PM DevINE Scheme Location : Mizoram State : Aizawl | Project Implementation Unit, PWD |  | 500 | Nil | 112.95 | 112.95 | 17.37 | 100.78 | 20.15% | 12.17 |  | Out of the 112.95 Crore sanctioned, a total amount of Rs. 100.78 Cr was utilised which includes DPR preparation and Appraisal cost, preparation of EIA/EMP report and Mobilisation Advance as well as SPS-01, SPS-02 & SPS-03 (contractor's bill)
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY 2026 - PROJECT IMPLEMENTATION UNIT, PWD
PHYSICAL ABSTRACT
Sl. No. | Name of the project Location and state | Name of the implementing Agency/ Deptt. | Approved cost & date | 5: Date of commencement of work /scheme; 6: Target date of completion of work/scheme; 7: Scope of work /scheme physical terms (e.g.Kms etc); 11: Physical Achievement |  | Remark
|  |  | Cost (lakhs) | 4: Date; 11: Achievement; 12: Percentage upto date progress; 13: Percentage during last month | Percentage during the report
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |  |  |  | 9 | 10 | 11 | 12 | 13
1 | Construction of Aizawl Bypass on Western Side under PM DevINE Scheme Location : Mizoram State : Aizawl | Project Implementation Unit, PWD | 4510 | 23.12.2024 | 23.12.2024 | 23.12.2027 | 1 | Earthwork up to top of sub-grade | Km | 45 | 24.085 | 53.52% | 48.88% | 4.642%
[7 empty] | 2 | Sub Base Course (SSB) | Km | 45 | 0.42 | 0.9333% | 0% | 0.9333%
[7 empty] | 3 | Seperation Layer (SAMI) | Km | 45 |  | 0% | 0% | 0%
[7 empty] | 4 | Bituminous Work | Km | 45 |  | 0% | 0% | 0%
[7 empty] | 5 | Wearing Course | Km | 45 |  | 0% | 0% | 0%
[7 empty] | 6 | Reconstruction and New Culverts on Existing road/realignmnet bypass - Hume Pipe Culvert | nos | 205 | 16 | 7.805% | 4.88% | 2.925%
[7 empty] | 7 | Reconstruction and New Culverts on Existing road/realignmnet bypass - RCC Box Culvert | nos | 12 |  | 0% | 0% | 0%
[7 empty] | 8 | Reconstruction and New Culverts on Existing road/realignmnet bypass - chutes | nos | 1278 |  | 0% | 0% | 0%
|  |  |  | 7: A; 8: A-Widening and repairs of minor bridges | 0%
|  |  |  | 7: 1; 8: Repair of minor bridge by construction of wing wall; 10: 0 | 0%
|  |  |  | 7: B; 8: B-New Minor Bridges | 0%
[7 empty] | 1 | Foundation + Substructure | Nos | 8 |  | 0% | 0% | 0%
[7 empty] | 2 | Super-structure | Nos | 8 |  | 0% | 0% | 0%
[7 empty] | 3 | Approaches | Nos | 8 |  | 0% | 0% | 0%
[7 empty] | 4 | Protection Work | Nos | 8 |  | 0% | 0% | 0%
[7 empty] | i | Counterfort retaining wall | RMT | 2140 |  | 0% | 0% | 0%
[7 empty] | ii | Plumb Concrete Retaining Wall | Nos | 1722 |  | 0% | 0% | 0%
[7 empty] | iii | Breast Wall | RMT | 946 |  | 0% | 0% | 0%
[7 empty] | iv | Toe Wall | RMT | 946 |  | 0% | 0% | 0%
[7 empty] | v | Gabion Breast Wall | RMT | 1355 | 479 | 35.35% | 23.62% | 11.73%
[7 empty] | vi | Lined Side Drain | MTR | 5000 |  | 0% | 0% | 0%
[7 empty] | vii | Crash Barrier | RMT | 2560 |  | 0% | 0% | 0%
[7 empty] | viii | Traffic Signages | Nos | 225 |  | 0% | 0% | 0%
|  |  |  | 7: ix; 8: Road Markings; 10: 13050; 12: 0%; 13: 0% | 0%
|  |  |  | 7: x; 8: Km Stones; 10: 220; 12: 0%; 13: 0% | 0%
|  |  |  | 7: xi; 8: Boundary Pillar; 10: 600; 12: 0%; 13: 0% | 0%
|  |  |  | 7: xii; 10: 35; 12: 0%; 13: 0% | 0%

## AZL ELEC DIV
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY 2026
Name Of Division : PWD, Electrical Division, Aizawl
Head of Account : Major & Minor Works and Deposit works 8443-108, D-III
Sl. No | Name of Works / Scheme | Unit | Approved Cost Amount (in Lakhs.) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month. |  | Achievement of works during the Month |  | Overall cummulative achievement |  | Remarks
[6 empty] | Phy (%) | Fin(Rs) | Phy (%) | Fin(Rs) | Phy (%) | Fin(Rs)
1 | 2 |  | 3 | 6 |  | 10 | 11 | 12 | 13 | 14 | 15 | 18
1 | I/E to Arrival & Departure Passenger Lobby at Lengpui Airport | % | 25.27 | 19.12.2020 | 1.4.2024 | 97% | - | 0% | - | 97% | 25.27 | Room modification (Civil Works) not yet ready
2 | Addl. Estimate for SITC of MRV/VRF Centralizes Air Conditioner Airport First Floor Departure Hall, Mizoram. | % | 247.74 | 12.03.2022 | 04.03.2024 | 98.5% | - | 0% | - | 98.5% | 244.44 | Completion stage, Testing and Comissioning left.
3 | SITC of EPABX System for Lengpui Airport Terminal Building. | % | 24.64 | 06.07.2022 | 29.06.2024 | 98% | - | 0% | - | 98% | 19.46 | Telephones stocked at site, ready be fixed in the rooms when occupied
4 | SITC of PA System at Lengpui Airport Terminal Building. | % | 36.36 | 06.07.2022 | 29.06.2024 | 99% | - | 0% | - | 99% | 28.82 | Ready for Commision
5 | Supply & Installation of Integrated Fire Hydrant System (Wise Riser)&SITC of Alarm System for Lengpui Airport Terminal Building. | % | 119.96 | 06.07.2022 | 29.06.2024 | 98% | - | 0% | - | 98% | 94.72 | Completion stage
6 | SITC of AVTRON IP Surveillance System for Lengpui Airport Terminal Building. | % | 94.76 | 06.07.2022 | 29.06.2024 | 98% | - | 0% | - | 98% | 67.61 | All system function and ready for Commission exept 6 nos. Camera at Ground Floor due to Civil works (Ceiling) not yet ready at Ground floor
7 | SITC of LAN SETUP at Lengpui Airport Terminal Building. | % | 20.05 | 06.07.2022 | 29.06.2024 | 99% | - | 0% | - | 99% | 15.76 | Completion stage
Sl. No | Name of Works / Scheme | Unit | Approved Cost Amount (in Lakhs.) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month. |  | Achievement of works during the Month |  | Overall cummulative achievement |  | Remarks
[6 empty] | Phy (%) | Fin(Rs) | Phy (%) | Fin(Rs) | Phy (%) | Fin(Rs)
1 | 2 |  | 3 | 6 |  | 10 | 11 | 12 | 13 | 14 | 15 | 18
8 | Renovation/Repairing of Internal Electrification to Polytechnic at Thingdawl (SH: Automobile Engineering Block) | % | 18.65 | 4.10.2023 | 18.11.2023 | 98% | - | 0% | - | 98% | 18.65 | I/E Work completed, Service connection awaited.
9 | Renovation/Repairing of Internal Electrification to Polytechnic at Thingdawl (SH: Textile Technology Block) | % | 18.71 | 4.10.2023 | 18.11.2023 | 98% | - | 0% | - | 98% | 18.71 | I/E Work completed, Service connection awaited.
10 | Renovation/Repairing of Internal Electrification to Polytechnic at Thingdawl (SH: Administrative Block) | % | 9.52 | 4.10.2023 | 18.11.2023 | 98% | - | 0% | - | 98% | 9.52 | I/E Work completed, Service connection awaited.
11 | Renovation/Repairing of Internal Electrification to Polytechnic at Thingdawl (SH: Common Facility Block) | % | 11.05 | 4.10.2023 | 18.11.2023 | 98% | - | 0% | - | 98% | 11.05 | I/E Work completed, Service connection awaited.
12 | SITC of 5-passenger Lift for Fast Track Court Building at Kolasib | % | 3.9 | 26.12.2024 | 31.08.2025 | 20% | - | 0% | - | 20% | - | Technical Sanction accorded,Building not yet ready for I/E
13 | SITC of 13-passenger Lift for Fast Track Court Building at Kolasib | % | 49.85 | 26.12.2024 | 31.08.2025 | 20% | - | 0% | - | 20% | - | TS accorded, Lift shaf & pit construction / modification required conveyed to PD-III
14 | I/E to Fast Track Court at Kolasib | % | 136.73 | 02.06.2024 |  | 20% | - | 0% | - | 20% | - | Technical Sanction accorded,Building not yet ready for I/E
15 | I/E to Construction od Warehouse and other Amenities at Zuangtui/Sairang (SH: 2000(1000X2)MT Godown) | % | 18.35 | 03.12.2025 | 28.02.26 | 0% | - | 75% | 12.96 | 95% | 12.96 | Technical Sanction accorded,Supply ordered placed, material waited
16 | I/E to Mizoram Legislator Home at Tuikhuahtlang , Aizawl. | % | 28.5 | 20.11.2024 | 30.05.25 | 100% | 28.5 | 0% | - | 100% | 28.5 | Completed
Sl. No | Name of Works / Scheme | Unit | Approved Cost Amount (in Lakhs.) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month. |  | Achievement of works during the Month |  | Overall cummulative achievement |  | Remarks
[6 empty] | Phy (%) | Fin(Rs) | Phy (%) | Fin(Rs) | Phy (%) | Fin(Rs)
1 | 2 |  | 3 | 6 |  | 10 | 11 | 12 | 13 | 14 | 15 | 18
17 | Repair and Maintenance of AC at Session Hall (Phase-I : Northern Side) | % | ` | 14.04.2025 | 12.07.25 | 100% | - | 0% | - | 100% | 8.78 | Completed
18 | New Electrification of MLA Staff Quarters 4 (four) Units (Qtr No. T-141/A, T-141/B, T-141/C and T-141/D) at Tuikhuahtlang, Aizawl. | % | 10.86 | 02.04.2025 | 30.05.27 | 100% | - | 0% | - | 100% | - | I/E works completed
19 | I/E to PHE, E-in-C Office at MINECO | % | 30.34 | 25.08.2025 | 30.09.25 | 100% | 29.46 | 0% | 2.95 | 100% | 29.46 | Completed
20 | Providing, Fixing and Installation of ESE type Lightning Arrester and Grounding System for Tall Trees at Lok Bhawan , Aizawl | % | 15.71 | 08.12.2025 | 31.01.26 | 40% | 10.58 | 60% | 0.49 | 100% | 11.07 | Completed
21 | Supply Installation Testing and Commissioning of Fire Fighting System for Car Parking at District Court, MINECO, Aizawl | % | 15.3575 | 21.11.2025 | 27.02.26 | 10% | - | 40% |  | 50% | - | I/E works in progress
22 | Supply and Fixing of Fire Fighting equipment for Lokj Bhawan | % | 1.377 | 06.11.2025 | 13.02.26 | 0% | - | 70% | - | 70% | - | I/E works in progress
23 | I/E to Staff Quarters (Block-C) at DIET Complex, Chaltlang, Aizawl. | % | 45.98 | - | - | 70% | 27.75 | 30% | - | 100% | 27.75 | I/E works completed
Sl. No | Name of Works / Scheme | Unit | Approved Cost Amount (in Lakhs.) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month. |  | Achievement of works during the Month |  | Overall cummulative achievement |  | Remarks
[6 empty] | Phy (%) | Fin(Rs) | Phy (%) | Fin(Rs) | Phy (%) | Fin(Rs)
1 | 2 |  | 3 | 6 |  | 10 | 11 | 12 | 13 | 14 | 15 | 18
24 | I/E to PWD Staff Quarters (3 Unit) at Serchhip, Aizawl. | % | 5.91 | - | - | - | 5.91 | 100% | - | 100% | 5.91 | I/E works completed
25 | OPD Building at District Hospital Saitual | % | 8.95 | - | - | 80% | 8.95 | 20% | - | 100% | 8.95 | I/E works completed
Sr. Executive Engineer, PWD.,
Electrical Division, Aizawl.

## AZL BUILDING DIV
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY 2026
Name of Division: Aizawl Building Division
Source of Funding : CSS
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of completion | Cummulative Progress at the end of last month |  | Acievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Improvement of Mizoram Secretariat Building at MINECO | Percen tage | 168.49 | 13.11.2023 | 31.03.2024 | 100% | 168.49 |  |  | 100% | 168.49 |  | Departmental
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY 2026
Name of Division: Aizawl Building Division
Source of Funding : State
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of completion | Cummulative Progress at the end of last month |  | Acievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of RCC link drain near Chief Minister's Office at Mc Donald Hill | Percen tage | 25 | 05.04.2025 | 31.08.2025 | 100% | 100% |  |  | 100% | 100% |  | Departmental
2 | Maintenance and furnishing of General Pool Quarters | Percen tage | 85 | 15.01.2025 | 31.03.2025 | 100% | 100% |  |  | 100% | 100% |  | Departmental
Sr.Executive Engineer, P.W.D.,
Aizawl Building Division,
Aizawl:Mizoram.

## CHAMPHAI DIV
MONTHLY PROSGESS REPORT OF WORKS FOR THE MONTH OF JANUARY, 2026
Name of Division : PWD., Champhai
SL.No. | Name of Scheme | Unit | Approved Cost (in lakhs) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of Works during the month |  | Overall Cumulative Achievement |  | Remarks | Mode of Tender
| Name of Work/Project |  |  |  |  | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
I | ANNUAL PLAN (5054)(20224-2025)
1 | Upgradation of Approach road to Tuipui Village from NH-6 (new Eden) Length - 1.625 Km | Km | 128.28 | 6.12.2024 | 6.12.2025 | 82% | 74.32 | 8% | _ | 90% | 74.32 | Work in Progress | Open Tender
2 | Construction of Bailey Bridge (60 ft span) over R. Tuimuk on approach road to Tuipui Village from NH-6 (New Eden) | Ft. | 53.06 | 22.8.2024 |  | 78% | 53.06 | _ | _ | 78% | 53.06 | Work in Progress | Deptt. | 0.053333
II | SASCI (2025-2026)
1 | Upgradation of Khankawn to Champhai (Phase - I) | Km | 600 | 6.6.2025 | 6.6.2026 | 5% |  | 10% | _ | 15% | _ | Work in Progress | Restricted Tender
2 | Construction of Champhai Ring Road Phase-I (Khankawn - Falkawn - Hmunhmeltha - Vengthar - Zote via Keilungliah) | Km | 2000 | 7.7.2025 | 7.7.2026 | 15% | _ | 5% | _ | 20% | _ | Work in Progress | Restricted Tender
3 | Upgradation of Khankawn to Champhai Road Under Part-V (Stimulating of Industrial Growth) (Phase - II) | Km | 600 | _ | 21.7.2026 | _ | _ | _ | _ | _ | _ | Mobilisation Stage | Restricted Tender
III | MAINTENANCE ACTION PLAN (3054)
1 | Improvement & resurfacing of Sobji Bazar to SIB Complex via Rohnaas House(Sobji Bazar SIB Complex) | Km | 8.18 | 13.10.2025 | 31.3.2026 | 100% | 7.41 | _ | _ | 100% | 7.41 | Work Completed | Departmental
2 | Improvement & resurfacing of Khawhluna Point Bethel to Thangvelas House (Sihdim Road) | Km | 21.55 | 13.10.2025 | 31.3.2026 | 100% | 19.6 | _ | _ | 100% | 19.6 | Work Completed | Departmental
3 | Improvement & resurfacing Excise Office approach road | Km | 2.48 | 13.10.2025 | 31.3.2026 | 10% | 2.21 | 90% | _ | 100% | 2.21 | Work Completed | Departmental
4 | Kanan Internal Road upto CNV Road via Seri(CNV Road Kanan Internal Road) | Km | 10.78 | 13.10.2025 | 31.3.2026 | 100% | 9.87 | _ | _ | 100% | 9.87 | Work Completed | Departmental
5 | Improvement & resurfacing of Chanem Ring Road (Chanem Building Chanem) | Km | 6.41 | 13.10.2025 | 31.3.2026 | 100% | 5.83 | _ | _ | 100% | 5.83 | Work Completed | Departmental
6 | Patch repair & resurfacing of Kahrawt Field to Vengsang HS via PHE Office (Kahrawt Field Vengsang High School) | Km | 9.72 | 13.10.2025 | 31.3.2026 | 60% | 8.69 | 40% | _ | 100% | 8.69 | Work Completed | Departmental
7 | Improvement & resurfacing of Tlangsam Community Hall Approach Road | Km | 8.01 | 13.10.2025 | 31.3.2026 | 40% | 5.54 | 60% | _ | 100% | 5.54 | Work Completed | Departmental
8 | Resurfacing of approach road to Hlakungpui mual, Khawbung (Balance portion including approach road to SA Quarter) | Km | 4.59 | 21.10.2025 | 31.3.2026 | 50% | 3.1 | 30% | _ | 80% | 3.1 | Work in Progress | Departmental
9 | Resurfacing of approach road to PHC Farkawn ( Farkawn PHC Farkawn) | Km | 10.55 | 21.10.2025 | 31.3.2026 | 75% | 10.55 | 25% | _ | 100% | 10.55 | Work Completed | Departmental
10 | Resurfacing of approach road to Zawlsei Middle School, Zawlsei | Km | 3.01 | 21.10.2025 | 31.3.2026 | 50% | 3.01 | 50% | _ | 100% | 3.01 | Work Completed | Departmental
11 | Resurfacing of approach road to mini Sport Complex, Khawbung | Km | 4.52 | 21.10.2025 | 31.3.2026 | 50% | 3.06 | 30% | _ | 80% | 3.06 | Work in Progress | Departmental
12 | Pothole Filling, Patch repair of Champhai - Khawbung road (Dungtlang to Khawbung) (64.000-71.000 kmp) | Km | 3.79 | 21.10.2025 | 31.3.2026 | 80% | 3.79 | 20% | _ | 100% | 3.79 | Work Completed | Departmental
13 | Construction of Unlined Side Drain on Lianchhiari Lunglen Tlang road at Dungtlang | Km | 5 | 21.10.2025 | 31.3.2026 | 100% | 5 | _ | _ | 100% | 5 | Work Completed | Departmental
IV | 3054 NON-PLAN R&B
1 | Upgradation of Zotlang to Mualnuam Road | Km | 70 | 4.9.2025 | 31.3.2026 | 100% | 67.08 | _ | 2.62 | 100% | 69.7 | Work Completed | Departmental
2 | Construction of Approach road to Khuangleng Ginger processing Center at Khuangleng | Km | 1.49 | 8.12.2025 | 8.01.2026 | 50% | _ | 50% | _ | 100% |  | Work Completed | Spot Quotation
V | ANNUAL PLAN (5054)(20225-2026)
1 | Resurfacing of Zawlsei to Khuangthing Road Phase-I ( Ch. 0.000 to 3.500 Kmp) | Km | 75.25 | 30.12.2025 | 30.3.2026 |  |  | 10% |  |  | 0.42 | Work Started | Open Tender
2 | Resurfacing of Kelkang Road from Champhai Side. | Km | 50.8 | 30.12.2025 | 30.3.2026 |  |  | 15% |  |  |  | Work Started | Open Tender
3 | Patch repair & Resurfacing of Khuangleng to Leisenzo Road | Km | 43.47 | 30.12.2025 | 30.3.2026 |  |  | 10% |  |  |  | Work Started | Open Tender
4 | Resurfacing of Melbuk Approach road ( Old Zokhawthar road | Km | 24.88 | 30.12.2025 | 30.3.2026 |  |  | 10% |  |  |  | Work Started | Open Tender
Sr. Executive Engineer, PWD.,
Champhai Division:Champhai

## HMUIFANG DIV
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY, 2026
Name of Division: Hmuifang Division, Aibawk
Rs. in Lakh
Sl. no | Name of Scheme | Unit | Approved Cost (Rs.in lakh) | Date of Commencement | Target Date of Completion : | Commulative Progress at the end of last month |  | Achievement of Works during the month |  | Overall Commulative Achievement |  | Remarks | Mode of Tender
| Name of Work/Project |  |  |  |  | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
CRF
1 | Widening to Single Lane with Geometric Improvement & Up-Gradation of Chhiahtlang to Lamchhip road in Mizoram |  | 6668.18 | 23.06.2017 | 23.06.2019 | 100% | 6282.93 |  |  | 100% | 6282.93 | Physically Completed | Restricted Tender
2 | Construction of Muallungthu to Lungphun Road |  | 5996 | 23.11.2017 | 23.11.2019 | [7 empty] | Restricted Tender
| i) Formation Cutting |  |  |  |  | 100% | 2460 |  |  | 100% | 2460 | Physically Completed
| ii) Permanent Works |  |  |  |  | 24.51% |  |  |  | 24.51% |  | Work in progress
| iii) Pavement | [10 empty] | not yet started
SASCI-II
1 | Construction of Agiculture Link Road to R. Mat from Chawilung, Lungsei, Samlukhai, Sialsuk |  | 173.57 | 14.12.2023 | 14.12.2024 | 100% | 173.57 |  |  | 100% | 173.57 | Physically & Financially Completed | Restricted Tender
2 | Restoration of damage due to cyclone remal under Aizawl Road North, Aizawl Road South & Hmuifang Division |  | 1170 | 17.04.2025 | 17.11.2025 | 100% |  |  |  | 100% |  | Physically completed Payment will be made by Aizawl Road South Division | Restricted Tender
3 | Restoration of damage due to cyclone remal under Hmuifang Division, Part-II |  | 1175 | 17.04.2025 | 17.11.2025 | 100% | 980 |  |  | 100% | 980 | Physically completed | Restricted Tender
5054
1 | Widening and Repair of Vantawng Approach Road | Km | 104.49 | 10.10.2024 | 10.03.2025 | 100% | 104.49 |  |  | 100% | 104.49 | Physically & Financially Completed | Departmental
Sr. Executive Engineer, PWD.,
Hmuifang Division, Aibawk

## Khawzawl
MONTHLY PROGRESS REPORT OF MAJOR WORKS 2025-2026 UNDER PWD KHAWZAWL DIVISION FOR THE MONTH OF JANUARY, 2026
Name of Division : Khawzawl Division.
Sl. No. | Name of Work | Category of road | Length (Km) | Amount of Technical Sanction (Rs. Lakh) | Date of Technical Sanction | Financial Progress (amount Rs. Lakh) |  |  | Physical Progress (in percentage) |  |  | Remarks
[6 empty] | Expenditure upto end of the month | Expenditure during the month | Total expenditure upto end of the month | Progress upto end of previous month | Progress during the month | Progress upto end of the month
1 | Resurfacing of Vengthar Bazar to Presbyterian English School at Khawzawl. | STR | 0.75 | 32.27 | 12.09.2025 |  | 30.65 | 30.65 |  | 100 | 100 | Work Completed
2 | Resurfacing of Approach Road to PHE Complex, EE Quarters, SDO Quarters and SDO Office. | STR | 0.38 | 21.52 | 12.09.2025 |  | 20.44 | 20.44 |  | 100 | 100 | Work Completed
3 | Resurfacing of Kawnzar to Taidawnkawn at Khawzawl. | STR | 1.13 | 49.72 | 12.09.2025 |  | 47.23 | 47.23 |  | 100 | 100 | Work Completed
4 | Resurfacing of Approach Road to Khawhai PHC. | STR | 0.744 | 47.17 | 12.09.2025 | [6 empty] | Work in Progress
5 | Pavement of Approach Road to IR (NH 102B to IR Camp) at NE.Khawdungsei. | STR | 0.487 | 17.46 | 15.09.2025 | [6 empty] | Work in Progress
Sr.Executive Engineer, PWD,
Khawzawl Division.

## KOLASIB DIV
MONTHLY PROGRESS REPORT
FOR THE MONTH OF JANUARY, 2026
UNDER KOLASIB DIVISION
Sl. No. | Name of Schemes | Quantity | Unit | Approved Cost (Rs in Lakh) | Date of Commencement | Target Date of Comple-tion | Cumulative Progress at the end of last month |  | Achievement of works during the month |  | Overall Cumulative achievement |  | Remarks | Mode of Tender
| Name of Works / Project | [5 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 |  | 3 | 4 | 6 | 7 | 8 | 9 | 10 | ♂11 | 12=(8+10) | 13=(9+11) | 14 | 15
1 | NABARD
1 | Construction of Meidum to Hortoki Phase-II
i | Earthwork and Permanent Work from 9.100 Km to 13.325 Km Package-I | 3.305 | Km | 13366 | 24.12.2021 | 29.04.2024 | 100% | 1035.621 |  |  | 100% | 1035.621 | Completed | Restricted Tender
ii | Earthwork and Permanent Work from Km 13.325 to Km 17.500 Package-II | 3.275 | Km |  | 25.12.2021 | 23.07.2025 | 97% | 933.465 |  |  | 97% | 933.465 |  | Restricted Tender
iii | Earthwork and Permanent Works from Km 17.500 to Km 21.725 Package-III | 3.315 | Km |  | 18.12.2021 | 16.11.2025 | 98% | 1223.502 |  |  | 98% | 1223.502 | Mobilisation & Machinery Advance Recovery Balance= Rs.7 lakh | Restricted Tender
iv | Earthwork and Permanent Works from Km 21.725 to Km 26.00 Package-IV | 3.355 | Km |  | 08.12.2021 | 19.05.2025 | 99% | 726.528 |  |  | 99% | 726.528 | Mobilisation & Machinery Advance Recovery Balance=Rs.79.589 lakh | Restricted Tender
v | Construction of Rigid Pavement : Package -I (Km 9.100-Km 15.730) | 5.58 | Km |  | 03.08.2022 | 10.12.2025 | 38% | 722.158 |  |  | 38% | 722.158 | Mobilisation & Machinery Advance Recovery Balance= Rs.173.459 lakh | Restricted Tender
vi | Construction of Rigid Pavement : Package -II (Km 15.730-Km 22.36) | 5.58 | Km |  | 03.08.2022 | 05.09.2025 | 9.17% | 188.463 |  |  | 9.17% | 188.463 | Mobilisation & Equipment Advance Recovery Balance= Rs.297.974 lakh | Restricted Tender
vii | Design & Construction of T-Beam Bridge package-I at Chhimluangte (CH : 0.450 Kmp) | 24 | 3: m; 6: 18.12.2021; 8: 100%; 9: 482.621 | 100% | 482.621 | Completed | Departmental |  | 367.621
viii | Design & Construction of T-Beam Bridge package-I at Dumkhel (CH : 5.500 Kmp) | 20 | m |  | 30.12.2024 | 30.06.2026 | 27% | 115.75 |  |  | 27% | 115.75 | Secured Advance Rs.62.24 lakh | Restricted Tender
ix | Design & Construction of T-Beam Bridge package-II at Bulung (CH : 10.200 Kmp) | 28 | 3: m; 6: 24.12.2021; 7: 02.10.2025; 8: 17.5% | 17.5% | 0 | Secured Advance Rs.82.080 lakh | Restricted Tender
x | Design & Construction of T-Beam Bridge package-II at Damdiai (CH : 23.50 Kmp) | 20 | 3: m; 8: 21.5% | 21.5% | 0 |  | Restricted Tender |  |  |  | 273.047
2 | Construction of BUSG Composite Bridge (Span=22.00m, Revised span=34.00m) over R. Chepte on Bilkhawthlir to Saiphai road under NABARD | 34 | m | 508.45 | 24.06.2019 | 30.11.2025 | 25% | 132.82 |  |  | 25% | 132.82 | NABARD Fund=Rs. 291.35 lakh SASCE Fund=Rs.217.10 Expenditure from NABARD=Rs.46.67 Expenditure from SASCE=Rs.86.15. Equipment Advance Recovery balance=Rs.8.037 | Restricted Tender | 26.1225 | 6.5306 |  | 244.05
3 | Construction of BUSG Composite Bridge (Span=22.00m) over R. Sesih on Bilkhawthlir to Saiphai road under NABARD | 22 | m | 291.35 | 24.06.2019 | 30.09.2025 | 99% | 248.894 |  |  | 99% | 248.894 | Expenditure includes centages Equipment Advance Recovery balance=Rs.25.298 lakh | Restricted Tender | 85.4278 | 84.5736 |  | 28.997
4 | Construction of Link Road from NH-306 (Vairengte) to Sabual Mual Arable Crop Land : length=3.720 Kms | 3.72 | Km | 417.58 | 13.08.2022 | 28.02.2025 | 100% | 406.303 |  |  | 100% | 406.303 | Physically Completed Expenditure includes centages | Restricted Tender
5 | Construction of approach Road to Railway Station in Mizoram (SH: Construction of Approach Road to Hortoki Railway Station | 2.51 | km | 625.97 | 18.07.2025 | 18.07.2026 | 23% | 130.27 | 1% |  | 24% | 130.27 |  | Restricted Tender
2 | SASCI | [15 empty] | 273.047
1 | Restoration of Damages due to Cyclone Remal under SASCI, 2024-2025 under Kolasib Division | [15 empty] | 24.153
i | Re-construction of Hume Pipe Culvert on Hmar Veng to Saidan Road, Kolasib | 7.5 | m | 17.147 | 16.06.2025 | 16.01.2026 | 100% | 17.147 |  |  | 100% | 17.147 | Completed | Restricted Tender
ii | Construction of Retaining Wall on Rengtekawn to NH 154(Zero Point) Road at 1.050 Kmp | 52 | m | 29.666 | 16.06.2025 | 16.01.2026 | 60% |  | 40% |  | 100% |  | Works physically completed |  |  |  | 244.05
iii | Construction of Breast Wall on Rengtekawn to NH 154(Zero Point) Road at 1.600 Kmp | 30 | m | 10.756 | 16.06.2025 | 16.01.2026 | 60% |  | 40% |  | 100% |  | Works physically completed |  |  |  | 4.844
iv | Re-construction of SPT Bridge over R.Chepte at 10.000 Kmp on Bilkhawthlir to Saiphai Road (SH: Approach Roads ) | 110 | m | 1.973 | 16.06.2025 | 16.01.2026 | 100% | 1.973 |  |  | 100% | 1.973 | Completed |  |  |  | 248.894
v | Construction of Hume Pipe Culvert near Lalrampana House on Rengtekawn NH 54-132 KV | 1 | nos | 5.456 | 16.06.2025 | 16.01.2026 | 100% | 5.456 |  |  | 100% | 5.456 | Completed
vi | Construction of SPT Bridge over Aitlanglui at Vairengte | 12 | m | 15 | 16.06.2025 | 16.01.2026 | 75% |  | 25% | 15 | 100% | 15 | Completed
vii | Construction of Retaining Wall at Serkhan to Bagha Road at 29.100 Kmp | 1 | nos | 4.358 | 16.06.2025 | 16.01.2026 | 100% | 4.358 |  |  | 100% | 4.358 | Completed
viii | Construction of Retaining Wall near Tumpui field on Main Feeder to Karkawn via Helipad | 1 | nos | 24.231 | 16.06.2025 | 16.01.2026 |  |  | 30% |  | 30% |  | Works in progress
ix | Construction of Retaining Wall at Serkhan to Bagha Road at 15.100 Kmp | 1 | nos | 15.409 | 16.06.2025 | 16.01.2026 | 100% | 15.409 |  |  | 100% | 15.409 | Completed
x | Construction of Retaining Wall at Serkhan to Bagha Road at 32.400 Kmp | 1 | nos | 11.154 | 16.06.2025 | 16.01.2026 | 100% | 11.154 |  |  | 100% | 11.154 | Completed
xi | Construction of Retaining Wall on Rengtekawn-Builum Road at 8.000 KMP | 1 | nos | 6.118 | 16.06.2025 | 16.01.2026 | 100% | 6.118 |  |  | 100% | 6.118 | Completed
xii | Construction of Retaining Wall on Rengtekawn-Builum Road at 5.600 KMP | 1 | nos | 24.108 | 16.06.2025 | 16.01.2026 | 60% | 24.108 | 40% |  | 100% |  | Works physically completed
xiii | Restoration of Damaged Pavement on Buhchang to Phaisen road at 7.350 Kmp | 27 | m | 12.677 | 16.06.2025 | 16.01.2026 | 100% | 12.677 |  |  | 100% | 12.677 | Completed
xiv | Re-Construction of Hume Pipe Culvert at 8.160 Kmp on Bilkhawthlir to Saiphai Road | 1 | nos | 7.21 | 16.06.2025 | 16.01.2026 | 100% | 7.21 |  |  | 100% | 7.21 | Completed
xv | Construction of Retaining Wall on Rengtekawn to Builum Road at 5.100 Kmp | 1 | nos | 11.736 | 16.06.2025 | 16.01.2026 | 100% | 11.736 |  |  | 100% | 11.736 | Completed
xvi | Re-Construction of Hume Pipe Culvert at 9.390 on Bilkhawthlir to Saiphai Road | 2 | nos | 11.965 | 16.06.2025 | 16.01.2026 | 100% |  |  | 11.965 | 100% | 11.965 | Completed
xvii | Restoration of Damaged Pavement on Buhchang to Phaisen road at 8.850 Kmp | 11 | m | 5.176 | 16.06.2025 | 16.01.2026 | 100% | 5.176 |  |  | 100% | 5.176 | Completed
xviii | Construction of Retaining Wall at Kawnpui to Hortoki Road at 15.100 Kmp | 1 | nos | 5.178 | 16.06.2025 | 16.01.2026 | 100% | 5.178 |  |  | 100% | 5.178 | Completed
3 | ANNUAL MAINTENANCE OPERATION PLAN 3054 (Departmental
i | Patch Repair from Main Feeder to PHE Office via Spring Field School Hmarveng | 490 | m | 8.5 | 18.08.2025 | 18.02.2026 | 100% |  |  | 8.5 | 100% | 8.5 | Completed | Departmental
ii | Resurfacing of Road from Presbyterian Church to MHIP Building (Section-II) at College Veng, Kolasib | 162 | m | 7.86 | 18.08.2025 | 18.02.2026 | 100% |  |  | 7.86 | 100% | 7.86 | Completed
iii | Resurfacing of approach Road and Courtyard of Circuit House, Kolasib | 64 | m | 6.8 | 18.08.2025 | 18.02.2026 | 100% |  |  | 6.8 | 100% | 6.8 | Completed
iv | Resurfacing of Appraoch Road to DEO Office, Project Veng Kolasib | 300 | m | 4.1 | 18.08.2025 | 18.02.2026 | 100% |  |  | 4.1 | 100% | 4.1 | Completed
v | Resurfacing of road from PWD Office to Salvation Hall at Main feeder Road, Hmarveng | 120 | m | 2.7 | 18.08.2025 | 18.02.2026 | 100% |  |  | 2.7 | 100% | 2.7 | Completed
vi | Construction of Retaining Wall near Ramchullova house Tumpui, Kolasib | 1 | nos | 0.9 | 18.08.2025 | 18.02.2026 | 100% |  |  | 0.9 | 100% | 0.9 | Completed
vii | Resurfacing of Approach Road to Integrated School, Vengthar, Kolasib | 230 | m | 3.8 | 18.08.2025 | 18.02.2026 | 100% |  |  | 3.8 | 100% | 3.8 | Completed
viii | Construction of Retaining Wall at Serkhan to Bagha Road Ch: 24.650 Kmp near N.Chaltlang | 1 | nos | 3.7 | 18.08.2025 | 18.02.2026 | 100% |  |  | 3.7 | 100% | 3.7 | Completed
ix | Resurfacing of Serkhan to Bagha Road from Ch : 3.300 Kmp to 3.650 Kmp (Nisapui Diversion) | 350 | m | 11.1 | 18.08.2025 | 18.02.2026 |  |  | 10% |  | 10% |  | Works in progress
x | Resurfacing of Approach Road & Couryard of PHC at Sentlang | 155 | 3: m; 4: 3.9; 6: 18.08.2025; 7: 18.02.2026
xi | Resurfacing of road from NH-306 to Vety Office, Kawnpui | 90 | m | 2.9 | 18.08.2025 | 18.02.2026 |  |  | 100% | 2.9 | 100% | 2.9 | Completed
xii | Resurfacing of SDO (Civil) Office to Hockey Academy, Kawnpui | 115 | m | 2.9 | 18.08.2025 | 18.02.2026 |  |  | 90% | 2.6 | 90% | 2.6 | Works in progress |  |  | 2.61
xiii | Patch repair and Resurfacing of Centenary Road, Bilkhawthlir | 480 | m | 17 | 18.08.2025 | 18.02.2026 | 100% |  |  | 17 | 100% | 17 | Completed
xiv | Patch repair and Resurfacing of Approach road to Baptist Church via Forest Department Complex, Bilkhawthlir | 176 | m | 3.4 | 18.08.2025 | 18.02.2026 | 100% |  |  | 3.4 | 100% | 3.4 | Completed
xv | Resurfacing of Bilkhawthlir Community Hall to Market, Bilkhawthlir Phase-I | 180 | m | 2.9 | 18.08.2025 | 18.02.2026 | 100% |  |  | 2.9 | 100% | 2.9 | Completed
5054 (Open Tender)
1 | Construction of Hume Pipe Culvert on Rengtekawn to Builum at Ch:8.900Kmp (Group -4) | 1 | nos | 5.8 | 15.12.2025 | 13.06.2026 | 10% |  | 90% | 4.808 | 100% | 4.808 | Completed | Open Tender
2 | Construction of Lined Side Drain on Rengtekawn to NH-154 (Zero Point) at different locations. | 1000 | 3: rm; 4: 20; 6: 15.12.2025; 7: 13.06.2026
3 | Re-construction of damaged Concrete Pavement on Rengtekawn to NH-154 (Zero Point) at Ch:3.200 Kmp (Group-1) | 20.63 | 3: cum; 4: 4.7; 6: 15.12.2025; 7: 13.06.2026
4 | Resurfacing of Mualvum Approach Road from 0.00 -2.380Kmp, Kawnpui (Group No 2) | 8330 | 3: sqm; 4: 69.3; 6: 15.12.2025; 7: 13.06.2026
Sr.Executive Engineer, PWD
Kolasib Division.

## KAWRTHAH DIV
MONTHLY PROGRESS REPORT FOR THE MONTH OF | [9 empty] | JANUARY, 2026
Name of Division |  | : KAWRTHAH
Source of Funding |  | : SASCI
Sl. No | Name of Works/Project | Unit |  | Approved Cost (in lakhs) | Date of Commencement | Target Date of Completion | Achievement upto previous month |  | Achievement for the month |  | Overall Cummulative achievement |  | Remarks | Mode of Contract
[7 empty] | Phy | Fin | Phy | Fin | Phy | Fin (actual)
1 | 2 | 3 |  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Additional works and Completion of Double Lane Bridge over River Teirei on Bairabi - Zamuang Road. |  |  | 5: 29.2.2024; 6: 15.11.2025; 9: -; 13: Construction of bridge portion & Approach road is physically completed; 14: Continued by the existing contractor i.e Sadguru Engineers & Allied Services Pvt.Ltd. For Bridge work & piling of Bank protection & Departmentally for Bank protection (Balanced work) and approach road.
| Bridge Work (Super Structure) | Nos | 1 | 4: 546.91; 7: 100%; 8: 1047.43; 10: 212.99; 11: 100%; 12: 1260.42
| River Banks Protection | Nos | 2 | 4: 475.69; 7: 93%; 9: 3%; 11: 96%
| Approach Road | Nos | 2 | 4: 298.46; 7: 90%; 9: 10%; 11: 100%
| Road Signages |  |  | 4: 25.6
| Total of Work Component : |  |  | 4: 1346.66; 8: 1047.43; 10: 212.99; 12: 1260.42
| Provision for Contingencies : |  |  | 4: 26.76
| Provision for Quality Control : |  |  | 4: 26.6
| Grand Total : |  |  | 4: 1400.02; 8: 1047.43; 10: 212.99; 12: 1260.42
| Overall physical Progress | : |  | 4: 99%
MONTHLY PROGRESS REPORT FOR THE MONTH OF |  |  |  | 10: JANUARY, 2026
Name of Division |  | : KAWRTHAH
Source of Funding |  | : SASCI
Sl. No | Name of Works/Project | Unit |  | Approved Cost (in lakhs) | Date of Commencement | Target Date of Completion | Achievement upto previous month |  | Achievement for the month |  | Overall Cummulative achievement |  | Remarks | Mode of Contract
[7 empty] | Phy | Fin | Phy | Fin (in lakhs) | Phy | Fin (in lakhs)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Strengthen ing of Zamuang - Hriphaw - Kolalian - Dulupcherra (ZHKD) Road (28.00 Kmp) | Km | 28 | 225 | 16.12.2023 | 30.6.2025 | 100% | 225 | - | - | 100% | 225 | Works completed | Contract after call of restricted tender
| Grand Total : |  |  | 4: 225; 7: 100%; 8: 225; 11: 100%; 12: 225
| Overall Physical Progress | : | 100%
MONTHLY PROGRESS REPORT FOR THE MONTH OF |  |  |  | 10: JANUARY, 2026
Name of Division |  | : KAWRTHAH
Source of Funding |  | : NABARD
Amount in lakhs
Sl. No | Name of Work/Project | Unit |  |  | Approved Cost (in lakh) | Date of Commencement | Target Date of Completion | Achievement upto previous month |  | Achievement for the month |  | Overall commulative achievement |  | Remarks | Mode of Contract
[8 empty] | Phy | Fin (lakh) | Phy | Fin (lakh) | Phy | Fin (actual)
1 | 2 | 3 |  |  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Double Lane BUSG Bridge (Span = 81m) over R.Langkaih on Mizoram-Tripura Border at Kanhmun | Bridge Works : |  |  | 13: Work in progress; 14: Contract after call of Restricted Tender
|  | a) Site Investigation & Design | 7% | % | 154.23 | 6.4.2018 | 31.12.2025 | 100% | 1656.47 | - | 162.93 | 100% | 1819.4
|  | b) Construction of Subway | 20% | % | 4: 440.65; 7: 100%; 11: 100%
|  | c) Foundation & Sub-Structure | 41% | % | 4: 903.34; 7: 93%; 9: 5%; 11: 98%
|  | d) Super-Structure | 30% | % | 4: 660.98; 7: 66%; 11: 66%
|  | e) Miscellaneous | 2% | % | 4: 44.06; 9: -
|  | f) Contingency |  |  | 4: 28.65; 7: -; 9: -; 11: -
|  | Grand Total : |  |  | 4: 2231.91; 8: 1656.47; 10: 162.93; 12: 1819.4
|  | Overall physical Progress :- |  |  | 4: 89%
MONTHLY PROGRESS REPORT FOR THE MONTH OF |  |  |  |  | 9: JANUARY, 2026
Name of Division |  | : KAWRTHAH
Source of Funding |  | : SASCI
Sl. No | Name of Works/Project | Unit |  | Approved Cost (in lakhs) | Date of Commencement | Target Date of Completion | Achievement upto previous month |  | Achievement for the month |  | Overall Cummulative achievement |  | Remarks | Mode of Contract
[7 empty] | Phy | Fin | Phy | Fin (in lakhs) | Phy | Fin (in lakhs)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Restoration of Damge due to Cyclone Remal under Kawrthah Division | Nos | 23 | 293.2 | 16.6.2025 | 16.1.2026 | 100% | 293.2 | - | - | 100% | 293.2 | Work completed. | Contract after call of restricted tender
| Grand Total : |  |  | 293.2 | 7: 293.2; 10: 100%; 11: 293.2
| Overall Physical Progress | : |  | 100%
MONTHLY PROGRESS REPORT FOR THE MONTH OF |  |  |  |  | 9: JANUARY, 2026
Name of Division |  | : KAWRTHAH
Source of Funding |  | : 5054 R&B
Sl. No | Name of Works/Project | Unit |  | Approved Cost (in lakhs) | Date of Commencement | Target Date of Completion | Achievement upto previous month |  | Achievement for the month |  | Overall Cummulative achievement |  | Remarks | Mode of Contract
[7 empty] | Phy | Fin | Phy | Fin (in lakhs) | Phy | Fin (in lakhs)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Construction of Retaining wall at Zawlnuam IB | Nos | 1 | 10.13 | 9.1.2026 | 9.4.2026 | - | - | 10% | - | 10% | - | Work cin progress. | Contract after call of tender
| Grand Total : |  |  | 10.13 | 10: 10%
| Overall Physical Progress | : |  | 10%
Sl. No. | Name of Works/Project | Unit | Qnty. | Approved Cost (in lakh) | Date of commencement | Target Date of completion | Achievement upto previous month |  | Achievement for the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[7 empty] | Phy | Fin | Phy | Fin | Phy | Fin (actual)
1 | 2 | 3 | 4 |  | 6 | 7 | 8 | 9 | 8 | 10 | 11 | 12 | 13 | 14
I. | ANNUAL MAINTENANCE OPERATION PLAN 2025-26 (3054) UNDER KAWRTHAH DIVISION.
| 1) Patch Repair of Kawrthah Internal Road (Puksut kawn - HS Veng) at Kawrthah | Km | 0.446 | 75.33 | 18.11.2025 | 31/12/2025 | 100% | 47.19 |  | 28.14 | 100% | 75.33 | Work completed | Departmental
| 2) Resurfacing of Hriphaw Town Road (Lalveng - Chhim veng) at Hriphaw Ch.0.400 - 7.395 Kmp | Km | 0.995 |  | 24.11.2025 | 31/12/2025 | 50% |  | 50% |  | 100% |  | Work completed
| 3) Patch repair of Chuhvel to Sihthiang Road | Km | 10.18 |  | 19.1.2026 | 31/03/2026 | - |  | 40% |  | 40% |  | Work in progress
| 4) Approach road to Damcherra market (From MVI office) (MVI office - Zakamlova building) | Km | 0.133 |  | 1.3.2026 | 31/03/2026 | - |  | - |  | - |  | Works not yet started
| 5) Approach road to Police Quarters (Police station at KDZKT Police Quarter) | Km | 0.124 |  | 12.1.2026 | 31/03/2026 | - |  | 100% |  | 100% |  | Work in progress
| 6) Re-surfacing of Approach road to VC House (Salvation Hall - VC House) Part-I at Tuidam | Km | 0.28 |  | 6: 2025-11-17; 7: 31/12/2025; 8: 100%; 11: 100%; 13: Work completed
| 7) Re-surfacing of Approach road to Forest IB at Kawrtethawveng | Km | 0.2 |  | 6: 2025-11-17; 7: 31/12/2025; 8: 100%; 11: 100%
| Total = |  |  | 75.33 | 9: 47.19; 10: 28.14; 12: 75.33
| Overall Physical progress | : | 77.14%
MONTHLY PROGRESS REPORT FOR THE MONTH OF |  |  |  |  | 9: JANUARY, 2026
Name of work/Project |  | : Construction of Up-gradation and Maintenance of Moroicherra to Lushaicherra (0.00 – 9.84 Kmp)
Name of Division |  | : Kawrthah
Date of Commencement |  | : 13.08.2024
Target Date of Completion |  | : 02.03.2026
Name of Contractor |  | : C.Vanlalruatkima, Lungdai
Sl. No | Components of Works | As per Agreement |  |  | 6: Achievement upto previous Month; 8: Achievement for the Month; 8: Overall Cummulative achievement; 11: Remarks/ Issues
|  | Qty | Unit | Item Amount (lakhs) | Phy Prog (Qty) | Fin Prog (lakh) | Phy Prog (Qty) | Fin Prog (lakh) | Phy Prog (Qty) | Fin Prog (lakh)
1 | 3 |  |  | 4 | 7 | 8 | 9 | 10 | 11 | 12 | 13
1 | A. Formation works : a) Clearing & setting | 9.84 | Km | 6.938 | 9.84 | 199.9 |  |  | 9.84 | 199.9 | Work in progress
b) New FC for curve Improvement
| Total of earthwork | 6562.8 | M3 | 4: 5.903; 7: 6562.8; 11: 6562.8
2 | B. Side Drains : a) Unlined Side drain
| a) Unlined Side Drain | 8940 | Rm | 4: 7.161; 7: 5445; 11: 5445
| b) Lined Side drain | 900 | Rm | 4: 15.728
3 | C. Protection works : | 126 | Rm | 4: 57.2; 7: 126; 11: 126
4 | D. Drainage Work a) HP Culvert | 15 | Nos | 4: 88.148; 7: 5; 9: 2; 11: 7
5 | E. Minor Bridge Hand/Guard Rail | 3 | Nos | 4: 1.121
6 | F. Pavement works :
| a) Scarifying Existing Bituminous | 8.72 | Km | 4: 3.419; 7: 8.72; 11: 8.72
| b) WBM -II | 9.84 | Km | 4: 131.045; 7: 9.1; 11: 9.1
| c) WBM -III | 9.84 | Km | 4: 131.045; 9: 0.5; 11: 0.5
| d) Prime coat | 9.84 | Km | 4: 25.37
| e) MSS | 9.84 | Km | 4: 117.646
| f) Tack Coat | 9.84 | Km | 4: 5.744
| g) Earthern Shouder | 9.84 | Km | 4: 6.489
7 | G. Road Sign |  |  | 4: 26.467
8 | H. Title information |  |  | 4: 0.285; 7: 2; 11: 2
9 | I. Citizen information |  |  | 4: 0.166; 7: 1; 11: 1
10 | J. PMGSY LOGO |  |  | 4: 0.949; 7: 4; 11: 4
11 | K. AMC | 5 | Years | 4: 38.87
| TOTAL OF WORK COMPONENT |  |  | 4: 669.694; 8: 199.9; 12: 199.9
| Overall Physical Progress = | 38.05%
MONTHLY PROGRESS REPORT FOR THE MONTH OF |  |  |  | 9: JANUARY, 2026
Name of work/Project |  | : Upgradation & Maintenance of Bairabi to Zamuang Road (Ch:0.00 to 24.20 Kmp)
Name of Division |  | : KAWRTHAH
Date of Commencement |  | : 29.8.2024
Target Date of Completion |  | : 1.3.2026
Name of Contractor |  | : Laltlanmawia, Kolasib
Sl. No. | Components of Works | As per Agreement |  | 7: Achievement upto previous Month; 9: Achievement for the Monthr; 11: Overall cummulative achievement; 13: Remarks/ Issues
|  | Qty | Unit | Item Amount (lakhs) | Phy Prog (Qty) | Fin Prog (lakh) | Phy Prog (Qty) | Fin Prog (lakh) | Phy Prog (Qty) | Fin Prog (lakh)
1 | 3 |  |  | 4 | 7 | 8 | 9 | 10 | 11 | 12 | 14
1 | Protection work | 77 | Rm | 4: 30.32; 14: Work in progress
2 | Side Drain
| i) LSD | 120 | Rm | 4: 4.11
| ii) ULSD | 24080 | Rm | 4: 22.35; 7: 3000; 11: 3000
3 | Pavement
| i) Subgrade | 24.2 | Km | 4: 84.63; 7: 12.2; 11: 12.2
| ii) GSB | 24.2 | Km | 4: 188.81; 7: 6.2; 9: 1.1; 11: 7.3
| iii) WBM-II | 24.2 | Km | 4: 501.1281
| iv) WBM-III | 24.2 | Km | 4: 492.4852
| v) Prime coat | 24.2 | Km | 4: 117.9918
| vi) Tack coat | 24.2 | Km | 4: 26.6613
| vii) MSS | 24.2 | Km | 4: 661.861
| viii)Shoulders | 24.2 | Km | 4: 27.08
4 | Road marking | 24.2 | Km | 4: 14.93
5 | KM Stone &Road Signs:
| i) Km Stone,Hm Stone etc. | 122 | No | 4: 11.77
| ii) Boundary pillar | 242 | No
| iii) Information & Cautionary Sign | 151 | No | 7: 2; 11: 2
6 | AMC |  |  | 4: 128.26
| GRAND TOTAL |  |  | 4: 2312.3874
| Overall Progress = | 10.1%
Sr.Executive Engineer, PWD.,
Kawrthah Division, Kawrthah.

## LBPD
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY, 2026 ( BUILDING WORKS )
Name of Division: Lunglei Building Project Division, Lunglei
Rs. in Lakh
Sl.no | Name of Scheme | Unit | Approved Cost (Rs.in lakh) | Date of Commencement | Target Date of Completion : | Commulative Progress at the end of last month |  | Achievement of Works during the month |  | Overall Commulative Achievement |  | Remarks | Mode of Tender
| Name of Work/Project |  |  |  |  | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
SASCI
1 | Construction of Laboratory Building at Civil Hospital, Lunglei (1st & 2nd Floor) Supplementary Works |  | 396 | 28.10.2022 | 28.4.2024 | 100% | 330.7 |  | 0 | 100% | 330.7 | Civil Works completed and I/E not yet started | Supplementary Works to sl.no(a) above
2 | Construction of Futsal ground at Lungdai, Kawnpui, Ngopa, Kawlkulh, Champhai, Serchhip & Siaha (Sh: Construction of Futsal Ground at Siaha)
1 | Construction of Meisatla Futsal Ground at Siaha |  | 34.786 | 20.03.23 | 20.09.23 | 49% | 21.84 | 0% | 0 | 49% | 21.84 | Work not completed due to site dispute | Restricted Tender
3 | Vertical Extention of Market Building at Kamalanagar |  | 124.52 | 23.03.24 | 31.12.2025 |  | 50.51 |  | 0 |  | 50.51 |  | Restricted Tender
1 | Vertical Extension of existing Bazaar Building at Kamalanagar-I with Tin Roofing |  |  |  |  | 75% |  | 5% |  | 80% |  | Work in Progress
2 | Construction of additional Bazaar Building by demolishing the existing dilapidated building that was constructed under BADP |  |  |  |  | 80% |  | 5% |  | 85% |  | Work in Progress
3 | 2. Construction of Rest House at PWD Complex Bunghmun. |  |  |  |  | 78% |  | 7% |  | 85% |  | Work in Progress
4 | Construction of Community Hall cum Health Clinic Center at Kawlhawk, Bungtlang West, South Lungdai and Serte |  | 10 | 23.03.24 | 23.07.25 |  | 0 |  | 0 |  | 0 |  | Restricted Tender
1 | Construction of Badminton Hall at Chhipphir |  |  |  |  | 95% |  | 5% |  | 100% |  | Completed
2 | Completion of Badminton Hall at Chhipphir |  |  |  |  | 95% |  | 5% |  | 100% |  | Completed
5 | Construction of Government Quarters (General Pool) at Venglai, Lunglei (Ramnghaka's Quarters Site) SH : Type-IV Quarters (2 units, 1 Block) |  | 248.83 | 13.05.2025 | 13.05.2026 | 36% | 43.83 | 9% | 0 | 45% | 43.83 | Work in Progress | Restricted Tender
6 | Construction of Government Quarters (General Pool) at Venglai, Lunglei (Soil Quarters Site) SH : Type-III Quarters (1 unit) Type-IV Quarters (2 units) |  | 256.29 | 14.05.2025 | 14.05.2026 | 45% | 45.74 | 10% | 49.26 | 55% | 95 | Work in Progress | Restricted Tender
7 | Construction of Government Quarters (General Pool) at Venglai, Lunglei (Zautea's Quarters Site) SH : Type-IV Quarters (1 unit, 1 Block) |  | 94.63 | 19.05.2025 | 19.05.2026 | 20% | 0 | 20% | 0 | 40% | 0 | Work in Progress | Restricted Tender
8 | Construction of GovernmentQuarters (General Pool) at Venglai, Lunglei (Numami's Quarters Site) SH : Type-IV Quarters (1 unit, 1 Block) |  | 94.63 | 13.05.2025 | 13.05.2026 | 100% | 81.89 | - | 8.59 | 100% | 90.48 | Completed | Restricted Tender
9 | Construction of Government Quarters (General Pool) at Venglai, Lunglei (Quarters No. 5 Site) SH : Type-III Quarters (2 units, 1 Block) |  | 155.61 | 13.05.2025 | 13.05.2026 | 35% | 0 | 10% | 0 | 45% | 0 | Work in Progress | Restricted Tender
10 | Construction of Government Quarters (General Pool) at Venglai, Lunglei (Zorini's Quarters Site) SH : Type-III Quarters (2 units, 1 Block) |  | 160.1 | 13.05.2025 | 13.05.2026 | 65% | 54.08 | 8% | 0 | 73% | 54.08 | Work in Progress | Restricted Tender
11 | Construction of Government Quarters (General Pool) at Venglai, Lunglei (Thapa's Quarters Site) SH : Type-III Quarters (2 units, 1 Block) |  | 160.1 | 13.05.2025 | 13.05.2026 | 70% | 44.3 | 8% | 43.11 | 78% | 87.41 | Work in Progress | Restricted Tender
12 | Construction of Government Quarters (General Pool) at Venglai, Lunglei (Pi Marcella's Quarters Site) SH: Type - III Quarters (2 Units) |  | 139.9 | 13.05.2025 | 13.05.2026 | 55% | 30 | 10% | 25 | 65% | 55 | Work in Progress | Restricted Tender
13 | Construction of Government Quarters (General Pool) at Venglai, Lunglei (Pi Marcella's Quarters Site) SH: Type - III Quarters (1 Unit) |  | 99.89 | 13.05.2025 | 13.05.2026 | 98% | 65.94 | 2% | 20.56 | 100% | 86.5 | Work in Progress | Restricted Tender
14 | Construction of Working Women Hostel at Ramthar Veng, Lunglei |  | 1408.7 | 14.05.2025 | 14.05.2027 | 7% | 100 | 3% | 0 | 10% | 100 | Work in Progress | Restricted Tender
15 | Construction of District Prison/Jail,Lunglei |  | 523.87 | 28.04.2025 | 28.04.2026 | 20% | 63.01 | 5% | 0 | 25% | 63.01 | Work in Progress | Restricted Tender
16 | Construction of Revenue Staff Quarters at Hnahthial |  | 206.7 | 29.07.2025 | 29.07.2026 | 10% | 0 | 15% | 0 | 25% | 0 | Work in Progress | Restricted Tender
17 | Construction of DCSO Office & Disaster Management & Rehabilitation Office Associated Parking at Lunglei |  | 1349 | 21.07.2025 | 21.07.2026 | 4% | 0 | 3% | 70 | 7% | 70 | Work in Progress | Restricted Tender
18 | Reconstruction of Thingsai PWD IB |  | 210 | 07.07.2025 | 07.07.2026 | 2% | 0 | 1% | 0 | 3% | 0 | Work in Progress | Restricted Tender
19 | Upgradation of District Research Office at Lunglei |  | 45.02 | 11.08.2025 | 11.08.2026 | 30% | 0 | 15% | 0 | 45% | 0 | Work in Progress | Restricted Tender
20 | Upgradation of District Research Office at Hnahthial |  | 25.8 | 18.08.2025 | 18.08.2026 | 30% | 0 | 5% | 0 | 35% | 0 | Work in Progress | Restricted Tender
21 | Creation of Critical Infrastructure for Mitigation & Prevention of Damages against Natural Disaster in MPL under SASCI Part-I (Cyclone Remal) 2024-2025
| 1. Construction of Hostel Superintendent's Quarters |  | 83.29 | 22.09.2025 | 22.09.2026 | 25% | 0 | 5% | 0 | 30% | 0 | Work in Progress | Restricted Tender
| 2. Construction of Girl's Hostel Building |  | 314.71 | 22.09.2025 | 22.09.2026 | 2% | 0 | 1% | 0 | 3% | 0 | Work in Progress | Restricted Tender
22 | Construction of Government Quarters (General Pool) at Lawngtlai at Additional DC Quarter |  | 148.42 | 28.04.2025 | 28.04.2026 | 30% | 0 | 5% | 0 | 35% | 0 | Work in Progress | Restricted Tender
23 | Construction of Government Quarters (General Pool) at Lawngtlai Electric Veng (near RD Office) |  | 754.19 | 28.04.2025 | 28.04.2026 | 15% | 0 | 2% | 0 | 17% | 0 | Work in Progress | Restricted Tender
24 | Construction of Government Quarters (General Pool) at Lawngtlai Electric Veng (near BDO Office) |  | 258.84 | 05.05.2025 | 05.05.2026 | 15% | 0 | 5% | 0 | 20% | 0 | Work in progress. | Restricted Tender
25 | Construction of Government Quarters (General Pool) at Lawngtlai Electric Veng (near A&T Office) |  | 257.57 | 28.04.2025 | 28.04.2026 | 20% | 0 | 5% | 0 | 25% | 0 | Work in progress. | Restricted Tender
26 | SDO (C) Office & Quarter at Chawngte |  | 95.76 | 20.07.2025 | 20.07.2026 | 0% | 0 | 5% | 0 | 5% | 0 | Work in progress. | Restricted Tender
27 | Construction of Circuit House Under DC Office, Lawngtlai District |  | 1000 | 19.07.2025 | 19.07.2026 | 10% | 0 | 2% | 0 | 12% | 0 | Work in progress. | Restricted Tender
28 | Construction of Office Building Cum Quarters at Lawngtlai (Commissioner of State Tax) |  | 358 | 15.07.2025 | 15.07.2026 | 10% | 0 | 5% | 0 | 15% | 0 | Work in progress. | Restricted Tender
29 | Upgradation of District Research Office at Lawngtlai |  | 24.07 | 11.08.2025 | 11.08.2026 | 100% | 0 | - | 0 | 100% | 0 | Completed | Restricted Tender
30 | Construction of Circuit Houses at Siaha |  | 624.99 | 28.04.2025 | 28.04.2026 | 23% | 0 | 7% | 102.38 | 30% | 102.38 | Work in progress. | Restricted Tender
31 | Construction of Government Quarters (General Pool) at New Siaha at Additional DC Quarters (Inside Gate) |  | 266.88 | 28.04.2025 | 28.04.2026 | 50% | 72.8 | 25% | 0 | 75% | 72.8 | Work in progress. | Restricted Tender
32 | Construction of Government Quarters (General Pool) at New Siaha at Additional DC Quarters (Outside Gate) |  | 279.49 | 28.04.2025 | 28.04.2026 | 72% | 83.99 | 3% | 0 | 75% | 83.99 | Work in progress. | Restricted Tender
33 | Construction of Government Quarters (General Pool) at New Siaha at Additional DC Quarters (Type III) |  | 320.74 | 28.04.2025 | 28.04.2026 | 34% | 65.91 | 16% | 0 | 50% | 65.91 | Work in progress. | Restricted Tender
34 | Construction of Government Quarters (General Pool) at New Siaha at Meisavaih Site-I (Type III, 4 unit) |  | 321.75 | 28.04.2025 | 28.04.2026 | 35% | 74.93 | 15% | 0 | 50% | 74.93 | Work in progress. | Restricted Tender
35 | Construction of Government Quarters (General Pool) at New Siaha at Meisavaih Site-II (Type III, 4 unit) |  | 321.9 | 28.05.2025 | 28.05.2026 | 65% | 81.1 | 5% | 0 | 70% | 81.1 | Work in progress. | Restricted Tender
36 | Construction of District Prison/Jail, Siaha |  | 1014.82 | 28.04.2025 | 28.04.2026 | 50% | 249.34 | 10% | 0 | 60% | 249.34 | Work in progress. | Restricted Tender
37 | SDO (C) Office & Quarters at Tipa |  | 91.57 | 07.07.2025 | 07.07.2026 | 19% | 0 | 21% | 0 | 40% | 0 | Work in progress. | Restricted Tender
38 | Upgradation of District Research Office at Siaha |  | 24.07 | 18.08.2025 | 18.08.2026 | 100% | 0 | - | 0 | 100% | 0 | Completed | Restricted Tender
1 | NABARD
CONSTRUCTION OF WAREHOUSES WITH ASSOCIATED INFRASTRUCTURE IN 12 LOCATIONS UNDER NABARD
| GROUP- III: | [11 empty] | Restricted Tender
| 1) Siaha SDC |  | 444.99 | 17.07.2023 | 31.3.2026 | 61% | 212.89 | 0% | 0 | 61% | 212.89 | No progress during month
| 2) Chapui |  | 197.82 | 17.07.2023 | 28.2.2026 | 90% | 101.53 | 2% | 0 | 92% | 101.53 | Works in progress.
1 | 3) Bungtlang South |  | 162.63 | 17.07.2023 | 31.12.2025 | 95% | 132.17 | 1% | 0 | 96% | 132.17 | Works near to completion | Restricted Tender
| GROUP- IV: | [11 empty] | Restricted Tender
| 1) Lungpher |  | 197.12 | 17.07.2023 | 17.7.2025 | 100% | 196.8 | - | 0 | 100% | 196.8 | Civil Works completed and I/E not yet started
| GROUP- VI: | [11 empty] | Restricted Tender
| 1) South Vanlaiphai |  | 187.15 | 17.07.2023 | 19.11.2025 | 85% | 117.29 | 2% | 0 | 87% | 117.29 | Works in progress.
| 2) Vawmbuk |  | 197.82 | 17.07.2023 | 31.12.2025 | 85% | 160.69 | 3% | 0 | 88% | 160.69 | Works in progress.
| GROUP-VIII: | [11 empty] | Restricted Tender
| 1) Hnahthial |  | 197.24 | 17.07.2023 | 19.07.2027 | 10% | 44.46 | 1% | 0 | 11% | 44.46 | Works in progress
| 2) Thingsai |  | 160.32 | 17.07.2023 | 13.10.2025 | 80% | 92.94 | 2% | 0 | 82% | 92.94 | Works in progress
| 3) Cherhlun |  | 85.61 | 17.07.2023 | 17.7.2025 | 97% | 67.46 | 1% | 0 | 98% | 67.46 | Works near to completion | Restricted Tender
| 4) Siata |  | 197.82 | 17.07.2023 | 31.12.2025 | 93% | 76.46 | 1% | 0 | 94% | 76.46 | No progress during the month | Restricted Tender
| GROUP-X: | [11 empty] | Restricted Tender
| 1) Vaseikai |  | 220.35 | 17.07.2023 | 20.12.2025 | 89% | 196.51 | 1% | 0 | 90% | 196.51 | Works in progress
| 2) Tlabung |  | 93.84 | 17.07.2023 | 13.12.2025 | 98% | 59.52 | 1% | 0 | 99% | 59.52 | Works near to completion
2 | Construction of Infrastructure Support for School of Agricultural Science at Hnahthial (Phase-II) | [10 empty] | Handover in process | Restricted Tender
| i) Boys Hostel |  | 659.4 | 08.04.2023 | 19.12.2025 | 100% | 342.5 |  | 0 | 100% | 342.5
| ii) Staff Quarter Type - III |  |  |  |  | 100% |  |  |  | 100%
| iii) Staff Quarter Type - II |  |  |  |  | 100% |  |  |  | 100%
| iv) Guest House |  |  |  |  | 100% |  |  |  | 100%
NEC
1 | Construction of Lunglei Market and Trade Centre at Electric/ Chanmari Veng, Lunglei |  | 1403.4 | 25.08.2022 | 16.01.2026 | 90% | 1082.33 | 4% | 0 | 94% | 1082.33 | Work in progress | Restricted Tender
CSS
1 | Construction of Academic Building for Nursing School at Lunglei (Upgradation) | - | 441.35 | 19.8.2024 | 19.08.2026 | 66% | 156.74 | 2% | 0 | 68% | 156.74 | Works in progress | Open Tender
2 | Construction of Fire Station at Lunglei, Mizoram |  | 195.2 | 04.08.2025 | 04.08.2026 | 4% | 0 | 3% | 0 | 7% | 0 | Work in Progress | Restricted Tender
3 | Construction of Fire Station at Hnahthial |  | 197.57 | 13.10.2025 | 13.10.2026 | 3% | 0 | 4% | 0 | 7% | 0 | Work in Progress | Restricted Tender
4 | Construction of Fire Station at Lawngtlai, Mizoram |  | 196.9 | 04.08.2025 | 04.08.2026 | 16% | 0 | 14% | 0 | 30% | 0 | Work in progress. | Restricted Tender
5 | Construction of Fire Station at Council Vaih, Siaha |  | 207.9 | 04.08.2025 | 04.08.2026 | 20% | 0 | 20% | 0 | 40% | 0 | Work in progress. | Restricted Tender
NEDP
1 | Construction of DC Bungalow (Type VI) at Siaha |  | 110.92 | 26.11.2018 | 23.05.2024 (Revised) | 100% | 109 | - | 0 | 100% | 109 | Handover in process | Restricted Tender
2 | Construction of DC Office Building at Siaha |  | 610.12 | 31.10.2018 | 31.12.2025 | 100% | 521.62 | - | 18.58 | 100% | 540.2 | Completed | Restricted Tender
NESIDS
1 | Construction of 50-Bedded District Hospital Complex and Procurement of Equipment at Hnahthial, Mizoram |  | 1378.86 | 25.6.2024 | 25.12.2026 | 37% | 148.83 | 2% | 0 | 39% | 148.83 | Work in progress | Open Tender
MINISTRY OF TRIBAL AFFAIRS
1 | Construction of Auditorium at Pukpui Lunglei |  | 523 | 16.9.2023 | 16.01.2025 | 0% | 0 | 2% | 0 | 2% | 0 | Work in progress | Restricted Tender
Sr. Executive Engineer, PWD.,
Lunglei Building Project Division, Lunglei
Sr. Executive Engineer, PWD.,
Lunglei Building Project Division, Lunglei

## LRD - I
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY 2026
Name of work |  | : | Rehabilitation of Aizawl - Thenzawl - Lunglei Road (100 - 164 Kmp) (Carriageway Width = 5.50m)
(Sh : Between 143.85 - 152.00 Kmp) (Annual Plan 5054)
Name of Contractor |  | : | SLT Infracon Pvt.LTD, Badarpurghat, Hailakandi, 78803,
( Rs. In lakh)
Sl. No. | Details of Works | Unit | Quantity | Approved Cost (Rs. In lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of Works during the month |  | Overall Cummulative achivement |  | Remarks
[7 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Scarifying the existing bituminous road surface | Km | 7.095 | 122.9209 | 24.04.2025 | 24.04.2026 | 3.52 |  | 1.48 |  | 5 |  | Setting up of Plant and Machinery. The delay in work progress was due to the signing of Supplementary Agreement upon redesigning of the road by CRRI
2 | Rolling of existing granular layer | Km | 8.15 | 118.8539 |  |  | 3.5 |  | 1 |  | 4.5
3 | WBM Grading - I | Km | 8.15 | 344.6442 |  |  | 0.3 |  | 3.2 |  | 3.5
| WBM Grading - II | Km | 8.15 | 345.939 |  |  | 0.03 |  | 0 |  | 0.03
5 | Prime Coat | Km | 7.095 | 24.9939
6 | Dense Graded Bituminous Macadam | Km | 7.095 | 409.732
7 | Tack Coat | Km | 7.095 | 12.2921
8 | Bituminous Concrete | Km | 7.095 | 376.97
9 | Earthen Shoulder | Km | 8.15 | 5.5374
10 | Sub surface drain 400mm x 400mm | No | 163 | 9.2421 |  |  | 40 |  |  |  | 40
11 | Scarifying existing PQC | Km | 1.055 | 18.2779 |  |  | 0.98 |  |  |  | 0.98
12 | Dry Lean Concrete | Sqm | 1.055 | 80.075 |  |  | 0 |  |  |  | 0
13 | Cement Concrete Pavement | Cum | 1.055 | 261.3731 |  |  | 0 |  |  |  | 0
14 | Boring with 125mm dia casing pipe | No | 10 | 4.98 |  |  | 0 |  |  |  | 0
15 | Gabion Wall | Rm | 34.45 | 17.937 |  |  | 0 |  |  |  | 0
16 | Toe Wall | Rm | 23.7 | 12.1945 |  |  | 0 |  |  |  | 0
17 | Retaining Wall | Rm | 13.2 | 9.3233 |  |  | 0 |  |  |  | 0
18 | RCC Lined Side Drain | Rm | 1500 | 82.916 |  |  | 0 |  |  |  | 0
| GRAND TOTAL |  |  | 2258.2023 |  |  | 6.43% |  |  |  | 14.21% | 0
MONTHLY PROGRESS REPORT UNDER LUNGLEI ROAD DIVISION - I, LUNGLEI
FOR THE MONTH OF JANUARY/2026
(Rs. in lakh)
Sl. No. | Name of Schemes | Quantity | Unit | Approved Cost (Rs in Lakh) | Date of Commencement | Target Date of Comple-tion | Cumulative Progress at the end of last month |  | Achievement of works during the month |  | Overall Cumulative achievement |  | Remarks | Mode of Tender
| Name of Works / Project | [5 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
SASCI
I | Aizawl-Thenzawl-Lunglei Road Between Kanghmun 'S' and Kikawn, Lunglei Phase-I, (Sh:- Group - A Between 100.00 - 120.00Kmp)
1 | Scarifying existing bituminous | 2129.55 | Sqm | 0.92 | 03.07.2023 | 30.09.2025 | 22554.77 | 9.7 |  |  | 22554.77 | 9.7 | Work completed. Deviation approval vide No.B-17024/91/CE-R/25/PW/153 of 24.9.2025
2 | Water Bound Macadam | 726.31 | Cum | 40.67 |  |  | 6745.29 | 377.74 |  |  | 6745.29 | 377.74
3 | OPC + Prime Coat | 14063.5 | Sqm | 66.09 |  |  | 15533.14 | 73 |  |  | 15533.14 | 73
4 | Seal coating + Tack Coat | 110000 | Sqm | 195.8 |  |  | 15533.14 | 27.65 |  |  | 15533.14 | 27.65
5 | DLC | 660.83 | Cum | 49.63 |  |  | 185.19 | 13.91 |  |  | 185.19 | 13.91
6 | PQC | 991.237 | Cum | 208.16 |  |  | 241.35 | 50.68 |  |  | 241.35 | 50.68
7 | RCC Hume Pipe Culvert | 1 | No | 9.9 |  |  | 1 | 9.9 |  |  | 1 | 9.9
8 | Lined Side Drain | 147.34 | Cum | 8.89 |  |  | 26.33 | 0.54 |  |  | 26.33 | 0.54
9 | Side Drain Clearance | 20000 | Rm | 18 |  |  | 20000 | 18 |  |  | 20000 | 18
10 | Clearing Road Side Jungle | 40 | Km | 4.36 |  |  | 40 | 4.36 |  |  | 40 | 4.36
11 | Breast Wall + Lined Side Drain with RCC Cover | 635.96 | m | 44.67 |  |  | 677.51 | 61.59 |  |  | 677.51 | 61.59
| TOTAL = |  |  | 647.09 |  |  | 100% | 647.07 |  |  | 100% | 647.07
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY 2026
Name of work |  | : | Construction of Approach Road for Engineering College at Pukpui, Lunglei, Mizoram (State Fund)
( Rs. in lakh)
Sl. No. | Details of Works | Unit | Quantity | Approved Cost (Rs. In lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of Works during the month |  | Overall Cummulative achivement |  | Remarks
[7 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Clearing and Grubbing Road Land | Hec | 0.378 | 0.73767 | 19.01.2026 | 19.01.2027 |  |  | 0.38 |  | 0.38 |  | Work in Progress
2 | Formation Cutting (Widening & Lowering) | Km | 2.73 | 19.3059 |  |  |  |  | 2.73 |  | 2.73
3 | Subgrade & Earthen Shoulder | Km | 2.73 | 56.928 |  |  |  |  | 0 |  | 0
4 | GSB | Km | 2.73 | 97.8359 |  |  |  |  | 0 |  | 0
5 | DLC | Km | 2.73 | 121.0032 |  |  |  |  | 0 |  | 0
6 | CC Pavement | Km | 2.73 | 421.3115 |  |  |  |  | 0 |  | 0
7 | Interlocking Concrete Block | Sqm | 4335.5 | 118.4459 |  |  |  |  | 0 |  | 0
8 | RCC Lined Side Drain | Km | 2.731 | 71.2943 |  |  |  |  | 0 |  | 0
9 | Hume Pipe Culvert | Nos | 8 | 57.8596 |  |  |  |  | 0 |  | 0
10 | RCC Causeway | Nos | 2 | 8.324 |  |  |  |  | 0 |  | 0
| GRAND TOTAL |  |  | 973.0458 | [6 empty] | 2.06%
MONTHLY PROGRESS REPORT UNDER LUNGLEI ROAD DIVISION - I, LUNGLEI
FOR THE MONTH OF JANUARY/2026
(Rs. in lakh)
Sl. No. | Name of Schemes | Quantity | Unit | Approved Cost (Rs in Lakh) | Date of Commencement | Target Date of Comple-tion | Cumulative Progress at the end of last month |  | Achievement of works during the month |  | Overall Cumulative achievement |  | Remarks | Mode of Tender
| Name of Works / Project | [5 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
ANNUAL PLAN (5054)
I | Construction of Bailey Bridge (SS) Over R.Sazek on Mauzam to New Sachan Road (Sh: Construction of Abutment & Wingwall)
| 1) Abutment Wall | 2 | Nos | 42.2 | 24.02.2025 | 31.03.2026 | 100% | 58.68 |  |  | 100% | 58.68 | Completed
| 2) Wing Wall | 1 | No |  |  |  | 100% |  |  |  | 100% |  | Completed
| 3) Gabian Wall | 3 | Nos |  |  |  | 100% |  |  |  | 100% |  | Completed
| 4) Steel Structure | 1 | No | 24.66 |  |  | 0% |  |  |  | 0% |  | Material Collection
| TOTAL = |  |  | 66.86 |  |  | 75% | 58.68 |  |  | 75% | 58.68
Sr. Executive Engineer, P.W.D.,
Lunglei Road Division-I, Lunglei

## LRD-II
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY, 2026
Name of Division: Lunglei Road Division-II, Lunglei
Source of Funding : SASCI
Sl. No | Name of Work/Scheme | Unit | Approved Cost (Rs. In Lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last Month |  | Achievement of Works during the Month |  | Overall Cummulative achievement |  | Remarks | Mode of Tender
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
I | SASCI
1 | Improvement and Widening of Public Playground at Zobawk including Construction of Retaining wall | Rm | 35 | 27.12.2023 | 26.12.2024 | 1% | 0 | 50% | 0 | 51% | 0 | Not yet started. EOT granted upto 28.02.2026 | Restricted Tender
Sr. Executive Engineer, PWD.,
Lunglei Road Division-II, Lunglei

## LAWNGTLAI DIV
Monthly Progressive Reportof 5054 (R&B) & SASCI for the Month of JANUARY 2026
Name of Division |  | : | Lawngtlai Division
Slno | Name of Work/Project | Unit (km) | Approved Cost (Rs.in lakh) | Date of Commencement | Target Date of Completion | Cumulative Progress at the end of last month |  | Achievement of Work During the Month |  | Overall Cumulative Achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
SASCI ( 2022-2023 & 2023-2024)
1 | Improvement of Thlengang to River Chhimtuipui Road ( Construction of RCC Dock Along with Approach Slab) | 2Nos | 23.31 | 11.05.2023 | 31.05.2024 | 100% | 23.31 |  |  | 100% | 23.31 | Completed | Item Rate
2 | Widening of Lawngtlai to Sahrilui chhuah (Kolodyne River) Balu road | 7.5 km | 94.8 | 11.05.2023 | 31.05.2024 | 100% | 40.49 |  |  | 100% | 94.8 | Completed | Item Rate
3 | Improvement of Bethel veng to Chengkawllui Road at College veng, Lawngtlai | 1.6 Km | 90.84 | 11.05.2023 | 31.05.2024 | 100% | 90.83 |  |  | 100% | 90.83 | Completed | Item Rate
4 | Formation cutting of Vathuampui to Mautlang Road | 8.00Km | 70.47 | 11.05.2023 | 31.05.2024 | 100% | 70.42 |  |  | 100% | 70.42 | Completed | Item Rate
5 | Widening of Bungtlang 'S' to Saikhawthlir Road | 5.00Km | 56.15 | 11.05.2023 | 31.05.2024 | 100% | 50.13 |  |  | 100% | 50.13 | Completed | Item Rate
6 | Widening of Hmawngbu to Kakichhuah Road | 7.50Km | 61.99 | 11.05.2023 | 31.05.2024 | 100% | 61.97 |  |  | 100% | 61.97 | Completed | Item Rate
7 | Improvement of Diltlang to Chawngtelui road (Construction of Retaining wall at certain locations) | 51.50Km | 25.07 | 11.5.2023 | 31.05.2024 | 51.5 | 25.07 |  |  | 100% | 25.07 | Completed | Item Rate
8 | Resurfacing of NH-54 to DTO Office (including courtyard) at Chanmari, Lawngtlai | 50.00m | 6.997 | 11.5.2023 | 31.05.2024 | 50 | 6.997 |  |  | 100% | 6.997 | Completed | Item Rate
9 | Construction of Minor Bridge between Khawmawi Bazar veng to Khawmawi vengthar | 1No | 34.48 | 11.5.2023 | 31.05.2024 | 1 No | 34.47 |  |  | 100% | 34.47 | Completed | Item Rate
10 | Blacktopping of Internal road at Lawngpuighat | 0.8Km | 81.65 | 11.5.2023 | 31.05.2024 | 0.8 | 81.63 |  |  | 100% | 81.63 | Completed | Item Rate
11 | Construction of Playground approach road at Thingfal Mamte veng | 420.00m | 19.49 | 11.5.2023 | 31.05.2024 | 420 | 19.49 |  |  | 100% | 19.49 | Completed | Item Rate
12 | Town extension Road at Electric Veng, Lawngtlai | 280Rm | 22.81 | 26.02.2024 | 31.12.2024 | 100% | 21.13 |  |  | 100% | 21.13 | Completed | Item Rate
13 | Construction of RDC road to Roliana Tuikhur at Lawngtlai | 122.00Rm | 9.96 | 26.02.2024 | 31.12.2024 | 100% | 9.45 |  |  | 100% | 9.45 | Completed | Item Rate
14 | Construction of Retaining Wall with steps at Bazar Thlanmual Road, Lawngtlai | 60.00Rm | 20 | 26.02.2024 | 31.12.2024 | 100% | 19.23 |  |  | 100% | 19.23 | Completed | Item Rate
15 | PCC Pavement of Internal Village Road at Lawngtlai L-IV | 150.00Rm | 10 | 26.02.2024 | 31.12.2024 | 100% | 9.6 |  |  | 100% | 9.6 | Completed | Item Rate
16 | Town extension Road at Lawngtlai L-III | 110.00Rm | 7.2 | 26.02.2024 | 31.12.2024 | 100% | 6.86 |  |  | 100% | 6.86 | Completed | Item Rate
17 | Construction of Culvert at Council veng to Bazar Road, Lawngtlai | 1No | 20 | 26.02.2024 | 31.12.2024 | 100% | 19.25 |  |  | 100% | 19.25 | Completed | Item Rate
18 | Village extension Road at Vaivakawn, Vawmbuk | 1.6 Km | 10 | 26.02.2024 | 31.12.2024 | 100% | 9.53 |  |  | 100% | 9.53 | Completed | Item Rate
19 | Internal Road Pavement (Approach road to PWD Rest House at Chawnhu) | 200.00Rm | 6.7 | 26.02.2024 | 31.12.2024 | 100% | 6.43 |  |  | 100% | 6.43 | Completed | Item Rate
20 | Construction of Side Drain near Piangliana Residence at Mualbu 'L' | 165.00Rm | 3.2 | 26.02.2024 | 31.12.2024 | 100% | 3.04 |  |  | 100% | 3.04 | Completed | Item Rate
21 | Approach Road Between PMGSY Road to Kawnkhua | 930.00Rm | 7.4 | 26.02.2024 | 31.12.2024 | 100% | 7.07 |  |  | 100% | 7.07 | Completed | Item Rate
22 | Construction of PCC Pavement from Nimaichondro House to Primary School at Ngunling khua | 80.00Rm | 4.5 | 26.02.2024 | 31.12.2024 | 100% | 3.96% |  |  | 100% | 3.96 | Completed | Item Rate
23 | Construction of Culvert at Berema Tuikhur to College veng road, Lawngtlai | 1 Nos | 8 | 26.02.2024 | 31.12.2024 | 100% | 7.69 |  |  | 100% | 7.69 | Completed | Item Rate
24 | Widening of Road from Paithar to Sihtlangpui | 6.90 Km | 20 | 26.02.2024 | 31.12.2024 | 100% | 19.39 |  |  | 100% | 19.39 | Completed | Item Rate
25 | Construction of Link Road from upper Saikah to Saikah 'L' | 2.20 Km | 5 | 26.02.2024 | 31.12.2024 | 100% | 4.74 |  |  | 100% | 4.74 | Completed | Item Rate
26 | Construction of Retaining Wall at College Veng, Lawngtlai | 18.00 Rm | 9 | 26.02.2024 | 31.12.2024 | 100% | 8.63 |  |  | 100% | 8.63 | Completed | Item Rate
27 | Construction of Link Road from Chawntlangpui to Khuailuichhuah | 4.80 Km | 75 | 26.02.2024 | 31.12.2024 | 100% | 72.01 |  |  | 100% | 72.01 | Completed | Item Rate
Restoration of Damage Due to Cyclone Remal under Lawngtlai Division
1 | (i) Restoration of collapsed road formation by Construction of Gabion wall at 1.400 kmp on DEO office to V.Zathanga Ground at L-IV, Lawngtlai | 17.00 Km | 20.62 | 09.07.2025 | 09.01.2026 | 0% | 0 | 100% |  | 100% | 0 | Physically Completed | Item Rate
2 | (ii) Restoration of collapsed road formation by Construction of Retaining Wall at various locations on Thingfal-Mamte-Thlengang-Tuipui Road | 34.50 Km | 19.14 | 09.07.2025 | 09.01.2026 | 100% | 0 |  |  | 100% | 0 | Physically Completed | Item Rate
3 | (iii) Restoration of collapsed road formation by Construction of Retaining Wall at various locations on Nalkawn to Chamdur Valley Road | 41.80 Km | 26.79 | 09.07.2025 | 09.01.2026 | 80% | 0 | 20% |  | 100% | 0 | Physically Completed | Item Rate
4 | (iv) Restoration of collapsed road formation by Construction of Gabion wall at 3.200 kmp on Lawngtlai to Tuipui Ferry Road | 45.00 Km | 23.45 | 09.07.2025 | 09.01.2026 | 40% | 0 | 60% |  | 100% | 0 | Physically Completed | Item Rate
5 | (v) Restoration of collapsed road formation at 6.700 kmp on Lawngtlai to Tuipui Ferry Road (Sh: Construction of Gabion wall, re-construction of HP culvert & Repair of pavement) | 22.00 Km | 39.16 | 09.07.2025 | 09.01.2026 | 60% | 0 | 40% |  | 100% | 0 | Physically Completed | Item Rate
5054 Co under Road & Bridge
1 | Construction of Slab Culverts on chawnhu 132/33 Kv Power Station Road & Approach Road to Chengkawltlang at Council Veng, Lawngtlai under 5054 | 6 Nos | 24.76 | 28.11.2024 | 03.06.2025 | 6 Nos | 24.76 |  |  | 6 Nos | 24.76 | Completed | Item Rate
2 | Blacktopping of Approach Road to Field at Diltlang South | 0.34 | 13.94 | 30.11.2025 | 21.03.2026 |  |  |  |  | 0% | 0 |  | Item Rate
3 | Widening of Pavement, Patch repair & Seal Coating of DTO Office to Down Town English School | 0.76 | 15.49 | 30.11.2025 | 21.03.2026 |  |  |  |  | 0% | 0 |  | Item Rate
4 | Patch repair & Seal Coating of 71 RCC to PHE Tanky at Chawnhu ( Phase-I) | 1.3 | 16.01 | 30.11.2025 | 21.03.2026 |  |  |  |  | 0% | 0 |  | Item Rate
5 | Patch repair & Seal Coating of MMTP Complex to Chawnh Kawn ( Southern Circle Office to Chawnhu Kawn) | 0.76 | 15.67 | 30.11.2025 | 21.03.2026 |  |  |  |  | 0% | 0 |  | Item Rate
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY 2026
Name of Division |  |  | : | LAWNGTLAI DIVISION
Source of funding&Name of work/Project |  |  | : | NABARD/ Improvement and Strengthening of Nalkawn - Chamdur Valley (NCV) (Section I & II) Road Under NABARD (Rs in lakh)
Sl No | Items of work |  | Unit | Qnty | Approved (Rs in lakh) | Date of commencement | Target dateof completion | Cummulative progress at the end of last month |  | Achievement of Works during the month |  | Overall cummulative achievement |  | Remarks | Mode of contract
[8 empty] | Physical | Fin | Physical | fin | physical | fin
1 | 2 |  | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Clearance of permanent landslip |  | cum | 16390.36 | 14.1 | 09.08.2019 | 31.12.2024 | 16390.36 | 14.1 |  |  | 16390.36 | 14.1 | Proposed for Terminationas per Review Meeting on 24.09.2025 | Item rate
2 | Retaining Wall |  | 3: rm; 4: 136; 5: 65.6; 8: 128; 9: 56.43; 12: 123; 13: 56.43
3 | H/P Culvert |  | 3: nos; 4: 34; 5: 240.3; 8: 34; 9: 240.3; 12: 34; 13: 240.3
4 | Pavement Works:-
a) | Sub Grade |  | 3: km; 4: 13.57; 5: 24.93; 8: 13.57; 9: 24.93; 12: 13.57; 13: 24.93
b) | WBM - I |  | 3: km; 4: 39.1; 5: 513.19; 8: 39.1; 9: 513.19; 12: 39.1; 13: 513.19
c) | WBM - II |  | 3: km; 4: 46.94; 5: 616.14; 8: 46.94; 9: 616.14; 12: 46.94; 13: 616.14
d) | Surface Course |  | 3: km; 4: 38.54; 5: 853.94; 8: 8; 9: 143.92; 12: 8; 13: 143.92
5 | Unlined Side Drain |  | 3: km; 4: 39; 5: 30.03; 8: 39; 9: 30.03; 12: 39; 13: 30.03
2358.23
| 3% Contingencies = |  | 5: 70.75; 9: 55.96; 13: 55.96
| 8% GST = |  | 5: 187.23; 9: 129.69; 13: 129.69
| 1% Labour cess = |  | 5: 0.2; 9: 0.2; 13: 0.2
| Grand Total = |  | 5: 2616.41; 9: 1824.89; 12: 71.04%; 13: 1824.89
* Physical progress percentege is updated considering weightage of each items .

## LLI ELEC DIV
MONTHLY PROGRESSIVE REPORT FOR THE MONTH OF JANUARY 2026
FOR WORKS UNDER STATE PLAN FUND
Name of Division : PWD Electrical Division,Lunglei.
Source of funding : State funding | [11 empty] | Rs in Lakhs
Sl No | Name of works/Project | Unit | Approval Cost(Rs in lakh) | Date of Commencement | Target Date of comp- letion | Cumulative Progress at the end of last month |  | Achievement of works during the Month |  | Overall Cumulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy. | Fin. | Phy. | Fin. | Phy. | Fin.
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | 8443-108-PW Deposit-III
| a) I/E to DC Bungalow(Type-VI) at Siaha. |  | 8.2 |  |  | 100% |  | 0% |  | 100% |  | Completed | Departmental
| b) I/E to Laboratory Building at Civil Hospital, Lunglei. (SH: First Floor,Second Floor & Third Floor) |  | 24.5 |  |  | 100% |  | 0% |  | 100% |  | Completed | Departmental
| c) SITC of 8 Passenger Lift for (G+3) Laboratory Building at Civil Hospital, Lunglei. |  | 40 | 2025-05-29 | 25.March/2026 | 100% |  | 0% |  | 100% |  | Completed | Contractor
| d) I/E to EE (PWD) Quarter at Hnahthial. |  | 6.19 |  |  | 100% |  | 0% |  | 100% |  | Completed | Departmental
2 | 4408 C.o on Food,storage & Warehouse.
| a) I/E to Staff Quarter(2 units) at Vaseikai,Lawngtlai District. |  | 5.4 |  |  | 0% |  | 40% |  | 40% |  | Material received building not yet ready for I/E works | Departmental
| b) I/E to 500MT Go-Down at Vaseikai,Lawngtlai District. |  | 5.37 |  |  | 0% |  | 0% |  | 0% |  | Material received | Departmental
| c) I/E to 250MT Go-Down at Tlabung,Lunglei District. |  | 4.22 |  |  | 40% |  | 60% |  | 100% |  | Completed | Departmental
3 | Deposit
| a) I/E to Staff Quarter(Type-II,2-Units)for Land Revenue & Settlement Department at Lunglei.. |  | 4.27 |  |  | 0% |  | 0% |  | 0% |  | Materials awaited | Departmental
4 | SASCI FUND ACCOUNT
| a) I/E to Szairep Community Hall at Sairep. |  | 1.273 |  |  | 70% |  | 30% |  | 100% |  | On going works | Departmental
| b) I/E to DM High School at Theiriat,Lunglei. |  | 2.194 |  |  | 100% |  | 0% |  | 100% |  | Completed | Departmental
| c) I/E to Market Building at Luangmual,Lunglei. |  | 5.034 |  |  | 100% |  | 0% |  | 100% |  | Completed | Departmental
| d) I/E to Circuit House at Hnahthial,Mizoram. |  | 31.59 |  |  | 100% |  | 0% |  | 100% |  | Completed | Departmental
| e) I/E to Gov't Quarter(General pool)at Venglai,Lunglei (Numami's Quarter site)Type-IV,1-Unit. |  | 6.9 |  |  | 0% |  | 0% |  | 0% |  | Materials awaited | Departmental
Executive Engineer, P.W.D.,
Electrical Division, Lunglei.

## MAMIT DIV
NAME OF DIVISION : MAMIT
MONTHLY PROGRESS FOR THE MONTH OF : JANUARY 2026
[6 empty] | Physical in % |  |  |  | Financial is Rs in lakh
Sl. No | Name of Schemet | Unit | Approved Cost (in lakhs) | Date of Commence- ment | Target date of Completion | Cummulative Progress at the end of last Month |  | Achievement of works during the month |  | Overall Cumulative achievement |  | Remarks | Mode of Tender
| Name of Work/ Project |  |  |  |  | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
NABARD
1 | Strengthening and Improvement of W.Phaileng to Marpara Road (0.00-30.00 Kmp) Package-I |  | 1854.59 | 15.03.2023 | 17.03.2026 | 87.53% | 858.17 | 9.47% | 0 | 97% | 858.17 |  | Restricted Tender | ` | `
| Price escalation | [5 empty] | 9.61 |  |  |  | 9.61
| Total | [5 empty] | 867.78 |  |  |  | 867.78
2 | Strengthening and Improvement of W.Phaileng to Marpara Road (30.00-80.00 Kmp) Package-II |  | 4778.8 | 15.03.2023 | 17.03.2026 | 75.1% | 3527.93 | 9.4% | 0 | 84.5% | 3527.93 |  | Restricted Tender
| Quality Control | [5 empty] | 32.43 |  | 0 |  | 32.43
| Contingency | [5 empty] | 82.68 |  | 0 |  | 82.68
| Price escalation | [5 empty] | 12.4 |  |  |  | 12.4
| Total | [5 empty] | 3655.44 |  | 0 |  | 3655.44
Sr.Executive Engineer, P.W.D.,
Mamit Division, Mamit

## MMPD
MONTHLY PROGRESS REPORT UNDER MULTI MODAL PROJECT DIVISION FOR THE MONTH OF JANUARY, 2026
SlNo | Name of Scheme | Unit | Approved Cost (in lakhs) | Date of Commencement | Target date of completion | Cumulative progress at the end of last month |  | Achievement of works during the month |  | Overall Cumulative achievement |  | Remarks | Mode of Tender
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
SASCI
Work under SASCI
NABARD
Work under NABARD
NEC
Work under NEC
PMGSY
Work under PMGSY
SEDP
Work under SEDP
CSS
Work under CSS
MoRTH
Work under MoRTH
1 | Construction of 2 Nos Reinforced Earth wall for restoration of road formation collapse at km 11.000 & km 11.050 and re-construction of Box culvert at km 11.000 on NH-502A in the state of Mizoram | mtr | 594.66 | 10.02.2025 | 30.11.2025 | 365 | 554.25 | 92 | 0 | 457 | 554.25 | Physically Completed during Dec 2025 | EPC Mode | 0
2 | STMC on NH 502A (KMMTTP) between Km 0.00 to Km 34.92 in the State of Mizoram | cum | 133.29 | 13.12.2024 | 12.12.2025 | 148452.7 | 81.09 | 862.875 | 0 | 149315.575 | 81.09 | Physically Completed during Dec 2025 | Item Rate. .
3 | STMC on NH 502A (KMMTTP) between Km 34.92 to Km 60.700 in the State of Mizoram | sqm | 99.38 | 13.12.2024 | 12.12.2025 | 207844.98 | 32.94 | 13817.6 | 0 | 221662.58 | 32.94 | Physically Completed during Dec 2025 | Item Rate
4 | STMC on NH 502A (KMMTTP) between Km 60.700 to Km 87.51 in the State of Mizoram | sqm | 106.31 | 13.12.2024 | 12.12.2025 | 243004.16 | 34.15 | 9324.63 | 0 | 252328.79 | 34.15 | Physically Completed during Dec 2025 | Item Rate
5 | STMC on NH 502 from Km 0.000 to Km 27.380 during 2025-2026 in the State of Mizoram | sqm | 162.76 | 09.12.2025 | 08.12.2026 |  |  |  |  | 0 | 0 |  | Item Rate
6 | Construction of new 2-lane Highway from Km 0.00-km 38.00 on NH 54 near Lawngtlai in Mizoram to support Kaladan Multi Modal Transit Transport Project in Phase A of SARDP-NE (pacakge-I) | Km | 43465 | 12.10.2010 | 12.10.2014 | 100% | 42680 |  |  | 100% | 42680 | Work physically Completed on 22.06.2023 | Item Rate
7 | Construction of new 2-lane Highway from km 38.00 to Km 70/00 in Mizoram to support Kaladan Multi Modal Transit Transport Project in Phase A of SARDP-NE (pacakge-II) | Km | 32224 | 12.10.2010 | 30.09.2014 | 100% | 30977 |  |  | 100% | 30977 | Work physically Completed on 30.04.2022 | Item Rate
8 | Construction of new 2-lane Highway from Km 70/00 to Km 99/00 in Mizoram to support Kaladan Multi Modal Transit Transport Project in Phase A of SARDP-NE (pacakge-III) | Km | 37459 | 12.10.2010 | 30.09.2014 | 100% | 36468 |  |  | 100% | 36468 | Work physically Completed on 23.06.2023 | Item Rate
Sr.Executive Engineer, PWD
Multi Modal Project Division
Lawngtlai: Mizoram

## NH - I
Montly Progress Report under National Highway Division-I, PWD., January, 2025
Sl. No | Name of Scheme | Unit | Approved Cost (in lakhs) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall Cummulative achievement |  | Remarks | Mode of Tender
| Name of Work/Project |  |  |  |  | Phy. | Fin. | Phy. | Fin. | Phy. | Fin.
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
SASCI
1 | Construction of Saiphal - Hortoki Road (13.800 km) | Phy in % Fin in lakh | 600 | 15.12.2023 | 15.12.2025 | 60.5% | 314.15 | 2% | 0 | 62.5% | 314.15 | On Going | Restricted tender
2 | Improvement of Approach road at Mamit (NH 44A) Junction to Mamit playgroaund | Phy in % Fin in lakh | 931.57 | 13.06.2025 | 12.06.2027 | 0.5% | - | 5% | - | 5.5% | - | On Going | Restricted tender
3 | Upgradation of Lengpui Airport (Upgradation of Runway to PCN 50) | Phy in % Fin in lakh | 9100 | 01.12.2025 | 31.03.2026 | 12.5% |  | 22.5% | 2000 | 35% | 2000 | On Going | Restricted tender
MoRTH
3 | Short Term Maintenance Contract on NH-44A/108 Rockfall Bypass Between km 0.000 to km 5.135 in the state of Mizoram. (Job No. RW/GHT/NH-44A/MZ/STMC/2024-25/2) | Phy in % Fin in lakh | 20.26 | 28.11.2024 | 27.11.2025 | 100% | 19.79 | 0% | 0.47 | 100% | 20.26 | Completed | Open Tender
4 | Short Term Maintenance Contract on NH-44A/108 Between km 16.670 to km 114.618 in the state of Mizoram. (Job No. RW/GHT/NH-44A/MZ/STMC/2024-25/1) | Phy in % Fin in lakh | 385.6 | 28.11.2024 | 27.11.2025 | 100% | 341.67 | 0% | 43.93 | 100% | 385.6 | Comppleted | Open Tender
5 | Short Term Maintenance Contract on NH-44A/108 Between km 16.670 to km 46.000 in the state of Mizoram. (Job No. RW/GHT/GHT/STMC/MZ/25-26/1) | Phy in % Fin in lakh | 387.79 | 05.12.2025 | 04.12.2026 | 10% | - | 25.33% | - | 35.33% | - | On Going | Open Tender
6 | Short Term Maintenance Contract on NH-44A/108 Between km 46.000 to km 84.350 in the state of Mizoram. (Job No. RW/GHT/GHT/STMC/MZ/25-26/2) | Phy in % Fin in lakh | 383.18 | 05.12.2025 | 04.12.2026 | 10% | - | 15.84% | - | 25.84% | - | On Going | Open Tender
7 | Short Term Maintenance Contract on NH-44A/108 Between km 84.350 to km 114.618 in the state of Mizoram. (Job No. RW/GHT/GHT/STMC/MZ/25-26/3) | Phy in % Fin in lakh | 3498.71 | 05.12.2025 | 04.12.2026 | 10% | - | 14.31% | - | 24.31% | - | On Going | Open Tender
8 | Performance Based Maintenance Contract (PBMC) under National Highway Division-I during 2023-24 on NH-6/54 between km 159/00 to km 178/00 (Length = 19.00 km) in the State of Mizoram. (Job No. 6/54-MZ-2023-24/124) | Phy in % Fin in lakh | 1891.98 | 29.08.2024 | 28.08.2029 | 78.2% | 1513.96 | 0.5% | 0 | 78.7% | 1513.96 | On Going | Open Tender
9 | Construction of Steel Arch (Semi Through) Bridge with Concrete Deck 90m Span Over River Tlawng at km 5.200 on NH-44A in the State of Mizoram on EPC Mode | Phy in % Fin in lakh | 4389.42 | 30.01.2021 | 26.3.2024 | 100% | 4389.43 | 0% | 0 | 100% | 4389.42 | Completed | Open Tender
10 | One Time Improvement of Diverted Road frm km 5.70 to km 19.60 of Old NH-44A (New NH-108) in the State of Mizoram.(Job No.44/MZ/2023-24/123) | Phy in % Fin in lakh | 861.21 | 16.06.2025 | 16.05.2026 | 44% | 93.12 | 48.65% |  | 92.65% | 93.12 | Ongoing | Open Tender
PM-DevINE
11 | Construction of Bamboo Link Road from Lengpui to Saiphal Baboo Plantation (41 km) under PM-DevINE ( Note: Change of Scope approved and Supplemantary Agreement signed. Progress report re-framed as per Change of Scope.) | Phy in % Fin in lakh | 6642 | 21.07.2024 | 19.01.2025 | 85.04% | 4449.91 | 9.21% | 0 | 94.25% | 4449.91 | On Going | Open Tender
Sr. Executive Engneer, PWD., National Highway Division-I Aizawl : Mizoram

## NH - II
MONTHLY PROGRESS REPORT OF NH-2 FOR THE MONTH OF JANUARY 2026
Name of Division : National Highway Division - II
Source of funding : MoRTH Name of Contractor : Nidhi Creative Infrastructure Pvt.Ltd | [9 empty] | Agreement Amount : ` 3,83,29,133.00
Sl No | Name of Work/Project | Item Description | Unit | Approved Cost (Rs in Lakh) | Date of Commencement | Target of Completion | Cummulative Progress at the end of last Month |  | Achievement of works during the Month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[7 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Short Term Maintenance Contract for NH-2 From km 10.000 to km 79.900 (OLD CHAINAGE FROM Km 130.000 TO Km 60.300) in the state of Mizoram. (Job No: RW /GHT/STMC/MZ/25-26/5) | Removal of rank vegetation/weeds and undesirable vegetation from shoulders, embankment slopes upto ROW (both sides) complete in all respects including breaking of clods, rough dressing and disposal of waste material and vegetation at a place outside ROW as per direction of Engineer-In-Charge and as per Maintenance Standards Clause 3.3 (Frequency will be once in a quarter). | sqm | 38329133 | 2025-12-09 | 08.12.2026 | 0 | 0 | 418200 | 493476 | 418200 | 493476 | Ongoing | Item Rate
2 |  | Clearing, cleaning, deepening and reshaping of roadside unlined/kaccha drains and making shallow kaccha lateral drains on shoulders wherever required, including removal and disposal of sediments, extraneous debris and vegetation growth blocking the free flow from site outside ROW with all leads and lifts complete in all respects as directed by the Engineerin-Charge and as per Maintenace Standards Clause no. 3.1 (Frequency of cleaning in urban areas will be quarterly whereas in rural areas, it will be twice in a year i.e. before and after monsoon) | Rm |  |  |  | 0 | 0 | 28700 | 2152500 | 28700 | 2152500
3 |  | Clearing slab/box type culverts and pipe culverts including clearing, cleaning and reshaping of upstream and down stream faces of these culverts within right of way. The job includes disposal of excess material recovered from site including vegetation outside ROW with all leads and lifts complete in all respects as per direction of Engineer-in-Charge. and as per Maintenance Standards Clause 3.1 (Frequency of cleaning will be one time in a year i.e. before start of monsoon). | No |  |  |  | 0 | 0 | 62 | 688386 | 62 | 688386
4 |  | Providing Random Rubble masonry in cement mortar 1:3 for drains, protection walls, boundary wall etc complete in all respect as per Technical Specifications Clause 309 and 1400 and as per directions of Engineer-in-Charge. | Cum |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
5 |  | Repair to all types of damaged stone/brick masonry work in superstructure and substructure of bridges/CD works including dismantling of damaged portion and reconstructing to match with existing pattern without causing any damage to the structure in cement work complete in all respects including testing etc. as directed by the Engineer conforming to MoRTH Specifications Clause no. 1000, 1300 and 1400. The rate quoted should be after due consideration of the salvage value of the dismantled material. | Cum |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
6 |  | Replacement of stolen/missing retro-reflectorised traffic sign boards by providing and fixing new retro reflectorised cautionary, mandatory and informatory sign | No |  |  |  | 0 | 0 | 40 | 0 | 0 | 0
7 |  | Providing and laying reinforced cement concrete pipe NP4/prestressed concrete pipe of 1200 mm dia for culverts on first class bedding of granular material including fixing collar with cement mortar 1:2, excavation, protection works, backfilling, concrete and masonry works in head walls and parapets all complete: | No |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
8 |  | Installation of Thrie Beam Metal Crash Barriers at accident prone location. | Rm |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
9 |  | Providing and marking of hot applied thermoplastic compound 2.5 mm thick including reflectorising glass beads @ 250 gms/sqm area, thickness of 2.5 mm is exclusive of surface applied glass beads as per IRC:35. The finished Surface to be level, uniform and free from streaks and holes complete in all respects. The job includes marking of centre line, shoulder line, edge line, zebra crossing marking, arrows and dashes marking at the junctions as per Technical Specifications Clause 803.4 complete in all respect and as per approval of the Engineer-in-Charge. | Sqm |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
10 |  | Road studs | No |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
11 | Short Term Maintenance Contract for NH-2 From km 10.000 to km 79.900 (OLD CHAINAGE FROM Km 130.000 TO Km 60.300) in the state of Mizoram. (Job No: RW /GHT/STMC/MZ/25-26/5) | Clearance of landslips | cum | 38329133 | 2025-12-09 | 08.12.2026 | 0 | 0 | 212.38 | 20388.48 | 212.38 | 20388.48 | Ongoing | Item Rate
12 |  | Providing treatment and repair to pot holes/ruts of any depth/patch repair of all types of bitumen pavement complete as per Technical Specification Clause 3004.2, and as per direction of Engineer by using paving grade bitumen/emulsion/cold ready mix material. The job includes removal of all failed material, trimming of completed excavation to provide firm vertical faces, cleaning of surface, painting of tack coat on the side and base of excavation as per Clause no. 503, back filling the patch with bituminous material as per Clause no. 509. Compacting trimming and finishing the surface to form a smooth continuous surface all as per Clause no. 3004.2 of Technical Specifications. (Total Area= 2156.25 Sqm, Total month=12 months) | Sqm/Month |  |  |  | 0 | 0 | 178.69 | 186162.82 | 178.69 | 186162.82
13 |  | Providing slurry seal for filling of hair cracks, surface cracks and preventive/renewal treatment as per MoRTH Specification Clause 512. (Total Area= 7762.50 Sqm, Total month=12 months) | Sqm/Month |  |  |  | 0 | 0 | 646.875 | 54777.38 | 646.875 | 54777.38
|  | Total | [5 empty] | 0 |  | 3595690.68 |  | 3595690.68 |  |  | 9.3811
MONTHLY PROGRESS REPORT OF WORKS UNDER 5054 FOR THE MONTH OF JANUARY 2026
Sl. No. | Name of road | Category of road | Length (Km/m) | Amount of Technical Sanction (Rs. Lakh) | Date of Technical Sanction | Financial Progress (Amount Rs. Lakh) |  |  | Physical Progress (in percentage) |  |  | Remarks
[6 empty] | Expenditure upto previous Month | Expenditure during the month | Total Expenditure | Progress upto end of previous Month | Progress during the month | Total Progress
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
1 | Resurfacing of Sakawrdai to Vaitin road | STR | 4.89 Km | 80 | 2025-09-02 | - | - | - | 15% | 50% | 65% | Ongoing
2 | Zohmun to Tinghmun road (8.500) | STR | 8.5 Km | 19.57 | 2025-09-02 | - | - | - | 10% | 30% | 40% | Ongoing
3 | Repair withn GSB Laying from NEEPCO to Mauchar | STR | 800 m | 34.23 | 2025-09-04 | - | - | - | 100% | 0% | 100%
Sr.Executive Engineer, PWD.,
National Highway Division-II
Aizawl : Mizoram

## NH-III
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY, 2026
Name of Division : National Highway Division-III, Thingdawl, Mizoram
Source of funding : MORTH/NH | [11 empty] | Rs in Lakh
Sl No | Name of Work/Project | Unit | Approved Cost (Rs in Lakh) | Date of Commencement | Target Date of Completion | Cumulative Progress at the end of last month |  | Achievement of works during the month |  | Overall Cumulative achievement |  | Remarks | Mode of Contract |  | Jan | 1.13
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Strengthening/Construction/Widening to 2-lane from km 89/00 to km 105/00 of NH-154 (New NH-6) under NH Division III in the state of Mizoram for the year 2022 – 23 (Length = 16 Km ) | Km | 8681 Lakhs | 04.09.2023 | 04.03.2025 | 97.71% | 5069.46 | 1.13% | 0 | 98.84% | 5069.46 | Work in Progress | EPC
2 | Strengthening of NH-154( New NH-06) between km 105.00 and Km 119.00 including bridge repair in the state of Mizoram | Km | 2753.00 lakh | 30.06.2025 | 31.05.2026 | 1% | 0 | 0% | 0 | 1% | 0 | Management Meeting was held on 22.01.2026 in the Chief Engineer's,Highways office and the contractor promise to speed up the progress of work and the progress will be reviewed on 5th.Feb,2026. | EPC
3 | Short Term Maintenance Contract on NH - 306A from km 0.00 to Km 10.00 & from Km 33.00 to Km 45.00 in the State of Mizoram ( Job No. RW/GHT/STMC/MZ/25-26/8) | Km | 443.23 lakh | 09.12.2025 | 08.12.2026 | 0% | 0 | 0% | 0 | 0% | 0 | Work not started | STMC
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY, 2026
Name of Division : National Highway Division-III, Thingdawl, Mizoram
Source of funding : NABARD | [10 empty] | Rs in Lakh
Sl No | Name of Work/Project | Unit | Approved Cost (Rs in Lakh) | Date of Commencement | Target Date of Completion | Cumulative Progress at the end of last month |  | Achievement of works during the month . |  | Overall Cumulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Upgradation of Road from Meidum to Hortoki Phase-I (Km 0.00 to Km 9.10) | Km | 4445 Lakhs | 26.05.2020 | 26.11.2021 1st EOT=211 days (21.11.2021-20.06.2022) 2nd EOT=375 days (21.06.2022-30.06.2023) 3rd EOT=243 days (30.06.2023-28.02.2024) 4th EoT=90 days (20.2,2024-28.5.2024) | 100% | 4356.17 | 0% | 0 | 100% | 4356.17 | completed | Item Rate
2 | Construction of road from Khamrang to Selesih Phase-I (Length =11.00 Kms) Group-A (0/00 to 3/600 Km) | Km | 6583.18 | 08.02.2021 | 08.08.2022 1st EOT=184 days (upto 08.02.2023, 2nd EOT= 150 days (upto 08.07.2023) | 83.33% | 388.92 | 0% | 0 | 83.33% | 388.92 |  | Item Rate
3 | Construction of road from Khamrang to Selesih Phase-I (Length =11.00 Kms) Group-B (3/60 to7/200 Km) | Km |  | 08.02.2021 | 08.08.2022 1st EOT=184 days (upto 08.02.2023; 2nd EOT=150 days (wef 09.02.2023- 08.07.2023) | 88.89% | 704.4 | 0% | 0 | 88.89% | 704.4 |  | Item Rate
4 | Construction of road from Khamrang to Selesih Phase-I (Length =11.00 Kms) Group-C (7/200 to 11/00 Km) | Km |  | 08.02.2021 | 08.08.2022 1st EOT=184 days (upto 08.02.2023; 2nd EOT=150 days (wef 09.02.2023-08.07.2023) | 47.78% | 336.16 | 0% | 18.32 | 47.78% | 354.48 |  | Item Rate
5 | Construction of road from Khamrang to Selesih Phase-I (Sh: Construction of Rigid Pavement from 7/00 to 11/00 Kmp = 4.00 kms) | Km |  | 16.08.2022 | EoT = 336 days upto 18.02.2026 | 25% | 432.6 | 5% | 0 | 30% | 432.6 |  | Item Rate
6 | [6 empty] | 46.89 |  |  |  | 46.89 | Contingency
7 | Construction of MDR from Khamrang (Dilsei) to Selesih (Sh: Constn of approach road to Mualkhang village) | Km | 14529.29 Lakhs | 08.02.2021 | 08.08.2022 | 100% | 122.25 | 0% | 0 | 100% | 122.25 |  | Item Rate
8 | Construction of road from Khamrang to Selesih Phase-II Group-1 (11/00 to 22/00 Km) | Km |  | 08.11.2021 | 08.05.2023 1st EOT=210 days (wef 09.05.2023- 04.12.2023 | 22.15% | 664.75 | 0% | 0 | 22.15% | 664.75 |  | Item Rate
9 | Construction of road from Khamrang to Selesih Phase-II Group-2 (22/00 to 25/00 Km) | Km |  | 22.11.2021 | 22.11.2022 1st EOT=90 days (upto 20.02.2023); 2nd EOT=90 days (wef 21.02.2023-21.05.2023); 3rd EOT=90 days (22.05.2023-19.08.2023) | 62.88% | 386.28 | 0% | 0 | 62.88% | 386.28 |  | Item Rate
10 | Construction of road from Khamrang to Selesih Phase-II Group-3 (25/00 to 28/00 Km) | Km |  | 11.11.2021 | 11.11.2022 1st EOT=104 days (upto 24.02.2023); 2nd EOT=90 days (wef 10.02.2023-11.05.2023) 3rd EOT=90days (Wef 12.05.23-09.08.2023) | 42.96% | 262.85 | 0% | 0 | 42.96% | 262.85 |  | Item Rate
11 | Construction of road from Khamrang to Selesih Phase-II (Sh: - Construction of Rigid Pavement from 11/00 to 19/00 Kmp = 8.00 kms) Group A | Km |  | 26.08.2023 | 26.08.2025 | 0% | 0 | 0% | 0 | 0% | 0 |  | Item Rate
12 | Construction of road from Khamrang to Selesih Phase-II (Sh: - Construction of Rigid Pavement from 19/00 to 28/00 Kmp = 9.00 kms) Group B | Km |  | 26.08.2023 | 26.08.2025 | 0% | 0 | 0% | 0 | 0% | 0 |  | Item Rate
13 | [6 empty] | 1.67 |  | 0.5 |  | 2.17 | Contingency
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY, 2026
Name of Division : National Highway Division-III, Thingdawl, Mizoram
Source of funding : SASCI | [10 empty] | Rs in Lakh
Sl No | Name of Work/Project | Unit | Approved Cost (Rs in Lakh) | Date of Commencement | Target Date of Completion | Cumulative Progress at the end of last month |  | Achievement of works during the month . |  | Overall Cumulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Restoration of damaged due to cyclone remal under Aizawl Road North Division (Part II) & National Highway Division III | Km | 262 | 21.6.2025 | 20.01.2026 | 66.77% | 96.76 | 33.23% | 153.18 | 100% | 249.94 | In progress | Item Rate | 3.07
Sr.Executive Engineer,PWD., National Highway Division-III, Thingdawl : Mizoram

## PD -I
MONTHLY PROGRESS REPORT UNDER EXECUTIVE ENGINEER, PROJECT DIVISION- I, PWD FOR JANUARY 2026
Sl. No. | Name of Scheme | Unit | Approved Cost (in lakhs) | Date of Commencement | Target date of completion | Cummulative progress at the end of last month |  | Achievement of work during the month |  | Overall cummulative achievement |  | Remarks | Mode of Tender
| Name of Work/Project |  |  |  |  | Phy (%) | Fin (₹) | Phy (%) | Fin (₹) | Phy (%) | Fin (₹)
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) | (10) | (11) | (12) | (13) | (14)
A. NEC
1 | C/o of Patient Lodging at Mawdiangdiang near NEIGRIMS, Shillong | 1 | 419.67 | 9.9.21 | 31.7.24 | 97% | 314.75 | 1% | 94.43 | 98% | 409.18 | EOT upto 9.9.25 | Item rate
2 | Co/ Veterinary Information and Resource Centre at Aizawl | 1 | 339.25 | 25.9.23 | 25.9.25 | 92% | 225.46 | 0% | 0 | 92% | 225.46 |  | Item rate
3 | C/o Aizawl Institute of Arts & Music for the NER, Tuivamit Tlang, Aizawl | 1 | 590.23 | 4.9.23 | 4.9.25 | 89% | 517.6842 | 0% | 0 | 89% | 517.6842 |  | Item rate
4 | Establishment of Central Medical Warehouse at Aizawl, Mizoram | 1 | 1101.11 | 14.8.23 | 14.8.25 | 43% | 325 | 2% | 0 | 45% | 325 |  | Item rate
5 | Infrastructure Development of Biotechnology Cell in Mizoram (C/O Building at MINECO | 1 | 188.66 | 10.7.23 | 10.1.25 | 44.8% | 69.55 | 0% | 0 | 44.8% | 69.55 | EOT upto 22.10.25 | Item rate
B. SASCI
6 | C/o Central Medical Warehouse at ZMC, Approach Road SH: Approach Road | 1 | 150 | 16.12.23 | 16.12.24 | 66% | 47.428 | 0% | 0 | 66% | 47.428 |  | Item rate
7 | C/o FCS&CA 1500 MT Capacity Godown at Sairang | 1 | 921.07 | 7.4.23 | 7.4.26 | 85% | 207.6424 | 3% | 0 | 88% | 207.6424 |  | Item rate
8 | Constn. of Govt. Staff Qtrs. (Block-C) at DIET Complex, Chaltlang. | 1 | 544 | 29.4.23 | 29.10.25 | 94.2% | 450.0945 | 0.3% | 0 | 94.5% | 450.0945 |  | Item rate
9 | Re-construction of Central Jail, Aizawl | 7 | 1329 | 16.5.25 | 16.5.26 |  |  |  | 2.3011 |  | 2.3011 |  | Item rate
| a. Vertical extension of Convict Women in Women Jail |  |  |  |  | 13.6% | 0 | 1% | 0 | 14.6% | 0
| b. Vertical extension of male ward |  |  |  |  | 31.1% | 0 | 0.9% | 0 | 32% | 0
| c. Superintendent Quarters |  |  |  |  | 22.8% | 0 | 6.3% | 0 | 29.1% | 0
| d.Male Kitchen & Dining Hall |  |  |  |  | 14.5% | 0 | 2.3% |  | 16.8% | 0
| e. Toilet at UTP Ward Duty Post (Women Prison) |  |  |  |  | 30.7% |  | 0.7% |  | 31.4%
| f. New Male Ward |  |  |  |  | 6.7% |  | 3.9% |  | 10.6%
| g. Medical Inspection Building |  |  |  |  | 6.6% |  | 0% |  | 6.6%
| h. Administration Building |  |  |  |  | 1.7% |  | 0.3% |  | 2%
10 | Construction of Working Women Hostel, Khatla | 1 | 2972 | 24.4.25 | 24.4.26 | 18.4% | 303.3356 | 1.2% | 0 | 19.6% | 303.3356 |  | Item rate
11 | Construction of Integrated Office Complex at MINECO, Aizawl | 1 | 60000 | 23.4.2025 |  | 10% | 195.0654 | 4% | 140 | 14% | 335.0654 |  | Item rate
12 | Construction of Working Women Hostel, ITI Veng, Aizawl | 1 | 1448.36 | 8.4.2025 | 8.4.2026 | 20% | 203.2575 | 0% | 0 | 20% | 203.2575 |  | Item rate
13 | Construction of New Campus for Govt. Aizawl West College Building | 2 |  |  |  | 7.5% | 208.3244 | 3% | 106.9166 | 10.5% | 315.241 |  | Item rate
| a. Administrative Building |  | 572.97 | 9.5.25 | 9.5.26 |  | 0 |  | 0 |  | 0
| b. Academic Building) |  | 201.36 | 9.5.25 | 9.5.26 |  | 208.3244 |  | 106.9166 |  | 315.241
14 | Construction of E-in-C, PHED Office at MINECO, Aizawl | 1 | 796 | 26.6.25 | 26.6.26 | 7.2% | 0 | 1% | 0 | 8.2% | 0 |  | Item rate
15 | Vertical Extension of Mizoram Upa Pawl Hqr. Building for Community Hall & Office at Khatla, Aizawl, Mizoram | 1 | 200 | 26.6.25 | 26.6.26 | 35% | 11.4566 | 1% | 0 | 36% | 11.4566 |  | Item rate
16 | Construction of Building for Additional Classroom at J. Thankima College, Aizawl | 1 | 984 | 4.7.25 | 4.7.26 | 1.6% | 0 | 0.4% | 0 | 2% | 0 |  | Item rate
17 | Construction of Government Residential Quarter Type-VI (4 units) at new Secretariat Complex, Khatla | 1 | 849.66 | 28.3.2025 | 28.3.2026 | 25% | 43.9262 | 7% | 54.0769 | 32% | 98.0032 |  | Item rate
18 | Construction of Government Residential Quarter Type-V (4 units) at new Secretariat Complex, Khatla | 1 | 692 | 25.3.2025 | 25.3.2026 | 25% | 81.0732 | 7% | 0 | 32% | 81.0732 |  | Item rate
19 | Construction of Examination Hall at MPSC Campus | 1 | 1092 | 26.6.25 | 26.6.26 | 9% | 87.5174 | 1% | 0 | 10% | 87.5174 |  | Item rate
20 | Construction of Market Building at Vaivakawn, Aizawl | 1 | 2535 | 5.6.25 | 5.6.26 | 0% | 35.6016 | 1% | 0 | 1% | 35.6016 | Dismantling of existing building in progress | Item rate
21 | Construction of State Emergency Operation Centre (SEOC) at MINECO | 1 | 3825 | 13.5.25 | 13.5.26 | 7.3% | 0 | 2.1% | 0 | 9.4% | 0 |  | Item rate
22 | Construction of MLA Hostel at Tuikual, Aizawl | 1 | 629.17 | 14.8.25 | 14.8.26 | 0.9% | 0 | 0.5% | 0 | 1.4% | 0 | Hindrance occur at work site | Item rate
23 | Vertical Extension of Chief Controller of Accounts Office Main & Annex Building | 1 |  |  |  | 0.9% | 0 | 0.2% | 0 | 1.1% | 0 | Work foreclosed. | Item rate
24 | Construction of Durbar Hall & Personal Branch of Raj Bhavan | 1 | 546.408 | 16.7.2025 | 16.7.2026 | 10% | 68.8758 | 2% | 0 | 12% | 68.8758 |  | Item rate
25 | Construction of Quarters, Barrack & Vertical Extension of DRC Office, Silchar & Sewer line at Mizoram House, Guwahati | 1 | 331 | 23.7.2025 | 23.7.2026 | 15% | 0 | 3% |  | 18% | 0 |  | Item rate
26 | Modernization of Govt Industrial Training Institute (ITI), Aizawl | 1 | 2500 | 28.4.2025 | 28.4.2026 | 25% | 0 | 4% | 202.1529 | 29% | 202.1529 |  | Item rate
27 | Construction of Bru Student Hostel at Tahnril | 1 | 415 | 1.7.2025 | 1.7.2026 | 0% |  | 1% |  | 1% | 0 |  | Item rate
20677111
(1): C. SEDP | 4135422.2 | 3928651.09
28 | Construction of High Court Parking Building at MINECO | 1 | 1960 | 2.7.20 | 29.8.24 | 100% | 1865.6115 | 0% | 0 | 100% | 1865.6115 | EOT upto 17.5.2025 | Item rate | 1400000 | 16748459.91
[14 empty] | 2735422.2 | 15348459.91
D. NABARD
29 | C/O 24 Warehouses with associated Infrastructure in 23 locations in Mizoram under NABARD (Group-II Zuangtui/ Sairang) | 1 | 440.97 | 17.7.23 | 31.3.25 | 99% | 268.3018 | 0% | 0 | 99% | 268.3018 |  | Item rate
E. CSS
30 | Construction of file rack inside record Room of District Court Building at MINECO | 1 | 45.1 | 8.8.25 | 8.9.25 | 100% | 45.1 | 0% | 0 | 100% | 45.1 | Works completed | Item rate
Executive Engineer, PWD
Project Division-I
Aizawl, Mizoram

## PD-II
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY, 2026
Name of Division: Project Division-II, P.W.D
Sl. No. | Name of Schemet | Unit | Approved cost (Rs.in lakh) | Date of Commence-ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Mode of Tender | Remarks
| Name of Work/Project |  |  |  |  | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | . | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 14 | 13
NABARD
1 | Construction of 24 Warehouses with associated Infrastructure in 23 lacations in Mizoram Group-I i) Construction of Warehouse and other amenities at Bairabi (1000 MT) | % | 316.55 | 17.07.2023 | (O)17.07.2025 (R)31.10.2025 | 100% | 185.6 | 0% | 0 | 100% | 185.6 | Item Rate | Work Completed
| ii) Construction of Warehouse and other amenities at Marpara (500 MT) | % | 235.73 | 17.07.2023 | (O)17.07.2025 (R)07.11.2025 | 100% | 167.02 | 0% | 0 | 100% | 167.02 | Item Rate | Work Physically Completed
| iii) Construction of Warehouse and other amenities at Sialsuk SC (200 MT) | % | 171.09 | 17.07.2023 | (O)17.07.2025 (R)11.01.2026 | 100% | 139.74 | 0% | 0 | 100% | 139.74 | Item Rate | Work Physically Completed
| iv) Construction of Warehouse and other amenities at Zawlnuam (200 MT) | % | 176 | 17.07.2023 | (O)17.07.2025 (R)30.11.2025 | 100% | 144.71 | 0% | 0 | 100% | 144.71 | Item Rate | Work Physically Completed
| v) Construction of Warehouse and other amenities at Kanhmun (200 MT) | % | 175.8 | 17.07.2023 | (0)17.07.2025 (R)30.11.2025 | 100% | 143.22 | 0% | 0 | 100% | 143.22 | Item Rate | Work Physically Completed
2 | Construction of 24 Warehouses with associated Infrastructure in 23 lacations in Mizoram Group-IX i) Construction of Warehouse and other amenities at Phuldungsei (200 MT) | % | 175.81 | 17.07.2023 | (O)17.07.2025 (R)10.11.2025 | 100% | 102.87 | 0% | 0 | 100% | 102.87 | Item Rate | Work Physically Completed
NEC
1 | Construction of Market Building at West Phaileng, Mamit District. | % | 278.25 | 22.08.2023 | 22.08.2025 | 90% | 208.69 | 7% | 0 | 97% | 208.69 | Item Rate | Work in Progress (EOT under process)
2 | Construction of Fish Farmers Training Centre at Lengpui | % | 924.32 | 20.06.2025 | 20.06.2027 | 18% | 243 | 12% | 0 | 30% | 243 | Item Rate | Work in Progress. Secured Advance Granted Rs. 243.00 lakh
NESIDS
1 | Construction of 100 Bedded District Hospital at Kolasib. | % | 2200 | 23.09.2022 | ( O) 23.09.2024 (R1) 13.10.2025 (R2) 28.02.2026 | 91% | 1583.92 | 1% | 0 | 92% | 1583.92 | EPC | Work in Progress.
CSS
1 | Construction of Fast Track Court Building at Kolasib. | % | 1799.85 | 20.09.2022 | (O) 20.09.2024 (R1) 18.02.2025 (R2) 31.05.2025 (R3) 31.07.2025 (R4)12.12.2025 | 100% | 1254.25 | 0% | 0 | 100% | 1254.25 | Item Rate | Work in Progress
ICMR
1 | Construction of Model Rural Health Research Unit at Lungtian Ram, Aibawk. | % | 207.5 | 21.09.2023 | 21.03.2025 | 100% | 187.5 | 0% | 0 | 100% | 187.5 | Item Rate | Work Physically Completed. There is a liability of Rs. 20 lakh for payment of the Contractor
SASCI
Work under SASCI 2024 - 2025 Part - I (Untied)
1 | Re-Construction of District Prison at Mamit | % | 453.37 | 14.05.2025 | 14.05.2026 | 20% | 45.08 | 15% | 0.31 | 35% | 45.39 | Item Rate | Work in Progress
2 | Re-Construction of District Prison at Kolasib | % | 751.03 | 27.05.2025 | 27.05.2026 | 60% | 198.44 | 5% | 0 | 65% | 198.44 | Item Rate | Work in Progress
Work under SASCI 2024 - 2025 Part - V
1 | Contruction of Civil SDO Qrts Type - IV at Kawnpui | % | 78.08 | 15.05.2025 | 15.5.2026 | 60% | 30.48 | 5% | 0 | 65% | 30.48 | Item Rate | Work in Progress
2 | Contruction of Civil SDO Qrts Type - IV at Bairabi | % | 82.32 | 15.05.2025 | 15.5.2026 | 90% | 0.7 | 8% | 0 | 98% | 0.7 | Item Rate | Work in Progress
3 | Contruction of Directorate of Economics & Statistics Office at MINECO, Aizawl | % | 207 | 30.04.2025 | 30.04.2026 | 30% | 50 | 10% | 0 | 40% | 50 | Item Rate | Work in Progress
4 | Upgradation of District Research Office at Kolasib | % | 24.03 | 20.08.2025 | 20.08.2026 | 100% | 0 | 0% | 0 | 100% | 0 | Item Rate | Work in Progress
5 | Upgradation of District Research Office at Mamit | % | 71.37 | 20.08.2025 | 20.08.2026 | 8% | 0 | 12% | 0 | 20% | 0 | Item Rate | Work in Progress
Work under SASCI 2024 - 2025 Part - VII (A)
1 | Contruction of Revenue Staff Quarters (Type - II & III) at Kolasib | % | 192.18 | 11.08.2025 | 11.08.2026 | 25% | 26.37 | 15% | 0 | 40% | 26.37 | Item Rate | Work in Progress
2 | Construction of DC Revenue (SO) Office at Mamit | % | 450 | 11.08.2025 | 11.08.2026 | 0% | 0 | 0% | 0 | 0% | 0 | Item Rate | Work yet to be started
3 | Re- Construction of DC Office Complex at Mamit | % | 1000 | 21.07.2025 | 21.07.2026 | 0% | 0 | 0% | 0 | 0% | 0 | Item Rate | Work yet to be started
Work under SASCI 2024 - 2025 Part -X
1 | Contruction of Working Women Hostel at ZMC / H Falkawn, Mizoram | % | 2634.06 | 14.05.2025 | 14.05.2026 | 20% | 216.8 | 2% | 0 | 22% | 216.8 | Item Rate | Work in Progress Secured Advance Granted for Rs. 213.55 lakh
2 | Contruction of Working Women Hostel at Thenzawl | % | 1100 | 15.05.2025 | 15.05.2026 | 16% | 107.11 | 7% | 0 | 23% | 107.11 | Item Rate | Work in Progress Secured Advance Granted for Rs. 104.91 lakh
Deposit Work
1 | Construction of Settlement Officer Quarters (Type-IV) at Kolasib | % | 66.87 | 1.10.2025 | 1.10.2026 | 10% | 0 | 5% | 0 | 15% | 0 | Item Rate | Work in Progress
Sr. Executive Engineer, PWD.,
Project Division-II, Aizawl

## PD- III
MONTHLY PROGRESS REPORT UNDER SPECIAL ASSISTANCE TO STATES FOR CAPITAL EXPENDITURE FOR THE MONTH OF JANUARY 2026
Sl. No. | Name of Project with brief description | Approved Cost (Rs. lakh) | First Installment |  | Second Installment |  | Component-wise break up of the Project | Component-wise Project milestones (Target date of completion) | Financial Progress (component wise in Rs.lakh | Physical Progress (component wise in %age) | Remarks, including Reason for non-achievement of milestone (If applicable)
|  |  | Date of Sanction | Amount (Rs.lakh) | Date of Sanction | Amount (Rs.lakh)
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Name of the Implementing Department : PWD, Project Division-III
1 | Improvement/ Upgradation of Operational/ Non-operational Facilities of Lengpui Airport. (SH : Renovation of Terminal Building) | 2124 | 16.03.2021 | 1577.66 | 19.10.2022 |  | A. Renovation of Terminal Building | 21.10.2023 Extended upto 31.12.2024 | 1773.36 | 99.5% | Work in Progress.
1. Earth Works
2.Dismantling Item
3.PCC works
4.RCC works
5.Brick walling
6.Plastering
7.Tile Flooring
8.Ceiling & Column Panneling with ACP Board
[6 empty] | 537 | 9.Painting with POP
10.Railing (Stainless Steel with Tuffen Glass)
11.Doors & Windows Fittings
12.Temporary Laminated Board Partition
13.Roof Treatment
14.Sanitary fittings
B.Sub-Surface Cable Channel
C.Roof Extension (LS)
MONTHLY PROGRESS REPORT UNDER SPECIAL ASSISTANCE TO STATES FOR CAPITAL EXPENDITURE FOR THE MONTH OF DECEMBER 2025
Sl. No. | Name of Project with brief description | Approved Cost (Rs. lakh) | First Installment |  | Second Installment |  | Component-wise break up of the Project | Component-wise Project milestones (Target date of completion) | Financial Progress (component wise in Rs.lakh | Physical Progress (component wise in %age) | Remarks, including Reason for non-achievement of milestone (If applicable)
|  |  | Date of Sanction | Amount (Rs.lakh) | Date of Sanction | Amount (Rs.lakh)
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Name of the Implementing Department : PWD, Project Division-III
1 | Const of 100 Bedded Dist hospital at Saitual ( Sh: Cons of OPD building at district hospital, Saitual) | 200 | 22.3.2022 | 200 |  |  | 1 Building portion with water supply & sanitary fittings. 2. Underground Sump (20,000 ltrs capacity) | 13.10.2025 | 193.92 | 100% | Work Completed
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Gov't Serchhip College ( Sh: Administrative Block) | % | 650 | 27.2.2023 | 27.2.2025 | 98% | 245.67 | 0.5% | 0 | 98.5% | 245.67 | Work in Progress | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Const. of Football ground and volleyball court at Vapar, Selam, tualcheng, Hnahla. Hmunhmeltha | % | 203 | 13.10.2023 | 13.10.2024 | 100% | 99.3 | 0% | 0 | 100% | 99.3 | Work completed | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Const. of Khawbung futsal ground, gallery, Roofing, Lighting & Laying of Artificial Turf | % | 255.5 | 14.10.2023 | 7.2.2025 | 100% | 114.93 | 0% | 0 | 100% | 114.93 | Work completed | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Const. of Community Hall at Dulte & Chhawrtui | % | 271 | 13.10.2023 | 13.10.2024 | 100% | 139.73 | 0% | 0 | 100% | 139.73 | Work completed | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Development of Community Centre at Zotlang, Champhai (Sh: Cons of Market Building cum community Hall & Futsal Ground) | % | 215 | 14.10.2023 | 7.2.2025 | 100% | 89.62 | 0% | 0 | 100% | 89.62 | Work completed | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Additional works for const. of General Nursing Midwifery (GNM) hostel and Nursing Hostel at champhai | % | 438 | 13.10.2023 | 7.2.2025 | 100% | 264.07 | 0% | 0 | 100% | 264.07 | Work completed | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Const of Public Playground at Keitum, Lungchhuan | % | 250 | 13.10.2023 | 13.10.2024 | 100% | 97.38 | 0% | 0 | 100% | 97.38 | Work completed | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Const. of Gov't Building at Serchhip District (Sh: PWD staff qtrs, Extension of Gov't Serchhip College and Kitchen cum Dining at PTS, Thenzawl, Mizoram) | % | 362 | 13.10.2023 | 13.10.2024 | 100% | 303.88 | 0% | 4.96 | 100% | 308.84 | Work completed | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Const of Community Resource Center at Baktawng and Chhuanthar | % | 350 | 13.10.2023 | 13.10.2024 | 100% | 139.9 | 0% | 0 | 100% | 139.9 | Work completed | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Const of Community Hall at Khawzawl Vengthar, Arro Village, Khawzawl Dinthar and Khawhai South | % | 209 | 13.10.2023 | 13.10.2024 | 100% | 79.25 | 0% | 0 | 100% | 79.25 | Work completed | PWD Form - 8
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Gov't Quarters (General pool) under SASCI 2024 - 2025 at Serchhip (1299.68 lakhs) | % | 344.74 | 24.4.2025 | 24.4.2026 | 50% | 150.29 | 3% | 1.81 | 53% | 152.1 | Work in progress | -
a) Type - IV & III Quarters (Design - A) at P & E Veng (Treasury Department Site)
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Gov't Quarters (General pool) under SASCI 2024 - 2025 at Serchhip (1299.68 lakhs) | % | 296.54 | 24.4.2025 | 24.4.2026 | 50% | 124.28 | 3% | 0 | 53% | 124.28 | Work in progress | -
b) Type - IV & III Quarters (Design - B) at P & E Veng ( Treasury Department Site)
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Gov't Quarters (General pool) under SASCI 2024 - 2025 at Serchhip (1299.68 lakhs) | % | 351.94 | 24.4.2025 | 24.4.2026 | 50% | 154.31 | 3% | 0.77 | 53% | 155.08 | Work in progress | -
c) Type - IV & III Quarters (Design - A) at P & E Veng ( Soil & Water Conservation Department Site)
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Gov't Quarters (General pool) under SASCI 2024 - 2025 at Serchhip (1299.68 lakhs) | % | 306.46 | 24.4.2025 | 24.4203 | 45% | 139.84 | 9% | 1.75 | 54% | 141.59 | Work in progress | -
d) Type - IV Quarters ( 3 Units) at Hospital Complex, Serchhip, Mizoram
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Circuit House under DC Office (SH: Construction of Circuit House at Serchhip) | % | 652 | 16.4.2025 | 16.4.2026 | 40% | 163.59 | 4% | 0.39 | 44% | 163.98 | Work in progress | -
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Circuit House under DC Office (SH: Construction of Circuit House at Khawzawl) | % | 1000 | 16.7.2025 | 16.7.2026 | 9% | 0 | 6% | 0 | 15% | 0 | Work in progress | -
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Re-construction of District Jail, Serchhip | % | 372.4 | 8.5.2025 | 8.5.2026
| 1. Repair & Extension of Administrative Building |  |  |  |  | - | 0 | - | 50.79 | - | 50.79 | To be done only after Multipurpose Hall is completed and this office is shifted.
| 2. Multipurpose hall & Barrack |  |  |  |  | 32% |  | 5% |  | 37% |  | Work in progress
| 3. Segregation Cell & Vocation Hall |  |  |  |  | 36% |  | 8% |  | 44% |  | Structure completed.
| 4. Guard Duty Post (1 no) |  |  |  |  | 65% |  | 15% |  | 80% |  | Nearly completed.
| 5. Extension of MI Room |  |  |  |  | - |  | - |  | - |  | To be done only after Segregation Cell is completed and this office is shifted.
| 6. Staff Quarters Type-IV |  |  |  |  | 2% |  | 4% |  | 6% |  | Work just started. Delayed due to change of site.
| 7. Repair & Renovation of Male ward-2, 1st floor and Chapel |  |  |  |  | 5% |  | 1% |  | 6% |  | Work in progress
| Overall |  |  |  |  | 25% | 0 | 5% | 50.79 | 30% | 50.79
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Re-construction of District Jail, Champhai | % | 826.88 | 16.4.2025 | 16.4.2026 |  | 98.04 |  | 0 |  | 98.04 |  | -
| 1. Male Ward |  |  |  |  | - |  | - |  | - |  | To be done only after Female ward is completed and Male prisoners shifted.
| 2. Female Ward |  |  |  |  | 53% |  | 7% |  | 60% |  | Structure completed.
| 3. Main Wall, Separation wall & Duty post |  |  |  |  | 14% |  | 4% |  | 18% |  | Work in progress
| 4. Type-II Quarters Block-I |  |  |  |  | 50% |  | 4% |  | 54% |  | Structure completed.
| 5. Type-II Quarters Block-II) |  |  |  |  | - |  | - |  | - |  | Is being used as Labour camp and site office. To be started after Basement of Bl-I is completd and labours can be shifted.
| Overall |  |  |  |  | 25% | 98.04 | 5% | 0 | 30% | 98.04
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Re-construction of District Jail, Saitual (Sh: Separation Wall (80m)) | % | 45.43 | 29.4.2025 | 29.4.2026 | 35% | 0 | 15% | 0 | 50% | 0 | Work in progress | -
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Working Women Hostels(Champhai), Mizoram. | % | 1366 | 8.04.2025 | 8.04.2026 | 8% | 0 | 4% | 0 | 12% | 0 | Work in progress | -
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Circuit House under DC Office (SH: Construction of Circuit House at Saitual) | % | 640 | 16.4.2025 | 16.4.2026 | 35% | 66.19 | 10% | 1.93 | 45% | 68.12 | Work in progress | -
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of DC's Bungalow at Saitual DC Complex, Saitual N | % | 224 | 4.7.2025 | 4.7.2026 | 35% | 0 | 15% | 0 | 50% | 0 | Work in progress | Restricted Tender
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Revenue Staff Quarters at Serchhip | % | 333.81 | 16.7.2025 | 16.7.2026 | 15% | 52.37 | 2% | 0 | 17% | 52.37 | Work in progress | Restricted Tender
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Revenue Staff Quarters at Saitual | % | 198.12 | 23.7.2025 | 23.7.2026 | 15% | 0 | 1% | 0 | 16% | 0 | Work in progress | Restricted Tender
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Revenue Staff Quarters at Khawzawl | % | 211.19 | 23.7.2025 | 23.7.2026 | 7% | 0 | 3% | 0 | 10% | 0 | Work in progress | -
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of DC Revenue (SO) Office at Champhai, Mizoram | % | 468 | 24.7.2025 | 24.7.2026 | 25% | 61.62 | 13% | 0.5 | 38% | 62.12 | Work in progress | Restricted Tender
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of SDO ( C ) Office and Quarter at N. Vanlaiphai | % | 189.29 | 4.7.2025 | 4.7.2026 | 58% | 114.39 | 10% | 0 | 68% | 114.39 | Work in progress | Restricted Tender
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of District Drugs Control and Awareness Centre at Serchhip excluding Bypass Road | % | 200 | 13.8.2025 | 13.8.2026 | 13% | 0 | 7% | 0 | 20% | 0 | Work in progress | Restricted Tender
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Upgradation of District Research Office at Champhai | % | 45 | 19.8.2025 | 19.8.2026 | 30% | 0 | 25% | 0 | 55% | 0 | Work in progress | Restricted Tender
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Upgradation of District Research Office at Khawzawl | % | 24.16 | 13.7.2025 | 13.7.2026 | 18% | 0 | 37% | 0 | 55% | 0 | Work in progress | Restricted Tender
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Upgradation of District Research Office at Serchhip | % | 21.7 | 19.8.2025 | 19.8.2026 | 100% | 0 | 0% | 0 | 100% | 0 | Work completed | Restricted Tender
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Upgradation of District Research Office at Saitual | % | 36.9 | 21.8.2025 | 21.8.2026 | 55% | 0 | 10% | 0 | 65% | 0 | Work in progress | Restricted Tender
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | NLCPR
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Name of work : Construction of Community Hall at various places in Mizoram ( Sh: Const. Of Community Hall at Saitual, Thingsulthliah, Maite, Tualbung, Lungpher, Buhban, Lenchim, Chawrtui and Puilo). | % | 206.49 | 22.2.2012 | 30.11.2019 |  |  |  |  | 100% | 186.01 | Completed and balance fund of Rs.20.48 (Rs. 16.35 Lakhs NLCPR + Rs. 4.13 Lakhs SMS) awaited for clearing liabilities.
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SPP
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Circuit House at Serchhip | % | 358.18 | - | - | - | - | - | - | - | - | Work not executed due to various reasons. Fund received Rs. 358.18 lakhs is kept at D-III
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SCA/SASCE
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Improvement/Upgradation of Operational/Non-operational facilitiies of Lengpui Airport, (Sh: Renovation of terminal building). | % | 2124 | 10.3.2021 | 31.12.2024 | 99.4% | 1773.36 | 0.1% | 0 | 99.5% | 1773.36 | Work in progress | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | ECRP - II
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of 50 Bedded critical care block at Champhai District Hospital, Mizoram | % | 1346.4 | 4.8.2023 | 4.2.2026 | 89% | 709.74 | 2% | 0 | 91% | 709.74 | Work in Progress | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | NABARD - WIF
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of 24 Warehouses with associated infrastructure in 23 locations in Mizoram under NABARD (Group VII : Teikhang ,Rabung & Dungtlang). | % | 336.53 | 17.7.2023 | 31.3.2025 | [6 empty] | Work in Progress | PWD Form - 8
| i) Construction of 200 MT warehouse at Teikhang |  |  |  |  | 0% | 70.49 | 0% | 0 | 100% | 70.49
| ii) Construction of 200 MT warehouse at Rabung |  |  |  |  | 0% | 70.58 | 0% | 0 | 100% | 70.58
| iii) Construction of 200 MT warehouse at Dungtlang |  |  |  |  | 0% | 81.89 | 0% | 0 | 100% | 81.89
| iv) Construction of staff quarters at Dungtlang |  |  |  |  | 99.7% | 0 | 0.1% | 0 | 99.8% | 0
| Overall |  |  |  |  | 99.7% | 222.96 | 0.1% | 0 | 99.8% | 222.96
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SCA to TSS/CSS
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Const of 100 Bedded Dist hospital at Saitual ( Sh: Cons of OPD building at district hospital, Saitual) | % | 200 | 13.10.2023 | 13.10.2025 | 100% | 193.92 | 0% | 6 | 100% | 199.92 | Work completed | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | NEC
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Creation of Passion fruit Processing unit at Cold Storage , New Champhai Mizoram. | % | 185.39 | 23.9.2022 | 24.3.2024 | 100% | 185.39 | 0% | 0 | 100% | 185.39 | Building work completed. Procurement of plants and machineries being taken up by D.C. Champhai. | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | NEC
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Zomi cultural Centre and preservation of historical sites at Champhai | % | 478.69 | 26.9.2022 | 7.2.2025 | 100% | 458.43 | 0% | 0 | 100% | 458.43 | Work completed | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | NEC
Sl no | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Biate Tea Tourism Circuit & Nature camp in Mizoram | % | 369.62 | 9.10.2023 | 9.10.2025 | 96.2% | 342.62 | 0.1% | 0 | 96.3% | 342.62 | Work in progress | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | NEC
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Establishing Mizo cultural heritage centre for protecting the historical and natural heritage of Mizo at Kawlri, Serchhip | % | 486.47 | 16.2.2024 | 16.2.2026 | 65% | 121.61 | 3% | 0 | 68% | 121.61 | Work in progress | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | NEC
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Auditorium at Bethel Veng Champhai | % | 1443.75 | 16.2.2024 | 16.2.2026 | 55% | 323.98 | 1% | 0 | 56% | 323.98 | Work in progress | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | NESIDS - OTRI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of 50 Bedded District Hospital Complex and Procurement of equipment at Khawzawl, Khawzawl District, Mizoram | % | 1775 | 11.6.2024 | 11.12.2026 | 72% | 660.75 | 1% | 0 | 73% | 660.75 | Work in progress | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | NESIDS-OTRI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of 50 Bedded District Hospital Complex and Procurement of equipment at Saitual, Saitual District, Mizoram | % | 1696 | 10.6.2024 | 10.12.2026 | 42% | 224.7 | 2% | 0 | 44% | 224.7 | The local NGO's wanted to shift the layout of the hospital main building towards the backside and lowering of the courtyard which will involve additional fund. The matter is brought to Health Department and decision is awaited. Work for quarters only in progress. | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | NEC
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Upgradation of Sports Infrastructure of Ngopa Playground at Saitual District, Mizoram. | % | 394.15 | 15.3.2025 | 15.9.2027 | 93% | 93.61 | 7% | 0 | 100% | 93.61 | Work in progress | _
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | NEC
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Our Heritage, Our Treasure at Vangchhia Tourist Spot, Champhai, Mizoram | % | 115.76 | 19.7.2025 | 19.7.2026 | 15% | 0 | 10% | 0 | 25% | 0 | Work in progress | _
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | NESIDS
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Improvement/Upgradation of Operational/Non-operational facilities of Lengpui Airport, (Sh: Elevated road with connected components of Terminal Building). | % | 1959 | 30.9.2021 | 30.11.2024 | 100% | 1959 | 0% | 0 | 100% | 1959 | Work completed | Turnkey
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | CSS
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Tourist Lodge at Champhai | % | 328.73 | 9.12.2010 | 30.11.2020 |  |  |  |  | 100% | 300 | Taken over by the Department on Dt.3.8.2021 . LOC amounting to Rs. 30.00 lakh submitted for clearing liaibility. Hence, release of LOC awaited for financial closure.
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | CSS
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Polytechnic at Chhiahtlang | % | 800 | [8 empty] | Only approach road is executed. Out of fund received amount Rs. 300.00 lakhs balance amount of Rs. 196.34 lakhs is kept at D-III
| i) Approach road |  |  | 3.3.2016 | 2.8.2016 |  |  |  |  | 100% | 103.67
ii) Administrative & Academic Block
iii) Hostel Block
iv) Staff Quarter
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | CSS
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Hostel for S.T Girls at Champhai | % | 462.75 | 18.9.2023 | 28.9.2025 | 87.5% | 162.77 | 0% | 0 | 87.5% | 162.77 | Work temporarily halted due to fund problem | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | CSS
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | 10 - Bedded Integrated AYUSH Hospital at Keifang, Saitual District | % | 750 | 13.10.2023 | 13.10.2025 | 77% | 342.39 | 3% | 0 | 80% | 342.39 | Work in progress | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | CSS
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Const of District Court Complex at Vengsang, Champhai. ( Sh: Main Building, phase- I) | % | 4915.35 | 17.10.2023 | 17.10.2026 | 71% | 1444.07 | 2% | 0 | 73% | 1444.07 | Work in progress | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | CSR
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of 100 Bedded District Hospital, Block A at Serchhip Mizoram under Powergrid CSR Initiative | % | 2100 | - | - | 28% | 0 | 1% | 0 | 29% | 0 | Revised DPR submitted to PGIL. Revised agreement to be signed with contractor after Revised DPR is approved by PGCIL. Only Supervision and Monitoring of work is under PWD. | -
Sr.Executive Engineer, PWD., Project Division - III Aizawl, Mizoram

## PD - IV
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY, 2026
Name of Division |  | : Project Division - IV
Source of funding |  | : SASCI
Sl. No. | Name of work/project | Unit | Approved cost (Rs. in lakh) | Date of commencement | Target date of completion | Cummulative progress at the end of last month |  | Achievement of works during the month |  | Overall Cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin |  |  | COPY 5
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Working Women Hostel (50 Bedded) at Ramhlun Sports Complex, Aizawl. | % | 1400 | 2025-05-14 | 2026-05-14 | 29% | 130.0859 | 1% | 70.8441 | 30% | 200.93 | Work in progress. | Item rate.
2 | Upgradation of Govt. Hrangbana College, Aizawl, Mizoram. | % | 200 | 2025-07-14 | 2026-07-14 | 85% | 115.8881 | 10% | 60.8019 | 95% | 176.69 | Work in progress. | Item rate.
3 | Construction of Retaining Wall and Drainage System in Various Higher Educations Institutions to Mitigate Effects of Cyclonic Storm. | % | 204
| a) Government Aizawl College, Mualpui | % | 38 | 2025-09-15 | 2026-09-15 | 98% | 0 | 2% | 36.55 | 100% | 36.55 | Work completed. | Item rate.
| b) Government Mizoram Law College, Luangmual | % | 72 | 2025-09-11 | 2026-09-11 | 50% | 0 | 15% | 0.69 | 65% | 0.69 | Work in progress. | Item rate.
| c) Mizoram Hindi Training College, Durtlang North | % | 94 | 2025-09-11 | 2026-09-11 | 98% | 0 | 2% | 79.63 | 100% | 79.63 | Work completed. | Item rate.
4 | Construction of Revenue Staff Qtr. Complex at Aizawl. | % | 500
| a) Construction of Revenue Staff Quarters at Kawltheihuan, Aizawl | % | 298 | N.A. | N.A. | 2.5% | 0 | 4.5% | 0 | 7% | 0 | Foundation works started. | Item rate.
| b) Construction of Revenue Staff Quarters at College Veng, Aizawl | % | 202 | N.A. | N.A. | 0% | 0 | 0% | 0 | 0% | 0 | Dismantling of existing quarters started. | Item rate.
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY, 2026
Name of Division |  | : Project Division - IV
Source of funding |  | : SASCE
Sl. No. | Name of work/project | Unit | Approved cost (Rs. in lakh) | Date of commencement | Target date of completion | Cummulative progress at the end of last month |  | Achievement of works during the month |  | Overall Cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Multi Utility Centre at Zemabawk, Aizawl, Mizoram | % | 800 | 2022-12-19 | 2025-12-30 | 94% | 356.14 | 0.4% | 143.6 | 94.4% | 499.74 | Work in progress. Expected to be completed in February 2026. | Item rate.
2 | Construction of Solid Waste Management Centre at Hualngohmun, Mizoram (Phase-I) | % | 1664 | 2023-04-07 | 2026-04-15 | 59% | 509.6972 | 1% | 249.9928 | 60% | 759.69 | Work in progress. | Item rate.
3 | Restoration/renovation of DC Office at Aizawl. | % | 2000 | 2025-04-08 | 2026-04-08 | 26.5% | 0 | 1% | 199.96 | 27.5% | 199.96 | Work in progress hindered due to late handover of construction site. | Item rate.
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY, 2026
Name of Division |  | : Project Division - IV
Source of funding |  | : NEC
Sl. No. | Name of work/project | Unit | Approved cost (Rs. in lakh) | Date of commencement | Target date of completion | Cummulative progress at the end of last month |  | Achievement of works during the month |  | Overall Cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of AYUSH Development Centre at MINECO Aizawl, Mizoram | % | 264.16 | 2022-12-07 | 17-08-2024 17.04.2025 (1st EOT) | 82% | 198.12 | 3% | 0 | 85% | 198.12 | Work in progress. EOT application in process. | Item rate.
1 | Establishment of Sinlung Hills Council Administrative Complex, Mizoram (Sh : Construction of Sinlung Hills Council Administrative Building at Sakawrdai) | % | 381.99 | 2021-11-08 | 31-07-2024 (1st EOT) 28.02.2025 (2nd EOT) | 98% | 295.1993 | 0.2% | 0 | 98.2% | 295.1993 | Work in progress. Work expected to be completed by march 2026. | Item rate.
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY, 2026
Name of Division |  | : Project Division - IV
Source of funding |  | : Article 275 (1)
Sl. No. | Name of work/project | Unit | Approved cost (Rs. in lakh) | Date of commencement | Target date of completion | Cummulative progress at the end of last month |  | Achievement of works during the month |  | Overall Cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Tribal Hostel at Suangpuilawn, Mizoram. | % | 320 | 2023-08-12 | 2025-07-22 | 76% | 139.9992 | 0% | 0 | 76% | 139.9992 | Work progress hindered due to irregularity in release of fund from Ministry. | Item rate.
2 | Construction of Multipurpose Community Hall at Darlawn, Mizoram. | % | 720 | 2023-08-12 | 2025-08-12 | 63% | 149.8635 | 0% | 0 | 63% | 149.8635 | Work progress hindered due to irregularity in release of fund from Ministry. | Item rate.
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY, 2026
Name of Division |  | : Project Division - IV
Source of funding |  | : NABARD
Sl. No. | Name of work/project | Unit | Approved cost (Rs. in lakh) | Date of commencement | Target date of completion | Cummulative progress at the end of last month |  | Achievement of works during the month |  | Overall Cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of 24 warehouses with associated infrastructure in 23 locations in Mizoram under NABARD (Group V : Zohmun) | % | 170.99 | 2023-07-17 | 17-07-2025 24-12-2025 (1st EOT) | 75% | 60.4338 | 5% | 64.5462 | 80% | 124.98 | Work in progress. Work expected to be completed by march 2026. | Item rate.
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY, 2026
Name of Division |  | : Project Division - IV
Source of funding |  | : NEDP
Sl. No. | Name of scheme | Unit | Approved cost (Rs. in lakh) | Date of commencement | Target date of completion | Cummulative progress at the end of last month |  | Achievement of works during the month |  | Overall Cumulative achievement |  | Remarks | Mode of contract
| Name of work/project |  |  |  |  | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Agriculture Growth Centre at Tuikual South, Aizawl. | % | 4555 | 2025-02-10 | 2026-02-10 | 27.5% | 762.6392 | 1% | 411.4408 | 28.5% | 1174.08 | Work in progress. | Item rate.
Sr. Executive Engineer, PWD
Project Division - IV
Aizawl : Mizoram

## SERCHHIP DIV
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY 2026
NAME OF DIVISION : Serchhip Division
Sl. No | Name of Schemet | Unit | Approved Cost (in lakhs) | Date of Commence- ment | Target date of Completion | Cummulative Progress at the end of last Month |  | Achievement of works during the month |  | Overall Cumulative achievement |  | Remarks | Mode of Tender
| Name of Work/ Project |  |  |  |  | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
SASCI
1 | Estimate for restoration of damage due to cyclone remal |  | 715 | 16.06.2025 | 16.01.2026 | 40% | 492.547 | 60% | 35.852 | 100% | 528.4 | Physically completed
MAINTENACE ACTION PLAN (MAP)
1 | Resurfacing of Appraoch Road to Chhimveng at Serchhip | Km | 11.63 | 21.08.2025 | 31.03.2026 | 100% | 10.47 |  |  | 100% | 10.47 | Completed | Departmental
2 | Resurfacing of Appraoch Road to Tlangnuamt Serchhip | Km | 5.06 | 21.08.2025 | 31.03.2026 | 100% | 4.55 |  |  | 100% | 4.55 | Completed | Departmental
3 | Pothole filling & Resurfacing of IB Peng - IOC at New Serchhip | Km | 16.91 | 21.08.2025 | 31.03.2026 | 100% | 15.22 |  |  | 100% | 15.22 | Completed | Departmental
4 | Path Repair with Premix Carpet with full surface seal coat on AOC to DIET Complex at Serchhip | Km | 22.97 | 21.08.2025 | 31.03.2026 | 100% | 20.67 |  |  | 100% | 20.67 | Completed | Departmental
5 | Construction of V-Shape side drain at Leisang to Sport Complex at Serchhip | Km | 2.91 | 21.08.2025 | 31.03.2026 | 100% | 2.61 |  |  | 100% | 2.61 | Completed | Departmental
6 | Path Repair with Premix Carpet with full surface seal coat on AOC Lane -II | Km | 3.19 | 21.08.2025 | 31.03.2026 | 100% | 2.87 |  |  | 100% | 2.87 | Completed | Departmental
7 | Resurfacing of Vety Ar Farm - Assam Riffle Gate-III at P&E veng,Serchhip | Km | 7.42 | 21.08.2025 | 31.03.2026 | 100% | 6.68 |  |  | 100% | 6.68 | Completed | Departmental
8 | Laying of Base course along Approach Road to Solid Waste Management Centre(PHED) Serchhip District | Km | 12.3 | 21.08.2025 | 31.03.2026 | 100% | 11.07 |  |  | 100% | 11.07 | Completed | Departmental
9 | Path repair of Leng to Sailulak | Km | 20.37 | 21.08.2025 | 31.03.2026 | 100% | 18.33 |  |  | 100% | 18.33 | Completed | Departmental
10 | Path repair of Chekawn to N.Vanlaiphai | Km | 18.69 | 21.08.2025 | 31.03.2026 | 100% | 16.82 |  |  | 100% | 16.82 | Completed | Departmental
PROGRESS REPORT OF NABARD WORKS FOR THE MONTH OF JANUARY, 2026
Name of Work :CONSTRUCTION OF LINK ROAD AND LAND IMPROVEMENT AT ZAWLPUI IN THE STATE OF MIZORAM
NABARD
Date of Commencement: 3rd May, 2025 | [7 empty] | Division Serchhip Division
Agreement Amount: Rs. 9,63,30,359.97 | [7 empty] | Period for Completion 18 Months
Name of Contractor:-Evergreen Construction & culsuntancy Khatla, Aizawl
Sl. No. | Name of Work | Unit | As per Agreement/Deviation |  | Progress upto the end of last month |  |  |  | Cum.Prog.Upto the end of this month |  | Remarks
|  |  | Qty | Amount | Physical | Financial | Physical | Financial | Physical | Financial
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Land Improvement | M3 | 124539 | 21669786 | 880.84 | 153266.16 | 6669.26 | 1160451.24 | 7550.1 | 1313717.4 | Work in Progress
| Restoration fo Rain cuts | Km | 10.837 | 3531843.57 | 7.51 | 2448695.47 | 3.327 | 0 | 10.837 | 2448695.47
2 | Compaction of Original Ground (Sub-grade) | Km | 10.837 | 1584396 | 10.811 | 1580595 | 0.026 | 0 | 10.837 | 1580595
3 | Granular Sub-Base | Km | 10.837 | 15311275.5 | 10.496 | 14834519.93 | 0.341 | 0 | 10.837 | 14834519.93
4 | Concrete Pavement | Km | 10.837 | 47880734 | 6.712 | 29657927.8282 | 1.96 | 0 | 8.672 | 29657927.8282
5 | Earthen Shoulder | Km | 10.837 | 1765164.38 | 0.95 | 164536.964 | 0 | 0 | 0.95 | 164536.964
| 5 Years Maintenance |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total : |  |  | 91743199.45 |  | 48839541.3522 |  | 1160451.24 |  | 49999992.5922
Over all Physical Progress in Percentage =66%
PROGRESS REPORT OF NABARD WORKS FOR THE MONTH OF JANNUARY, 2026
Name of Work :IMPROVEMENT OF SERCHHIP(CHAWMKAI) TO ZOTE SOUTH ROAD, SERCHHIP DISTRICT IN THE STATE OF MIZORAM
NABARD
Date of Commencement: 14th May, 2025 | [7 empty] | Division Serchhip Division
Agreement Amount: Rs. 21,80,92,941.13 | [7 empty] | Period for Completion 18 Months
Name of Contractor:-Huapzo Construction & consultancy Services, bawnkawn Shalom, Aizawl
Sl. No. | Name of Work | Unit | As per Agreement |  | Progress upto the end of last month |  | Progress during the month |  | Cum.Prog.Upto the end of this month |  | Remarks
|  |  | Qty | Amount | Physical | Financial | Physical | Financial | Physical | Financial
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Formation Cutting | Km | 14 | 22273648.36 | 14 | 22272972.35 | 0 | 0 | 14 | 22272972.35 | Work in Progress
2 | Compaction of Original Ground (Sub-grade) | Km | 14 | 4620000 | 5 |  | 9 |  | 14
3 | Granular Sub-Base | Km | 14 | 33446000 | 0 |  | 5 |  | 5
4 | WBM – II | Km | 6 | 8045730 | 0 |  | 0 |  | 0
5 | WBM – III | Km | 6 | 8197200 | 0 |  | 0 |  | 0
6 | Prime coat | Km | 6 | 2079000 | 0 |  | 0 |  | 0
7 | Tack coat | Km | 6 | 673200 | 0 |  | 0 |  | 0
8 | OGPC | Km | 6 | 6138000 | 0 |  | 0 |  | 0
9 | Seal Coat | Km | 6 | 2079000 | 0 |  | 0 |  | 0
10 | Concrete Pavement | Km | 8 | 48708000 | 0 |  | 0 |  | 0
12 | Surface Drain | Km | 6 | 13720000 | 0 |  | 0 |  | 0
13 | Protection Wall | Rm | 200 | 11297837 | 20 |  | 20 |  | 40
14 | Lined Side drain | Rm | 6762 | 17484569.315 | 0 |  | 0 |  | 0
15 | Culverts, H/P, Minor Bridge | Nos | 28 | 27614827.646 | 0 |  | 1 |  | 1
16 | Road Furnitures | Nos | 14 | 1390550 | 0
| 5 Years Maintenance |  |  | 10385378.14 | 0
| Total : |  |  | 218152940.461 |  | 22272972.35 |  | 0 |  | 22272972.35
| Over all Physical Progress in Percentage = |  |  | 17.29%
PROGRESS REPORT OF NABARD WORKS FOR THE MONTH OF JANUARY, 2026
Name of Work :WIDENING & IMPROVEMENT OF APPROACH ROAD TO PARAGLIDING GROUND AT SERCHHIP
NABARD
Date of Commencement: 8h May, 2025 | [7 empty] | Division Serchhip Division
Agreement Amount: Rs. 3,45,63,310.77 | [7 empty] | Period for Completion 18 Months
Name of Contractor:-Evergreen Construction & culsuntancy Khatla, Aizawl
Sl. No. | Name of Work | Unit | As per Agreement |  | Progress upto the end of last month |  | Progress during the month |  | Cum.Prog.Upto the end of this month |  | Remarks
|  |  | Qty | Amount | Physical | Financial | Physical | Financial | Physical | Financial
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Widening | Km | 4.7 | 1588390.58 | 2.7 | 1433216.78 | 2 |  | 4.7 | 1433216.78 | Work in Progress
2 | Compaction of Original Ground (Sub-grade) | Km | 4.7 | 123375 | 2 | 123375 | 2.7 |  | 4.7 | 123375
3 | Granular Sub-Base | Km | 4.7 | 6274422 | 1.5 | 3281069 | 1.5 |  | 3 | 3281069
10 | Concrete Pavement | Km | 8 | 24350700 | 0 | 5148030 | 1.5 |  | 1.5 | 5148030
16 | Road Furnitures | Nos | 64 | 580551.25 | 0 |  | 0 |  | 0
| 5 Years Maintenance |  |  | 1645871.94 |  |  |  |  | 0
| Total : |  |  | 34563310.77 |  | 9985690.78 |  | 0 |  | 9985690.78
Overall Physical Progress in % |  | = | 56.52%
PROGRESS REPORT OF NABARD WORKS FOR THE MONTH OF JANUARY, 2026
Name of Work :IMPROVEMENT OF KIKAWN TO HMARVENG, SERCHHIP
NABARD
Date of Commencement: 14th May, 2025 | [7 empty] | Division Serchhip Division
Agreement Amount: Rs. 15,51,98,719.23 | [7 empty] | Period for Completion 18 Months
Name of Contractor:-Studio Hamlet, Champhai Vengthlang, Champhai
Sl. No. | Name of Work | Unit | As per Agreement |  | Progress upto the end of last month |  | Progress during the month |  | Cum.Prog.Upto the end of this month |  | Remarks
|  |  | Qty | Amount | Physical | Financial | Physical | Financial | Physical | Financial
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Formation Cutting | Km | 6 | 52027848.88 | 3 | 12725640.84 | 3 | - | 6 | 12725640.84 | Work in Progress
| Compaction of Original Ground (Sub-grade) | Km | 6 | 805500 | 0 |  | 5.5 |  | 5.5
| Embankment | Km | 4 | 3420000 | 0 |  | 3 |  | 3
2 | Granular Sub-Base | Km | 6 | 14231250 | 0 |  | 0 |  | 0
4 | WBM – I | Km | 6 | 7290000 | 0 |  | 0 |  | 0
5 | WBM – II | Km | 6 | 7290000 | 0 |  | 0 |  | 0
6 | Prime coat | Km | 6 | 2160000 | 0 |  | 0 |  | 0
7 | Tack coat | Km | 6 | 1170000 | 0 |  | 0 |  | 0
8 | OGPC | Km | 6 | 6120000 | 0 |  | 0 |  | 0
| Seal Coat | Km | 6 | 1980000 | 0 |  | 0 |  | 0
9 | Earthen shoulder | Km | 6 | 1890000 | 0 |  | 0 |  | 0
| Surface Drain | Km | 6 | 900000 | 0 |  | 0 |  | 0
10 | Protection Wall | Rm | 1605 | 30932668.8 | 0 |  | 75 |  | 75
12 | Lined Side drain | Rm | 4666.85 | 11891072.7 | 0 |  | 0 |  | 0
13 | H/P Culvert NP3 | Nos | 12 | 5699963.25 | 0 |  | 0 |  | 0
| 5 Years Maintenance |  |  | 7390415.2
| Total : |  |  | 155198718.83 |  | 12725640.84 |  |  |  | 12725640.84
Overall Physical Progress in % |  | = | 18.09%
PROGRESS REPORT OF UNTIEDED WORKS FOR THE MONTH OF JANUARY, 2026
Name of Work :POTHOLE FILLING WITH WBM,PREMIXCARPET WITH SEALCOAT AT ESSENTIAL PLACES ON SERCHHIP TO THENZAWL ROAD
5054 UNTIEDED FUND
Date of Commencement: 2nd JANUARY, 2026 | [7 empty] | Division Serchhip Division
Agreement Amount: Rs. 49,25,415.02 | [7 empty] | Period for Completion 3 Months
Name of Contractor:-
Sl. No. | Name of Work | Unit | As per Agreement |  | Progress upto the end of last month |  | Progress during the month |  | Cum.Prog.Upto the end of this month |  | Remarks
|  |  | Qty | Amount | Physical | Financial | Physical | Financial | Physical | Financial
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Scrarifying | m2 | 973.57 | 51599.21 | 0 | 0 | 331.74 | 0 | 331.74 | 0
2 | WBM – II | m3 | 73.02 | 446913.8 | 0 | 0 | 37.67 | 0 | 37.67 | 0
3 | Prime coat | m2 | 973.57 | 117432.01 | 0 | 0 | 200 | 0 | 200 | 0
4 | Tack coat | m2 | 9900 | 391347 | 0 | 0 | 200 | 0 | 200 | 0
5 | OGPC | m2 | 9900 | 2883969 | 0 | 0 | 200 | 0 | 200 | 0
6 | Seal Coat | m2 | 9900 | 1034154 | 0 | 0 | 200 | 0 | 200 | 0
| Total : |  |  | 4925415.02 |  | 0 |  | 0 |  | 0
Sr, Executive Engineer,PWD
Serchhip Division:Serchhip

## SAITUAL DIV
MONTHLY PROGRESS FOR THE MONTH OF : JANUARY 2026
NAME OF DIVISION : PWD Saitual Division | [5 empty] | Physical in % |  |  |  | Financial is Rs in lakh
Sl. No | Name of Scheme | Unit | Approved Cost (in lakhs) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last Month |  | Achievement of works during the month |  | Overall Cumulative achievement |  | Remarks | Mode of Tender
| Name of Work/ Project |  |  |  |  | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
NESIDS
1 | Improvement & Upgradation of Daido to Vawngkawt- Buangpuilawn (Manipur) Road |  | 2404 | 14.03.2024 | 14.09.2025 | 100% | 1626.13 |  |  | 100% | 1626.13 | Security Deposit amounting to Rs. 0.93 Cr. Is lying in CNA Account | Open Tender
SASCI-II
1 | Improvement of Khawlek - Ratu Road (Length = 6Km) |  | 130 | 05.10.23 | 05.10.24 | 100% | 126.14 |  |  | 100% | 126.14 |  | Restricted Tender
2 | Widening and reconstruction of culverts on 3rd Road from Sedaikawn to PWD Kawn, Saitual (Length = 2.220Kms) |  | 137.52 | 05.10.23 | 05.10.24 | 100% | 137.52 |  |  | 100% | 137.52 |  | Restricted Tender
3 | Rigid pavement of Sakeibangla to ZMC via Thingsulthliah Road Thingsulthliah, PCC Pavement = 3.00km, Side drain = 2000m,R/Wall = 10m, Culvert = 2 Nos |  | 55.78 | 05.10.23 | 05.10.24 | 100% | 55.78 |  |  | 100% | 55.78 |  | Restricted Tender
4 | Pothole & Patch repair on Saitual to Phullen Road. ( 2.00 km ) |  | 15.5 | 05.10.23 | 05.10.24 | 100% | 15.5 |  |  | 100% | 15.5
SASCI & SASCI-II
1 | Restoration of damages due to cyclone remal under Khawzawl, Saitual & Serchhip Division (Saitual Division) |  | 165.25 | 16.06.2025 | 16.01.2026 | 100% | 59.76 |  |  | 100% | 59.76 |  | Restricted Tender | 21.53
2 | Restoration of damages due to cyclone remal under saitual division PART-II |  | 598.92 | 16.06.2025 | 16.01.2026 | 100% | 345.59 |  |  | 100% | 345.59 |  | Restricted Tender | 12.64
SASCI-V
1 | Extension of Saitual Town Via Khiangpuizawl under part V |  | 441.35 | 23.06.2025 | 23.06.2026 | 19.33% | 82.09 | 8.76% |  | 28.09% | 82.09 |  | Restricted Tender
SEDP
1 | Construction of Khanpui - Tualbung Road Phase-II |  | 1576.01 | 15.01.20 | 15.06.22 | 100% | 1575.73 |  |  | 100% | 1575.73
Sr. Executive Engineer, PWD.,
Saitual Division, Saitual.

## SIAHA DIV
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY 2026
Name of Division : PWD Siaha Division
Sl.No. | Name of Scheme | Unit | Approved Cost (in lakhs) | Date of Commencement | Target date of Completion | Commulative Progress at the end of last Month |  | Achievement of work during the month |  | Overall Cummulative achievement |  | Remarks | Mode of Tender
| Name of Work/Project |  |  |  |  | Phy | Fin | Phy | Fin | Phy | Fin |  |  | 0.1278
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | SASCI
1 | Widening,Blacktopping and Improvement of of Road from Saihatlangkawn Beat post-Primary School-II - District Court Complex and Magistrate Rrsidence. | % | 360 | 21.08.2025 | 21.12.2025 | 64.01% |  | 29% |  | 93.01% |  | Work in progress | Item rate Contract
2 | Extension of Culvert Apron at 0.75 km on AOC to Saiha Tlawngkawn Road | % | 3.03 | 09.06.2025 | 09.01.2026 | [6 empty] | Work not yet started | Item rate Contract
3 | Reconstruction of RCC Slab Culvert on Saiha to Tuisumpui road at Ch.7.600km | % | 12.12 | 09.06.2025 | 09.01.2026 | 100% |  |  |  | 100% |  | Work Completed | Item rate Contract
4 | Restoration of Collapsed Retaining wall on Niawhtlang - Chakhang road (0.000 - 44.050)kmp at Ch.2.500 | % | 8.46 | 09.06.2025 | 09.01.2026 | 100% |  |  |  | 100% |  | Work Completed | Item rate Contract
2 | NABARD
Work under NABARD
1 | Up-gradation of Laki to Vahai Road From Ch. 0.00 km to Ch. 15.56 km | % | 1809.4429 | 28.06.2024 | 27.06.2026 | 74.92% | 1262.75 | 1.68% |  | 76.6% | 1262.75 | 1. Work in Progress 2. Deviation approved vide Letter No.B.12051/1/21/MMPC/PWD/40 Dt. 21.07.25 | Item rate Contract | 0.13%
3 | NEC
Work under NEC
4 | PMGSY
Work under PMGSY
5 | SEDP
Work under SEDP
6 | CSS
Work under CSS
7 | MoRTH
Work under MoRTH
A | 5054: (2024-2025)
1 | Annual Plan 2024 - 2025 Construction of Bailey Bridge (TDR) 170 ft span over R.Tuisumpui | % | 250 | 02.12.2024 |  | 3% | 220 |  |  | 3% | 220 | Work in progress | All bridge materials received at site.
B | 5054: (2025-2026)
1 | Pothole Filling and resurfacing of Approach Road to Helipad Via DC Bungalow road | % | 4.42 | 20.11.2025 | 21.01.2026 |  |  | 100% |  | 100% |  | Work physically Completed | Item rate Contract
2 | Pothole filling and resurfacing of DC Bungalow Court Yard) | % | 0.78 | 20.11.2025 | 21.01.2026 |  |  | 100% |  | 100% |  | Contractor not yet started | Item rate Contract
3 | Widening of pavement at selected locations on Circuit House to Bazar Traffic point road via Civil Hospital | % | 19.24 | 20.11.2025 | 21.03.2026 |  |  | 50% |  | 50% |  | Work in progress | Item rate Contract
4 | Construction of link drain at Tuisumpui Bridge site to prevent erosion of abutment foundation | % | 5.98 | 20.11.2025 | 21.02.2026 |  |  | 100% |  | 100% |  | Work is physically completed | Item rate Contract
5 | Pothole filling, Patch Repair & Resurfacing of BRTF Road to Suakkunga Road (Police Outpost - Suakkunga Road) at Bualpui NG (0.000 - 1.200 kmp) | % | 27.13 | 20.11.2025 | 21.03.2026 |  |  | 70% |  | 70% |  | Work in progress | Item rate Contract
6 | Pothole filling, Patch Repair & Resurfacing of Approach road to PHC Chhuarlung (0.000 - 0.370) km | % | 7.31 | 20.11.2025 | 21.02.2026 | [6 empty] | not yet started | Item rate Contract
7 | Restoration of RCC Slab Culvert on Maisa-Lawngban Road at Ch.2.80 km | % | 6.88 | 20.11.2025 | 21.02.2026 | [6 empty] | Contractor not yet started | Item rate Contract
8 | Construction of Lined Side Drain on Tipa 'V' - Tipa 'L' Road (Tipa Lal Veng Peng Thuam - Waiting Shed on NH-02 at Tipa 'V') | % | 6.16 | 20.11.2025 | 21.02.2026 |  |  | 20% |  | 20% |  | Work in progress | Item rate Contract
9 | Restoration of RCC Slab Culvert on Phura - Lungpuk Road at Ch. 15.80 km | % | 5.72 | 20.11.2025 | 21.02.2026 | [6 empty] | Contractor not yet started | Item rate Contract
| Total= |  | 83.62
9 | CRF | [13 empty] | Withh = | 5.74
a) | Construction of Road from Chakhei to Siasi road (Length = 20 km) under CRF: Group-A (SH: FC & Pavement Works) | % | 4982.15 | 08.07.19 | 20.12.2024 | 99.99% | 3074.35 |  |  | 99.99% | 3074.35 | Work in progress | Item rate Contract |  | CC = | 29.2685 | 21.7265 | 2.6723 | 24.3989
b) | Construction of Road from Chakhei to Siasi road (Length = 20 km) under CRF: Group-B (SH: Permanent Works) | % |  | 08.07.19 | 20.12.2024 | 100% | 976.65 |  |  | 100% | 976.65 | Work completed | Item rate Contract |  | QC = | 3.6 | 7.5419 | 0.92765 | 8.4695
10 | 3054 | [14 empty] | 32.8685 |  |  | 32.8684
Work under Annual Maintenance Action Plan (3054) During 2025-26 under PWD Siaha Division
1 | Maintenance and Improvement of Approach road to PHC with PCC at Sangau | % | 14.53 | 18.08.2025 | 31.03.2026 | 100% |  |  | 0 | 100% | 0 | Work completed | Departmental
2 | Construction of Retaining Wall on Tlangpui - Niawhtlang Road (0.000 - 14.000) kmp at Ch. 7.500 km | % | 6.66 | 07.07.2025 | 08.09.2025 | 100% |  |  | 0 | 100% | 0 | Work completed | Departmental
3 | Pothole filling of Meisatla forest check Gate to NH54B Tawngtaina Part-II | % | 14.72 | [8 empty] | Work to be started soon | Departmental
4 | Resurfacing of Approach road to GHSS Complex at New Siaha | % | 1.45 | [8 empty] | Work to be started soon | Departmental
5 | Pothole filling & Resurfacing of Er.VL khuma Residence to Council Veng via Council Veng Hall road | % | 19.08 | [8 empty] | Work to be started soon | Departmental
6 | Pothole filling, Patch repair & Resurfacing of Bualpui Bazar - PWD Complex at Bualpui 'NG' Phase I | % | 6.23 |  |  |  |  | 10% |  | 10% |  | Work to be started soon | Departmental
7 | Pothole filling, Patch repair & Resurfacing of Chheihlu - Chakhang Road from Ch.1.000 km to Ch.2.000 km | % | 10.63 | [8 empty] | Work to be started soon | Departmental
8 | Strengthening of Tuipang 'V' Tuipang 'L' Road (Tuipang Lal Veng Peng thuam-Waiting Shed Tuipang 'V') (0.140 km - 0.280 km) | % | 10.68 | [8 empty] | Work to be started soon | Departmental
9 | Reconstruction of Damaged slab Culvert Type -I on Siachangkawn - Vawmbuk road (0.000 - 12.250) km | % | 3.49 |  |  |  |  | 100% |  | 100% |  | Work completed | Departmental
10 | Repair of RCC Slab Culvert on Phura - Lungpuk road at Ch.16.300 km | % | 5.57 | [8 empty] | Work to be started soon | Departmental
11 | Construction of Approach road to Kaochao East IB With PCC Pavement | % | 25 | [8 empty] | Work to be started soon | Departmental
| Total |  | 118.04
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY, 2026
Name of Division: Siaha Division
Name of contractor: Tantia Constructions Ltd., DD-30, Sector -I, Salt Lake City, Kalkata
Aggrement amount : Rs.43,07,95,440.00
B.Physical Report
Sl.No. | Name of the project Location and State | Name of the Implementing Agency/Deptt | Approved Cost by MDoNER/NEC & Date of Approval |  | Date of Actual Commencement of work/Scheme | Target date of completion of work/scheme | Scope of the work/scheme in physical terms (eg. Kms, etc) |  | Physical achievemnt |  | Remark
|  |  | Cost | Date |  |  |  |  | Percentage weightage (previous month) | Percentage weightage (reporting month)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |  | 9 | 10 | 11
| Upgradation of Saiha - Lungbun - Tluangram - Haka Road in the State of Mizoram under North East Special Infrastructure Development Scheme(NESIDS) on EPC Mode. | PWD Siaha Division, Siaha | 50.21 | 2021-01-29 | 29.10.2021 | 31.03.2024 |  |  |  |  | Work completed
1 | Earthwork (Formation width=7.5m) |  | 6.04 |  |  |  | 12.66 | Km | 14.02%
| a) Site Clearance and cutting of Trees | [5 empty] | 12.66 | Km
| b) In Cutting | [5 empty] | 12.66 | Km
| i) Ordinary soil | [5 empty] | 324097.97 | Cum
| ii) Soft Rock | [5 empty] | 135654.24 | Cum
| iii) Hard Rock | [5 empty] | 20610.41 | Cum
2 | Pavement (width=7.5m)
| a) Granular Sub-Base (GSB = 150 mm) |  | 3.69 |  |  |  | 12.66 | Km | 8.565%
| b) Wet Mix Macadam (WMM = 250 mm) |  | 7.43 |  |  |  | 12.66 | Km | 17.25%
3 | Bituminous Courses
| a) DBM (60 mm) |  | 6.71 |  |  |  | 12.66 | Km | 15.58%
| b) BC (30 mm) |  | 4.45 |  |  |  | 12.66 | Km | 10.33%
4 | Side Drain |  | 2.7 | 2021-01-29 | 29.10.2021 | 31.03.2024 | 10010 | Rm | 6.267% |  | Work completed
| a) Concrete Lined Side drain | [5 empty] | 6340 | Rm
| b) Unlined Side Drain | [5 empty] | 3670 | Rm
5 | Protection Work (Retaining Wall) |  | 3.46 |  |  |  | 486 | Rm | 8.032%
| a) Type-I (Ht.= 3m) | [5 empty] | 160 | Rm
| b) Type-II (Ht.= 4m) | [5 empty] | 117 | Rm
| c) Type-III (Ht.= 5m) | [5 empty] | 209 | Rm
6 | Cross Drainage Works (Box Culvert) |  | 8.08 |  |  |  | 53 | No. | 18.76%
| a) Type-I ( 1.5mx1.5m) | [5 empty] | 38 | No.
| b) Type-II ( 2mx2m) | [5 empty] | 11 | No.
| c) Type-III ( 3mx4m) | [5 empty] | 2 | No.
| d) Type-IV ( 4mx5m) | [5 empty] | 2 | No.
7 | Project Facilities
| a) Traffic signages & Road safety measures, Km stones, Informatory signs etc. |  | 0.25 |  |  |  | 12.66 | km | 0.58%
| b) PCC Parapet Wall |  | 0.27 |  |  |  | 360 | Rm | 0.6267%
100%
[9 empty] | Total = | 100%
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY, 2026
Name of Division: Siaha Division
Name of contractor: Tantia Constructions Ltd., DD-30, Sector -I, Salt Lake City, Kalkata
Aggrement amount : Rs.43,07,95,440.00
| A.Financial Report | [10 empty] | ANNEXURE - F
| Sl.No. | Name of the project Location and State | Name of the Implementing Agency/Deptt | Approved Cost by MDoNER |  | Fund released by MDoNER/NEC |  | Expenditure made |  | Unspent balance out of the fund released | Status of submission of U/Cs | Remark
|  |  |  | Origincal cost | Revised cost | During | Since inception (Cumulative) | During the month vis-a-vis target | Since inception (cumulative)
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
| 1 | Upgradation of Saiha - Lungbun - Tluangram - Haka Road in the State of Mizoram under North East Special Infrastructure Development Scheme(NESIDS) on EPC Mode. | PWD Siaha Division, Siaha | 50.21 Cr | Nil | NIL | 42.44 | NIL | 42.44 | 0 | Nil | Work completed
Name of the Officer : Er. K.LUAIMINTHANGA
Designation : Sr. Executive Engineer, PWD,
Date with Seal : 05.01.2026

## TLABUNG DIV
MONTHLY PROGRESS REPORT FOR THE MONTH OF JANUARY / 2026 UNDER PWD, TLABUNG DIVISION.
[10 empty] | Physical in % |  | Financial in lakh
Sl No | Name of Scheme | Unit | Approved cost (in lakh) | Date of Commencement | Target date of completion | Cummulative progress at the end of last mont |  | Achievement of works during the month |  | Overall Cummulative achievement |  | Remarks | Mode of Contract
| Name of works / Project |  |  |  |  | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
A | SASCI
1 | Strengthening of Chawngte and Borapansury road | km | 391.3 | 22.06.2023 | 22.06.2024 | 69% | 273.78 |  |  | 69% | 273.78 | On-going Extension granted upto Dt.31.03.2026 | Item Rate
2 | Restoration of Damage Due to Cyclone Remal under Tlabung Division | Km | 800 | 16.06.2025 | 16.01.2026 | 90% | 506.26 |  |  | 90% | 506.26 |  | Item Rate
B | NABARD
1 | Improvement of Chawngte - Borapansury Road (0.000-30.00)KMP | Km | 3987 | 15.03.2023 | 15.03.2025 | 34% | 1022.997 | 3% |  | 37% | 1022.997 | On-going Extension granted upto Dt.13.07.2026 | Item Rate
2 | Const of Galvanised Steel Concrete Composit Bridge over Borapansury River on Chawngte to Borapansury road | Nos | 635.69 | 13.05.2024 | 13.05.2026 | 5% | 0 |  |  | 5% | 0 |  | Item Rate
(R.LALRINMAWIA)
Sr. Executive Engineer, PWD..
Tlabung Division, Tlabung