## ARND
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL, 2026
Name of Work : 5054-C.O. on Roads & Bridges under Aizawl Road North Division for the year 2025-2026
Name of Scheme : State funding (5054)
Sanctioned Amount : Rs. 254.74 lakh
Agreement Amount : Rs. 230.32 lakh
Name of Contractor : M/s Sumati Creative Infrastructure Pvt. Ltd., Dhanbad, Jharkhand
Name of Division : Aizawl Road North Division
Sl. No. | Sub-Head of works | Unit | Qnty | Approved Cost (in lakh) | Date of Commencement | Target Date of Completion | Commulative Progress at the end of Last Month |  | Achievement of Works during the Month |  | Overall cumulative achievement |  | Remarks | Mode of Contract
[7 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Resurfacing of RIPANS Approach Road | Km | 0.8 | 254.74 | 2025-12-27 | 2026-06-27 | 100% | 234.85 | 0% | - | 100% | 234.85 | Works in progress | Item rate
2 | Resurfacing of Zonuam Internal road Part-II | Km | 0.4 |  |  |  | 100% |  | 0% |  | 100%
3 | Patch repair of Industrial Complex road at Zuangtui (Hangi lunglen tlang) | Km | 3.5 |  |  |  | 100% |  | 0% |  | 100%
4 | Construction of Flexible Pavement at Brigade Lower lane road | Km | 0.5 |  |  |  | 100% |  | 0% |  | 100%
5 | Construction of Flexible Pavement at Brigade field ring road | Km | 0.25 |  |  |  | 100% |  | 0% |  | 100%
6 | Improvement of Approach road to Central Jail at Sakawrtuichhun | Km | 2.5 |  |  |  | 100% |  | 0% |  | 100%
7 | Construction of V-Shaped Side Drain at Leitan Thlanmual Road | Km | 0.62 |  |  |  | 100% |  | 0% |  | 100%
8 | Widening of UPHC to Mualhnihna tuikhur road at Zemabawk | Km | 0.5 |  |  |  | 100% |  | 0% |  | 100%
9 | SMBT near EFCI Church at Zembawk East | Km | 0.285 |  |  |  | 100% |  | 0% |  | 100%
10 | Junction Improvement near Modern School at Saron Veng | Km | 0.05 |  |  |  | 100% |  | 0% |  | 100%
| Total = |  |  | 254.74
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL, 2026
Name of Work : Patch repair of various roads under Aizawl Road North Sub Division-III | [8 empty] | Name of Contractor: Vanlalvuta Chinzah
Agreement Amount : ₹ 2,69,71,259.00 | [8 empty] | Date of Commencement: 17.3.2026
Name of Division : Aizawl Road North Sub-Division-III | [8 empty] | Target date of Completion: 24.6.2026
Source of funding: 5054 (Untied)
OVERALL ACHIEVEMENT (PHY) - 100%
Sl. No. | Name of Project | Unit | Approved Cost (Rs. in lakh) | Date of Commencement | Target date of completion | Cumulative Progress at the end of last month |  | Achievement works during the month |  | Overall cummulative achievement |  | Remarks | Mode of contract
[6 empty] | Phy. | Fin. | Phy. | Fin. | Phy. | Fin.
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
PATCH REPAIR OF VARIOUS ROADS UNDER AIZAWL ROAD NORTH SUB DIVISION-III
1 | Patch repair and seal coat | Km | 269.71 | 2026-03-17 | 2026-06-24 | 0% | 0% | 70% | - | 70% | - | Phy Completed | Item Rate
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL, 2026
Name of Work : Improvement & Upgradation of various roads under Aizawl Road North Sub Division-III | [8 empty] | Name of Contractor: Lalremruata, Zemabawk
Agreement Amount : ₹ 1,07,47,080.00 | [8 empty] | Date of Commencement: 17.3.2026
Source of funding: 5054 (Untied) | [8 empty] | Target date of Completion: 24.6.2026
OVERALL ACHIEVEMENT (PHY) - 100%
Sl. No. | Name of Project | Unit | Approved Cost (Rs. in lakh) | Date of Commencement | Target date of completion | Cumulative Progress at the end of last month |  | Achievement works during the month |  | Overall cummulative achievement |  | Remarks | Mode of contract
[6 empty] | Phy. | Fin. | Phy. | Fin. | Phy. | Fin.
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
IMPROVEMENT & UPGRADATION OF VARIOUS ROADS UNDER AIZAWL ROAD NORTH SUB DIVISION-III
1 | Patch repair and seal coat | Km | 107.47 | 2026-03-17 | 2026-06-24 | 0% | 0% | 70% | - | 70% | - | Phy Completed | Item Rate
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL, 2026
Name of Work : Resurfacing of road within Aizawl city under Aizawl Road North Division
Name of Scheme : State Funding
Tender Amount : Rs. 2145.56 lakh
Agreement Amount : Rs. 2145.56 lakh
Name of Contractor : Nidhi Creative infrastructure Pvt.Ltd.
Name of Division : Aizawl Road North Division
Sl. No. | Name of works | Unit | Qnty | Approved Cost (in lakh) | Date of Commencement | Target Date of Completion | Commulative Progress at the end of Last Month |  | Achievement of Works during the Month |  | Overall cumulative achievement |  | Remarks | Mode of Contract
[7 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Non Bituminous Base Course | sqm | 8495 | 52.55 | 2025-04-17 | 2026-10-17 | 100% | 2133.1 | 0% | - | 100% | 2133.1 | Works in progress | EPC
2 | Construction of Flexible Pavement | km | 44.63 | 1647.25 |  |  | 100% |  | 0% |  | 100%
3 | Construction of Rigid Pavement | km | 1.5 | 397.57 |  |  | 0% |  | 0% |  | 0%
4 | Construction of Hume Pipe Culvert | No. | 1 | 6.14 |  |  | 100% |  | 0% |  | 100%
5 | Widening of Tlaklui to Sihpui road Junction | Rm | 60 | 42.05 |  |  | - |  | 2% |  | 2%
| Total = |  |  | 2145.56 |  |  | 25.43% | 99.42% | 4.85% | 0% | 30.28% | 99.42%
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL, 2026
Name of Work : Widening and Improvement of Road from Durtlang Leitan To Sihphir Section (Length 10.25 Km) of Aizawl - Durtlang - Lungdai - Kawnpui Road in the State Of Mizoram | [7 empty] | Name of Contractor : M/s SLT Infracon Private Limited
Name of Scheme : CRF | [7 empty] | Date of Commencement : 14/07/2023
Tender Amount : Rs. 46.57 Crore | [7 empty] | Target date of Completion : 31/01/2025
Agreement Amount : Rs. 35.53 Crore | [7 empty] | Revised Target date of Completion : NIL
Name of Division : Aizawl Road North Division | [7 empty] | D-III Balance :
OVERALL ACHIEVEMENT (PHY) - 88.66% | [10 empty] | (Rs. in lakh)
Sl. No. | Name of Works | Unit | Cost (in lakh) | Date of commencement | Target date of completion | Cumulative Progress at the end of last month |  | Achievement works during the month |  | Overall cumulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Scarifying | Rm | 7.76 | 14.7.23 | 31.1.25 | 100% | 2572.88 | 0% | - | 100% | 2572.88 | In Progress (Rs. 39,64,426.00 kept in D - III) | EPC
2 | Earthwork | Cum | 102.89 |  |  | 100% |  | 0% |  | 100%
3 | Granular Sub-Base (GSB) | m3 | 166.68 |  |  | 100% |  | 0% |  | 100%
4 | Dry Lean Concrete (DLC) | Rm | 299.22 |  |  | 100% |  | 0% |  | 100%
5 | Pavement Quality Concrete (PQC) | Rm | 1638.24 |  |  | 100% |  | 0% |  | 100%
6 | Slope Protection | Rm | 715.77 |  |  | 90% |  | 0% |  | 90%
7 | Lined Side Drain | Rm | 148.94 |  |  | 70% |  | 5% |  | 75%
8 | Hume Pipe | Nos. | 484.5 |  |  | 100% |  | 0% |  | 100%
9 | RCC Slab Culvert | Nos. | 57.66 |  |  | 100% |  | 0% |  | 100%
10 | Crash barrier | Rm | 34.56 |  |  | 0% |  | 0% |  | 0%
11 | Traffic Signages | Nos. | 3.91 |  |  | 0% |  | 0% |  | 0%
12 | Road Marking | Rm | 7.91 |  |  | 0% |  | 0% |  | 0%
13 | Km Stone | Nos. | 0.38 |  |  | 0% |  | 0% |  | 0%
14 | Flexible Pavement | Rm | 320.52 |  |  | 0% |  | 100% |  | 100%
15 | Lined Side Drain with Steel Grating | Rm | 12.54 |  |  | 60% |  | 15% |  | 75%
16 | Cable Duct | Nos. | 15.91 |  |  | 100% |  | 0% |  | 100%
17 | Zebra Crossing | Sqm | 2.06 |  |  | 0% |  | 0% |  | 0%
18 | Road Stud | Nos. | 11.35 |  |  | 0% |  | 0% |  | 0%
19 | Foothpath | Rm | 362.84 |  |  | 15% |  | 25% |  | 40%
20 | Waiting Shed | Nos. | 9.04 |  |  | 0% |  | 0% |  | 0%
4402.68
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL, 2026
Name of Work : Balance Work for Construction of Two Lane Road From Sihhmui To Ramrikawn Road (Stage-I: Length 14.50 Kms) | [9 empty] | Name of Contractor: F. Lalawmpuia, Tuikual S
Agreement Amount : Rs. 8,74,00,000.00 | [9 empty] | Date of Commencement: 12.03.2026
Agreement No.: AGM - 21/SBD/CE-HW/2025-26 Dt. 25.02.2026 | [9 empty] | Target date of Completion: 12.09.2027
Name of Division : Aizawl Road North Division
Source of funding : CRIF
Sl. No. | Name of Project | Unit |  | Approved Cost (₹ in lakh) | Date of Commencement | Target date of completion | Cumulative Progress at the end of last month |  | Achievement works during the month |  | Overall cummulative achievement |  | Remarks | Mode of contract
[7 empty] | Phy. | Fin. | Phy. | Fin. | Phy. | Fin.
1 | 2 | 3 |  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
A. | FORMATION CUTTING : |  |  | 5: 12.03.2026; 6: 12.09.2027; 13: Work in Progress; 14: Item rate
a | Clearing, setting, etc. | 1 | Km | 4: 0.225; 7: 100%; 8: -; 9: 0%; 10: -; 11: 100%
b | Earthwork (Formation Cutting) | 24011.6679 | Cum | 4: 79.06; 7: 70%; 8: -; 9: 10%; 10: -; 11: 80%
B. | SIDE DRAINS :
| Unlined Side drain | 13260 | Rm | 4: 38.1
| Concrete lined drain | 944 | Rm | 4: 22.36
C. | RETAINING STRUCTURES :
a | RETAINING WALL | 251 | Rm | 4: 217.07; 7: 30%; 8: -; 9: 10%; 10: -; 11: 40%
D. | CROSS DRAINAGE WORKS :
a | HP CULVERT | 6 | No | 4: 36.485; 7: 10%; 8: -; 9: 0%; 10: -; 11: 10%
b | BOX CULVERT
| Type- III (7m X 7m) | 2 | No | 4: 324.67
E | RCC Counterfort Rwall | 42 | Rm | 4: 156.03
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL, 2026 UNDER NABARD
OVERALL ACHIEVEMENT (PHY) - 92.39%
Sl. No. | Name of Project | Unit | Approved Cost (Rs. in lakh) | Date of Commencement | Target date of completion | Cumulative Progress at the end of last month |  | Achievement works during the month |  | Overall cummulative achievement |  | Remarks | Mode of contract
[6 empty] | Phy. | Fin. | Phy. | Fin. | Phy. | Fin.
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
IMPROVEMENT OF RAMRIKAWN TO NH-54 VIA SAKAWRTUICHHUN ROAD (3.00 Kmp - 7.50 Kmp = 4.50 Km)
1 | Rigid Pavement of Ramrikawn to Sakawrtuichhun | Rm | 480.72 | - | - | 92% | 379.5 | - | - | 92% | 379.50 (Rs. 58,99,116.00 kept in D - III) | Work in progress | Departmental
2 | Resurfacing of Ramrikawn to Zihnghalkawn 980Rm | Rm |  | 4: -; 5: -; 6: 100%; 8: -; 10: 100%; 12: Phy Completed
3 | Construction of approach road to Chawlhhmun from Power Grid at Tuivamit | Rm |  | 4: -; 5: -; 6: 100%; 8: -; 10: 100%; 12: Phy Completed
4 | Constn. of R/Wall at Ch 4.230 Kmp at Sakawrtuichhun | Rm |  | 4: -; 5: -; 6: 100%; 8: -; 10: 100%; 12: Phy Completed
5 | Constn. of R/Wall at Ch 3.420 Kmp at Sakawrtuichhun | Rm |  | 4: -; 5: -; 6: 100%; 8: -; 10: 100%; 12: Phy Completed
6 | Constn. of R/Wall at Ch 6.340 Kmp at Sakawrtuichhun | Rm |  | 4: -; 5: -; 6: 100%; 8: -; 10: 100%; 12: Phy Completed
7 | Constn of Slab Culvert at 5.900 kmp at Sakawrtuichhun | Rm |  | 4: -; 5: -; 6: 100%; 8: -; 10: 100%; 12: Phy Completed
8 | Constn. of R/Wall at Ch 3.000 Kmp at Sakawrtuichhun | Rm |  | 4: -; 5: -; 6: 100%; 8: -; 10: 100%; 12: Phy Completed
9 | Constn. of R/Wall at Ch 3.500 Kmp at Sakawrtuichhun | Rm |  | 4: -; 5: -; 6: 100%; 8: -; 10: 100%; 12: Phy Completed
10 | Constn. of R/Wall at Ch 4.620 Kmp at Sakawrtuichhun | Rm |  | - | - | 100% |  | - |  | 100% |  | Phy Completed | Departmental
11 | Constn. of R/Wall at Ch 5.360 Kmp at Sakawrtuichhun | Rm |  | 4: -; 5: -; 6: 100%; 8: -; 10: 100%; 12: Phy Completed
12 | Constn. of R/Wall at Ch 5.200 Kmp at Sakawrtuichhun | Rm |  | 4: -; 5: -; 6: 100%; 8: -; 10: 100%; 12: Phy Completed
13 | Constn. of R/Wall at Ch 6.050 Kmp at Sakawrtuichhun |  |  | 4: -; 5: -; 6: 100%; 8: -; 10: 100%; 12: Phy Completed
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL, 2026
PM - DevINE
A. Physical Report
(Rs. in lakhs)
Sl No | Name of the project, location and State | Name of the Implementing Agency/Deptt. | Approved cost by MDoNER/NEC & Date of Approval | 5: Date of actual commencement of work/scheme; 6: Target date of completion of work/scheme; 7: Scope of the work/scheme in physical terms (eg. Kms etc); 9: Physical Achievement; 11: Remarks
|  |  | Cost | 4: Date; 9: Percentage(during the month); 10: Percentage till the reporting period
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |  | 9 | 10 | 11
1 | Construction of Bamboo Link Road from Tuirial Airfield to North Chaltlang (18 Kms) under PM - DevINE | Public Works Department | 3358 | 17.4.23 | 01.08.2023 | 20.10.2025 | Widening | 18.00 Kms | 2.06% | 89.9% | Work in progress
[7 empty] | Retaining Wall | 587.60 Kms
[7 empty] | Culverts | 38.00 Kms
[7 empty] | Lined Side Drain | 9000.00 Kms
[7 empty] | Unlined Side Drain | 8706.00 Rm
[7 empty] | Rigid Pavement | 17.00 Kms
[7 empty] | Flexible Pavement | 1.00 Km
[7 empty] | Road Furnitures | 18.00 Kms
MONTHLY PROGRESS REPORT FOR THE MONTH OF MARCH, 2026
PM - DevINE
B. Financial Report
(Rs. in lakhs)
Sl No | Name of the project, location and State | Name of the Implementing Agency/Deptt. | Approved cost by MDoNER/NEC & Date of Approval | 5: Fund released by MDoNER/NEC; 7: Expenditure made; 9: Unspent balance out of the fund released; 10: Status of submission of U/Cs; 11: Remarks
|  |  | Original Cost | 4: Revised Cost; 5: During 2024 - 2025; 6: Since inception (cumulative); 7: During the month vis-à-vis target; 8: Since inception (cumulative)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Construction of Bamboo Link Road from Tuirial Airfield to North Chaltlang (18 Kms) under PM - DevINE | Public Works Department | Rs. 3358.00 on 06.02.23 | Rs. 3374.42 on 02.09.25 | - | - | - | 2298.78 | - | - | Work in progress
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL, 2026 UNDER ARND
Name of Work : Repair and Resurfacing of Zuangtui to Muthi Road |  |  |  | 8: Name of Contractor: H. Lalrema, Khatla South Veng, Aizawl
Agreement Amount : ₹ 39,43,560.00 |  |  |  | 8: Date of Commencement: 04.02.2026
Agreement No.: T-11013/115/25/ARN/AGM/2 Dt. 21.01.2026 |  |  |  | 8: Target date of Completion: 04.05.2026
Name of Division : Aizawl Road North Division
Source of funding: 5054
Overall Physical Achievement : 100%
Sl. No. | Name of Project | Unit |  | Approved Cost (Rs. in lakh) | Date of Commencement | Target date of completion | Cumulative Progress at the end of last month |  | Achievement works during the month |  | Overall cummulative achievement |  | Remarks | Mode of contract
[7 empty] | Phy. | Fin. | Phy. | Fin. | Phy. | Fin.
1 | 2 | 3 |  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Scarifying Existing Granular Surface | 600.46 | cum | 30233 | 04.02.2026 | 04.05.2026 | 100% |  | 0% |  | 100% | (Rs. 39,43,560.00 kept in D - III) | Phy Completed | Item Rate
2 | Water Bound Macadam | 60.05 | cum | 4: 357590; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed
3 | Prime Coat | 600.46 | cum | 4: 30900; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed
4 | Tack Coat | 9322.5 | cum | 4: 3284876; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed
5 | Close Graded Premix Surfacing/Mixed Seal Surfacing | 9322.5 | cum | 4: 239961; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL, 2026 UNDER ARND
Name of Work : Resurfacing of Approach Road to Bungbangla at Zemabawk |  |  |  | 8: Name of Contractor: Lalsangliani, Kanan Veng, Aizawl
Agreement Amount : ₹ 42,97,915.00 |  |  |  | 8: Date of Commencement: 04.02.2026
Agreement No.: T-11013/115/25/ARN/AGM/3 Dt. 21.01.2026 |  |  |  | 8: Target date of Completion: 04.05.2026
Name of Division : Aizawl Road North Division
Source of funding: 5054
Overall Physical Achievement : 100%
Sl. No. | Name of Project | Unit |  | Approved Cost (Rs. in lakh) | Date of Commencement | Target date of completion | Cumulative Progress at the end of last month |  | Achievement works during the month |  | Overall cummulative achievement |  | Remarks | Mode of contract
[7 empty] | Phy. | Fin. | Phy. | Fin. | Phy. | Fin.
1 | 2 | 3 |  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Scarifying Existing Granular Surface | 3026 | cum | 161497 | 04.02.2026 | 04.05.2026 | 100% | 42.97 | 0% | - | 100% | 42.97 | Phy Completed | Item Rate
2 | Water Bound Macadam | 458.1 | cum | 4: 2634556; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed
3 | Prime Coat | 3026 | cum | 4: 165007; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed
4 | Open Graded Premix Surfacing | 3026 | cum | 4: 825038; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed
5 | Tack Coat | 3026 | cum | 4: 163827; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed
6 | Seal Coat | 3026 | cum | 4: 347990; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL, 2026 ARND
Name of Work : Widening and Pavement of roads from Federation Enclave, Ainawn to Luangmual Thlanmual via Gan Sabra Luangmual under SASCI 2025-2026 Part-I |  |  |  | 9: Name of Contractor : LL Consultancy, Chhinga Veng
Agreement Amount : ₹ 2,57,53,982.11 |  |  |  | 9: Date of Start of Work : 25.02.2026
Agreement No.: AGM-18/SBD/CE-HW/2025-2026 Dt. 10.02.2026 |  |  |  | 9: Stipulated Date of Completion : 25.02.2027
Name of Division : Aizawl Road North Sub-Division-III
Source of funding: SASCI-I
Overall Physical Achievement : 0.60%
Sl. No. | Name of Project | Unit |  | Approved Cost (Rs. in lakh) | Date of Commencement | Target date of completion | Cumulative Progress at the end of last month |  | Achievement works during the month |  | Overall cummulative achievement |  | Remarks | Mode of contract
[7 empty] | Phy. | Fin. | Phy. | Fin. | Phy. | Fin.
1 |  | 3 |  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Earthwork | 1400 | Rm | 11.9455 | 2026-02-25 | 2027-02-25 | 5% | - | 10% | - | 15% | - | Work in Progress | Item Rate
2 | Flexible Pavement | 0.4 | Rm | 17.546 |  |  | 0% | - | 0% | - | 0% | - | Not yet started
3 | Rigid Pavement | 1400 | Rm | 135.4398 |  |  | 0% | - | 0% | - | 0% | - | Not yet started
4 | Hume Pipe Culvert | 6 | No. | 24.1483 |  |  | 0% | - | 0% | - | 0% | - | Not yet started
5 | Extension of Hume Pipe Culvert | 4 | No. | 8.7248 |  |  | 0% | - | 0% | - | 0% | - | Not yet started
6 | Retaining Wall | 80 | Rm | 35.0004 |  |  | 0% | - | 0% | - | 0% | - | Not yet started
7 | V-shaped Side Drain | 1200 | Rm | 24.7351 |  |  | 0% | - | 0% | - | 0% | - | Not yet started
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL, 2026 UNDER ARND
Name of Work : Construction of Approach Road to Thuhruk Lui Bridge on Agriculture Link Road at Mat Phai, Serchhip and Bengbawng Zau at Durtlang, Aizawl District |  |  |  | 8: Name of Contractor: Lalrintluangi, Durtlang Dawrkawn, Aizawl
Agreement Amount : ₹ 2,38,41,678.00 |  |  |  | 8: Date of Commencement: 19.09.2025
Agreement No.: AGM-6/SE-CC/PWD/2025-2026 Dt. 04.09.2025 |  |  |  | 8: Target date of Completion: 19.05.2026
Name of Division : Aizawl Road North Division
Source of funding: SASCI-V
Overall Physical Achievement : 64.36%
Sl. No. | Name of Project | Unit |  | Approved Cost (Rs. in lakh) | Date of Commencement | Target date of completion | Cumulative Progress at the end of last month |  | Achievement works during the month |  | Overall cummulative achievement |  | Remarks | Mode of contract
[7 empty] | Phy. | Fin. | Phy. | Fin. | Phy. | Fin.
1 | 2 | 3 |  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Thuhruk lui bridge on Agriculture link Road at Mat Phai, Serchhip | 224.64 | cum | 8493645 | 19.09.2025 | 19.05.2026 | 0% | 4.64 | 0% | 70 | 0% | 74.64 | Not yet started | Item Rate
2 | Bengbawng Zau at Durtlang, Aizawl District
a | Widening | 1574 | Rm | 4: 3398792; 7: 75%; 9: 25%; 11: 100%; 13: Work in progress
b | Pavement | 1541 | Rm | 4: 4073045; 7: 0%; 9: 100%; 11: 100%; 13: Phy Completed
a | Retaining Wall | 89 | Rm | 4: 2447247; 7: 85%; 9: 15%; 11: 100%; 13: Phy Completed
b | RCC Frame Retaining Wall | 43 | Rm | 4: 1659702; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed
c | V-Shape Side Drain | 1120 | Rm | 4: 3428100; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed
d | Drain Cover | 60 | Rm | 4: 141147; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed
e | Cross Drain | 2 | No. | 4: 200000; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL, 2026 UNDER ARND
Name of Work : Construction of Approach Road to IGC Complex, Luangmual under SASCI Part V of 2024-2025 |  |  |  | 8: Name of Contractor: Zonunpuii, Kolasib Hmar Veng
Agreement Amount : ₹ 4,80,67,489.00 |  |  |  | 8: Date of Commencement: 03.07.2025
Agreement No.: AGM-2/SE-CC/PWD/2025-2026 Dt. 18.06.2025 |  |  |  | 8: Target date of Completion: 03.07.2026
Name of Division : Aizawl Road North Sub-Division-III
Source of funding: SASCI-V
Overall Physical Achievement : 91.00%
Sl. No. | Name of Project | Unit |  | Approved Cost (Rs. in lakh) | Date of Commencement | Target date of completion | Cumulative Progress at the end of last month |  | Achievement works during the month |  | Overall cummulative achievement |  | Remarks | Mode of contract
[7 empty] | Phy. | Fin. | Phy. | Fin. | Phy. | Fin.
1 | 3 | 3 |  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Improvement of IGC, Luangmual |  |  | 5: 2025-07-03; 6: 2026-07-03; 8: 216.24; 10: 93.58; 12: 309.82
a | Earthwork | 200 | Rm | 4: 978568; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed; 14: Item Rate
b | Flexible Pavement | 1500 | Rm | 4: 20821135; 7: 0%; 9: 100%; 11: 100%; 13: Phy Completed
c | Re-construction of slabs culvert | 4 | No. | 4: 988218; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed
d | Hume Pipe Culvert | 5 | No. | 4: 1545232; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed
e | Retaining Wall | 60 | Rm | 4: 1773085; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed
f | RCC Line side drain with cover | 200 | Rm | 4: 1374490; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed
g | Trapezoidal side drain | 500 | Rm | 4: 1632485; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed
2 | Improvement of road from Tanhril Presbyterian Church to MZU
a | Flexible Pavement | 800 | Rm | 4: 6170189; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed; 14: Item Rate
b | Hume Pipe Culvert | 2 | No. | 4: 996811; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed
3 | Improvement of road from Tlana Lungdawh kawn to PWD Site |  |  | 5: 2025-07-03; 6: 2026-07-03; 8: -; 10: -; 12: -
a | Earthwork | 980 | Rm | 4: 1456657; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed; 14: Item Rate
b | Rigid Pavement | 1000 | Rm | 4: 7526950; 7: 50%; 9: 10%; 11: 60%; 13: Work in progress; 14: Item Rate
c | Flexible Pavement | 800 | Rm | 4: 1308555
d | Hume Pipe Culvert | 3 | No. | 4: 1495114; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed; 14: Item Rate
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL, 2026 UNDER ARND
Name of Work : Improvement of Road from Ainawn to Tuithum |  |  |  | 8: Name of Contractor: F. Lalmalsawma, Tuikual
Agreement Amount : ₹ 16,35,30,525.00 |  |  |  | 8: Date of Commencement: 15.07.2025
Agreement No.: AGM-3/SE-CC/PWD/2025-2026 Dt. 01.07.2025 |  |  |  | 8: Target date of Completion: 15.07.2026
Name of Division : Aizawl Road North Sub-Division-III
Source of funding: SASCI-V
Overall Physical Achievement : 16.00%
Sl. No. | Name of Project | Unit |  | Approved Cost (Rs. in lakh) | Date of Commencement | Target date of completion | Cumulative Progress at the end of last month |  | Achievement works during the month |  | Overall cummulative achievement |  | Remarks | Mode of contract
[7 empty] | Phy. | Fin. | Phy. | Fin. | Phy. | Fin.
1 | 2 | 3 |  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Earthwork | 4682 | Rm | 20371452 | 2025-07-15 | 2026-07-15 | 90% | 250.56 | 5% | 364.38 | 95% | 614.94 | Work in Progress | Item Rate
2 | RCC side drain | 2000 | Rm | 4: 7896319
3 | RCC Slab Culvert | 4 | No. | 4: 2912158
4 | Hume Pipe Culvert | 5 | No. | 2614215 |  |  | 75% |  | 5% | - | 80% | - | Work in Progress | Item Rate
5 | Retaining Wall | 200 | Rm | 9720546 |  |  | 20% |  | 30% | - | 50% | - | Work in Progress | Item Rate
6 | RCC Frame Structure Retaining Wall | 70 | Rm | 4: 3729602
7 | Minor Bridge | 4 | No. | 4: 23515882
8 | Rigid Pavement | 2380 | Rm | 4: 74239201
9 | Flexible Pavement | 2000 | Rm | 4: 18531150
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL, 2026 UNDER ARND
Name of Work : Construction of Various Earth Retaining and Drainage Structure for Mitigation of Vaivakawn Zohnuai Subsidence Areas |  |  |  | 8: Name of Contractor: Jenny Lalthansangi, Vavakawn Zohnuai
Agreement Amount : ₹ 2,96,11,018.00 |  |  |  | 8: Date of Commencement: 15.07.2025
Agreement No.: AGM-4/SE-CC/PWD/2025-2026 Dt. 01.07.2025 |  |  |  | 8: Target date of Completion: 01.03.2026
Name of Division : Aizawl Road North Sub-Division-III
Source of funding: SASCI-V
Sl. No. | Name of Project | Unit |  | Approved Cost (Rs. in lakh) | Date of Commencement | Target date of completion | Cumulative Progress at the end of last month |  | Achievement works during the month |  | Overall cummulative achievement |  | Remarks | Mode of contract
[7 empty] | Phy. | Fin. | Phy. | Fin. | Phy. | Fin.
1 | 2 |  | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Breast Wall on lower side of Pu Sangthanmawia's Land. | 20 | Rm | 29611018 | 2025-07-15 | 2026-03-01 | 100% | 287.84 | 0% | - | 100% | 287.84 | Phy Completed | Item rate
2 | Construction of Breast Wall on Uphill side of RK Road. | 30 | 3: Rm; 7: 20%; 9: 30%; 11: 50%; 13: Work in Progress
3 | Construction of Composite Retaining Wall (Section 1) above NH-6 | 28 | 3: Rm; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed
4 | Construction of Composite Retaining Wall(Section 2) above NH-6 | 28 | 3: Rm; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed
5 | Construction of Breast Wall above NH-6(below RK Road) | 25 | 3: Rm; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed
6 | Construction of Breast Wall on Uphill Side of NH-6 (Near Link Drain) | 15 | 3: Rm; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed
7 | Construction of RCC Line Drain below NH-6(50 m) | 50 | 3: Rm; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed
8 | Construction of RCC Side Drain along NH-6 (Near Culvert,20 m) | 20 | 3: Rm; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed
9 | Construction of Retaining Wall at Nutumi Road | 35 | Rm | 29611018 | 2025-07-15 | 2026-03-01 | 100% |  | 0% | - | 100% | - | Phy Completed | Item rate
10 | Construction of Hume Pipe Culvert at MZU Road | 1 | 3: No.; 7: 0%; 9: 0%; 11: 0%; 13: Not yet started
11 | Construction of side drain at Various places | 1217 | 3: Rm; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed
12 | Clearance of link drain at various places | 122 | 3: Rm; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL, 2026 UNDER ARND
Name of Work : Restoration Of Damage Due To Cyclone Remal Under Aizawl Road North Division, Aizawl Road South Division And Hmuifang Division |  |  | 7: Name of Contractor : Fredy Vanlalngila, Dinthar-I
Agreement Amount : ₹ 11,24,97,994.21 |  |  | 7: Date of Commencement : 27.06.2025
Agreement No.: 4/CE-HW/2025-2026 Dt. 01.06.2025 |  |  | 7: Target date of Completion :27.01.2026
Name of Division : Aizawl Road North Division
Source of funding: Cyclone Remal
Sl. No. | Name of Project | Unit | Approved Cost (Rs. in lakh) | Date of Commencement | Target date of completion | Cumulative Progress at the end of last month |  | Achievement works during the month |  | Overall cummulative achievement |  | Remarks | Mode of contract
[6 empty] | Phy. | Fin. | Phy. | Fin. | Phy. | Fin.
1 | 2 |  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Retaining Wall below Zoramthanga's House | Rm | 20 | 2025-07-01 | 2026-01-31 | 100% | 347.15 | 0% | - | 100% | Rs. 347.15 lakhs bill forwarded to Executive Engineer, Aizawl Road South Division for payment being the Nodal Officer for payment | Phy Completed | Item Rate
2 | Restoration of H/P Culvert at Falkland | Nos | 4: 5; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed; 14: Item Rate
3 | Restoration of Breast Wall at Armed Veng South | Rm | 4: 6; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed; 14: Item Rate
4 | Restoration of Retaining Wall Collapsed at Ramthar North | Rm | 4: 18.01; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed; 14: Item Rate
5 | Construction of Retaining Wall at Falkland | Rm | 4: 3; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed; 14: Item Rate
6 | Construction of Retaining Wall at Thuampui Vengthar | Rm | 4: 8; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed; 14: Item Rate
7 | Construction of Gabion Wall on Darnamlui for Restoration of formation edge collapsed at Ramthar North, Aizawl | Rm | 4: 90.44; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed; 14: Item Rate
8 | Construction of Breast wall at Berawtlang | Km | 20.58 | 1.7.2025 | 30.7.2025 | 100% | 347.15 | 0% | - | 100% | Rs. 347.15 lakhs bill forwarded to Executive Engineer, Aizawl Road South Division for payment being the Nodal Officer for payment | Phy Completed | Item Rate
9 | Construction of Breast wall at Thuampui to Selesih road at Ch:6.000kmp | Km | 21.08 | - | - | 100% |  | 0% |  | 100% |  | Phy Completed | Item Rate
10 | Widening of Lungbial road for diversion of collapsed Balcony on approach road to Berawtlang | Km | 41.06 | - | - | 100% |  | 0% |  | 100% |  | Phy Completed | Item Rate
11 | Construction of retaining wall near Pu Lalzarzoliana's house at Lungbial | Km | 2 | 1.7.2025 | 22.7.2025 | 100% |  | 0% |  | 100% |  | Phy Completed | Item Rate
12 | Construction of Reataining wall at Thuampui to Selesih at Ch:11.800 kmp | Km | 2.43 | 1.7.2025 | 30.7.2025 | 100% |  | 0% |  | 100% |  | Phy Completed | Item Rate
13 | Construction of RCC balcony at Gosen veng at Zuangtui | Km | 17.89 | - | - | 100% |  | 0% |  | 100% |  | Phy Completed | Item Rate
14 | Construction of RCC Rectangular side drain at RIPANS at Zemabawk | Km | 22.01 | - | - | 100% |  | 0% |  | 100% |  | Phy Completed | Item Rate
15 | Construction of Retaining wall at Thuampui to Selesih road at Ch:2.200 kmp | Km | 7.98 | 1.7.2025 | 18.7.2025 | 100% |  | 0% |  | 100% |  | Phy Completed | Item Rate
16 | Repair of Culvert and Retaining Wall @ ch. 3.900 Kmp at MZU Road | Rm | 3.61 | 2025-06-27 | 2026-01-27 | 100% |  | 0% |  | 100% |  | Phy Completed | Item Rate
17 | Construction of Retaing Wall @ ch. 6.325 Kmp at MZU Road | Rm | 4: 4.14; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed; 14: Item Rate
18 | Construction of Retaing Wall at approach road to Tanhril at 0.200 Kmp | Rm | 4: 3.61; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed; 14: Item Rate
19 | Construction of Retaining Wall @ ch. 1.600 Kmp on NH-54 to Sakawrtuichhun Road | Rm | 4: 7.88; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed; 14: Item Rate
20 | Construction of Retaining Wall @ ch. 0.980 Kmp on Zohnuai to Ropaiabawk road | Rm | 11.77 | 2025-06-27 | 2026-01-27 | 100% | 347.15 | 0% | - | 100% | Rs. 347.15 lakhs bill forwarded to Executive Engineer, Aizawl Road South Division for payment being the Nodal Officer for payment | Phy Completed | Item Rate
21 | Construction of Retaining Wall @ ch. 0.200 Kmp on NH-54 to Sakawrtuichhun Road | Rm | 4: 9.44; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed; 14: Item Rate
22 | Construction of Retaining near Pu B. Lalhmingsanga's house at Zonuam | Rm | 4: 1.84; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed; 14: Item Rate
23 | Construction of Retaining Wall at MUP road, Chanmari West | Rm | 4: 6.02; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed; 14: Item Rate
24 | Construction of Retaining Wall @ ch. 1.550 Kmp on Zohnuai to Ropaiabawk Road | Rm | 4: 7.1; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed; 14: Item Rate
25 | Construction of Retaining Wall @ ch. 1.150 on Zohnuai to Ropaiabawk road | Rm | 4: 10.05; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed; 14: Item Rate
26 | Restoration of Sinking portion near Sangthanmawia's house, Vaivakawn | Rm | 4: 70.45; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed; 14: Item Rate
27 | Construction of Retaining Wall near Pi Zaihnuni's house at Chawnpui | Rm | 4: 5.88; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed; 14: Item Rate
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL, 2026 UNDER ARND
Name of Work : Restoration Of Damage Due To Cyclone Remal Under Aizawl Road North Division (Part-II) And National Highway Division-III |  |  | 9: Name of Contractor : Kevin Vanlaltlana, Bungkawn
Agreement Amount : ₹ 11,24,97,994.21 |  |  | 9: Date of Commencement : 13.06.2025
Agreement No.: 4/CE-HW/2025-2026 Dt. 01.06.2025 |  |  | 9: Target date of Completion :13.01.2026
Name of Division : Aizawl Road North Sub-Division-III
Source of funding: Cyclone Remal
Overall Physical Achievement : 100%
Sl No | Name of Project | Unit |  | Approved Cost (Rs. in lakh) | Date of Commencement | Target date of completion | Cumulative Progress at the end of last month |  | Achievement works during the month |  | Overall cummulative achievement |  | Remarks | Mode of contract
[7 empty] | Phy. | Fin. | Phy. | Fin. | Phy. | Fin.
1 | 2 | 3 |  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Improvement of side drain and cross drain at Zotlang internal road | 30 | Rm | 259355.69 | 2025-06-13 | 2026-01-13 | 100% | - | 0% | - | 100% | Rs. 16.14 lakhs bill forwarded to Executive Engineer, National Highway Division - III, for payment being the Nodal Officer for payment | Phy Completed | Item Rate
2 | Construction of V shape side drain from Lalhmingliana Hnamte house to T. Lalzapi's house at Zotlang | 100 | Rm | 4: 386896.83; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed; 14: Item Rate
3 | Construction of V shape side drain from C. Thanchhuma house to Rosiamliana Ralte's house at Zotlang | 40 | Rm | 4: 154811.1; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed; 14: Item Rate
4 | Construction of drain below Pu Lalduhawma's house at Chawlhhmun | 77 | Rm | 4: 812604.91; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed; 14: Item Rate
Sr. Executive Engineer, PWD.,
Aizawl Road North Division,
Aizawl :Mizoram

## ARSD
MONTHLY PROGRESS REPORT UNDER AIZAWL ROAD SOUTH DIVISION, PWD
FOR THE MONTH OF APRIL 2026
Sl. No. | Name of Schemes | Unit | Approved Cost (Rs in Lakh) | Date of Commencement | Target Date of Comple-tion | Cumulative Progress at the end of last month |  | Achievement of works during the month |  | Overall Cumulative achievement |  | Remarks | Mode of Tender
| Name of Works / Project |  |  |  |  | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
I | SEDP (2019-2020)
| Const.of Approach Road to Aizawl College at Mualpui | Rm | 415 | 2021-07-26 | 2022-04-26 | 73% | 300 |  |  | 73% | 300 | On Going ES was accorded vide No.B.12031/17/2019-PWD(T) Dt.26.3.2020 (Rs.100 lakhs); No.G.20016/3/2021-FBT Dt.7.10.2021 (Rs.100 lakhs) and No. B.12031/29/2021-PWD(T) dt. 01.03.2023 (Rs. 100 lakhs) respectively, which totalled Rs.300 out of Rs. 415.00. The remaining balance/ ES was asked for Approval vide No.B.16012/6/22/T(ARS)/I/5 Dt.29th Sept,2022. It was regretted due to Financial Constraint as the year has been declared as year of consolidation vide No. B. 12031/17/2019-PWD(T) dt. 23rd July, 2024. | Item Rate Contract
II | NEDP (2018-2019)
| Construction of Bridge on Chhinga Vengthar to Tuithiang road | Rm | 586.36 | 2021-04-19 | 2022-10-31 | 100% | 200 |  |  | 100% | 200 | Physical Works Completed according to Working Estimate E/S Amount of Rs.200.00 Lakh. The remaining ES was asked for Allocation vide No.B.16011/69-C/15/T(ARS)/28 dated: 23rd Jan, 2023 in which balance ES from Higher Authority is awaited. | Restricted tender
III | Central Road Fund
| Construction of BUG Bridge over R.Tlawng on Aizawl - Reiek - W.Lungdar Road at 14.800 Kmp | Rm | 757.56 | 10:10 | 31.10.24 | 100% | 750.57 |  |  | 100% | 750.57 | Work Completed | EPC mode
IV | PMGSY | [12 empty] | 0
| Upgradation & Maintenance of Hlimen to Samtlang to Lungleng Road | Rm | 1262.12 | 2026-03-17 | 2027-03-17 | 2% |  | 2% |  | 4% |  | On going | e-tendering | 1262.12
V | Restoration of Damage due to Cyclone Remal under ARSD under SASCI 2024-2025 | Rm | 1170 | 2025-07-02 | 2026-02-02 | 100% | 1056.97 |  | 4.22 | 100% | 1061.19 | Work Completed | Restricted tender | 108.81
VI | Maubawk to MINECO Bypass Road on Western Side under SASCI (2025-2026) | [12 empty] | 0
| Formation Cutting | Km | 13.9832 | 15.8.2025 | 15.6.2026 | 100% | 70.88 | - | 39.42 | 100% | 110.3 | Completed | Restricted tender | -96.3168
| Pavement Works | Km | 22.434 | [8 empty] | Not yet started |  | 22.434
| RCC Slab Culvert | No | 68.8716 | [8 empty] | Not yet started
| Protection Work | [10 empty] | On going
| a) Retaining Wall | Rm | 94.1991 |  |  | 95% |  | 0% |  | 95% |  | On going
| b) Breast Wall | Rm | 75.5109 |  |  | 90% |  | 5% |  | 95% |  | On going
| Construction of RCC Balcony Roadway | Rm | 125 |  |  | 30% |  | 20% |  | 50% |  | On going
| Total = |  | 399.9987
VII | Resurfacing leh Road within Aizawl City under Aizawl Road South Division | Rm | 2231.39 | 2025-04-17 | 2025-10-17 | 98% | 1791.61 | 0.66% | 142.77 | 98.66% | 1934.38 | On going | Restricted Tender
VIII | Strengthening and Improvement of State Highways & Other Roads under Mizoram under Central Circle (5054 under ARSD during 2025-26) | Rm | 262.29 | 2025-12-27 | 2026-05-27 | 38% |  | 41.69% |  | 79.69% | 79.94 | On going | Open tender
IX | Repair of Maintenance of the work Aizawl-Reiek-W. Lungdar Under 5054 (Untied Fund) under Aizawl Road South Division during 2025-2026 Additional
1 | Construction of Retaining Wall at Ch 6.700 Kmp on Aizawl Reiek W.Lungdar Road | Rm | 4.89 | 28.2.2026 | 28.5.2026 | 10% |  | 80% | 45.23 | 90% | 45.23 | On going | Open Tender
2 | Construction of Retaining Wall at Ch 32.300 Kmp on Aizawl Reiek W.Lungdar Road | Rm | 3.15 |  |  | 10% |  | 90% |  | 100% |  | Completed
3 | Construction of Retaining Wall at Ch 34.200 Kmp on Aizawl Reiek W.Lungdar Road | Rm | 4.59 |  |  | 10% |  | 90% |  | 100% |  | Completed
4 | Extension of R.C.C Slab Culvert at Ch 4.250 Kmp on Aizawl Reiek W.Lungdar Road | Rm | 13.94 |  |  | 90% |  | 5% |  | 95% |  | On going
5 | Extension of R.C.C Slab Culvert at Ch 4.350 Kmp on Aizawl Reiek W.Lungdar Road | Rm | 18.66 |  |  | 90% |  | 10% |  | 100% |  | Completed
| Total = |  | 45.23
X | Upgradation & Augmentation of Hridaikawn to Pharbawkkawn Road, Aizawl District under SASCI 2025-26 Part-I | [11 empty] | Restricted Tender
1 | Earthwork for widening (including unline side drain) | Km | 80.4377 | 2026-03-03 | 2026-03-03 | 30% |  | 5% |  | 35% |  | On going
2 | Construction of rigid pavement on Hridaikawn to Pharbawkkawn (Aizawl Western bypass) | Km | 269.8597 | [8 empty] | Not yet started
3 | Bituminous Concrete on Hridaikawn to Pharbawkkawn (0+000 km to 0+680 km - repair of existing flexible pavement | Km | 16.0921 | [8 empty] | Not yet started
4 | Retaining Wall | Rm | 77.3251 | [8 empty] | Not yet started
5 | Hume Pipe Culvert | No | 56.2744 | [8 empty] | Not yet started
| Total = |  | 499.989
XI | New Alignment of Road (Masihi Sangati Church to Mission Vengthlang Cemetery Road), Aizawl | [11 empty] | Restricted Tender
1 | Formation Cutting | Km | 108.2656 | 2026-03-20 | 2026-09-20 | 20% |  | 30% |  | 50% |  | On going
2 | Construction of Hume Pipe Culvert | No | 37.618 | [8 empty] | Not yet started
3 | Construction of Retaining Wall |  | 64.1171 |  |  | 10% |  | 20% |  | 30% |  | On going
| Total = |  | 210.0007
XII | Annual Plan 5054 R&B Untied Fund under Aizawl Road South Division during 2025-2026
1 | Patch Repair and Seal Coat at various places |  | 227.17 | 2026-03-21 | 2026-06-21 | 35% |  | 0% | 172.65 | 35% | 172.65 | On Going | Open tender | MIZ
2 | Resurfacing at various places |  | 375.23 | 2026-04-01 | 2026-07-01 |  |  | 49% |  | 49% |  | On going | Open tender | VAI
3 | Construction of Rigid Pavement on Pharbawk to Mauhak internal road via Haimual Tlangnuam West |  | 17 | 2026-04-01 | 2026-09-30 |  |  | 80% |  | 80% |  | On going | Open tender
4 | Construction of Turning Point at Maubawk Tamdo veng |  | 20.47 | 2026-04-01 | 2026-09-30 |  |  | 50% |  | 50% |  | On going | Open tender
| Total = |  | 639.87
Sr.Executive Engineer, PWD;
Aizawl Road South Division,
Aizawl, Mizoram.

## PIU
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL 2026 - PROJECT IMPLEMENTATION UNIT, PWD
Source of Funding : PM DevINE
SL. No. | Name of work /Project. | Approved Cost (Rs) | Name of Implementing agency/Dept. | Date of Commencement | Target Date of Completion | Cummulative progress at the end of last month |  | Achievement of works during the month |  | Overall cumulative achievement |  | Remarks | Mode of Contract
[6 empty] | Physical | Financial | Physical | Financial | Physical | Financial
1 | 2 | 3 | 4 | 5 | 6 | 7 | 24.3 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Aizawl Bypass on Western Side under PM DevINE Scheme Location : Mizoram State : Aizawl | 500 Cr | Project Implementation Unit, PWD | 16.01.2025 | 16.01.2028 | 25.05% | 24.29% | 2.107% | 0.002% | 27.16% | 24.29% |  | EPC
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL 2026 - PROJECT IMPLEMENTATION UNIT, PWD
PHYSICAL ABSTRACT
1: Sl. No.; 2: Name of the project Location and state; 3: Name of the implementing Agency/ Deptt.; 4: Approved cost & date; 6: Date of commencement of work /scheme; Physical 7: Target date of completion of work/scheme; Financial 24.3: Scope of work /scheme physical terms (e.g.Kms etc); Financial 12: Physical Achievement |  | Remark
4: Cost (lakhs); 5: Date; Financial 12: Achievement; Financial 13: Percentage upto date progress; Financial 14: Percentage during last month | Percentage during the report
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |  |  |  | 9 | 10 | 11 | 12 | 13
1 | Construction of Aizawl Bypass on Western Side under PM DevINE Scheme Location : Mizoram State : Aizawl | Project Implementation Unit, PWD | 4510 | 23.12.2024 | 23.12.2024 | 16.01.2028 | 1 | Earthwork up to top of sub-grade | Km | 45 | 30.7 | 68.22% | 53.52% | 14.7%
Financial 24.3: 2; Physical 9: Sub Base Course (SSB); Financial 10: Km; Physical 11: 45; Financial 12: 9.96; Financial 13: 22.13%; Financial 14: 0.9333% | 21.2%
Financial 24.3: 3; Physical 9: Seperation Layer (SAMI); Financial 10: Km; Physical 11: 45; Financial 13: 0%; Financial 14: 0% | 0%
Financial 24.3: 4; Physical 9: Bituminous Work; Financial 10: Km; Physical 11: 45; Financial 13: 0%; Financial 14: 0% | 0%
Financial 24.3: 5; Physical 9: Wearing Course; Financial 10: Km; Physical 11: 45; Financial 13: 0%; Financial 14: 0% | 0%
Financial 24.3: 6; Physical 9: Reconstruction and New Culverts on Existing road/realignmnet bypass - Hume Pipe Culvert; Financial 10: nos; Physical 11: 205; Financial 12: 29; Financial 13: 14.15%; Financial 14: 7.805% | 6.341%
Financial 24.3: 7; Physical 9: Reconstruction and New Culverts on Existing road/realignmnet bypass - RCC Box Culvert; Financial 10: nos; Physical 11: 12; Financial 12: 5; Financial 13: 41.67%; Financial 14: 0% | 41.67%
Financial 24.3: 8; Physical 9: Reconstruction and New Culverts on Existing road/realignmnet bypass - chutes; Financial 10: nos; Physical 11: 1278; Financial 12: 115.6; Financial 13: 9.045%; Financial 14: 0% | 9.045%
Financial 24.3: A; Physical 9: A-Widening and repairs of minor bridges | 0%
Financial 24.3: 1; Physical 9: Repair of minor bridge by construction of wing wall; Physical 11: 0 | 0%
Financial 24.3: B; Physical 9: B-New Minor Bridges | 0%
Financial 24.3: 1; Physical 9: Foundation + Substructure; Financial 10: Nos; Physical 11: 8; Financial 13: 0%; Financial 14: 0% | 0%
Financial 24.3: 2; Physical 9: Super-structure; Financial 10: Nos; Physical 11: 8; Financial 13: 0%; Financial 14: 0% | 0%
Financial 24.3: 3; Physical 9: Approaches; Financial 10: Nos; Physical 11: 8; Financial 13: 0%; Financial 14: 0% | 0%
Financial 24.3: 4; Physical 9: Protection Work; Financial 10: Nos; Physical 11: 8; Financial 13: 0%; Financial 14: 0% | 0%
Financial 24.3: i; Physical 9: Counterfort retaining wall; Financial 10: RMT; Physical 11: 2140; Financial 13: 0%; Financial 14: 0% | 0%
Financial 24.3: ii; Physical 9: Plumb Concrete Retaining Wall; Financial 10: Nos; Physical 11: 1722; Financial 13: 0%; Financial 14: 0% | 0%
Financial 24.3: iii; Physical 9: Breast Wall; Financial 10: RMT; Physical 11: 946; Financial 12: 150; Financial 13: 15.86%; Financial 14: 0% | 15.86%
Financial 24.3: iv; Physical 9: Toe Wall; Financial 10: RMT; Physical 11: 946; Financial 13: 0%; Financial 14: 0% | 0%
Financial 24.3: v; Physical 9: Gabion Breast Wall; Financial 10: RMT; Physical 11: 1355; Financial 12: 1166.5; Financial 13: 86.09%; Financial 14: 35.35% | 50.74%
Financial 24.3: vi; Physical 9: Lined Side Drain; Financial 10: MTR; Physical 11: 5000; Financial 13: 0%; Financial 14: 0% | 0%
Financial 24.3: vii; Physical 9: Crash Barrier; Financial 10: RMT; Physical 11: 2560; Financial 13: 0%; Financial 14: 0% | 0%
Financial 24.3: viii; Physical 9: Traffic Signages; Financial 10: Nos; Physical 11: 225; Financial 13: 0%; Financial 14: 0% | 0%
Financial 24.3: ix; Physical 9: Road Markings; Physical 11: 13050; Financial 13: 0%; Financial 14: 0% | 0%
Financial 24.3: x; Physical 9: Km Stones; Physical 11: 220; Financial 13: 0%; Financial 14: 0% | 0%
Financial 24.3: xi; Physical 9: Boundary Pillar; Physical 11: 600; Financial 13: 0%; Financial 14: 0% | 0%
Financial 24.3: xii; Physical 9: Direction and Place identification; Physical 11: 35; Financial 13: 0%; Financial 14: 0% | 0%
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL 2026 - PROJECT IMPLEMENTATION UNIT, PWD
FINANCIAL REPORT
Sl. No. | Name of project Location and state | Name of Implementing agency/Dept. |  | Approved Cost |  | Fund Released by MDoNER |  | Expenditure Made |  | Unspent balance out of the fund released | Status of submission U/Cs | Remarks
|  |  |  | Orignal cost INR in Crore | Revised cost INR in Crore | During 2024-25 INR in Crore | Since inception (cummulative) | During the month vis-à-vis target | Since inception (Cummulative)
1 | 2 | 3 |  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Construction of Aizawl Bypass on Western Side under PM DevINE Scheme Location : Mizoram State : Aizawl | Project Implementation Unit, PWD |  | 500 | Nil | 20.28 | 133.2349 | 20.37 | 131.49 | 1.7449 | 2 nos. of UC's submitted: 1) 61.09 Crore 2) 51.48 Crore | Mobilization Advance (Rs): 22,59,26,457.00 Recovered: 12,56,81,688.00 Balance : 10,02,44,769.00
| Bill paid to the Contractor | Rs. 96.77Cr
| Financial Progress of the Contractor | 24.29%
| Total Expenditure (Exclusive of Mobilisation Advance) Crore |  | = | 4: 121.46
| Financial Progress (%) |  | = | 4: 24.29%
| Agreement Amount (in Crore) |  | = | 4: 451.85; 10: (K.LALBIAKTHANGA) Project Director, PIU, PWD Cum Authority Engineer Aizawl, Mizoram
| Exp. Amount (in Crore) |  | = | 4: 119.74
| Financial Progress of Civil Works |  | = | 4: 26.5%

## AZBD
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL 2026
Name of Division: Aizawl Building Division
Source of Funding : UIDF
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of completion | Cummulative Progress at the end of last month |  | Acievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Various storm drains and erosion mitigation at MINECO, Aizawl | Percen tage | 220 | 01.03.2026 | 01.02.2027 |  |  | 60% | 2169951 | 60% | 2169951 |  | Departmental
Sr.Executive Engineer, P.W.D.,
Aizawl Building Division,
Aizawl:Mizoram.

## AZL ELEC DIV
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL 2026
Name Of Division : PWD, Electrical Division, Aizawl
Head of Account : Major & Minor Works and Deposit works 8443-108, D-III
Sl. No | Name of Works / Scheme | Unit | Approved Cost Amount (in Lakhs.) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month. |  | Achievement of works during the Month |  | Overall cummulative achievement |  | Remarks
[6 empty] | Phy (%) | Fin(Rs) | Phy (%) | Fin(Rs) | Phy (%) | Fin(Rs)
1 | 2 |  | 3 | 6 |  | 10 | 11 | 12 | 13 | 14 | 15 | 18
1 | SITC of 13 Passenger Lift - 1 no., 2-opening, 900mm centre opening Stainless Steel Cable with Automatic Rescue Device (ARD) for Hydraulic Lift with Minor Civil Works at Lengpui Airport Mizoram | % | 39.24 | 08.09.2021 | 01.04.2024 | 100% | - | 0% | - | 100% | 39.24 | Completed and ready for handover to Aviation
2 | I/E to Arrival & Departure Passenger Lobby at Lengpui Airport | % | 25.27 | 19.12.2020 | 1.4.2024 | 97% | 25.27 | 0% | - | 97% | 25.27 | Completed except toilets (Lad & Gents) electrical room and drinking water point as modification of room is to be done
3 | Street Light Parking light at Lengpui Airport | % | 37.32 | 06.07.2022 | 1.4.2024 | 100% | 37.32 | 0% | - | 100% | 37.32 | Completed
4 | Addl. Estimate for SITC of MRV/VRF Centralizes Air Conditioner Airport First Floor Departure Hall, Mizoram. | % | 247.74 | 12.03.2022 | 04.03.2024 | 98.5% | 244.44 | 0% | - | 98.5% | 244.44 | Completed and ready for final testing and commissioning once upgradation of power house Lengpui Airport is ready
5 | SITC of EPABX System for Lengpui Airport Terminal Building. | % | 24.64 | 06.07.2022 | 29.06.2024 | 98% | 19.46 | 0% | - | 98% | 19.46 | Completed and ready for handover to Aviation
6 | SITC of PA System at Lengpui Airport Terminal Building. | % | 36.36 | 06.07.2022 | 29.06.2024 | 99% | 28.82 | 0% | - | 100% | 28.82 | Completed and ready for handover to Aviation
Sl. No | Name of Works / Scheme | Unit | Approved Cost Amount (in Lakhs.) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month. |  | Achievement of works during the Month |  | Overall cummulative achievement |  | Remarks
[6 empty] | Phy (%) | Fin(Rs) | Phy (%) | Fin(Rs) | Phy (%) | Fin(Rs)
1 | 2 |  | 3 | 6 |  | 10 | 11 | 12 | 13 | 14 | 15 | 18
7 | Supply & Installation of Integrated Fire Hydrant System (Wise Riser)&SITC of Alarm System for Lengpui Airport Terminal Building. | % | 119.96 | 06.07.2022 | 29.06.2024 | 98% | 94.72 | 0% | - | 98% | 94.72 | Completed and ready for handover to Aviation except 15 nos. smoke detector to installed at Hallway near toilets (Lad & Gents) at Southern side due to ceiling work pending
8 | SITC of AVTRON IP Surveillance System for Lengpui Airport Terminal Building. | % | 94.76 | 06.07.2022 | 29.06.2024 | 98% | 67.61 | 0% | - | 98% | 67.61 | Completed and ready for handover to Aviation except 6 nos. Dome camera at Hallway near toilets (Lad & Gents) due to ceiling work pending
9 | SITC of LAN SETUP at Lengpui Airport Terminal Building. | % | 20.05 | 06.07.2022 | 29.06.2024 | 99% | 15.76 | 0% | - | 99% | 15.76 | Completed and final checking for handover to Aviation
10 | Estimate for I/E of Energy Meter for Terminal Building at Lengpui Airport | % | 7.99 | 06.07.2022 |  | 100% | 7.99 | 0% | - | 100% | 7.99 | Completed and ready for handover to Aviation
11 | Renovation/Repairing of Internal Electrification to Polytechnic at Thingdawl (SH: Automobile Engineering Block) | % | 18.65 | 4.10.2023 | 18.11.2023 | 98% | 18.65 | 0% | - | 98% | 18.65 | I/E Work completed, Service connection awaited.
12 | Renovation/Repairing of Internal Electrification to Polytechnic at Thingdawl (SH: Textile Technology Block) | % | 18.71 | 4.10.2023 | 18.11.2023 | 98% | 18.71 | 0% | - | 98% | 18.71 | I/E Work completed, Service connection awaited.
13 | Renovation/Repairing of Internal Electrification to Polytechnic at Thingdawl (SH: Administrative Block) | % | 9.52 | 4.10.2023 | 18.11.2023 | 98% | 9.52 | 0% | - | 98% | 9.52 | I/E Work completed, Service connection awaited.
Sl. No | Name of Works / Scheme | Unit | Approved Cost Amount (in Lakhs.) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month. |  | Achievement of works during the Month |  | Overall cummulative achievement |  | Remarks
[6 empty] | Phy (%) | Fin(Rs) | Phy (%) | Fin(Rs) | Phy (%) | Fin(Rs)
1 | 2 |  | 3 | 6 |  | 10 | 11 | 12 | 13 | 14 | 15 | 18
14 | SITC of 5-passenger Lift for Fast Track Court Building at Kolasib | % | 3.9 | 26.12.2024 | 31.08.2025 | 40% | - | 20% | - | 60% |  | All materials delivered at site work to be started soon
15 | SITC of 13-passenger Lift for Fast Track Court Building at Kolasib | % | 49.85 | 26.12.2024 | 31.08.2025 | 40% | - | 0% | - | 60% |  | All materials delivered at site work to be started soon
16 | Impvt/Upgradation of Operational/Non-Operational facilities of Lengpui Airport(SH:Northern Side Baggage conveyor belt) | % | 192.5 | 22.07.2024 | 18.12.2024 | 100% | - | 0% | - | 100% | 373.6 | Completed and final checking being done for handover to Aviation
17 | Impvt/Upgradation of Operational/Non-Operational facilities of Lengpui Airport(SH:Southern Side Baggage conveyor belt) | % | 192.5 | 22.07.2024 | 18.12.2024 | 100% |  | 0% |  | 100% |  | Completed and final checking being done for handover to Aviation
18 | I/E to Fast Track Court at Kolasib | % | 136.73 | 02.06.2024 |  | 20% | - | 0% | - | 20% |  | Technical Sanction accorded, requirement submitted
19 | SITC of Signages for Lengpui Airport Terminal Building at Ground Floor | % | 13.26 | 31.10.2025 | 31.01.26 | 99% | - | 79% | 12.86 | 99% | 12.86 | Completed and ready for handover after room allotment done
20 | SITC of Signages for Lengpui Airport Terminal Building at First Floor | % | 15.04 | 31.10.2025 | 31.01.26 | 99% | - |  | 14.59 | 99% | 14.59 | Completed and ready for handover after room allotment done
Sl. No | Name of Works / Scheme | Unit | Approved Cost Amount (in Lakhs.) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month. |  | Achievement of works during the Month |  | Overall cummulative achievement |  | Remarks
[6 empty] | Phy (%) | Fin(Rs) | Phy (%) | Fin(Rs) | Phy (%) | Fin(Rs)
1 | 2 |  | 3 | 6 |  | 10 | 11 | 12 | 13 | 14 | 15 | 18
21 | SITC of Arrival Carousal No.1 at Ground Floor Lengpui Airport Terminal Building | % | 184.74 | 27.01.2026 | 27.07.26 | 50% | - | 20% | - | 70% |  | Production stage under progress and to be completed by July 2026
22 | SITC of Arrival Carousal No.2 at Ground Floor Lengpui Airport Terminal Building | % | 184.74 | 27.01.2026 | 27.07.26 | 50% | - |  | - | 50% |  | Production stage under progress and to be completed by July 2026
23 | SITC of Electrical Installation for Arrival Carousal (No.1&No.2) at Ground Floor Lengpui Airport Terminal Building | % | 6.36 | 27.01.2026 | 27.07.26 | 10% | - | 0% | - | 10% |  | To be completed by July 2026
24 | SITC of Multi V-VRF Air Conditioning System (185.6TR) for Arrival Hall (Northern Side) at Lengpui Airport Terminal Building Ground Floor. | % | 247.29 | 27.01.2026 | 27.07.26 | 20% | - | 10% | - | 20% |  | Production stage under progress and to be completed by July 2026
25 | SITC of Multi V-VRF Air Conditioning System (176TR) for Arrival Hall (Southern Side) at Lengpui Airport Terminal Building Ground Floor. | % | 237.84 | 27.01.2026 | 27.07.26 | 20% | - |  | - | 20% |  | Production stage under progress and to be completed by July 2026
26 | SITC of Electrical Installation for Multi V-VRF Air Conditioning System (361.6 TR) for Arrival Hall (Northern & Southern Side) at Lengpui Airport Terminal Building Ground Floor. | % | 58.92 | 27.01.2026 | 27.07.26 | 10% | - | 0% | - | 10% |  | To be completed by July 2026
27 | SITC of Runway centre line lights (Northern Side) at Lengpui Airport, Mizoram | % | 167.63 | 23.03.2026 | 21.04.2026 | 50% | - | 20% | 167.6% | 70% | 167.63 | Ongoing work and to be completed by April 2026 bur EOT being applied for approval
Sl. No | Name of Works / Scheme | Unit | Approved Cost Amount (in Lakhs.) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month. |  | Achievement of works during the Month |  | Overall cummulative achievement |  | Remarks
[6 empty] | Phy (%) | Fin(Rs) | Phy (%) | Fin(Rs) | Phy (%) | Fin(Rs)
1 | 2 |  | 3 | 6 |  | 10 | 11 | 12 | 13 | 14 | 15 | 18
28 | SITC of Runway centre line lights (Southern Side), shifting of Taxiway Edge lights & raising of runway edge lights at Lengpui Airport, Mizoram | % | 148.91 | 23.03.2026 | 21.04.2026 | 30% | - | 20% | - | 50% |  | Ongoing work and to be completed by April 2026
29 | I/E to SDO (Civil) Type-IV Qtrs. at Kawnpui under SASCI 2024-2025 Part V | % | 5.8756 | 27.03.2026 | 10.05.2026 | 20% | - | 50% | - | 70% |  | To be completed by April 2026
30 | Repair and Maintenance of AC at Session Hall (Phase-I : Northern Side) | % | 16.06 | 14.04.2025 | 12.07.25 | 100% | 8.78 | 0% | 2.46 | 100% | 11.24 | Completed
31 | New Electrification of MLA Staff Quarters 4 (four) Units (Qtr No. T-141/A, T-141/B, T-141/C and T-141/D) at Tuikhuahtlang, Aizawl. | % | 10.86 | 02.04.2025 | 30.05.27 | 100% | 10.4 | 0% | 0.35 | 100% | 10.75 | Completed
32 | Providing, Fixing and Installation of ESE type Lightning Arrester and Grounding System for Tall Trees at Lok Bhawan , Aizawl | % | 15.71 | 08.12.2025 | 31.01.26 | 100% | 15.71 |  |  | 100% | 15.71 | Completed
33 | I/E to Staff Quarters (Block-C) at DIET Complex, Chaltlang, Aizawl. | % | 45.98 | - | - | 100% | 45.98 |  | - | 100% | 45.98 | Completed
Sr. Executive Engineer, PWD.,
Electrical Division, Aizawl.

## CHAMPHAI DIV
MONTHLY PROSGESS REPORT OF WORKS FOR THE MONTH OF APRIL, 2026
Name of Division : PWD., Champhai
SL.No. | Name of Scheme | Unit | Approved Cost (in lakhs) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of Works during the month |  | Overall Cumulative Achievement |  | Remarks | Mode of Tender
| Name of Work/Project |  |  |  |  | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
I | ANNUAL PLAN (5054)(20224-2025)
1 | Upgradation of Approach road to Tuipui Village from NH-6 (new Eden) Length - 1.625 Km | Km | 128.28 | 6.12.2024 | 6.12.2025 | 90% | 74.32 | 10% | _ | 100% | 74.32 | Work physically completed | Open Tender
2 | Construction of Bailey Bridge (60 ft span) over R. Tuimuk on approach road to Tuipui Village from NH-6 (New Eden) | Ft. | 53.06 | 22.8.2024 |  | 85% | 53.06 | _ | _ | 85% | 53.06 | Work in Progress | Deptt. |  |  | 0.053333
II | SASCI (2025-2026)
1 | Upgradation of Khankawn to Champhai (Phase - I) | Km | 600 | 6.6.2025 | 6.6.2026 | 20% |  | 5% | 11.33 | 25% | 11.33 | Work in Progress | Restricted Tender |  |  | TT=0.6
2 | Construction of Champhai Ring Road Phase-I (Khankawn - Falkawn - Hmunhmeltha - Vengthar - Zote via Keilungliah) | Km | 2000 | 7.7.2025 | 7.7.2026 | 30% |  | 10% | _ | 40% | _ | Work in Progress | Restricted Tender | 4.1 | TOTAL LENGTH=14 |  | 0.25
3 | Upgradation of Khankawn to Champhai Road Under Part-V (Stimulating of Industrial Growth) (Phase - II) | Km | 600 | _ | 21.7.2026 | _ | _ | 5% | _ | 5% | _ | Work in Progress | Restricted Tender |  |  |  | 25
4 | Upgradation of Zotlang to Tlangsam Road in Champhai District | Km | 300 | 9.2.2026 | 9.2.2027 | 60% |  | 10% |  | 70% |  | Work in Progress | Restricted Tender
5 | Construction of last mile connectivity road Selam to Kawlbem, Lungphunlian to Khuangphah | Km | 1446.71 |  |  | 5% |  | 5% | _ | 10% | _ | Work in Progress | Restricted Tender
III | 3054 NON-PLAN R&B
1 | Upgradation of Zotlang to Mualnuam Road | Km | 70 | 4.9.2025 | 31.3.2026 | 100% | 69.7 | _ |  | 100% | 69.7 | Work Completed | Departmental
2 | Construction of Approach road to Khuangleng Ginger processing Center at Khuangleng | Km | 30 | 8.12.2025 | 8.01.2026 | 100% | 30 | _ |  | 100% | 30 | Work Completed | Spot Quotation
IV | ANNUAL PLAN (5054) (2025-2026)
1 | Resurfacing of Zawlsei to Khuangthing Road Phase-I ( Ch. 0.000 to 3.500 Kmp) | Km | 75.25 | 30.12.2025 | 30.3.2026 | 100% | 75.25 | _ | _ | 100% | 75.25 | Work Completed | Open Tender
2 | Resurfacing of Kelkang Road from Champhai Side. | Km | 50.8 | 30.12.2025 | 30.3.2026 | 100% | 50.8 | _ | _ | 100% | 50.8 | Work Completed | Open Tender
3 | Patch repair & Resurfacing of Khuangleng to Leisenzo Road | Km | 43.47 | 30.12.2025 | 30.3.2026 | 100% | 43.47 | _ | _ | 100% | 43.47 | Work Completed | Open Tender
4 | Resurfacing of Melbuk Approach road ( Old Zokhawthar road | Km | 24.88 | 30.12.2025 | 30.3.2026 | 100% | 24.88 | _ | _ | 100% | 24.88 | Work Completed | Open Tender
V | 5054 (UNTIED FUND)
1 | Improvement & Strengthening of Champhai Town Road (SH: 1. Improvement & Strengthening of District Hospital to DC Office at Keifangtlang, Champhai) | Km | 62.55 | 23.3.2026 | 23.6.2026 | _ | _ | 50% | _ | 50% | _ | Work in Progress | Open Tender
2 | Improvement & Strengthening of Champhai Town Road (SH: 2. Improvement & Strengthening of Bethel kawn to DFO Office (Eastern), Champhai) | Km | 14.41 | 23.3.2027 | 23.6.2026 | _ | _ | 50% | _ | 50% | _ | Work in Progress | Open Tender
3 | Improvement & Strengthening of Champhai Town Road (SH: 3. Reconstruction of Khuangleng - Vanzau - Bungzung Road (Severely Damaged Portion) | Km | 48.04 | 18.3.2026 | 18.8.2026 | _ | _ | 10% | _ | 10% | _ | Work in Progress | Open Tender
4 | Improvement & Strengthening of Champhai Town Road (SH: 4. Awmpui Bazar to Vety Road via LM MS(Awmpui Bazar Vety Road) ph - III) | Km | 18.29 | 23.3.2026 | 23.6.2026 | _ | _ | 5% | _ | 5% | _ | Work in Progress | Open Tender
5 | Construction of HP Culvert, Breast wall, extension of apron and restoration of damaged pavement at Sazep village on Leithum to Vangchhe road | Km | 26.85 |  |  | _ | _ | 10% | _ | 10% | _ | Work in Progress | Open Tender
6 | Repair of damaged pavement surface of Hnahlan to Tualcheng road 0.000 -13.780 Km | Km | 48.05 | 18.3.2026 | 18.8.2026 | _ | _ | 100% | _ | 100% | _ | Work Completed | Open Tender
Sr. Executive Engineer, PWD.,
Champhai Division:Champhai

## HMUIFANG DIV
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL, 2026
Name of Division: Hmuifang Division, Aibawk
Rs. in Lakh
Sl. no | Name of Scheme | Unit | Approved Cost (Rs.in lakh) | Date of Commencement | Target Date of Completion | Commulative Progress at the end of last month |  | Achievement of Works during the month |  | Overall Commulative Achievement |  | Remarks | Mode of Tender
| Name of Work/Project |  |  |  |  | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
CRF
1 | Widening to Single Lane with Geometric Improvement & Up-Gradation of Chhiahtlang to Lamchhip road in Mizoram |  | 6668.18 | 23.06.2017 | 23.06.2019 | 100% | 6282.93 |  |  | 100% | 6282.93 | Physically Completed | Restricted Tender
2 | Balance work of Construction of Muallungthu to Lungphun Road (Length-25.00 Km) |  | 3215 | 10.03.2026 | 10.09.2027 |  |  | 2% |  | 2% |  | Work in progress | Restricted Tender
i) Formation Cutting
ii) Protection Works
iii) CD Works
iv) Pavement Works
v) Side Drain
vi) Km Stone & Road Sign
SASCI-II
1 | Construction of Agriculture Link Road to R.Mat from Chawilung, Lungsei, Samlukhai, Sialsuk |  | 173.57 | 14.12.2023 | 14.12.2024 | 100% | 173.57 |  |  | 100% | 173.57 | Physically & Financially Completed | Restricted Tender
2 | Restoration of damage due to cyclone remal under Aizawl Road North, Aizawl Road South & Hmuifang Division |  | 1170 | 17.04.2025 | 17.11.2025 | 100% |  |  |  | 100% |  | Physically completed Payment will be made by Aizawl Road South Division | Restricted Tender
3 | Restoration of damage due to cyclone remal under Hmuifang Division, Part-II |  | 1175 | 17.04.2025 | 17.11.2025 | 100% | 980 |  |  | 100% | 980 | Physically completed | Restricted Tender
5054
1 | Widening and Repair of Vantawng Approach Road | Km | 104.49 | 10.10.2024 | 10.03.2025 | 100% | 104.49 |  |  | 100% | 104.49 | Physically & Financially Completed | Departmental
2 | 5054-C.O on Roads & Bridges under Hmuifang Division for the year 2025-2026 a) Patch repair of Aibawk - Darlung Road 14.00-30.200 Kmp |  | 84 | 16.12.2025 | 10.03.2026 | 100% | 84 |  |  | 100% | 84 | Physically & Financially Completed | Open tender
| b) Extension of PCC pavement of Vantawng Khawhthla view point (Balance Portion) at Thenzawl |  |  |  |  | 100% |  |  |  | 100%
Sr. Executive Engineer, PWD.,
Hmuifang Division, Aibawk

## Khawzawl
MONTHLY PROGRESS REPORT OF MAJOR WORKS 2025-2026 UNDER PWD KHAWZAWL DIVISION FOR THE MONTH OF MARCH, 2026
Name of Division : Khawzawl Division.
Sl. No. | Name of Work | Category of road | Length (Km) | Amount of Technical Sanction (Rs. Lakh) | Date of Technical Sanction | Financial Progress (amount Rs. Lakh) |  |  | Physical Progress (in percentage) |  |  | Remarks
[6 empty] | Expenditure upto end of the month | Expenditure during the month | Total expenditure upto end of the month | Progress upto end of previous month | Progress during the month | Progress upto end of the month
1 | Resurfacing of Vengthar Bazar to Presbyterian English School at Khawzawl. | STR | 0.75 | 32.27 | 12.09.2025 | 30.65 |  | 30.65 | 100 |  | 100 | Work Completed
2 | Resurfacing of Approach Road to PHE Complex, EE Quarters, SDO Quarters and SDO Office. | STR | 0.38 | 21.52 | 12.09.2025 | 20.44 |  | 20.44 | 100 |  | 100 | Work Completed
3 | Resurfacing of Kawnzar to Taidawnkawn at Khawzawl. | STR | 1.13 | 49.72 | 12.09.2025 | 47.23 |  | 47.23 | 100 |  | 100 | Work Completed
4 | Resurfacing of Approach Road to Khawhai PHC. | STR | 0.744 | 47.17 | 12.09.2025 | 44.81 |  | 44.81 | 100 |  | 100 | Work Completed
5 | Pavement of Approach Road to IR (NH 102B to IR Camp) at NE.Khawdungsei. | STR | 0.487 | 17.46 | 15.09.2025 |  | 16.58 | 16.58 | 100 |  | 100 | Work Completed
6 | Resufacing of Khawzawl to Ngaizawl Road | VT | 3 | 47.17 | 02.03.2026 |  | 47.17 | 47.17 |  | 100 | 100 | Work Completed
7 | Construction of Pavement and side Drain on the Approach to Tomoto Collection Centre at Tualte. | VR | 0.17 | 8.97 | 02.03.2026 |  | 8.97 | 8.97 |  | 100 | 100 | Work Completed
8 | Resurfacing & Repair of Ngopa-Mimbung Road. | ODR | 1.5 | 44.81 | 02.03.2026 |  | 44.8 | 44.8 |  | 100 | 100 | Work Completed
NESIDS
MONTHLY PROGRESS FOR THE MONTH OF APRIL 2026 (A.FINANCIAL REPORT)
Sl. No | Name of the project, Location & State | Name of Implementing Agency/Dept | Approved Cost by MDoNER/NEC |  | Fund released by MDoNER/NEC |  | Expenditure made |  | Unspent balance out of fund released (Rs in lakhs) | Status of submission of U/Cs | Remarks
|  |  | Original Cost (Rs in lakhs) | Revised Cost (Rs in lakhs) | During 2025-2026 | Since inception (Cumulative) | During the month vis-a-vis-target | Since inception (Cumulative)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Construction of Tualpui to Champhai Road (Single lane), Mizoram (Length L=21.058Km) | Mizoram, PWD |  | 5701 |  |  |  |  | 5701 |  | Payment is for Advance on Mobilization. Therefore, there is no actual expenditure yet
MONTHLY PROGRESS FOR THE MONTH OF APRIL 2026 (B.PHYSICAL REPORT)
Sl. No | Name of the project, Location & State | Name of Implementing Agency/Dept | Approved Cost by MDoNER/NEC |  | Date of actual commencement of work/Scheme | Target date of completion of work/scheme | Scope of work/Scheme in physical terms (eg.Kms, etc) |  |  | Physical achievement |  | Remarks
|  |  | Cost (Rs in lakhs) | Date | [5 empty] | percentage (during the month) | Percentage (Overall)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |  |  | 9 | 10 | 11
1 | Construction of Tualpui to Champhai Road (Single lane), Mizoram (Length L=21.058Km) | Mizoram, PWD | 5701 | 21.06.2026 | 16.03.2026 | 15.09.2027 | OVERALL PROGRESS |  |  |  |  | Work has just commenced on 16.03.2026. Therefore, there is no significant progress yet
[7 empty] | 1 | Site Clearance | 21.058 Km | 1 | 4.75%
[7 empty] | 2 | FC | 21.058 Km | 1 | 4.75%
[7 empty] | 3 | Pavement |  | 0 | 0
[8 empty] | a) CTSB | 20.918 Km | 0 | 0
[8 empty] | b)WBM-I | 20.918 Km | 0 | 0
[8 empty] | c) WBM-II | 20.918 Km | 0 | 0
[8 empty] | d) BT | 20.918 Km | 0 | 0
[7 empty] | 4 | LSD | 3701 Rm | 0 | 0
[7 empty] | 5 | Protection Work | 817 Rm | 0 | 0
[7 empty] | 6 | CD Works | 98 Nos | 0 | 0
[7 empty] | 7 | TS & RM | 21 Km | 0 | 0
[7 empty] | 8 | Parapet | 360 Nos | 0 | 0
[7 empty] | 9 | BUG Bridge | 90 Rm | 0 | 0
Sr.Executive Engineer, PWD,
Khawzawl Division.

## KOLASIB DIV
MONTHLY PROGRESS REPORT
FOR THE MONTH OF APRIL, 2026
UNDER KOLASIB DIVISION
Sl. No. | Name of Schemes | Quantity | Unit | Approved Cost (Rs in Lakh) | Date of Commencement | Target Date of Comple-tion | Cumulative Progress at the end of last month |  | Achievement of works during the month |  | Overall Cumulative achievement |  | Remarks | Mode of Tender
| Name of Works / Project | [5 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 |  | 3 | 4 | 6 | 7 | 8 | 9 | 10 | ♂11 | 12=(8+10) | 13=(9+11) | 14 | 15
1 | NABARD
1 | Construction of Meidum to Hortoki Phase-II
i | Earthwork and Permanent Work from 9.100 Km to 13.325 Km Package-I | 3.305 | Km | 13366 | 24.12.2021 | 29.04.2024 | 100% | 1035.621 |  |  | 100% | 1035.621 | Completed | Restricted Tender
ii | Earthwork and Permanent Work from Km 13.325 to Km 17.500 Package-II | 3.275 | Km |  | 25.12.2021 | 23.07.2025 | 97% | 933.465 | 3% |  | 100% | 933.465 |  | Restricted Tender
iii | Earthwork and Permanent Works from Km 17.500 to Km 21.725 Package-III | 3.315 | Km |  | 18.12.2021 | 16.11.2025 | 98% | 1223.502 | 2% |  | 100% | 1223.502 | Mobilisation & Machinery Advance Recovery Balance= Rs.7 lakh | Restricted Tender
iv | Earthwork and Permanent Works from Km 21.725 to Km 26.00 Package-IV | 3.355 | Km |  | 08.12.2021 | 19.05.2025 | 99% | 726.528 |  |  | 99% | 726.528 | Mobilisation & Machinery Advance Recovery Balance=Rs.79.589 lakh | Restricted Tender
v | Construction of Rigid Pavement : Package -I (Km 9.100-Km 15.730) | 5.58 | Km |  | 03.08.2022 | 10.12.2025 | 38% | 722.158 | 9% |  | 47% | 722.158 | Mobilisation & Machinery Advance Recovery Balance= Rs.173.459 lakh | Restricted Tender
vi | Construction of Rigid Pavement : Package -II (Km 15.730-Km 22.36) | 5.58 | Km |  | 03.08.2022 | 05.09.2025 | 9.17% | 188.463 |  |  | 9.17% | 188.463 | Mobilisation & Equipment Advance Recovery Balance= Rs.297.974 lakh | Restricted Tender
vii | Design & Construction of T-Beam Bridge package-I at Chhimluangte (CH : 0.450 Kmp) | 24 | 3: m; 6: 18.12.2021; 8: 100%; 9: 482.621 | 100% | 482.621 | Completed | Departmental
viii | Design & Construction of T-Beam Bridge package-I at Dumkhel (CH : 5.500 Kmp) | 20 | m |  | 30.12.2024 | 30.06.2026 | 28% | 115.75 | 1% |  | 29% | 115.75 | Secured Advance Rs.62.24 lakh | Restricted Tender
ix | Design & Construction of T-Beam Bridge package-II at Bulung (CH : 10.200 Kmp) | 28 | 3: m; 6: 24.12.2021; 7: 02.10.2025; 8: 17.5% | 17.5% | 0 | Secured Advance Rs.82.080 lakh | Restricted Tender
x | Design & Construction of T-Beam Bridge package-II at Damdiai (CH : 23.50 Kmp) | 20 | 3: m; 8: 21.5% | 21.5% | 0 |  | Restricted Tender
2 | Construction of BUSG Composite Bridge (Span=22.00m, Revised span=34.00m) over R. Chepte on Bilkhawthlir to Saiphai road under NABARD | 34 | m | 508.45 | 24.06.2019 | 30.11.2025 | 25% | 132.82 |  |  | 25% | 132.82 | Fund : NABARD=Rs. 291.35 lakh SASCE=Rs.217.10 lakh Expenditure : NABARD=Rs.46.67 SASCE=Rs.86.15. Equipt. Adv. Recovery balance=Rs.8.037 | Restricted Tender
3 | Construction of BUSG Composite Bridge (Span=22.00m) over R.Sesih on Bilkhawthlir to Saiphai road under NABARD | 22 | m | 291.35 | 24.06.2019 | 30.09.2025 | 90% | 248.894 | 0% | 42.456 | 90% | 291.35 |  | Restricted Tender
4 | Construction of Link Road from NH-306 (Vairengte) to Sabual Mual Arable Crop Land : Length = 3.720 Kms | 3.72 | Km | 417.58 | 13.08.2022 | 28.02.2025 | 100% | 417.58 |  |  | 100% | 417.58 | Completed | Restricted Tender
5 | Construction of approach Road to Railway Station in Mizoram (SH: Construction of Approach Road to Hortoki Railway Station | 2.51 | km | 625.97 | 18.07.2025 | 18.07.2026 | 66% | 312.97 | 6.5% |  | 72.5% | 312.97 |  | Restricted Tender
2 | SASCI | [15 empty] | 0
1 | Restoration of Damages due to Cyclone Remal under SASCI, 2024-2025 under Kolasib Division
i | Re-construction of Hume Pipe Culvert on Hmar Veng to Saidan Road, Kolasib | 7.5 | m | 17.147 | 16.06.2025 | 16.01.2026 | 100% | 17.147 |  |  | 100% | 17.147 | Completed | Restricted Tender
ii | Construction of Retaining Wall on Rengtekawn to NH 154(Zero Point) Road at 1.050 Kmp | 52 | m | 29.666 | 16.06.2025 | 16.01.2026 | 100% | 29.666 |  |  | 100% | 29.666 | Completed
iii | Construction of Breast Wall on Rengtekawn to NH 154(Zero Point) Road at 1.600 Kmp | 30 | m | 10.756 | 16.06.2025 | 16.01.2026 | 100% | 10.756 |  |  | 100% | 10.756 | Completed
iv | Re-construction of SPT Bridge over R.Chepte at 10.000 Kmp on Bilkhawthlir to Saiphai Road (SH: Approach Roads ) | 110 | m | 1.973 | 16.06.2025 | 16.01.2026 | 100% | 1.973 |  |  | 100% | 1.973 | Completed
v | Construction of Hume Pipe Culvert near Lalrampana House on Rengtekawn NH 54-132 KV | 1 | nos | 5.456 | 16.06.2025 | 16.01.2026 | 100% | 5.456 |  |  | 100% | 5.456 | Completed
vi | Construction of SPT Bridge over Aitlanglui at Vairengte | 12 | m | 15 | 16.06.2025 | 16.01.2026 | 100% | 15 |  |  | 100% | 15 | Completed
vii | Construction of Retaining Wall at Serkhan to Bagha Road at 29.100 Kmp | 1 | nos | 4.358 | 16.06.2025 | 16.01.2026 | 100% | 4.358 |  |  | 100% | 4.358 | Completed
viii | Construction of Retaining Wall near Tumpui field on Main Feeder to Karkawn via Helipad | 1 | nos | 24.231 | 16.06.2025 | 16.01.2026 | 100% |  |  | 24.22 | 100% | 24.22 | Completed
ix | Construction of Retaining Wall at Serkhan to Bagha Road at 15.100 Kmp | 1 | nos | 15.409 | 16.06.2025 | 16.01.2026 | 100% | 15.409 |  |  | 100% | 15.409 | Completed
x | Construction of Retaining Wall at Serkhan to Bagha Road at 32.400 Kmp | 1 | nos | 11.154 | 16.06.2025 | 16.01.2026 | 100% | 11.154 |  |  | 100% | 11.154 | Completed
xi | Construction of Retaining Wall on Rengtekawn-Builum Road at 8.000 KMP | 1 | nos | 6.118 | 16.06.2025 | 16.01.2026 | 100% | 6.118 |  |  | 100% | 6.118 | Completed
xii | Construction of Retaining Wall on Rengtekawn-Builum Road at 5.600 KMP | 1 | nos | 24.108 | 16.06.2025 | 16.01.2026 | 100% | 24.108 |  |  | 100% | 24.108 | Completed
xiii | Restoration of Damaged Pavement on Buhchang to Phaisen road at 7.350 Kmp | 27 | m | 12.677 | 16.06.2025 | 16.01.2026 | 100% | 12.677 |  |  | 100% | 12.677 | Completed
xiv | Re-Construction of Hume Pipe Culvert at 8.160 Kmp on Bilkhawthlir to Saiphai Road | 1 | nos | 7.21 | 16.06.2025 | 16.01.2026 | 100% | 7.21 |  |  | 100% | 7.21 | Completed
xv | Construction of Retaining Wall on Rengtekawn to Builum Road at 5.100 Kmp | 1 | nos | 11.736 | 16.06.2025 | 16.01.2026 | 100% | 11.736 |  |  | 100% | 11.736 | Completed
xvi | Re-Construction of Hume Pipe Culvert at 9.390 on Bilkhawthlir to Saiphai Road | 2 | nos | 11.965 | 16.06.2025 | 16.01.2026 | 100% | 11.965 |  |  | 100% | 11.965 | Completed
xvii | Restoration of Damaged Pavement on Buhchang to Phaisen road at 8.850 Kmp | 11 | m | 5.176 | 16.06.2025 | 16.01.2026 | 100% | 5.176 |  |  | 100% | 5.176 | Completed
xviii | Construction of Retaining Wall at Kawnpui to Hortoki Road at 15.100 Kmp | 1 | nos | 5.178 | 16.06.2025 | 16.01.2026 | 100% | 5.178 |  |  | 100% | 5.178 | Completed
3 | ANNUAL MAINTENANCE OPERATION PLAN 3054 (Departmental
i | Patch Repair from Main Feeder to PHE Office via Spring Field School Hmarveng | 490 | m | 8.5 | 18.08.2025 | 18.02.2026 | 100% | 8.5 |  |  | 100% | 8.5 | Completed | Departmental
ii | Resurfacing of Road from Presbyterian Church to MHIP Building (Section-II) at College Veng, Kolasib | 162 | m | 7.86 | 18.08.2025 | 18.02.2026 | 100% | 7.86 |  |  | 100% | 7.86 | Completed
iii | Resurfacing of approach Road and Courtyard of Circuit House, Kolasib | 64 | m | 6.8 | 18.08.2025 | 18.02.2026 | 100% | 6.8 |  |  | 100% | 6.8 | Completed
iv | Resurfacing of Appraoch Road to DEO Office, Project Veng Kolasib | 300 | m | 4.1 | 18.08.2025 | 18.02.2026 | 100% | 4.1 |  |  | 100% | 4.1 | Completed
v | Resurfacing of road from PWD Office to Salvation Hall at Main feeder Road, Hmarveng | 120 | m | 2.7 | 18.08.2025 | 18.02.2026 | 100% | 2.7 |  |  | 100% | 2.7 | Completed
vi | Construction of Retaining Wall near Ramchullova house Tumpui, Kolasib | 1 | nos | 0.9 | 18.08.2025 | 18.02.2026 | 100% | 0.9 |  |  | 100% | 0.9 | Completed
vii | Resurfacing of Approach Road to Integrated School, Vengthar, Kolasib | 230 | m | 3.8 | 18.08.2025 | 18.02.2026 | 100% | 3.8 |  |  | 100% | 3.8 | Completed
viii | Construction of Retaining Wall at Serkhan to Bagha Road Ch: 24.650 Kmp near N.Chaltlang | 1 | nos | 3.7 | 18.08.2025 | 18.02.2026 | 100% | 3.7 |  |  | 100% | 3.7 | Completed
ix | Resurfacing of Serkhan to Bagha Road from Ch : 3.300 Kmp to 3.650 Kmp (Nisapui Diversion) | 350 | m | 11.1 | 18.08.2025 | 18.02.2026 | 100% |  |  |  | 100% | 11.1 | Completed
x | Resurfacing of Approach Road & Couryard of PHC at Sentlang | 155 | m | 3.9 | 18.08.2025 | 18.02.2026 | 100% |  |  |  | 100% | 3.9 | Completed
xi | Resurfacing of road from NH-306 to Vety Office, Kawnpui | 90 | m | 2.9 | 18.08.2025 | 18.02.2026 | 100% | 2.9 |  |  | 100% | 2.9 | Completed
xii | Resurfacing of SDO (Civil) Office to Hockey Academy, Kawnpui | 115 | m | 2.9 | 18.08.2025 | 18.02.2026 | 100% | 2.6 |  |  | 100% | 2.6 | Completed |  | 2.61
xiii | Patch repair and Resurfacing of Centenary Road, Bilkhawthlir | 480 | m | 17 | 18.08.2025 | 18.02.2026 | 100% | 17 |  |  | 100% | 17 | Completed
xiv | Patch repair and Resurfacing of Approach road to Baptist Church via Forest Department Complex, Bilkhawthlir | 176 | m | 3.4 | 18.08.2025 | 18.02.2026 | 100% | 3.4 |  |  | 100% | 3.4 | Completed
xv | Resurfacing of Bilkhawthlir Community Hall to Market, Bilkhawthlir Phase-I | 180 | m | 2.9 | 18.08.2025 | 18.02.2026 | 100% | 2.9 |  |  | 100% | 2.9 | Completed
[15 empty] | 94 | 100
68
Sr.Executive Engineer, PWD
Kolasib Division.

## KAWRTHAH DIV
MONTHLY PROGRESS REPORT FOR THE MONTH OF | [9 empty] | APRIL, 2026
Name of Division |  | : KAWRTHAH
Source of Funding |  | : SASCI
Sl. No | Name of Works/Project | Unit |  | Approved Cost (in lakhs) | Date of Commencement | Target Date of Completion | Achievement upto previous month |  | Achievement for the month |  | Overall Cummulative achievement |  | Remarks | Mode of Contract
[7 empty] | Phy | Fin | Phy | Fin | Phy | Fin (actual)
1 | 2 | 3 |  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Additional works and Completion of Double Lane Bridge over River Teirei on Bairabi - Zamuang Road. |  |  | 5: 29.2.2024; 6: 15.11.2025; 9: -; 13: Works completed; 14: Continued by the existing contractor i.e Sadguru Engineers & Allied Services Pvt.Ltd. For Bridge work & piling of Bank protection & Departmentally for Bank protection (Balanced work) and approach road.
| Bridge Work (Super Structure) | Nos | 1 | 4: 546.91; 7: 100%; 8: 1260.42; 11: 100%; 12: 1260.42
| River Banks Protection | Nos | 2 | 4: 475.69; 7: 100%; 11: 100%
| Approach Road | Nos | 2 | 4: 298.46; 7: 100%; 11: 100%
| Road Signages |  |  | 4: 25.6; 7: 100%; 11: 100%
| Total of Work Component : |  |  | 4: 1346.66; 8: 1260.42; 12: 1260.42
| Provision for Contingencies : |  |  | 4: 26.76
| Provision for Quality Control : |  |  | 4: 26.6
| Grand Total : |  |  | 4: 1400.02; 8: 1260.42; 12: 1260.42
| Overall physical Progress | : |  | 4: 100%
MONTHLY PROGRESS REPORT FOR THE MONTH OF |  |  |  | 10: APRIL, 2026
Name of Division |  | : KAWRTHAH
Source of Funding |  | : NABARD
Amount in lakhs
Sl. No | Name of Work/Project | Unit |  |  | Approved Cost (in lakh) | Date of Commencement | Target Date of Completion | Achievement upto previous month |  | Achievement for the month |  | Overall commulative achievement |  | Remarks | Mode of Contract
[8 empty] | Phy | Fin (lakh) | Phy | Fin (lakh) | Phy | Fin (actual)
1 | 2 | 3 |  |  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Double Lane BUSG Bridge (Span = 81m) over R.Langkaih on Mizoram-Tripura Border at Kanhmun | Bridge Works : |  |  | 13: Work in progress; 14: Contract after call of Restricted Tender
|  | a) Site Investigation & Design | 7% | % | 154.23 | 6.4.2018 | 31.03.2026 | 100% | 1956.46 | - |  | 100% | 1956.46
|  | b) Construction of Subway | 20% | % | 4: 440.65; 7: 100%; 11: 100%
|  | c) Foundation & Sub-Structure | 41% | % | 4: 903.34; 7: 99%; 11: 99%
|  | d) Super-Structure | 30% | % | 4: 660.98; 7: 80.7%; 9: 6.3%; 11: 87%
|  | e) Miscellaneous | 2% | % | 4: 44.06; 9: -
|  | f) Contingency |  |  | 4: 28.65; 7: -; 9: -; 11: -
|  | Grand Total : |  |  | 4: 2231.91; 8: 1956.46; 12: 1956.46
|  | Overall physical Progress :- |  |  | 4: 95.69%
MONTHLY PROGRESS REPORT FOR THE MONTH OF |  |  |  |  | 9: APRIL, 2026
Name of Division |  | : KAWRTHAH
Source of Funding |  | : 5054 R&B
Sl. No | Name of Works/Project | Unit |  | Approved Cost (in lakhs) | Date of Commencement | Target Date of Completion | Achievement upto previous month |  | Achievement for the month |  | Overall Cummulative achievement |  | Remarks | Mode of Contract
[7 empty] | Phy | Fin | Phy | Fin (in lakhs) | Phy | Fin (in lakhs)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Re-Seal Coating of Bunghmun to W.Mualthuam Road (6.250 - 12.400 Kmp) | Nos | 1 | 30 | 18.4.2026 | 19.4.2027 | - | - | - | - | - | - | Noy yet started | Contract after call of tender
| Grand Total : |  |  | 30 | bar: 6; 9; 11
| Overall Physical Progress | : | 0%
MONTHLY PROGRESS REPORT FOR THE MONTH OF |  |  |  |  | 9: APRIL, 2026
Name of Division |  | : KAWRTHAH
Source of Funding |  | : 5054 R&B
Sl. No | Name of Works/Project | Unit |  | Approved Cost (in lakhs) | Date of Commencement | Target Date of Completion | Achievement upto previous month |  | Achievement for the month |  | Overall Cummulative achievement |  | Remarks | Mode of Contract
[7 empty] | Phy | Fin | Phy | Fin (in lakhs) | Phy | Fin (in lakhs)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Panel Conncrete of Zawlnuam to Zawlpui Road | [5 empty] | - | - | - | - | - | - | Material collection on-going | Contract after call of tender
| WBM | 45 | m3 | 3.54 | 18.4.2026 | 19.4.2027 | - | - | - | - | - | -
| PQC | 450 | m3 | 73.76 | bar: 6 to 11
| 3 % Contingencies |  |  | 2.32 | bar: 6 to 11
| 1% Labour cess |  |  | 0.77 | bar: 6 to 11
| Grand Total : |  |  | 80
| Overall Physical Progress | : | 0%
MONTHLY PROGRESS REPORT FOR THE MONTH OF |  |  |  |  | 9: APRIL, 2026
Name of Division |  | : KAWRTHAH
Source of Funding |  | : 5054 R&B
Sl. No | Name of Works/Project | Unit |  | Approved Cost (in lakhs) | Date of Commencement | Target Date of Completion | Achievement upto previous month |  | Achievement for the month |  | Overall Cummulative achievement |  | Remarks | Mode of Contract
[7 empty] | Phy | Fin | Phy | Fin (in lakhs) | Phy | Fin (in lakhs)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Re-Seal Coating of Bunghmun to W.Mualthuam Road (0.00 - 6.250 Kmp) | Nos | 1 | 30.03 | 14.1.2026 | 14.7.2026 | - | - | - | - | - | - | Material collection on-going | Contract after call of tender
| Grand Total : |  |  | 30.03 | bar: 6; 9; 11
| Overall Physical Progress | : | 0%
Sr.Executive Engineer, PWD.,
Kawrthah Division, Kawrthah.

## LBPD
MONTHLY PROGRESS REPORT FOR THE MONTH OF April, 2026 ( BUILDING WORKS )
Name of Division: Lunglei Building Project Division, Lunglei
Rs. in Lakh
Sl.no | Name of Scheme | Unit | Approved Cost (Rs.in lakh) | Date of Commencement | Target Date of Completion : | Commulative Progress at the end of last month |  | Achievement of Works during the month |  | Overall Commulative Achievement |  | Remarks | Mode of Tender
| Name of Work/Project |  |  |  |  | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
SASCI
1 | Vertical Extention of Market Building at Kamalanagar |  | 124.52 | 23.03.24 | 31.12.2025 |  | 50.51 |  | 0 |  | 50.51 |  | Restricted Tender
1 | Vertical Extension of existing Bazaar Building at Kamalanagar-I with Tin Roofing |  |  |  |  | 95% |  | 15% |  | 100% |  | Work in Progress
2 | Construction of additional Bazaar Building by demolishing the existing dilapidated building that was constructed under BADP |  |  |  |  | 95% |  | 10% |  | 100% |  | Work in Progress
3 | 2. Construction of Rest House at PWD Complex Bunghmun. |  |  |  |  | 93% |  | 8% |  | 100% |  | Work in Progress
2 | Construction of Community Hall cum Health Clinic Center at Kawlhawk, Bungtlang West, South Lungdai and Serte |  | 10 | 23.03.24 | 23.07.25 |  | 0 |  | 0 |  | 0 |  | Restricted Tender
1 | Construction of Badminton Hall at Chhipphir |  |  |  |  | 100% |  | - |  | 100% |  | Completed
2 | Completion of Badminton Hall at Chhipphir |  |  |  |  | 100% |  | - |  | 100% |  | Completed
3 | GENERAL POOLS
1 | Construction of Government Quarters (General Pool) at Venglai, Lunglei (Ramnghaka's Quarters Site) SH : Type-IV Quarters (2 units, 1 Block) |  | 214.99 | 13.05.2025 | 13.05.2026 | 52% | 43.83 | 3% | 75.98 | 55% | 119.81 | Work in Progress | Restricted Tender
2 | Construction of Government Quarters (General Pool) at Venglai, Lunglei (Soil Quarters Site) SH : Type-III Quarters (1 unit) Type-IV Quarters (2 units) |  | 221.37 | 14.05.2025 | 14.05.2026 | 60% | 95 | 5% | 0 | 65% | 95 | Work in Progress | Restricted Tender
3 | Construction of Government Quarters (General Pool) at Venglai, Lunglei (Zautea's Quarters Site) SH : Type-IV Quarters (1 unit, 1 Block) |  | 79.29 | 19.05.2025 | 19.05.2026 | 48% | 0 | 4% | 0 | 52% | 0 | Work in Progress | Restricted Tender
4 | Construction of GovernmentQuarters (General Pool) at Venglai, Lunglei (Numami's Quarters Site) SH : Type-IV Quarters (1 unit, 1 Block) |  | 79.29 | 13.05.2025 | 13.05.2026 | 100% | 90.48 | - | 0 | 100% | 90.48 | Completed | Restricted Tender
5 | Construction of Government Quarters (General Pool) at Venglai, Lunglei (Quarters No. 5 Site) SH : Type-III Quarters (2 units, 1 Block) |  | 133.42 | 13.05.2025 | 13.05.2026 | 55% | 0 | 2% | 0 | 57% | 0 | Work in Progress | Restricted Tender
6 | Construction of Government Quarters (General Pool) at Venglai, Lunglei (Zorini's Quarters Site) SH : Type-III Quarters (2 units, 1 Block) |  | 137.99 | 13.05.2025 | 13.05.2026 | 78% | 54.08 | 2% | 50.18 | 80% | 104.26 | Work in Progress | Restricted Tender
7 | Construction of Government Quarters (General Pool) at Venglai, Lunglei (Thapa's Quarters Site) SH : Type-III Quarters (2 units, 1 Block) |  | 137.99 | 13.05.2025 | 13.05.2026 | 83% | 87.41 | 2% | 0 | 85% | 87.41 | Work in Progress | Restricted Tender
8 | Construction of Government Quarters (General Pool) at Venglai, Lunglei (Pi Marcella's Quarters Site) SH: Type - III Quarters (2 Units) |  | 120.02 | 13.05.2025 | 13.05.2026 | 70% | 55 | 5% | 0 | 75% | 55 | Work in Progress | Restricted Tender
9 | Construction of Government Quarters (General Pool) at Venglai, Lunglei (Pi Marcella's Quarters Site) SH: Type - III Quarters (1 Unit) |  | 86.52 | 13.05.2025 | 13.05.2026 | 100% | 86.5 | - | 0 | 100% | 86.5 | Completed | Restricted Tender
4 | Construction of Working Women Hostel at Ramthar Veng, Lunglei |  | 1186.47 | 14.05.2025 | 14.05.2027 | 13% | 100 | 2% | 0 | 15% | 100 | Work in Progress | Restricted Tender
5 | Construction of District Prison/Jail,Lunglei |  | 523.87 | 28.04.2025 | 28.04.2026 | 28% | 63.01 | 2% | 71.42 | 30% | 134.43 | Work in Progress | Restricted Tender
6 | Construction of Revenue Staff Quarters at Hnahthial |  | 186.4 | 29.07.2025 | 29.07.2026 | 45% | 0 | 5% | 45 | 50% | 45 | Work in Progress | Restricted Tender
7 | Construction of DCSO Office & Disaster Management & Rehabilitation Office Associated Parking at Lunglei |  | 1170.65 | 21.07.2025 | 21.07.2026 | 10% | 70 | 3% | 22.05 | 13% | 92.05 | Work in Progress | Restricted Tender
8 | Reconstruction of Thingsai PWD IB |  | 192.35 | 07.07.2025 | 07.07.2026 | 4% | 0 | 1% | 0 | 5% | 0 | Work in Progress | Restricted Tender
9 | Upgradation of District Research Office at Lunglei |  | 41.27 | 11.08.2025 | 11.08.2026 | 55% | 0 | 5% | 15.96 | 60% | 15.96 | Work in Progress | Restricted Tender
10 | Upgradation of District Research Office at Hnahthial |  | 24.8 | 18.08.2025 | 18.08.2026 | 36% | 0 | 64% | 6.78 | 100% | 6.78 | Completed | Restricted Tender
11 | Creation of Critical Infrastructure for Mitigation & Prevention of Damages against Natural Disaster in MPL under SASCI Part-I (Cyclone Remal) 2024-2025
| 1. Construction of Hostel Superintendent's Quarters |  | 75.11 | 22.09.2025 | 22.09.2026 | 35% | 0 | 2% | 0 | 37% | 0 | Work in Progress | Restricted Tender
| 2. Construction of Girl's Hostel Building |  | 292.18 | 22.09.2025 | 22.09.2026 | 4% | 0 | 1% | 0 | 5% | 0 | Work in Progress | Restricted Tender
12 | GENERAL POOLS
1 | Construction of Government Quarters (General Pool) at Lawngtlai at Additional DC Quarter |  | 133.09 | 28.04.2025 | 28.04.2026 | 35% | 0 | 15% | 0 | 55% | 0 | Work in Progress | Restricted Tender
2 | Construction of Government Quarters (General Pool) at Lawngtlai Electric Veng (near RD Office) |  | 648.26 | 28.04.2025 | 28.04.2026 | 17% | 0 | 13% | 0 | 30% | 0 | Work in Progress | Restricted Tender
3 | Construction of Government Quarters (General Pool) at Lawngtlai Electric Veng (near BDO Office) |  | 220.73 | 05.05.2025 | 05.05.2026 | 20% | 0 | 15% | 0 | 35% | 0 | Work in progress. | Restricted Tender
4 | Construction of Government Quarters (General Pool) at Lawngtlai Electric Veng (near A&T Office) |  | 219.67 | 28.04.2025 | 28.04.2026 | 25% | 0 | 10% | 0 | 35% | 0 | Work in progress. | Restricted Tender
13 | SDO (C) Office & Quarter at Chawngte |  | 183.24 | 20.07.2025 | 20.07.2026 | 20% | 0 | 5% | 0 | 25% | 0 | Work in progress. | Restricted Tender
14 | Construction of Circuit House Under DC Office, Lawngtlai District |  | 765.04 | 19.07.2025 | 19.07.2026 | 20% | 0 | 5% | 0 | 25% | 0 | Work in progress. | Restricted Tender
15 | Construction of Office Building Cum Quarters at Lawngtlai (Commissioner of State Tax) |  | 296.08 | 15.07.2025 | 15.07.2026 | 25% | 0 | 5% | 0 | 30% | 0 | Work in progress. | Restricted Tender
16 | Upgradation of District Research Office at Lawngtlai |  | 23.14 | 11.08.2025 | 11.08.2026 | 100% | 0 | - | 23.14 | 100% | 23.14 | Completed | Restricted Tender
17 | Construction of Circuit Houses at Siaha |  | 522.13 | 28.04.2025 | 28.04.2026 | 36% | 102.38 | 6% | 0 | 42% | 102.38 | Work in progress. | Restricted Tender
18 | GENERAL POOLS
1 | Construction of Government Quarters (General Pool) at New Siaha at Additional DC Quarters (Inside Gate) |  | 228.26 | 28.04.2025 | 28.04.2026 | 80% | 72.8 | 5% | 0 | 85% | 72.8 | Work in progress. | Restricted Tender
2 | Construction of Government Quarters (General Pool) at New Siaha at Additional DC Quarters (Outside Gate) |  | 239.98 | 28.04.2025 | 28.04.2026 | 80% | 83.99 | 5% | 0 | 85% | 83.99 | Work in progress. | Restricted Tender
3 | Construction of Government Quarters (General Pool) at New Siaha at Additional DC Quarters (Type III) |  | 273.97 | 28.04.2025 | 28.04.2026 | 60% | 65.91 | 7% | 82.26 | 67% | 148.17 | Work in progress. | Restricted Tender
4 | Construction of Government Quarters (General Pool) at New Siaha at Meisavaih Site-I (Type III, 4 unit) |  | 274.93 | 28.04.2025 | 28.04.2026 | 60% | 74.93 | 7% | 72.73 | 67% | 147.66 | Work in progress. | Restricted Tender
5 | Construction of Government Quarters (General Pool) at New Siaha at Meisavaih Site-II (Type III, 4 unit) |  | 274.79 | 28.05.2025 | 28.05.2026 | 73% | 81.1 | 5% | 59.45 | 78% | 140.55 | Work in progress. | Restricted Tender
19 | Construction of District Prison/Jail, Siaha |  | 916.33 | 28.04.2025 | 28.04.2026 | 65% | 249.34 | 2% | 0 | 67% | 249.34 | Work in progress. | Restricted Tender
20 | SDO (C) Office & Quarters at Tipa |  | 184.71 | 07.07.2025 | 07.07.2026 | 50% | 0 | 7% | 66.87 | 57% | 66.87 | Work in progress. | Restricted Tender
21 | Upgradation of District Research Office at Siaha |  | 22.82 | 18.08.2025 | 18.08.2026 | 100% | 0 | - | 0 | 100% | 0 | Completed | Restricted Tender
22 | NABARD
CONSTRUCTION OF WAREHOUSES WITH ASSOCIATED INFRASTRUCTURE IN 12 LOCATIONS UNDER NABARD
| GROUP- III: | [11 empty] | Restricted Tender
| 1) Siaha SDC |  | 444.99 | 17.07.2023 | 31.3.2026 | 62% | 115.02 |  | 0 | 62% | 115.02 | No progress during month
| 2) Chapui |  | 217.02 | 17.07.2023 | 28.2.2026 | 100% | 81.18 |  | 96.49 | 100% | 81.18 | Works Completed
| 3) Bungtlang South |  | 180.45 | 17.07.2023 | 15.02.2026 | 100% | 155.62 |  | 34.38 | 100% | 155.62 | Works Completed | Restricted Tender
22 | GROUP- IV: | [11 empty] | Restricted Tender
| 1) Lungpher |  | 197.12 | 17.07.2023 | 17.7.2025 | 100% | 196.77 | - | 0 | 100% | 196.77 | Works Completed
| GROUP- VI: | [11 empty] | Restricted Tender
| 1) South Vanlaiphai |  | 206.2 | 17.07.2023 | 24.03.2026 | 100% | 187.14 |  | 74.65 | 100% | 187.14 | Works Completed
| 2) Vawmbuk |  | 217.1 | 17.07.2023 | 31.12.2025 | 100% | 197.86 | - | 40.18 | 100% | 197.86 | Works Completed
| GROUP-VIII: | [11 empty] | Restricted Tender
| 1) Hnahthial |  | 197.24 | 17.07.2023 | 19.07.2027 | 25% |  |  | 0 | 25% |  | Works in progress
| 2) Thingsai |  | 177.51 | 17.07.2023 | 13.12.2025 | 100% | 160.32 |  | 94.14 | 100% | 160.32 | Works Completed
| 3) Cherhlun |  | 93.26 | 17.07.2023 | 13.12.2025 | 100% | 85.61 |  | 38.34 | 100% | 85.61 | Works Completed | Restricted Tender
| 4) Siata |  | 217.09 | 17.07.2023 | 13.12.2025 | 100% | 193.77 |  | 119.33 | 100% | 193.77 | Works Completed | Restricted Tender
| GROUP-X: | [11 empty] | Restricted Tender
| 1) Vaseikai |  | 260.81 | 17.07.2023 | 31.03.2026 | 100% | 220.35 |  | 40.5 | 100% | 220.35 | Works Completed
| 2) Tlabung |  | 93.84 | 17.07.2023 | 06.03.2026 | 100% | 84.84 |  | 30.5 | 100% | 84.84 | Works Completed
23 | Construction of Infrastructure Support for School of Agricultural Science at Hnahthial (Phase-II) | [10 empty] | Civil works completedand handover in process | Restricted Tender
| i) Boys Hostel |  | 659.4 | 08.04.2023 | 19.12.2025 | 100% | 342.5 |  | 0 | 100% | 342.5
| ii) Staff Quarter Type - III |  |  |  |  | 100% |  |  |  | 100%
| iii) Staff Quarter Type - II |  |  |  |  | 100% |  |  |  | 100%
| iv) Guest House |  |  |  |  | 100% |  |  |  | 100%
24 | Construction of PHC at Chhuarlung, Mizoram |  | 362.62 | 22.12.2025 | 22.12.2026 | 10% | 0 | 20% | 0 | 30% | 0 | Work in progress | Restricted Tender
25 | NEC
1 | Construction of Lunglei Market and Trade Centre at Electric/ Chanmari Veng, Lunglei |  | 1403.4 | 25.08.2022 | 16.01.2026 | 98% | 1082.33 | 2% | 321.07 | 100% | 1403.4 | Civil Works completed | Restricted Tender
26 | CSS
1 | Construction of Academic Building for Nursing School at Lunglei (Upgradation) | - | 441.35 | 19.8.2024 | 19.08.2026 | 72% | 156.74 | 2% | 58.21 | 74% | 214.95 | Works in progress | Open Tender
2 | Construction of Fire Station at Lunglei, Mizoram |  | 178.46 | 04.08.2025 | 04.08.2026 | 10% | 0 | 2% | 0 | 12% | 0 | Work in Progress | Restricted Tender
3 | Construction of Fire Station at Hnahthial |  | 173.9 | 13.10.2025 | 13.10.2026 | 15% | 0 | 3% | 0 | 18% | 0 | Work in Progress | Restricted Tender
4 | Construction of Fire Station at Lawngtlai, Mizoram |  | 180.78 | 04.08.2025 | 04.08.2026 | 36% | 0 | 4% | 0 | 40% | 0 | Work in progress. | Restricted Tender
5 | Construction of Fire Station at Council Vaih, Siaha |  | 207.9 | 04.08.2025 | 04.08.2026 | 45% | 0 | 20% | 65.99 | 65% | 65.99 | Work in progress. | Restricted Tender
27 | NEDP
1 | Construction of DC Bungalow (Type VI) at Siaha |  | 110.92 | 26.11.2018 | 23.05.2024 (Revised) | 100% | 109 | - | 0 | 100% | 109 | Handover in process | Restricted Tender
2 | Construction of DC Office Building at Siaha |  | 610.12 | 31.10.2018 | 31.12.2025 | 100% | 540.2 | - | 0 | 100% | 540.2 | Completed | Restricted Tender
28 | NESIDS
1 | Construction of 50-Bedded District Hospital Complex and Procurement of Equipment at Hnahthial, Mizoram |  | 1378.86 | 25.6.2024 | 25.12.2026 | 42% | 148.83 | 1% | 196.52 | 43% | 345.35 | Work in progress | Open Tender
29 | MINISTRY OF TRIBAL AFFAIRS
1 | Construction of Auditorium at Pukpui Lunglei |  | 523 | 16.9.2023 | 16.01.2025 | 5% | 0 | 2% | 0 | 7% | 0 | Work in progress | Restricted Tender
Sr. Executive Engineer, PWD.,
Lunglei Building Project Division, Lunglei

## LRD - I
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL/ 2026
Name of work |  | : | Rehabilitation of Aizawl - Thenzawl - Lunglei Road (100 - 164 Kmp) (Carriageway Width = 5.50m)
(Sh : Between 143.85 - 152.00 Kmp) (Annual Plan 5054)
Name of Contractor |  | : | SLT Infracon Pvt.LTD, Badarpurghat, Hailakandi, 78803,
( Rs. In lakh)
Sl. No. | Details of Works | Unit | Quantity | Approved Cost (Rs. In lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of Works during the month |  | Overall Cummulative achivement |  | Remarks |  | Work Progress Calc
[7 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Scarifying the existing bituminous road surface | Km | 7.095 | 122.9209 | 24.04.2025 | 24.04.2026 | 5 | 381.02 |  |  | 5 | 381.02 | Setting up of Plant and Machinery. The delay in work progress was due to the signing of Supplementary Agreement upon redesigning of the road by CRRI |  | 0.2886
2 | Rolling of existing granular layer | Km | 8.15 | 118.8539 |  |  | 5 |  |  |  | 5 |  |  |  | 0.34286 | 3.7
3 | WBM Grading - I | Km | 8.15 | 344.6442 |  |  | 5 |  |  |  | 5 |  |  |  | 0.11824
| WBM Grading - II | Km | 8.15 | 345.939 |  |  | 3.6 |  | 1.4 |  | 5 |  |  |  | 0.084813
5 | Prime Coat | Km | 7.095 | 24.9939 |  |  | 2 |  | 2 |  | 4 |  |  |  | 0.56774 | -1.48
6 | Dense Graded Bituminous Macadam | Km | 7.095 | 409.732 |  |  | 2 |  | 2 |  | 4 |  |  |  | 0.034632
7 | Tack Coat | Km | 7.095 | 12.2921 |  |  |  |  | 4 |  | 4 |  |  |  | 0
8 | Bituminous Concrete | Km | 7.095 | 376.97 | [10 empty] | 0 | 0
9 | Earthen Shoulder | Km | 8.15 | 5.5374 |  |  |  |  | 5 |  | 5 |  |  |  | 0
10 | Sub surface drain 400mm x 400mm | No | 163 | 9.2421 |  |  | 140 |  |  |  | 140 |  |  |  | 2469.1358
11 | Scarifying existing PQC | Km | 1.055 | 18.2779 |  |  | 0.98 |  |  |  | 0.98 |  |  |  | 0.056566
12 | Dry Lean Concrete | Sqm | 1.055 | 80.075 |  |  | 0.4 |  | 0.36 |  | 0.76 |  |  |  | 0.0052701
13 | Cement Concrete Pavement | Cum | 1.055 | 261.3731 |  |  | 0 |  | 0.38 |  | 0.38 |  |  |  | 0
14 | Boring with 125mm dia casing pipe | No | 10 | 4.98 |  |  | 0 | [7 empty] | 0
15 | Gabion Wall | Rm | 34.45 | 17.937 |  |  | 0 | [7 empty] | 0
16 | Toe Wall | Rm | 23.7 | 12.1945 |  |  | 0 | [7 empty] | 0
17 | Retaining Wall | Rm | 13.2 | 9.3233 |  |  | 0 | [7 empty] | 0
18 | RCC Lined Side Drain | Rm | 1500 | 82.916 |  |  | 0 | [7 empty] | 0
| GRAND TOTAL |  |  | 2258.2023 |  |  | 31.07% | 381.02 |  |  | 44.96% | 381.02 |  |  | 2470.6345
109.4%
MONTHLY PROGRESS REPORT UNDER LUNGLEI ROAD DIVISION - I, LUNGLEI
FOR THE MONTH OF APRIL/2026
(Rs. in lakh)
Sl. No. | Name of Schemes | Quantity | Unit | Approved Cost (Rs in Lakh) | Date of Commencement | Target Date of Comple-tion | Cumulative Progress at the end of last month |  | Achievement of works during the month |  | Overall Cumulative achievement |  | Remarks | Mode of Tender
| Name of Works / Project | [5 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
ANNUAL PLAN (5054)
I | Construction of Bailey Bridge (SS) Over R.Sazek on Mauzam to New Sachan Road (Sh: Construction of Abutment & Wingwall)
| 1) Abutment Wall | 2 | Nos | 42.2 | 24.02.2025 | 31.03.2026 | 100% | 58.68 |  |  | 100% | 58.68 | Completed
| 2) Wing Wall | 1 | No |  |  |  | 100% |  |  |  | 100% |  | Completed
| 3) Gabian Wall | 3 | Nos |  |  |  | 100% |  |  |  | 100% |  | Completed
| 4) Steel Structure | 1 | No | 24.66 |  |  | 0% |  |  |  | 0% |  | Material Collection
| TOTAL = |  |  | 66.86 |  |  | 75% | 58.68 |  |  | 75% | 58.68
MONTHLY PROGRESS REPORT UNDER LUNGLEI ROAD DIVISION - I, LUNGLEI
FOR THE MONTH OF APRIL/2026
ANNUAL PLAN (5054) | [10 empty] | (Rs. in lakh)
Sl. No. | Name of Schemes | Quantity | Unit | Approved Cost (Rs in Lakh) | Date of Commencement | Target Date of Comple-tion | Cumulative Progress at the end of last month |  | Achievement of works during the month |  | Overall Cumulative achievement |  | Remarks | Mode of Tender
| Name of Works / Project | [5 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Primary School to Colony Road Rahsiveng (Primary Rahsiveng Colony Road) | 120 | m | 11.07 | 26.01.2026 | 26.05.2026 | 0% |  | 71.15% |  | 71.15% |  | Work in Progress
2 | Restoration of Cement Concrete Pavement on Ramzotlang Baptist Church Approach Road (C. Thanzuala tuikhur to Pi Thangberi's house) | 119.5 | m | 11.64 |  |  | 71.16% |  |  |  | 71.16% |  | Work in Progress
3 | Resurfacing of Civil Hospital Approach Road (Civil Hospital ATL Main Road. | 0.14 | Km | 7.83 | 26.01.2026 | 26.05.2026 | 100% |  |  |  | 100% |  | Completed
4 | Resurfacing of Thana to Venglai HS Venglai (Thana Venglai Pi Chalnawni'S House) | 0.16 | Km | 6.71 | 26.01.2026 | 26.05.2026 | 100% |  |  |  | 100% |  | Completed
| TOTAL = | [5 empty] | 0.68 |  |  |  | 86%
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL/2026
Name of work |  | : | Construction of Approach Road for Engineering College at Pukpui, Lunglei, Mizoram (SASCI)
( Rs. in lakh)
Sl. No. | Details of Works | Unit | Quantity | Approved Cost (Rs. In lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of Works during the month |  | Overall Cummulative achivement |  | Remarks
[7 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Clearing and Grubbing Road Land | Hec | 0.378 | 0.73767 | 19.01.2026 | 19.01.2027 | 0.38 |  |  | 96.45 | 0.38 | 96.45 | Work in Progress
2 | Formation Cutting (Widening & Lowering) | Km | 2.73 | 19.3059 |  |  | 2.73 |  |  |  | 2.73
3 | Subgrade & Earthen Shoulder | Km | 2.73 | 56.928 |  |  | 2.73 |  |  |  | 2.73
4 | GSB | Km | 2.73 | 97.8359 |  |  | 2.73 |  |  |  | 2.73
5 | DLC | Km | 2.73 | 121.0032 |  |  |  |  | 0.75 |  | 0.75
6 | CC Pavement | Km | 2.73 | 421.3115
7 | Interlocking Concrete Block | Sqm | 4335.5 | 118.4459 |  |  |  |  | 700 |  | 700
8 | RCC Lined Side Drain | Km | 2.731 | 71.2943
9 | Hume Pipe Culvert | Nos | 8 | 57.8596 |  |  | 6 |  |  |  | 6
10 | RCC Causeway | Nos | 2 | 8.324
| GRAND TOTAL |  |  | 973.0458 |  |  | 12.29% |  |  | 96.45 | 27.81% | 96.45
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL/2026
Name of work |  | : | Construction of PCC Flooring at Various Locations viz.(II) Melte to Khawiva
Name of Contractor |  | : | K. Laltluangkima, Tanhril, Aizawl
| Name of Scheme | : | SASCI | [7 empty] | (Rs. in lakh)
Sl. No. | Details of Works | Unit | Quantity | Approved Cost (Rs. In lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of Works during the month |  | Overall Cummulative achivement |  | Remarks
[7 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Subgrade & Earthen Shoulder | Km | 2 | 15.041 | 02.02.2026 | 02.02.2027 | 2 |  |  |  | 2 |  | Work in Progress
2 | GSB | Km | 2 | 37.5 |  |  | 0 |  | 0.3 |  | 0.3
3 | CC Pavement | Km | 2 | 123 |  |  | 0 |  |  |  | 0
| GRAND TOTAL |  |  | 175.541 |  |  | 8.57% |  |  |  | 11.77%
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL/2026
| Name of work | : | Construction of PCC Flooring at Various Locations viz. (IV) Lena Stadium to New Maite
| Name of Contractor | : | K. Laltluangkima, Tanhril, Aizawl
| Name of Scheme | : | SASCI
(Rs.in lakh)
Sl. No. | Details of Works | Unit | Quantity | Approved Cost (Rs. In lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of Works during the month |  | Overall Cummulative achivement |  | Remarks
[7 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Subgrade & Earthen Shoulder | m | 130 | 0.80808 | 02.02.2026 | 02.02.2027 | 130 |  |  |  | 130 | 0 | Work in progress
2 | GSB | m | 130 | 1.9497 |  |  | 80 |  | 50 |  | 130 | 0
3 | CC Pavement | m | 130 | 7.995 |  |  | 0 |  | 130 |  | 130 | 0
| GRAND TOTAL |  |  | 10.7527 |  |  | 18.67% |  |  |  | 100% | 0
MONTHLY PROGRESS REPORT UNDER SASCI FOR THE MONTH OF APRIL/ 2026
NAME OF WORK : |  | Improvement and upgradation of Buarpui to Bunghmun Road (0.000-17.800 kmp)
NAME OF SCHEME : |  | SASCI
NAME OF DIVISION : |  | PWD, Lunglei Road Division-I, Lunglei.
NAME OF CONTRACTOR: |  | Urban Infraproject Pvt.Ltd
DATE OF START : |  | Dt.27th Jan 2026
DATE OF COMPLETION : |  | Dt.27th Jan 2027
T/S AMOUNT: |  | 96153730.54
(Rs. In lakh)
Sl.No | Details of works | As per Agreement |  |  | Achievement up to the previous month |  | Achievement during the month |  | Overall Cumulative achievement |  | Remarks
|  | Unit | Qnty | Cost ( in Lakh) | Phy. | Fin. | Phy. | Fin. | Phy. | Fin. (actual)
1 | 2 | 3 | 4 | 5 | 8 | 9 | 8 | 9 | 12 | 13 | 14
1 | Subgrade | Km | 17.15 | 26.46 | 2.5 |  | 4 |  | 6.5 |  | Work in progress
2 | WBM Gr - I (Layer-1) | Km | 14 | 242.4177 | 0.25 |  | 5.55 |  | 5.8
3 | WBM Gr - I (Layer-2) | Km | 17.15 | 222.6402
4 | OPC/Seal coat | Km | 17.15 | 437.0906
5 | Eartrhen Shoulder | Km | 17.15 | 14.9287
6 | Unlined Side Drain | Rm | 15000 | 18
|  |  | Total | 961.5373 | 0.01% |  |  |  | 0.02%
MONTHLY PROGRESS REPORT UNDER SASCI FOR THE MONTH OF APRIL/ 2026
NAME OF WORK : |  | Improvement of PCC Approach Road to Blue Mount Cluster (Zau) 11kms at Vanhne, Lunglei
NAME OF SCHEME : |  | SASCI
NAME OF DIVISION : |  | PWD, Lunglei Road Division-I, Lunglei.
NAME OF CONTRACTOR: |  | Vaube Projects
DATE OF START : |  | Dt.10th February 2026
DATE OF COMPLETION : |  | Dt.10th February 2027
T/S AMOUNT: |  | 24999998.42
(Rs. In lakh)
Sl.No | Details of works | As per Agreement |  |  | Achievement up to the previous month |  | Achievement during the month |  | Overall Cumulative achievement |  | Remarks
|  | Unit | Qnty | Cost ( in Lakh) | Phy. | Fin. | Phy. | Fin. | Phy. | Fin. (actual)
1 | 2 | 3 | 4 | 5 | 8 | 9 | 8 | 9 | 12 | 13 | 14
1 | Compacting Original Ground supporting Subgrade etc. | Cum | 965.63 | 10.52 | 0 |  |  |  | 600 |  | Secured advanced amounting to Rs 124267.00 Submitted on dt.20.3.2026
2 | PCC M 25 Pavement | Km | 5.15 | 239.47 | 0 |  | 550 |  | 550.25
| TOTAL = |  |  | 249.99 | 7.26% |  |  |  | 10.62%
Sr. Executive Engineer, P.W.D.,
Lunglei Road Division-I, Lunglei

## LRD-II
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL, 2026
Name of Division: Lunglei Road Division-II, Lunglei
Source of Funding : SASCI
Sl. No | Name of Work/Scheme | Unit | Approved Cost (Rs. In Lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last Month |  | Achievement of Works during the Month |  | Overall Cummulative achievement |  | Remarks | Mode of Tender
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
I | SASCI
1 | Improvement and Widening of Public Playground at Zobawk including Construction of Retaining wall | Rm | 35 | 27.12.2023 | 26.12.2024 | 100% | 0 | 0% | 35 | 100% | 35 | Completed | Restricted Tender
Sr. Executive Engineer, PWD.,
Lunglei Road Division-II, Lunglei

## LAWNGTLAI DIV
Monthly Progressive Report of SASCI for the Month of APRIL 2026
Name of Division |  | : | Lawngtlai Division
Slno | Name of Work/Project | Unit (km) | Approved Cost (Rs.in lakh) | Date of Commencement | Target Date of Completion | Cumulative Progress at the end of last month |  | Achievement of Work During the Month |  | Overall Cumulative Achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | (i) Restoration of collapsed road formation by Construction of Gabion wall at 1.400 kmp on DEO office to V.Zathanga Ground at L-IV, Lawngtlai | 17.00 Km | 20.62 | 09.07.2025 | 09.01.2026 | 100% | 20.62 |  |  | 100% | 20.62 | Completed | Item Rate
2 | (ii) Restoration of collapsed road formation by Construction of Retaining Wall at various locations on Thingfal-Mamte-Thlengang-Tuipui Road | 34.50 Km | 19.14 | 09.07.2025 | 09.01.2026 | 100% | 19.04 |  |  | 100% | 19.04 | Completed | Item Rate
3 | (iii) Restoration of collapsed road formation by Construction of Retaining Wall at various locations on Nalkawn to Chamdur Valley Road | 41.80 Km | 26.79 | 09.07.2025 | 09.01.2026 | 100% | 26.79 |  |  | 100% | 26.79 | Completed | Item Rate
4 | (iv) Restoration of collapsed road formation by Construction of Gabion wall at 3.200 kmp on Lawngtlai to Tuipui Ferry Road | 45.00 Km | 23.45 | 09.07.2025 | 09.01.2026 | 100% | 0 |  |  | 100% | 0 | Physically Completed | Item Rate
5 | (v) Restoration of collapsed road formation at 6.700 kmp on Lawngtlai to Tuipui Ferry Road (Sh: Construction of Gabion wall, re-construction of HP culvert & Repair of pavement) | 22.00 Km | 39.16 | 09.07.2025 | 09.01.2026 | 100% | 39.16 |  |  | 100% | 39.16 | Completed | Item Rate
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL 2026
Name of Division |  |  | : | LAWNGTLAI DIVISION
Source of funding&Name of work/Project |  |  | : | NABARD/ Improvement and Strengthening of Nalkawn - Chamdur Valley (NCV) (Section I & II) Road Under NABARD | [10 empty] | (Rs in lakh)
Sl No | Items of work |  | Unit | Qnty | Approved (Rs in lakh) | Date of commencement | Target dateof completion | Cummulative progress at the end of last month |  | Achievement of Works during the month |  | Overall cummulative achievement |  | Remarks | Mode of contract
[8 empty] | Physical | Fin | Physical | Fin | physical | Fin
1 | 2 |  | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Clearance of permanent landslip |  | cum | 16390.36 | 14.1 | 09.08.2019 | 31.12.2024 | 16390.36 | 14.1 |  |  | 16390.36 | 14.1 | Proposed for Termination as per Review Meeting on 24.09.2025 | Item rate
2 | Retaining Wall |  | 3: rm; 4: 136; 5: 65.6; 8: 128; 9: 56.43; 12: 123; 13: 56.43
3 | H/P Culvert |  | 3: nos; 4: 34; 5: 240.3; 8: 34; 9: 240.3; 12: 34; 13: 240.3
4 | Pavement Works:-
a) | Sub Grade |  | 3: km; 4: 13.57; 5: 24.93; 8: 13.57; 9: 24.93; 12: 13.57; 13: 24.93
b) | WBM - I |  | 3: km; 4: 39.1; 5: 513.19; 8: 39.1; 9: 513.19; 12: 39.1; 13: 513.19
c) | WBM - II |  | 3: km; 4: 46.94; 5: 616.14; 8: 46.94; 9: 616.14; 12: 46.94; 13: 616.14
d) | Surface Course |  | 3: km; 4: 38.54; 5: 853.94; 8: 8; 9: 143.92; 12: 8; 13: 143.92
5 | Unlined Side Drain |  | 3: km; 4: 39; 5: 30.03; 8: 39; 9: 30.03; 12: 39; 13: 30.03
2358.23
| 3% Contingencies = |  | 5: 70.75; 9: 55.96; 13: 55.96
| 8% GST = |  | 5: 187.23; 9: 129.69; 13: 129.69
| 1% Labour cess = |  | 5: 0.2; 9: 0.2; 13: 0.2
| Grand Total = |  | 5: 2616.41; 9: 1824.89; 12: 71.04%; 13: 1824.89
* Physical progress percentege is updated considering weightage of each items .
Monthly Progressive Report of 5054 (ROADS & BRIDGES) for the Month of APRIL 2026
Name of Division |  | : | 3: Lawngtlai Division
Slno | Name of Work/Project | Unit (km) | Approved Cost (Rs.in lakh) | Date of Commencement | Target Date of Completion | Cumulative Progress at the end of last month |  | Achievement of Work During the Month |  | Overall Cumulative Achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Maintenance of Roads within Lawngtlai Town under 5054 (R&B) | 3.16 | 61.11 | 30.11.2025 | 21.03.2026 | 60% | 0 | 30% | 0 | 90% | 0 | Work in Progress | Item Rate
Monthly Progressive Report of 5054 (ROADS & BRIDGES) for the Month of APRIL 2026
Name of Work |  | : | 3: Patch Repair & Full Length Seal Coating of Approach Road to KVK at Chawnhu, Lawngtlai
Name of Scheme |  | : | 3: 5054 (R&B); 8: Date of Start of Work; 11: :; 12: 13.02.2026
Name of Division |  | : | 3: Lawngtlai Division; 8: Time of Completion; 11: :; 12: 3 Months
Name of Contractor |  | : | 3: Rorelliana, Council Veng, Lawngtlai
Sl/ no | Name of Work/Project | Unit (km) | Approved Cost (Rs.in lakh) | Date of Commencement | Target Date of Completion | Cumulative Progress at the end of last month |  | Achievement of Work During the Month |  | Overall Cumulative Achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Patch Repair & Full Length Seal Coating of Approach Road to KVK at Chawnhu, Lawngtlai |  | 6.72 | 25.03.2026 | 25.06.2026 | 0% | 0 | 0% | 0 | 0% | 0 | Material Collection | Item Rate
Monthly Progressive Report of 5054 (ROADS & BRIDGES) for the Month of APRIL 2026
Name of Work |  | : | 3: Patch Repair of Bazar Veng to AOC Road via PWD Offoce at Lawngtlai
Name of Scheme |  | : | 3: 5054 (R&B); 8: Date of Start of Work; 11: :; 12: 13.02.2026
Name of Division |  | : | 3: Lawngtlai Division; 8: Time of Completion; 11: :; 12: 3 Months
Name of Contractor |  | : | 3: Rorelliana, Council Veng, Lawngtlai
Sl/ no | Name of Work/Project | Unit (km) | Approved Cost (Rs.in lakh) | Date of Commencement | Target Date of Completion | Cumulative Progress at the end of last month |  | Achievement of Work During the Month |  | Overall Cumulative Achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Patch Repair of Bazar Veng to AOC Road via PWD Offoce at Lawngtlai |  | 14.42 | 25.03.2026 | 25.06.2026 | 0% | 0 | 100% | 0 | 100% | 0 | Physically Completed | Item Rate
Monthly Progressive Report of 5054 (ROADS & BRIDGES) for the Month of APRIL 2026
Name of Work |  | : | 3: Patch Repair, Seal Coating and Rehabilitation of Sinking Area of Sangchema Road, Lawngtlai
Name of Scheme |  | : | 3: 5054 (R&B); 8: Date of Start of Work; 11: :; 12: 13.02.2026
Name of Division |  | : | 3: Lawngtlai Division; 8: Time of Completion; 11: :; 12: 3 Months
Name of Contractor |  | : | 3: Rorelliana, Council Veng, Lawngtlai
Sl/ no | Name of Work/Project | Unit (km) | Approved Cost (Rs.in lakh) | Date of Commencement | Target Date of Completion | Cumulative Progress at the end of last month |  | Achievement of Work During the Month |  | Overall Cumulative Achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Patch Repair, Seal Coating and Rehabilitation of Sinking Area of Sangchema Road, Lawngtlai |  | 9.6 | 25.03.2026 | 25.06.2026 |  | 0 | 0% | 0 | 0% | 0 | Material Collection | Item Rate
Monthly Progressive Report of 5054 (ROADS & BRIDGES) for the Month of APRIL 2026
Name of Work |  | : | 3: Improvement of Thingfal to mamte - Thlengang - Tuipui Road from Chainage 17/000 - 21/400 Kmp
Name of Scheme |  | : | 3: 5054 (R&B); 8: Date of Start of Work; 11: :; 12: 13.02.2026
Name of Division |  | : | 3: Lawngtlai Division; 8: Time of Completion; 11: :; 12: 3 Months
Name of Contractor |  | : | 3: NC. Beichakhei, New Colony, Siaha
Sl/ no | Name of Work/Project | Unit (km) | Approved Cost (Rs.in lakh) | Date of Commencement | Target Date of Completion | Cumulative Progress at the end of last month |  | Achievement of Work During the Month |  | Overall Cumulative Achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Improvement of Thingfal to mamte - Thlengang - Tuipui Road from Chainage 17/000 - 21/400 Kmp |  | 105.76 | 25.03.2026 | 25.06.2026 | 0% | 0 | 0% | 0 | 0% | 0 | Material Collection | Item Rate
Monthly Progressive Report of 5054 (ROADS & BRIDGES) for the Month of APRIL 2026
Name of Work |  | : | 3: Improvement of 3rd IR Battalian Headquarter Approach Road & Internal Road at Thingkah, Mizoram
Name of Scheme |  | : | 3: 5054 (R&B); 8: Date of Start of Work; 11: :; 12: 13.02.2026
Name of Division |  | : | 3: Lawngtlai Division; 8: Time of Completion; 11: :; 12: 3 Months
Name of Contractor |  | : | 3: K. Lalhmuna, Bazar Veng, Lawngtlai
Sl/ no | Name of Work/Project | Unit (km) | Approved Cost (Rs.in lakh) | Date of Commencement | Target Date of Completion | Cumulative Progress at the end of last month |  | Achievement of Work During the Month |  | Overall Cumulative Achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Improvement of 3rd IR Battalian Headquarter Approach Road & Internal Road at Thingkah, Mizoram |  | 76.9 | 25.03.2026 | 25.06.2026 |  | 0 | 5% | 0 | 5% | 0 | Work in Progress | Item Rate
Monthly Progressive Report of 5054 (ROADS & BRIDGES) for the Month of APRIL 2026
Name of Work |  | : | 3: Patch Repairing & Seal Coating of Approach Road Chengkawllui road at College Veng from NH-54
Name of Scheme |  | : | 3: 5054 (R&B); 8: Date of Start of Work; 11: :; 12: 13.02.2026
Name of Division |  | : | 3: Lawngtlai Division; 8: Time of Completion; 11: :; 12: 3 Months
Name of Contractor |  | : | 3: Departmental
Sl/ no | Name of Work/Project | Unit (km) | Approved Cost (Rs.in lakh) | Date of Commencement | Target Date of Completion | Cumulative Progress at the end of last month |  | Achievement of Work During the Month |  | Overall Cumulative Achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Patch Repairing & Seal Coating of Approach Road Chengkawllui road at College Veng from NH-54 | 1.01 | 15 | 25.03.2026 | 25.06.2026 | 0% | 0 | 10% | 0 | 10% | 0 | Work in Progress | Item Rate
Monthly Progressive Reportof AGRICULTURE LINK ROAD for the Month of APRIL 2026
Name of Work |  | : | 3: Construction of Agriculture Link Road from BRTF Road to Sekulhkai at Hmunnuam Village
Name of Scheme |  | : | 3: NABARD; 8: Date of Start of Work; 11: :; 12: 13.02.2026
Name of Division |  | : | 3: Lawngtlai Division; 8: Time of Completion; 11: :; 12: 6 Months
Name of Contractor |  | : | 3: JH. Vanramngaia, Vengpui - II Lawngtlai
Sl/ no | Name of Work/Project | Unit (km) | Approved Cost (Rs.in lakh) | Date of Commencement | Target Date of Completion | Cumulative Progress at the end of last month |  | Achievement of Work During the Month |  | Overall Cumulative Achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Agriculture Link Road from BRTF Road to Sekulhkai at Hmunnuam Village |  | 69.52 | 13.02.2026 | 13.08.2026 | 14% | 0 | % | 0 | 14% | 0 | Work in Progress | Item Rate
Monthly Progressive Reportof AGRICULTURE LINK ROAD for the Month of APRIL 2026
Name of Work |  | : | 3: Construction of Agriculture Link Road from Diltlang to Telhpuichangzawl at Diltlang South
Name of Scheme |  | : | 3: NABARD; 8: Date of Start of Work; 11: :; 12: 13.02.2026
Name of Division |  | : | 3: PWD, Lawngtlai Division; 8: Time of Completion; 11: :; 12: 6 Months
Name of Contractor |  | : | 3: T. Lawmchhunga, Chandmary: Lawngtlai
Sl/ no | Name of Work/Project | Unit (km) | Approved Cost (Rs.in lakh) | Date of Commencement | Target Date of Completion | Cumulative Progress at the end of last month |  | Achievement of Work During the Month |  | Overall Cumulative Achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Agriculture Link Road from Diltlang to Telhpuichangzawl at Diltlang South | 2.00 Kms | 19.9 | 13.02.2026 | 13.08.2026 | 95% | 0 | 5% | 0 | 100% | 0 | Physically Completed | Item Rate
Monthly Progressive Reportof AGRICULTURE LINK ROAD for the Month of APRIL 2026
Name of Work |  | : | 3: Construction of Agriculture Link Road from Diltlang to Changmual at Diltlang South Village
Name of Scheme |  | : | 3: NABARD
Name of Division |  | : | 3: PWD, Lawngtlai Division; 8: Date of Start of Work; 11: :; 12: 13.02.2026
Name of Contractor |  | : | 3: T. Lawmchhunga, Chandmary: Lawngtlai; 8: Time of Completion; 11: :; 12: 6 Months
Sl/ no | Name of Work/Project | Unit (km) | Approved Cost (Rs.in lakh) | Date of Commencement | Target Date of Completion | Cumulative Progress at the end of last month |  | Achievement of Work During the Month |  | Overall Cumulative Achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Agriculture Link Road from Diltlang to Changmual at Diltlang South Village | 5.00 Kms | 51.76 | 13.02.2026 | 13.08.2026 | 14% | 0 | 0% | 0 | 14% | 0 | Work in Progress | Item Rate
Monthly Progressive Reportof AGRICULTURE LINK ROAD for the Month of APRIL 2026
Name of Work |  | : | 3: Construction of Agriculture Link Road from Ngengpuikai to Khangapuilui at Ngengpuikai Village
Name of Scheme |  | : | 3: NABARD; 8: Date of Start of Work; 11: :; 12: 13.02.2026
Name of Division |  | : | 3: Lawngtlai Division; 8: Time of Completion; 11: :; 12: 6 Months
Name of Contractor |  | : | 3: H. Lalnghakzuala, Council Veng, Lawngtlai
Sl/ no | Name of Work/Project | Unit (km) | Approved Cost (Rs.in lakh) | Date of Commencement | Target Date of Completion | Cumulative Progress at the end of last month |  | Achievement of Work During the Month |  | Overall Cumulative Achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Agriculture Link Road from Ngengpuikai to Khangapuilui at Ngengpuikai Village | 5.00 Kms | 51.17 | 13.02.2026 | 13.08.2026 | 80% | 0 | 20% | 0 | 100% | 0 | Physically Completed | Item Rate
Monthly Progressive Reportof AGRICULTURE LINK ROAD for the Month of APRIL 2026
Name of Work |  | : | 3: Construction of Agriculture Link Road from Chawngtelui to Ramri Lui at Chawngtelui Village
Name of Scheme |  | : | 3: NABARD; 8: Date of Start of Work; 11: :; 12: 13.02.2026
Name of Division |  | : | 3: Lawngtlai Division; 8: Time of Completion; 11: :; 12: 6 Months
Name of Contractor |  | : | 3: H. Lalnghakzuala, Council Veng, Lawngtlai
Sl/ no | Name of Work/Project | Unit (km) | Approved Cost (Rs.in lakh) | Date of Commencement | Target Date of Completion | Cumulative Progress at the end of last month |  | Achievement of Work During the Month |  | Overall Cumulative Achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Agriculture Link Road from Chawngtelui to Ramri Lui at Chawngtelui Village | 7.00 Kms | 19.9 | 13.02.2026 | 13.08.2026 | 90% | 0 | 10% | 0 | 100% | 0 | Physically Completed | Item Rate
Sr. Executive Engineer, PWD
Lawngtlai Division : Lawngtlai

## MAMIT DIV
MONTHLY PROGRESS REPORT FOR THE MONTH OF MARCH 2026
Name of Work : Strengthening & Improvement of W.Phaileng to Marapara Road | [8 empty] | Name of Contractor: |  |  | SLT Infracon Pvt. Ltd.
| (00.00 - 30.00 Kmp) Package-I | [7 empty] | Date of Commencement |  |  | : 15th March 2023
Name of Scheme : |  | NABARD | [6 empty] | Target date of completion |  |  | : 15th March 2025
Sanction Amount : | [8 empty] | EOT |  |  | : 7th March 2026
Agreement Amount : |  | Rs. 1854.59 Lakhs | [6 empty] | Overall Achievement |  |  | : 100.00 %
Supplementary Agreement Amt : |  | Rs. 453.88 Lakhs
Name of Division : |  | Mamit | [10 empty] | (Rupees in Lakhs)
Sl. No. | Items of Works | Unit | Qnty | Cost (in lakh) | Achievement upto previous year 2025-2026 |  | Achievement upto previous month |  | Achievement during the month |  | Target for the next month |  | Overall Cumulative achievement |  | Remarks
[5 empty] | Phy | Fin | Phy | Fin | Phy | Fin | Phy | Fin | Phy (8+10) | Fin (9+11)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
1 | Hill Side Drain Clearance | Rm | 30000 | 2308.47 | 30000 | 858.17 | 30000 | 1901.04 | 0 | 82.2 |  |  | 30000 | 1983.24 | Physically Completed
2 | Maintenance of earth Shoulder | m2 | 30000 |  | 0 |  | 30000 |  | 0 |  |  |  | 30000
3 | Scarifying Granular surface | m2 | 38030.793 |  | 36815.5 |  | 38030.75 |  | 0 |  |  |  | 38030.75
4 | Clearing Grass & removal of Rubbish etc., C) MDRs, SHs, NHs etc. | Km | 60 |  | 60 |  | 60 |  | 0 |  |  |  | 60
5 | WBM, Grading – I | m3 | 763.38 |  | 763.38 |  | 763.38 |  | 0 |  |  |  | 763.38
6 | WBM, Grading – II | m3 | 2852.31 |  | 2761.163 |  | 2852.313 |  | 0 |  |  |  | 2852.313
7 | Prime Coat, (iii) High Porosity | m2 | 54285.4 |  | 39371.12 |  | 54285.4 |  | 0 |  |  |  | 54285.4
8 | Tack Coat, (iii) Granular Treated Primer | m2 | 128550.51 |  | 40056.733 |  | 128550.51 |  | 0 |  |  |  | 128550.51
9 | Bituminous Macadam, (i) For Grading-I (40mm nominal size) | m3 | 2490.03 |  | 1968.75 |  | 2490.03 |  | 0 |  |  |  | 2490.03
10 | Bituminous Concrete, Case-II using Modified Bitumen (ii) For Grading-II 910mm nominal size) | m3 | 3543.75 |  | 1201.702 |  | 3543.75 |  | 0 |  |  |  | 3543.75
11 | Retaining wall | No. | 23 |  | 6 |  | 23 |  | 0 |  |  |  | 23
12 | Hume Pipe Culvert | No. | 4 |  | 4 |  | 4 |  | 0 |  |  |  | 4
13 | Land Slide Clearance in soil | m3 | 6796.86 |  | 4920.75 |  | 6796.86 |  | 0 |  |  |  | 6796.86
14 | Land Slide Clearance in Hard Rock requiring Blasting | m3 | 1640.25 |  | 1640.25 |  | 1640.25 |  | 0 |  |  |  | 1640.25
15 | Coping Between Parapets (CM 1:3) | m2 | 2.3
15 | Price Escalation |  |  |  |  | 9.61 |  | 9.61 | [5 empty] | 9.61
| Grand Total = |  |  | 2308.47 |  | 867.78 |  | 1910.65 | [5 empty] | 1992.85
MONTHLY PROGRESS REPORT FOR THE MONTH OF MARCH 2026
Name of Work : Strengthening & Improvement of W.Phaileng to Marapara Road | [8 empty] | Name of Contractor: |  |  | SLT Infracon Pvt. Ltd.
| (30.00 - 80.00 Kmp) Package-II | [7 empty] | Date of Commencement |  |  | : 15th March 2023
Name of Scheme : |  | NABARD | [6 empty] | Target date of completion |  |  | : 15th March 2025
Sanction Amount : | [8 empty] | EOT |  |  | : 7th March 2026
Agreement Amount : |  | Rs. 4778.80 Lakhs | [6 empty] | Overall Achievement |  |  | 88.5%
Supplementary Agreement Amt : |  | Rs. 458.77 Lakhs
Name of Division : |  | Mamit | [10 empty] | (Rupees in Lakhs)
Sl. No. | Items of Works | Unit | Qnty | Cost (in lakh) | Achievement upto previous year 2025-2026 |  | Achievement upto previous month |  | Achievement during the month |  | Target for the next month |  | Overall Cumulative achievement |  | Remarks
[5 empty] | Phy | Fin | Phy | Fin | Phy | Fin | Phy | Fin | Phy (8+10) | Fin (9+11)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
1 | Hill Side Drain Clearance | Rm | 47830 | 5237.57 | 47830 | 2740.33 | 47830 | 4082.69 | 0 | 89.36 |  |  | 47830 | 4172.05 | Due to Supplementary Agreement, quantity of WBM Gr-I&II, Prime Coat, Land Slide Clearance in soil & Number of retaining walls increases. Price Escalation, Contingency and QC expenditure is outside of agreement but within sanction amount.
2 | Maintenance of earth Shoulder | m2 | 50000 |  | 13500 |  | 16000 |  | 0 |  | 34000 |  | 16000
3 | Scarifying Granular surface | m2 | 164913.595 |  | 137472.8 |  | 149742.8 |  | 4000 |  | 11170.795 |  | 153742.8
4 | Clearing Grass & removal of Rubbish etc., C) MDRs, SHs, NHs etc. | Km | 100 |  | 100 |  | 100 |  | 0 |  |  |  | 100
5 | WBM, Grading – I | m3 | 4382.781 |  | 3426.96 |  | 3898.96 |  | 150 |  | 333.821 |  | 4048.96
6 | WBM, Grading – II | m3 | 11765.238 |  | 10310.46 |  | 11230.71 |  | 300 |  | 234.528 |  | 11530.71
7 | Prime Coat, (iii) High Porosity | m2 | 218857.395 |  | 149625 |  | 167292.22 |  | 0 |  | 51565.175 |  | 167292.22
8 | Tack Coat, (iii) Granular Treated Primer | m2 | 196875 |  | 63000 |  | 63000 |  | 86625 |  | 47250 |  | 149625
9 | Bituminous Macadam, (i) For Grading-I (40mm nominal size) | m3 | 9843.75 |  | 7481.25 |  | 8364.6 |  | 0 |  | 1479.15 |  | 8364.6
10 | Bituminous Concrete, Case-II using Modified Bitumen (ii) For Grading-II 910mm nominal size) | m3 | 5906.25 |  | 1890 |  | 1890 |  | 2598.75 |  | 1417.5 |  | 4488.75
11 | Surface Drain in Hard Rock | m | 500 |  | 500 |  | 500 |  | 0 |  |  |  | 500
12 | Lined Side Drain | m | 1670 |  | 450 |  | 450 |  | 0 |  |  |  | 450
13 | Retaining wall | No. | 33 |  | 25 |  | 31 |  | 0 |  |  |  | 31
14 | Hume Pipe Culvert | No. | 12 |  | 7 |  | 7 |  | 0 |  |  |  | 7
15 | Slab Culvert | No. | 2 |  | 2 |  | 2 |  | 0 |  |  |  | 2
16 | Land Slide Clearance in soil | m3 | 14368.734 |  | 9865.069 |  | 14368.73 |  | 0.004 |  |  |  | 14368.734
17 | Land Slide Clearance in Hard Rock requiring Blasting | m3 | 3288.356 |  | 3288.356 |  | 3288.356 |  | 0 |  |  |  | 3288.356
18 | GSB (i)Grading-I | m3 | 360 | [5 empty] | 0 |  |  |  | 360
19 | Coping Between Parapets (CM 1:3) | m2 | 2.439 | [7 empty] | 2.439
20 | Quality Control |  |  |  |  | 32.43 |  | 76.45 | [5 empty] | 76.45
21 | Contingency |  |  |  |  | 82.68 |  | 82.68 |  | 4.04 |  |  |  | 86.72
22 | Price Escalation |  |  |  |  | 12.4 |  | 12.4 | [5 empty] | 12.4
| Grand Total = |  |  | 5237.57 |  | 2867.84 |  | 4254.22 |  | 93.4 |  |  |  | 4347.62
SASCI
Sl. No. | Items of Works | Unit | Approved cost (Rs.in lakh) | Date of commencement | Target date of completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall Cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Restoration of danage Due to Cyclone Remal under Mamit, Kawrthah and Kolasib Division |  | 289.4 | 16.06.2025 | 16.01.2026 | 98% | 276.95 |  |  | 0.98 | 276.95 | Work in progress | Item rate
EI & ISC
Sl. No. | Items of Works | Unit | Approved cost (Rs.in lakh) | Date of commencement | Target date of completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall Cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Imrpvement of Tuipuibari to W.Kawnpui Road, (0.00 - 9.00 kmp) under EI & ISC Scheme |  | 4870 | 20.03.2020 | 20.03.2022 | 99% | 81.69% |  |  | 99 | 81.69 | Work in progress | Item rate
MONTHLY PROGRESS REPORT FOR THE MONTH OF MARCH 2026
Name of Division : |  | Mamit Division
Source of funding : |  | EI & ISC
Sl. No. | Name of Work/Project | Unit | Approved Cost (Rs. In lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the Month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Improvement of Tuipuibari to W.Kawnpui Road, (0.00 - 9.00 Kmp) under EI & ISC Scheme |  | 4870 | 20.03.2020 | 20.03.2022 | 99% | 81.69% | 0% |  | 99% | 81.69% |  | EPC
PROGRESS REPORT OF STRENGTHENING AND IMPROVEMENT OF STATE ROAD FOR THE MONTH OF MARCH 2026 (3054 )
Sl. No. | Name of Road | Amount of Technical Sanction (Rs. Lakh) | Date of Technical Sanction | Financial Progress (Amount Rs. Lakh) |  |  | Physical Progress (in percentage) |  |  | Remarks
|  |  |  | Expenditure upto end of previous month | Expenditure during the month | Total Expenditure upto end of the month | Progress upto end of previous month | Progress during the month | Progress upto end of the month
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 10
1 | Repair of Pukzing to Silsury Road at essential stretches | 50 | 17.09.2025 | 47.17 | 2.83 | 50 | 100% |  | 100%
2 | Repair of Phuldungsei to Parvatui Road at essential stretches | 20 |  |  | 11.37 | 11.37 | 60% | 20% | 80%
3 | Repair of Approcah from Marpara Road to Lallen | 10 |  | 9.42 | 0.58 | 10 | 100% |  | 100%
4 | Construction of Retaining Wall in W.Phaileng at essential places | 30 |  | 28.28 | 1.72 | 30 | 100% |  | 100%
5 | Construction of Retaining Wall at Ch:0.150Kmp on approach to Khawrihnim Godown | 4.22 |  | 3.98 | 0.24 | 4.22 | 100% |  | 100%
6 | Patch repair and resurfacing of Dintharkawn to SDO Civil Complex at W.Phaileng | 8.37 |  | 8.05 | 0.32 | 8.37 | 100% |  | 100%
7 | Construction of V-shape side drain on W.Phaileng Town Roads | 12.14 |  |  | 12.14 | 12.14 | 95% | 5% | 100%
8 | Construction of Retaining Wall on approach road to Agriculture Complex at W.Phaileng | 10.96 |  | 10.53 | 0.43 | 10.96 |  | 100% | 100%
| Grand Total = | 145.69 |  | 107.43 | 29.63 | 137.06
PROGRESS REPORT OF ANNUAL MAINTENANCE ACTION PLAN 2025-2026 FOR THE MONTH OF MARCH 2026 (3054)
Sl. No. | Name of Road | Length (Km) | Amount of Technical Sanction (Rs. Lakh) | Date of Technical Sanction | Financial Progress (Amount Rs. Lakh) |  |  | Physical Progress (in percentage) |  |  | Remarks
[5 empty] | Expenditure upto end of previous month | Expenditure during the month | Total Expenditure upto end of the month | Progress upto end of previous month | Progress during the month | Progress upto end of the month
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Pothole filling & Resurfacing of PWD Complex Internal Roads at Mamit | 0.4 | 6.13 | 21.10.2025 | 6.13 |  | 6.13 | 100% |  | 100%
2 | Flexible Pavement of Footpath - Ring Road at Mamit | 0.32 | 14.42 |  | 14.42 |  | 14.42 | 100% |  | 100%
| PCC V-shape Side Drain | 176.00m
3 | Resurfacing of Approach Road to PHC Complex at W.Phaileng | 0.32 | 8.3 |  | 8.3 |  | 8.3 | 100% |  | 100%
4 | Resurfacing of Road from H/S Veng to charkawn via Bazar at Mamit | 0.46 | 14.54 |  | 14.54 |  | 14.54 | 100% |  | 100%
5 | Pothole filling & Resurfacing of DC Complex Internal Roads at Mamit | 0.75 | 11.64 |  | 11.64 |  | 11.64 | 100% |  | 100%
6 | Pothole filling & Resurfacing of Approach Road to RD Complex at W.Phaileng | 0.49 | 8.3 |  | 8.3 |  | 8.3 | 100% |  | 100%
7 | Resurfacing of Approach Road to Agriculture Complex at W.Phaileng | 0.58 | 8.4 |  | 8.4 |  | 8.4 | 100% |  | 100%
8 | Resurfacing of Approach Road to P & E Office Complex at Mamit | 0.24 | 3.15 |  | 3.15 |  | 3.15 | 100% |  | 100%
9 | Resurfacing of Approach Road to SP Qtrs Complex at Mamit | 0.12 | 1.87 |  | 1.87 |  | 1.87 | 100% |  | 100%
10 | Pothole Filling & Resurfacing from CMO Qtrs to Ngarpet Road at Mamit | 0.17 | 2.8 |  | 2.8 |  | 2.8 | 100% |  | 100%
11 | Pothole Filling & Resurfacing of Approach Road and Internal Roads PHED Complex at Mamit | 0.17 | 5.29 |  | 5.29 |  | 5.29 | 100% |  | 100%
12 | Restoration of raincut and petty landslips on Tuipuibari to W.Kawnpui Road(9.00 - 18.00 km) | 9 | 5 |  | 5 |  | 5 | 100% |  | 100%
13 | Pothole Fiiiling & Resurfacing of Approach Road to Belleikawn Road at W.Phaileng | 0.2 | 2.5 |  | 2.5 |  | 2.5 | 100% |  | 100%
| Grand Total = |  | 92.34 |  | 92.34 | 0 | 92.34
PROGRESS REPORT OF ROAD SAFETY MEASURES UNDER MAMIT FOR THE MONTH OF MARCH 2026 (3054)
Sl. No. | Name of Road | Amount of Technical Sanction (Rs. Lakh) | Date of Technical Sanction | Financial Progress (Amount Rs. Lakh) |  |  | Physical Progress (in percentage) |  |  | Remarks
|  |  |  | Expenditure upto end of previous month | Expenditure during the month | Total Expenditure upto end of the month | Progress upto end of previous month | Progress during the month | Progress upto end of the month
1 | 2 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Road safety measures for Mamit Town | 5 | 18.03.2026 |  | 5 | 5 |  | 100% | 100%
| Grand Total = | 5 |  | 0 | 5 | 5
PROGRESS REPORT OF STRENGTHENING AND IMPROVEMENT OF STATE ROAD FOR THE MONTH OF MARCH 2026 ( 5054 )
Sl. No. | Name of Road | Amount of Technical Sanction (Rs. Lakh) | Date of Technical Sanction | Financial Progress (Amount Rs. Lakh) |  |  | Physical Progress (in percentage) |  |  | Remarks
|  |  |  | Expenditure upto end of previous month | Expenditure during the month | Total Expenditure upto end of the month | Progress upto end of previous month | Progress during the month | Progress upto end of the month
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 10
1 | Profile Correction of Road from PWD Office - DC Office at Mamit | 53.67 | 17.11.2025 |  | 32.27 | 32.27 | - | 59% | 59%
2 | Construction of Retaing Wall on Tourist Lodge-PHC at W.Phaileng | 7.77 |  | 7.38 | 0.39 | 7.77 |  | 100% | 100%
3 | Construction of PCC Pavement on Approach Road to Helipad at W.Phaileng (Balance Portion) | 16.73 |  |  | 0.95 | 0.95 | 10% | 65% | 75%
| Grand Total = | 78.17 |  |  | 33.61
MONTHLY PROGRESS REPORT FOR THE MONTH OF MARCH 2026
Name of Division : |  | Mamit Division
Source of funding : |  | SASCI
Name of Contractor : |  | H. Zorempuia
Sl. No. | Name of Work/Project | Unit | Approved Cost (Rs. In lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the Month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Restoration of Damage Due to Cyclone Remal Under Mamit, Kawrthah and Kolasib Division |  | 289.4 | 16.06.2025 | 16.01.2026 | 98% | 248.73 |  | 28.22 | 98% | 276.95 | Work in Progress | Item Rate
Sr. Executive Engineer, P.W.D.,
Mamit Division, Mamit
Sr. Executive Engineer, P.W.D.,
Mamit Division, Mamit

## MMPD
MONTHLY PROGRESS REPORT UNDER MULTI MODAL PROJECT DIVISION FOR THE MONTH OF APRIL, 2026
SlNo | Name of Scheme | Unit | Approved Cost (in lakhs) | Date of Commencement | Target date of completion | Cumulative progress at the end of last month |  | Achievement of works during the month |  | Overall Cumulative achievement |  | Remarks | Mode of Tender
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
SASCI
Work under SASCI
1 | Construction of Side Drain along NH-54 and on different parts of Lawngtlai Town | mtr | 200 | 18.02.2026 | 18.08.2026 | 0 |  | 0 |  | 0 |  | Work not yet started. | Restricted
NABARD
Work under NABARD
NEC
Work under NEC
PMGSY
Work under PMGSY
SEDP
Work under SEDP
CSS
Work under CSS
MoRTH
Work under MoRTH
1 | Construction of 2 Nos Reinforced Earth wall for restoration of road formation collapse at km 11.000 & km 11.050 and re-construction of Box culvert at km 11.000 on NH-502A in the state of Mizoram | mtr | 594.66 | 10.02.2025 | 30.11.2025 | 457 | 554.25 | 0 | 0 | 457 | 554.25 | Physically Completed during Dec 2025 | EPC Mode | #REF!
2 | STMC on NH 502 from Km 0.000 to Km 27.380 during 2025-2026 in the State of Mizoram | sqm | 162.76 | 09.12.2025 | 08.12.2026 | 2562 |  | 250 |  | 2812 | 0 |  | Item Rate
3 | Construction of new 2-lane Highway from Km 0.00-km 38.00 on NH 54 near Lawngtlai in Mizoram to support Kaladan Multi Modal Transit Transport Project in Phase A of SARDP-NE (pacakge-I) | Km | 43465 | 12.10.2010 | 12.10.2014 | 100% | 42680 |  |  | 100% | 42680 | Work physically Completed on 22.06.2023 | Item Rate
4 | Construction of new 2-lane Highway from km 38.00 to Km 70/00 in Mizoram to support Kaladan Multi Modal Transit Transport Project in Phase A of SARDP-NE (pacakge-II) | Km | 32224 | 12.10.2010 | 30.09.2014 | 100% | 30977 |  |  | 100% | 30977 | Work physically Completed on 30.04.2022 | Item Rate
5 | Construction of new 2-lane Highway from Km 70/00 to Km 99/00 in Mizoram to support Kaladan Multi Modal Transit Transport Project in Phase A of SARDP-NE (pacakge-III) | Km | 37459 | 12.10.2010 | 30.09.2014 | 100% | 36468 |  |  | 100% | 36468 | Work physically Completed on 23.06.2023 | Item Rate
Executive Engineer, PWD
Multi Modal Project Division
Lawngtlai: Mizoram

## NH - I
Monthly Progress Report under National Highway Division-I, PWD., April, 2026
Sl. No | Name of Scheme | Unit | Approved Cost (in lakhs) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall Cummulative achievement |  | Remarks | Mode of Tender
| Name of Work/Project |  |  |  |  | Phy. | Fin. | Phy. | Fin. | Phy. | Fin.
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
SASCI
1 | Construction of Saiphal - Hortoki Road (21.150 km) | Phy in % Fin in lakh | 600 | 15.12.2023 | 15.12.2025 | 75% | 314.15 | 5% |  | 80% | 314.15 | On Going | Restricted tender
2 | Improvement of Approach road at Mamit (NH 44A) Junction to GSA playgroaund | Phy in % Fin in lakh | 989 | 13.06.2025 | 12.06.2027 | 25% | 80.31 | 1% |  | 26% | 80.31 | On Going | Restricted tender
3 | Upgradation of Lengpui Airport (Upgradation of Runway to PCN 50) | Phy in % Fin in lakh | 9100 | 01.12.2025 | 31.03.2026 | 78% | 6304.2 | 7% |  | 85% | 6304.2 | On Going | Restricted tender
MoRTH
1 | Short Term Maintenance Contract on NH-44A/108 Between km 16.670 to km 46.000 in the state of Mizoram. (Job No. RW/GHT/GHT/STMC/MZ/25-26/1) | Phy in % Fin in lakh | 387.79 | 05.12.2025 | 04.12.2026 | 82.55% | 271.7 | 7.45% |  | 90% | 271.7 | On Going | Open Tender
2 | Short Term Maintenance Contract on NH-44A/108 Between km 46.000 to km 84.350 in the state of Mizoram. (Job No. RW/GHT/GHT/STMC/MZ/25-26/2) | Phy in % Fin in lakh | 383.18 | 05.12.2025 | 04.12.2026 | 74.63% | 285.21 | 16.37% |  | 91% | 285.21 | On Going | Open Tender
3 | Short Term Maintenance Contract on NH-44A/108 Between km 84.350 to km 114.618 in the state of Mizoram. (Job No. RW/GHT/GHT/STMC/MZ/25-26/3) | Phy in % Fin in lakh | 349.8 | 05.12.2025 | 04.12.2026 | 80.23% | 281 | 12.77% |  | 93% | 281 | On Going | Open Tender
4 | Short Term Maintenance Contract on NH-6 (Spur) from km 0.000 to 38.000 in the state of Mizoram (Job No. RW/GHT/STMC/MZ/25-26/4) | Phy in % Fin in lakh | 388.9 | 09.12.2025 | 08.12.2026 | 34% | 130.99 | 8% |  | 42% | 130.99 | On Going | Open Tender
5 | Performance Based Maintenance Contract (PBMC) under National Highway Division-I during 2023-24 on NH-6/54 between km 159/00 to km 178/00 (Length = 19.00 km) in the State of Mizoram. (Job No. 6/54-MZ-2023-24/124) | Phy in % Fin in lakh | 1891.98 | 29.08.2024 | 28.08.2029 | 79.15% | 1513.96 | 0.2% |  | 79.35% | 1513.96 | On Going | Open Tender
6 | One Time Improvement of ByPass Road of Old Alignment of NH-44A(Old) from (i) km 27.500 to km 35.400, (ii) Km 50.220 to 70.100, (iii) 75.00 to Km 91.500, (iv) Km 105.000 to Km 111.000 & Km 111.250 to Km 112.700, (v) Km 120.240 to Km 121.840 in the State of Mizoram | Phy in % Fin in lakh | 48.63 | 11.03.2026 | 10.09.2027 | [6 empty] | Under Mobilization | Open Tender
5054
1 | Resurfacing of Dampui Approach Road | Phy in % Fin in lakh | 72.78 | 31.01.2026 | 28.06.2026 | [6 empty] | On going | Open Tender
2 | Resurfacing of Saiphal Junction to W.Serzawl Road (Length = 4800 rm) and construction of Retaining Wall at Ch.8.500 kn on Sairang-Lengte-Nghalchawm Road | Phy in % Fin in lakh | 94.98 | 31.01.2026 | 28.06.2026 |  |  | 100% |  | 100% |  | On going | Open Tender
3 | Construction of RCC Balcony @ 0.200 km, PCC lined Side Drain and R/Wall @ 0.00 km & 0.010 km of Tuidam Approach Road | Phy in % Fin in lakh | 120.94 | 31.01.2023 | 28.06.2026 |  |  | 5% |  | 5% |  | On going | Open Tender
Sr. Executive Engneer, PWD., National Highway Division-I Aizawl : Mizoram

## NH - II
MONTHLY PROGRESS REPORT OF NH-150 FOR THE MONTH OF MARCH 2026
Sl No | Name of Scheme | Approved cost (in lakh) | Date of Comenciment | Target Date of Completion | Cummulative Progress at the end of last Month |  | Achievement of works during the Month |  | Overall cummulative achievement |  | Remarks
| Name of Project |  |  |  | Phy (in %) | Fin (in lakh) | Phy (in %) | Fin (in lakh) | Phy (in %) | Fin (in lakh)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
MoRTH
1 | Construction of 2 laning with paved shoulder flexible Pavement from Km 42.80 to Km 60.30 of NH- 150 road during 2016-17 within Mizoram State under NH(O) Scheme. | 20594.82 | 29.11.2017 | 22.05.2021 | 100% | 14000 | 0% | 0 | 100% | 14000 | Work under Defect Liability period
2 | Reconstruction of single lane pavement from Km 130.00 to Km 140.00 on NH-150 in the State of Mizoram on EPC Mode (Job No. 150/MZ/2019-20/119) | 3440.95 | 23.11.2020 | 26.05.2023 | 100% | 2441.16 | 0% | 0 | 100% | 2441.16 | Work under Defect Liability period
3 | Consultancy Services for Project Management including Preparation of Feasibility Study/Detailed Project report for two laning with Paved Shoulders of stretches from Km 0/00 to Km 42/80 and from Km 60/00 to Km 140/00 on NH-150 NH(O) Package No. DPR/MZ/NER/2015/13 | 166.03 | 24.06.2017 | 20.05.2018 | 80% | 39.18 | 0% | 0 | 80% | 39.18 | 3rd RA bill in Process
4 | Short Term Maintenance Contract for NH-6 (150 to 180/000 Kmp) i.e : 30 length for the year 2024-25 under National Highway Division- II, Aizawl in the state of Mizoram. (Job No.RW/GHT/NH-6/MZ/STMC/MZ/2024-25/3) | 116.03 | 20.12.2024 | 19.12.2025 | 100% | 106.55 | 100% | 9.48 | 100.1% | 116.03 | Works Completed on 19.12.2025
5 | One Time Improvement of Old alignment fron Km 42.80 to 60.30 of NH-2 (Old NH-150) by passed by the new alignment in the State of Mizoram | 767.5 | 04.10.2024 | 04.10.2025 | 100% | 649.14 | 100% | 0 | 100% | 767.5 | Works physically Completed on 28.2.2026
6 | Short Term Maintenance Contract for NH-2 from Km 97.200 to Km 140.00 (Old chainage from Km 42.800 to Km 0.00) in the State of Mizoram. (Job No.RW/GHT/STMC/MZ/2025-26/6) | 192.82 | 2025-12-09 | 2026-12-08 | 7.76% | 14.96 | 46.87% | 90.38 | 54.63% | 105.34 | Work in progress
7 | Short Term Maintenance Contract for NH-2 From km 10.000 to km 79.900 (OLD CHAINAGE FROM Km 130.000 TO Km 60.300) in the state of Mizoram. (Job No: RW /GHT/STMC/MZ/25-26/5) | 383.29 | 2025-12-09 | 2026-12-08 | 9.38% | 30.78 | 72.97% | 281.66 | 82.35% | 312.44 | Work in progress
Sr.Executive Engineer,PWD
National Highway Division - II
Aizawl : Mizoram

## NH-III
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL, 2026
Name of Division : National Highway Division-III, Thingdawl, Mizoram
Source of funding : MORTH/NH | [12 empty] | Rs in Lakh
Sl No | Name of Work/Project | Unit | Approved Cost (Rs in Lakh) | Date of Commencement | Target Date of Completion | Cumulative Progress at the end of last month |  | Achievement of works during the month |  | Overall Cumulative achievement |  | Fin (%) | Remarks | Mode of Contract | agg.amt
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Strengthening/Construction/Widening to 2-lane from km 89/00 to km 105/00 of NH-154 (New NH-6) under NH Division III in the state of Mizoram for the year 2022 – 23 (Length = 16 Km ) | Km | 8681 Lakhs | 04.09.2023 | 04.03.2025 | 99.89% | 5247.03 | 0% | 0 | 99.89% | 5247.03 | 98.81% | Work in Progress | EPC | 5310
2 | Strengthening of NH-154( New NH-06) between km 105.00 and Km 119.00 including bridge repair in the state of Mizoram | Km | 2753.00 lakh | 30.06.2025 | 31.05.2026 | 10.42% | 0 | 2.2% | 124.88 | 12.62% | 124.88 | 7.83% | Work in slow progress | EPC | 1595
3 | Short Term Maintenance Contract on NH - 306A from km 0.00 to Km 10.00 & from Km 33.00 to Km 45.00 in the State of Mizoram ( Job No. RW/GHT/STMC/MZ/25-26/8) | Km | 443.23 lakh | 09.12.2025 | 08.12.2026 | 18% | 0 | 5% | 0 | 23% | 0 | 0% | Work in progress | STMC | 346.28
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL, 2026
Name of Division : National Highway Division-III, Thingdawl, Mizoram
Source of funding : NABARD | [10 empty] | Rs in Lakh
Sl No | Name of Work/Project | Unit | Approved Cost (Rs in Lakh) | Date of Commencement | Target Date of Completion | Cumulative Progress at the end of last month |  | Achievement of works during the month . |  | Overall Cumulative achievement |  | Fin (%) | Remarks | Mode of Contract | Agg.Amt
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 1
1 | Upgradation of Road from Meidum to Hortoki Phase-I (Km 0.00 to Km 9.10) | Km | 4445 Lakhs | 26.05.2020 | 26.11.2021 1st EOT=211 days (21.11.2021-20.06.2022) 2nd EOT=375 days (21.06.2022-30.06.2023) 3rd EOT=243 days (30.06.2023-28.02.2024) 4th EoT=90 days (20.2,2024-28.5.2024) | 100% | 4356.17 | 0% | 0 | 100% | 4356.17 |  | completed | Item Rate
1 | Construction of road from Khamrang to Selesih Phase-I (Length =11.00 Kms) Group-A (0/00 to 3/600 Km) | Km | 6583.18 | 08.02.2021 | 08.08.2022 1st EOT=184 days (upto 08.02.2023, 2nd EOT= 150 days (upto 08.07.2023) | 83.33% | 388.92 | 0% | 0 | 83.33% | 388.92 |  |  | Item Rate
2 | Construction of road from Khamrang to Selesih Phase-I (Length =11.00 Kms) Group-B (3/60 to7/200 Km) | Km |  | 08.02.2021 | 08.08.2022 1st EOT=184 days (upto 08.02.2023; 2nd EOT=150 days (wef 09.02.2023- 08.07.2023) | 88.89% | 704.4 | 0% | 0 | 88.89% | 704.4 |  |  | Item Rate
3 | Construction of road from Khamrang to Selesih Phase-I (Length =11.00 Kms) Group-C (7/200 to 11/00 Km) | Km |  | 08.02.2021 | 08.08.2022 1st EOT=184 days (upto 08.02.2023; 2nd EOT=150 days (wef 09.02.2023-08.07.2023) | 47.78% | 317.84 | 0% | 0 | 47.78% | 317.84 |  | Incorrect figure i.e Rs. 354.48 lakh was shown inadvertently for expenditure of the work from July,2025 onwards whereas the correct figure would have been Rs. 317.84. Rectification has been made from the month of March 2026. | Item Rate
4 | Construction of road from Khamrang to Selesih Phase-I (Sh: Construction of Rigid Pavement from 7/00 to 11/00 Kmp = 4.00 kms) | Km |  | 16.08.2022 | EoT = 336 days upto 18.02.2026 | 40% | 432.6 | 5% | 0 | 45% | 432.6 |  |  | Item Rate
| Construction of road from Khamrang to Selesih Phase-I (Contingency ) = | [9 empty] | 47.79
5 | Construction of road from Khamrang to Selesih Phase-II Group-1 (11/00 to 22/00 Km) | Km |  | 08.11.2021 | 08.05.2023 1st EOT=210 days (wef 09.05.2023- 04.12.2023 | 22.15% | 664.75 | 0% | 0 | 22.15% | 664.75 |  |  | Item Rate
6 | Construction of road from Khamrang to Selesih Phase-II Group-2 (22/00 to 25/00 Km) | Km |  | 22.11.2021 | 22.11.2022 1st EOT=90 days (upto 20.02.2023); 2nd EOT=90 days (wef 21.02.2023-21.05.2023); 3rd EOT=90 days (22.05.2023-19.08.2023) | 62.88% | 386.28 | 0% | 0 | 62.88% | 386.28 |  |  | Item Rate
7 | Construction of road from Khamrang to Selesih Phase-II Group-3 (25/00 to 28/00 Km) | Km |  | 11.11.2021 | 11.11.2022 1st EOT=104 days (upto 24.02.2023); 2nd EOT=90 days (wef 10.02.2023-11.05.2023) 3rd EOT=90days (Wef 12.05.23-09.08.2023) | 42.96% | 262.85 | 0% | 0 | 42.96% | 262.85 |  |  | Item Rate
8 | Construction of road from Khamrang to Selesih Phase-II (Sh: - Construction of Rigid Pavement from 11/00 to 19/00 Kmp = 8.00 kms) Group A | Km |  | 26.08.2023 | 26.08.2025 | 0% | 0 | 0% | 0 | 0% | 0 |  |  | Item Rate
9 | Construction of road from Khamrang to Selesih Phase-II (Sh: - Construction of Rigid Pavement from 19/00 to 28/00 Kmp = 9.00 kms) Group B | Km |  | 26.08.2023 | 26.08.2025 | 0% | 0 | 0% | 0 | 0% | 0 |  |  | Item Rate
Construction of road from Khamrang to Selesih Phase-II (Contingency ) = | [10 empty] | 62.54
Sr.Executive Engineer,PWD., National Highway Division-III, Thingdawl : Mizoram

## PD -I
MONTHLY PROGRESS REPORT UNDER EXECUTIVE ENGINEER, PROJECT DIVISION- I, PWD FOR APRIL 2026
Sl. No. | Name of Scheme | Unit | Approved Cost (in lakhs) | Date of Commencement | Target date of completion | Cummulative progress at the end of last month |  | Achievement of work during the month |  | Overall cummulative achievement |  | Remarks | Mode of Tender
| Name of Work/Project |  |  |  |  | Phy (%) | Fin (₹) | Phy (%) | Fin (₹) | Phy (%) | Fin (₹)
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) | (10) | (11) | (12) | (13) | (14)
A. NEC
1 | C/o of Patient Lodging at Mawdiangdiang near NEIGRIMS, Shillong | 1 | 419.67 | 9.9.21 | 9.9.2025 (Revised) | 100% | 409.18 |  | 0 | 100% | 409.18 | EOT upto 9.9.25 | Item rate
2 | Co/ Veterinary Information and Resource Centre at Aizawl | 1 | 339.25 | 25.9.23 | 25.9.25 | 100% | 339.07 |  |  | 100% | 339.0672 |  | Item rate
3 | C/o Aizawl Institute of Arts & Music for the NER, Tuivamit Tlang, Aizawl | 1 | 590.23 | 4.9.23 | 4.9.25 | 95% | 621.22 | 3% |  | 98% | 621.221 |  | Item rate
4 | Establishment of Central Medical Warehouse at Aizawl, Mizoram | 1 | 1101.11 | 14.8.23 | 14.8.25 | 52% | 650 | 1% |  | 53% | 650 |  | Item rate
5 | Infrastructure Development of Biotechnology Cell in Mizoram (C/O Building at MINECO | 1 | 188.66 | 10.7.23 | 10.1.25 | 45.2% | 69.55 | 0.2% | 0 | 45.4% | 69.55 | EOT upto 22.10.25 | Item rate
B. SASCI
6 | C/o Central Medical Warehouse at ZMC, Approach Road (SH: Approach Road) | 1 | 150 | 16.12.23 | 16.12.24 | 66% | 47.428 | 0% | 0 | 66% | 47.428 |  | Item rate
7 | C/o FCS&CA 1500 MT Capacity Godown at Sairang | 1 | 921.07 | 7.4.23 | 7.4.26 | 92% | 207.6424 | 1% | 0 | 93% | 207.6424 |  | Item rate
8 | Constn. of Govt. Staff Qtrs. (Block-C) at DIET Complex, Chaltlang. | 1 | 544 | 29.4.23 | 29.10.25 | 96% | 450.0945 | 4% | 0 | 100% | 450.0945 |  | Item rate
9 | Construction of E-in-C, PHED Office at MINECO, Aizawl | 1 | 796 | 26.6.25 | 26.6.26 | 12% | 0 | 7% | 0 | 19% | 0 |  | Item rate
10 | Vertical Extension of Mizoram Upa Pawl Hqr. Building for Community Hall & Office at Khatla, Aizawl, Mizoram | 1 | 200 | 26.6.25 | 26.6.26 | 41% | 34.2476 | 0% | 0 | 41% | 34.2476 |  | Item rate
11 | Construction of Examination Hall at MPSC Campus | 1 | 1092 | 26.6.25 | 26.6.26 | 12% | 87.5174 | 5% | 0 | 17% | 87.5174 |  | Item rate
12 | Construction of Market Building at Vaivakawn, Aizawl | 1 | 2535 | 5.6.25 | 5.6.26 | 5% | 35.99 | 5% |  | 10% | 35.9922 | Work in progress | Item rate
13 | Construction of MLA Hostel at Tuikual, Aizawl | 1 | 2679 | 14.8.25 | 14.8.26 | 1.9% | 0 | 0.1% | 0 | 2% | 0 |  | Item rate
14 | Construction of Government Residential Quarter Type-V (4 units) at new Secretariat Complex, Khatla | 1 | 692 | 25.3.2025 | 25.3.2026 | 38% | 82.6 | 1% |  | 39% | 82.6015 |  | Item rate
15 | Construction of Government Residential Quarter Type-VI (4 units) at new Secretariat Complex, Khatla | 1 | 849.66 | 28.3.2025 | 28.3.2026 | 38% | 98.0032 | 1% | 0 | 39% | 98.0032 |  | Item rate
16 | Construction of Working Women Hostel, ITI Veng, Aizawl | 1 | 1448.36 | 8.4.2025 | 8.4.2026 | 33% | 272.26 |  |  | 33% | 272.2561 |  | Item rate
17 | Construction of Integrated Office Complex at MINECO, Aizawl | 1 | 6000 | 23.4.2025 | 23.4.2026 | 22% | 416.22 | 3% |  | 25% | 416.2227 |  | Item rate
18 | Modernization of Govt Industrial Training Institute (ITI), Aizawl | 1 | 2500 | 28.4.2025 | 28.4.2026 | 40% | 492.42 | 5% |  | 45% | 495.4188 |  | Item rate
19 | Construction of Durbar Hall & Personal Branch of Raj Bhavan | 1 | 682.7 | 16.7.2025 | 16.7.2026 | 23% | 68.8758 | 2% | 0 | 25% | 68.8758 |  | Item rate
20 | Construction of Quarters, Barrack & Vertical Extension of DRC Office, Silchar & Sewer line at Mizoram House, Guwahati | 1 | 331 | 23.7.2025 | 23.7.2026 | 27% | 0 | 1% | 0 | 28% | 0 |  | Item rate
21 | Construction of AMC Building at Aizawl, Mizoram | 1 | 5000 | 25.04.26 | 25.04.26 | 25% | 120 | 3% |  | 28% | 120 |  | Item rate
22 | Construction of State Emergency Operation Centre (SEOC) at MINECO | 1 | 1850 | 13.5.25 | 13.5.26 | 15.2% | 208.42 | 0.6% |  | 15.8% | 208.4242 |  | Item rate
23 | Construction of Working Women Hostel, Khatla | 1 | 2972 | 24.4.25 | 24.4.26 | 23.3% | 306.34 | 0.4% |  | 23.3% | 306.3356 |  | Item rate
24 | Construction of Building for Additional Classroom at J. Thankima College, Aizawl | 1 | 984 | 4.7.25 | 4.7.26 | 4% | 0 | 4% | 0 | 8% | 0 |  | Item rate
25 | Re-construction of Central Jail, Aizawl | 7 | 1329 | 16.5.25 | 16.5.26 | 26.7% | 180.94 | 6.7% |  | 33.4% | 180.9356 |  | Item rate
| a. Vertical extension of male ward |  |  |  |  | 35.1% |  | 12.9% |  | 48%
| b. Superintendent Quarters |  |  |  |  | 65.6% |  | 15.8% |  | 81.4%
| c. Vertical extension of Convict Women in Women Jail |  |  |  |  | 14.9% |  | 0.2% |  | 15.1%
| d. Toilet at UTP Ward Duty Post (Women Prison) |  |  |  |  | 36.1% |  | 15% |  | 51.1%
| e.Male Kitchen & Dining Hall |  |  |  |  | 23.1% |  | 6.1% |  | 29.2%
| f. New Male Ward |  |  |  |  | 18.9% |  | 1.9% |  | 20.8%
| g. Medical Inspection Building |  |  |  |  | 16.9% |  | 0.4% |  | 17.3%
| h. Administration Building |  |  |  |  | 2.8% |  | 1.9% |  | 4.7%
26 | Construction of New Campus for Govt. Aizawl West College Building | 2 |  |  |  | 14.5% | 430.9094 | 5% | 0 | 19.5% | 430.9094 |  | Item rate
| a. Administrative Building |  | 697 | 9.5.25 | 9.5.26 |  | 115.6684 |  | 0 |  | 115.6684
| b. Academic Building) |  | 2347 | 9.5.25 | 9.5.26 |  | 315.241 |  | 0 |  | 315.241
27 | Vertical Extension of Chief Controller of Accounts Office Main & Annex Building | 1 | 786 | 26.8.2025 | 26.8.2026 | 1.5% | 40 | 1% |  | 2.5% | 40.0003 |  | Item rate
28 | Construction of Bru Student Hostel at Tahnril | 1 | 415 | 1.7.2025 | 1.7.2026 | 7.5% | 40.76 | 10.3% |  | 17.8% | 40.7607 |  | Item rate
| Construction of Deputy Speaker's Bungalow at Aizawl, Mizoram | 1 | 302 | 26.2.2026 | 26.2.2027 |  |  | 0.5% |  | 0.5% |  |  | Item rate
| Construction of Market & Parking at Chawnpui near BCM Church, Chawnpui, Aizawl | 1 | 220 | 5.3.2026 | 5.3.2027 |  |  | 0.5% |  | 0.5% |  |  | Item rate
C. SEDP
29 | Construction of High Court Parking Building at MINECO | 1 | 1960 | 2.7.20 | 29.8.24 | 100% | 1876.89 | 0% |  | 100% | 1876.8943 | EOT upto 17.5.2025 | Item rate
D. NABARD
30 | C/O 24 Warehouses with associated Infrastructure in 23 locations in Mizoram under NABARD (Group-II Zuangtui/ Sairang) | 1 | 485.94 | 17.7.23 | 17.7.2025 | 99.5% | 360.31 | 0% |  | 99.5% | 360.3148 |  | Item rate
Executive Engineer, PWD
Project Division-I
Aizawl, Mizoram

## PD-II
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL, 2026
Name of Division: Project Division-II, P.W.D
Sl.No. | Name of Schemet | Unit | Approved cost (Rs.in lakh) | Date of Commence-ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Mode of Tender | Remarks
| Name of Work/Project |  |  |  |  | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | . | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 14 | 13
NABARD
1 | Construction of 24 Warehouses with associated Infrastructure in 23 locations in Mizoram Group-I i) Construction of Warehouse and other amenities at Bairabi (1000 MT) | % | 316.55 | 17.07.2023 | (O)17.07.2025 (R)31.10.2025 | 100% | 316.38 | 0% | 0 | 100% | 316.38 | Item Rate | Civil Works Completed Electrification yet to start
| ii) Construction of Warehouse and other amenities at Marpara (500 MT) | % | 235.73 | 17.07.2023 | (O)17.07.2025 (R)07.11.2025 | 100% | 234.95 | 0% | 0.78 | 100% | 235.73 | Item Rate | Work Completed
| iii) Construction of Warehouse and other amenities at Sialsuk (200 MT) | % | 171.09 | 17.07.2023 | (O)17.07.2025 (R)11.01.2026 | 100% | 170.42 | 0% | 0.5 | 100% | 170.92 | Item Rate | Work Completed
| iv) Construction of Warehouse and other amenities at Zawlnuam (200 MT) | % | 176 | 17.07.2023 | (O)17.07.2025 (R)30.11.2025 | 100% | 175.03 | 0% | 0.97 | 100% | 176 | Item Rate | Work Completed
| v) Construction of Warehouse and other amenities at Kanhmun (200 MT) | % | 175.8 | 17.07.2023 | (0)17.07.2025 (R)30.11.2025 | 100% | 175.03 | 0% | 0.77 | 100% | 175.8 | Item Rate | Work Completed
2 | Construction of 24 Warehouses with associated Infrastructure in 23 lacations in Mizoram Group-IX i) Construction of Warehouse and other amenities at Phuldungsei (200 MT) | % | 175.81 | 17.07.2023 | (O)17.07.2025 (R)10.11.2025 | 100% | 174.93 | 0% | 0.88 | 100% | 175.81 | Item Rate | Work Completed
NEC
1 | Construction of Market Building at West Phaileng, Mamit District. | % | 278.25 | 22.08.2023 | 22.08.2025 | 98.5% | 208.69 | 0.5% | 15 | 99% | 223.69 | Item Rate | Work in Progress (EOT under process)
2 | Construction of Fish Farmers Training Centre at Lengpui | % | 924.32 | 20.06.2025 | 20.06.2027 | 37% | 610.71 | 3% | 0 | 40% | 610.71 | Item Rate | Work in Progress. Secured Advance Granted Rs. 243.00 lakh
NESIDS
1 | Construction of 100 Bedded District Hospital at Kolasib. | % | 2200 | 23.09.2022 | ( O) 23.09.2024 (R1) 13.10.2025 (R2) 28.02.2026 | 94% | 1859.41 | 1% | 0 | 95% | 1859.41 | EPC | Work in Progress. EOT under process
CSS
1 | Construction of Fast Track Court Building at Kolasib. | % | 1799.85 | 20.09.2022 | (O) 20.09.2024 (R1) 18.02.2025 (R2) 31.05.2025 (R3) 31.07.2025 (R4)12.12.2025 | 100% | 1257.92 | 0% | 0 | 100% | 1257.92 | Item Rate | Civil Works Completed Electrification yet to start
ICMR
1 | Construction of Model Rural Health Research Unit at Lungtian Ram, Aibawk. | % | 207.5 | 21.09.2023 | 21.03.2025 | 100% | 207.5 | 0% | 0 | 100% | 207.5 | Item Rate | Work Completed
SASCI
Work under SASCI 2024 - 2025 Part - I (Untied)
1 | Re-Construction of District Prison at Mamit | % | 453.37 | 14.05.2025 | 14.05.2026 | 45% | 188.5 | 10% | 0.31 | 55% | 188.81 | Item Rate | Work in Progress
2 | Re-Construction of District Prison at Kolasib | % | 751.03 | 27.05.2025 | 27.05.2026 | 70% | 230.13 | 2% | 66.78 | 72% | 296.91 | Item Rate | Work in Progress
Work under SASCI 2024 - 2025 Part - V
1 | Contruction of Civil SDO Qrts Type - IV at Kawnpui | % | 78.08 | 15.05.2025 | 15.5.2026 | 75% | 38.67 | 5% | 10.47 | 80% | 49.14 | Item Rate | Work in Progress
2 | Contruction of Civil SDO Qrts Type - IV at Bairabi | % | 82.32 | 15.05.2025 | 15.5.2026 | 100% | 67.65 | 0% | 0 | 100% | 67.65 | Item Rate | Civil Works Completed Electrification yet to start
3 | Construction of Directorate of Economics & Statistics Office at MINECO, Aizawl | % | 207 | 30.04.2025 | 30.04.2026 | 55% | 100 | 10% | 0 | 65% | 100 | Item Rate | Work in Progress
4 | Upgradation of District Research Office at Kolasib | % | 24.03 | 20.08.2025 | 20.08.2026 | 100% | 22.05 | 0% | 0 | 100% | 22.05 | Item Rate | Work Completed
5 | Upgradation of District Research Office at Mamit | % | 71.37 | 20.08.2025 | 20.08.2026 | 35% | 20 | 10% | 0 | 45% | 20 | Item Rate | Work in Progress
Work under SASCI 2024 - 2025 Part - VII (A)
1 | Contruction of Revenue Staff Quarters (Type - II & III) at Kolasib | % | 192.18 | 11.08.2025 | 11.08.2026 | 45% | 60 | 5% | 0 | 50% | 60 | Item Rate | Work in Progress
2 | Construction of DC Revenue (SO) Office at Mamit | % | 450 | 11.08.2025 | 11.08.2026 | 0% | 0 | 0% | 0 | 0% | 0 | Item Rate | Work yet to be started
3 | Re- Construction of DC Office Complex at Mamit | % | 1000 | 21.07.2025 | 21.07.2026 | 0% | 10.91 | 0% | 0 | 0% | 10.91 | Item Rate | Work yet to be started
Work under SASCI 2024 - 2025 Part -X
1 | Contruction of Working Women Hostel at ZMC / H Falkawn, Mizoram | % | 2634.06 | 14.05.2025 | 14.05.2026 | 29% | 554.26 | 4% | 0.5 | 33% | 554.76 | Item Rate | Work in Progress Secured Advance Granted for Rs. 213.55 lakh
2 | Contruction of Working Women Hostel at Thenzawl | % | 1100 | 15.05.2025 | 15.05.2026 | 27% | 277.95 | 2% | 5.32 | 29% | 283.27 | Item Rate | Work in Progress Secured Advance Granted for Rs. 104.91 lakh
Work under SASCI 2025 - 2026 Part -I
1 | Construction of Hlimen & Saikhamakawn Community Hall | % | 500 | 09.03.2026 | 09.03.2027 | 0% | 0 | 0% | 0 | 0% | 0 | Item Rate | Work just started
Deposit Work
1 | Construction of Settlement Officer Quarters (Type-IV) at Kolasib | % | 66.87 | 1.10.2025 | 1.10.2026 | 45% | 0 | 10% | 14.63 | 55% | 14.63 | Item Rate | Work in Progress
HRDEM (MoHFW)
1 | Construction of National Emergency Life Support (NELS) at ZMC/H, Falkawn | % | 140 | 20.01.2026 | 20.01.2027 | 10% | 0 | 2% | 17.87 | 12% | 17.87 | Item Rate | Work in progress
Sr. Executive Engineer, PWD.,
Project Division-II, Aizawl

## PD- III
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Gov't Serchhip College ( Sh: Administrative Block) | % | 650 | 27.2.2023 | 15.10.2025 | 99.5% | 245.67 | 0.1% | 0 | 99.6% | 245.67 | Work in Progress | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Const. of Football ground and volleyball court at Vapar, Selam, tualcheng, Hnahla. Hmunhmeltha | % | 203 | 13.10.2023 | 13.10.2024 | 100% | 99.3 | 0% | 0 | 100% | 99.3 | Work completed | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Const. of Khawbung futsal ground, gallery, Roofing, Lighting & Laying of Artificial Turf | % | 255.5 | 14.10.2023 | 7.2.2025 | 100% | 114.93 | 0% | 0 | 100% | 114.93 | Work completed | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Const. of Community Hall at Dulte & Chhawrtui | % | 271 | 13.10.2023 | 02.03.2025 | 100% | 139.73 | 0% | 0 | 100% | 139.73 | Work completed | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Development of Community Centre at Zotlang, Champhai (Sh: Cons of Market Building cum community Hall & Futsal Ground) | % | 215 | 14.10.2023 | 7.2.2025 | 100% | 89.62 | 0% | 0.36 | 100% | 89.98 | Work completed | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Additional works for const. of General Nursing Midwifery (GNM) hostel and Nursing Hostel at champhai | % | 438 | 13.10.2023 | 7.2.2025 | 100% | 264.07 | 0% | 0 | 100% | 264.07 | Work completed | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Const of Public Playground at Keitum, Lungchhuan | % | 250 | 13.10.2023 | 13.10.2024 | 100% | 97.38 | 0% | 0.12 | 100% | 97.5 | Work completed | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Const. of Gov't Building at Serchhip District (Sh: PWD staff qtrs, Extension of Gov't Serchhip College and Kitchen cum Dining at PTS, Thenzawl, Mizoram) | % | 362 | 13.10.2023 | 18.04.2025 | 100% | 308.84 | 0% | 0 | 100% | 308.84 | Work completed | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Const of Community Resource Center at Baktawng and Chhuanthar | % | 350 | 13.10.2023 | 13.10.2024 | 100% | 139.9 | 0% | 0.1 | 100% | 140 | Work completed | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OFAPRIL 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Const of Community Hall at Khawzawl Vengthar, Arro Village, Khawzawl Dinthar and Khawhai South | % | 209 | 13.10.2023 | 13.10.2024 | 100% | 79.25 | 0% | 0 | 100% | 79.25 | Work completed | PWD Form - 8
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Gov't Quarters (General pool) under SASCI 2024 - 2025 at Serchhip (1299.68 lakhs) | % | 344.74 | 24.4.2025 | 24.4.2026 | 68% | 153.6 | 5% | 0 | 73% | 153.6 | Work in progress | -
a) Type - IV & III Quarters (Design - A) at P & E Veng (Treasury Department Site)
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Gov't Quarters (General pool) under SASCI 2024 - 2025 at Serchhip (1299.68 lakhs) | % | 296.54 | 24.4.2025 | 24.4.2026 | 69% | 127.69 | 5% | 2.26 | 74% | 129.95 | Work in progress | -
b) Type - IV & III Quarters (Design - B) at P & E Veng ( Treasury Department Site)
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Gov't Quarters (General pool) under SASCI 2024 - 2025 at Serchhip (1299.68 lakhs) | % | 351.94 | 24.4.2025 | 24.4.2026 | 65% | 160.39 | 2% |  | 67% | 160.39 | Work in progress | -
c) Type - IV & III Quarters (Design - A) at P & E Veng ( Soil & Water Conservation Department Site)
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Gov't Quarters (General pool) under SASCI 2024 - 2025 at Serchhip (1299.68 lakhs) | % | 306.46 | 24.4.2025 | 24.4203 | 69% | 143.39 | 4% |  | 73% | 143.39 | Work in progress | -
d) Type - IV Quarters ( 3 Units) at Hospital Complex, Serchhip, Mizoram
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Circuit House under DC Office (SH: Construction of Circuit House at Serchhip) | % | 652 | 16.4.2025 | 16.4.2026 | 57% | 168.74 | 4% | 94.65 | 61% | 263.39 | Work in progress | -
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Circuit House under DC Office (SH: Construction of Circuit House at Khawzawl) | % | 1000 | 16.7.2025 | 16.7.2026 | 20% | 0 | 3% | 116.09 | 23% | 116.09 | Work in progress | -
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Re-construction of District Jail, Serchhip | % | 372.4 | 8.5.2025 | 8.5.2026
| 1. Repair & Extension of Administrative Building |  |  |  |  | 0% | 50.79 | 0% | 50.72 | 0% | 101.51 | To be done only after Multipurpose Hall is completed and this office is shifted.
| 2. Multipurpose hall & Barrack |  |  |  |  | 39% |  | 0% |  | 39% |  | Work in progress
| 3. Segregation Cell & Vocation Hall |  |  |  |  | 60% |  | 5% |  | 65% |  | Structure completed.
| 4. Guard Duty Post (1 no) |  |  |  |  | 95% |  | 1% |  | 96% |  | Nearly completed.
| 5. Extension of MI Room |  |  |  |  | 20% |  | 30% |  | 50% |  | To be done only after Segregation Cell is completed and this office is shifted.
| 6. Staff Quarters Type-IV |  |  |  |  | 26% |  | 15% |  | 41% |  | Work just started. Delayed due to change of site.
| 7. Repair & Renovation of Male ward-2, 1st floor and Chapel |  |  |  |  | 8% |  | 0% |  | 8% |  | Work in progress
| Overall |  |  |  |  | 39% | 50.79 | 8% | 50.72 | 47% | 101.51
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Re-construction of District Jail, Champhai | % | 826.88 | 16.4.2025 | 16.4.2026 | [7 empty] | -
| 1. Male Ward |  |  |  |  | 0% | 171.46 | 0% | 0 | 0% | 171.46 | To be done only after Female ward is completed and Male prisoners shifted.
| 2. Female Ward |  |  |  |  | 75% |  | 5% |  | 80% |  | Structure completed.
| 3. Main Wall, Separation wall & Duty post |  |  |  |  | 42% |  | 10% |  | 52% |  | Work in progress
| 4. Type-II Quarters Block-I |  |  |  |  | 59% |  | 10% |  | 69% |  | Structure completed.
| 5. Type-II Quarters Block-II) |  |  |  |  | 0% |  | 0% |  | 0% |  | Is being used as Labour camp and site office. To be started after Basement of Bl-I is completd and labours can be shifted.
| Overall |  |  |  |  | 46% | 171.46 | 4% | 0 | 50% | 171.46
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Re-construction of District Jail, Saitual (Sh: Separation Wall (80m)) | % | 45.43 | 29.4.2025 | 29.4.2026 | 72% | 22.26 | 28% |  | 100% | 22.26 | Work in progress | -
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Working Women Hostels(Champhai), Mizoram. | % | 1366 | 8.04.2025 | 8.04.2026 | 17% | 100.93 | 3% | 0 | 20% | 100.93 | Work in progress | -
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Circuit House under DC Office (SH: Construction of Circuit House at Saitual) | % | 640 | 16.4.2025 | 16.4.2026 | 47% | 212.72 | 3% |  | 50% | 212.72 | Work in progress | -
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of DC's Bungalow at Saitual DC Complex, Saitual N | % | 224 | 4.7.2025 | 4.7.2026 | 60% | 0 | 5% | 79.18 | 65% | 79.18 | Work in progress | Restricted Tender
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Revenue Staff Quarters at Serchhip | % | 333.81 | 16.7.2025 | 16.7.2026 | 32% | 53.47 | 5% | 38.86 | 37% | 92.33 | Work in progress | Restricted Tender
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Revenue Staff Quarters at Saitual | % | 198.12 | 23.7.2025 | 23.7.2026 | 21% | 0 | 5% | 23.79 | 26% | 23.79 | Work in progress | Restricted Tender
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Revenue Staff Quarters at Khawzawl | % | 211.19 | 23.7.2025 | 23.7.2026 | 14% | 0 | 1% | 0 | 15% | 0 | Work in progress | -
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of DC Revenue (SO) Office at Champhai, Mizoram | % | 468 | 24.7.2025 | 24.7.2026 | 60% | 169.47 | 10% | 0 | 70% | 169.47 | Work in progress | Restricted Tender
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of SDO ( C ) Office and Quarter at N. Vanlaiphai | % | 189.29 | 4.7.2025 | 4.7.2026 | 88% | 114.39 | 5% | 0 | 93% | 114.39 | Work in progress | Restricted Tender
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of District Drugs Control and Awareness Centre at Serchhip excluding Bypass Road | % | 200 | 13.8.2025 | 13.8.2026 | 37% | 58.28 | 6% |  | 43% | 58.28 | Work in progress | Restricted Tender
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Upgradation of District Research Office at Champhai | % | 45 | 19.8.2025 | 19.8.2026 | 75% | 0 | 1% | 30.33 | 76% | 30.33 | Work in progress | Restricted Tender
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Upgradation of District Research Office at Khawzawl | % | 24.16 | 13.7.2025 | 13.7.2026 | 100% | 0 | 0% | 24.15 | 100% | 24.15 | Work in progress | Restricted Tender
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Upgradation of District Research Office at Serchhip | % | 21.7 | 19.8.2025 | 19.8.2026 | 100% | 10.8 | 0% |  | 100% | 10.8 | Work completed | Restricted Tender
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Upgradation of District Research Office at Saitual | % | 36.9 | 21.8.2025 | 21.8.2026 | 100% | 5.83 |  | 19.17 | 100% | 25 | Work completed | Restricted Tender
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | NLCPR
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Name of work : Construction of Community Hall at various places in Mizoram ( Sh: Const. Of Community Hall at Saitual, Thingsulthliah, Maite, Tualbung, Lungpher, Buhban, Lenchim, Chawrtui and Puilo). | % | 206.49 | 22.2.2012 | 30.11.2019 |  | 195.43 |  |  | 100% | 195.43 | Completed and balance fund of Rs.20.48 (Rs. 16.35 Lakhs NLCPR + Rs. 4.13 Lakhs SMS) awaited for clearing liabilities.
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SPP
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Circuit House at Serchhip | % | 358.18 | - | - | - | - | - | - | - | - | Work not executed due to various reasons. Fund received Rs. 358.18 lakhs is kept at D-III
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SCA/SASCE
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Improvement/Upgradation of Operational/Non-operational facilitiies of Lengpui Airport, (Sh: Renovation of terminal building). | % | 2124 | 10.3.2021 | 19.5.2026 | 99.6% | 1773.36 | 0% | 0 | 99.6% | 1773.36 | Power & Electricity Department seek fund amounting to Rs.3.20 crore from Governmentt of Mizoram for installation of new power supply. Until and unless the new power supply system is completed, work could not be continued. | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF MARCH 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | ECRP - II
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of 50 Bedded critical care block at Champhai District Hospital, Mizoram | % | 1391.86 | 4.8.2023 | 5.9.2026 | 93% | 709.74 | 1% | 5.19 | 94% | 714.93 | Work in Progress | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | NABARD - WIF
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of 24 Warehouses with associated infrastructure in 23 locations in Mizoram under NABARD (Group VII : Teikhang ,Rabung & Dungtlang). | % | 336.53 | 17.7.2023 | 31.3.2026 | [6 empty] | Teikhang Warehouse is inaugurated on 30.04.2023 Civil Works at Rabung Warehouse is compled I/E Work in progress at Dungtlang Warehouse | PWD Form - 8
| i) Construction of 200 MT warehouse at Teikhang |  |  |  |  | 100% | 70.49 | 0% | 0 | 100% | 70.49
| ii) Construction of 200 MT warehouse at Rabung |  |  |  |  | 100% | 70.58 | 0% | 0 | 100% | 70.58
| iii) Construction of 200 MT warehouse at Dungtlang |  |  |  |  | 100% | 81.89 | 0% | 0 | 100% | 81.89
| iv) Construction of staff quarters at Dungtlang |  |  |  |  | 100% | 0 | 0% | 6.68 | 100% | 6.68
| Overall |  |  |  |  | 100% | 222.96 | 0% | 6.68 | 100% | 229.64
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | NABARD RIDF- XXX
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction Of Urban Primary Health Centre at Champhai | % | 176.9 | 7.10.2025 | 7.10.2026 | 3% | 0 | 7% | 0 | 10% | 0 |  | -
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | NABARD RIDF- XXX
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction Of Ngopa CHC | % | 572.8 | 18.05.2026 | 18.05.2027 | 0% | 0 | 1% | 0 | 1% | 0 |  | -
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | NABARD RIDF- XXX
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction Of Kawlkulh PHC | % | 401.03 | 16.12.2025 | 16.12.2026 | 1% | 0 |  | 0 | 1% | 0 |  | -
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SCA to TSS/CSS
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Const of 100 Bedded Dist hospital at Saitual ( Sh: Cons of OPD building at district hospital, Saitual) | % | 200 | 13.10.2023 | 13.10.2025 | 100% | 199.92 | 0% | 0 | 100% | 199.92 | Work completed | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | NEC
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Creation of Passion fruit Processing unit at Cold Storage , New Champhai Mizoram. | % | 185.39 | 23.9.2022 | 24.3.2024 | 100% | 185.39 | 0% | 0 | 100% | 185.39 | Building work completed. Procurement of plants and machineries being taken up by D.C. Champhai. | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | NEC
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Zomi cultural Centre and preservation of historical sites at Champhai | % | 478.69 | 26.9.2022 | 7.2.2025 | 100% | 458.43 | 0% | 0 | 100% | 458.43 | Work completed | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | NEC
Sl no | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Biate Tea Tourism Circuit & Nature camp in Mizoram | % | 369.62 | 9.10.2023 | 31.03.2026 | 97.6% | 342.62 | 0.5% | 0 | 98.1% | 342.62 | Work in progress | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | NEC
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Establishing Mizo cultural heritage centre for protecting the historical and natural heritage of Mizo at Kawlri, Serchhip | % | 486.47 | 16.2.2024 | 16.12.2026 | 74% | 182.46 | 2% |  | 76% | 182.46 | Work in progress | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | NEC
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Auditorium at Bethel Veng Champhai | % | 1443.75 | 16.2.2024 | 17.12.2026 | 59% | 647.98 | 1% |  | 60% | 647.98 | Work in progress | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | NESIDS - OTRI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of 50 Bedded District Hospital Complex and Procurement of equipment at Khawzawl, Khawzawl District, Mizoram | % | 1775 | 11.6.2024 | 11.12.2026 | 77% | 660.75 | 1% | 0 | 78% | 660.75 | Work in progress | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | NESIDS-OTRI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of 50 Bedded District Hospital Complex and Procurement of equipment at Saitual, Saitual District, Mizoram | % | 1696 | 10.6.2024 | 10.12.2026 | 46% | 378.53 | 1% | 0 | 47% | 378.53 | The local NGO's wanted to shift the layout of the hospital main building towards the backside and lowering of the courtyard which will involve additional fund. The matter is brought to Health Department and decision is awaited. Work for quarters only in progress. | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | NESIDS (OTRI)
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Upgradation of Infrastructures in GM Higher Secondary School at Champhai, Mizoram | % | 13.5 | - | - | 0% | 0 | 0% | 0 | 0% | 0 |  | Restricted Tender
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF MARCH 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | NEC
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Upgradation of Sports Infrastructure of Ngopa Playground at Saitual District, Mizoram. | % | 394.15 | 15.3.2025 | 15.9.2027 | 100% | 347.76 | 0% |  | 100% | 347.76 | Work in progress | _
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | NEC
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Our Heritage, Our Treasure at Vangchhia Tourist Spot, Champhai, Mizoram | % | 115.76 | 19.7.2025 | 19.7.2026 | 40% | 30.19 | 6% |  | 46% | 30.19 | Work in progress | _
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | NESIDS
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Improvement/Upgradation of Operational/Non-operational facilities of Lengpui Airport, (Sh: Elevated road with connected components of Terminal Building). | % | 1959 | 30.9.2021 | 25.3.2025 | 100% | 1959 | 0% | 0 | 100% | 1959 | Work completed | Turnkey
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | CSS
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Tourist Lodge at Champhai | % | 328.73 | 9.12.2010 | 30.11.2020 |  |  |  |  | 100% | 300 | Taken over by the Department on Dt.3.8.2021 . LOC amounting to Rs. 30.00 lakh submitted for clearing liaibility. Hence, release of LOC awaited for financial closure.
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | CSS
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Polytechnic at Chhiahtlang | % | 800 | [8 empty] | Only approach road is executed. Out of fund received amount Rs. 300.00 lakhs balance amount of Rs. 196.34 lakhs is kept at D-III
| i) Approach road |  |  | 3.3.2016 | 2.8.2016 |  |  |  |  | 100% | 103.67
ii) Administrative & Academic Block
iii) Hostel Block
iv) Staff Quarter
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | CSS
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Hostel for S.T Girls at Champhai | % | 462.75 | 18.9.2023 | 30.6.2026 | 87.5% | 162.77 | 0% | 0 | 87.5% | 162.77 | Work temporarily halted due to fund problem since May 2025 | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | CSS
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | 10 - Bedded Integrated AYUSH Hospital at Keifang, Saitual District | % | 750 | 13.10.2023 | 7.10.2026 | 83% | 415.15 | 2% |  | 85% | 415.15 | Work in progress | PWD Form - 8 | Secured Advance Check leh angai
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | CSS
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Const of District Court Complex at Vengsang, Champhai. ( Sh: Main Building, phase- I) | % | 4915.35 | 17.10.2023 | 17.10.2026 | 77% | 1795.14 | 1% | 115.06 | 78% | 1910.2 | Work in progress | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | CSR
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of 100 Bedded District Hospital, Block A at Serchhip Mizoram under Powergrid CSR Initiative | % | 2100 | - | - | 30% | 0 | 0.5% | 0 | 30.5% | 0 | Revised DPR submitted to PGIL. Revised agreement to be signed with contractor after Revised DPR is approved by PGCIL. Only Supervision and Monitoring of work is under PWD. | -
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | Fire & Emergency Services Department
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Fire Station Khawzawl | % | 194.38 | - | - | 0% | 0 | 0% | 0 | 0% | 0 |  | Restricted Tender
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | Fire & Emergency Services Department
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Fire Station Saitual | % | 193.46 | - | - | 0% | 0 | 0% | 0 | 0% | 0 |  | Restricted Tender
`
Sr.Executive Engineer, PWD., Project Division - III Aizawl, Mizoram

## Hnahthial
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL, 2026
Name of Division: Hnahthial Division
Sl.No. | Name of Work/Project | Unit | Approved cost (Rs.in lakh) | Date of Commence-ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Mode of Tender | Remarks
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | . | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 14 | 13
Works under 3054 MRFB Maintenance Action Plan 2025-2026 under PWD Hnahthial Division, Hnahthial
1 | Patch repair, Seal Coating and Profile Correction of Road from PWD Office to Nauhruaikawn, Hnahthial | m | 22.28 | 27.10.2025 | 31.03.2026 | 100% |  | 0% |  | 100% | 22.28
2 | Patch repair and resurfacing of NH-54 to Bazarkawn via Kanan Veng at Hnahthial | m | 7.45 | 27.10.2025 | 31.03.2026 | 100% |  | 0% |  | 100% | 7.45
3 | Resurfacing of PWD Office Complex Internal Road and Courtyard, Hnahthial | m | 12.36 | 27.10.2025 | 31.03.2026 | 100% |  | 0% |  | 100% | 12.36
4 | Patch repair and Seal Coating Approach Road to NH-02 (Hnahthial By-Pass Road) Electric Veng Hnahthial | m | 7.68 | 27.10.2025 | 31.03.2026 | 100% |  | 0% |  | 100% | 7.68
5 | Patch repair and resurfacing of Southern High School to Thingsai Road at Hnahthial | m | 19.04 | 27.10.2025 | 31.03.2026 | 100% |  | 0% |  | 100% | 19.04
6 | Resurfacing of Approach Road to PHC Pangzawl | m | 19.22 | 27.10.2025 | 31.03.2026 | 100% |  | 0% |  | 100% | 19.22
7 | Patch repair and Seal Coating from Rohnuna House to Duhthluaii House Hnahthial | m | 10.96 | 27.10.2025 | 31.03.2026 | 100% |  | 0% |  | 100% | 10.96
Works under Annual Plan (5054) during 2025-2026 under PWD Hnahthial Division, Hnahthial
1 | Resurfacing of F.Zachhuma House to CL.Biaka House at S.Vanlaiphai | m | 15.07 | 7.02.2026 | 7.05.2026 | 5% |  | 95% |  | 100% | NIL | Completed | Open
2 | Patch Repair and seal coating of Hnahthial to Thingsai Road | m | 77.67 | 7.02.2026 | 7.08.2026 | 20% |  | 30% |  | 50% | NIL | Not yet completed | Open
SASCI
1 | Construction of PCC Flooring at Various locations viz. (I) Haulawng to Hmuntlang (ii) Melte to Khawiva (iii) Ramrikawn to Pangzawl (iv) Lena Stadium to New Maite.(SH: Ramrikawn to Pangzawl) | % | 58.56 | 2.02.2026 | 2.02.2027 | 61% |  | 3% |  | 64%
2 | Construction of Drain along NH-54 and on different parts within Hnahthial Town, Hnahthial District | % | 240.39 | 2.02.2026 | 2.02.2027 | 65% |  | 2% |  | 67%
| NABARD | (Name of Contractor : Urban Infraprojects Private Limited AE-0310, 1st Floor, Salt Lake, Sector-1 Kolkata -700064)
1 | Construction of Galvanised Steel Truss Bridge over Mat River on Hnahthial to Haulawng Road | Rm | 1447.94 | 1.11.2025 | 31.10.2027 | 25% |  | 3% |  | 28% | 96.68 | Work in progress

## PD - IV
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL, 2026
Name of Division |  | : Project Division - IV
Source of funding |  | : SASCI
Sl. No. | Name of work/project | Unit | Approved cost (Rs. in lakh) | Date of commencement | Target date of completion | Cummulative progress at the end of last month |  | Achievement of works during the month |  | Overall Cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Working Women Hostel (50 Bedded) at Ramhlun Sports Complex, Aizawl. | % | 1400 | 2025-05-14 | 2026-05-14 | 33% | 354.34 | 2% | 1.39 | 35% | 355.73 | Work in progress. | Item rate.
2 | Upgradation of Govt. Hrangbana College, Aizawl, Mizoram. | % | 200 | 2025-07-14 | 2026-07-14 | 100% | 200 | 0% | 0 | 100% | 200 | Work completed on 20.03.2026 | Item rate.
3 | Construction of Retaining Wall and Drainage System in Various Higher Educations Institutions to Mitigate Effects of Cyclonic Storm. | % | 204
| a) Government Aizawl College, Mualpui | % | 38 | 2025-09-15 | 2026-09-15 | 100% | 38 | 0% | 0 | 100% | 38 | Work completed. | Item rate.
| b) Government Mizoram Law College, Luangmual | % | 72 | 2025-09-11 | 2026-09-11 | 80% | 0.69 | 20% | 0 | 100% | 0.69 | Work completed on 20.04.2026. | Item rate.
| c) Mizoram Hindi Training College, Durtlang North | % | 94 | 2025-09-11 | 2026-09-11 | 100% | 94 | 0% | 0 | 100% | 94 | Work completed. | Item rate.
4 | Construction of Revenue Staff Qtr. Complex at Aizawl. | % | 500
| a) Construction of Revenue Staff Quarters at Kawltheihuan, Aizawl | % | 298 | 2026-12-15 | 12/15/2027. | 7% | 0 | 7% | 0 | 14% | 0 | Work in progress. | Item rate.
| b) Construction of Revenue Staff Quarters at College Veng, Aizawl | % | 202 | 2026-01-21 | 2027-01-21 | 0% | 0 | 5% | 0 | 5% | 0 | Work in progress. | Item rate.
4 | Construction of Revenue Staff Qtr. Complex at Aizawl. | % | 500
| a) Construction of Revenue Staff Quarters at Kawltheihuan, Aizawl | % | 298 | 2026-12-15 | 15-12-2027. | 14% | 0 | 22% | 0 | 36% | 0 | Work in progress. | Item rate.
| b) Construction of Revenue Staff Quarters at College Veng, Aizawl | % | 202 | 2026-01-21 | 2027-01-21 | 5% | 0 | 25% | 0 | 30% | 0 | Work in progress. | Item rate.
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL, 2026
Name of Division |  | : Project Division - IV
Source of funding |  | : SASCE
Sl. No. | Name of work/project | Unit | Approved cost (Rs. in lakh) | Date of commencement | Target date of completion | Cummulative progress at the end of last month |  | Achievement of works during the month |  | Overall Cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Multi Utility Centre at Zemabawk, Aizawl, Mizoram | % | 800 | 2022-12-19 | 2026-03-31 | 96.5% | 499.74 | 1% | 0 | 97.5% | 499.74 | Work in progress. | Item rate.
2 | Construction of Solid Waste Management Centre at Hualngohmun, Mizoram (Phase-I) | % | 1664 | 2023-04-07 | 2026-04-15 | 63.5% | 859.69 | 1.5% | 0 | 65% | 859.69 | Work in progress. | Item rate.
3 | Restoration/renovation of DC Office at Aizawl. | % | 2000 | 2025-04-08 | 2026-04-08 | 29% | 199.96 | 1% | 140 | 30% | 339.96 | Work in progress. | Item rate.
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL, 2026
Name of Division |  | : Project Division - IV
Source of funding |  | : Article 275 (1)
Sl. No. | Name of work/project | Unit | Approved cost (Rs. in lakh) | Date of commencement | Target date of completion | Cummulative progress at the end of last month |  | Achievement of works during the month |  | Overall Cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Tribal Hostel at Suangpuilawn, Mizoram. | % | 320 | 2023-08-12 | 2025-07-22 | 76% | 139.9992 | 0% | 0 | 76% | 139.9992 | Work progress hindered due to irregularity in release of fund from Ministry. | Item rate.
2 | Construction of Multipurpose Community Hall at Darlawn, Mizoram. | % | 720 | 2023-08-12 | 2025-08-12 | 63% | 149.8635 | 0% | 0 | 63% | 149.8635 | Work progress hindered due to irregularity in release of fund from Ministry. | Item rate.
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL, 2026
Name of Division |  | : Project Division - IV
Source of funding |  | : NABARD
Sl. No. | Name of work/project | Unit | Approved cost (Rs. in lakh) | Date of commencement | Target date of completion | Cummulative progress at the end of last month |  | Achievement of works during the month |  | Overall Cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of 24 warehouses with associated infrastructure in 23 locations in Mizoram under NABARD (Group V : Zohmun) | % | 170.99 | 2023-07-17 | 17-07-2025 24-12-2025 (1st EOT) | 85% | 124.98 | 15% | 45.33 | 100% | 170.31 | Work Completed. | Item rate.
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL, 2026
Name of Division |  | : Project Division - IV
Source of funding |  | : NEDP
Sl. No. | Name of scheme | Unit | Approved cost (Rs. in lakh) | Date of commencement | Target date of completion | Cummulative progress at the end of last month |  | Achievement of works during the month |  | Overall Cumulative achievement |  | Remarks | Mode of contract
| Name of work/project |  |  |  |  | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Agriculture Growth Centre at Tuikual South, Aizawl. | % | 4555 | 2025-02-10 | 2026-02-10 | 30% | 1330.52 | 1% | 0 | 31% | 685.52 | Work in progress. | Item rate.
Sr. Executive Engineer, PWD
Project Division - IV
Aizawl : Mizoram

## SERCHHIP DIV
PROGRESS REPORT OF NABARD WORKS FOR THE MONTH OF APRIL, 2026
Name of Work :CONSTRUCTION OF LINK ROAD AND LAND IMPROVEMENT AT ZAWLPUI IN THE STATE OF MIZORAM
NABARD
Date of Commencement: 3rd May, 2025 | [7 empty] | Division Serchhip Division
Agreement Amount: Rs. 9,63,30,359.97 | [7 empty] | Period for Completion 18 Months
Name of Contractor:-Evergreen Construction & culsuntancy Khatla, Aizawl
Sl. No. | Name of Work | Unit | As per Agreement/Deviation |  | Progress upto the end of last month |  |  |  | Cum.Prog.Upto the end of this month |  | Remarks
|  |  | Qty | Amount | Physical | Financial | Physical | Financial | Physical | Financial
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Land Improvement | M3 | 124539 | 21669786 | 87050 | 1313717.4 | 25780 |  | 112830 | 1313717.4 | Work in Progress
| Restoration fo Rain cuts | Km | 10.837 | 3531843.57 | 10.837 | 2448695.47 |  |  | 10.837 | 2448695.47
2 | Compaction of Original Ground (Sub-grade) | Km | 10.837 | 1584396 | 10.837 | 1580595 |  |  | 10.837 | 1580595
3 | Granular Sub-Base | Km | 10.837 | 15311275.5 | 10.837 | 14834519.93 |  |  | 10.837 | 14834519.93
4 | Concrete Pavement | Km | 10.837 | 47880734 | 8.672 | 29657927.83 | 1.52 |  | 10.192 | 29657927.8282
5 | Earthen Shoulder | Km | 10.837 | 1765164.38 | 8.45 | 164536.96 | 1.52 |  | 9.97 | 164536.964
| 5 Years Maintenance |  |  | 4587160
| Total : |  |  | 96330359.45 |  | 49999992.59 |  |  |  | 49999992.5922
1 | Contincency |  |  | 2752296
| Quiality Control |  |  | 917432
| Over all Total |  |  | 100000087.45
Over all Physical Progress in Percentage=95%
PROGRESS REPORT OF NABARD WORKS FOR THE MONTH OF APRIL, 2026
Name of Work :IMPROVEMENT OF SERCHHIP(CHAWMKAI) TO ZOTE SOUTH ROAD, SERCHHIP DISTRICT IN THE STATE OF MIZORAM
NABARD
Date of Commencement: 14th May, 2025 | [7 empty] | Division Serchhip Division
Agreement Amount: Rs. 21,80,92,941.13 | [7 empty] | Period for Completion 18 Months
Name of Contractor:-Huapzo Construction & consultancy Services, bawnkawn Shalom, Aizawl
Sl. No. | Name of Work | Unit | As per Agreement |  | Progress upto the end of last month |  | Progress during the month |  | Cum.Prog.Upto the end of this month |  | Remarks
|  |  | Qty | Amount | Physical | Financial | Physical | Financial | Physical | Financial
1 | 2 | 3 | 4 | 5 | 6 | 7 |  | 9 | 10 | 11 | 12
1 | Formation Cutting | Km | 14 | 22273648.36 | 14 | 22272972.35 |  |  | 14 | 22272972.35 | Work in Progress
2 | Compaction of Original Ground (Sub-grade) | Km | 14 | 4620000 | 14 | 4648958.85 |  |  | 14 | 4618958.85
3 | Granular Sub-Base | Km | 14 | 33446000 | 14 | 31055996.62 |  |  | 14 | 31055996.62
4 | WBM – II | Km | 6 | 8045730 |  |  |  |  | 0
5 | WBM – III | Km | 6 | 8197200 |  |  |  |  | 0
6 | Prime coat | Km | 6 | 2079000 |  |  |  |  | 0
7 | Tack coat | Km | 6 | 673200 |  |  |  |  | 0
8 | OGPC | Km | 6 | 6138000 |  |  |  |  | 0
9 | Seal Coat | Km | 6 | 2079000 |  |  |  |  | 0
10 | Concrete Pavement | Km | 8 | 48708000 | 4 | 22812871.5 |  |  | 4 | 22812871.5
12 | Surface Drain | Km | 6 | 13720000 |  |  |  |  | 0
13 | Protection Wall | Rm | 200 | 11297837 | 40 |  |  |  | 40
14 | Lined Side drain | Rm | 6762 | 17484569.315 |  |  |  |  | 0
15 | Culverts, H/P, Minor Bridge | Nos | 28 | 27725827.65 | 2 |  |  |  | 2
16 | Road Furnitures | Nos | 14 | 1219550 | 0
| 5 Years Maintenance |  |  | 10385378.14 | 0
| Total : |  |  | 218092940.46 |  | 80760799.32 |  |  |  | 80760799.32 |  | ,
| Contincency |  |  | 6231227 | [5 empty] | 303700
| Quiality Control |  |  | 2077076
| Over all Total |  |  | 226401243.46 |  | 80760799.32 |  |  |  | 81064499.32
| Over all Physical Progress in Percentage = |  |  | 33.29%
PROGRESS REPORT OF NABARD WORKS FOR THE MONTH OF APRIL, 2026
Name of Work :WIDENING & IMPROVEMENT OF APPROACH ROAD TO PARAGLIDING GROUND AT SERCHHIP
NABARD
Date of Commencement: 8h May, 2025 | [7 empty] | Division Serchhip Division
Agreement Amount: Rs. 3,45,63,310.77 | [7 empty] | Period for Completion 18 Months
Name of Contractor:-Evergreen Construction & culsuntancy Khatla, Aizawl
Sl. No. | Name of Work | Unit | As per Agreement |  | Progress upto the end of last month |  | Progress during the month |  | Cum.Prog.Upto the end of this month |  | Remarks
|  |  | Qty | Amount | Physical | Financial | Physical | Financial | Physical | Financial
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Widening | Km | 4.7 | 1588390.58 | 4.7 | 1433216.78 |  |  | 4.7 | 1433216.78 | Work in Progress
2 | Compaction of Original Ground (Sub-grade) | Km | 4.7 | 123375 | 4.7 | 123375 |  |  | 4.7 | 123375
3 | Granular Sub-Base | Km | 4.7 | 6274422 | 3.78 | 7472934.45 |  |  | 3.78 | 7472934.45
10 | Concrete Pavement | Km | 8 | 24350700 | 3.5 | 8909378 | 1.2 |  | 4.7 | 8909378
16 | Road Furnitures | Nos | 64 | 580551.25 |  |  | 900 |  | 900
| 5 Years Maintenance |  |  | 1645871.94
| Total : |  |  | 34563310.77 |  | 17938904.23 |  |  |  | 17938904.23
Contincency
Quiality Control
Over all Total
Overall physical Progress in % = 100%
PROGRESS REPORT OF NABARD WORKS FOR THE MONTH OF APRIL, 2026
Name of Work :IMPROVEMENT OF KIKAWN TO HMARVENG, SERCHHIP
NABARD
Date of Commencement: 14th May, 2025 | [7 empty] | Division Serchhip Division
Agreement Amount: Rs. 15,51,98,719.23 | [7 empty] | 8
Name of Contractor:-Studio Hamlet, Champhai Vengthlang, Champhai
Sl. No. | Name of Work | Unit | As per Agreement |  | Progress upto the end of last month |  | Progress during the month |  | Cum.Prog.Upto the end of this month |  | Remarks
|  |  | Qty | Amount | Physical | Financial | Physical | Financial | Physical | Financial
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Formation Cutting | Km | 6 | 52027848.88 | 6 | 499.17 |  |  | 6 | 499.17 | Work in Progress
| Compaction of Original Ground (Sub-grade) | Km | 6 | 805500 | 5.5 | 5.95 |  |  | 5.5 | 5.95
| Embankment | Km | 4 | 3420000 | 4 | 25.82 |  |  | 4 | 25.82
2 | Granular Sub-Base | Km | 6 | 14231250 | 3 | 72.15 |  |  | 3 | 72.15
4 | WBM – I | Km | 6 | 7290000 | 3 | 36.93 |  |  | 3 | 36.93
5 | WBM – II | Km | 6 | 7290000 | 3 | 36.93 |  |  | 3 | 36.93
6 | Prime coat | Km | 6 | 2160000
7 | Tack coat | Km | 6 | 1170000
8 | OGPC | Km | 6 | 6120000
| Seal Coat | Km | 6 | 1980000
9 | Earthen shoulder | Km | 6 | 1890000
| Surface Drain | Km | 6 | 900000 |  |  | 2 |  | 2
10 | Protection Wall | Rm | 1605 | 30932668.8 | 130 |  | 109 |  | 239
12 | Lined Side drain | Rm | 4666.85 | 11891072.7
13 | H/P Culvert NP3 | Nos | 12 | 5699963.25 | 2 |  |  |  | 2
| 5 Years Maintenance |  |  | 7390415.2
Total: |  |  |  | 155198718.83 |  | 676.95 |  |  |  | 676.95
| Contincency |  |  |  | 1.21 | 6.2 |  |  |  | 6.2
Quiality Control
Over all Total
Over all Physical Progress in Percentage =34%
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL 2026
NAME OF DIVISION : Serchhip Division
Sl. No | Name of Schemet | Unit | Approved Cost (in lakhs) | Date of Commence- ment | Target date of Completion | Cummulative Progress at the end of last Month |  | Achievement of works during the month |  | Overall Cumulative achievement |  | Remarks | Mode of Tender
| Name of Work/ Project |  |  |  |  | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
SASCI
1 | Estimate for restoration of damage due to cyclone remal |  | 715 | 16.06.2025 | 16.01.2026 | 100% | 596.01 |  |  | 100% | 596.01 | Physically completed
MAINTENACE ACTION PLAN (MAP)
1 | Resurfacing of Appraoch Road to Chhimveng at Serchhip | Km | 11.63 | 21.08.2025 | 31.03.2026 | 100% | 10.47 |  |  | 100% | 10.47 | Completed | Departmental
2 | Resurfacing of Appraoch Road to Tlangnuamt Serchhip | Km | 5.06 | 21.08.2025 | 31.03.2026 | 100% | 4.55 |  |  | 100% | 4.55 | Completed | Departmental
3 | Pothole filling & Resurfacing of IB Peng - IOC at New Serchhip | Km | 16.91 | 21.08.2025 | 31.03.2026 | 100% | 15.22 |  |  | 100% | 15.22 | Completed | Departmental
4 | Path Repair with Premix Carpet with full surface seal coat on AOC to DIET Complex at Serchhip | Km | 22.97 | 21.08.2025 | 31.03.2026 | 100% | 20.67 |  |  | 100% | 20.67 | Completed | Departmental
5 | Construction of V-Shape side drain at Leisang to Sport Complex at Serchhip | Km | 2.91 | 21.08.2025 | 31.03.2026 | 100% | 2.61 |  |  | 100% | 2.61 | Completed | Departmental
6 | Path Repair with Premix Carpet with full surface seal coat on AOC Lane -II | Km | 3.19 | 21.08.2025 | 31.03.2026 | 100% | 2.87 |  |  | 100% | 2.87 | Completed | Departmental
7 | Resurfacing of Vety Ar Farm - Assam Riffle Gate-III at P&E veng,Serchhip | Km | 7.42 | 21.08.2025 | 31.03.2026 | 100% | 6.68 |  |  | 100% | 6.68 | Completed | Departmental
8 | Laying of Base course along Approach Road to Solid Waste Management Centre(PHED) Serchhip District | Km | 12.3 | 21.08.2025 | 31.03.2026 | 100% | 11.07 |  |  | 100% | 11.07 | Completed | Departmental
9 | Path repair of Leng to Sailulak | Km | 20.37 | 21.08.2025 | 31.03.2026 | 100% | 18.33 |  |  | 100% | 18.33 | Completed | Departmental
10 | Path repair of Chekawn to N.Vanlaiphai | Km | 18.69 | 21.08.2025 | 31.03.2026 | 100% | 16.82 |  |  | 100% | 16.82 | Completed | Departmental
Sr. Executive Engineer,PWD
Serchhip Division: Serchhip

## SAITUAL DIV
MONTHLY PROGRESS REPORT FOR THE MONTH OF MARCH 2026
Source of Funding : SASCI-II (2023-2024)
Sl. No | Name of Work Project | Unit | Estimated Amount (in Lakhs) | Cumulative Progress at the end of last month |  | Achievement of works during the month |  | Overall Cummulative achievement |  | Remarks
|  |  |  | Physical (in %) | Financial (in Lakhs) | Physical (in %) | Financial (in Lakhs) | Physical (in %) | Financial (in Lakhs)
1 | 2 | 3 | 4 | 7 | 8 | 9 | 10 | 11 | 12 | 13
I | Improvement of Khawlek - Ratu Road (Length =6.00 Km)
Name of Sub-Head
1 | PCC Flooring between Pu Lalhmuthara house to Govt. Primary School-I Approach road 380 m At Vanbawng | Km | 25 | 100% | 25 |  |  | 100% | 25 | Works Completed | 0
2 | PCC Flooring between Govt. Middle School to Sub Centre 40 m At Daido | Km | 20 | 100% | 20 |  |  | 100% | 20 | Works Completed | 0
3 | PCC Flooring of khaw entered extend-na road 500 m At NE Tlangnuam | Km | 20 | 100% | 20 |  |  | 100% | 20 | Works Completed | 0
4 | Construction of approach road to CC puk (on-going works from SASCI Phase-I) 5 km At Luangpawn | Km | 20 | 100% | 20 |  |  | 100% | 20 | Works Completed | 0
5 | Construction of Link Road Between Sihfa to Tuivawl (Saitluk Link Road) 3 km At Sihfa | Km | 25 | 100% | 21.8358 |  |  | 100% | 21.8358 | Works Completed | 3.1642
6 | Construction of Link road from Buhban to Ramtang Road (1 km laih tawh) - 4 km At Buhban | Km | 20 | 100% | 19.3047 |  |  | 100% | 19.3047 | Works Completed | 0.69532
|  | Km | 130 |  | 126.1405 |  | 0 |  | 126.1405 |  | 97.0311 | 3.8595 | 2.9689
II | Widening, Pavement & Construction of culverts on 3rd Road from Sedaikawn to PWD Kawn, Saitual L= 2.220Kms
Name of Sub-Head
1 | Widening and reconstruction of culverts on 3rd Road from Sedaikawn to PWD Kawn, Saitual | Km | 137.52 | 100% | 137.5194 |  |  | 100% | 137.5194 | Works Completed
|  | Km | 137.52 |  | 137.5194 |  | 0 |  | 137.5194
III | Rigid pavement of Sakeibangla to ZMC via Thingsulthliah Road Thingsulthliah, PCC Pavement = 3.00km, Side drain = 2000m,R/Wall = 10m, Culvert = 2 Nos |  | 55.78
Name of Sub-Head
1 | PCC Flooring of Emau Road to Mangluaia (L) House, Thingsulthliah-I (L=400m) | Km | 27.6 | 100% | 27.6 |  |  | 100% | 27.6 | Works Completed
2 | PCC Flooring of Salem Veng to Aichalkawn road, Thingsulthliah-II (L=350m) | Km | 28.18 | 100% | 28.18 |  |  | 100% | 28.18 | Works Completed
|  | Km | 55.78 |  | 55.78 |  | 0 |  | 55.78
IV | Improvement of Roads and Infrastructures at District Headquarters: Saiha, lawngtlai, Lunglei, Hnahthial, Serchhip, Champhai, Khawzawl, Saitual, Kolasib, Mamit (Departmental)
Name of Sub-Head
| (A) IMPROVEMENT OF SaitualTown Road | Km | 15.5
1 | Pothole & Patch repair on Saitual to Phullen Road. ( 2.00 km ) | Km | 15.5 | 100% | 15.5 |  |  | 100% | 15.5 | Works Completed
|  | Km | 15.5 |  | 15.5 |  |  |  | 15.5
Source of Funding : SASCI (2025-2026)
I | RESTORATION OF DAMAGES DUE TO CYCLONE REMAL UNDER KHAWZAWL, SAITUAL & SERCHHIP DIVISION
1 | Re-Construction of Retaining Wall on E. Phaileng - Suangpuilawn Road - Ch.12.500 Kmp |  | 20.95 | 100% |  |  |  | 100% | 0 | Works Completed
2 | Re-Construction of Retaining Wall on E. Phaileng - Suangpuilawn Road - Ch.15.100 Kmp |  | 14.26 | 100% |  |  |  | 100% | 0 | Work in Progress
3 | Re-Construction of Retaining Wall on E. Phaileng - Suangpuilawn Road - Ch.12.680 Kmp |  | 16.77 | 100% |  |  |  | 100% | 0 | Works Completed
4 | Re-Construction of Retaining Wall on Rulchawm - Mualpheng Road - Ch.5.470 Kmp |  | 2.63 | 100% |  |  |  | 100% | 0 | Works not started
5 | Re-Construction of Retaining Wall on Mualpheng - Maite Road - Ch.19.680 Kmp |  | 6.61 | 100% |  |  |  | 100% | 0 | Works Completed
6 | Construction of Retaining Wall (Formation Collapsed) on Khanpui to Tualbung Road - Ch.14.700 Kmp |  | 20.57 | 100% | 20.5484 |  |  | 100% | 20.5484 | Works Completed
7 | Construction of Retaining Wall (Formation Collapsed) on Khanpui to Tualbung Road - Ch.2.800 Kmp |  | 15 | 100% | 14.9872 |  |  | 100% | 14.9872 | Works Completed
8 | Construction of Retaining Wall (Formation Collapsed) on N. Lungpher to Buhban Road at 3.500 kmp |  | 24.25 | 100% | 24.2241 |  |  | 100% | 24.2241 | Works Completed
9 | Re-Construction of Retaining Wall on E. Phaileng - Suangpuilawn Road - Ch.10.200 Kmp |  | 16.01 | 100% |  |  |  | 100% | 0 | Works Completed
10 | Re-Construction of Retaining Wall on Mualpheng - Maite Road - Ch.9.450 Kmp |  | 3.7 | 100% |  |  |  | 100% | 0 | Works Completed
11 | Re-Construction of Retaining Wall on Mualpheng - Maite Road - Ch.9.620 Kmp |  | 4.87 | 100% |  |  |  | 100% | 0 | Works Completed
12 | Re-Construction of Retaining Wall on Mualpheng - Maite Road - Ch.9.790 Kmp |  | 3.72 | 100% |  |  |  | 100% | 0 | Works Completed
13 | Re-Construction of Retaining Wall on Mualpheng - Maite Road - Ch.14.350 Kmp |  | 15.91 | 100% |  |  |  | 100% | 0 | Works Completed
| TOTAL |  | 165.25 |  | 59.7598 |  | 0 |  | 59.7598 |  | 92.3077
Source of Funding : SASCI-II (2025-2026)
I | RESTORATION OF DAMAGES DUE TO CYCLONE REMAL UNDER SAITUAL DIVISION PART-II
1 | Construction of Retaining Wall at Ch.0.800 Kmp on Phullen to Phuaibuang Road |  | 9.2 | 100% |  |  | 9.19 | 100% | 9.19 | Works Completed
2 | Repair of Damaged Slab Culvert at Ch.12.010 kmp on Phullen to Phuaibuang Road |  | 32.5 | 100% |  |  | 32.492 | 100% | 32.492 | Works Completed
3 | Construction of Retaining Wall at Ch.21.400 kmp on Phullen to Phuaibuang Road |  | 7.5 | 100% | 7.475 |  |  | 100% | 7.475 | Works Completed
4 | Construction of Retaining Wall at Ch.10.800 kmp on Phullen to Zawngin Road |  | 7.5 | 100% | 7.224 |  |  | 100% | 7.224 | Works Completed
5 | Restoration of Sinking Pavement at Ch.26.200 kmp on Phullen to Phuaibuang Road |  | 12.5 | 100% | 11.386 |  |  | 100% | 11.386 | Works Completed
6 | Restoration of Collapse Pavement with Retaining Wall at Ch.11.350 kmp on E. Phaileng to Suangpuilawn Road |  | 13.2 | 100% | 13.177 |  |  | 100% | 13.177 | Works Completed
7 | Construction of Culvert Wing Wall at 6.000 kmp on Dilkhan to N. Lungpher Road |  | 32.57 | 100% | 32.533 |  |  | 100% | 32.533 | Works Completed
8 | Construction of Culvert Wing Wall at 7.510 kmp on Dilkhan to N. Lungpher Road |  | 46.04 | 100% | 46.0302 |  |  | 100% | 46.0302 | Works Completed
9 | Construction of Retaining Wall (Formation Collapsed) at 2.900 kmp on N. Lungpher to Buhban Road |  | 24.25 | 100% | 24.2289 |  |  | 100% | 24.2289 | Works Completed
10 | Construction of Culvert Wing Wall at 5.400 kmp on Khanpui to Tualbung Road |  | 16.45 | 100% | 16.4299 |  |  | 100% | 16.4299 | Works Completed
11 | Re-construction of RCC Slab Culvert on Khanpui to Tualbung Road at Ch. 8.000 Kmp |  | 53.18 | 100% | 53.171 |  |  | 100% | 53.171 | Works Completed
12 | Re-construction of RCC Slab Culvert on Khanpui to Tualbung Road at Ch. 11.750 Kmp |  | 9.43 | 100% | 9.3999 |  |  | 100% | 9.3999 | Works Completed
13 | Re-construction of H/P Culvert on Saitual to Phullen Road at Ch.34.000 Kmp |  | 25 | 100% | 24.9795 |  |  | 100% | 24.9795 | Works Completed
14 | Construction of Culvert Wing Wall at 7.500 kmp on Dilkhan-N.Lungpher Road |  | 19.19 | 100% | 19.1678 |  |  | 100% | 19.1678 | Works Completed
15 | Construction of Retaining Wall( Formation Collapsed) at 3.400 kmp on -N.Lungpher-Buhban Road |  | 8.48 | 100% | 8.4589 |  |  | 100% | 8.4589 | Works Completed
16 | Construction of Retaining Wall( Formation Collapsed) at 3.600 kmp on -N.Lungpher-Buhban Road |  | 16.01 | 100% | 15.9956 |  |  | 100% | 15.9956 | Works Completed
17 | Re-Construction of H/P Culvert on Khanpui-Tualbung Road at 5.450 kmp |  | 5.54 | 100% | 5.54 |  |  | 100% | 5.54 | Works Completed
18 | Construction of Retaining Wall at Ch.5.410 Kmp on Rulchawm to Mualpheng Road |  | 4.1 | 100% | 4.0981 |  |  | 100% | 4.0981 | Works Completed
19 | Construction of Retaining Wall at Ch.0.630 Kmp on Mualpheng to Maite Road |  | 2.24 | 100% | 2.2387 |  |  | 100% | 2.2387 | Works Completed
20 | Re-Construction of Retaining Wall at Ch.11.610 Kmp on Mualpheng to Maite Road |  | 2.24 | 100% | 2.2217 |  |  | 100% | 2.2217 | Works Completed
21 | Construction of Retaining Wall at Ch.12.500 Kmp on Mualpheng to Maite Road |  | 9.42 | 100% | 9.3453 |  |  | 100% | 9.3453 | Works Completed
22 | Re-Construction of Retaining Wall at Ch.14.330 Kmp on Mualpheng to Maite Road |  | 8.17 | 100% | 8.1284 |  |  | 100% | 8.1284 | Works Completed
23 | Construction of Retaining Wall at Ch.14.370 Kmp on Mualpheng to Maite Road |  | 4.13 | 100% | 4.1281 |  |  | 100% | 4.1281 | Works Completed
24 | Construction of Retaining Wall at Ch.14.400 Kmp on Mualpheng to Maite Road |  | 8.73 | 100% | 8.4446 |  |  | 100% | 8.4446 | Works Completed
25 | Re-Construction of Retaining Wall at Ch.15.200 Kmp on Mualpheng to Maite Road |  | 4.18 | 100% | 3.7939 |  |  | 100% | 3.7939 | Works Completed
26 | Construction of RCC Slab Culvert at Ch.15.850 Kmp on Mualpheng to Maite Road |  | 17.04 | 100% |  |  | 16.9898 | 100% | 16.9898 | Work in Progress
27 | Re-Construction of Retaining Wall at Ch.17.920 Kmp on Mualpheng to Maite Road |  | 4.95 | 100% | 4.9172 |  |  | 100% | 4.9172 | Works Completed
28 | Re-Construction of Retaining Wall at Ch.21.500 Kmp on Mualpheng to Maite Road |  | 7.59 | 100% | 7.5684 |  |  | 100% | 7.5684 | Works Completed
29 | Construction of Retaining Wall at Ch.1.185 Kmp on Approach Road to Helipad, Saitual |  | 6.93 | 100% | 6.8877 |  |  | 100% | 6.8877 | Works Completed
30 | Construction of Retaining Wall at Ch.1.200 Kmp on Approach Road to Helipad, Saitual |  | 30.66 | 100% |  |  | 30.6242 | 100% | 30.6242 | Works Completed
31 | Widening and Construction of Pavement including Patch Repair on Saitual-Sihfa Road |  | 150 | 80.49% | 95.4073 | 19.51% | 54.5906 | 100% | 149.9979 | Work in Progress
| TOTAL |  | 598.92 |  | 452.3762 |  | 134.6966 |  | 596.2628 |  | 92.2581
Source of Funding : SASCI-V (2025-2026)
| EXTENSION OF SAITUAL TOWN VIA KHIANGPUIZAWL |  | 459
1 | Formation Cutting (Widening) |  | 12.6369 | 100% | 12.6231 |  |  | 100% | 12.6231 |  | 459.0003 | 2.7531 | 0
2 | H/P Culvert Type-I at 0.260 Kmp |  | 6.5324 | 100% | 6.5194 |  |  | 100% | 6.5194 |  | 459.0003 | 1.4232 | 0
3 | H/P Culvert Type-I at 0.580 Kmp |  | 6.7627 | 100% | 6.7513 |  |  | 100% | 6.7513 |  | 459.0003 | 1.4734 | 0
4 | H/P Culvert Type-I at 0.880 Kmp |  | 6.835 | 100% | 6.829 |  |  | 100% | 6.829 |  | 459.0003 | 1.4891 | 0
5 | H/P Culvert Type-I at 0.940 Kmp |  | 6.5056 | 100% | 6.4932 |  |  | 100% | 6.4932 |  | 459.0003 | 1.4173 | 0
6 | H/P Culvert Type-I at 1.215 Kmp |  | 5.7678 | 100% | 5.7461 |  |  | 100% | 5.7461 |  | 459.0003 | 1.2566 | 0
7 | H/P Culvert Type-I at 1.475 Kmp |  | 6.5614 | 100% | 0 |  |  | 100% | 0 |  | 459.0003 | 1.4295 | 0
8 | Slab Culvert Type-V at 1.730 Kmp |  | 48.1297 | 0% | 0 | 30% |  | 30% | 0 |  | 459.0003 | 10.4858 | 3.1457
9 | Slab Culvert Type-III at 1.860 Kmp |  | 28.8488 | 0% | 0 | 100% |  | 100% | 0 |  | 459.0003 | 6.2851 | 6.2851
10 | Slab Culvert Type-V at 2.060 Kmp |  | 48.1297 | 55% | 0 | 45% |  | 100% | 0 |  | 459.0003 | 10.4858 | 4.7186
11 | Retaining Wall at 2.120 Kmp |  | 9.1518 | 80% | 0 |  |  | 80% | 0 |  | 459.0003 | 1.9939 | 0
12 | Masonry Side Drain (2450m) |  | 67.7844 | 0% | 0 | 30% |  | 30% | 0 |  | 459.0003 | 14.7678 | 4.4303
13 | Pavement (WBM1 + WBM2 + BCM + Seal Coat) |  | 187.7003 | 80% | 143.088 | 10% |  | 90% | 143.088 |  | 459.0003 | 40.8933 | 4.0893
14 | 3% Contingency |  | 13.2404 | 0% | 0 |  |  | 0% | 0 |  | 459.0003 | 2.8846 | 0
15 | 1% Quality Control |  | 4.4135 | 0% | 0 |  |  | 0% | 0 |  | 459.0003 | 0.96154 | 0
| TOTAL |  | 459.0003 |  | 188.0502 |  | 0 |  | 188.0502 |  |  | 100 | 22.6691 | 15.1691
Sr. Executive Engineer, PWD.,
Saitual Division, Saitual.
9774031494

## SIAHA DIV
MONTHLY PROGRESS REPORT FOR THE MONTH OF MARCH 2026
Name of Division : PWD Siaha Division
Sl. No. | Name of Scheme | Unit | Approved Cost (in lakhs) | Date of Commencement | Target date of Completion | Commulative Progress at the end of last Month |  | Achievement of work during the month |  | Overall Cummulative achievement |  | Remarks | Mode of Tender
| Name of Work/Project |  |  |  |  | Phy | Fin | Phy | Fin | Phy | Fin |  |  | 0.1278
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | SASCI
1 | Widening,Blacktopping and Improvement of of Road from Saihatlangkawn Beat post-Primary School-II - District Court Complex and Magistrate Residence. | % | 360 | 21.08.2025 | 21.12.2025 | 71% |  | 8% |  | 79% |  | Work in progress | Item rate Contract
2 | Extension of Culvert Apron at 0.700km on AOC to Saiha Tlawngkawn Road | % | 3.03 | 09.06.2025 | 5.12.2025 |  |  | 100% | 3.03 | 100% | 3.03 | Work Completed | Item rate Contract
3 | Reconstruction of RCC Slab Culvert on Saiha to Tuisumpui road at Ch.7.600km | % | 12.12 | 09.06.2025 | 09.01.2026 | 100% |  |  | 12.12 | 100% | 12.12 | Work Completed | Item rate Contract
4 | Restoration of Collapsed Retaining wall on Niawhtlang - Chakhang road (0.000 - 44.050)kmp at Ch.2.500 | % | 8.46 | 09.06.2025 | 09.01.2026 | 100% |  |  | 8.46 | 100% | 8.46 | Work Completed | Item rate Contract
2 | NABARD
Work under NABARD
1 | Up-gradation of Laki to Vahai Road From Ch. 0.00 km to Ch. 15.56 km | % | 1809.4429 | 28.06.2024 | 27.06.2026 | 77.94% | 1262.75 | 7.4% |  | 85.34% | 1262.75 | 1. Work in Progress 2. Deviation approved vide Letter No.B.12051/1/21/MMPC/PWD/40 Dt. 21.07.25 | Item rate Contract | 0.13%
3 | NEC
Work under NEC
4 | PMGSY
Work under PMGSY
5 | SEDP
Work under SEDP
6 | CSS
Work under CSS
7 | MoRTH
Work under MoRTH
A | 5054: (2024-2025)
1 | Annual Plan 2024 - 2025 Construction of Bailey Bridge (TDR) 170 ft span over R.Tuisumpui | % | 250 | 02.12.2024 |  | 100% | 220 |  | 30 | 100% | 250 | Work completed | Item rate Contract
B | 5054: (2025-2026)
1 | Pothole Filling and resurfacing of Approach Road to Helipad Via DC Bungalow road | % | 4.42 | 20.11.2025 | 21.01.2026 |  |  | 100% | 4.42 | 100% | 4.42 | Work completed | Item rate Contract
2 | Pothole filling and resurfacing of DC Bungalow Court Yard) | % | 0.78 | 20.11.2025 | 21.01.2026 |  |  | 100% | 0.78 | 100% | 0.78 | Work completed | Item rate Contract
3 | Widening of pavement at selected locations on Circuit House to Bazar Traffic point road via Civil Hospital | % | 19.24 | 20.11.2025 | 21.03.2026 | 50% |  | 50% | 19.24 | 100% | 19.24 | Work completed | Item rate Contract
4 | Construction of link drain at Tuisumpui Bridge site to prevent erosion of abutment foundation | % | 5.98 | 20.11.2025 | 21.02.2026 |  |  | 100% | 5.98 | 100% | 5.98 | Work completed | Item rate Contract
5 | Pothole filling, Patch Repair & Resurfacing of BRTF Road to Suakkunga Road (Police Outpost - Suakkunga Road) at Bualpui NG (0.000 - 1.200 kmp) | % | 27.13 | 20.11.2025 | 21.03.2026 | 100% |  |  | 27.13 | 100% | 27.13 | Work completed | Item rate Contract
6 | Pothole filling, Patch Repair & Resurfacing of Approach road to PHC Chhuarlung (0.000 - 0.370) km | % | 7.31 | 20.11.2025 | 21.02.2026 | [6 empty] | Change of Work approval awaited | Item rate Contract
7 | Restoration of RCC Slab Culvert on Maisa-Lawngban Road at Ch.2.80 km | % | 6.88 | 20.11.2025 | 21.02.2026 |  |  | 100% | 6.88 | 100% | 6.88 | Work completed | Item rate Contract
8 | Construction of Lined Side Drain on Tipa 'V' - Tipa 'L' Road (Tipa Lal Veng Peng Thuam - Waiting Shed on NH-02 at Tipa 'V') | % | 6.16 | 20.11.2025 | 21.02.2026 | 100% |  |  | 6.16 | 100% | 6.16 | Work completed | Item rate Contract
9 | Restoration of RCC Slab Culvert on Phura - Lungpuk Road at Ch. 15.80 km | % | 5.72 | 20.11.2025 | 21.02.2026 |  |  | 100% | 5.72 | 100% | 5.72 | Work completed | Item rate Contract
| Total= |  | 83.62
9 | CRF | [13 empty] | Withh = | 5.74
a) | Construction of Road from Chakhei to Siasi road (Length = 20 km) under CRF: Group-A (SH: FC & Pavement Works) | % | 4982.15 | 08.07.19 | 20.12.2024 | 99.99% | 3074.35 | 0.01% |  | 100% | 3074.35 | Work completed | Item rate Contract |  | CC = | 29.2685 | 21.7265 | 2.6723 | 24.3989
b) | Construction of Road from Chakhei to Siasi road (Length = 20 km) under CRF: Group-B (SH: Permanent Works) | % |  | 08.07.19 | 20.12.2024 | 100% | 976.65 |  |  | 100% | 976.65 | Work completed | Item rate Contract |  | QC = | 3.6 | 7.5419 | 0.92765 | 8.4695
10 | 3054 | [14 empty] | 32.8685 |  |  | 32.8684
Work under Annual Maintenance Action Plan (3054) During 2025-26 under PWD Siaha Division
1 | Maintenance and Improvement of Approach road to PHC with PCC at Sangau | % | 14.53 | 18.08.2025 | 31.03.2026 | 100% |  |  | 14.53 | 100% | 14.53 | Work completed | Departmental
2 | Construction of Retaining Wall on Tlangpui - Niawhtlang Road (0.000 - 14.000) kmp at Ch. 7.500 km | % | 6.66 | 07.07.2025 | 08.09.2025 | 100% |  |  | 6.66 | 100% | 6.66 | Work completed | Departmental
3 | Pothole filling of Meisatla forest check Gate to NH54B Tawngtaina Part-II | % | 14.72 |  |  |  |  | 100% | 14.72 | 100% | 14.72 | Work completed | Departmental
4 | Resurfacing of Approach road to GHSS Complex at New Siaha | % | 1.45 |  |  |  |  | 100% | 1.45 | 100% | 1.45 | Work completed | Departmental
5 | Pothole filling & Resurfacing of Er.VL khuma Residence to Council Veng via Council Veng Hall road | % | 19.08 |  |  |  |  | 100% | 19.08 | 100% | 19.08 | Work completed | Departmental
6 | Pothole filling, Patch repair & Resurfacing of Bualpui Bazar - PWD Complex at Bualpui 'NG' Phase I | % | 6.23 | 19.01.2026 | 05.02.2026 | 100% |  |  | 6.23 | 100% | 6.23 | Work completed | Departmental
7 | Pothole filling, Patch repair & Resurfacing of Chheihlu - Chakhang Road from Ch.1.000 km to Ch.2.000 km | % | 10.63 | 13.03.2026 |  |  |  | 100% | 10.63 | 100% | 10.63 | Work completed | Departmental
8 | Strengthening of Chheihlu - Chakhang road from Ch.3.00km to Ch.5.00km. | % | 10.68 | 16.02.2026 | 31.03.2026 |  |  | 100% | 10.68 | 100% | 10.68 | Work completed | Departmental
9 | Reconstruction of Damaged slab Culvert Type -I on Siachangkawn - Vawmbuk road (0.000 - 12.250) km | % | 3.49 |  |  |  |  | 100% | 3.49 | 100% | 3.49 | Work completed | Departmental
10 | Repair of RCC Slab Culvert on Phura - Lungpuk road at Ch.16.300 km | % | 5.57 | 24.02.2026 | 31.03.2026 |  |  | 100% | 5.57 | 100% | 5.57 | Work completed | Departmental
11 | Construction of Approach road to Kaochao East IB With PCC Pavement | % | 25 | 02.02.2026 | 31.03.2026 | 10% |  | 90% | 25 | 100% | 25 | Work completed | Departmental
| Total |  | 118.04
Executive Engineer, PWD
Siaha Division

## TLABUNG DIV
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL /2026
NAME OF ROAD : Improvement of Chawngte - Borapansury Road (0.000-30.00)KMP
Name of Division : Tlabung Division
Source of Funding : NABARD | [15 empty] | 455
Name of Contractor :Malsawmsangzela, Dam Veng, Aizawl.
Sanction Amount : Rs. 4381.00 Lakh
Sl. No | Name of Work/Project | Unit | Approved Cost (in Lakh) |  | Date of Commencement | Target Dt. Of Completion | Cummulative progress at the end of last mont |  | Achievement of works during the month |  | Overall Cummulative achievement |  | Remarks | Mode of Contract
|  |  | Qnty. | Cost |  |  | Phy | Fin | Phy. | Fin | Phy. | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Sub-grade preparation | Km | 30 | 76.73 | Dt.15.march.2023 | Dt.15.march.2025 | 30 | 1499.61 |  |  | 30 | 1499.61 | Extension granted upto Dt.13.07.2026 | Item Rate | 100
2 | GSB | Km | 20 | 668.7 |  |  | 20 |  |  |  | 20 |  |  |  | 100
3 | WBM | Km | 1.342 | 42.57 |  |  | 1.342 |  |  |  | 1.342 |  |  |  | 100
4 | ANT | Km | 10 | 241.45
5 | Grove Concrete | km | 30 | 2298.83 |  |  | 6.5 |  | 1.5 |  | 8 |  |  |  | 26.6667
6 | Eathen shoulder | Km | 30 | 213.39 |  |  | 1.6 |  |  |  | 1.6 |  |  |  | 5.3333 |  | 1.5
7 | PROTECTION WORKS : | Rm | 146.5 | 99.26 |  |  | 146.5 |  |  |  | 146.5 |  |  |  | 100 | 41
8 | HP culvert | No | 15 | 94.09 |  |  | 12 |  | 2 |  | 14 |  |  |  | 93.3333 |  | 187.5
9 | Unline Side Drain | km | 30 | 91.13 |  |  | 7.5 |  |  |  | 20 |  |  |  | 66.6667
10 | Lined Side Drain | Rm | 2475 | 58.58 |  |  |  |  | 150 |  | 150 |  |  |  | 6.0606
11 | Tick Shape Side Drain | Rm | 4515 | 100.68 |  |  | 700 |  | 500 |  | 1200 |  |  |  | 26.5781
12 | i) 5th Kilometre Stone | No | 6 | 0.5404 | [10 empty] | 0
13 | ii) Ordinary Kilometre Stone | No | 25 | 1.0651 | [10 empty] | 0
|  |  | Total | 3987.0155 |  |  |  | 1499.61 |  |  |  | 1499.61 |  |  | 624.6387
[6 empty] | Overall Physical achievement in % |  |  |  |  | 52.0532 |  |  |  | 1200 | 100
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL /2026
NAME OF ROAD : Const of Galvanised Steel Concrete Composit Bridge over Borapansury River on Chawngte to Borapansury road
Name of Division : Tlabung Division
Source of Funding : NABARD
Name of Contractor :Urban Infra Projects Private Limited.
Agreement Amount : Rs. 635.69Lakh
Sl. No | Name of Work/Project | Unit | Approved Cost (in Lakh) |  | Date of Commencement | Target Dt. Of Completion | Cummulative progress at the end of last mont |  | Achievement of works during the month |  | Overall Cummulative achievement |  | Remarks | Mode of Contract
|  |  | Qnty. | Cost |  |  | Phy | Fin | Phy. | Fin | Phy. | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
| I FOUNDATION |  |  |  | Date.31.May.2024 | Dt.31.may.2026 | [7 empty] | Item Rate
1 | Earthwork in excavation of foundation in Ordinary rock | m3 | 532.5 | 4.264 | [10 empty] | 0
2 | Earthwork in excavation of foundation in Hard rock | m3 | 220 | 2.754 | [10 empty] | 0
3 | Plain /reinforced cement concrete in open foundation | m3 | 41.23 | 5.154
4 | Footing H.RCC Grade M15 | m3 | 215.67 | 32.354
5 | Supplying, fitting and placing un-coated HYSD bar reinforcement in foundation | MT | 19.01 | 25.664
II SUB-STRUCTURE
6 | Plain /reinforced cement concrete in sub-structure | m3 | 188.75 | 33.044
7 | Furnishing and placing reinforcement /prestressed cement concrete in super-structure | m3 | 88.93 | 17.794
8 | Supplying, fitting and placing un-coated HYSD bar reinforcement in sub-structure | MT | 66.67 | 90
9 | Providing weep hole in brick masonry/plain/ reinforced concrete abutment, wing wall/ return wall with 100mm dia | each | 250 | 4.54
10 | Back filling behind abutment, wing wall and return wall | m3 | 532.98 | 15.99
11 | Providing and laying of filter media with granular material/ stone crushed aggregates | m3 | 144 | 5.04
12 | Supplying, fitting and fixing in position true to line and level POT cum PTFE bearing conforming | No | 12 | 15.6
| III SUPER-STRUCTURE |  |  |  | Date.31.May.2024 | Dt.31.may.2026
13 | Supplying, fabricating and erecting the fabricated galvanised steel built-up | Ton | 81.13 | 202.83
14 | Furnishing and placing reinforcement /prestressed cement concrete in super-structure | m3 | 80.25 | 19.26
15 | PCC M15 Grade leveling course below approach slab | m3 | 11.18 | 1.397
16 | Reinforced Cement concrete approach slab including reinforcement and formwork | m3 | 22.36 | 4.025
17 | Mastic asphalt (Providing and laying 12mm thick mastic asphalt wearing course on top of deck slab excluding prome coat) | sqm | 180 | 2.16
18 | Strip seal expension joint | rm | 21.3 | 5.112
19 | Supplying, fitting and placing un-coated HYSD bar reinforcement in super-structure | ton | 20.22 | 27.297
20 | Reinforced Cement concrete crash barrier | m | 134 | 16.08
21 | Drain Spouts | no | 12 | 0.216
IV-APPROACH ROAD
22 | Excavation in soil by mechanical means | m3 | 1820 | 3.644
23 | Embakement construction with material obtained from borrow pits | m3 | 2296 | 8.274
24 | PCC 1:3:6 in foundation | m3 | 2.1 | 0.254
25 | Stone masonry work in cement mortar for substructure | m3 | 144.1 | 12.974
26 | Plain /reinforced cement concrete in sub-structure | m3 | 1.77 | 0.25
27 | GSB (Plant Mix Method) | m3 | 116.59 | 4.66
28 | Dry Lean cement concrete sub-base | m3 | 78.93 | 7.89
29 | Cement concrete pavement | m3 | 197.31 | 39.46
30 | Providing and laying of filter media with granular material/ stone crushed aggregates | m3 | 31.8 | 1.27
V. ROAD SIGNAGES, MAKINGS etc.
31 | Reto-reflectorised Traffic signs | each | 2 | 0.362
32 | 60 cm equilateral triangle | each | 2 | 0.2
33 | 60 cm circular | each | 2 | 0.2
34 | 60 cm x 4 cm rectangular | each | 2 | 0.2
35 | Road marking with hot applied thermoplastic compound with reflectorising glass beads on bituminous surface | m3 | 35.875 | 0.864 | Date.31.May.2024 | Dt.31.may.2026
36 | Type-A, "W" : Metal beam crash barrier | m | 143.5 | 12.054
VI RIVER BANK PROTECTION
37 | Boulder apron laid in wire crates | m3 | 160 | 10.4
38 | Gabian structure for erosion control, river training works and protection works | m3 | 24 | 2.16
|  | Total = |  | 635.691
Overall Physical achievement in % | [10 empty] | 1
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL / 2026
NAME OF ROAD : STRENGTHENING OF CHAWNGTE TO BORAPANSURY ROAD
Name of Division : Tlabung Division
Source of Funding : SASCI-2022-23
Contractor : Lalroenga, Republic Veng, Aizawl
Sanction Amount : Rs 405.00 Lakh
Sl. No | Name of Work/Project | Unit | Approved Cost (in Lakh) |  | Date of Commencement | Target Dt. Of Completion | Cummulative progress at the end of last mont |  | Achievement of works during the month |  | Overall Cummulative achievement |  | Remarks | Mode of Contract
|  |  | Qnty. | Cost |  |  | Phy. | Fin | Phy. | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Pot-holes with WBM Materials | m3 | 1007.01 | 73.1244 | 22.July.2023 | 22.July.2024 | 1007.01 | 273.78 |  |  | 1007.01 | 273.78 | Completed Extension granted upto Dt.31.03.2026 | Item Rates
2 | WBM -Gr-II | m3 | 800.16 | 45.76 |  |  | 800.16 |  |  |  | 800.16
3 | WBM -Gr-III | m3 | 668.82 | 38.25 |  |  | 668.82 |  |  |  | 668.82
4 | Prime Coat | m2 | 35850 | 21.8685 |  |  | 35850 |  |  |  | 35850
5 | Tack Coat | m2 | 35850 | 13.2294 |  |  | 35850 |  |  |  | 35850
6 | Open-Graded Premix Surfacing | m2 | 35850 | 119.3094 |  |  | 35850 |  |  |  | 35850
7 | Seal Coat | m2 | 35850 | 52.341 |  |  | 35850 |  |  |  | 35850
8 | R/Wall | rm | 42.68 | 19.07 |  |  | 42.68 |  |  |  | 42.68
9 | RCC Cross Drain | rm | 33.5 | 8.47 |  |  | 33.5 |  |  |  | 33.5
| Total= |  |  | 391.4227 |  |  |  | 273.78 |  |  |  | 273.78
[7 empty] | Overall Physical achievement in % |  |  |  | 100
MONTHLY PROGRESS REPORT FOR THE MONTH OF APRIL / 2026
NAME OF ROAD : Restoration of Damage Due to Cyclone Remal under Tlabung Division
Name of Division : Tlabung Division
Source of Funding : SASCI-2025-26
Contractor : Laltlanmawia, Hmar Veng , Kolasib
Sanction Amount : Rs 830.00 Lakh
Sl. No | Name of Work/Project | Unit | Approved Cost (in Lakh) |  | Date of Commencement | Target Dt. Of Completion | Cummulative progress at the end of last mont |  | Achievement of works during the month |  | Overall Cummulative achievement |  | Remarks | Mode of Contract
|  |  | Qnty. | Cost |  |  | Phy. | Fin | Phy. | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | PCC Pavement | Km | 2.024 | 597.29 | 16.06.2025 | 16.01.2026 | 1.724 | 666.92 | 0.076 |  | 1.8 | 666.92 | Ongoing works | Item Rates
2 | Retaining Wall | Rm | 211.93 | 114.97 |  |  | 211.93 |  |  |  | 211.93
3 | Plum Concrete Retaining wall | Rm | 51 | 57.03 |  |  | 51 |  |  |  | 51
4 | RCC Hume Pipe Culvert | Nos | 2 | 17.65 |  |  | 2 |  |  |  | 2
5 | RCC Slab Culvert | Nos | 2 | 13.06 |  |  | 2 |  |  |  | 2
| Total= |  |  | 800 |  |  |  | 666.92 |  |  |  | 666.92
[7 empty] | Overall Physical achievement in % |  |  |  | 97.7866
Executive Engineer,PWD
Tlabung Division, Tlabung