## ARND
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY, 2026
Name of Work : 5054-C.O. on Roads & Bridges under Aizawl Road North Division for the year 2025-2026
Name of Scheme : State funding (5054)
Sanctioned Amount : Rs. 254.74 lakh
Agreement Amount : Rs. 230.32 lakh
Name of Contractor : M/s Sumati Creative Infrastructure Pvt. Ltd., Dhanbad, Jharkhand
Name of Division : Aizawl Road North Division
Sl. No. | Sub-Head of works | Unit | Qnty | Approved Cost (in lakh) | Date of Commencement | Target Date of Completion | Commulative Progress at the end of Last Month |  | Achievement of Works during the Month |  | Overall cumulative achievement |  | Remarks | Mode of Contract
[7 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 |  | weightage | Last month | During
1 | Resurfacing of RIPANS Approach Road | Km | 0.8 | 254.74 | 2025-12-27 | 2026-06-27 | 100% | 230.32 | 0% | - | 100% | 230.32 | Completed | Item rate |  | 1 | 1 | 0
2 | Resurfacing of Zonuam Internal road Part-II | Km | 0.4 |  |  |  | 100% |  | 0% |  | 100% |  |  |  |  | 0 | 0 | 0
3 | Patch repair of Industrial Complex road at Zuangtui (Hangi lunglen tlang) | Km | 3.5 |  |  |  | 100% |  | 0% |  | 100% |  |  |  |  | 0 | 0 | 0
4 | Construction of Flexible Pavement at Brigade Lower lane road | Km | 0.5 |  |  |  | 100% |  | 0% |  | 100% |  |  |  |  | 0 | 0 | 0
5 | Construction of Flexible Pavement at Brigade field ring road | Km | 0.25 |  |  |  | 100% |  | 0% |  | 100% |  |  |  |  | 0 | 0 | 0
6 | Improvement of Approach road to Central Jail at Sakawrtuichhun | Km | 2.5 |  |  |  | 100% |  | 0% |  | 100% |  |  |  |  | 0 | 0 | 0
7 | Construction of V-Shaped Side Drain at Leitan Thlanmual Road | Km | 0.62 |  |  |  | 100% |  | 0% |  | 100% |  |  |  |  | 0 | 0 | 0
8 | Widening of UPHC to Mualhnihna tuikhur road at Zemabawk | Km | 0.5 |  |  |  | 100% |  | 0% |  | 100% |  |  |  |  | 0 | 0 | 0
9 | SMBT near EFCI Church at Zembawk East | Km | 0.285 |  |  |  | 100% |  | 0% |  | 100% |  |  |  |  | 0 | 0 | 0
10 | Junction Improvement near Modern School at Saron Veng | Km | 0.05 |  |  |  | 100% |  | 0% |  | 100%
| Total = |  |  | 254.74 | [11 empty] | 1 | 100% | 0%
[5 empty] | MONTHLY PROGRESS REPORT FOR THE MONTH OF | JULY |  |  | 2026
Name of Work : Patch repair of various roads under Aizawl Road North Sub Division-III | [8 empty] | Name of Contractor: Vanlalvuta Chinzah
Agreement Amount : ₹ 2,69,71,259.00 | [8 empty] | Date of Commencement: 17.3.2026
Name of Division : Aizawl Road North Sub-Division-III | [8 empty] | Target date of Completion: 24.6.2026
Source of funding: 5054 (Untied)
OVERALL ACHIEVEMENT (PHY) - 100%
Sl. No. | Name of Project | Unit | Approved Cost (Rs. in lakh) | Date of Commencement | Target date of completion | Cumulative Progress at the end of last month |  | Achievement works during the month |  | Overall cummulative achievement |  | Remarks | Mode of contract
[6 empty] | Phy. | Fin. | Phy. | Fin. | Phy. | Fin.
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
PATCH REPAIR OF VARIOUS ROADS UNDER AIZAWL ROAD NORTH SUB DIVISION-III
1 | Patch repair and seal coat | Km | 269.71 | 2026-03-17 | 2026-06-24 | 100% | 269.71 | 0% | - | 100% | 269.71 | Completed | Item Rate
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY, 2026
Name of Work : Improvement & Upgradation of various roads under Aizawl Road North Sub Division-III | [8 empty] | Name of Contractor: Lalremruata, Zemabawk
Agreement Amount : ₹ 1,07,47,080.00 | [8 empty] | Date of Commencement: 17.3.2026
Source of funding: 5054 (Untied) | [8 empty] | Target date of Completion: 24.6.2026
OVERALL ACHIEVEMENT (PHY) - 100%
Sl. No. | Name of Project | Unit | Approved Cost (Rs. in lakh) | Date of Commencement | Target date of completion | Cumulative Progress at the end of last month |  | Achievement works during the month |  | Overall cummulative achievement |  | Remarks | Mode of contract
[6 empty] | Phy. | Fin. | Phy. | Fin. | Phy. | Fin.
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
IMPROVEMENT & UPGRADATION OF VARIOUS ROADS UNDER AIZAWL ROAD NORTH SUB DIVISION-III
1 | Patch repair and seal coat | Km | 107.47 | 2026-03-17 | 2026-06-24 | 100% | 107.47 | 0% | - | 100% | 107.47 | Completed | Item Rate
Name of Work : Detailed Estimate for Annual Plan 5054 R&B Untied Fund under Aizawl Road North Division during 2025-2026 (Patch Repair & Resurfacing of roads at various places under Aizawl Road north Sub Divsision-I & II)
Name of Scheme : State funding (5054-untied)
Sanctioned Amount : Rs. 762.35 lakh
Agreement Amount : Rs. 230.32 lakh
Name of Contractor : H. Zorempuia, Sihphir Venghlun
Name of Division : Aizawl Road North Division
Sl. No. | Items of work | Unit | Amount (in lakh) | Date of Commencement | Target Date of Completion | Commulative Progress at the end of Last Month |  | Achievement of Works during the Month |  | Overall cumulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Scarifying Existing Granular Surface | sqm | 1.07 | 2026-03-21 | 2026-06-21 | 100% | 184.62 | 0% | - | 100% | 184.62 | Phy Completed | Item rate
2 | Water Bound Macadam | cum | 17.44 |  |  | 100% |  | 0% |  | 100% |  | Phy Completed | Item rate
3 | Prime coat | sqm | 0.002306 |  |  | 100% |  | 0% |  | 100% |  | Phy Completed | Item rate
4 | Tack coat | sqm | 6.57 |  |  | 100% |  | 0% |  | 100% |  | Phy Completed | Item rate
5 | Mixed Seal Surfacing | sqm | 98.85 |  |  | 100% |  | 0% |  | 100% |  | Phy Completed | Item rate
6 | Open - Graded Premix Surfacin | sqm | 0.18 |  |  | 100% |  | 0% |  | 100% |  | Phy Completed | Item rate
7 | Seal Coat | sqm | 2.04 |  |  | 100% |  | 0% |  | 100% |  | Phy Completed | Item rate
8 | Patch repair and Seal coating of BSNL to BRTF road at Durtlang North (ICFAI road Sihphir rd) | Km | 8.55 |  |  | 100% |  | 0% |  | 100% |  | Phy Completed | Item rate
9 | Construction of Breast wall at Ch:0.350kmp on approach road to RIPANS |  | 6.5 |  |  | 0% |  | 50% |  | 50% |  | Work in progress | Item rate
10 | Construction of PR&R.wall and Drain on approach road to Galilee veng upto Lungbial | Km | 24.13 |  |  | 0% |  | 90% |  | 90% |  | Work in progress | Item rate
11 | Patch repair and Seal coating of Synod Hospital approach road at Durtlang | Km | 10 |  |  | 100% |  | 0% |  | 100% |  | Phy Completed | Item rate
12 | Patch repair and seal coating of Leitan to Agape via Govt.High school at Durtlang | Km | 10.68 |  |  | 100% |  | 0% |  | 100% |  | Phy Completed | Item rate
13 | Patch repair and seal coating of Chaltlang Indoor Stadium to Dingdi veng | Km | 4 |  |  | 100% |  | 0% |  | 100% |  | Phy Completed | Item rate
14 | Patch repair and seal coating of approach road to Agape at Durtlang (Lane-I) | Km | 6.66 |  |  | 0% |  | 100% |  | 100% |  | Phy Completed | Item rate
15 | Patch repair and seal coating of Durtlang Lower lane road | Km | 7.77 |  |  | 0% |  | 0% |  | 0% |  | Not yet started
16 | Patch repair and seal coating of Chaltlang Lower lane road | Km | 6.66 |  |  | 100% |  | 0% |  | 100% |  | Phy Completed | Item rate
17 | Patch repair and seal coating of approach road to Chaltlang Dawrkawn to Tatkawng veng | Km | 4.44 |  |  | 100% |  | 0% |  | 100% |  | Phy Completed | Item rate
18 | Patch repair and seal coating of YMA road Chaltlang North Salem veng to Lily veng | Km | 3.33 |  |  | 100% |  | 0% |  | 100% |  | Phy Completed | Item rate
19 | Patch repair and seal coating of DC Workshop to Sairang road petrol pump via Lily veng | Km | 3.13 |  |  | 0% |  | 0% |  | 0% |  | Not yet started
20 | Patch repair and seal coating of Approach road to NIT at Chaltlang | Km | 2.08 |  |  | 0% |  | 0% |  | 0% |  | Not yet started
21 | Thuampui to Selesih road (Sinking area) | Km | 5.55 |  |  | 100% |  | 0% |  | 100% |  | Phy Completed | Item rate
22 | Patch repair of approach road to Tourist complex at Berawtlang via Lungbial diversion at Zemabawk | Km | 5.55 |  |  | 100% |  | 0% |  | 100% |  | Phy Completed | Item rate
23 | Patch repair and seal coating of Chaltlang Indoor Stadium to Lower lane | Km | 3.33 |  |  | 100% |  | 0% |  | 100% |  | Phy Completed | Item rate
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY, 2026
Name of Work : Resurfacing of road within Aizawl city under Aizawl Road North Division
Name of Scheme : State Funding
Tender Amount : Rs. 2145.56 lakh
Agreement Amount : Rs. 2145.56 lakh
Name of Contractor : Nidhi Creative infrastructure Pvt.Ltd.
Name of Division : Aizawl Road North Division
Sl. No. | Name of works | Unit | Qnty | Approved Cost (in lakh) | Date of Commencement | Target Date of Completion | Commulative Progress at the end of Last Month |  | Achievement of Works during the Month |  | Overall cumulative achievement |  | Remarks | Mode of Contract
[7 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Non Bituminous Base Course | sqm | 8495 | 52.55 | 2025-04-17 | 2026-10-17 | 100% | 2133.1 | 0% | 12.46 | 100% | 2145.56 | Phy Completed | EPC
2 | Construction of Flexible Pavement | km | 44.63 | 1647.25 |  |  | 100% |  | 0% |  | 100%
3 | Construction of Rigid Pavement | km | 1.5 | 397.57 |  |  | 100% |  | 0% |  | 100%
4 | Construction of Hume Pipe Culvert | No. | 1 | 6.14 |  |  | 100% |  | 0% |  | 100%
5 | Widening of Tlaklui to Sihpui road Junction | Rm | 60 | 42.05 |  |  | 100% |  | 0% |  | 100%
| Total = |  |  | 2145.56 |  |  | 25.43% | 99.42% | 74.57% |  | 100% | 100%
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY, 2026
Name of Work : Widening and Improvement of Road from Durtlang Leitan To Sihphir Section (Length 10.25 Km) of Aizawl - Durtlang - Lungdai - Kawnpui Road in the State Of Mizoram | [7 empty] | Name of Contractor : M/s SLT Infracon Private Limited
Name of Scheme : CRF | [7 empty] | Date of Commencement : 14/07/2023
Tender Amount : Rs. 46.57 Crore | [7 empty] | Target date of Completion : 31/01/2025
Agreement Amount : Rs. 35.53 Crore | [7 empty] | Revised Target date of Completion : NIL
Name of Division : Aizawl Road North Division | [7 empty] | D-III Balance :
OVERALL ACHIEVEMENT (PHY) - 95.40% | [10 empty] | (Rs. in lakh)
Sl. No. | Name of Works | Unit | Cost (in lakh) | Date of commencement | Target date of completion | Cumulative Progress at the end of last month |  | Achievement works during the month |  | Overall cumulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Scarifying | Rm | 7.76 | 14.7.23 | 31.1.25 | 100% | 2572.88 | 0% | 1789 | 100% | 4361.88 | - | EPC
2 | Earthwork | Cum | 102.89 |  |  | 100% |  | 0% |  | 100%
3 | Granular Sub-Base (GSB) | m3 | 166.68 |  |  | 100% |  | 0% |  | 100%
4 | Dry Lean Concrete (DLC) | Rm | 299.22 |  |  | 100% |  | 0% |  | 100%
5 | Pavement Quality Concrete (PQC) | Rm | 1638.24 |  |  | 100% |  | 0% |  | 100%
6 | Slope Protection | Rm | 715.77 |  |  | 90% |  | 0% |  | 90%
7 | Lined Side Drain | Rm | 148.94 |  |  | 80% |  | 5% |  | 85%
8 | Hume Pipe | Nos. | 484.5 |  |  | 100% |  | 0% |  | 100%
9 | RCC Slab Culvert | Nos. | 57.66 |  |  | 100% |  | 0% |  | 100%
10 | Crash barrier | Rm | 34.56 |  |  | 10% |  | 20% |  | 30%
11 | Traffic Signages | Nos. | 3.91 |  |  | 0% |  | 0% |  | 0%
12 | Road Marking | Rm | 7.91 |  |  | 0% |  | 0% |  | 0%
13 | Km Stone | Nos. | 0.38 |  |  | 0% |  | 0% |  | 0%
14 | Flexible Pavement | Rm | 320.52 |  |  | 100% |  | 0% |  | 100%
15 | Lined Side Drain with Steel Grating | Rm | 12.54 |  |  | 85% |  | 0% |  | 85%
16 | Cable Duct | Nos. | 15.91 |  |  | 100% |  | 0% |  | 100%
17 | Zebra Crossing | Sqm | 2.06 |  |  | 0% |  | 0% |  | 0%
18 | Road Stud | Nos. | 11.35 |  |  | 0% |  | 0% |  | 0%
19 | Foothpath | Rm | 362.84 |  |  | 70% |  | 15% |  | 85%
20 | Waiting Shed | Nos. | 9.04 |  |  | 75% |  | 35% |  | 75%
4402.68
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY, 2026
Name of Work : Balance Work for Construction of Two Lane Road From Sihhmui To Ramrikawn Road (Stage-I: Length 14.50 Kms) | [9 empty] | Name of Contractor: F. Lalawmpuia, Tuikual S
Agreement Amount : Rs. 8,74,00,000.00 | [9 empty] | Date of Commencement: 12.03.2026
Agreement No.: AGM - 21/SBD/CE-HW/2025-26 Dt. 25.02.2026 | [9 empty] | Target date of Completion: 12.09.2027
Name of Division : Aizawl Road North Division
Source of funding : CRIF
Sl. No. | Name of Project | Unit |  | Approved Cost (₹ in lakh) | Date of Commencement | Target date of completion | Cumulative Progress at the end of last month |  | Achievement works during the month |  | Overall cummulative achievement |  | Remarks | Mode of contract
[7 empty] | Phy. | Fin. | Phy. | Fin. | Phy. | Fin.
1 | 2 | 3 |  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
A. | FORMATION CUTTING : |  |  | 5: 12.03.2026; 6: 12.09.2027; 13: Work in Progress; 14: Item rate
a | Clearing, setting, etc. | 1 | Km | 4: 0.225; 7: 100%; 8: -; 9: 0%; 10: -; 11: 100%
b | Earthwork (Formation Cutting) | 24011.6679 | Cum | 4: 79.06; 7: 100%; 8: -; 9: 0%; 10: -; 11: 100%
B. | SIDE DRAINS :
| Unlined Side drain | 13260 | Rm | 4: 38.1
| Concrete lined drain | 944 | Rm | 4: 22.36
C. | RETAINING STRUCTURES :
a | RETAINING WALL | 251 | Rm | 4: 217.07; 7: 40%; 8: -; 9: 0%; 10: -; 11: 40%
D. | CROSS DRAINAGE WORKS :
a | HP CULVERT | 6 | No | 4: 36.485; 7: 0%; 8: -; 9: 50%; 10: -; 11: 50%
b | BOX CULVERT |  |  | 7: 10%; 8: -; 9: 0%; 10: -; 11: 10%
| Type- III (7m X 7m) | 2 | No | 4: 324.67
E | RCC Counterfort Rwall | 42 | Rm | 4: 156.03
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY, 2026 UNDER NABARD
OVERALL ACHIEVEMENT (PHY) - 100%
Sl. No. | Name of Project | Unit | Approved Cost (Rs. in lakh) | Date of Commencement | Target date of completion | Cumulative Progress at the end of last month |  | Achievement works during the month |  | Overall cummulative achievement |  | Remarks | Mode of contract
[6 empty] | Phy. | Fin. | Phy. | Fin. | Phy. | Fin.
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
IMPROVEMENT OF RAMRIKAWN TO NH-54 VIA SAKAWRTUICHHUN ROAD (3.00 Kmp - 7.50 Kmp = 4.50 Km)
1 | Rigid Pavement of Ramrikawn to Sakawrtuichhun | Rm | 480.72 | 13.9.2024 | - | 97% | 438.49 | 3% | - | 100% | 438.49 (Rs. 30,00,830.00 kept in D - III) | Phy Completed | Departmental
2 | Resurfacing of Ramrikawn to Zihnghalkawn 980Rm | Rm |  | 6: 100%; 8: -; 10: 100%; 12: Phy Completed
3 | Construction of approach road to Chawlhhmun from Power Grid at Tuivamit | Rm |  | 6: 100%; 8: -; 10: 100%; 12: Phy Completed
4 | Constn. of R/Wall at Ch 4.230 Kmp at Sakawrtuichhun | Rm |  | 6: 100%; 8: -; 10: 100%; 12: Phy Completed
5 | Constn. of R/Wall at Ch 3.420 Kmp at Sakawrtuichhun | Rm |  | 6: 100%; 8: -; 10: 100%; 12: Phy Completed
6 | Constn. of R/Wall at Ch 6.340 Kmp at Sakawrtuichhun | Rm |  | 6: 100%; 8: -; 10: 100%; 12: Phy Completed
7 | Constn of Slab Culvert at 5.900 kmp at Sakawrtuichhun | Rm |  | 6: 100%; 8: -; 10: 100%; 12: Phy Completed
8 | Constn. of R/Wall at Ch 3.000 Kmp at Sakawrtuichhun | Rm |  | 6: 100%; 8: -; 10: 100%; 12: Phy Completed
9 | Constn. of R/Wall at Ch 3.500 Kmp at Sakawrtuichhun | Rm |  | 6: 100%; 8: -; 10: 100%; 12: Phy Completed
10 | Constn. of R/Wall at Ch 4.620 Kmp at Sakawrtuichhun | Rm |  | - | - | 100% |  | - |  | 100% |  | Phy Completed | Departmental
11 | Constn. of R/Wall at Ch 5.360 Kmp at Sakawrtuichhun | Rm |  | 6: 100%; 8: -; 10: 100%; 12: Phy Completed
12 | Constn. of R/Wall at Ch 5.200 Kmp at Sakawrtuichhun | Rm |  | 6: 100%; 8: -; 10: 100%; 12: Phy Completed
13 | Constn. of R/Wall at Ch 6.050 Kmp at Sakawrtuichhun |  |  | 6: 100%; 8: -; 10: 100%; 12: Phy Completed
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY, 2026
PM - DevINE
A. Physical Report
(Rs. in lakhs)
Sl No | Name of the project, location and State | Name of the Implementing Agency/Deptt. | Approved cost by MDoNER/NEC & Date of Approval | 5: Date of actual commencement of work/scheme; 6: Target date of completion of work/scheme; 7: Scope of the work/scheme in physical terms (eg. Kms etc); 9: Physical Achievement; 11: Remarks
|  |  | Cost | 4: Date; 9: Percentage(during the month); 10: Percentage till the reporting period
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |  | 9 | 10 | 11
1 | Construction of Bamboo Link Road from Tuirial Airfield to North Chaltlang (18 Kms) under PM - DevINE | Public Works Department | 3358 | 17.4.23 | 01.08.2023 | 20.10.2025 | Widening | 18.00 Kms | 1.2% | 88.12% | Work in progress
[7 empty] | Retaining Wall | 587.60 Kms
[7 empty] | Culverts | 38.00 Kms
[7 empty] | Lined Side Drain | 9000.00 Kms
[7 empty] | Unlined Side Drain | 8706.00 Rm
[7 empty] | Rigid Pavement | 17.00 Kms
[7 empty] | Flexible Pavement | 1.00 Km
[7 empty] | Road Furnitures | 18.00 Kms
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY, 2026
PM - DevINE
B. Financial Report
(Rs. in lakhs)
Sl No | Name of the project, location and State | Name of the Implementing Agency/Deptt. | Approved cost by MDoNER/NEC & Date of Approval | 5: Fund released by MDoNER/NEC; 7: Expenditure made; 9: Unspent balance out of the fund released; 10: Status of submission of U/Cs; 11: Remarks
|  |  | Original Cost | 4: Revised Cost; 5: During 2024 - 2025; 6: Since inception (cumulative); 7: During the month vis-à-vis target; 8: Since inception (cumulative)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Construction of Bamboo Link Road from Tuirial Airfield to North Chaltlang (18 Kms) under PM - DevINE | Public Works Department | Rs. 3358.00 on 06.02.23 | Rs. 3374.42 on 02.09.25 | - | - | - | 2298.78 | - | - | Work in progress
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY, 2026 UNDER ARND
Name of Work : Repair and Resurfacing of Zuangtui to Muthi Road |  |  |  | 8: Name of Contractor: H. Lalrema, Khatla South Veng, Aizawl
Agreement Amount : ₹ 39,43,560.00 |  |  |  | 8: Date of Commencement: 04.02.2026
Agreement No.: T-11013/115/25/ARN/AGM/2 Dt. 21.01.2026 |  |  |  | 8: Target date of Completion: 04.05.2026
Name of Division : Aizawl Road North Division
Source of funding: 5054
Overall Physical Achievement : 100%
Sl. No. | Name of Project | Unit |  | Approved Cost (Rs. in lakh) | Date of Commencement | Target date of completion | Cumulative Progress at the end of last month |  | Achievement works during the month |  | Overall cummulative achievement |  | Remarks | Mode of contract
[7 empty] | Phy. | Fin. | Phy. | Fin. | Phy. | Fin.
1 | 2 | 3 |  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Scarifying Existing Granular Surface | 600.46 | cum | 30233 | 04.02.2026 | 04.05.2026 | 100% |  | 0% |  | 100% | (Rs. 39,43,560.00 kept in D - III) | Phy Completed | Item Rate
2 | Water Bound Macadam | 60.05 | cum | 4: 357590; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed
3 | Prime Coat | 600.46 | cum | 4: 30900; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed
4 | Tack Coat | 9322.5 | cum | 4: 3284876; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed
5 | Close Graded Premix Surfacing/Mixed Seal Surfacing | 9322.5 | cum | 4: 239961; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY, 2026 UNDER ARND
Name of Work : Resurfacing of Approach Road to Bungbangla at Zemabawk |  |  |  | 8: Name of Contractor: Lalsangliani, Kanan Veng, Aizawl
Agreement Amount : ₹ 42,97,915.00 |  |  |  | 8: Date of Commencement: 04.02.2026
Agreement No.: T-11013/115/25/ARN/AGM/3 Dt. 21.01.2026 |  |  |  | 8: Target date of Completion: 04.05.2026
Name of Division : Aizawl Road North Division
Source of funding: 5054
Overall Physical Achievement : 100%
Sl. No. | Name of Project | Unit |  | Approved Cost (Rs. in lakh) | Date of Commencement | Target date of completion | Cumulative Progress at the end of last month |  | Achievement works during the month |  | Overall cummulative achievement |  | Remarks | Mode of contract
[7 empty] | Phy. | Fin. | Phy. | Fin. | Phy. | Fin.
1 | 2 | 3 |  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Scarifying Existing Granular Surface | 3026 | cum | 161497 | 04.02.2026 | 04.05.2026 | 100% | 42.97 | 0% | - | 100% | 42.97 | Completed | Item Rate
2 | Water Bound Macadam | 458.1 | cum | 4: 2634556; 7: 100%; 9: 0%; 11: 100%; 13: Completed
3 | Prime Coat | 3026 | cum | 4: 165007; 7: 100%; 9: 0%; 11: 100%; 13: Completed
4 | Open Graded Premix Surfacing | 3026 | cum | 4: 825038; 7: 100%; 9: 0%; 11: 100%; 13: Completed
5 | Tack Coat | 3026 | cum | 4: 163827; 7: 100%; 9: 0%; 11: 100%; 13: Completed
6 | Seal Coat | 3026 | cum | 4: 347990; 7: 100%; 9: 0%; 11: 100%; 13: Completed
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY, 2026
Name of Work : Construction & Improvement of Internal roads at Chhinga Veng & Armed Veng South under SASCI 2025-26 Part-I
Name of Scheme : SASCI
Tender Amount : Rs. 384.61 lakh
Agreement Amount : Rs. 384.51 lakh
Name of Contractor : AGG Construction & Consultancy Services, Khatla South, Aizawl
Name of Sub-Division : Aizawl Road North Sub-Division-I
Sl. No. | Sub-Head of works | Unit | Qnty | Approved Cost (in lakh) | Date of Commencement | Target Date of Completion | Commulative Progress at the end of Last Month |  | Achievement of Works during the Month |  |  | Overall cumulative achievement |  | Remarks | Mode of Contract
[7 empty] | Phy | Fin | Phy | Fin |  | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 |  | 12 | 13 | 14 | 15
1 | Continuation of New Road from Lalhmingliana Sailo House to Siamphunga Lei at Tuithiang Veng | Rm | 54 | 33.04 | 2026-04-01 | 2026-12-01 | 0% | - | 14.81% | - |  | 14.81% | - | Works in progress | Item rate
2 | Continuation of Bethany Road at Chhinga Veng | Rm | 220 | 31.37 |  |  | 30.91% | - | 37.27% | - |  | 68.18% | -
3 | Construction of RCC Balcony from Pu Biakngura's House to Pu Chhawntluanga's House on Chhinga Vengthar | Rm | 120 | 97.53 |  |  | 0% | - | 0% | - |  | 0% | -
4 | Improvement of Armed Veng South Internal Road from Pu Zaliana's House to Pu Pakunga (L) House | Rm | 300 | 222.57 |  |  | 33.33`% | - | 16.67% | - | 42 | 50% | -
| Total = | Rm | 694 | 4: 384.51; 7: 21.82%; 9: 13.96%; 12: 35.78%
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY, 2026 UNDER SASCI - II
Sl No | Name of works | Unit | Approved Cost (in lakh) | Date of Comment | Target Date of Completion | Commulative Progress at the end of Last Month |  | Achievement of Works during the Month |  | Overall cumulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
SUB - DIVISION - I
1.CONSTRUCTION OF RCC DRAIN AND PCC PAVEMENT AT CHHINGA VENG AND ELECTRIC VENG
1 | Resurfacing of Armed Veng South to Bethlehem Vengthlang Road at Ch : 0.677 - 1.230 km | Rm | 10.91 | 6.12.2023 | 15.12.2023 | 100% | 151.5 | - | - | 100% | 151.5 | Phy Completed | Restricted
2 | Reconstruction of Collapsed RCC Slab Culvert on Armed Veng South to Bethlehem Vengthlang (Old Zoo Road) near Rawra Chhutna | No | 1.2 | 6.12.2023 | 15.12.2023 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
3 | Balance Work of Construction of RCC Pavement on District Jail to Lower Armed Veng Road (Service Road) | Rm | 1.84 | 10.4.2023 | 11.4.2023 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
4 | Construction of New Road from Lalhmingliana Sailo House to Siamphunga Lei at Tuithiang Phase-II | Rm | 30.14 | 11.3.2024 | 27.3.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
5 | Construction of Drainage System at Aizawl Civil Hospital, Dawrpui West Area | Rm | 14.52 | 18.3.2023 | 24.3.2023 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
6 | Construction of Retaining Wall on Dawrpui Thlanmual Plot-3 | Rm | 6.03 | 24.4.2024 | 3.5.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
7 | Construction of RCC Pavement on Hostel Square at Armed Veng South | Rm | 4.17 | 5.2.2024 | 14.2.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
8 | Construction of RCC Pavement between Pu Thansanga's House to Pu Ronghakliana's House on Armed Veng South Local Council Road | Rm | 2.17 | 19.2.2024 | 23.2.2024 | 100% | 151.5 | - | - | 100% | 151.5 | Phy Completed | Restricted
9 | Construction of PCC Pavement near Pu Larry Lalrova's House Saron Veng | Rm | 4.24 | 8.4.2024 | 13.4.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
10 | Construction of V-Shape Side drain near Rawra Chhutna | Rm | 0.11923 | 12.3.2024 | 15.3.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
11 | Construction of Retaining Wall on Dawrpui Thlanmual Plot - 1 | Rm | 10.95 | 4.4.2024 | 15.4.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
12 | Construction of Retaining Wall on Dawrpui Thlanmual Plot - 2 | Rm | 8.11 | 3.5.2024 | 14.5.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
13 | Construction of Breast Wall on Armed Veng South Local Council Road near Pu Lalnghakliana's House | Rm | 5.94 | 15.4.2024 | 20.4.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
14 | Construction of Breast Wall between Chawngneihkunga's House to Khupneihvunga's House | Rm | 6.41 | 6.2.2024 | 23.2.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
15 | Widening of Road between Chawngneihkunga's House to Khupneihvunga's House | Rm | 9.14 | 22.4.2024 | 10.5.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
16 | Construction of Retaining Wall below Chhinga Veng Thlanmual | Rm | 36.86 | 26.2.2024 | 15.3.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| TOTAL = |  | 152.7492
2. IMPROVEMENT OF ROAD FROM RAMHLUN VENGTHAR TO RAMHLUN SPORT COMPLEX, AIZAWL.
17 | Construction of RCC Balcony on Ramhlun South Cemetery at Ramhlun South | Rm | 42.94 | 8.3.2024 | 22.3.2024 | 100% | 222.94 | - | - | 100% | 222.94 | Phy Completed | Restricted
18 | Construction of RCC Frame Structure Breast Wall near Ramhlun South Cemetary | Rm | 25.61 | 8.2.2024 | 16.2.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
19 | Construction of Retaining Wall below Presbyterian Church, Laipuitlang | Rm | 3.93 | 16.1.2024 | 13.2.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
20 | Construction of RCC Pavement & Lowering on Jubilee road at Ramhlun Vengthar | Rm | 58.59 | 4.3.2024 | 22.3.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
21 | Construction of RCC Rectangular side drain with cover near Jubilee road at Ramhlun Vengthar | Rm | 3.65 | 3.4.2024 | 12.3.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
22 | Construction of Steel Grate Cover Side Drain near Jubilee road at Ramhlun Vengthar | No | 1.49 | 3.4.2024 | 10.4.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
23 | Construction of Breast wall on Turning Point at Tetea Road Ramthar North | Rm | 5.65 | 6.2.2024 | 23.2.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
24 | Construction of RCC Pavement on Tetea Road (Below Pu Dawngliana House) at Ramthar North | Rm | 7.89 | 2.4.2024 | 26.4.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
25 | Construction of Retaining wall on Tetea Road Block-I at Ramthar North | Rm | 6.63 | 1.2.2024 | 19.2.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
26 | Construction of Retaining wall on Tetea Road Block-II at Ramthar North | Rm | 1.83 | 13.1.2024 | 12.2.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
27 | Construction of Breast Wall Below Step at NHC Ramhlun Venglai | Rm | 3.33 | 15.1.2024 | 16.2.2024 | 100% | 222.94 | - | - | 100% | 222.94 | Phy Completed | Restricted
28 | Construction of Breast Wall Vertical Extension NHC at Ramhlun Venglai | Rm | 5.6 | 1.2.2024 | 19.2.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
29 | Construction of RCC Rectangular side drain with cover NHC at Ramhlun Venglai | Rm | 0.97 | 2.2.2024 | 20.2.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
30 | Construction of RCC Rectangular side drain with cover on Rokhuma Colney to PC.Lalzuiliana House(Bishop Road) at Ramthar | Rm | 2.98 | 12.3.2024 | 25.4.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
31 | Construction of Breast Wall Below St.Lawrence School at Ramthar | Rm | 6.56 | 6.3.2024 | 22.3.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
32 | Construction of Breast Wall near Boxing hall at Ramhlun Venglai | Rm | 9.38 | 26.3.2024 | 4.4.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
33 | Construction of Retaining Wall on Sihpui to Tlaklui road at Pu C Lalnunmawia's House | Rm | 8.81 | 5.3.2024 | 21.3.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
34 | Construction of PCC Pavement on ICI road Complex Vengthlang at Ramhlun Sport Complex | Rm | 3.51 | 8.3.2024 | 20.3.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
35 | Construction of Retaining wall near Pu.Rosangpuia House at Ramhlun Sport Complex | Rm | 4.22 | 5.3.2024 | 24.4.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
36 | Construction of Breast wall on LC Road near Lianhnuna Road at Ramhlun Sport Complex | Rm | 3.09 | 4.3.2024 | 25.3.2024 | 100% | - | - | - | 100% | - | Phy Completed | Restricted
37 | Construction of RCC Side drain near Pu.Para House at Ramhlun Sport Complex | Rm | 0.49 | 5.3.2024 | 20.3.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
38 | Construction of RCC Footpath on LC Road near Pu HC Thangvela's House to Pu B Zanghinglova's House | Rm | 16.85 | 12.3.2024 | 25.3.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| TOTAL = |  | 224
WORK UNDER IMPLEMENTATION OF ARTICLE 275 (1) PHASE - II
39 | Construction of Bethany Road at Chhinga Veng | Rm | 70 | 7.10.2023 | 30.11.2023 | 100% | - | - |  | 100% |  | Phy Completed | Restricted
SUB - DIVISION - II
UPAGRADATION OF BETHEL VENG ROAD AT ZEMABAWK, AIZAWL WITH APPROACH ROAD TO ZOKHAWSANG BYPASSS ROAD
40 | Upagradation of Bethel Veng Road at Zemabawk, Aizawl with approach road to Zokhawsang Bypass Road
| 1. PCC Pavement at Ch: 0.000 - 0.580kmp | Rm | 57.8 | 14.12.23 | 14.12.24 | 100% | 154.89 | - | - | 100% | 154.89 | Phy Completed | Restricted
| 2. Construction of PCC V shape side drain at Ch: 0.000kmp | Rm | 1.57 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 3. Clearance of Landslip | Nos | 20.83 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
41 | Additional requirement for Upgradation of Bethel Veng road at Zemabawk
| 1. Earthwork for Widening (Additional) | Km | 69.54 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 2. RCC Frame Retaining Walls no1 | Rm | 5.2 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| TOTAL = |  | 154.94
IMPROVEMENT OF MUTHI - TUIRIAL LINK ROAD
42 | 1. Widening & Curve Improvement | Km | 134.74 | 14.12.23 | 14.12.24 | 100% | 170.24 | - | - | 100% | 170.24 | On-Going | Restricted
2. Construction of Slab Culvert
| i. Slab Culvert Type-I | Nos | 11.5 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | On-Going | Restricted
3. Construction of Retaining Wall
| i. Retaining Wall Type - I | Rm | 10 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Work in Progress | Restricted
| ii. Retaining Wall Type - II | Rm | 14 | 4: 14.12.23; 5: 14.12.24; 6: -; 8: -; 10: -; 12: Not yet started
| TOTAL = |  | 170.24
CONSTRUCTION OF BAMBOO LINK ROAD FROM NAUSEL, CHAMDUR, LUNGSANG, PUMPELHSEI, KAWRBEL
43 | Construction of Nausel - Tuirial Bamboo Link Road |  |  | 7: 261.48; 9: -; 11: 261.48
| 1. Formation Cutting | Km | 36.01 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 2. Construction of Slab Culvert | Nos | 59.39 | 6: 100%; 8: -; 10: 100%; 12: Phy Completed; 13: Restricted
| At chainage between 0.000 to 3.500 Kmp | Nos |  | 4: 14.12.23; 5: 14.12.24; 6: -; 8: -; 10: -; 12: Not yet started
| 3. Construction of Retaining Wall |  |  | 6: 100%; 8: -; 10: 100%; 12: Phy Completed; 13: Restricted
At chainage between 0.000 to 3.500 Kmp
| Retaining Wall | Nos | 30.92 | 4: 14.12.23; 5: 14.12.24; 6: -; 8: -; 10: -; 12: Not yet started
44 | Concrete Pavement of Sihphir Neibawih khawhnuai kawng balance |  |  | 7: 261.48; 11: 261.48
| 1. Concrete Pavement | Rm | 36.28 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
2. Construction of Slab Culvert
| At chainage between 0.000 to 0.503 Kmp | Nos | 21.52 | 4: 14.12.23; 5: 14.12.24; 6: -; 8: -; 10: -; 12: Not yet started
| Retaining Wall Type - I | Nos | 13.99
| Retaining Wall Type - II | Nos | 8.2
45 | Construction of Hmunte Road at Muthi
| 1. Formation Cutting | Km | 36.57 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy completed | Restricted
| 2. Construction of Slab Culvert |  |  | 6: 100%; 8: -; 10: 100%; 12: Phy completed; 13: Restricted
| At chainage between 0.000 to 1.000 Kmp | Nos | 16.57 | 4: 14.12.23; 5: 14.12.24; 6: -; 8: -; 10: -; 12: Not yet started
| At chainage between 1.000 to 2.000 Kmp | Nos | 14.5 | 4: 14.12.23; 5: 14.12.24; 6: -; 8: -; 10: -; 12: Not yet started
3. Construction of Retaining Wall
At chainage between 0.000 to 2.000 Kmp
| Retaining Wall | Rm | 7.18 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy completed | Restricted
46 | Construction of Chamdur - Kawrbellui Road
| 1. Formation Cutting | Km | 30.5 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| TOTAL = |  | 311.63
CONSTUCTION OF ROAD FROM ZEMABAWK NORTH TO CWC AND MUALZEN
47 | Construction of New Road from Zemabawk North Dinthar Veng to CWC including Protetion Works & Cross Drain |  |  | 7: 246.4; 9: -; 11: 246.4
| 1. Formation Cutting | Km | 72.46 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 2. Construction of Slab Culvert Type-I | Nos | 8 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 3. Construction of Slab Culvert Type-II | Nos | 12 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 4. Construction of Slab Culvert Type-III | Nos | 16.94 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 5. Construction of Retaining Wall Type-I | Rm | 25 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
48 | Construction of New Road from Zemabawk North Thlanmual Hnuai to Mualzen including Protetion Works & Cross Drain
| 1. Formation Cutting | Km | 60.12 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
2. Construction of Slab Culvert
| At chainage between 0.000 to 1.500 Kmp | Nos | 28.6 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| At chainage between 1.500 to 3.000 Kmp | Nos | 23.28 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| TOTAL = |  | 246.4
CONSTRUCTION OF ROAD FROM FALKLAND TO GALILEE VIA MITLAMUAL AT ZEMABAWK, AIZAWL
49 | Construction of Widening & New Road from Falkland to Mitlamual including protection Works & Cross Drain |  |  | 7: 134.4; 9: -; 11: 134.4
| 1. Widening and New Cutting | Km | 42.16 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 2. Construction of Slab Culvert Type-I | Nos | 2.64 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
50 | Construction of New Road from Zemabawk Galile Vailui to Mitlamual including Protection Works and Cross Drain
| 1. Formation Cutting | Km | 52.09 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 2. Construction of PCC Pavement | Rm | 22.88 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 3. Construction of Slab Culvert Type-I | Nos | 14.63 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| TOTAL = |  | 134.4
CONSTRUCTION OF ROAD FROM FALKLAND TO ZEMABAWK NORTH VIA THUAMPUI
51 | Construction of New Road from Falkland Penniel Road to Thuampui Vengthar and BS Farm to UPC BiakIn at Pi Vani Lui Link Road including Protection Work & Cross Drain (1.00 Km) |  |  | 7: 151.99; 9: -; 11: 151.99
| 1. Widening of Road | Rm | 29.22 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 2. Construction of PCC Pavement on BS Farm to UPC BiakIn | Rm | 32.18 | 4: 14.12.23; 5: 14.12.24; 6: -; 8: -; 10: -; 12: Not yet started
| 3. Construction of Slab Culvert at Ch : 0.360 Kmp | No | 4.3 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 4. Construction of RCC Link Drain at Ch 0.000-0.112 km | Rm | 25 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 5. Construction of RCC Link Drain With Cover at Ch 0.000 km | Rm | 3.72 | 4: 14.12.23; 5: 14.12.24; 6: -; 8: -; 10: -; 12: Not yet started
| 6. Construction of RCC Link Drain With Cover at Ch 0.120 km | Rm | 5.58 | 4: 14.12.23; 5: 14.12.24; 6: -; 8: -; 10: -; 12: Not yet started
52 | Construction of New Road RAY to BS Farm Falkland including Protection Works and Cross Drain (0.800Km) | bar: 9
| 1. Lowering and Widening | Rm | 10.14 | 14.12.23 | 14.12.24 | 100% | - | - |  | 100% |  | Phy Completed | Restricted
| 2. Construction of PCC Pavement on RAY to BS Farm Falkland | Rm | 10.48 | 4: 14.12.23; 5: 14.12.24; 6: -; 8: -; 10: -; 12: Not yet started
| 3. Construction of Retaining Wall | Rm | 8.84 | 4: 14.12.23; 5: 14.12.24; 6: -; 8: -; 10: -; 12: Not yet started
| 4. Construction of V-Shape | Rm | 4.2 | 4: 14.12.23; 5: 14.12.24; 6: -; 8: -; 10: -; 12: Not yet started
| 5. Construction of missing Link at BCM Multipurepose Centre at Falkland Veng | Rm | 6.34 | 4: 14.12.23; 5: 14.12.24; 6: -; 8: -; 10: -; 12: Not yet started
53 | Construction of Step near Pu Ringdika's House | Rm | 1.4 | 4: 14.12.23; 5: 14.12.24; 6: -; 8: -; 10: -; 12: Not yet started
54 | Repairing of Kailiana Concrete Pavement Road at Zemabawk North | Rm | 10.6 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| TOTAL = |  | 152
CONSTRUCTION OF TUIRIAL AIRFIELD TO MUTHI AND ZOKHAWSANG AGRICULTURE
55 | Construction of New Road from Tuirial Airfield Runway to Muthi lui Lalchhuana Leilet including Protetion Works & Cross Drain |  |  | 7: 107.072; 9: -; 11: 107.072
| 1. Formation Cutting | Km | 40.94 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 2. Construction of RCC Slab Culvert | No | 66.58 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| TOTAL = |  | 107.52
CONSTRUCTION OF ROAD FROM THUAMPUI TO NH - 6 (ZEMABAWK)
56 | Construction of Link Drain near Pi Diki House at Sihphir | Rm | 10 | 14.12.23 | 14.12.24 | 100% | 181.88 | - | - | 100% | 181.88 | Phy Completed | Restricted
57 | Pavement of AR Complex at Zokhawsang | Km | 59 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
58 | Resurfacing of Women Polytechnic Internal road at Durtlang | Km | 27 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
59 | Improvement of Dinthar Veng to Muthi Lui Road (Balance Portion) at Zemabawk
| 1. Concrete Pavement | Rm | 31.5 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 2. Construction of RCC Slab Culvert No.1 | No | 6.3 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 2. Construction of RCC Slab Culvert No.2 | No | 5.91
| 3. Construction of Retaining Wall | Rm | 5 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 4. Construction of U shape Side Drain | Rm | 8.29 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
60 | Resurfacing of Sihpui to Ramhlun Vengthar Bus Turning Point at Ch : 1.052 - 1.357 km | m² | 11 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
61 | Patch repair of Vaivakawn to MZU via Zonuam. | m² | 18 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| TOTAL = |  | 182
UPGRADATION OF INTERNAL ROADS AT DURTLANG, BAWNGKAWN, CHALTLANG, ZUANGTUI, RAMHLUN & RAMTHAR
62 | Construction of Rectangular Side Drain with cover at Tatkawng Veng | Rm | 1.68 | 14.12.23 | 14.12.24 | 100% | 134.4 | - | - | 100% | 134.4 | Phy Completed | Restricted
63 | Construction of Concrete Pavement of Durtlang tlak lam Thlanmual Road | Rm | 20 | 4: 14.12.23; 5: 14.12.24; 6: -; 8: -; 10: -; 12: Not yet started
64 | Construction of Concrete Pavement of Gosen Veng Kawngpui at Zuangtui | Rm | 7 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
65 | Construction of PCC Flooring at Rivenga Road at Muanna Veng | Rm | 10 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
66 | Construction of PCC Flooring Internal Road - Zamliana Road to K.Thankunga Road at Selesih | Rm | 5 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
67 | Vantlang Step near K.Thankunga House at Selesih | Rm | 5 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
68 | Construction of PCC Flooring Laitan Ramthar Biak In lane at Leitan Ramthar | Rm | 10 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
69 | Construction of Concrete Pavement on Bawngkawn Thlanmual to Thuampui Road | Rm | 22.87 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
70 | Steel Grate Cover Side Drain on PC.Malsawma House to Rev.C.Vanlalhruaia House at Ramhlun South | Rm | 2.2727 | 4: 14.12.23; 5: 14.12.24; 6: -; 7: -; 12: On-Going
71 | Construction of RCC Foot Step near PC.Lalzuiliana House Ramthar | Rm | 14.6908 | 14.12.23 | 14.12.24 | - | - | 0% |  | 0% |  | Not yet started
72 | Construction of RCC Link Drain near PC.Lalzuiliana House at Ramthar | Rm | 8.3752 | 14.12.23 | 14.12.24 | - | - | 0% |  | 0% |  | Not yet started
73 | Steel Grate Cover Side Drain on PC Malsawma House to Rev. C.Vanlalhruaia House at Ramhlun South | Rm | 8.04 | 14.12.23 | 14.12.24 | - | - | - | - | - | - | Not yet started
74 | Construction of RCC Foot Step near PC.Lalzuiliana House Ramthar | Rm | 16.58 | 4: 14.12.23; 5: 14.12.24; 6: -; 8: -; 10: -; 12: Not yet started
75 | Construction of RCC Link Drain near PC.Lalzuiliana House at Ramthar | Rm | 8.42 | 4: 14.12.23; 5: 14.12.24; 6: -; 8: -; 10: -; 12: Not yet started
76 | Construction of Breast Wall Below PC.Laltanpuia House at Ramthar North | Rm | 7.37 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
77 | Construction of Breast Wall near Pu.Lalrammuana Ralte House at Ramthar North | Rm | 5.76 | 4: 14.12.23; 5: 14.12.24; 6: -; 8: -; 10: -; 12: Not yet started
78 | Construction of RCC Foot Step near Pi.Manmawii House at Ramhlun South | Rm | 6.68 | 4: 14.12.23; 5: 14.12.24; 6: -; 8: -; 10: -; 12: Not yet started
| TOTAL = |  | 134.4
IMPROVEMENT OF ROAD FROM DURTLANG LEITAN TO DURTLANG RAMTHAR AT DURTLANG
79 | Construction of Road at Selesih. Aizawl (Sh: Construction of Concrete Pavement and Culvert etc) |  |  | 7: 224.16; 9: -; 11: 224.16
| 1. Concrete Pavement of Pu Dinga Road | Rm | 5 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
80 | Improvement of road at Durtlang North, Aizawl. (Sh: Construction of Concrete Pavement etc)
| 1. Construction of Concrete Pavement & Cross Drain on Vungkhama road inlcuding Chhingtei Road at Durtlang North | Rm | 15 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 2. Construction of Concrete Pavement of Durtlang North Thlanmual | Rm | 10 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
81 | Improvement of road at Durtlang, Aizawl. (Sh : Construction of Concrete Pavement, Cross Drain with cover, V Shape Side Drain, slab culvert and link Drain etc) | bar: 7; 9
| 1. Construction of PCC V shape Side Drain at Centenary Road & Women Polytechnic approach road at Durtlang | Rm | 5 | 4: 14.12.23; 5: 14.12.24; 6: -; 8: -; 10: -; 12: Not yet started
| 2. Concrete Pavement of Lalnu road at Suaka Veng, Durtlang (Balance Portion) | Rm | 5.4 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 3. Construction of Cross Drain with cover on Durtlang Field | Rm | 0.99516 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 4. Construction of Step including Link Drain at Centenary Road, Durtlang | Rm | 20 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
82 | Construction and Improvement of road at Durtlang Leitan, Aizawl.(Sh : Construction of Concrete Pavement, RCC frame Retaining Wall, Cross Drain with cover, U Shape Side Drain and link Drain etc)
| 1. Construction of PCC V Shape Side and Retaining Wall at Gospel Thunder Team compound, Durtlang Leitan | Rm | 20 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 2. Construction of RCC Frame RW at Zotui Road, Durtlang Leitan | Rm | 3.5 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 3. Patch repair of Durtlang Leitan SIRD Road | Km | 5.05 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
83 | Improvement of Road at Durtlang Ramthar, Aizawl (Sh : Construction of Concrete Pavement, Cross Drain and Re-Surfacing) | bar: 7; 9
| 1. Resurfacing of 3rd Lane at Durtlang Ramthar | Rm | 29.5 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 2. Concrete pavement of approach road to Durtlang Ramthar Prebyterian Church including cross drainage | Km | 30.5 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
84 | Improvement of Road at Chaltlang Lily veng, AizawL (Sh : Widening . of road, Construction of Concrete Pavement, RCC R/Wall and Re-Surfacing etc)
| 1. Resurfacing of Chaltlang Lily Veng internal road (Balance) | Km | 3 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 2. Reconstruction of step from State Guest House to Lily Veng internal road | Rm | 6 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 3. Construction of RCC Balcony & Masonry Step near R.lalmanga House at Chaltlang Lily Veng | Rm | 14 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
85 | Improvement of Road at Chaltlang, Aizawl. (Sh: Junction improvement. Construction of Concrete Pavement, U Shape drain, Retainning Wall & Step) | bar: 7; 9; 11
| 1. Concrete Pavement of Road near F.Malsawma Residence at Chaltlang | Rm | 2.5 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 2. Construction of Retaining Wall & Concrete pavement on AMC Road at Dingdi Veng, Chaltlang | Rm | 9.7 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
86 | Improvement of Road at Bawngkawn, Aizawl. (Sh : Construction of Balcony, Link Drain, Retaing Wall & Concrete Pavement)
| 1. Construction of retaining Wall near Pu. Salemthara Residence at Brigade, Bawngkawn | Rm | 2.6 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 2. Concrete Pavement of Liansailova road, Bawngkawn | Rm | 10 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 3. Concrete Pavement of Shalom Road at Bawngkawn Hmar Veng (Balance Portion) | Rm | 10 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| 4. Concrete Pavement on Upper Bawngkawn Hmar Veng | Rm | 4.5 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
87 | Construction of additional protection work at Bethel Veng | Rm | 13 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| TOTAL = |  | 225.2452
IMPROVEMENT OF ROAD FROM ZEMABAWK TO LUNGBIAL ROAD IN THE LOCALITY OF ZEMABAWK AT AIZAWL
88 | CONSTRUCTION OF ROAD AT SIHPHIR |  |  | 7: 214.17; 9: -; 11: 214.17
| i.Concrete pavement of approach road to Sihphir Rescue Center road at Sihphir Kawnveng | Rm | 8.8 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| ii.Formation Cutting , Concrete Pavement & Step of Sunhlu tlang (Prayer Mountain) at Sihphir Tlang Veng | Rm | 7.9 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| iii.Construction of Step including retaining wall near Pu Zakhuma House at Sihphir field veng | Rm | 3.66 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| iv.Construction of link Drain with cover near Pi Liani House at Sihphir Dinthar | Rm | 1.74 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| v.Construction of Link drain near Pu H.Lalfakzuala, Sihphir Dinthar | Rm | 2.61 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
89 | CONSTRUCTION OF CONCRETE PAVEMENT AT ZUANGTUI, AIZAWL
| i.RCC Balcony Gosen Veng to 132 KV substation at Zuangtui | Rm | 26.13 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
90 | CONCRETE PAVEMENT RIVENGA ROAD AT MUANNA VENG, AIZAWL
| i.Concrete Pavement of Rivenga Road at Muanna Veng | Rm | 7.3 | 14.12.23 | 14.12.24 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
91 | CONSTRUCTION OF ROAD AT MUTHI, AIZAWL | bar: 9; 11
| i.Concrete Pavement at ch:0.000 - 0.715kmp Muthi peng to kawn | Rm | 8.6 | 14.12.23 | 14.12.24 | 100% | - | - |  | 100% |  | Phy Completed | Restricted
92 | CONSTRUCTION OF ROAD AT NAUSEL
| i.Concrete Pavement at Nausel Thlanmual kawng | Rm | 8.2 | 14.12.23 | 14.12.24 | 100% | - | - |  | 100% |  | Phy Completed | Restricted
93 | IMPROVEMENT OF ROAD AT SIHPHIR VENGHLUN
| i.Construction of Retaining Wall at Thuampui Selesih road at Ch:4.300Kmp, Durtlang | Rm | 6.14 | 14.12.23 | 14.12.24 | 100% | - | - |  | 100% |  | Phy Completed | Restricted
94 | Construction of New Road from Zemabawk North Thlanmual to Thuampui Thlanmual including Protetion Works & Cross Drain
| i. Formation Cutting | Km | 51.36 | 14.12.23 | 14.12.24 | 100% | - | - |  | 100% |  | Phy Completed | Restricted
| ii. Construction of RCC Slab Culvert | No | 33.04 | 14.12.23 | 14.12.24 | 100% | - | - |  | 100% |  | Phy Completed | Restricted
95 | CONSTRUCTION OF ROAD AT FALKLAND, AIZAWL
| i.Construction of PCC Pavement on Local Council Road to RAY at Falkland | Rm | 27.79 | 14.12.23 | 14.12.24 | - | - | - | - | - | - | Not yet started
| ii.Construction of PCC Pavement on Rabboni Road at Falkland | Rm | 5.1404 | 14.12.23 | 14.12.24 | - | - | - | - | - | - | Not yet started
| iii.Construction of PCC Pavement on Local Council Road Falkland | Rm | 11.332 | 14.12.23 | 14.12.24 | - | - | - | - | - | - | Not yet started
| iv.PCC Pavement on Approach Road to Vai Lui via Rev Lalsangliana's House at Falkland Veng | Rm | 5.7395 | 14.12.23 | 14.12.24 | - | - | - | - | - | - | Not yet started
| TOTAL = |  | 215.4818
SUB - DIVISION - III
CONSTRUCTION OF PCC PAVEMENT AT SIHHMUI TO NH-54. (LENGTH = 7.00Kms, PCC PAVEMENT = 7.00Kms)
96 | Widening of road from Law college to PCI road at Luangmual, Aizawl (Sh: Earth Work for Widening of existing road) | Rm. | 11.95 | 2023-12-14 | 2024-12-14 | 100% | 194.63 | - | - | 100% | 194.63 | Phy Completed | Restricted
97 | Improvement & Upgradation of road at Chawlhhmun, Aizawl |  | 26 | 4: 2023-12-14; 5: 2024-12-14
| Sh: 1. Construction of PCC Pavement of Pu Muantea's road at Chawlhhmun | Rm. |  | 6: 100%; 8: -; 10: 100%; 12: Phy Completed; 13: Restricted
| 2. Construction of PCC Pavement near Pu Fabiana's house at Chawlhhmun | Rm. |  | 6: 100%; 8: -; 10: 100%; 12: Phy Completed; 13: Restricted
98 | Improvement & Upgradation of road at Zotlang, Aizawl |  | 20.29 | 4: 2023-12-14; 5: 2024-12-14; 7: -; 9: -; 11: -
| Sh: 1. Construction of RCC Pavement at Zotlang to Zohnuai | Rm. |  | 6: 100%; 8: -; 10: 100%; 12: Phy Completed; 13: Restricted
| 2. Construction of Retaining Wall for Pi Romawii Approach Road at Zotlang | Rm. |  | 6: 100%; 8: -; 10: 100%; 12: Phy Completed; 13: Restricted
| 3. Construction of RCC Pavement at Zotlang to Zohnuai Biak In | Rm. |  | 6: 100%; 8: -; 10: 100%; 12: Phy Completed; 13: Restricted
99 | Construction of approach road (RCC Pavement) to Community Hall (NH 44A) at Sihhmui | Rm. | 15.91 | 2023-12-14 | 2024-12-14 | 100% |  | - |  | 100% |  | Phy. Completed | Restricted
100 | Improvement & Upgradation of road from PCI to Anganwadi at Lungverh |  | 77.98 | 4: 2023-12-14; 5: 2024-12-14
| Sh: 1. Construction of RCC Pavement from PCI to Anganwadi at Lungverh | Rm. |  | 6: 100%; 8: -; 10: 100%; 12: Phy. Completed; 13: Restricted
| 2. Construction of RCC Slab Culvert at Thlanmual kawr | Rm. |  | 6: 100%; 8: -; 10: 100%; 12: Phy. Completed; 13: Restricted
| 3. Construction of RCC Slab Culvert at Pu Rinnunga kawmthlang | Rm. |  | 6: 100%; 8: -; 10: 100%; 12: Phy. Completed; 13: Restricted
| 4. Retaining wall at F Suakliana Kawmchhak | Rm. |  | 6: 100%; 8: -; 10: 100%; 12: Phy. Completed; 13: Restricted
101 | Rangvamual internal road | Rm | 23.27 | 6: 100%; 8: -; 10: 100%; 12: Phy. Completed; 13: Restricted
102 | Phunchawng internal road | Rm | 19.23 | 6: 100%; 8: -; 10: 100%; 12: Phy. Completed; 13: Restricted
| TOTAL = |  | 194.63
IMPROVEMENT OF INTERNAL ROADS AT HUNTHAR, CHANMARI WEST, RANGVAMUAL, PHUNCHAWNG & CHHINGA VENG. (IMPROVEMENT OF ROADS PCC PAVEMENT = 20.00 KMS, PAVEMENT = 5.00 KMS, LINK DRAIN = 100.00M)
103 | Patch Repair and Seal Coating of Approach Road to Tanhril, Aizawl | Rm | 23.08 | 2023-12-14 | 2024-12-14 | 100% | 61.48 | - | - | 100% | 61.48 | Phy. Completed | Restricted
104 | Construction of PCC Pavement of Approach Road to Tawngtai Bethel Camping Centre, Sakawrtuichhun, Aizawl | Rm. | 9.49 | 2023-12-14 | 2024-12-14 | 100% |  | - |  | 100% |  | Phy. Completed | Restricted
105 | Rigid Pavement of Gan Sabra Road | Rm. | 19.33 | 2023-12-14 | 2024-12-14 | 100% |  | - |  | 100% |  | Phy. Completed | Restricted
106 | Construction of PCC Pavement of Road from Saikaphleia' House to Muanthanga's House at Lungverh. Length = 120.00Rm. | Rm. | 9.51 | 2023-12-14 | 2024-12-14 | 100% |  | - |  | 100% |  | Phy. Completed | Restricted
| TOTAL = |  | 61.41
CONSTRUCTION OF LUNGHLU ROAD AT CHANMARI WEST AIZAWL (Length = 4.00Kms, Ew = 4.00Kms, Pavement = 4.00Kms, Side Drain = 4500m, R/W 30m, Culvert = 10.Nos)
107 | Construction of RCC Frame structure Retaining Wall I at Lunghlu Road, Hunthar | Rm | 14.49 | 2023-12-14 | 2024-12-14 | 100% | 163.51 | - | - | 100% | 163.51 | Phy. Completed | Restricted
108 | Patch repair and Seal coat of MUP Road at Chanmari West, Aizawl | Rm | 11.5532 | 2023-12-14 | 2024-12-14 | 100% |  | - |  | 100% |  | Phy. Completed | Restricted
109 | Patch repair and Seal Coat from BT Bakery to Protective Home Via Zarkawt Thlanmual | Rm | 29.9487 | 2023-12-14 | 2024-12-14 | 100% |  | - |  | 100% |  | Phy. Completed | Restricted
110 | Construction of RCC Road at Methodist mual Turning Point to Edenthar Anganwadi Centre No. 1 at Edenthar | Rm | 8.76 | 2023-12-14 | 2024-12-14 | 100% |  | - |  | 100% |  | Phy. Completed | Restricted
111 | Construction of RCC Link drain near Hotel Platinum at Zarkawt | Rm | 0.84926 | 6.12.2023 | 9.12.2023 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
112 | Improvement of Zarkawt Valley Approach Road Phase-II | Rm | 47.0033 | 19.2.2024 | 29.2.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
113 | Construction of Retaining wall near Babula's House at Chanmari | Rm | 13.28 | 5.2.2024 | 14.2.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
114 | Repair of Link Drain with Cover near J.Thangdailova House at Electric Veng | Rm | 9.64 | 8.2.2024 | 16.2.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
115 | Construction of New Cemetery Road at Electric Veng | Rm | 28 | 2.2.2024 | 15.2.2024 | 100% |  | - |  | 100% |  | Phy Completed | Restricted
| TOTAL = |  | 163.5244
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY, 2026 ARND
Name of Work : Widening and Pavement of roads from Federation Enclave, Ainawn to Luangmual Thlanmual via Gan Sabra Luangmual under SASCI 2025-2026 Part-I |  |  |  | 9: Name of Contractor : LL Consultancy, Chhinga Veng
Agreement Amount : ₹ 2,57,53,982.11 |  |  |  | 9: Date of Start of Work : 25.02.2026
Agreement No.: AGM-18/SBD/CE-HW/2025-2026 Dt. 10.02.2026 |  |  |  | 9: Stipulated Date of Completion : 25.02.2027
Name of Division : Aizawl Road North Sub-Division-III
Source of funding: SASCI-I
Overall Physical Achievement : 7.00%
Sl. No. | Name of Project | Unit |  | Approved Cost (Rs. in lakh) | Date of Commencement | Target date of completion | Cumulative Progress at the end of last month |  | Achievement works during the month |  | Overall cummulative achievement |  | Remarks | Mode of contract
[7 empty] | Phy. | Fin. | Phy. | Fin. | Phy. | Fin.
1 |  | 3 |  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Earthwork | 1400 | Rm | 11.9455 | 2026-02-25 | 2027-02-25 | 45% | - | 5% | - | 50% | - | Work in Progress | Item Rate
2 | Flexible Pavement | 0.4 | Rm | 17.546 |  |  | 0% | - | 0% | - | 0% | - | Not yet started
3 | Rigid Pavement | 1400 | Rm | 135.4398 |  |  | 0% | - | 0% | - | 0% | - | Not yet started
4 | Hume Pipe Culvert | 6 | No. | 24.1483 |  |  | 16% | - | 0% | - | 16% | - | Work in Progress
5 | Extension of Hume Pipe Culvert | 4 | No. | 8.7248 |  |  | 0% | - | 0% | - | 0% | - | Not yet started
6 | Retaining Wall | 80 | Rm | 35.0004 |  |  | 0% | - | 20% | - | 20% | - | Work in Progress
7 | V-shaped Side Drain | 1200 | Rm | 24.7351 |  |  | 0% | - | 0% | - | 0% | - | Not yet started
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY, 2026 UNDER ARND
Name of Work : Construction of Approach Road to Thuhruk Lui Bridge on Agriculture Link Road at Mat Phai, Serchhip and Bengbawng Zau at Durtlang, Aizawl District |  |  |  | 8: Name of Contractor: Lalrintluangi, Durtlang Dawrkawn, Aizawl
Agreement Amount : ₹ 2,38,41,678.00 |  |  |  | 8: Date of Commencement: 19.09.2025
Agreement No.: AGM-6/SE-CC/PWD/2025-2026 Dt. 04.09.2025 |  |  |  | 8: Target date of Completion: 19.05.2026
Name of Division : Aizawl Road North Division
Source of funding: SASCI-V
Overall Physical Achievement : 100%
Sl. No. | Name of Project | Unit |  | Approved Cost (Rs. in lakh) | Date of Commencement | Target date of completion | Cumulative Progress at the end of last month |  | Achievement works during the month |  | Overall cummulative achievement |  | Remarks | Mode of contract
[7 empty] | Phy. | Fin. | Phy. | Fin. | Phy. | Fin.
1 | 2 | 3 |  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Thuhruk lui bridge on Agriculture link Road at Mat Phai, Serchhip | 224.64 | cum | 8493645 | 19.09.2025 | 19.05.2026 | 0% | 74.64 | 100% | - | 100% | 74.64 | Phy Completed | Item Rate
2 | Bengbawng Zau at Durtlang, Aizawl District
a | Widening | 1574 | Rm | 4: 3398792; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed
b | Pavement | 1541 | Rm | 4: 4073045; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed
a | Retaining Wall | 89 | Rm | 4: 2447247; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed
b | RCC Frame Retaining Wall | 43 | Rm | 4: 1659702; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed
c | V-Shape Side Drain | 1120 | Rm | 4: 3428100; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed
d | Drain Cover | 60 | Rm | 4: 141147; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed
e | Cross Drain | 2 | No. | 4: 200000; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY, 2026 UNDER ARND
Name of Work : Construction of Approach Road to IGC Complex, Luangmual under SASCI Part V of 2024-2025 |  |  |  | 8: Name of Contractor: Zonunpuii, Kolasib Hmar Veng
Agreement Amount : ₹ 4,80,67,489.00 |  |  |  | 8: Date of Commencement: 03.07.2025
Agreement No.: AGM-2/SE-CC/PWD/2025-2026 Dt. 18.06.2025 |  |  |  | 8: Target date of Completion: 03.07.2026
Name of Division : Aizawl Road North Sub-Division-III
Source of funding: SASCI-V
Overall Physical Achievement : 100%
Sl. No. | Name of Project | Unit |  | Approved Cost (Rs. in lakh) | Date of Commencement | Target date of completion | Cumulative Progress at the end of last month |  | Achievement works during the month |  | Overall cummulative achievement |  | Remarks | Mode of contract
[7 empty] | Phy. | Fin. | Phy. | Fin. | Phy. | Fin.
1 | 3 | 3 |  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Improvement of IGC, Luangmual |  |  | 5: 2025-07-03; 6: 2026-07-03; 8: 470.73; 10: -; 12: 470.73
a | Earthwork | 200 | Rm | 4: 978568; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed; 14: Item Rate
b | Flexible Pavement | 1500 | Rm | 4: 20821135; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed
c | Re-construction of slabs culvert | 4 | No. | 4: 988218; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed
d | Hume Pipe Culvert | 5 | No. | 4: 1545232; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed
e | Retaining Wall | 60 | Rm | 4: 1773085; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed
f | RCC Line side drain with cover | 200 | Rm | 4: 1374490; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed
g | Trapezoidal side drain | 500 | Rm | 4: 1632485; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed
2 | Improvement of road from Tanhril Presbyterian Church to MZU
a | Flexible Pavement | 800 | Rm | 4: 6170189; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed; 14: Item Rate
b | Hume Pipe Culvert | 2 | No. | 4: 996811; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed
3 | Improvement of road from Tlana Lungdawh kawn to PWD Site |  |  | 5: 2025-07-03; 6: 2026-07-03; 8: -; 10: -; 12: -
a | Earthwork | 980 | Rm | 4: 1456657; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed; 14: Item Rate
b | Rigid Pavement | 1000 | Rm | 4: 7526950; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed; 14: Item Rate
c | Flexible Pavement | 800 | Rm | 4: 1308555
d | Hume Pipe Culvert | 3 | No. | 4: 1495114; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed; 14: Item Rate
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY, 2026 UNDER ARND
Name of Work : Improvement of Road from Ainawn to Tuithum |  |  |  | 8: Name of Contractor: F. Lalmalsawma, Tuikual
Agreement Amount : ₹ 16,35,30,525.00 |  |  |  | 8: Date of Commencement: 15.07.2025
Agreement No.: AGM-3/SE-CC/PWD/2025-2026 Dt. 01.07.2025 |  |  |  | 8: Target date of Completion: 15.07.2026
Name of Division : Aizawl Road North Sub-Division-III
Source of funding: SASCI-V
Overall Physical Achievement : 18.50%
Sl. No. | Name of Project | Unit |  | Approved Cost (Rs. in lakh) | Date of Commencement | Target date of completion | Cumulative Progress at the end of last month |  | Achievement works during the month |  | Overall cummulative achievement |  | Remarks | Mode of contract
[7 empty] | Phy. | Fin. | Phy. | Fin. | Phy. | Fin.
1 | 2 | 3 |  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Earthwork | 4682 | Rm | 20371452 | 2025-07-15 | 2026-07-15 | 95% | 614.94 | 0% | 526.32 | 95% | 1141.26 | Work in Progress | Item Rate
2 | RCC side drain | 2000 | Rm | 4: 7896319
3 | RCC Slab Culvert | 4 | No. | 4: 2912158
4 | Hume Pipe Culvert | 5 | No. | 2614215 |  |  | 100% |  | 0% | - | 100% | - | Phy Completed | Item Rate
5 | Retaining Wall | 200 | Rm | 9720546 |  |  | 60% |  | 10% | - | 70% | - | Work in Progress | Item Rate
6 | RCC Frame Structure Retaining Wall | 70 | Rm | 4: 3729602; 7: 20%; 9: 20%; 11: 40%; 13: Work in Progress; 14: Item Rate
7 | Minor Bridge | 4 | No. | 4: 23515882
8 | Rigid Pavement | 2380 | Rm | 4: 74239201
9 | Flexible Pavement | 2000 | Rm | 4: 18531150
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY, 2026 UNDER ARND
Name of Work : Construction of Various Earth Retaining and Drainage Structure for Mitigation of Vaivakawn Zohnuai Subsidence Areas |  |  |  | 8: Name of Contractor: Jenny Lalthansangi, Vavakawn Zohnuai
Agreement Amount : ₹ 2,96,11,018.00 |  |  |  | 8: Date of Commencement: 15.07.2025
Agreement No.: AGM-4/SE-CC/PWD/2025-2026 Dt. 01.07.2025 |  |  |  | 8: Target date of Completion: 01.03.2026
Name of Division : Aizawl Road North Sub-Division-III
Source of funding: SASCI-V
Sl. No. | Name of Project | Unit |  | Approved Cost (Rs. in lakh) | Date of Commencement | Target date of completion | Cumulative Progress at the end of last month |  | Achievement works during the month |  | Overall cummulative achievement |  | Remarks | Mode of contract
[7 empty] | Phy. | Fin. | Phy. | Fin. | Phy. | Fin.
1 | 2 |  | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Breast Wall on lower side of Pu Sangthanmawia's Land. | 20 | Rm | 29611018 | 2025-07-15 | 2026-03-01 | 100% | 307.94 | 0% | - | 100% | 307.94 | Phy Completed | Item rate
2 | Construction of Breast Wall on Uphill side of RK Road. | 30 | 3: Rm; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed
3 | Construction of Composite Retaining Wall (Section 1) above NH-6 | 28 | 3: Rm; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed
4 | Construction of Composite Retaining Wall(Section 2) above NH-6 | 28 | 3: Rm; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed
5 | Construction of Breast Wall above NH-6(below RK Road) | 25 | 3: Rm; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed
6 | Construction of Breast Wall on Uphill Side of NH-6 (Near Link Drain) | 15 | 3: Rm; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed
7 | Construction of RCC Line Drain below NH-6(50 m) | 50 | 3: Rm; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed
8 | Construction of RCC Side Drain along NH-6 (Near Culvert,20 m) | 20 | 3: Rm; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed
9 | Construction of Retaining Wall at Nutumi Road | 35 | Rm | 29611018 | 2025-07-15 | 2026-03-01 | 100% |  | 0% | - | 100% | - | Phy Completed | Item rate
10 | Construction of Hume Pipe Culvert at MZU Road | 1 | 3: No.; 7: 0%; 9: 100%; 11: 100%; 13: Phy Completed
11 | Construction of side drain at Various places | 1217 | 3: Rm; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed
12 | Clearance of link drain at various places | 122 | 3: Rm; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY, 2026 UNDER ARND
Name of Work : Restoration Of Damage Due To Cyclone Remal Under Aizawl Road North Division, Aizawl Road South Division And Hmuifang Division |  |  | 7: Name of Contractor : Fredy Vanlalngila, Dinthar-I
Agreement Amount : ₹ 11,24,97,994.21 |  |  | 7: Date of Commencement : 27.06.2025
Agreement No.: 4/CE-HW/2025-2026 Dt. 01.06.2025 |  |  | 7: Target date of Completion :27.01.2026
Name of Division : Aizawl Road North Division
Source of funding: Cyclone Remal
Sl. No. | Name of Project | Unit | Approved Cost (Rs. in lakh) | Date of Commencement | Target date of completion | Cumulative Progress at the end of last month |  | Achievement works during the month |  | Overall cummulative achievement |  | Remarks | Mode of contract
[6 empty] | Phy. | Fin. | Phy. | Fin. | Phy. | Fin.
1 | 2 |  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Retaining Wall below Zoramthanga's House | Rm | 20 | 2025-07-01 | 2026-01-31 | 100% | 347.15 | 0% | - | 100% | Rs. 347.15 lakhs bill forwarded to Executive Engineer, Aizawl Road South Division for payment being the Nodal Officer for payment | Phy Completed | Item Rate
2 | Restoration of H/P Culvert at Falkland | Nos | 4: 5; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed; 14: Item Rate
3 | Restoration of Breast Wall at Armed Veng South | Rm | 4: 6; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed; 14: Item Rate
4 | Restoration of Retaining Wall Collapsed at Ramthar North | Rm | 4: 18.01; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed; 14: Item Rate
5 | Construction of Retaining Wall at Falkland | Rm | 4: 3; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed; 14: Item Rate
6 | Construction of Retaining Wall at Thuampui Vengthar | Rm | 4: 8; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed; 14: Item Rate
7 | Construction of Gabion Wall on Darnamlui for Restoration of formation edge collapsed at Ramthar North, Aizawl | Rm | 4: 90.44; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed; 14: Item Rate
8 | Construction of Breast wall at Berawtlang | Km | 20.58 | 1.7.2025 | 30.7.2025 | 100% | 347.15 | 0% | - | 100% | Rs. 347.15 lakhs bill forwarded to Executive Engineer, Aizawl Road South Division for payment being the Nodal Officer for payment | Phy Completed | Item Rate
9 | Construction of Breast wall at Thuampui to Selesih road at Ch:6.000kmp | Km | 21.08 | - | - | 100% |  | 0% |  | 100% |  | Phy Completed | Item Rate
10 | Widening of Lungbial road for diversion of collapsed Balcony on approach road to Berawtlang | Km | 41.06 | - | - | 100% |  | 0% |  | 100% |  | Phy Completed | Item Rate
11 | Construction of retaining wall near Pu Lalzarzoliana's house at Lungbial | Km | 2 | 1.7.2025 | 22.7.2025 | 100% |  | 0% |  | 100% |  | Phy Completed | Item Rate
12 | Construction of Reataining wall at Thuampui to Selesih at Ch:11.800 kmp | Km | 2.43 | 1.7.2025 | 30.7.2025 | 100% |  | 0% |  | 100% |  | Phy Completed | Item Rate
13 | Construction of RCC balcony at Gosen veng at Zuangtui | Km | 17.89 | - | - | 100% |  | 0% |  | 100% |  | Phy Completed | Item Rate
14 | Construction of RCC Rectangular side drain at RIPANS at Zemabawk | Km | 22.01 | - | - | 100% |  | 0% |  | 100% |  | Phy Completed | Item Rate
15 | Construction of Retaining wall at Thuampui to Selesih road at Ch:2.200 kmp | Km | 7.98 | 1.7.2025 | 18.7.2025 | 100% |  | 0% |  | 100% |  | Phy Completed | Item Rate
16 | Repair of Culvert and Retaining Wall @ ch. 3.900 Kmp at MZU Road | Rm | 3.61 | 2025-06-27 | 2026-01-27 | 100% |  | 0% |  | 100% |  | Phy Completed | Item Rate
17 | Construction of Retaing Wall @ ch. 6.325 Kmp at MZU Road | Rm | 4: 4.14; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed; 14: Item Rate
18 | Construction of Retaing Wall at approach road to Tanhril at 0.200 Kmp | Rm | 4: 3.61; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed; 14: Item Rate
19 | Construction of Retaining Wall @ ch. 1.600 Kmp on NH-54 to Sakawrtuichhun Road | Rm | 4: 7.88; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed; 14: Item Rate
20 | Construction of Retaining Wall @ ch. 0.980 Kmp on Zohnuai to Ropaiabawk road | Rm | 11.77 | 2025-06-27 | 2026-01-27 | 100% | 347.15 | 0% | - | 100% | Rs. 347.15 lakhs bill forwarded to Executive Engineer, Aizawl Road South Division for payment being the Nodal Officer for payment | Phy Completed | Item Rate
21 | Construction of Retaining Wall @ ch. 0.200 Kmp on NH-54 to Sakawrtuichhun Road | Rm | 4: 9.44; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed; 14: Item Rate
22 | Construction of Retaining near Pu B. Lalhmingsanga's house at Zonuam | Rm | 4: 1.84; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed; 14: Item Rate
23 | Construction of Retaining Wall at MUP road, Chanmari West | Rm | 4: 6.02; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed; 14: Item Rate
24 | Construction of Retaining Wall @ ch. 1.550 Kmp on Zohnuai to Ropaiabawk Road | Rm | 4: 7.1; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed; 14: Item Rate
25 | Construction of Retaining Wall @ ch. 1.150 on Zohnuai to Ropaiabawk road | Rm | 4: 10.05; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed; 14: Item Rate
26 | Restoration of Sinking portion near Sangthanmawia's house, Vaivakawn | Rm | 4: 70.45; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed; 14: Item Rate
27 | Construction of Retaining Wall near Pi Zaihnuni's house at Chawnpui | Rm | 4: 5.88; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed; 14: Item Rate
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY, 2026 UNDER ARND
Name of Work : Restoration Of Damage Due To Cyclone Remal Under Aizawl Road North Division (Part-II) And National Highway Division-III |  |  | 9: Name of Contractor : Kevin Vanlaltlana, Bungkawn
Agreement Amount : ₹ 11,24,97,994.21 |  |  | 9: Date of Commencement : 13.06.2025
Agreement No.: 4/CE-HW/2025-2026 Dt. 01.06.2025 |  |  | 9: Target date of Completion :13.01.2026
Name of Division : Aizawl Road North Sub-Division-III
Source of funding: Cyclone Remal
Overall Physical Achievement : 100%
Sl No | Name of Project | Unit |  | Approved Cost (Rs. in lakh) | Date of Commencement | Target date of completion | Cumulative Progress at the end of last month |  | Achievement works during the month |  | Overall cummulative achievement |  | Remarks | Mode of contract
[7 empty] | Phy. | Fin. | Phy. | Fin. | Phy. | Fin.
1 | 2 | 3 |  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Improvement of side drain and cross drain at Zotlang internal road | 30 | Rm | 259355.69 | 2025-06-13 | 2026-01-13 | 100% | - | 0% | - | 100% | Rs. 16.14 lakhs bill forwarded to Executive Engineer, National Highway Division - III, for payment being the Nodal Officer for payment | Phy Completed | Item Rate
2 | Construction of V shape side drain from Lalhmingliana Hnamte house to T. Lalzapi's house at Zotlang | 100 | Rm | 4: 386896.83; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed; 14: Item Rate
3 | Construction of V shape side drain from C. Thanchhuma house to Rosiamliana Ralte's house at Zotlang | 40 | Rm | 4: 154811.1; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed; 14: Item Rate
4 | Construction of drain below Pu Lalduhawma's house at Chawlhhmun | 77 | Rm | 4: 812604.91; 7: 100%; 9: 0%; 11: 100%; 13: Phy Completed; 14: Item Rate
Sr. Executive Engineer, PWD.,
Aizawl Road North Division,
Aizawl

## ARSD
MONTHLY PROGRESS REPORT UNDER AIZAWL ROAD SOUTH DIVISION, PWD
FOR THE MONTH OF JULY 2026
Sl. No. | Name of Schemes | Unit | Approved Cost (Rs in Lakh) | Date of Commencement | Target Date of Comple-tion | Cumulative Progress at the end of last month (June) |  | Achievement of works during the month (July) |  | Overall Cumulative achievement |  | Remarks | Mode of Tender
| Name of Works / Project |  |  |  |  | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
I | PMGSY
| Upgradation & Maintenance of Hlimen to Samtlang to Lungleng Road | Rm | 1262.12 | 2026-03-17 | 2027-03-17 | 4% |  | 1% |  | 5% |  | On going | e-tendering
II | Resurfacing of Road within Aizawl City under Aizawl Road South Division | Rm | 2248.61 | 2025-04-17 | 2025-10-17 | 96% | 2119.17 | 4% | 106.94 | 100% | 2226.11 | Work Completed | Restricted Tender
III | Strengthening and Improvement of State Highways & Other Roads under Mizoram under Central Circle (5054 under ARSD during 2025-26) | Rm | 262.29 | 2025-12-27 | 2026-05-27 | 98% | 205.01 | 0.3% | 23.25 | 98.3% | 228.26 | On going | Open tender
IV | Annual Plan 5054 R&B Untied Fund under Aizawl Road South Division during 2025-2026
1 | Patch Repair and Seal Coat at various places |  | 227.17 | 2026-03-21 | 2026-06-21 | 73% | 172.65 | 27% | 45.09 | 100% | 217.74 | Work Completed | Open tender
2 | Resurfacing at various places |  | 375.23 | 2026-04-01 | 2026-07-01 | 25% | 18.68 | 0% |  | 25% | 18.68 | On going | Open tender
3 | Construction of Rigid Pavement on Pharbawk to Mauhak internal road via Haimual Tlangnuam West |  | 17 | 2026-04-01 | 2026-09-30 | 100% |  | 0% | 15.53 | 100% | 15.53 | Work Completed | Open tender
4 | Construction of Turning Point at Maubawk Tamdo veng |  | 20.47 | 2026-04-01 | 2026-09-30 | 95% |  | 4% |  | 99% |  | On going | Open tender
| Total = |  | 639.87 | [5 empty] | 60.62 |  | 251.95
V | Restoration of Damage due to Cyclone Remal under ARSD under SASCI 2024-2025 | Rm | 1170 | 2025-07-02 | 2026-02-02 | 100% | 1154.5 | 0% | 0.03 | 100% | 1154.53 | Work Completed | Restricted tender
VI | Maubawk to MINECO Bypass Road on Western Side under SASCI (2024-2025)
| Formation Cutting | Km | 13.9832 | 15.8.2025 | 15.6.2026 | 100% | 110.3 | - | 0 | 100% | 110.3 | Completed | Restricted tender
| Pavement Works | Km | 22.434 | [8 empty] | Not yet started
| RCC Slab Culvert | No | 68.8716 | [8 empty] | Not yet started
Protection Work
| a) Retaining Wall | Rm | 94.1991 |  |  | 95% |  | 0% |  | 95% |  | On going
| b) Breast Wall | Rm | 75.5109 |  |  | 95% |  | 0% |  | 95% |  | On going
| Construction of RCC Balcony Roadway | Rm | 125 |  |  | 80% |  | 5% |  | 85% |  | On going
| Total = |  | 399.9987 |  |  |  | 110.3 |  |  |  | 110.3
VII | Upgradation & Augmentation of Hridaikawn to Pharbawkkawn Road, Aizawl District under SASCI 2025-26 Part-I | [11 empty] | Restricted Tender
1 | Earthwork for widening (including unline side drain) | Km | 80.4377 | 2026-03-03 | 2027-03-03 | 45% |  | 0% |  | 45% |  | On going
2 | Construction of rigid pavement on Hridaikawn to Pharbawkkawn (Aizawl Western bypass) | Km | 269.8597 | [8 empty] | Not yet started
3 | Bituminous Concrete on Hridaikawn to Pharbawkkawn (0+000 km to 0+680 km - repair of existing flexible pavement | Km | 16.0921 | [8 empty] | Not yet started
4 | Retaining Wall | Rm | 77.3251 | [8 empty] | Not yet started
5 | Hume Pipe Culvert | No | 56.2744 | [8 empty] | Not yet started
| Total = |  | 500
VIII | New Alignment of Road (Masihi Sangati Church to Mission Vengthlang Cemetery Road), Aizawl under SASCI 2025-26 Part-I | [11 empty] | Restricted Tender
1 | Formation Cutting | Km | 108.2656 | 2026-03-20 | 2026-09-20 | 70% |  | 0% | 31.72 | 70% | 31.72 | On going
2 | Construction of Hume Pipe Culvert | No | 37.618 |  |  | 10% |  | 30% |  | 40% |  | On going
3 | Construction of Retaining Wall |  | 64.1171 |  |  | 65% |  | 5% |  | 70% |  | On going
| Total = |  | 210.0007 | [5 empty] | 31.72 |  | 31.72
IX | Upgradation of Bailey Bridge over R. Tuikual on Lawipu to MZU Road |  | 652 | 17.03.2026 | 16.03.2028 | 0% | 71.51 | 0% |  | 0% | 71.51 | Expenditure incurred is procurement of Bailey Bridge parts which is now being redesigned bycontractor.
X | Upgradation and Widening of Main Road at A.R. Area, Aizawl under SASCI 2025-26 Part-IV |  | 2300 | 2026-04-15 | 2027-04-15 |  |  | 6% |  | 6% |  | On going | EPC Mode
XI | Constuction of approach road to common cemetery of 7 localities (Armed veng 'S', Tuithiang, Bethlehem veng, Bethlehem Vengthlang, College veng, Republic veng and ITI veng) at Mualpui, Aizawl under SASCI 2025-2026 Part-IX |  | 400 | 11.08.2026 | 11.06.2027 | 0% |  | 0% |  | 0% |  | Not yet started | Restricted Tender
XII | Construction of approach road to Joint YMA Cemetery at Salem veng, Aizawl under SASCI 2025-2026 Part-IV |  | 300 | 09.07.2026 | 09.02.2027 | 0% |  | 0% |  | 0% |  | Not yet started | Restricted Tender
XIII | SEDP (2019-2020)
| Const.of Approach Road to Aizawl College at Mualpui | Rm | 415 | 2021-07-26 | 2022-04-26 | 73% | 300 |  |  | 73% | 300 | On Going ES was accorded vide No B.12031/17/2019-PWD(T) Dt. 26.3.2020 (Rs. 100 lakhs); No. G.20016/3/2021-FBT Dt. 7.10.2021 (Rs. 100 lakhs) and No. B.12031/29/2021-PWD(T) Dt. 1.3.2023 respectively, which totalled Rs 300 out of Rs 415. The remaining balance/E.S was asked for Approval vide No. B.16012/6/22/T(ARS)/I/5 Dt. 29th Sept. 2022. It was regretted due to Financial Constraint as the year has been declared as year of consolidation vide no. B. 12031/17/2019-PWD(T) Dt. 23rd July, 2024. Since balance is not expected in the near future, fore closure of the contract is also submitted | Item Rate Contract
XIV | NEDP (2018-2019)
| Construction of Bridge on Chhinga Vengthar to Tuithiang road | Rm | 586.36 | 2021-04-19 | 2022-10-31 | 100% | 200 |  |  | 100% | 200 | Physical Works Completed according to Working Estimate E/S Amount of Rs.200.00 Lakh. The remaining ES was asked for Allocation vide No.B.16011/69-C/15/T(ARS)/28 dated: 23rd Jan, 2023 in which balance ES from Higher Authority is awaited. | Restricted tender
XV | Central Road Fund
| Construction of BUG Bridge over R.Tlawng on Aizawl - Reiek - W.Lungdar Road at 14.800 Kmp | Rm | 757.56 | 10.10.2018 | 31.10.24 | 100% | 750.57 |  |  | 100% | 750.57 | Work Completed | EPC mode
XVI | 3054 MAINTENANCE ACTION PLAN FOR 2026-2027 UNDER PWD AIZAWL ROAD SOUTH DIVISION
| Resurfacing at various places |  | 370.57 |  |  | 0% | - | 0% | - | 0% | - | Not yet started
Sr. Executive Engineer, PWD;
Aizawl Road South Division,
Aizawl, Mizoram.

## PIU
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026 - PROJECT IMPLEMENTATION UNIT, PWD
Source of Funding : PM DevINE
SL. No. | Name of work /Project. | Approved Cost (Rs) | Name of Implementing agency/Dept. | Date of Commencement | Target Date of Completion | Cummulative progress at the end of last month |  | Achievement of works during the month |  | Overall cumulative achievement |  | Remarks | Mode of Contract
[6 empty] | Physical | Financial | Physical | Financial | Physical | Financial
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Aizawl Bypass on Western Side under PM DevINE Scheme Location : Mizoram State : Aizawl | 500 Cr | Project Implementation Unit, PWD | 16.01.2025 | 16.01.2028 | 32.18% | 28.32% | 1.312% | -0.00256% | 33.49% | 28.32% | Financial progress of Contractor/ Civil works: 30.95% | EPC
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026 - PROJECT IMPLEMENTATION UNIT, PWD
FINANCIAL REPORT
Sl. No. | Name of project Location and state | Name of Implementing agency/Dept. |  | Approved Cost |  | Fund Released by MDoNER |  | Expenditure Made |  | Unspent balance out of the fund released | Status of submission U/Cs | Remarks
|  |  |  | Orignal cost INR in Crore | Revised cost INR in Crore | During 2025-26 INR in Crore | Since inception (cummulative) | During the month vis-à-vis target | Since inception (Cummulative)
1 | 2 | 3 |  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Construction of Aizawl Bypass on Western Side under PM DevINE Scheme Location : Mizoram State : Aizawl | Project Implementation Unit, PWD |  | 500 | Nil | 21.45 | 152.95 | 20.1 | 141.59 | 1.35 | 2 nos. of UC's submitted: 1) 61.09 Crore 2) 51.48 Crore
| Bill paid to the Contractor | Rs. 96.77Cr
| Financial Progress of the Contractor | 28.32%
| Total Expenditure (Exclusive of Mobilisation Advance) Crore |  | = | 4: 141.5872
| Financial Progress (%) |  | = | 4: 28.32%
| Agreement Amount (in Crore) |  | = | 4: 451.85
| Exp. Amount (in Crore) |  | = | 4: 139.8566
| Financial Progress of Civil Works |  | = | 4: 30.95%
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026 - PROJECT IMPLEMENTATION UNIT, PWD
PHYSICAL ABSTRACT
Sl. No. | Name of the project Location and state | Name of the implementing Agency/ Deptt. | Approved cost & date | 5: Date of commencement of work /scheme; 6: Target date of completion of work/scheme; 7: Scope of work /scheme physical terms (e.g.Kms etc); 11: Physical Achievement
|  |  | Cost (lakhs) | 4: Date; 11: Achievement; 12: Percentage upto date progress | Percentage during last month | Percentage during the report
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |  |  |  | 9 | 10 | 11 | 12
1 | Construction of Aizawl Bypass on Western Side under PM DevINE Scheme Location : Mizoram State : Aizawl | Project Implementation Unit, PWD | 4510 | 23.12.2024 | 16.01.2025 | 16.01.2028 | 1 | Earthwork up to top of sub-grade | Km | 45 | 34.545 | 76.77% | 68.63% | 8.138%
[7 empty] | 2 | Sub Base Course (SSB) | Km | 45 | 9.96 | 22.13% | 22.13% | 0%
[7 empty] | 3 | Seperation Layer (SAMI) | Km | 45 | 3.2 | 7.111% | 1.333% | 5.778%
[7 empty] | 4 | Bituminous Work | Km | 45 | 3.17 | 7.044% | 0.2222% | 6.822%
|  |  |  | 7: 5; 8: Wearing Course; 9: Km; 10: 45; 12: 0% | 0% | 0%
[7 empty] | 6 | Reconstruction and New Culverts on Existing road/realignmnet bypass - Hume Pipe Culvert | nos | 205 | 41 | 20% | 16.59% | 3.415%
[7 empty] | 7 | Reconstruction and New Culverts on Existing road/realignmnet bypass - RCC Box Culvert | nos | 16 | 9 | 56.25% | 50% | 6.25%
[7 empty] | 8 | Reconstruction and New Culverts on Existing road/realignmnet bypass - chutes | nos | 1278 | 322 | 25.2% | 20% | 5.196%
|  |  |  | 7: A; 8: A-Widening and repairs of minor bridges |  | 0%
[7 empty] | 1 | Repair of minor bridge by construction of wing wall |  | 0
[7 empty] | B | B-New Minor Bridges
|  |  |  | 7: 1; 8: Foundation + Substructure; 9: Nos; 10: 8; 12: 0% | 0% | 0%
|  |  |  | 7: 2; 8: Super-structure; 9: Nos; 10: 8; 12: 0% | 0% | 0%
|  |  |  | 7: 3; 8: Approaches; 9: Nos; 10: 8; 12: 0% | 0% | 0%
|  |  |  | 7: 4; 8: Protection Work; 9: Nos; 10: 8; 12: 0% | 0% | 0%
[7 empty] | i | Counterfort retaining wall | RMT | 2140 | 15 | 0.7009% | 0% | 0.7009%
[7 empty] | ii | Plumb Concrete Retaining Wall | Nos | 1722 | 222 | 12.89% | 0% | 12.89%
[7 empty] | iii | Breast Wall | RMT | 946 | 530 | 56.03% | 26.43% | 29.6%
[7 empty] | iv | Toe Wall | RMT | 946 | 188 | 19.87% | 0% | 19.87%
[7 empty] | v | Gabion Breast Wall | RMT | 1355 | 1355 | 100% | 86.09% | 13.91%
[7 empty] | vi | Lined Side Drain | MTR | 5000 | 3919 | 78.38% | 0% | 78.38%
|  |  |  | 7: vii; 8: Crash Barrier; 9: RMT; 10: 2560; 12: 0% | 0% | 0%
|  |  |  | 7: viii; 8: Traffic Signages; 9: Nos; 10: 225; 12: 0% | 0% | 0%
|  |  |  | 7: ix; 8: Road Markings; 10: 13050; 12: 0% | 0% | 0%
|  |  |  | 7: x; 8: Km Stones; 10: 220; 12: 0% | 0% | 0%
|  |  |  | 7: xi; 8: Boundary Pillar; 10: 600; 12: 0% | 0% | 0%
|  |  |  | 7: xii; 8: Direction and Place identification; 10: 35; 12: 0% | 0% | 0%
(R. LALDUHTHLANGA) Executive Engineer (Procurement), PIU, PWD for Project Director, PIU, PWD Cum Authority Engineer Aizawl, Mizoram

## AZBD
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026
Name of Division: Aizawl Building Division
Source of Funding : UIDF
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of completion | Cummulative Progress at the end of last month |  | Acievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Various storm drains and erosion mitigation at MINECO, Aizawl | Percen tage | 220 | 01.03.2026 | 01.02.2027 | 70% | 11104948 | 10% |  | 80% | 11104948 |  | Departmental
Sr.Executive Engineer, P.W.D.,
Aizawl Building Division,
Aizawl:Mizoram.

## AZL ELEC DIV
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026
Name Of Division : PWD, Electrical Division, Aizawl
Head of Account : Major & Minor Works and Deposit works 8443-108, D-III
Sl. No | Name of Works / Scheme | Unit | Approved Cost Amount (in Lakhs.) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month. |  | Achievement of works during the Month |  | Overall cummulative achievement |  | Remarks
[6 empty] | Phy (%) | Fin(Rs) | Phy (%) | Fin(Rs) | Phy (%) | Fin(Rs)
1 | 2 |  | 3 | 6 |  | 10 | 11 | 12 | 13 | 14 | 15 | 18
1 | I/E to Arrival & Departure Passenger Lobby at Lengpui Airport | % | 25.27 | 19.12.2020 | 1.4.2024 | 97% | 25.27 | 0% | - | 97% | 25.27 | Completed except toilets (Lad & Gents) electrical room and drinking water point as modification of room is to be done
2 | Addl. Estimate for SITC of MRV/VRF Centralizes Air Conditioner Airport First Floor Departure Hall, Mizoram. | % | 247.74 | 12.03.2022 | 12.06.2025 | 98.5% | 244.44 | 0% | - | 98.5% | 244.44 | Completed and ready for final testing and commissioning once upgradation of power house Lengpui Airport is ready
3 | SITC of EPABX System for Lengpui Airport Terminal Building. | % | 24.64 | 06.07.2022 | 29.06.2025 | 98% | 19.46 | 2% | 5.18 | 100% | 24.64 | Handover to Aviation
4 | SITC of PA System at Lengpui Airport Terminal Building. | % | 36.36 | 06.07.2022 | 29.06.2025 | 99% | 28.82 | 1% | 7.53 | 100% | 36.35 | Handover to Aviation
5 | Supply & Installation of Integrated Fire Hydrant System (Wise Riser)&SITC of Alarm System for Lengpui Airport Terminal Building. | % | 119.96 | 06.07.2022 | 29.06.2025 | 98% | 94.72 | 2% | 25.24 | 100% | 119.96 | Handover to Aviation
6 | SITC of AVTRON IP Surveillance System for Lengpui Airport Terminal Building. | % | 94.76 | 06.07.2022 | 29.06.2024 | 98% | 67.61 | 2% | 27.15 | 100% | 94.76 | Handover to Aviation
7 | SITC of LAN SETUP at Lengpui Airport Terminal Building. | % | 20.05 | 06.07.2022 | 29.06.2024 | 99% | 15.76 | 1% | 4.29 | 100% | 20.05 | Handover to Aviation
8 | SITC of 5-passenger Lift for Fast Track Court Building at Kolasib | % | 3.9 | 26.12.2023 | 28.02.2026 | 97% | - | 3% | - | 100% |  | Completed and commissioned, ready for handover
9 | SITC of 13-passenger Lift for Fast Track Court Building at Kolasib | % | 49.85 | 26.12.2023 | 28.02.2026 | 97% | - | 3% | - | 100% |  | Completed and commissioned, ready for handover
10 | Impvt/Upgradation of Operational/Non-Operational facilities of Lengpui Airport(SH:Northern Side Baggage conveyor belt) | % | 192.5 | 22.07.2024 | 18.12.2024 | 100% | 373.6 | 0% | - | 100% | 373.6 | Handover to Aviation
11 | Impvt/Upgradation of Operational/Non-Operational facilities of Lengpui Airport(SH:Southern Side Baggage conveyor belt) | % | 192.5 | 22.07.2024 | 18.12.2024 | 100% |  | 0% |  | 100% |  | Handover to Aviation
12 | I/E to Fast Track Court at Kolasib | % | 136.73 | 02.05.2024 | 45 days after materials at site | 42% | - | 28% | - | 70% |  | Materials being received and work is also being executed
13 | SITC of Signages for Lengpui Airport Terminal Building at Ground Floor | % | 13.26 | 31.10.2025 | 31.01.26 | 99% | 12.86 | 0% | 0 | 99% | 12.86 | Completed and ready for handover after room allotment done
14 | SITC of Signages for Lengpui Airport Terminal Building at First Floor | % | 15.04 | 31.10.2025 | 31.01.26 | 99% | 14.59 |  |  | 99% | 14.59 | Completed and ready for handover after room allotment done
15 | SITC of Arrival Carousal No.1 at Ground Floor Lengpui Airport Terminal Building | % | 184.74 | 27.01.2026 | 27.07.26 | 97% | - | 3% | - | 100% |  | Handover to Aviation
16 | SITC of Arrival Carousal No.2 at Ground Floor Lengpui Airport Terminal Building | % | 184.74 | 27.01.2026 | 27.07.26 | 75% | - |  | - | 75% |  | Full materials deliverd at site
17 | SITC of Electrical Installation for Arrival Carousal (No.1&No.2) at Ground Floor Lengpui Airport Terminal Building | % | 6.36 | 27.01.2026 | 27.07.26 | 50% | - |  | - | 50% |  | Electrical installation for Carousal No.2 will be done alongwith Carousal No.2 installation
18 | SITC of Multi V-VRF Air Conditioning System (185.6TR) for Arrival Hall (Northern Side) at Lengpui Airport Terminal Building Ground Floor. | % | 247.29 | 27.01.2026 | 27.07.26 | 75% | - | 7% | - | 82% |  | All materials delivered at site and installation work is ongoing
19 | SITC of Multi V-VRF Air Conditioning System (176TR) for Arrival Hall (Southern Side) at Lengpui Airport Terminal Building Ground Floor. | % | 237.84 | 27.01.2026 | 27.07.26 | 45% | - | 20% | - | 60% |  | All high site materials delivered at site, few low site materials balance for delivery
20 | SITC of Electrical Installation for Multi V-VRF Air Conditioning System (361.6 TR) for Arrival Hall (Northern & Southern Side) at Lengpui Airport Terminal Building Ground Floor. | % | 58.92 | 27.01.2026 | 27.07.26 | 10% | - | 0% | - | 10% |  | To be completed alongwith AC installation
21 | SITC of Runway centre line lights (Northern Side) at Lengpui Airport, Mizoram | % | 230.21 | 23.03.2026 | 31.05.2026 | 96% | 167.63 | 3% |  | 99% | 167.63 | Completed, final commissioning left
22 | SITC of Runway centre line lights (Southern Side), shifting of Taxiway Edge lights & raising of runway edge lights at Lengpui Airport, Mizoram | % | 204.5 | 23.03.2026 | 31.05.2026 | 94% | 148.91 | 4% | - | 98% | 148.91 | Only few works balance
23 | I/E to SDO (Civil) Type-IV Qtrs. at Kawnpui under SASCI 2024-2025 Part V | % | 6.55 | 27.03.2026 | 10.05.2026 | 100% | - |  | 5.88 | 100% | 5.88 | Completed
24 | SITC of split type Air Conditioners (2 Nos of 1TR each) for SDO (Civil) Type-IV Quarters at Kawnpui, under SASCI 2024-2025 Part-V | % | 1.59 | 16.06.2026 | 25.06.2026 | 100% | - |  | 1.59 | 100% | 1.59 | Completed
25 | I/E to SDO (Civil) Type-IV Qtrs at Bairabi under SASCI 2024-2025 Part -V | % | 6.6 | 16.06.2026 | 20.07.2026 | 20% | - | 75% |  | 95% |  | Few works left, service connection balance
26 | SITC of split type Air Conditioners (4 Nos of 1TR each) for SDO (Civil) Type-IV Quarters at Bairabi, under SASCI 2024-2025 Part-V | % | 3.2 | 27.07.2026 | 5.08.2026 | 10% |  | 10% |  | 10% |  | Work order given
27 | Diesel Generator power supply line to cath Lab (Eastern side) at Civil Hospital, Aizawl | % | 9.51 | 29.05.2026 | 15.08.2026 | 40% |  | 58% | 6.4 | 98% | 6.4 | Ongoing works
28 | I/E to SDO (Civil) Type-IV Qtrs. at North Vanlaiphai SH: Type-IV Quarter (1 Block, 1 Unit) | % | 6.57 | 2026-05-21 | 2026-07-06 | 80% |  | 20% |  | 100% |  | I/E works completed
29 | I/E to SDO (Civil) Type-IV Qtrs. at North Vanlaiphai SH: Office building | % | 5.31 | 2026-05-21 | 2026-07-06 | 90% |  | 10% |  | 100% |  | I/E works completed
30 | I/E to Multi utility centre at Zemabawk, Aizawl | % | 60 | 2026-05-29 | 14.08.2026 | 10% |  | 70% |  | 80% |  | I/E works in progress
Sr. Executive Engineer, PWD.,
Electrical Division, Aizawl.

## CHAMPHAI DIV
MONTHLY PROSGESS REPORT OF WORKS FOR THE MONTH OF JULY, 2026
Name of Division : PWD., Champhai
SL.No. | Name of Scheme | Unit | Approved Cost (in lakhs) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of Works during the month |  | Overall Cumulative Achievement |  | Remarks | Mode of Tender
| Name of Work/Project |  |  |  |  | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
I | ANNUAL PLAN (5054)(20224-2025)
1 | Upgradation of Approach road to Tuipui Village from NH-6 (new Eden) Length - 1.625 Km | Km | 128.28 | 6.12.2024 | 6.12.2025 | 100% | 74.32 |  | 47.49 | 100% | 121.81 | Work physically completed | Open Tender
2 | Construction of Bailey Bridge (60 ft span) over R. Tuimuk on approach road to Tuipui Village from NH-6 (New Eden) | Ft. | 53.06 | 22.8.2024 |  | 85% | 53.06 | _ | _ | 85% | 53.06 | Work in Progress | Deptt. |  | 0.053333
II | SASCI (2025-2026)
1 | Upgradation of Khankawn to Champhai (Phase - I) | Km | 600 | 6.6.2025 | 6.6.2026 | 35% | 11.33 | 2% | 34.02 | 37% | 45.35 | Work in Progress | Restricted Tender |  | TT=3.75 |  |  | Ring Road = 7.67 |  | 7.676
2 | Construction of Champhai Ring Road Phase-I (Khankawn - Falkawn - Hmunhmeltha - Vengthar - Zote via Keilungliah) | Km | 2000 | 7.7.2025 | 7.7.2026 | 45% |  | 16.4% | _ | 61.4% | _ | Work in Progress | Restricted Tender | TOTAL LENGTH=12.5 |  |  | July=7.67 |  | 0.25
3 | Upgradation of Khankawn to Champhai Road Under Part-V (Stimulating of Industrial Growth) (Phase - II) | Km | 600 | _ | 21.7.2026 | 35% |  | 5% | _ | 40% | _ | Work in Progress | Restricted Tender | [5 empty] | 25
4 | Upgradation of Zotlang to Tlangsam Road in Champhai District | Km | 300 | 9.2.2026 | 9.2.2027 | 70% | 144.48 |  |  | 70% | 144.48 | Work in Progress | Restricted Tender |  |  | 0.41408
5 | Construction of last mile connectivity road Selam to Kawlbem, Lungphunlian to Khuangphah | Km | 570 | 2.2.2026 | 2.2.2027 | 14% |  | 6% | _ | 20% | _ | Work in Progress | Restricted Tender
6 | Construction of Elevated Road RCC from Electric Veng to Bethel Veng | Km | 200 | 27.4.2026 | 27.4.2027 | 59.8% |  |  | _ | 59.8% | _ | Work in Progress | Restricted Tender
7 | Improvement and Upgradation of Champhai Dist. Headquarters under SASCI 2025-26 Part-VIII | Km | 1153.86 | 17.7.2026 | 17.7.2027 | [6 empty] | Mobilisation Stage | Restricted Tender
8 | Improvement & Upgradation of Champhai to Tlangsam Road under SASCI 2025-26 Part IX | Km | [9 empty] | Tender Satge | Restricted Tender
III | 5054 (Untied Fund) (2025-2026)
1 | Improvement & Strengthening of Champhai Town Road (SH: 1. Improvement & Strengthening of District Hospital to DC Office at Keifangtlang, Champhai) | Km | 62.55 | 23.3.2026 | 23.6.2026 | 100% | _ |  | 32.19 | 100% | 32.19 | Work Completed | Open Tender
2 | Improvement & Strengthening of Champhai Town Road (SH: 2. Improvement & Strengthening of Bethel kawn to DFO Office (Eastern), Champhai) | Km | 14.41 | 23.3.2027 | 23.6.2026 | 100% | _ |  | 1.5 | 100% | 1.5 | Work Completed | Open Tender
3 | Improvement & Strengthening of Champhai Town Road (SH: 3. Reconstruction of Khuangleng - Vanzau - Bungzung Road (Severely Damaged Portion) | Km | 48.04 | 18.3.2026 | 18.8.2026 | 100% | _ |  | 7.5 | 100% | 7.5 | Work in Progress | Open Tender
4 | Improvement & Strengthening of Champhai Town Road (SH: 4. Awmpui Bazar to Vety Road via LM MS(Awmpui Bazar Vety Road) ph - III) | Km | 18.29 | 23.3.2026 | 23.6.2026 | 100% | _ |  | 1 | 100% | 1 | Work in Progress | Open Tender
5 | Construction of HP Culvert, Breast wall, extension of apron and restoration of damaged pavement at Sazep village on Leithum to Vangchhe road | Km | 26.85 | 7.4.2026 | 7.6.2026 | 70% | _ | 5% | 6 | 75% | 6 | Work in Progress | Open Tender
6 | Repair of damaged pavement surface of Hnahlan to Tualcheng road 0.000 -13.780 Km | Km | 48.05 | 18.3.2026 | 18.8.2026 | 100% | _ |  | 48.04 | 100% | 48.04 | Work Completed | Open Tender
Executive Engineer, PWD.,
Champhai Division:Champhai

## HMUIFANG DIV
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY, 2026
Name of Division: Hmuifang Division, Aibawk
Rs. in Lakh
Sl. no | Name of Scheme | Unit | Approved Cost (Rs.in lakh) | Date of Commencement | Target Date of Completion | Commulative Progress at the end of last month |  | Achievement of Works during the month |  | Overall Commulative Achievement |  | Remarks | Mode of Tender
| Name of Work/Project |  |  |  |  | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
CRF
1 | Widening to Single Lane with Geometric Improvement & Up-Gradation of Chhiahtlang to Lamchhip road in Mizoram |  | 6668.18 | 23.06.2017 | 23.06.2019 | 100% | 6282.93 |  |  | 100% | 6282.93 | Physically Completed | Restricted Tender
2 | Balance work of Construction of Muallungthu to Lungphun Road (Length - 25.00 Km) |  | 3215 | 10.03.2026 | 10.09.2027 | [7 empty] | Restricted Tender
| i) Formation Cutting |  |  |  |  | 4% |  |  |  | 4% | 0 | Work in progress
ii) Protection Works
iii) CD Works
iv) Pavement Works
v) Side Drain
vi) Km Stone & Road Sign
5054
1 | Widening and Repair of Vantawng Approach Road | Km | 104.49 | 10.10.2024 | 10.03.2025 | 100% | 104.49 |  |  | 100% | 104.49 | Physically & Financially Completed | Departmental
2 | 5054-C.O on Roads & Bridges under Hmuifang Division for the year 2025-2026 |  | 84 | 16.12.2025 | 16.03.2026 |  | 84 |  |  |  | 84 | Physically & Financially Completed | Open tender
| a) Patch repair of Aibawk - Darlung Road 14.00-30.200 Kmp |  |  |  |  | 100% |  |  |  | 100%
| b) Extension of PCC pavement of Vantawng Khawhthla view point (Balance Portion) at Thenzawl |  |  |  |  | 100% |  |  |  | 100%
MPR OF SASCI PROJECTS
| Email |  |  |  | pwdhmuifangdivision@gmail.com
| Name of Department |  |  |  | PWD, Hmuifang Division
| Reporting Month |  |  |  | July, 2026
WORK WISE DETAILS
| Year of SASCI (FY) |  |  |  | 2024-2025
| Name of Item/ Work |  |  |  | Restoration of damage due to cyclone remal under Aizawl Road North, Aizawl Road South & Hmuifang Division
| Total Project Cost (Rs.) |  |  |  | 117000000
| Physical Progress (%) during the month |  |  |  | 0%
| Physical Progress (%) up to previous month |  |  |  | 100%
Financial Progress (%) during the month
| Financial Progress (%) up to previous month |  |  |  | Physically completed. Payment will be made by Aizawl Road South Division
Upload MPR Documents (up to 10 files, max 10 MB per file)
Sr. Executive Engineer, PWD.,
|  | MPR OF SASCI PROJECTS | [9 empty] | Hmuifang Division, Aibawk
| Email |  |  |  | pwdhmuifangdivision@gmail.com
| Name of Department |  |  |  | PWD, Hmuifang Division
| Reporting Month |  |  |  | July, 2026
WORK WISE DETAILS
| Year of SASCI (FY) |  |  |  | 2024-2025
| Name of Item/ Work |  |  |  | Restoration of damage due to cyclone remal under Hmuifang Division, Part-II
| Total Project Cost (Rs.) |  |  |  | 117500000
| Physical Progress (%) during the month |  |  |  | 0%
| Physical Progress (%) up to previous month |  |  |  | 100%
| Financial Progress (%) during the month |  |  |  | 2276828
| Financial Progress (%) up to previous month |  |  |  | 113907000
Upload MPR Documents (up to 10 files, max 10 MB per file)

## Khawzawl
MONTHLY PROGRESS REPORT OF PMGSY WORKS FOR THE MONTH OF JULY, 2026.
Name of Work : Upgradation & Maintenance of Kawlkulh to NE Bualpui Road (Ch. 0.00 to 24.00 Kmp)
Division : Khawzawl
Date of Commencement: 05.09.2024
Target Date of Completion : 04.09.2026
Name of Contractor : Shri Balaji Construction Company, Aspur Road, Tijwad District
Sl. No. | Component of Works | As per Agreement |  |  | Achievement upto the previous month |  | Achievement during the month |  | Comulative Achievement |  | Remarks
|  | Qty. | Unit | Item Amount (lakh) | Phy Prog (Qty) | Fin Prog (lakh) | Phy Prog (Qty) | Fin Prog (lakh) | Phy Prog (Qty) | Fin Prog (lakh)
1 | Formation Cutting | 23 | Km | 420.5539 | 22.7 | 389.84 |  |  | 22.7 | 389.84 | Work in Progress
2 | ULSD | 22276 | m | 9.4234 | 21000 | 9.42 |  |  | 21000 | 9.42
3 | Permanent Work
| a) R/Wall | 100 | m | 18.5827 | 78 | 9.91 |  |  | 78 | 9.91
| b) H/P Culvert Extension Restoration/New Construction | 82 | No. | 120.76 | 61 | 105.15 |  |  | 61 | 105.15
| c) LSD | 1724 | m | 19.8411
| d) Parapet | 200 | No. | 2.0265
4 | Pavement Work
| a) FDR Base Course | 24 | Km | 885.234 | 24 | 879.62 |  |  | 24 | 879.62
| b) WBM-III | 24 | Km | 339.8456 | 6.3 | 76.57 |  |  | 6.3 | 76.57
| c)Wearing course (MSS) | 24 | Km | 737.9505
| d) Shoulder | 24 | Km | 5.2553
5 | Road signages
| 1) 5th KM Stone | 6 | No. | 0.3
| 2) Ordinary KM Stone | 19 | No. | 0.665
| 3) 200m Stone | 96 | No. | 1.44 | 96 | 0 |  |  | 96 | 0
| 4) Boundary pillars | 240 | No. | 3.6
| 5)Pillars Painting | 33.91 | sqm | 0.050868
| 6)Speed limit | 11 | No. | 0.715
| 7) Right/Left hand curve | 144 | No. | 9.36
| 8) School | 11 | No. | 0.715
| 9) Men at work | 5 | No. | 0.325
| 10) Falling rocks | 11 | No. | 0.715
| 11) Destination sign | 1.62 | sqm | 0.162
5 | 12) Place identification sign | 0.75 | sqm | 0.075 | [6 empty] | Work in Progress
| 13) Advance direction sign | 1.62 | sqm | 0.162
| 14) Direction sign | 12.96 | sqm | 1.296
| 15) Painting lines, Dashes etc. | 4800 | sqm | 24
| 16) PMGSY LOGO | 13 | 2 km | 1.3
| 17) Title information | 2 | No. | 0.2 | 2 | 0.2 |  |  | 2 | 0.2
| 18) Citizen information | 1 | No. | 0.15 | 1 | 0.15 |  |  | 1 | 0.15
6 | AMC 1st Year | 24 | Kms | 16.8
7 | AMC 2nd Year | 24 | Kms | 20.4
8 | AMC 3rd Year | 24 | Kms | 24
9 | AMC 4th Year | 24 | Kms | 30
10 | AMC 5th Year | 24 | Kms | 36
11 | Deduct reusable hard rock @15% | 1524.108 | m3 | -12.9549 |  | -12.95 |  |  |  | -12.9549
Total A = |  |  |  | 2718.949 |  | 1457.91 |  | 0 |  | 1457.9051
Deviation/Additional Items
1 | Granular material( Dressing of road with quarry waste) | 1292.09 | m3 | 37.9731 | 1292.09 | 37.97 |  |  | 1292.09 | 37.97
2 | Dismantling of CI water pipe | 2000 | m | 4.4523 | 2000 | 4.45 |  |  | 2000 | 4.45
3 | RCC Slab Culvert | 43 | No. | 84.1235 | 25 | 21.42 |  |  | 25 | 21.42
4 | Additional HP Culvert (Single Cell & Double Cell)/New construction of HP Culvert | 20 | No. | 43.8637 | 20 | 18.34 |  |  | 20 | 18.34
Total B = |  |  |  | 170.4126 |  | 82.18 |  | 0 |  | 82.18
Total Amount (A+B) = |  |  |  | 2889.3616 | 0.59 | 1540.09 |  | 0 | 59.33% | 1540.0851
MONTHLY PROGRESS REPORT OF PMGSY WORKS FOR THE MONTH OF JULY,2026.
Name of Work : Upgradation & Maintenance of Kawlkulh to Lungpho upto Rullam (0.000 - 39.50 kmp)
Division : Khawzawl
Date of Commencement: 23.08.2024
Target Date of Completion : 12.10.2026
Name of Contractor : Zoremtluanga, Zemabawk, Aizawl
Sl. No. | Component of Works | As per Agreement |  |  | Achievement upto the previous month |  | Achievement during the month |  | Comulative Achievement |  | Remarks
|  | Qty. | Unit | Item Amount (lakh) | Phy Prog (Qty) | Fin Prog (lakh) | Phy Prog (Qty) | Fin Prog (lakh) | Phy Prog (Qty) | Fin Prog (lakh)
1 | Formation Cutting | 39.5 | Km | 384.99 | 39.5 | 362.55 |  |  | 39.5 | 362.55 | Work in Progress
2 | ULSD | 39.5 | Km | 46.22 | 39500 | 43.15 |  |  | 39500 | 43.15
3 | Permanent Work
| a) R/Wall | 820 | m | 217.63 | 605 | 217.62 |  |  | 605 | 217.62
| c) HP culvert Type-I | 52 | No. | 256.81 | 42 | 161.64 |  |  | 42 | 161.64
| d)RCC Slab Culvert-II | 3 | No. | 35.82
| e) LSD | 650 | m | 12.37
| f) Parapet | 560 | No. | 44.44
4 | Pavement Work
| a) Compacting Ground | 2 | Km | 2.48
| b) Scarifying | 31.095 | Km | 25.85
| c)WBM-II | 35.945 | Km | 384.61
| d) WBM-III | 35.945 | Km | 384.61
| e) Wearing course (MSS) | 35.945 | Km | 673.87
| f) Shoulder | 35.945 | Km | 81.48
| g) Rigid Pavement | 3.555 | Km | 319.23
5 | Road signages
| 1) 5th KM Stone | 9 | each | 0.6
| 2) Ordinary KM Stone | 32 | No. | 1.26
| 3) 200m Stone | 158 | No. | 1.11
| 4) Boundary pillars | 395 | No. | 3.43
| 5) Pillars Painting | 55.81 | sqm | 0.12
| 6)Speed limit | 2 | No. | 0.1
| 7) Right/Left hand curve | 125 | No. | 5.96
5 | 8) School | 1 | No. | 0.05 | [6 empty] | Work in Progress
| 9) Men at work | 2 | No. | 0.1
| 10) Falling rocks | 2 | No. | 0.1
| 11) Destination sign | 1.62 | sqm | 0.09
| 12) Place identification sign | 0.75 | sqm | 0.04
| 13) Advance direction sign | 1.62 | sqm | 0.09
| 14) Direction sign | 0.36 | sqm | 0.02
| 15) Painting lines, Dashes etc. | 11861.85 | sqm | 25.08
| 16) PMGSY LOGO | 20 | 2 km | 4.99
| 17) Title information | 2 | Nos | 0.3 | 1 | 0.3 |  |  | 1 | 0.3
| 18) Citizen information | 1 | Nos | 0.18 | 1 | 0.18 |  |  | 1 | 0.18
6 | AMC 1st Year | 39.5 | kms | 19.75
7 | AMC 2nd Year | 39.5 | kms | 23.7
8 | AMC 3rd Year | 39.5 | kms | 29.63
9 | AMC 4th Year | 39.5 | kms | 35.55
10 | AMC 5th Year | 39.5 | kms | 47.4
11 | Deduct Reusable Hard Rock@15% | 1364.3 | m3 | -11.6 |  | -11.6 |  |  |  | -11.6
Total A = |  |  |  | 3058.46 |  | 773.84 |  | 0 |  | 773.84
Deviation/Additional Items
1 | Granular Sub-Base (Fully damaged stretches) | 787.5 | m3 | 24.45
Total B = |  |  |  | 24.45 |  | 0 |  | 0 |  | 0
Total Amount (A+B) = |  |  |  | 3082.91 |  | 773.84 |  | 0 | 27.5% | 773.84
MONTHLY PROGRESS REPORT OF PMGSY WORKS FOR THE MONTH OF JULY,2026.
Name of Work : Upgradation & Maintenance of Kawlkulh to Lungpho to Ngentiang (0.000 - 11.840 kmp)
Division : Khawzawl
Date of Commencement: 29.08.2024
Target Date of Completion: 14.12.2026
Name of Contractor : Laltlanmawia, Kolasib
Sl. No. | Component of Works | As per Agreement |  |  | Achievement upto the previous month |  | Achievement during the month |  | Comulative Achievement |  | Remarks
|  | Qty. | Unit | Item Amount (lakh) | Phy Prog (Qty) | Fin Prog (lakh) | Phy Prog (Qty) | Fin Prog (lakh) | Phy Prog (Qty) | Fin Prog (lakh)
1 | Formation Cutting | 11.84 | Km | 79.92 | 11.84 | 73.13 |  |  | 11.84 | 73.13 | Work in Progress.
2 | ULSD | 11840 | m | 13.25 | 11840 | 11.18 |  |  | 11840 | 11.18
3 | Permanent Work
| a) R/Wall | 380 | m | 180.37 | 380 | 180.37 |  |  | 380 | 180.37
| b) HP culvert Type-I | 23 | No. | 150.28 | 23 | 150.2 |  |  | 23 | 150.2
| c)RCC Slab Culvert-II | 1 | No. | 16.06 | 1 | 16.03 |  |  | 1 | 16.03
| d) LSD | 1900 | m | 53.54 | 1800 | 52.87 |  |  | 1800 | 52.87
| e) Parapet | 560 | No. | 17.64
4 | Pavement Work
| a) Compacting Ground | 1 | Km | 1.07 | 1 | 0.87 |  |  | 1 | 0.87
| b) Scarifying | 5.78 | Km | 4.15 | 5.78 | 2.05 |  |  | 5.78 | 2.05
| c) WBM-III | 9.34 | Km | 149.86 | 7.2 | 48.12 |  |  | 7.2 | 48.12
| d) Prime Coat | 9.34 | Km | 35.98
| e) Tack Coat | 9.34 | Km | 20.11
| f) Wearing course (MSS) | 9.34 | Km | 151.64
| g) Shoulder | 11.555 | Km | 24.89
| h) Rigid Pavement | 0.285 | Km | 10.34
5 | Road signages
| 1) 5th KM Stone | 3 | each | 0.19
| 2) Ordinary KM Stone | 10 | No. | 0.37
| 3) 200m Stone | 47 | No. | 0.31
| 4) Boundary pillars | 118 | No. | 0.97
| 5) Pillars painting | 119 | No. | 0.03
| 6)Speed limit | 2 | No. | 0.09
5 | 7) Right/Left hand curve | 125 | No. | 5.66 | [6 empty] | Work in Progress.
| 8) School | 1 | No. | 0.05
| 9) Men at work | 2 | No. | 0.09
| 10) Falling rocks | 2 | No. | 0.09
| 11) Destination sign | 1.62 | sqm | 0.08
| 12) Place identification sign | 0.75 | sqm | 0.04
| 13) Advance direction sign | 1.62 | sqm | 0.08
| 14) Direction sign | 0.36 | sqm | 0.02
| 15) Painting lines, Dashes etc. | 3813.15 | sqm | 7.66
| 16) PMGSY LOGO | 6 | 2 km | 0.52
| 17) Title information | 2 | Nos | 0.29 | 1 | 0.29 |  |  | 1 | 0.29
| 18) Citizen information | 1 | Nos | 0.17 | 1 | 0.17 |  |  | 1 | 0.17
6 | AMC 1st Year | 11.84 | kms | 5.92
7 | AMC 2nd Year | 11.84 | kms | 7.1
8 | AMC 3rd Year | 11.84 | kms | 8.88
9 | AMC 4th Year | 11.84 | kms | 10.66
10 | AMC 5th Year | 11.84 | kms | 14.21
11 | Deduct Reusable Hard Rock@15% | 544.6 | m3 | -4.63 |  | -4.63 |  |  |  | -4.63
Total A = |  |  |  | 967.95 |  | 530.65 |  | 0 |  | 530.65
Deviation/Additional Items
1 | Panelled Concrete | 2.215 | Km | 80.35
2 | Granular Sub-Base | 1 | Km | 12.23 | 1.05 | 17.05 |  |  | 1.05 | 17.05
3 | WBM-II | 1 | Km | 9.73 | 1.05 | 12.43 |  |  | 1.05 | 12.43
Total B = |  |  |  | 102.31 |  | 29.48 |  | 0 |  | 29.48
Total Amount (A+B) = |  |  |  | 1070.26 |  | 560.13 |  | 0 | 57% | 560.13
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY, 2026
Name of work |  | : Construction of Approch Road from Demdum to Tuichang pump House.
Source of Funding |  | : SASCI (2025-2026)
Name of Contractor |  | : RZ Consultancy, Khawzawl Zuchhip Veng.
Sl. No. | Items of Work | Unit | As Per Agreement |  | Date of Commencement (As per agreement) | Target date of Completion (As per agreement) | Cummulative Progress at the end of the last month |  | Achievement of works during the month |  | Overall Cumulative achievement |  | Remarks | Mode of contract
|  |  | Qnty. | Amount (in Lakhs) |  |  | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Subgrade | Km | 2.9 | 22.92 | 2026-02-03 | 2027-02-03 | 2.9 | - | 0 | - | 2.9 | - |  | Restricted Tender
2 | GSB | Km | 2.9 | 8.7 |  |  | 2.9 | - | 0 |  | 2.9 | -
3 | PCC | Km | 2.9 | 136.52 |  |  | 2 | - | 0.4 |  | 2.4 | -
4 | H/P Culvert | Nos | 5 | 115.39 |  |  | 5 | 115.34 | 0 |  | 5 | 115.34
5 | ULSD | m | 2900 | 4.93 |  |  | 2000 | - |  |  | 2000 | -
| TOTAL = |  |  | 288.46 |  |  |  | 115.34 |  |  | 92% | 115.34
MONTHLY PROGRESS REPORT OF MAJOR WORKS 2025-2026 UNDER PWD KHAWZAWL DIVISION FOR THE MONTH OF JULY, 2026
Name of Division : Khawzawl Division.
Sl. No. | Name of Work | Category of road | Length (Km) | Amount of Technical Sanction (Rs. Lakh) | Date of Technical Sanction | Financial Progress (amount Rs. Lakh) |  |  | Physical Progress (in percentage) |  |  | Remarks
[6 empty] | Expenditure upto end of the month | Expenditure during the month | Total expenditure upto end of the month | Progress upto end of previous month | Progress during the month | Progress upto end of the month
1 | Patch Repair with Seal Coating of E. Lungdar to Biate Road | VR | 12 | 66.04 | 2026-02-02 |  |  |  |  | 8.18 | 25 | Work in Progress
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY, 2026 FOR CONSTRUCTION OF TUALPUI TO CHAMPHAI ROAD (Single Lane), MIZORAM UNDER NESIDS (Roads) (LENGTH 21.058 KMS) ON EPC MODE
A. Financial Report
Sl No | Name of the project Location and state | Name of the implementing agency/Deptt | Approved cost by MDoNER/NEC & Date of Approval |  | Fund resleased by MDoNER/NEC |  | Date of actual commen cement | Target date of completion | Expenditure Made |  | Unspent balance out of the fund released | Status of submission of U/Cs | Remarks
|  |  | Original cost (Cr.) | Revised cost (Cr.) | During 2026-2027 | Since inception (cummulative) |  |  | During the month vis-à-vis target (Cr.) | Since inception (cummulative) (Cr.)
1 | 2 | 3 | 4 | 5 | 6 | 7 |  |  | 8 | 9 | 10 | 11 | 12
1 | 0 | 0 | 0 | N.A. | 8.38 | 13.6 | 0 | 0 | 4.8 | 4.83 | 1.44 |  | (i) Rs 2.48 Crore was paid for Equipment Advance (ii) Rs 0.53 Crore was paid for DPR cost for the work.
B. Physical Report
[13 empty] | Month: |  | July | 2026
Sl. No. | Name of the project Location and state | Name of the implementing agency/Deptt | Approved cost by MDoNER/ NEC & Date of Approval (Cr.) |  | Date of Actual commencement | Target date completion of work/ scheme | Scope of work/scheme in physical terms. (eg. Kms etc) | [5 empty] | Physical achievement (Percentage from each component) |  |  | Physical Achievement (Percentage from Total Work) |  |  | Remarks | Physical Achievement absolute for working out percentatge
[13 empty] | Upto date progress | Upto Previous | Reporting Period | Upto date progress | Upto Previous | Reporting Period |  | Upto date progress | Upto Previous | Reporting Period
|  |  | Cost | Date
1 | 2 | 3 | 4 | 5 | 6 | 7 |  | 8 | unit | Qnty | Amount | Weightage | 9 |  | 10 |  |  |  | 11
1 | Construction of Tualpui to Champhai Road (Single Lane), Mizoram (Length=21.058 Km) | PWD Khawzawl Division, Govt. of Mizoram | 57.01 | 2026-01-21 | 2026-03-16 | 2027-09-15 | 1 | Road Works | [10 empty] | Ongoing Work
[7 empty] | 1.1 | Earthwork up to top of the embankment | Km | 21.058 |  | 20.82% | 43.21% | 35.62% | 7.598% | 8.998% | 7.416% | 1.582% |  | 9.1 | 7.5 | 1.6
[7 empty] | 1.2 | Hard Shoulder | Km | 20.918 |  | 2.269% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0 | 0
[7 empty] | 1.3 | Subgrade | Km | 20.918 |  | 0.6292% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0 | 0
[7 empty] | 1.4 | Sub-Base Course (CTSB) | Km | 20.918 |  | 7.805% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0 | 0
[7 empty] | 1.5 | Base Course (CTB) | Km | 20.918 |  | 8.032% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0 | 0
[7 empty] | 1.6 | Wearing Course (Prime Coat + Tack Coat + Bituminous Concrete) | Km | 20.918 |  | 9.863% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0 | 0
[7 empty] | 1.7 | RCC Box Culvert | No | 98 |  | 21.28% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0 | 0
[7 empty] | 2 | Minor Bridges
[7 empty] | 2.1 | Foundation | No | 2 |  | 0.5491% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0 | 0
[7 empty] | 2.2 | Sub-Structure | No | 2 |  | 4.404% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0 | 0
[7 empty] | 2.3 | Super-Structure (including bearings) | m | 30 |  | 3.847% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0 | 0
[7 empty] | 3 | Other Works
[7 empty] | 3.1 | Jungle Clearance including felling of trees | Km | 21.058 |  | 0.1066% | 43.21% | 35.62% | 7.598% | 0.04607% | 0.03797% | 0.0081% |  | 9.1 | 7.5 | 1.6
[7 empty] | 3.2 | Masonry Lined Side Drains | m | 15000 |  | 10.3% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0 | 0
[7 empty] | 3.3 | Masonry Retaining Wall | m | 530 |  | 5.578% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0 | 0
[7 empty] | 3.4 | Breast Wall | m | 202 |  | 1.316% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0 | 0
[7 empty] | 3.5 | Gabion Wall | m | 60 |  | 0.8323% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0 | 0
[7 empty] | 3.6 | RCC Retaining Wall | m | 25 |  | 0.7441% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0 | 0
[7 empty] | 3.7 | Traffic Signs & Road Safety, Road Signs, KM Stones, informatory signs, etc | Km | 21 |  | 0.9778% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0 | 0
[7 empty] | 3.8 | PCC Parapet Wall | No | 360 |  | 0.6417% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0 | 0
[12 empty] | 100% |  |  |  | 9.044% | 7.454% | 1.59%
MONTHLY PROGRESS REPORT OF PROJECTS UNDER PWD, KHAWZAWL DIVISION MONTH JULY 2026
Source of Funding :NESIDS | [12 empty] | (Rs.in lakh)
Sl. No. | Name of Project/Project | Approved Cost (Rs. in Lakhs) | Name of Division | Date of Comencement | Target Date of completion | Cummulative Progress at the end of last month |  | Achivement of works during the month |  | Overall cummulative achivement |  | Remarks | Mode of Contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | 0 | 5701 | Khawzawl Division | 2026-03-16 | 0 | 0% | 281.37 | 0% | 234.84 | 0% | 516.21 | Rs 52.66 Lakhs was paid for DPR cost. | EPC
Sr.Executive Engineer,PWD.,
Khawzawl Division : Khawzawl

## KOLASIB DIV
MONTHLY PROGRESS REPORT
FOR THE MONTH OF JULY, 2026
UNDER KOLASIB DIVISION
Sl. No. | Name of Schemes | Quantity | Unit | Approved Cost (Rs in Lakh) | Date of Commencement | Target Date of Comple-tion | Cumulative Progress at the end of last month |  | Achievement of works during the month |  | Overall Cumulative achievement |  | Remarks | Mode of Tender
| Name of Works / Project | [5 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 |  | 3 | 4 | 6 | 7 | 8 | 9 | 10 | ♂11 | 12=(8+10) | 13=(9+11) | 14 | 15
1 | NABARD
1 | Construction of Meidum to Hortoki Phase-II
i | Earthwork and Permanent Work from 9.100 Km to 13.325 Km Package-I | 3.305 | Km | 13366 | 24.12.2021 | 29.04.2024 | 100% | 1035.621 |  |  | 100% | 1035.621 | Completed | Restricted Tender
ii | Earthwork and Permanent Work from Km 13.325 to Km 17.500 Package-II | 3.275 | Km |  | 25.12.2021 | 30.04.2026 | 100% | 933.465 |  |  | 100% | 933.465 |  | Restricted Tender
iii | Earthwork and Permanent Works from Km 17.500 to Km 21.725 Package-III | 3.315 | Km |  | 18.12.2021 | 30.04.2026 | 100% | 1223.502 |  |  | 100% | 1223.502 | Mobilisation & Machinery Advance Recovery Balance= Rs.7 lakh | Restricted Tender
iv | Earthwork and Permanent Works from Km 21.725 to Km 26.00 Package-IV | 3.355 | Km |  | 08.12.2021 | 19.05.2025 | 99% | 726.528 |  |  | 99% | 726.528 | Mobilisation & Machinery Advance Recovery Balance=Rs.79.589 lakh | Restricted Tender
v | Construction of Rigid Pavement : Package -I (Km 9.100-Km 15.730) | 5.58 | Km |  | 03.08.2022 | 31.07.2026 | 62% | 722.158 | 3% |  | 65% | 722.158 | Mobilisation & Machinery Advance Recovery Balance= Rs.173.459 lakh | Restricted Tender
vi | Construction of Rigid Pavement : Package -II (Km 15.730-Km 22.36) | 5.58 | Km |  | 03.08.2022 | 05.09.2025 | 9.17% | 188.463 |  |  | 9.17% | 188.463 | Mobilisation & Equipment Advance Recovery Balance= Rs.297.974 lakh | Restricted Tender
vii | Design & Construction of T-Beam Bridge package-I at Chhimluangte (CH : 0.450 Kmp) | 24 | 3: m; 6: 18.12.2021; 8: 100%; 9: 482.621 | 100% | 482.621 | Completed | Departmental
viii | Design & Construction of T-Beam Bridge package-I at Dumkhel (CH : 5.500 Kmp) | 20 | m |  | 30.12.2024 | 30.06.2026 | 42% | 115.75 |  |  | 42% | 115.75 | Secured Advance Rs.62.24 lakh | Restricted Tender
ix | Design & Construction of T-Beam Bridge package-II at Bulung (CH : 10.200 Kmp) and Damdiai River ( Ch.23.500 kmp) on Meidum-Hortoki Road (Phase-ll), under an EPC-Type Contract | 28 | m |  | 24.12.2021 | 30.07.2026 | 41.5% |  | 5% |  | 46.49% | 0 | Secured Advance Rs.82.080 lakh | Restricted Tender
20 | bar: 3
2 | Construction of BUSG Composite Bridge (Span=22.00m, Revised span=34.00m) over R. Chepte on Bilkhawthlir to Saiphai road under NABARD | 34 | m | 508.45 | 24.06.2019 | 30.11.2025 | 24% | 132.82 |  | 4.16 | 24% | 136.98 | Fund : NABARD=Rs. 291.35 lakh SASCE=Rs.217.10 lakh Expenditure : NABARD=Rs.46.67 SASCE=Rs.90.31. Equipt. Adv. Recovery balance=Rs.8.037 | Restricted Tender
3 | Construction of BUSG Composite Bridge (Span=22.00m) over R. Sesih on Bilkhawthlir to Saiphai road under NABARD | 22 | m | 291.35 | 24.06.2019 | 30.09.2025 | 90% | 291.35 | 0% |  | 90% | 291.35 |  | Restricted Tender | 291.35
4 | Construction of approach Road to Railway Station in Mizoram (SH: Construction of Approach Road to Hortoki Railway Station | 2.51 | km | 625.97 | 18.07.2025 | 23.01.2027 | 81.9% | 376.5 | 4.4% |  | 86.3% | 376.5 |  | Restricted Tender
2 | 5054 (UNTIED FUND)
1 | Patch Repair of Kolasib Main Feeder from Diakkawn to Hmarveng Thlanmual Peng, Kolasib | 1.9 | km | 40 | 09.05.2026 | 08.08.2026 | 0% |  | 5% |  | 5% |  |  | Open Tender
2 | Resurfacing of Hmarveng to NH-54 Via Saidan, Kolasib | 2.3 | km | 46 | 09.05.2026 | 08.08.2026 | 0% |  | 5% |  | 5% |  |  | Open Tender
3 | Resurfacing NH-306 to New Diakkawn Community Hall via Diakkawn Bazar, Kolasib | 0.89 | km | 18 | 09.05.2027 | 08.08.2027 | 0% |  | 10% |  | 10% |  |  | Open Tender
4 | Construction of Retaining Wall necessitated by Road Formation Collapse at 47.00 Kmp on Serkhan-Bagha Road | 1 | 3: no; 4: 51; 6: 23.05.2026; 7: 22.09.2026 |  |  |  | Open Tender
5 | Resurfacing of Serkhan-Bagha Road (Saipum- N.Hlimen) | 2.88 | 3: km; 4: 300; 6: 04.05.2026; 7: 04.05.2026 |  |  |  | Open Tender
6 | Widening of Road from FCI Godown to the Court of additional District Judge, Kolasib | 0.2 | km | 14 | 17.06.2026 | 17.09.2026 | 0% |  | 60% |  | 60% |  |  | Open Tender
Sr.Executive Engineer, PWD
Kolasib Division.

## KAWRTHAH DIV
MONTHLY PROGRESS REPORT FOR THE MONTH OF | [9 empty] | JULY, 2026
Name of Division |  | : KAWRTHAH
Source of Funding |  | : SASCI
Sl. No | Name of Works/Project | Unit |  | Approved Cost (in lakhs) | Date of Commencement | Target Date of Completion | Achievement upto previous month |  | Achievement for the month |  | Overall Cummulative achievement |  | Remarks | Mode of Contract
[7 empty] | Phy | Fin | Phy | Fin | Phy | Fin (actual)
1 | 2 | 3 |  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Additional works and Completion of Double Lane Bridge over River Teirei on Bairabi - Zamuang Road. |  |  | 5: 29.2.2024; 6: 15.11.2025; 9: -; 13: Works completed; 14: Continued by the existing contractor i.e Sadguru Engineers & Allied Services Pvt.Ltd. For Bridge work & piling of Bank protection & Departmentally for Bank protection (Balanced work) and approach road.
| Bridge Work (Super Structure) | Nos | 1 | 4: 546.91; 7: 100%; 8: 1395.37; 11: 100%; 12: 1395.37
| River Banks Protection | Nos | 2 | 4: 475.69; 7: 100%; 11: 100%
| Approach Road | Nos | 2 | 4: 298.46; 7: 100%; 11: 100%
| Road Signages |  |  | 4: 25.6; 7: 100%; 11: 100%
| Total of Work Component : |  |  | 4: 1346.66; 12: 1395.37
| Provision for Contingencies : |  |  | 4: 26.76
| Provision for Quality Control : |  |  | 4: 26.6
| Grand Total : |  |  | 4: 1400.02; 8: 1395.37; 12: 1395.37
| Overall physical Progress | : |  | 4: 100%
MONTHLY PROGRESS REPORT FOR THE MONTH OF |  |  |  | 10: JULY, 2026
Name of Division |  | : KAWRTHAH
Source of Funding |  | : NABARD
Amount in lakhs
Sl. No | Name of Work/Project | Unit |  |  | Approved Cost (in lakh) | Date of Commencement | Target Date of Completion | Achievement upto previous month |  | Achievement for the month |  | Overall commulative achievement |  | Remarks | Mode of Contract
[8 empty] | Phy | Fin (lakh) | Phy | Fin (lakh) | Phy | Fin (actual)
1 | 2 | 3 |  |  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Double Lane BUSG Bridge (Span = 81m) over R.Langkaih on Mizoram-Tripura Border at Kanhmun | Bridge Works : |  |  | 13: Work in progress; 14: Contract after call of Restricted Tender
|  | a) Site Investigation & Design | 7% | % | 154.23 | 6.4.2018 | 31.07.2026 | 100% | 2106.46 | - |  | 100% | 2106.46
|  | b) Construction of Subway | 20% | % | 4: 440.65; 7: 100%; 11: 100%
|  | c) Foundation & Sub-Structure | 41% | % | 4: 903.34; 7: 100%; 11: 100%
|  | d) Super-Structure | 30% | % | 4: 660.98; 7: 100%; 11: 100%
|  | e) Miscellaneous | 2% | % | 4: 44.06; 7: 50%; 9: 50%; 11: 100%
|  | f) Contingency |  |  | 4: 28.65; 7: -; 9: -; 11: -
|  | Grand Total : |  |  | 4: 2231.91; 8: 2106.46; 12: 2106.46
|  | Overall physical Progress :- |  |  | 4: 100%
MONTHLY PROGRESS REPORT FOR THE MONTH OF |  |  |  |  | 9: JULY, 2026
Name of Division |  | : KAWRTHAH
Source of Funding |  | : 5054 R&B
Sl. No | Name of Works/Project | Unit |  | Approved Cost (in lakhs) | Date of Commencement | Target Date of Completion | Achievement upto previous month |  | Achievement for the month |  | Overall Cummulative achievement |  | Remarks | Mode of Contract
[7 empty] | Phy | Fin | Phy | Fin (in lakhs) | Phy | Fin (in lakhs)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Panel Conncrete of Zawlnuam to Zawlpui Road |  |  |  | 12: Works completed; 13: Contract after call of tender
| WBM | 45 | m3 | 3.54 | 18.4.2026 | 19.4.2027 | 100% | - |  | - | 100% | -
| PQC | 450 | m3 | 73.76 | 6: 100%; 10: 100%
| 3 % Contingencies |  |  | 2.32 | bar: 6; 8; 10
| 1% Labour cess |  |  | 0.77 | bar: 6; 8; 10
| Grand Total : |  |  | 80
| Overall Physical Progress | : | 100%
MONTHLY PROGRESS REPORT FOR THE MONTH OF |  |  |  |  | 9: JULY, 2026
Name of Division |  | : KAWRTHAH
Source of Funding |  | : 5054 R&B
Sl. No | Name of Works/Project | Unit |  | Approved Cost (in lakhs) | Date of Commencement | Target Date of Completion | Achievement upto previous month |  | Achievement for the month |  | Overall Cummulative achievement |  | Remarks | Mode of Contract
[7 empty] | Phy | Fin | Phy | Fin (in lakhs) | Phy | Fin (in lakhs)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Re-Seal Coating of Bunghmun to W.Mualthuam Road (0.00 - 6.250 Kmp) | Nos | 1 | 30.03 | 14.1.2026 | 14.7.2026 | 14% | - |  | - | 14% | - | Work in progress | Contract after call of tender
| Grand Total : |  |  | 30.03 | 6: 14%; 9: -; 10: 14%; 11: -
| Overall Physical Progress | : | 14%
Sr.Executive Engineer, PWD.,
Kawrthah Division, Kawrthah.

## LBPD
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY, 2026 ( BUILDING WORKS )
Name of Division: Lunglei Building Project Division, Lunglei
Rs. in Lakh
Sl.no | Name of Scheme | Unit | Approved Cost (Rs. In lakh) | Agreement Amount (Rs.in lakh) | Date of Commencement | Target Date of Completion : | Commulative Progress at the end of last month |  | Achievement of Works during the month |  | Overall Commulative Achievement |  | Remarks | Mode of Tender
| Name of Work/Project | [5 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
SASCI 2023-24
1 | Vertical Extention of Market Building at Kamalanagar |  |  | 124.52 | 23.03.24 | 31.03.2026 |  | 113.33 |  | 0 |  | 113.33 |  | Item Rated Tender
1 | Vertical Extension of existing Bazaar Building at Kamalanagar-I with Tin Roofing |  | 50 |  |  |  | 100% |  | - |  | 100% |  | Completed
2 | Construction of additional Bazaar Building by demolishing the existing dilapidated building that was constructed under BADP |  | 50 |  |  |  | 100% |  | - |  | 100% |  | Completed |  | 91.0135
3 | 2. Construction of Rest House at PWD Complex Bunghmun. |  | 24.52 |  |  |  | 100% |  | - |  | 100% |  | Completed
SASCI 2024-25
4 | Construction of Government Quarters (General Pool) at Venglai, Lunglei (Zautea's Quarters Site) SH : Type-IV Quarters (1 unit, 1 Block) | PART-V | 94.63 | 79.29 | 19.05.2025 | 19.05.2026 Revised to 30.07.2026 | 100% | 10.34 | 0% | 82.11 | 100% | 92.45 | Completed | Item Rated Tender | 212.1
5 | Construction of Government Quarters (General Pool) at Venglai, Lunglei (Quarters No. 5 Site) SH : Type-III Quarters (2 units, 1 Block) |  | 155.61 | 133.42 | 13.05.2025 | 13.05.2026 Revised to 31.08.2026 | 93% | 99.15 | 2% | 6.4 | 95% | 105.55 | Work in Progress | Item Rated Tender | 32573433
7 | Construction of Working Women Hostel at Ramthar Veng, Lunglei | PART-X | 1408.7 | 1186.47 | 14.05.2025 | 14.05.2026 Revised to 14.01.2027 | 33% | 313.56 | 2% | 12.17 | 35% | 325.73 | Work in Progress | Item Rated Tender | 37172067
8 | Construction of District Prison/Jail,Lunglei | PART-I | 588.92 | 523.87 | 28.04.2025 | 28.04.2026 Revised to 13.02.2027 |  | 134.43 |  | 75.51 |  | 209.94 |  |  | 40.0748
| Construction of Male Ward | [5 empty] | 7% |  | 1% |  | 8% |  | Work in Progress | Item Rated Tender
| Vertical Extension of Female Ward | [5 empty] | 100% |  | - |  | 100% |  | Completed | Item Rated Tender
| Construction of Recreation Center | [5 empty] | 99% |  | 0% |  | 99% |  | Work in Progress | Item Rated Tender
| Construction of Separation Wall | [5 empty] | 100% |  | - |  | 100% |  | Completed | Item Rated Tender
| Vertical Extension of Security Main Wall | [5 empty] | 10% |  | 2% |  | 12% |  | Work in Progress | Item Rated Tender
| Construction of Visitor's Toilet | [5 empty] | 75% |  | 2% |  | 77% |  | Work in Progress | Item Rated Tender
| Construction of Security Duty Post | [5 empty] | 20% |  | 2% |  | 22% |  | Work in Progress | Item Rated Tender
9 | Construction of Revenue Staff Quarters at Hnahthial | PART-V | 206.7 | 186.4 | 29.07.2025 | 29.07.2026 | 80% | 82.13 | 2% | 1.14 | 82% | 83.27 | Work in Progress | Item Rated Tender | 44.6727
10 | Construction of DCSO Office & Disaster Management & Rehabilitation Office Associated Parking at Lunglei | PART-V | 1349 | 1170.65 | 21.07.2025 | 21.07.2026 | 22% | 225.62 | 2% | 26.34 | 24% | 251.96 | Work in Progress | Item Rated Tender | 21.5231
11 | Reconstruction of Thingsai PWD IB | PART-V | 210 | 192.35 | 07.07.2025 | 07.07.2026 | 15% | 0 | 2% | 0 | 17% | 0 | Work in Progress | Item Rated Tender | 0
12 | Creation of Critical Infrastructure for Mitigation & Prevention of Damages against Natural Disaster in MPL under SASCI Part-I (Cyclone Remal) 2024-2025 | PART-I | [12 empty] | #DIV/0!
| 1. Construction of Hostel Superintendent's Quarters |  | 83.29 | 75.11 | 22.09.2025 | 22.09.2026 | 57% | 0 | 1% | 0 | 58% | 0 | Work in Progress | Item Rated Tender | 0
| 2. Construction of Girl's Hostel Building |  | 314.71 | 292.18 | 22.09.2025 | 22.09.2026 | 20% | 0 | 3% | 0 | 23% | 0 | Work in Progress | Item Rated Tender | 0
SASCI 2025-26
13 | Development and Establishment of Post Tlang as Amusement Park, Buarpui Village, Lunglei District | PART-I | 230 | 216.58 | 16.03.2026 | 16.03.2027 | 2% | 0 | 1% | 0 | 3% | 0 | Work in Progress | Item Rated Tender | 0
14 | Construction of Public Community Hall at Thingsai, Hnahthial District | PART-I | 250 | 227.48 | 23.02.2026 | 23.02.2027 | 4% | 0 | 1% | 0 | 5% | 0 | Work in Progress | Item Rated Tender | 0
15 | Construction of Treasury Office, Treasury Officers Quarters and Treasury Staff Quarters at Hnahthial | PART-I | 300 | 272.12 | 06.04.2026 | 06.04.2027 | 0% | 0 | 0% | 0 | 0% | 0 | Work not yet started (Physical progress corrected) | Item Rated Tender | 0
SASCI 2024-25
16 | Construction of Government Quarters (General Pool) at Lawngtlai at Additional DC Quarter | PART-V | 148.42 | 133.09 | 28.04.2025 | 28.04.2026 Revised to 31.08.2026 | 72% | 43.53 | 3% | 0 | 75% | 43.53 | Work in Progress | Item Rated Tender
17 | Construction of Government Quarters (General Pool) at Lawngtlai Electric Veng (near RD Office No.1) (SH : Type-IV Quarters (1 Block, 2 Units) | PART-V | 251 | 648.26 | 28.04.2025 | 28.04.2026 Revised to 11.11.2026 | 0% | 100 | 0% | 0 | 0% | 100 | Not yet started | Item Rated Tender
| Construction of Government Quarters (General Pool) at Lawngtlai Electric Veng (near RD Office No.2) (SH : Type-IV Quarters (1 Block, 2 Units) |  | 251.55 |  |  |  | 58% |  | 2% |  | 60% |  | Work in Progress | Item Rated Tender
| Construction of Government Quarters (General Pool) at Lawngtlai Electric Veng (near RD Office No.3) (SH : Type-IV Quarters (1 Block, 2 Units) |  | 251.64 |  |  |  | 58% |  | 2% |  | 60% |  | Work in Progress | Item Rated Tender
18 | Construction of Government Quarters (General Pool) at Lawngtlai Electric Veng (near BDO Office) | PART-V | 258.84 | 220.73 | 05.05.2025 | 05.05.2026 Revised to 30.10.2026 | 60% | 60.5 | 3% | 0 | 63% | 60.5 | Work in progress. | Item Rated Tender
19 | Construction of Government Quarters (General Pool) at Lawngtlai Electric Veng (near A&T Office) | PART-V | 257.57 | 219.67 | 28.04.2025 | 28.04.2026 Revised to 30.09.2026 | 48% | 69.35 | 4% | 0 | 52% | 69.35 | Work in progress. | Item Rated Tender
20 | SDO (C) Office & Quarter at Chawngte | PART-I | 204.55 | 183.24 | 20.07.2025 | 20.07.2026
| SDO (C) Office at Chawngte | [5 empty] | 50% | 36.83 | 5% | 0 | 55% | 36.83 | Work in progress. (EOT in process) | Item Rated Tender
| SDO (C) Quarter at Chawngte | [5 empty] | 20% |  | 5% |  | 25% |  |  | Item Rated Tender
21 | Construction of Circuit House Under DC Office, Lawngtlai District | PART-I | 1000 | 765.04 | 19.07.2025 | 19.07.2026 | 36% | 0 | 2% | 183.47 | 38% | 183.47 | Work in progress. (EOT in process) | Item Rated Tender
22 | Construction of Office Building Cum Quarters at Lawngtlai (Commissioner of State Tax) | PART-I | 358 | 296.08 | 15.07.2025 | 15.07.2026 | 40% | 0 | 5% | 66.45 | 45% | 66.45 | Work in progress. (EOT in process) | Item Rated Tender
SASCI 2025-26
23 | Construction of Common Service Centre (Multipurpose Hall) at Vengpui-I, Lawngtlai District | PART-I | 300 | 277.76 | 06.04.2026 | 06.04.2027 | 0% | 0 | 0% | 0 | 0% | 0 | Not yet started | Item Rated Tender
SASCI 2024-25
24 | Construction of Circuit Houses at Siaha | PART-V | 624.99 | 522.13 | 28.04.2025 | 28.04.2026 Revised to 30.11.2026 | 68% | 261.12 | 3% | 0 | 71% | 261.12 | Work in progress. | Item Rated Tender
25 | Construction of Government Quarters (General Pool) at New Siaha at Additional DC Quarters (Inside Gate) | PART-V | 266.88 | 228.26 | 28.04.2025 | 28.04.2026 | 93% | 160.34 | 2% | 6.22 | 95% | 166.56 | Work in progress. (EOT in process) | Item Rated Tender
26 | Construction of Government Quarters (General Pool) at New Siaha at Additional DC Quarters (Outside Gate) | PART-V | 279.49 | 239.98 | 28.04.2025 | 28.04.2026 | 93% | 156.04 | 2% | 12.75 | 95% | 168.79 | Work in progress. (EOT in process) | Item Rated Tender
27 | Construction of Government Quarters (General Pool) at New Siaha at Additional DC Quarters (Type III) | PART-V | 320.74 | 273.97 | 28.04.2025 | 28.04.2026 Revised to 30.11.2026 | 80% | 193.89 | 2% | 12.48 | 82% | 206.37 | Work in progress. | Item Rated Tender
28 | Construction of Government Quarters (General Pool) at New Siaha at Meisavaih Site-I (Type III, 4 unit) | PART-V | 321.75 | 274.93 | 28.04.2025 | 28.04.2026 Revised to 30.11.2026 | 73% | 188.88 | 2% | 12.55 | 75% | 201.43 | Work in progress. | Item Rated Tender
29 | Construction of Government Quarters (General Pool) at New Siaha at Meisavaih Site-II (Type III, 4 unit) | PART-V | 321.9 | 274.79 | 28.05.2025 | 28.05.2026 Revised to 31.10.2026 | 83% | 185.57 | 1% | 12.55 | 84% | 198.12 | Work in progress. | Item Rated Tender
30 | Construction of District Prison/Jail, Siaha | PART-I |  | 916.33 | 28.04.2025 | 28.04.2026 Revised to 30.11.2026 |  | 249.34 |  | 0 |  | 249.34
| Construction of Female Ward |  | 168.46 |  |  |  | 62% |  | 8% |  | 70% |  | Work in progress. | Item Rated Tender
| Construction of Administrative Building |  | 299.53 |  |  |  | 70% |  | 10% |  | 80% |  | Work in progress. | Item Rated Tender
| Construction of Type-III Staff Quarters (1 No.) |  | 75.5 |  |  |  | 66% |  | 2% |  | 68% |  | Work in progress. | Item Rated Tender
30 | Construction of Security Main Wall | PART-I | 103.25 | 916.33 | 28.04.2025 | 28.04.2026 Revised to 30.11.2026 | 95% | 249.34 | 5% |  | 100% |  | Completetd | Item Rated Tender
| Construction of Security Post |  | 55.14 |  |  |  | 55% |  | 25% |  | 80% |  | Work in progress. | Item Rated Tender
| Construction of Visitor's Toilet |  | 12.45 |  |  |  | 0% |  | 0% |  | 0% |  | Not yet started | Item Rated Tender
| Construction of Separation Wall |  | 68.13 |  |  |  | 0% |  | 0% |  | 0% |  | Not yet started | Item Rated Tender
| Vertical Extension of Security Main Wall |  | 21.96 |  |  |  | 0% |  | 0% |  | 0% |  | Not yet started | Item Rated Tender
| Construction of Type-II Staff Quarters (3 No.) |  | 159.84 |  |  |  | 70% |  | 2% |  | 72% |  | Work in progress. | Item Rated Tender
| Construction of Barrack |  | 50.57 |  |  |  | 71% |  | 4% |  | 75% |  | Work in progress. | Item Rated Tender
31 | SDO (C) Office & Quarters at Tipa | PART-I | 206.16 | 184.71 | 07.07.2025 | 07.07.2026 | 96% | 180.1 | 2% | 1.98 | 98% | 182.08 | Work in progress. | Item Rated Tender | 98.5761
1 | NABARD | [13 empty] | #DIV/0!
| CONSTRUCTION OF WAREHOUSES WITH ASSOCIATED INFRASTRUCTURE IN 12 LOCATIONS UNDER NABARD | [13 empty] | #DIV/0!
| GROUP- III: | [12 empty] | Item Rated Tender | #DIV/0!
| 1) Siaha SDC |  | 509.86 | 444.99 | 17.07.2023 | 31.03.2026 Revised to 31.08.2026 | 66% | 211.3 | 4% | 0 | 70% | 211.3 | Works in progress |  | 47.4842
| 2) Chapui |  | 217.02 | 197.82 | 17.07.2023 | 28.2.2026 | 100% | 81.18 | - | 0 | 100% | 81.18 | Completed |  | 41.0373
| 3) Bungtlang South |  | 180.45 | 162.63 | 17.07.2023 | 15.02.2026 | 100% | 155.62 | - | 0 | 100% | 155.62 | Completed | Item Rated Tender | 95.6896
| GROUP- IV: | [12 empty] | Item Rated Tender | #DIV/0!
| 1) Lungpher |  | 216.98 | 197.12 | 17.07.2023 | 17.7.2025 | 100% | 196.77 | - | 0 | 100% | 196.77 | Completed |  | 99.8224
| GROUP- VI: | [12 empty] | Item Rated Tender | #DIV/0!
| 1) South Vanlaiphai |  | 206.2 | 187.15 | 17.07.2023 | 24.03.2026 | 100% | 187.14 | - | - | 100% | 187.14 | Completed |  | 99.9947
| 2) Vawmbuk |  | 217.1 | 197.82 | 17.07.2023 | 31.12.2025 | 100% | 197.82 | - | - | 100% | 197.82 | Completed |  | 100
| GROUP-VIII: | [12 empty] | Item Rated Tender | #DIV/0!
| 1) Hnahthial |  | 217.01 | 197.24 | 17.07.2023 | 19.07.2027 | 35% | 0 | 2% | 0 | 37% | 0 | Works in progress |  | 0
| 2) Thingsai |  | 177.52 | 160.32 | 17.07.2023 | 13.12.2025 | 100% | 160.32 | - | - | 100% | 160.32 | Completed |  | 100
1 | 3) Cherhlun |  | 93.26 | 85.61 | 17.07.2023 | 13.12.2025 | 100% | 85.61 | - | - | 100% | 85.61 | Completed | Item Rated Tender | 100
| 4) Siata |  | 217.09 | 197.82 | 17.07.2023 | 13.12.2025 | 100% | 193.77 | - | 0 | 100% | 193.77 | Completed | Item Rated Tender | 97.9527
| GROUP-X: | [12 empty] | Item Rated Tender | #DIV/0!
| 1) Vaseikai |  | 260.81 | 220.35 | 17.07.2023 | 31.03.2026 | 100% | 220.35 | - | - | 100% | 220.35 | Completed |  | 100
| 2) Tlabung |  | 102.29 | 93.84 | 17.07.2023 | 06.03.2026 | 100% | 84.84 | - | 0 | 100% | 84.84 | Completed |  | 90.4092
2 | Construction of Infrastructure Support for School of Agricultural Science at Hnahthial (Phase-II) | [11 empty] | Handover is under process | Item Rated Tender | #DIV/0!
| i) Boys Hostel |  | 685 | 659.4 | 08.04.2023 | 19.12.2025 | 100% | 342.5 | - | 318.06 | 100% | 660.56 |  |  | 100.1759
| ii) Staff Quarter Type - III | [5 empty] | 100% |  | - |  | 100% |  |  |  | #DIV/0!
| iii) Staff Quarter Type - II | [5 empty] | 100% |  | - |  | 100% |  |  |  | #DIV/0!
| iv) Guest House | [5 empty] | 100% |  | - |  | 100% |  |  |  | #DIV/0!
3 | Construction of PHC at Chhuarlung, Mizoram |  | 430.25 | 362.62 | 22.12.2025 | 22.12.2026 | 45% | 0 | 5% | 0 | 50% | 0 | Work in progress | Item Rated Tender | 0
| NEC | [13 empty] | #DIV/0!
1 | Construction of Lunglei Market and Trade Centre at Electric/ Chanmari Veng, Lunglei |  | 1403.4 | 1403.4 | 25.08.2022 | 16.01.2026 | 100% | 1403.4 | - | 0 | 100% | 1403.4 | Handover is under process | Item Rated Tender | 100
| CSS | [13 empty] | #DIV/0!
1 | Construction of Academic Building for Nursing School at Lunglei (Upgradation) | - | 500 | 441.36 | 19.8.2024 | 19.08.2026 | 92% | 298.24 | 6% | 0 | 98% | 298.24 | Works near to completion | Item Rated Tender | 67.573
2 | Construction of Fire Station at Lunglei, Mizoram |  | 195.2 | 178.46 | 04.08.2025 | 04.08.2027 | 30% | 54.87 | 2% | 0 | 32% | 54.87 | Work in Progress | Item Rated Tender | 30.7464
3 | Construction of Fire Station at Hnahthial |  | 197.57 | 173.9 | 13.10.2025 | 13.10.2026 | 65% | 87.81 | 0% | 0 | 65% | 87.81 | Work in no Progress | Item Rated Tender | 50.4945
4 | Construction of Fire Station at Lawngtlai, Mizoram |  | 196.9 | 180.78 | 04.08.2025 | 04.08.2027 | 58% | 53.36 | 4% | 0 | 62% | 53.36 | Work in progress. | Item Rated Tender | 29.5165
5 | Construction of Fire Station at Council Vaih, Siaha |  | 207.9 | 189.37 | 04.08.2025 | 04.08.2027 | 77% | 125.02 | 5% | 0 | 82% | 125.02 | Work in progress. | Item Rated Tender | 66.0189
| NEDP | [13 empty] | #DIV/0!
1 | Construction of DC Office Building at Siaha |  | 610.12 | 509.08 | 31.10.2018 | 31.12.2025 | 100% | 569.3 | - | 0 | 100% | 569.3 | Civil works completed, I/E in process | Item Rated Tender | 111.8292
| NESIDS | [13 empty] | #DIV/0!
1 | Construction of 50-Bedded District Hospital Complex and Procurement of Equipment at Hnahthial, Mizoram |  | 1798.72 | 1378.87 | 25.6.2024 | 25.12.2026 | 38% | 344.71 | 10% | 0 | 48% | 344.71 | Work in progress (Physical progress corrected) | Item Rated Tender | 24.9995
i) Construction of Staff Quarters Type-IV, 1 Block, 2 Units
i) Construction of Staff Quarters Type-III, 1 Block, 3 Units
iii) Procurement of Equipment
| MINISTRY OF TRIBAL AFFAIRS | [13 empty] | #DIV/0!
1 | Construction of Auditorium at Pukpui Lunglei |  | 523 | 470.09 | 16.09.2023 Revised to 15.12.2025 | 16.01.2025 Revised to 15.04.2027 | 23% | 0 | 2% | 0 | 25% | 0 | Work in progress | Item Rated Tender | 0
Sr. Executive Engineer, PWD.,
Lunglei Building Project Division, Lunglei

## LRD - I
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY/ 2026
Name of work |  | : | Rehabilitation of Aizawl - Thenzawl - Lunglei Road (100 - 164 Kmp) (Carriageway Width = 5.50m)
(Sh : Between 143.85 - 152.00 Kmp) (Annual Plan 5054)
Name of Contractor |  | : | SLT Infracon Pvt.LTD, Badarpurghat, Hailakandi, 78803,
Date of Commencement |  | : | 24.04.2025
Date of Completion |  | : | 24.04.2026 | [5 empty] | ( Rs. In lakh)
Extension of Time |  | : | 03.12.2026
Sl. No. | Details of Works | Unit | Quantity | Approved Cost (Rs. In lakh) | Cummulative Progress at the end of last month |  | Achievement of Works during the month |  | Overall Cummulative achivement |  | Remarks
[5 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Scarifying the existing bituminous road surface | Km | 7.095 | 122.92 | 5.2 | 74.32 | 0 | 0.79 | 5.2 | 75.11 | Work in progress
2 | Rolling of existing granular layer | Km | 8.15 | 118.85 | 5.2 | 82.17 | 0 | 1.88 | 5.2 | 84.05
3 | WBM Grading - I | Km | 8.15 | 344.64 | 5.2 | 222.85 | 0 | 5.07 | 5.2 | 227.92
4 | WBM Grading - II | Km | 8.15 | 345.94 | 5.2 | 223.68 | 0 | 5.09 | 5.2 | 228.77
5 | Prime Coat | Km | 7.095 | 24.99 | 4 | 15.23 | 0 | 0 | 4 | 15.23
6 | Dense Graded Bituminous Macadam | Km | 7.095 | 409.73 | 4 | 249.67 | 0 | 0 | 4 | 249.67
7 | Tack Coat | Km | 7.095 | 12.29 | 4 | 7.49 | 0 | 0 | 4 | 7.49
8 | Bituminous Concrete | Km | 7.095 | 376.97 | 0 | 0 | 0 | 0 | 0 | 0
9 | Earthen Shoulder | Km | 8.15 | 5.54 | 5 | 0 | 0 | 0 | 5 | 0
10 | Sub surface drain 400mm x 400mm | No | 163 | 9.24 | 140 | 5.76 | 0 | 0.93 | 140 | 6.69
11 | Scarifying existing PQC | Km | 1.055 | 18.28 | 0.98 | 16.98 | 0.075 | 1.3 | 1.055 | 18.28
12 | Dry Lean Concrete | Sqm | 1.055 | 80.07 | 0.94 | 35.86 | 0.115 | 44.21 | 1.055 | 80.07
13 | Cement Concrete Pavement | Cum | 1.055 | 261.37 | 0.94 | 117.05 | 0.115 | 144.32 | 1.055 | 261.37
14 | Boring with 125mm dia casing pipe | No | 10 | 4.98 | 0 | 0 | 0 | 0 | 0 | 0
15 | Gabion Wall | Rm | 34.45 | 17.94 | 0 | 0 | 0 | 0 | 0 | 0
16 | Toe Wall | Rm | 23.7 | 12.19 | 0 | 0 | 0 | 0 | 0 | 0
17 | Retaining Wall | Rm | 13.2 | 9.32 | 0 | 0 | 0 | 0 | 0 | 0
18 | RCC Lined Side Drain | Rm | 1500 | 82.92 | 550 | 0 | 250 | 43.95 | 800 | 43.95
| GRAND TOTAL |  |  | 2258.2 | 57% | 1051.06 |  | 247.54 | 57% | 1298.6
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026
Name of work |  | : | Improvement & Upgradation of Aizawl - Thenzawl - Lunglei Road (SH : Between 152.00 - 164.00 Kmp) Package - I
Name of Contractor |  | : | SLT Infracon Pvt.LTD, Badarpurghat, Hailakandi, 78803,
Date of Commencement |  | : | 27.03.2026
Target date of Completion |  | : | 27.03.2026 | [5 empty] | (Rs.in lakh)
Sl. No. | Details of Works | Unit | Quantity | Approved Cost (Rs. In lakh) | Cummulative Progress at the end of last month |  | Achievement of Works during the month |  | Overall Cummulative achivement |  | Remarks
[5 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | WBM Grading - I | Km | 12 | 3.52 | 2.6 | 0 | 0 | 0 | 2.6 | 0 | Work in Progress
2 | WBM Grading - II | Km | 12 | 3.52 | 2.6 | 0 | 0 | 0 | 2.6 | 0
3 | Prime Coat | Km | 12 | 0.59 | 2.6 | 0 | 0 | 0 | 2.6 | 0
4 | Dense Graded Bituminous Macadam | Km | 12 | 729.36 | 2.6 | 167.96 | 0 | 0 | 2.6 | 167.96
5 | Tack Coat | Km | 12 | 29.96 | 2.6 | 6.9 | 0 | 0 | 2.6 | 6.9
6 | Bituminous Concrete | Km | 12 | 463.64 | 2.6 | 106.77 | 0 | 0 | 2.6 | 106.77
7 | Earthen Shoulder | Km | 12 | 5.27 | 2.6 | 0 | 0 | 0 | 2.6 | 0
| GRAND TOTAL |  |  | 1235.86 | 21.67% | 281.63 |  |  | 21.67% | 281.63
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY/2026
Name of work |  | : | Construction of Approach Road for Engineering College at Pukpui, Lunglei, Mizoram (SASCI)
Name of Contractor |  | : | RNH Consultant, Bawngkawn, Aizawl
Date of Commencement |  | : | 19.01.2026
Target date of Completion |  | : | 19.01.2026 | [5 empty] | ( Rs. in lakh)
Sl. No. | Details of Works | Unit | Quantity | Approved Cost (Rs. In lakh) | Cummulative Progress at the end of last month |  | Achievement of Works during the month |  | Overall Cummulative achivement |  | Remarks
[5 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Clearing and Grubbing Road Land | Hec | 0.38 | 0.74 | 0.38 | 0.74 | 0 | 0 | 0.38 | 0.74 | Work in Progress
2 | Formation Cutting (Widening & Lowering) | Km | 2.73 | 19.31 | 2.73 | 19.29 | 0 | 0 | 2.73 | 19.29
3 | Subgrade & Earthen Shoulder | Km | 2.73 | 56.93 | 2.73 | 54.42 | 0 | 0 | 2.73 | 54.42
4 | GSB | Km | 2.73 | 97.84 | 2.73 | 92.55 | 0 | 0 | 2.73 | 92.55
5 | DLC | Km | 2.73 | 121 | 1.55 | 0 | 0 | 0 | 1.55 | 0
6 | CC Pavement | Km | 2.73 | 421.31 | 0.7 | 0 | 0 | 0 | 0.7 | 0
7 | Interlocking Concrete Block | Sqm | 4335.5 | 118.45 | 2400 | 8.43 | 0 | 0 | 2400 | 8.43
8 | RCC Lined Side Drain | Km | 2.73 | 71.29 | 0 | 0 | 0 | 0 | 0 | 0
9 | Hume Pipe Culvert | Nos | 8 | 57.86 | 7 | 29.21 | 1 | 0 | 8 | 29.21
10 | RCC Causeway | Nos | 2 | 8.32 | 0 | 0 | 0 | 0 | 0 | 0
| GRAND TOTAL |  |  | 973.05 | 48.81% | 204.64 |  |  | 48.81% | 204.64
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY/2026
Name of work |  | : | Construction of PCC Flooring at Various Locations viz. (II) Melte to Khawiva.
Name of Contractor |  | : | K. Laltluangkima, Tanhril, Aizawl
Name of Scheme |  | : | SASCI
Date of Commencement |  | : | 02.02.2026
Target date of Completion |  | : | 02.02.2027
(Rs. in lakh)
Sl. No. | Details of Works | Unit | Quantity | Approved Cost (Rs. In lakh) | Cummulative Progress at the end of last month |  | Achievement of Works during the month |  | Overall Cummulative achivement |  | Remarks
[5 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Subgrade & Earthen Shoulder | Km | 2 | 15.04 | 2 | 0 | 0 |  | 2 | 0 | Work in Progress
2 | GSB | Km | 2 | 37.5 | 0.3 | 0 | 0.1 |  | 0.4 | 0
3 | CC Pavement | Km | 2 | 123 | 0 | 0 | 0 |  | 0 | 0
| GRAND TOTAL= |  |  | 175.54 | 11.77% | 0 |  |  | 12.84% | 0
MONTHLY PROGRESS REPORT UNDER SASCI FOR THE MONTH OF JULY/ 2026
NAME OF WORK : |  | Improvement of PCC Approach Road to Blue Mount Cluster (Zau) 11kms at Vanhne, Lunglei
NAME OF SCHEME : |  | SASCI
NAME OF DIVISION : |  | PWD, Lunglei Road Division-I, Lunglei.
NAME OF CONTRACTOR: |  | Vaube Projects
DATE OF START : |  | Dt.10th February 2026
DATE OF COMPLETION : |  | Dt.10th February 2027
T/S AMOUNT: |  | ₹2,49,99,998.42
(Rs. In lakh)
Sl.No | Details of works | Unit | Qnty | As per Agreement Cost | Cummulative Progress at the end of last month |  | Achievement during the month |  | Overall Cumulative achievement |  | Remarks
[5 empty] | Phy. | Fin. | Phy. | Fin. | Phy. | Fin.
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Compacting Original Ground supporting Subgrade etc. | Cum | 965.63 | 10.52 | 600 | 7.97 |  |  | 600 | 7.97 | Work in Progress
2 | PCC M 25 Pavement | Km | 5.15 | 239.47 | 1.52 | 18.6 | 0.34 |  | 1.86 | 18.6
| TOTAL = |  |  | 249.99 | 29.5% | 26.57 |  |  | 36.11% | 26.57
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY/ 2026
Name of work |  | : | Resurfacing of Lunglei Rown Road & Construction of Retaining Wall at Essential Locations (SH : 1. Resurfacing of Sacred Heart School Approach Road Venglai (Parallel Road Veglai 2nd Para Venglai))
Name of Contractor |  | : | Lalsangliani, Kanan Veng, Aizawl
Date of Commencement |  | : | 20.04.2026
Target date of Completion |  | : | 20.08.2026
( Rs in lakh)
Sl. No. | Details of Works | Unit | Quantity | Approved Cost (Rs. In lakh) | Cummulative Progress at the end of last month |  | Achievement of Works during the month |  | Overall Cummulative achivement |  | Remarks
[5 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | WBM | m3 | 413.6 | 26.54 | 100 | 0 | 0 | 0 | 100 | 0 | Work in Progress
2 | Prime Coat | Km | 1.767 | 3.12 | 0.55 | 0 | 0 | 0 | 0.55 | 0
3 | Tack Coat | Km | 1.767 | 2.51 | 0.55 | 0 | 0 | 0 | 0.55 | 0
4 | OGPC | Km | 1.767 | 17.32 | 0.55 | 0 | 0 | 0 | 0.55 | 0
5 | Seal Coat | Km | 1.767 | 5.97 | 0.55 | 0 | 0 | 0 | 0.55 | 0
| GRAND TOTAL= |  |  | 55.46 | 27.8% | 0 |  |  | 27.8%
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY/ 2026
Name of work |  | : | Resurfacing of Lunglei Rown Road & Construction of Retaining Wall at Essential Locations (SH : 1. Restoration of Collapsed Retaining Wall at Chainage 0.335 Kmp on Zohnuai - Ramzotlang Approach Road)
Name of Contractor |  | : | Luna Guite, Chanmari, Lunglei
Date of Commencement |  | : | 20.04.2026
Target date of Completion |  | : | 20.08.2026
( Rs in lakh)
Sl. No. | Details of Works | Unit | Quantity | Approved Cost (Rs. In lakh) | Cummulative Progress at the end of last month |  | Achievement of Works during the month |  | Overall Cummulative achivement |  | Remarks
[5 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Retaining Wall | m | 12 | 16.44 | 12 | 16.44 |  |  | 12 | 16.44 | Work Completed
| GRAND TOTAL= |  |  | 55.46 | 100% | 16.44 |  |  | 100% | 16.44
Executive Engineer, P.W.D.,
Lunglei Road Division-I, Lunglei

## LRD-II
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY, 2026
No. Tech- 11035/2026/MPR/LRD-II/1(i) | [11 empty] | Dt. 30th July, 2026
Name of Division: Lunglei Road Division-II, Lunglei
Source of Funding :
Sl. No | Name of Work/Scheme | Unit | Approved Cost (Rs. In Crore) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last Month |  | Achievement of Works during the Month |  | Overall Cummulative achievement |  | Remarks | Mode of Tender
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
I | STATE FUND
| Rehabilitation of Aizawl-Thenzawl-Lunglei Road (100-164 Kmp) (Carriageway Width = 5.50m) (Sh For FY 2024-2025, Between 134.22 - 143.85 Kmp) Package-I |  | 45.89 | 04.04.2025 | 20.12.2026 | 16% | 223.58 | 0% | 218.56 | 16% | 442.14 | ₹ 219.54 lakh secured advance balance | Restricted Tender
II | SASCI PART-I (2025-2026)
1 | Construction of PCC flooring at various locations viz, i) Haulawng to Hmuntlang ii) Melte to Khawiva iii) Ramrikawn to Pangzawl, and iv) Lena Stadium to New Maite. Haulawng- Hmuntlang Road |  | 4.39 | 02.02.2026 | 02.02.2027 | 17% | 0 | 0% | 0 | 17% | 0 |  | Restricted Tender
2 | Construction of PCC Pavement of Vaisam to Zehtet Road via Sailen, Lunglei District |  | 10.62 | 02.02.2026 | 02.02.2027 | 3.2% | 0 | 0% | 0 | 3.2% | 0 |  | Restricted Tender
3 | Improvement & Upgradation of Aizawl Thenzawl Lunglei Road (SH: Between 129.00 - 134.22 Kmp) Package-III |  | 23.68 | 27.03.2026 | 27.03.2027 | 1% | 0 | 0% | 0 | 1% | 0 |  | Restricted Tender
Sr. Executive Engineer, PWD.,
Lunglei Road Division-II, Lunglei

## LAWNGTLAI DIV
Monthly Progress Report under SASCI for the Month of July 2026
Name of Division |  | : |  | Lawngtlai Division
Slno | Name of Work/Project | Unit (km) | Quantity | Approved Cost (Rs.in lakh) | Date of Commencement | Target Date of Completion | Cumulative Progress at the end of last month |  | Achievement of Work During the Month |  | Overall Cumulative Achievement |  | Remarks | Mode of Contract
[7 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 |  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Restoration of Damage Due to Cyclone Remal under Lawngtlai Division
1 | (i) Restoration of collapsed road formation by Construction of Gabion wall at 1.400 kmp on DEO office to V.Zathanga Ground at L-IV, Lawngtlai | Km | 17 | 20.62 | 09.07.2025 | 09.01.2026 | 100% | 20.62 |  |  | 100% | 20.62 | Completed | Item Rate
2 | (ii) Restoration of collapsed road formation by Construction of Retaining Wall at various locations on Thingfal-Mamte-Thlengang-Tuipui Road | Km | 34.5 | 19.14 | 09.07.2025 | 09.01.2026 | 100% | 19.04 |  |  | 100% | 19.04 | Completed | Item Rate
3 | (iii) Restoration of collapsed road formation by Construction of Retaining Wall at various locations on Nalkawn to Chamdur Valley Road | Km | 41.8 | 26.79 | 09.07.2025 | 09.01.2026 | 100% | 26.79 |  |  | 100% | 26.79 | Completed | Item Rate
4 | (iv) Restoration of collapsed road formation by Construction of Gabion wall at 3.200 kmp on Lawngtlai to Tuipui Ferry Road | Km | 45 | 23.45 | 09.07.2025 | 09.01.2026 | 100% | 0 |  | 45 | 100% | 45 | Completed | Item Rate
5 | (v) Restoration of collapsed road formation at 6.700 kmp on Lawngtlai to Tuipui Ferry Road (Sh: Construction of Gabion wall, re-construction of HP culvert & Repair of pavement) | Km | 22 | 39.16 | 09.07.2025 | 09.01.2026 | 100% | 39.16 |  |  | 100% | 39.16 | Completed | Item Rate
Monthly Progress Report under SASCI 2025-2026( Part - IV) for the Month of July 2026
Construction of Fair Weather Road from KMMTTP to Lungmak under SASCI (Part-IV)
Division: Lawngtlai Division |  |  |  | 7: Name of Contractor: Zothan Consultancy Service, A-66, Luangmual: Aizawl
Slno | Name of Work/Project | Unit (km) | Quantity | Approved Cost (Rs.in lakh) | Date of Commencement | Target Date of Completion | Cumulative Progress at the end of last month |  | Achievement of Work During the Month |  | Overall Cumulative Achievement |  | Remarks | Mode of Contract
[7 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 |  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Fair Weather Road from KMMTTP to Lungmak under SASCI (Part-IV) | Km | 6.5 | 1274.99 | 12.06.2026 | 12.06.2027 |  |  | 5% | 0 | 5% | 0 | Work in Progress | Item Rate
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026
Name of Division |  |  | : | 4: LAWNGTLAI DIVISION
Source of funding&Name of work/Project |  |  | : | 4: NABARD/ Improvement and Strengthening of Nalkawn - Chamdur Valley (NCV) (Section I & II) Road Under NABARD; 14: (Rs in lakh)
Sl No | Items of work |  | Unit | Qnty | Approved (Rs in lakh) | Date of commencement | Target dateof completion | Cummulative progress at the end of last month |  | Achievement of Works during the month |  | Overall cummulative achievement |  | Remarks | Mode of contract
[8 empty] | Physical | Fin | Physical | Fin | physical | Fin
1 | 2 |  | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Clearance of permanent landslip |  | cum | 16390.36 | 14.1 | 09.08.2019 | 31.12.2024 | 16390.36 | 14.1 |  |  | 16390.36 | 14.1 | Proposed for Termination as per Review Meeting on 24.09.2025 | Item rate
2 | Retaining Wall |  | 3: rm; 4: 136; 5: 65.6; 8: 128; 9: 56.43; 12: 123; 13: 56.43
3 | H/P Culvert |  | 3: nos; 4: 34; 5: 240.3; 8: 34; 9: 240.3; 12: 34; 13: 240.3
4 | Pavement Works:-
a) | Sub Grade |  | 3: km; 4: 13.57; 5: 24.93; 8: 13.57; 9: 24.93; 12: 13.57; 13: 24.93
b) | WBM - I |  | 3: km; 4: 39.1; 5: 513.19; 8: 39.1; 9: 513.19; 12: 39.1; 13: 513.19
c) | WBM - II |  | 3: km; 4: 46.94; 5: 616.14; 8: 46.94; 9: 616.14; 12: 46.94; 13: 616.14
d) | Surface Course |  | 3: km; 4: 38.54; 5: 853.94; 8: 8; 9: 143.92; 12: 8; 13: 143.92
5 | Unlined Side Drain |  | 3: km; 4: 39; 5: 30.03; 8: 39; 9: 30.03; 12: 39; 13: 30.03
2358.23
| 3% Contingencies = |  | 5: 70.75; 9: 55.96; 13: 55.96
| 8% GST = |  | 5: 187.23; 9: 129.69; 13: 129.69
| 1% Labour cess = |  | 5: 0.2; 9: 0.2; 13: 0.2
| Grand Total = |  | 5: 2616.41; 9: 1824.89; 12: 71.04%; 13: 1824.89
* Physical progress percentege is updated considering weightage of each items .
Monthly Progressive Report under 5054 (ROADS & BRIDGES) for the Month of JULY 2026
Name of Work |  | : | 3: Maintenance of Roads within Lawngtlai Town under 5054 (R&B)
Name of Scheme |  | : | 3: 5054 (R&B); 8: Date of Start of Work; 11: :; 12: 30.11.2025
Name of Division |  | : | 3: Lawngtlai Division; 8: Time of Completion; 11: :; 12: 21.03.2026
Name of Contractor |  | : | 3: Rorelliana Council Veng, Lawngtlai; 8: Revised Date of Completion; 11: :; 12: 21.04.2026
Slno | Name of Work/Project | Unit (km) | Approved Cost (Rs.in lakh) | Date of Commencement | Target Date of Completion | Cumulative Progress at the end of last month |  | Achievement of Work During the Month |  | Overall Cumulative Achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Maintenance of Roads within Lawngtlai Town under 5054 (R&B) | 3.16 | 61.11 | 30.11.2025 | 21.03.2026 | 100% | 0 |  | 0 | 100% | 0 | Physically Complted | Item Rate
Monthly Progressive Report under 5054 (ROADS & BRIDGES) for the Month of JULY 2026
Name of Work |  | : | 3: Patch Repair & Full Length Seal Coating of Approach Road to KVK at Chawnhu, Lawngtlai
Name of Scheme |  | : | 3: 5054 (R&B); 8: Date of Start of Work; 11: :; 12: 13.02.2026
Name of Division |  | : | 3: Lawngtlai Division; 8: Time of Completion; 11: :; 12: 3 Months
Name of Contractor |  | : | 3: Rorelliana, Council Veng, Lawngtlai
Sl/ no | Name of Work/Project | Unit (km) | Approved Cost (Rs.in lakh) | Date of Commencement | Target Date of Completion | Cumulative Progress at the end of last month |  | Achievement of Work During the Month |  | Overall Cumulative Achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Patch Repair & Full Length Seal Coating of Approach Road to KVK at Chawnhu, Lawngtlai |  | 6.72 | 25.03.2026 | 25.06.2026 | 100% | 0 |  |  | 100% | 0 | Physically Completed | Item Rate
Monthly Progressive Report under 5054 (ROADS & BRIDGES) for the Month of JULY 2026
Name of Work |  | : | 3: Patch Repair of Bazar Veng to AOC Road via PWD Offoce at Lawngtlai
Name of Scheme |  | : | 3: 5054 (R&B); 8: Date of Start of Work; 11: :; 12: 13.02.2026
Name of Division |  | : | 3: Lawngtlai Division; 8: Time of Completion; 11: :; 12: 3 Months
Name of Contractor |  | : | 3: Rorelliana, Council Veng, Lawngtlai
Sl/ no | Name of Work/Project | Unit (km) | Approved Cost (Rs.in lakh) | Date of Commencement | Target Date of Completion | Cumulative Progress at the end of last month |  | Achievement of Work During the Month |  | Overall Cumulative Achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Patch Repair of Bazar Veng to AOC Road via PWD Offoce at Lawngtlai |  | 14.42 | 25.03.2026 | 25.06.2026 | 100% | 0 |  |  | 100% | 0 | Physically Completed | Item Rate
Monthly Progressive Report under 5054 (ROADS & BRIDGES) for the Month of JULY 2026
Name of Work |  | : | 3: Patch Repair, Seal Coating and Rehabilitation of Sinking Area of Sangchema Road, Lawngtlai
Name of Scheme |  | : | 3: 5054 (R&B); 8: Date of Start of Work; 11: :; 12: 13.02.2026
Name of Division |  | : | 3: Lawngtlai Division; 8: Time of Completion; 11: :; 12: 3 Months
Name of Contractor |  | : | 3: Rorelliana, Council Veng, Lawngtlai
Sl/ no | Name of Work/Project | Unit (km) | Approved Cost (Rs.in lakh) | Date of Commencement | Target Date of Completion | Cumulative Progress at the end of last month |  | Achievement of Work During the Month |  | Overall Cumulative Achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Patch Repair, Seal Coating and Rehabilitation of Sinking Area of Sangchema Road, Lawngtlai |  | 9.6 | 25.03.2026 | 25.06.2026 | 100% | 0 |  |  | 100% | 0 | Physically Completed | Item Rate
Monthly Progressive Report under 5054 (ROADS & BRIDGES) for the Month of JULY 2026
Name of Work |  | : | 3: Improvement of Thingfal to mamte - Thlengang - Tuipui Road from Chainage 17/000 - 21/400 Kmp
Name of Scheme |  | : | 3: 5054 (R&B); 8: Date of Start of Work; 11: :; 12: 13.02.2026
Name of Division |  | : | 3: Lawngtlai Division; 8: Time of Completion; 11: :; 12: 3 Months
Name of Contractor |  | : | 3: NC. Beichakhei, New Colony, Siaha
Sl/ no | Name of Work/Project | Unit (km) | Approved Cost (Rs.in lakh) | Date of Commencement | Target Date of Completion | Cumulative Progress at the end of last month |  | Achievement of Work During the Month |  | Overall Cumulative Achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Improvement of Thingfal to mamte - Thlengang - Tuipui Road from Chainage 17/000 - 21/400 Kmp | 4.400Km | 105.76 | 25.03.2026 | 25.06.2026 | 0% | 0 | 0% | 0 | 0% | 0 | Material Collection | Item Rate
Monthly Progressive Report under 5054 (ROADS & BRIDGES) for the Month of JULY 2026
Name of Work |  | : | 3: Improvement of 3rd IR Battalian Headquarter Approach Road & Internal Road at Thingkah, Mizoram
Name of Scheme |  | : | 3: 5054 (R&B); 8: Date of Start of Work; 11: :; 12: 13.02.2026
Name of Division |  | : | 3: Lawngtlai Division; 8: Time of Completion; 11: :; 12: 3 Months
Name of Contractor |  | : | 3: K. Lalhmuna, Bazar Veng, Lawngtlai
Sl/ no | Name of Work/Project | Unit (km) | Approved Cost (Rs.in lakh) | Date of Commencement | Target Date of Completion | Cumulative Progress at the end of last month |  | Achievement of Work During the Month |  | Overall Cumulative Achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Improvement of 3rd IR Battalian Headquarter Approach Road & Internal Road at Thingkah, Mizoram |  | 76.9 | 25.03.2026 | 25.06.2026 | 50% | 0 | 20% | 0 | 70% | 0 | Work in Progress | Item Rate
Monthly Progressive Report under 5054 (ROADS & BRIDGES) for the Month of JULY 2026
Name of Work |  | : | 3: Patch Repairing & Seal Coating of Approach Road Chengkawllui road at College Veng from NH-54
Name of Scheme |  | : | 3: 5054 (R&B); 8: Date of Start of Work; 11: :; 12: 13.02.2026
Name of Division |  | : | 3: Lawngtlai Division; 8: Time of Completion; 11: :; 12: 3 Months
Name of Contractor |  | : | 3: Departmental
Sl/ no | Name of Work/Project | Unit (km) | Approved Cost (Rs.in lakh) | Date of Commencement | Target Date of Completion | Cumulative Progress at the end of last month |  | Achievement of Work During the Month |  | Overall Cumulative Achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Patch Repairing & Seal Coating of Approach Road Chengkawllui road at College Veng from NH-54 | 7.00 Km | 15 | 25.03.2026 | 25.06.2026 | 100% | 0 |  | 0 | 100% | 0 | Physically Completed | Item Rate
Monthly Progressive Reportof AGRICULTURE LINK ROAD for the Month of JULY 2026
Name of Work |  | : | 3: Construction of Agriculture Link Road from BRTF Road to Sekulhkai at Hmunnuam Village
Name of Scheme |  | : | 3: NABARD; 8: Date of Start of Work; 11: :; 12: 13.02.2026
Name of Division |  | : | 3: Lawngtlai Division; 8: Time of Completion; 11: :; 12: 6 Months
Name of Contractor |  | : | 3: JH. Vanramngaia, Vengpui - II Lawngtlai
Sl/ no | Name of Work/Project | Unit (km) | Approved Cost (Rs.in lakh) | Date of Commencement | Target Date of Completion | Cumulative Progress at the end of last month |  | Achievement of Work During the Month |  | Overall Cumulative Achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Agriculture Link Road from BRTF Road to Sekulhkai at Hmunnuam Village | 7.00 Km | 69.52 | 13.02.2026 | 13.08.2026 | 30% | 0 | 0% | 0 | 0% | 0 | Work in Progress | Item Rate
Monthly Progressive Reportof AGRICULTURE LINK ROAD for the Month of JULY 2026
Name of Work |  | : | 3: Construction of Agriculture Link Road from Diltlang to Telhpuichangzawl at Diltlang South
Name of Scheme |  | : | 3: NABARD; 8: Date of Start of Work; 11: :; 12: 13.02.2026
Name of Division |  | : | 3: PWD, Lawngtlai Division; 8: Time of Completion; 11: :; 12: 6 Months
Name of Contractor |  | : | 3: T. Lawmchhunga, Chandmary: Lawngtlai
Sl/ no | Name of Work/Project | Unit (km) | Approved Cost (Rs.in lakh) | Date of Commencement | Target Date of Completion | Cumulative Progress at the end of last month |  | Achievement of Work During the Month |  | Overall Cumulative Achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Agriculture Link Road from Diltlang to Telhpuichangzawl at Diltlang South | 2.00 Kms | 19.9 | 13.02.2026 | 13.08.2026 | 100% | 0 |  |  | 100% | 0 | Physically Completed | Item Rate
Monthly Progressive Reportof AGRICULTURE LINK ROAD for the Month of JULY 2026
Name of Work |  | : | 3: Construction of Agriculture Link Road from Diltlang to Changmual at Diltlang South Village
Name of Scheme |  | : | 3: NABARD
Name of Division |  | : | 3: PWD, Lawngtlai Division; 8: Date of Start of Work; 11: :; 12: 13.02.2026
Name of Contractor |  | : | 3: T. Lawmchhunga, Chandmary: Lawngtlai; 8: Time of Completion; 11: :; 12: 6 Months
Sl/ no | Name of Work/Project | Unit (km) | Approved Cost (Rs.in lakh) | Date of Commencement | Target Date of Completion | Cumulative Progress at the end of last month |  | Achievement of Work During the Month |  | Overall Cumulative Achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Agriculture Link Road from Diltlang to Changmual at Diltlang South Village | 5.00 Kms | 51.76 | 13.02.2026 | 13.08.2026 | 50% | 0 |  |  | 50% | 0 | Work in Progress | Item Rate
Monthly Progressive Reportof AGRICULTURE LINK ROAD for the Month of JULY 2026
Name of Work |  | : | 3: Construction of Agriculture Link Road from Ngengpuikai to Khangapuilui at Ngengpuikai Village
Name of Scheme |  | : | 3: NABARD; 8: Date of Start of Work; 11: :; 12: 13.02.2026
Name of Division |  | : | 3: Lawngtlai Division; 8: Time of Completion; 11: :; 12: 6 Months
Name of Contractor |  | : | 3: H. Lalnghakzuala, Council Veng, Lawngtlai
Sl/ no | Name of Work/Project | Unit (km) | Approved Cost (Rs.in lakh) | Date of Commencement | Target Date of Completion | Cumulative Progress at the end of last month |  | Achievement of Work During the Month |  | Overall Cumulative Achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Agriculture Link Road from Ngengpuikai to Khangapuilui at Ngengpuikai Village | 5.00 Kms | 51.17 | 13.02.2026 | 13.08.2026 | 100% | 0 |  |  | 100% | 0 | Physically Completed | Item Rate
Monthly Progressive Reportof AGRICULTURE LINK ROAD for the Month of JULY 2026
Name of Work |  | : | 3: Construction of Agriculture Link Road from Chawngtelui to Ramri Lui at Chawngtelui Village
Name of Scheme |  | : | 3: NABARD; 8: Date of Start of Work; 11: :; 12: 13.02.2026
Name of Division |  | : | 3: Lawngtlai Division; 8: Time of Completion; 11: :; 12: 6 Months
Name of Contractor |  | : | 3: H. Lalnghakzuala, Council Veng, Lawngtlai
Sl/ no | Name of Work/Project | Unit (km) | Approved Cost (Rs.in lakh) | Date of Commencement | Target Date of Completion | Cumulative Progress at the end of last month |  | Achievement of Work During the Month |  | Overall Cumulative Achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Agriculture Link Road from Chawngtelui to Ramri Lui at Chawngtelui Village | 7.00 Kms | 19.9 | 13.02.2026 | 13.08.2026 | 100% | 0 |  |  | 100% | 0 | Physically Completed | Item Rate
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026
(A. FINANCIAL REPORT)
ANNEXURE - F
Sl. No. | Name of Project Location and State |  | 3: Name of Implementing Agency/ Dept.; 4: Approved Cost by Mdoner/NEC; 6: Fund Release by MDoner/NEC; 8: Expenditure Made; 10: Unspent balance out of the fund released; 11: Status of Submission of U/Cs; 12: Remarks
|  |  |  | Original Cost( Rs in Lakhs) | Revised Cost | During | Since inception (Cumulative) | During vis-à-vis Target | Since inception (Cumulative)
1 | 2 |  | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Improvement & Upgradation of Lawngtlai to Tuipui Ferry Road in the State of Mizoram under North East Special Infrastructure Developmant Scheme (NESIDS) |  | Mizoram, PWD | 2897.87 | Nil | Nil | 2633 | Nil | 2633 | Nil | U/C amounting to Rs. 121.55 Submitted on 14th October 2025 | Physically Completed
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026
(B. PHYSICAL REPORT)
ANNEXURE - F
Sl. No. | Name of the Project Location and State | Name of the Implementing Agency/Dept. | 3: Approved Cost by Mdoner/NEC; 5: Date of Actual Commencement of Work/ Scheme; 7: Target Date of Completion of Work/Scheme; 9: Scope of the Work/Scheme in Physical Terms( eg. Kms, etc); 11: Physical Achievement | Remarks
[11 empty] | Percentage ( During Month) | Percentage During the Reporting Month
|  |  | Cost | Date
1 | 2 | 3 | 4 | 5 | 6 |  | 7 |  | 8 |  | 9 | 10 | 11
1 | Improvement and Upgradation of Lawngtlai to Tuipui Ferrry Road ( Length= 10.00)Km | Mizoram, PWD | 2633 | 13.01.2020 | 08.08.2019 |  | 30.06.2023 |  | 1. Earth Work:- |  |  | 100% | Physically Completed
[9 empty] | a) Jungle Clearance | 3.50 Ha
[9 empty] | b) Formation cutting | 6.83 Km
2. Pavement works
[9 empty] | a) Subgrade | 7.570 Km
[9 empty] | b) Sub-Base | 7.570 Km
[9 empty] | c) Base Course | 7.570 Km
[9 empty] | d) Wearing course | 9.000 Km
3. Protection Work:-
[9 empty] | a) RCC Slab Culvert | 3 Nos
[9 empty] | b) H/P Culverts | 26 Nos
[9 empty] | c) Retaining Wall | 255.00 Rm
4. Drainage Work:-
[9 empty] | a) Lined Side Drain | 9000.00 Rm
[9 empty] | b) Side Drain Cover | 345.00 Rm
[9 empty] | c) Link Drain | 60.00 Rm
[9 empty] | d) Cross Drain | 4 Nos
5. Road Furniture:-
[9 empty] | a) Km Stone | 9 Nos
[9 empty] | b) Road Signages | 76 Nos
[9 empty] | c) Road Marking | 9.00 Km
[9 empty] | e) Metal Beam | 600 Rm
[9 empty] | 6. Landslip Clearance | 5292.02 cum
Sr. Executive Engineer, PWD
Lawngtlai Division : Lawngtlai

## MAMIT DIV
PROGRESS REPORT OF STRENGTHENING AND IMPROVEMENT OF STATE ROAD FOR THE MONTH OF JULY, 2026 (5054)
Sl. No. | Name of Road | Sanction Amount (Rs in Lakh) | Date of Technical Sanction | Financial Progress (Rs.in Lakh) |  |  | Physical Progress (in percentage) |  |  | Remarks
|  |  |  | Expenditure upto end of previous month | Expenditure during the month | Total Expenditure upto end of the month | Progress upto end of previous month | Progress during the month | Progress upto end of the month
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
1 | Profile Correction of Road from PWD Office - DC Office at Mamit | 55.83 | 17.11.2025 | 53.14 | 0 | 53.14 | 100% |  | 100% | Completed
2 | Construction of Retaing Wall on Tourist Lodge-PHC at W.Phaileng | 8.08 |  | 7.77 |  | 7.77 | 100% |  | 100% | Completed
3 | Construction of PCC Pavement on Approach Road to Helipad at W.Phaileng (Balance Portion) | 17.4 |  | 0.95 | 15.89 | 16.84 | 100% |  | 100% | Completed
PROGRESS REPORT OF STRENGTHENING AND IMPROVEMENT OF STATE ROAD FOR THE MONTH OF JULY, 2026 (5054)
Sl. No. | Name of Road | Sanction Amount (Rs in Lakh) | Date of Technical Sanction | Financial Progress (Rs.in Lakh) |  |  | Physical Progress (in percentage) |  |  | Remarks
|  |  |  | Expenditure upto end of previous month | Expenditure during the month | Total Expenditure upto end of the month | Progress upto end of previous month | Progress during the month | Progress upto end of the month
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
1 | Pothole Filling and Resurfacing of Luangpawl Approach Road at Mamit | 18.91 | 02.02.2026 | 0 | 0 | 0 | 1% | 0 | 1% | Bituminous Works could not be executed due to rain
2 | Construction of Flexible Pavement of Approach Road to 4th IR Bn. Hqrs from NH 108 | 30.09 |  | 0 | 0 | 0 | 1% | 0 | 1%
3 | Construction of Flexible Pavement on Zomuantlang to New Kawnpui Road on Eastern Side | 70 | [7 empty] | Not yet started
PROGRESS REPORT OF STRENGTHENING AND IMPROVEMENT OF STATE ROAD FOR THE MONTH OF JULY 2026 (3054 )
Sl. No. | Name of Road | Amount of Technical Sanction (Rs. Lakh) | Date of Technical Sanction | Financial Progress (Amount Rs. Lakh) |  |  | Physical Progress (in percentage) |  |  | Remarks
|  |  |  | Expenditure upto end of previous month | Expenditure during the month | Total Expenditure upto end of the month | Progress upto end of previous month | Progress during the month | Progress upto end of the month
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 10
1 | Repair of Pukzing to Silsury Road at essential stretches | 50 | 17.09.2025 | 50 |  | 50 | 100% |  | 100%
2 | Repair of Phuldungsei to Parvatui Road at essential stretches | 20 |  | 11.37 |  | 11.37 | 100% |  | 100%
3 | Repair of Approcah from Marpara Road to Lallen | 10 |  | 10 |  | 10 | 100% |  | 100%
4 | Construction of Retaining Wall in W.Phaileng at essential places | 30 |  | 30 |  | 30 | 100% |  | 100%
5 | Construction of Retaining Wall at Ch:0.150Kmp on approach to Khawrihnim Godown | 4.22 |  | 4.22 |  | 4.22 | 100% |  | 100%
6 | Patch repair and resurfacing of Dintharkawn to SDO Civil Complex at W.Phaileng | 8.37 |  | 8.37 |  | 8.37 | 100% |  | 100%
7 | Construction of V-shape side drain on W.Phaileng Town Roads | 12.14 |  | 12.14 |  | 12.14 | 100% |  | 100%
8 | Construction of Retaining Wall on approach road to Agriculture Complex at W.Phaileng | 10.96 |  | 10.96 |  | 10.96 | 100% |  | 100%
| Grand Total = | 145.69 |  | 137.06 |  | 137.06
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026
Name of Work : Strengthening & Improvement of W.Phaileng to Marapara Road | [8 empty] | Name of Contractor: |  |  | SLT Infracon Pvt. Ltd.
| (00.00 - 30.00 Kmp) Package-I | [7 empty] | Date of Commencement |  |  | : 15th March 2023
Name of Scheme : |  | NABARD | [6 empty] | Target date of completion |  |  | : 15th March 2025
Sanction Amount : | [8 empty] | EOT |  |  | : 7th March 2026
Agreement Amount : |  | Rs. 1854.59 Lakhs | [6 empty] | Overall Achievement |  |  | : 100.00 %
Supplementary Agreement Amt : |  | Rs. 453.88 Lakhs
Name of Division : |  | Mamit | [10 empty] | (Rupees in Lakhs)
Sl. No. | Items of Works | Unit | Qnty | Cost (in lakh) | Achievement upto previous year 2025-2026 |  | Achievement upto previous month |  | Achievement during the month |  | Target for the next month |  | Overall Cumulative achievement |  | Remarks
[5 empty] | Phy | Fin | Phy | Fin | Phy | Fin | Phy | Fin | Phy (8+10) | Fin (9+11)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
1 | Hill Side Drain Clearance | Rm | 30000 | 2308.47 | 30000 | 858.17 | 30000 | 1983.24 | 0 |  |  |  | 30000 | 1987.4 | Physically Completed
2 | Maintenance of earth Shoulder | m2 | 30000 |  | 0 |  | 30000 |  | 0 |  |  |  | 30000
3 | Scarifying Granular surface | m2 | 41030.49 |  | 36815.5 |  | 41030.49 |  | 0 |  |  |  | 41030.49
4 | Clearing Grass & removal of Rubbish etc., C) MDRs, SHs, NHs etc. | Km | 60 |  | 60 |  | 60 |  | 0 |  |  |  | 60
5 | WBM, Grading – I | m3 | 988.37 |  | 763.38 |  | 988.37 |  | 0 |  |  |  | 988.37
6 | WBM, Grading – II | m3 | 3077.29 |  | 2761.163 |  | 3077.29 |  | 0 |  |  |  | 3077.29
7 | Prime Coat, (iii) High Porosity | m2 | 59212.87 |  | 39371.12 |  | 59212.87 |  | 0 |  |  |  | 59212.87
8 | Tack Coat, (iii) Granular Treated Primer | m2 | 121806.1 |  | 40056.733 |  | 121806.1 |  | 0 |  |  |  | 121806.1
9 | Bituminous Macadam, (i) For Grading-I (40mm nominal size) | m3 | 3054.31 |  | 1968.75 |  | 3054.31 |  | 0 |  |  |  | 3054.31
10 | Bituminous Concrete, Case-II using Modified Bitumen (ii) For Grading-II 910mm nominal size) | m3 | 3507.9 |  | 1201.702 |  | 3507.9 |  | 0 |  |  |  | 3507.9
11 | Retaining wall | No. | 146 |  | 6 |  | 146 |  | 0 |  |  |  | 146
12 | Hume Pipe Culvert | No. | 4 |  | 4 |  | 4 |  | 0 |  |  |  | 4
13 | Land Slide Clearance in soil | m3 | 6796.76 |  | 4920.75 |  | 6796.76 |  | 0 |  |  |  | 6796.76
14 | Land Slide Clearance in Hard Rock requiring Blasting | m3 | 1640.16 |  | 1640.25 |  | 1640.16 |  | 0 |  |  |  | 1640.16
15 | Coping Between Parapets (CM 1:3) | m2 | 2.3
15 | Price Escalation |  |  |  |  | 9.61 |  | 9.61 | [5 empty] | 9.61
| Grand Total = |  |  | 2308.47 |  | 867.78 |  | 1992.85 | [5 empty] | 1997.01
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026
Name of Work : Strengthening & Improvement of W.Phaileng to Marapara Road | [8 empty] | Name of Contractor: |  |  | SLT Infracon Pvt. Ltd.
| (30.00 - 80.00 Kmp) Package-II | [7 empty] | Date of Commencement |  |  | : 15th March 2023
Name of Scheme : |  | NABARD | [6 empty] | Stipulated Target date of completion |  |  | : 15th March 2025
Sanction Amount : | [8 empty] | 2nd EOT |  |  | : 31.07.2026
Agreement Amount : |  | Rs. 4778.80 Lakhs | [6 empty] | Overall Achievement |  |  | 100%
Supplementary Agreement Amt : |  | Rs. 458.77 Lakhs
Name of Division : |  | Mamit | [10 empty] | (Rupees in Lakhs)
Sl. No. | Items of Works | Unit | Qnty | Cost (in lakh) | Achievement upto previous year 2025-2026 |  | Achievement upto previous month |  | Achievement during the month |  | Target for the next month |  | Overall Cumulative achievement |  | Remarks
[5 empty] | Phy | Fin | Phy | Fin | Phy | Fin | Phy | Fin | Phy (8+10) | Fin (9+11)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
1 | Hill Side Drain Clearance | Rm | 47830 | 5237.57 | 47830 | 2740.33 | 47830 | 4172.05 | 0 |  |  |  | 47830 | 4982.04 | Physically completed
2 | Maintenance of earth Shoulder | m2 | 50000 |  | 13500 |  | 16000 |  | 34000 |  |  |  | 50000
3 | Scarifying Granular surface | m2 | 139782 |  | 137472.8 |  | 139782 |  | 0 |  |  |  | 139782
4 | Clearing Grass & removal of Rubbish etc., C) MDRs, SHs, NHs etc. | Km | 100 |  | 100 |  | 100 |  | 0 |  |  |  | 100
5 | WBM, Grading – I | m3 | 4737.785 |  | 3426.96 |  | 4382.78 |  | 355.005 |  |  |  | 4737.785
6 | WBM, Grading – II | m3 | 10483.65 |  | 10310.46 |  | 10483.65 |  | 0 |  |  |  | 10483.65
7 | Prime Coat, (iii) High Porosity | m2 | 199843.125 |  | 149625 |  | 191953.2 |  | 7889.925 |  |  |  | 199843.125
8 | Tack Coat, (iii) Granular Treated Primer | m2 | 197780.625 |  | 63000 |  | 196709.33 |  | 1071.295 |  |  |  | 197780.625
9 | Bituminous Macadam, (i) For Grading-I (40mm nominal size) | m3 | 9889.031 |  | 7481.25 |  | 9597.66 |  | 291.371 |  |  |  | 9889.031
10 | Bituminous Concrete, Case-II using Modified Bitumen (ii) For Grading-II 910mm nominal size) | m3 | 5933.419 |  | 1890 |  | 5901.28 |  | 32.139 |  |  |  | 5933.419
11 | Surface Drain in Hard Rock | m | 5000 |  | 500 |  | 500 |  | 4500 |  |  |  | 5000
12 | Lined Side Drain | m | 3520 |  | 450 |  | 850 |  | 2670 |  |  |  | 3520
13 | Retaining wall | No. | 33 |  | 25 |  | 31 |  | 2 |  |  |  | 33
14 | Hume Pipe Culvert | No. | 12 |  | 7 |  | 10 |  | 2 |  |  |  | 12
15 | Slab Culvert | No. | 2 |  | 2 |  | 2 |  | 0 |  |  |  | 2
16 | Land Slide Clearance in soil | m3 | 15868.468 |  | 9865.069 |  | 14368.73 |  | 1499.738 |  |  |  | 15868.468
17 | Land Slide Clearance in Hard Rock requiring Blasting | m3 | 4106.07 |  | 3288.356 |  | 3288.356 |  | 817.714 |  |  |  | 4106.07
18 | GSB (i)Grading-I | m3 | 772.5 |  |  |  | 360 |  | 412.5 |  |  |  | 772.5
19 | Coping Between Parapets (CM 1:3) | m2 | 2.439 |  |  |  | 2.439 |  | 0 |  |  |  | 2.439
20 | Quality Control |  |  |  |  | 32.43 |  | 36.83 | [5 empty] | 36.83
21 | Contingency |  |  |  |  | 82.68 |  | 157.49 | [5 empty] | 157.49
22 | Price Escalation |  |  |  |  | 12.4 |  | 12.4 | [5 empty] | 12.4
| Grand Total = |  |  | 5237.57 |  | 2867.84 |  | 4378.77 | [5 empty] | 5188.76
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026
Name of Division : |  | Mamit Division
Source of funding : |  | SASCI
Name of Contractor : |  | H. Zorempuia
Sl. No. | Name of Work/Project | Unit | Approved Cost (Rs. In lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the Month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Restoration of Damage Due to Cyclone Remal Under Mamit, Kawrthah and Kolasib Division |  | 300.97 | 16.06.2025 | 16.01.2026 | 98% | 276.47 | 100% | 21.24 | 100% | 297.71 | Works physically completed | Item Rate
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026
Name of Division : |  | Mamit Division
Source of funding : |  | EI & ISC
Sl. No. | Name of Work/Project | Unit | Approved Cost (Rs. In lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the Month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Physical | Fin | Physical | Fin | Physical | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Improvement of Tuipuibari to W.Kawnpui Road, (0.00 - 9.00 Kmp) under EI & ISC Scheme |  | 4870 | 20.03.2020 | 20.03.2022 | 99% | 81.69% | 0% |  | 99% | 81.69% |  | EPC
Sr. Executive Engineer, PWD
Mamit Division, Mamit

## MMPD
MONTHLY PROGRESS REPORT UNDER MULTI MODAL PROJECT DIVISION FOR THE MONTH OF JULY, 2026
SlNo | Name of Scheme | Unit | Approved Cost (in lakhs) | Date of Commencement | Target date of completion | Cumulative progress at the end of last month |  | Achievement of works during the month |  | Overall Cumulative achievement |  | Remarks | Mode of Tender
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
SASCI
Work under SASCI
1 | Construction of Side Drain along NH-54 and on different parts of Lawngtlai Town | mtr | 200 | 18.02.2026 | 18.08.2026 | 0 |  | 0 |  | 0 |  | Work not yet started. | Restricted
NABARD
Work under NABARD
NEC
Work under NEC
PMGSY
Work under PMGSY
SEDP
Work under SEDP
CSS
Work under CSS
MoRTH
Work under MoRTH
1 | Construction of 2 Nos Reinforced Earth wall for restoration of road formation collapse at km 11.000 & km 11.050 and re-construction of Box culvert at km 11.000 on NH-502A in the state of Mizoram | mtr | 594.66 | 10.02.2025 | 30.11.2025 | 457 | 554.25 | 0 | 0 | 457 | 554.25 | Physically Completed during Dec 2025 | EPC Mode | #REF!
2 | STMC on NH 502 from Km 0.000 to Km 27.380 during 2025-2026 in the State of Mizoram | sqm | 162.76 | 09.12.2025 | 08.12.2026 | 4435 | 64.68 | 380 | 0 | 4815 | 64.68 |  | Item Rate
3 | Construction of new 2-lane Highway from Km 0.00-km 38.00 on NH 54 near Lawngtlai in Mizoram to support Kaladan Multi Modal Transit Transport Project in Phase A of SARDP-NE (pacakge-I) | Km | 43465 | 12.10.2010 | 12.10.2014 | 100% | 42680 |  |  | 100% | 42680 | Work physically Completed on 22.06.2023 | Item Rate
4 | Construction of new 2-lane Highway from km 38.00 to Km 70/00 in Mizoram to support Kaladan Multi Modal Transit Transport Project in Phase A of SARDP-NE (pacakge-II) | Km | 32224 | 12.10.2010 | 30.09.2014 | 100% | 30977 |  |  | 100% | 30977 | Work physically Completed on 30.04.2022 | Item Rate
5 | Construction of new 2-lane Highway from Km 70/00 to Km 99/00 in Mizoram to support Kaladan Multi Modal Transit Transport Project in Phase A of SARDP-NE (pacakge-III) | Km | 37459 | 12.10.2010 | 30.09.2014 | 100% | 36468 |  |  | 100% | 36468 | Work physically Completed on 23.06.2023 | Item Rate
Executive Engineer, PWD
Multi Modal Project Division
Lawngtlai: Mizoram

## NH - I
Montly Progress Report under National Highway Division-I, PWD., July, 2026
Sl. No | Name of Scheme | Unit | Approved Cost (in lakhs) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall Cummulative achievement |  | Remarks | Mode of Tender
| Name of Work/Project |  |  |  |  | Phy. | Fin. | Phy. | Fin. | Phy. | Fin.
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
SASCI
1 | Construction of Saiphal - Hortoki Road (21.150 km) | Phy in % Fin in lakh | 600 | 15.12.2023 | 15.12.2025 | 80% | 314.15 |  | 89.75 | 80% | 403.9 | On Going | Restricted tender
2 | Improvement of Approach road at Mamit (NH 44A) Junction to GSA playgroaund | Phy in % Fin in lakh | 989 | 13.06.2025 | 12.06.2027 | 58% | 296.2 | 1% | 112.38 | 59% | 408.58 | On Going | Restricted tender
3 | Upgradation of Lengpui Airport (Upgradation of Runway to PCN 50) | Phy in % Fin in lakh | 9100 | 01.12.2025 | 31.03.2026 | 96% | 7367.38 |  |  | 96% | 7367.38 | On Going | Restricted tender
MoRTH
1 | Short Term Maintenance Contract on NH-44A/108 Between km 16.670 to km 46.000 in the state of Mizoram. (Job No. RW/GHT/GHT/STMC/MZ/25-26/1) | Phy in % Fin in lakh | 387.79 | 05.12.2025 | 04.12.2026 | 97.45% | 271.69 | 1.25% | 113.35 | 98.7% | 385.04 | Foreclosed | Open Tender
2 | Short Term Maintenance Contract on NH-44A/108 Between km 46.000 to km 84.350 in the state of Mizoram. (Job No. RW/GHT/GHT/STMC/MZ/25-26/2) | Phy in % Fin in lakh | 383.18 | 05.12.2025 | 04.12.2026 | 99% | 285.21 |  | 111.33 | 99% | 396.54 | Foreclosed | Open Tender
3 | Short Term Maintenance Contract on NH-44A/108 Between km 84.350 to km 114.618 in the state of Mizoram. (Job No. RW/GHT/GHT/STMC/MZ/25-26/3) | Phy in % Fin in lakh | 349.8 | 05.12.2025 | 04.12.2026 | 99% | 281 |  | 66.38 | 99% | 347.38 | Foreclosed | Open Tender
4 | Short Term Maintenance Contract on NH-6 (Spur) from km 0.000 to 38.800 in the state of Mizoram (Job No. RW/GHT/STMC/MZ/25-26/4) | Phy in % Fin in lakh | 388.9 | 09.12.2025 | 08.12.2026 | 82% | 130.99 | 3% | 178.64 | 85% | 309.63 | On Going | Open Tender
5 | Performance Based Maintenance Contract (PBMC) under National Highway Division-I during 2023-24 on NH-6/54 between km 159/00 to km 178/00 (Length = 19.00 km) in the State of Mizoram. (Job No. 6/54-MZ-2023-24/124) | Phy in % Fin in lakh | 1891.98 | 29.08.2024 | 28.08.2029 | 79.75% | 1596.77 | 0.2% |  | 79.95% | 1596.77 | On Going | Open Tender
6 | One time Improvement of ByPass Road of Old Alignment of NH-44A (Old) from (i) km 27.500 to km 35.400, (ii) Km 50.220 to Km 70.100, (iii) 75.00 to Km 91.500, (iv) Km 105.000 to Km 111.000 & Km 111.250 to Km 112.700, (v) Km 120.240 to Km 121.840 in the State of Mizoram | Phy in % Fin in lakh | 4863 | 11.03.2026 | 10.09.2027 | 3% |  |  | 55.75 | 3% | 55.75 | On Going | Open Tender
5054
1 | Strengthening & Improvement of State Highway & Other State Roads under Mizoram (Sh: Resurfacing of Dampui Approach Road) | Phy in % Fin in lakh | 72.78 | 31.01.2026 | 28.06.2026 |  |  | 100% | 65.23 | 100% | 65.23 | Completed | Open Tender
2 | Resurfacing of Saiphal Junction to W.Serzawl Road (Length=4800 rm) and Construction of Retaining Wall at Ch. 8.500 km on Sairang-Lengte-Nghalchawm Road | Phy in % Fin in lakh | 94.98 | 31.01.2026 | 28.06.2026 | 100% | 82.12 | 100% |  | 100% | 82.12 | Completed | Open Tender
3 | Construction of RCC Balcony @ 0.200 km, PCC lined Side Drain and R/Wall @ 0.00 km & 0.010 km of Tuidam Approach Road | Phy in % Fin in lakh | 110.48 | 31.01.2023 | 28.06.2026 | 30% |  | 5% |  | 35% | 0 | On Going | Open Tender
4 | Consrtrucrtion of R/Wall @ km 1.050 on Dampui approach road | Phy in % Fin in lakh | 26.89 | 02.05.2026 | 02.07.2026 | 23% |  | 13% | 9.86 | 36% | 9.86 | On Going | Open Tender
Construction of R/Wall @ Km 3.150 on Tuidam Approach Road
Construction of Masonry Lined side drain on Saiphal Junction to W. Serzawl (L=300.00M)
Sr. Executive Engneer, PWD., National Highway Division-I Aizawl : Mizoram

## NH - II
MONTHLY PROGRESS REPORT FOR VAITIN TO ZILTHAW (R.TUIRUANG) ROAD AND CONSTRUCTION OF RETAINING WALL AND PROTECTION WALL OF CHHIM VENG BIAKIN AT SAWKARDAI FOR THE MONTH OF JULY, 2026
Name of Division : National Highway Division - II
Source of funding : 5054 R&B Name of Contractor : Vanramhluna, Ramhlun South, Aizawl | [16 empty] | Agreement Amount : `45,44,800.00
Lenth of Project = 929.00 Rm
Sl No | Name of Work/Project | Item Description | Unit | Qty. |  | Item Agmt. Amt. (Rs in Lakh) | Approved Cost (Rs in Lakh) | Date of Commencement | Target of Completion | Cummulative Progress at the end of last Month |  |  |  | Achievement of works during the Month |  |  |  | Overall cummulative achievement |  |  |  | Remarks | Mode of Contract
[10 empty] | Phy |  | Fin |  | Phy |  | Fin |  | Phy |  | Fin
[10 empty] | Qty. | % | Amount | % | Qty. | % | Amount | % | Qty. | % | Amount | %
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
1 | Construction of Vaitin to Zilthaw (R.Tuiruang)Road and Retaining Wall and Protection of Chhim veng Biakin at Sakawrdai | Restoration of rain cuts with soil | m3 | 501.57 |  | 2.056 | 4544800 | 20.04.2026 | 03.07.2026 | 240 | 47.85% | 0 | 0% | 0 | 0% | 0 | 0% | 240 | 47.85% | 0 | 0% | Protection works and Masonry lined side drains were completed. Due to heavy rainfall and slipery of road, works cannot be execute smoothly. | Item Rate
|  | GSB-I | m3 | 297.28 |  | 11.912 |  |  |  | 45 | 15.14% | 0 | 0% | 0 | 0% | 0 | 0% | 45 | 15.14% | 0 | 0%
|  | WBM-I | m3 | 278.7 |  | 13.823 |  |  |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
|  | Earthen shoulder | m3 | 111.48 |  | 0.77 |  |  |  | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
|  | Protection wall | Rm | 64 | 1 No | 15.515 |  |  |  | 64 | 100% | 0 | 0% | 0 | 0% | 0 | 0% | 64 | 100% | 0 | 0%
|  | Masonary Lined Side Drain | Rm | 64 | 1 No | 1.372 |  |  |  | 64 | 100% | 0 | 0% | 0 | 0% | 0 | 0% | 64 | 100% | 0 | 0%
| Total |  |  |  |  | 45.448 |  |  |  |  | 43.83% | 0 | 0% |  | 0% | 0 | 0% |  | 43.83% | 0 | 0%
MONTHLY PROGRESS REPORT FOR 306 'A' FOR THE MONTH OF JULY, 2026
Name of Division : National Highway Division - II
Source of funding : SASCI 2026-26 Part-I Name of Contractor : Zoremtluanga | [15 empty] | Agreement Amount : ` 4,79,76,224.11
Lenth of Project = 4.250 Km.
Sl No | Name of Work/Project | Item Description | Unit | Qty. |  | Item Agmt. Amt. (Rs in Lakh) | Approved Cost (Rs in Lakh) | Date of Commencement | Target of Completion | Cummulative Progress at the end of last Month |  |  |  | Achievement of works during the Month |  |  |  | Overall cummulative achievement |  |  |  | Remarks | Mode of Contract
[10 empty] | Phy |  | Fin |  | Phy |  | Fin |  | Phy |  | Fin
[10 empty] | Qty. | % | Amount | % | Qty. | % | Amount | % | Qty. | % | Amount | %
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
1 | Construction of Mauchar to Tuirial Road, Aizawl District under SASCI 2025-2026 Part-I | Earthwork & Subgrade | m3 | 4685.63 |  | 2108531.25 | 47976224.11 | 24.03.2026 | 24.01.2027 | 4685.63 | 100% | 0 | 0% | 0 | 0% | 0 | 0% | 4685.63 | 100% | 0 | 0% | Work halted due to Monsoon | Item Rate
|  | GSB | m3 | 1561.88 |  | 7965562.5 |  |  |  | 1561.88 | 100% | 0 | 0% | 0 | 0% | 0 | 0% | 1561.88 | 100% | 0 | 0%
|  | PCC | m3 | 1472.63 |  | 35048475 |  |  |  | 827.79 | 56.21% | 0 | 0% | 0 | 0% | 0 | 0% | 827.79 | 56.21% | 0 | 0%
|  | Breast Wall | Rm | 24 | 3 Nos. | 994162.4 |  |  |  | 24 | 100% | 0 | 0% | 0 | 0% | 0 | 0% | 24 | 100% | 0 | 0%
|  | HP Culvert | No | 3 | 3 nos. | 1859492.96 |  |  |  | 3 | 100% | 0 | 0% | 0 | 0% | 0 | 0% | 3 | 100% | 0 | 0%
| Total |  |  |  |  | 47976224.11 |  |  |  |  | 91.24% | 0 | 0% |  | 0% | 0 | 0% |  | 91.24% | 0 | 0%
Sr. Executive Engineer, PWD.,
National Highway Division-II
Aizawl : Mizoram

## NH-III
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY, 2026
Name of Division : National Highway Division-III, Thingdawl, Mizoram
Source of funding : 5054 ( R&B ) | [12 empty] | Rs in Lakh
Sl No | Name of Work/Project | Unit | Approved Cost (Rs in Lakh) | Date of Commencement | Target Date of Completion | Cumulative Progress at the end of last month |  | Achievement of works during the month |  | Overall Cumulative achievement |  | Fin (%) | Remarks | Mode of Contract | agg.amt
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Blacktopping of approach road from NH-54 to Vengthar thlanmual, Thingdawl | Km | 20 | 03.05.2026 | 03.07.2026 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | Works cannot be started due to Monsoon Rain | Tender | 63.93 | 0
2 | Resurfacing & Patch repair of approach road to NF Railway Godown, Biaabi (NH-154-RailwayGodown) Part 1 & 2 | Km | 50 | 03.05.2026 | 03.07.2026 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |  | Tender
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY, 2026
Name of Division : National Highway Division-III, Thingdawl, Mizoram
Source of funding : MORTH/NH | [12 empty] | Rs in Lakh
Sl No | Name of Work/Project | Unit | Approved Cost (Rs in Lakh) | Date of Commencement | Target Date of Completion | Cumulative Progress at the end of last month |  | Achievement of works during the month |  | Overall Cumulative achievement |  | Fin (%) | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Strengthening/Construction/Widening to 2-lane from km 89/00 to km 105/00 of NH-154 (New NH-6) under NH Division III in the state of Mizoram for the year 2022 – 23 (Length = 16 Km ) | Km | 8681 Lakhs | 04.09.2023 | 04.03.2025 | 99.89% | 5186.39 | 0% | 0 | 99.89% | 5186.39 | 97.67% |  | EPC
2 | Strengthening of NH-154( New NH-06) between km 105.00 and Km 119.00 including bridge repair in the state of Mizoram | Km | 2753.00 lakh | 30.06.2025 | 31.05.2026 | 13.03% | 124.88 | 0% | 0 | 13.03% | 100.02 | 7.83% | The upto date expenditure Rs. 124.88 is shown from the month of April, 2026 which is as per passed amount by this division. However, it has been realized that the ROpasses figure in SPS-01 is 84.76 lakh which differs from the previous mount by Rs. 40.10 lakh. As a result, the total upto date expenditure is lesser thatn the amount already reported. Moreover, an additional expenditure of GST bill Ts. 15/.25 lakh was added to the upto dae expenditure which has bee updated to Rs. 100.02 lakh as shown inthis report. Henceforth, aditional expenditure to be incurred from the coming bill will be shown in the MPR only after RO passed figure has been received. | EPC
3 | Short Term Maintenance Contract on NH - 306A from km 0.00 to Km 10.00 & from Km 33.00 to Km 45.00 in the State of Mizoram ( Job No. RW/GHT/STMC/MZ/25-26/8) | Km | 443.23 lakh | 09.12.2025 | 08.12.2026 | 23% | 0 | 17% | 0 | 40% | 0 | 0% | Work in progress | STMC
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY, 2026
Name of Division : National Highway Division-III, Thingdawl, Mizoram
Source of funding : NABARD | [10 empty] | Rs in Lakh
Sl No | Name of Work/Project | Unit | Approved Cost (Rs in Lakh) | Date of Commencement | Target Date of Completion | Cumulative Progress at the end of last month |  | Achievement of works during the month . |  | Overall Cumulative achievement |  | Fin (%) | Remarks | Mode of Contract | Agg.Amt
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
1 | Upgradation of Road from Meidum to Hortoki Phase-I (Km 0.00 to Km 9.10) | Km | 4445 Lakhs | 26.05.2020 | 26.11.2021 1st EOT=211 days (21.11.2021-20.06.2022) 2nd EOT=375 days (21.06.2022-30.06.2023) 3rd EOT=243 days (30.06.2023-28.02.2024) 4th EoT=90 days (20.2,2024-28.5.2024) | 100% | 4356.17 | 0% | 0 | 100% | 4356.17 |  | completed | Item Rate
1 | Construction of road from Khamrang to Selesih Phase-I (Length =11.00 Kms) Group-A (0/00 to 3/600 Km) | Km | Original =6583.18. RE 1 = 4028.61 | 08.02.2021 | 20.11.2021 1st EOT=184 days (upto 08.02.2023; 2nd EOT=150 days (wef 09.02.2023- 08.07.2023) 3rd EoT 9.7.2023-5.12.2023 submitted to SE (not granted)vide NH-16/1/2021/PWD/NHD-III/48 Dt. 13.10.2023 | 83.33% | 388.92 | 0% | 0 | 83.33% | 388.92 | 54.8609 | Work abandoned due to alignment overlap with 4-lane NH. | Item Rate | 708.92
2 | Construction of road from Khamrang to Selesih Phase-I (Length =11.00 Kms) Group-B (3/60 to7/200 Km) | Km | Original =6583.18. RE 1 = 4028.61 | 08.02.2021 | 20.11.2021 1st EOT=184 days (upto 08.02.2023; 2nd EOT=150 days (wef 09.02.2023-08.07.2023) 3rd EoT 9.7.2023-5.12.2023 submitted to SE (not granted)vide NH-16/1/2021/PWD/NHD-III/40 Dt. 21.7.2023 | 88.89% | 704.4 | 0% | 0 | 88.89% | 704.4 | 100.2106 | Work abandoned due to alignment overlap with 4-lane NH. Expenditure exceeds Agreement amount. | Item Rate | 702.92
3 | Construction of road from Khamrang to Selesih Phase-I (Length =11.00 Kms) Group-C (7/200 to 11/00 Km) | Km |  | 08.02.2021 | 20.11.2021 1st EOT=184 days (upto 08.02.2023; 2nd EOT=150 days (wef 09.02.2023-08.07.2023) 3rd EoT 9.7.2023-5.12.2023 submitted to SE (not granted)vide NH-16/1/2021/PWD/NHD-III/40 Dt. 21.7.2023 | 47.78% | 317.84 | 0% | 0 | 47.78% | 317.84 | 45.2216 |  | Item Rate | 702.85
4 | Construction of road from Khamrang to Selesih Phase-I (Sh: Construction of Rigid Pavement from 7/00 to 11/00 Kmp = 4.00 kms) | Km | Original =6583.18. RE 1 = 4028.61 | 16.08.2022 | 16.02.2024 1st EoT = 397 days 17.2.2024 to 19.03.2025 2nd EoT = 336 days 20.3.2025 to 18.02.2026 3rd EoT = 336 days i.e 19.02.2026 to18.01.2027 | 45% | 432.6 | 0% | 0 | 45% | 517.11 | 35.3357 |  | Item Rate | 1463.42
| Construction of road from Khamrang to Selesih Phase-I (Contingency ) = | [9 empty] | 47.79
5 | Construction of road from Khamrang to Selesih Phase-II Group-1 (11/00 to 22/00 Km) | Km | 14529.29 for Phase-II | 08.11.2021 | 08.05.2023 1st EOT=210 days (wef 09.05.2023 - 04.12.2023 2nd EoT 206 days 4.12.2023-27.6.2024 submitted to SE (not granted)vide NH-16/1/2021/PWD/NHD-III/62 Dt. 1.8.2024 | 22.15% | 664.75 | 0% | 0 | 22.15% | 664.75 | 26.202 |  | Item Rate | 2537.02
6 | Construction of road from Khamrang to Selesih Phase-II Group-2 (22/00 to 25/00 Km) | Km |  | 22.11.2021 | 22.11.2022 1st EOT=90 days (upto 20.02.2023); 2nd EOT=90 days (wef 21.02.2023-21.05.2023); 3rd EOT=90 days (22.05.2023-19.08.2023) 4th EoT 90 days 20.8.2023-18.11.2023 submitted to SE (not granted)vide NH-16/1/2021/PWD/NHD-III/44 Dt. 16.09.2023 | 62.88% | 386.28 | 0% | 0 | 62.88% | 386.28 | 88.6492 |  | Item Rate | 435.74
7 | Construction of road from Khamrang to Selesih Phase-II Group-3 (25/00 to 28/00 Km) | Km | 14529.29 for Phase II | 11.11.2021 | 11.11.2022 1st EOT=90 days (upto 09.02.2023); 2nd EOT=90 days (wef 10.02.2023-11.05.2023) 3rd EOT=90days (Wef 12.05.23-09.08.2023) 4th EoT 90 days 10.8.2023-8.11.2023 submitted to SE (not granted)vide NH-16/1/2021/PWD/NHD-III/42 Dt. 7.8.2023 | 42.96% | 262.85 | 0% | 0 | 42.96% | 262.85 | 42.9543 |  | Item Rate | 611.93
8 | Construction of road from Khamrang to Selesih Phase-II (Sh: - Construction of Rigid Pavement from 11/00 to 19/00 Kmp = 8.00 kms) Group A | Km |  | 26.08.2023 | 26.08.2025 | 0% | 0 | 0% | 0 | 0% | 0 | 0 |  | Item Rate | 2841.21
9 | Construction of road from Khamrang to Selesih Phase-II (Sh: - Construction of Rigid Pavement from 19/00 to 28/00 Kmp = 9.00 kms) Group B | Km | 14529.29 for Phase II | 26.08.2023 | 26.08.2025 | 0% | 0 | 0% | 0 | 0% | 0 | 0 |  | Item Rate | 2525.52
Construction of road from Khamrang to Selesih Phase-II (Contingency ) = | [10 empty] | 62.54
Sr.Executive Engineer,PWD., National Highway Division-III, Thingdawl : Mizoram

## PD -I
MONTHLY PROGRESS REPORT UNDER EXECUTIVE ENGINEER, PROJECT DIVISION- I, PWD FOR JULY 2026
Sl. No. | Name of Scheme | Unit | Approved Cost (in lakhs) | Date of Commencement | Target date of completion | Cummulative progress at the end of last month |  | Achievement of work during the month |  | Overall cummulative achievement |  | Remarks | Mode of Tender
| Name of Work/Project |  |  |  |  | Phy (%) | Fin (₹) | Phy (%) | Fin (₹) | Phy (%) | Fin (₹)
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) | (10) | (11) | (12) | (13) | (14)
A. NEC
1 | C/o of Patient Lodging at Mawdiangdiang near NEIGRIMS, Shillong | 1 | 419.67 | 9.9.21 | 9.9.2025 | 100% | 409.18 | 0% | 10.42 | 100% | 419.6 | Works completed | Item rate
2 | Co/ Veterinary Information and Resource Centre at Aizawl | 1 | 339.25 | 25.9.23 | 25.9.25 | 100% | 339.07 | 0% |  | 100% | 339.0672 | Works completed | Item rate
3 | C/o Aizawl Institute of Arts & Music for the NER, Tuivamit Tlang, Aizawl | 1 | 590.23 | 4.9.23 | 4.9.25 | 100% | 621.22 | 0% |  | 100% | 621.221 | Works completed | Item rate
4 | Establishment of Central Medical Warehouse at Aizawl, Mizoram | 1 | 1101.11 | 14.8.23 | 14.8.25 | 57% | 650 | 3% | 325 | 60% | 975 | E.O.T upto 31.12.26 | Item rate
5 | Infrastructure Development of Biotechnology Cell in Mizoram (C/O Building at MINECO | 1 | 188.66 | 10.7.23 | 10.1.25 | 49.1% | 69.55 | 0.8% | 0 | 49.9% | 69.55 | EOT upto 4.7.26 | Item rate
B. SASCI
6 | C/o Central Medical Warehouse at ZMC, Approach Road (SH: Approach Road) | 1 | 150 | 16.12.23 | 16.12.24 | 66% | 47.428 | 0% | 0 | 66% | 47.428 | EOT upto 18.6.26 | Item rate
7 | C/o FCS&CA 1500 MT Capacity Godown at Sairang | 1 | 921.07 | 7.4.23 | 23.6.2026 | 96% | 332.98 | 1% | 2 | 97% | 334.98 | EOT upto 31.7.26 | Item rate
8 | Constn. of Govt. Staff Qtrs. (Block-C) at DIET Complex, Chaltlang. | 1 | 544 | 29.4.23 | 29.10.25 | 100% | 450.0945 | 0% | 0 | 100% | 450.0945 | Works completed | Item rate
9 | Construction of E-in-C, PHED Office at MINECO, Aizawl | 1 | 796 | 26.6.25 | 26.6.26 | 25% | 0 | 2% | 85.02 | 27% | 85.02 | EOT upto 11.5.27 | Item rate
10 | Vertical Extension of Mizoram Upa Pawl Hqr. Building for Community Hall & Office at Khatla, Aizawl, Mizoram | 1 | 200 | 26.6.25 | 26.6.26 | 50% | 95.45 | 5% |  | 55% | 95.45 |  | Item rate
11 | Construction of Examination Hall at MPSC Campus | 1 | 1092 | 26.6.25 | 26.6.26 | 25% | 205.62 | 2% |  | 27% | 205.62 |  | Item rate
12 | Construction of Market Building at Vaivakawn, Aizawl | 1 | 2535 | 5.6.25 | 5.6.26 | 15% | 43.89 | 5% | 132.11 | 20% | 176 | EOT upto 26.2.27 | Item rate
13 | Construction of MLA Hostel at Tuikual, Aizawl | 1 | 2679 | 14.8.25 | 14.8.26 | 10.7% | 0 | 3.9% | 7.09 | 14.6% | 7.09 |  | Item rate
14 | Construction of Government Residential Quarter Type-V (4 units) at new Secretariat Complex, Khatla | 1 | 692 | 25.3.2025 | 25.3.2026 | 42% | 117.62 | 3% | 48.03 | 45% | 165.65 | EOT upto 15.11.26 | Item rate
15 | Construction of Government Residential Quarter Type-VI (4 units) at new Secretariat Complex, Khatla | 1 | 849.66 | 28.3.2025 | 28.3.2026 | 42% | 146.93 | 3% | 41.12 | 45% | 188.05 | EOT upto 15.11.26 | Item rate
16 | Construction of Working Women Hostel, ITI Veng, Aizawl | 1 | 1818 | 8.4.2025 | 8.4.2026 | 37% | 356.61 | 2% |  | 39% | 356.61 | EOT upto 5.10.26 | Item rate
17 | Construction of Integrated Office Complex at MINECO, Aizawl | 1 | 6000 | 23.4.2025 | 23.4.2026 | 30% | 416.22 | 1% |  | 31% | 416.2227 |  | Item rate
18 | Modernization of Govt Industrial Training Institute (ITI), Aizawl | 1 | 2500 | 28.4.2025 | 28.4.2026 | 55% | 636.58 | 5% | 87.39 | 60% | 723.97 | EOT upto 15.11.26 | Item rate
19 | Construction of Durbar Hall & Personal Branch of Raj Bhavan | 1 | 682.7 | 16.7.2025 | 16.7.2026 | 29% | 111.75 | 1% | 27.166 | 30% | 138.916 |  | Item rate
20 | Construction of Quarters, Barrack & Vertical Extension of DRC Office, Silchar & Sewer line at Mizoram House, Guwahati | 1 | 331 | 23.7.2025 | 23.7.2026 | 30% | 0 |  | 24.19 | 30% | 24.19 |  | Item rate
21 | Construction of AMC Building at Aizawl, Mizoram | 1 | 5000 | 25.04.26 | 25.04.26 | 32% | 120 | 1% | 91.67 | 33% | 211.67 | EOT upto 22.1.27 | Item rate
22 | Construction of Government Bethlehem High School, Bethlehem VT | 1 | 220 | 4.2.2025 | 4.2.2027 | 25% | 50 | 2% |  | 27% | 50 |  | Item rate
23 | Construction of Multipurpose Community Cultural Centre at Bethlehem Vengthlang, Aizawl | 1 | 950 | 4.2.2025 | 4.2.2027 | 10% | 100 | 2% |  | 12% | 100 |  | Item rate
24 | Construction of State Emergency Operation Centre (SEOC) at MINECO | 1 | 1850 | 13.5.25 | 13.5.26 | 21.3% | 209.82 | 2.2% | 4.56 | 23.5% | 214.38 | EOT upto 26.4.27 | Item rate
25 | Construction of Working Women Hostel, Khatla | 1 | 2972 | 24.4.25 | 24.4.26 | 25.5% | 445.38 | 1% |  | 26.5% | 445.38 | EOT upto 20.1.27 | Item rate
26 | Construction of Building for Additional Classroom at J. Thankima College, Aizawl | 1 | 984 | 4.7.25 | 4.7.26 | 10.8% | 0 | 1.2% | 1.3 | 12% | 1.3 |  | Item rate
27 | Re-construction of Central Jail, Aizawl | 7 | 1329 | 16.5.25 | 16.5.26 | 46.7% | 183.03 | 2.4% |  | 49.1% | 183.03 | EOT upto 13.1.27 | Item rate
28 | Construction of New Campus for Govt. Aizawl West College Building | 2 |  |  |  | 25% | 434.91 | 3% | 230.94 | 28% | 665.85 |  | Item rate
| a. Administrative Building |  | 697 | 9.5.25 | 9.5.26 |  | 119.67 |  | 91.45 |  | 211.12 | EOT upto 6.1.27
| b. Academic Building) |  | 2347 | 9.5.25 | 9.5.26 |  | 315.241 |  | 139.49 |  | 454.731 | EOT upto 4.2.27
29 | Vertical Extension of Chief Controller of Accounts Office Main & Annex Building | 1 | 786 | 26.8.2025 | 26.8.2026 | 6.5% | 94.13 | 5.5% |  | 12% | 94.13 |  | Item rate
30 | Construction of Bru Student Hostel at Tahnril | 1 | 415 | 1.7.2025 | 1.7.2026 | 23.5% | 77.87 | 2.4% |  | 25.9% | 77.87 | EOT upto 27.2.27 | Item rate
31 | Construction of Deputy Speaker's Bungalow at Aizawl, Mizoram | 1 | 302 | 26.2.2026 | 26.2.2027 | 0.55% |  | 0.27% |  | 0.82% |  |  | Item rate
32 | Construction of Market & Parking at Chawnpui near BCM Church, Chawnpui, Aizawl | 1 | 220 | 5.3.2026 | 5.3.2027 | 4.1% |  | 1% | 25.88 | 5.1% | 25.88 |  | Item rate
C. SEDP
33 | Construction of High Court Parking Building at MINECO | 1 | 1960 | 2.7.20 | 29.8.24 | 100% | 1886.21 | 0% | 2.08 | 100% | 1888.29 | Works completed | Item rate
D. NABARD
34 | C/O 24 Warehouses with associated Infrastructure in 23 locations in Mizoram under NABARD (Group-II Zuangtui/ Sairang) | 1 | 485.94 | 17.7.23 | 17.7.2025 | 99.5% | 360.31 | 0% |  | 99.5% | 360.3148 | EOT upto 31.7.26 | Item rate
Executive Engineer, PWD
Project Division-I
Aizawl, Mizoram

## PD-II
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY, 2026
Name of Division: Project Division-II, P.W.D
Sl.No. | Name of Schemet | Unit | Approved cost (Rs.in lakh) | Date of Commence-ment | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Mode of Tender | Remarks
| Name of Work/Project |  |  |  |  | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | . | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 14 | 13
NABARD
1 | Construction of 24 Warehouses with associated Infrastructure in 23 locations in Mizoram Group-I i) Construction of Warehouse and other amenities at Bairabi (1000 MT) | % | 316.55 | 17.07.2023 | (O)17.07.2025 (R)31.10.2025 | 100% | 316.38 | 0% | 0 | 100% | 316.38 | Item Rate | Work Completed
| ii) Construction of Warehouse and other amenities at Marpara (500 MT) | % | 235.73 | 17.07.2023 | (O)17.07.2025 (R)07.11.2025 | 100% | 234.95 | 0% | 0.78 | 100% | 235.73 | Item Rate | Work Completed
| iii) Construction of Warehouse and other amenities at Sialsuk (200 MT) | % | 171.09 | 17.07.2023 | (O)17.07.2025 (R)11.01.2026 | 100% | 170.42 | 0% | 0.5 | 100% | 170.92 | Item Rate | Work Completed
| iv) Construction of Warehouse and other amenities at Zawlnuam (200 MT) | % | 176 | 17.07.2023 | (O)17.07.2025 (R)30.11.2025 | 100% | 175.03 | 0% | 0.97 | 100% | 176 | Item Rate | Work Completed
| v) Construction of Warehouse and other amenities at Kanhmun (200 MT) | % | 175.8 | 17.07.2023 | (0)17.07.2025 (R)30.11.2025 | 100% | 175.03 | 0% | 0.77 | 100% | 175.8 | Item Rate | Work Completed
2 | Construction of 24 Warehouses with associated Infrastructure in 23 lacations in Mizoram Group-IX i) Construction of Warehouse and other amenities at Phuldungsei (200 MT) | % | 175.81 | 17.07.2023 | (O)17.07.2025 (R)10.11.2025 | 100% | 174.93 | 0% | 0.88 | 100% | 175.81 | Item Rate | Work Completed
NEC
1 | Construction of Market Building at West Phaileng, Mamit District. | % | 278.25 | 22.08.2023 | 22.08.2025 | 100% | 278.25 | 0% | 0 | 100% | 278.25 | Item Rate | Work Completed (COS under process)
2 | Construction of Fish Farmers Training Centre at Lengpui | % | 924.32 | 20.06.2025 | 20.06.2027 | 55% | 486 | 5% | 0 | 60% | 486 | Item Rate | Work in Progress.
NESIDS
1 | Construction of 100 Bedded District Hospital at Kolasib. | % | 2200 | 23.09.2022 | ( O) 23.09.2024 (R1) 13.10.2025 (R2) 28.02.2026 | 97% | 1859.41 | 1% | 0 | 98% | 1859.41 | EPC | Work in Progress. (EOT under process)
2 | Construction of Development of heliport and helipads in Thenzawl, Mizoram | % | 1200 | 19.05.2026 | 19.05.2028 | 0% | 0 | 1.5% | 0 | 1.5% | 0 | EPC | Work in Progress.
CSS
1 | Construction of Fast Track Court Building at Kolasib. | % | 1799.85 | 20.09.2022 | (O) 20.09.2024 (R1) 18.02.2025 (R2) 31.05.2025 (R3) 31.07.2025 (R4)12.12.2025 | 100% | 1604.06 | 0% | 0 | 100% | 1604.06 | Item Rate | Work Completed
ICMR
1 | Construction of Model Rural Health Research Unit at Lungtian Ram, Aibawk. | % | 207.5 | 21.09.2023 | 21.03.2025 | 100% | 207.5 | 0% | 0 | 100% | 207.5 | Item Rate | Work Completed
SASCI
Work under SASCI 2024 - 2025 Part - I (Untied)
1 | Re-Construction of District Prison at Mamit | % | 453.37 | 14.05.2025 | (O)14.05.2026 (R1)30.07.2026 | 75% | 189.59 | 10% | 158.88 | 85% | 348.47 | Item Rate | Work in Progress
2 | Re-Construction of District Prison at Kolasib | % | 751.03 | 27.05.2025 | (O)27.05.2026 (R1)27.10.2026 | 76% | 304.22 | 2% | 70.39 | 78% | 374.61 | Item Rate | Work in Progress
Work under SASCI 2024 - 2025 Part - V
1 | Contruction of Civil SDO Qrts Type - IV at Kawnpui | % | 78.08 | 15.05.2025 | 15.5.2026 | 100% | 49.14 | 0% | 22.68 | 100% | 71.82 | Item Rate | Work in Progress
2 | Contruction of Civil SDO Qrts Type - IV at Bairabi | % | 82.32 | 15.05.2025 | 15.5.2026 | 100% | 77.82 | 0% | 0 | 100% | 77.82 | Item Rate | Civil Works Completed Electrification yet to start
3 | Construction of Directorate of Economics & Statistics Office at MINECO, Aizawl | % | 207 | 30.04.2025 | (O) 30.04.2026 (R1)10.09.2026 | 85% | 100 | 5% | 37.28 | 90% | 137.28 | Item Rate | Work in Progress
4 | Upgradation of District Research Office at Kolasib | % | 24.03 | 20.08.2025 | 20.08.2026 | 100% | 22.05 | 0% | 0 | 100% | 22.05 | Item Rate | Work Completed
5 | Upgradation of District Research Office at Mamit | % | 71.37 | 20.08.2025 | 20.08.2026 | 55% | 39.03 | 25% | 16.84 | 80% | 55.87 | Item Rate | Work in Progress
Work under SASCI 2024 - 2025 Part - VII (A)
1 | Contruction of Revenue Staff Quarters (Type - II & III) at Kolasib | % | 192.18 | 11.08.2025 | 11.08.2026 | 65% | 67.14 | 3% | 53.6 | 68% | 120.74 | Item Rate | Work in Progress
2 | Construction of DC Revenue (SO) Office at Mamit | % | 450 | 11.08.2025 | 11.08.2026 | 0% | 0 | 0% | 0 | 0% | 0 | Item Rate | Work yet to be started
3 | Re- Construction of DC Office Complex at Mamit | % | 1000 | 21.07.2025 | 21.07.2026 | 5% | 10.91 | 3% | 0 | 8% | 10.91 | Item Rate | Work in Progress EOT under process
Work under SASCI 2024 - 2025 Part -X
1 | Contruction of Working Women Hostel at ZMC / H Falkawn, Mizoram | % | 2634.06 | 14.05.2025 | (O)14.05.2026 (R1)31.01.2027 | 40% | 556.22 | 0.5% | 126.46 | 40.5% | 682.68 | Item Rate | Work in Progress Secured Advance Granted for Rs. 213.55 lakh
2 | Contruction of Working Women Hostel at Thenzawl | % | 1100 | 15.05.2025 | (O)15.05.2026 (R1)16.10.2026 | 32% | 284.21 | 2% | 0 | 34% | 284.21 | Item Rate | Work in Progress Secured Advance Granted for Rs. 104.91 lakh
Work under SASCI 2025 - 2026 Part -I
1 | Construction of Hlimen & Saikhamakawn Community Hall | % | 500 | 09.03.2026 | 09.03.2027 | 3% | 0 | 2% | 0 | 5% | 0 | Item Rate | Work just started
Deposit Work
1 | Construction of Settlement Officer Quarters (Type-IV) at Kolasib | % | 66.87 | 1.10.2025 | 1.10.2026 | 95% | 14.87 | 5% | 0 | 100% | 14.87 | Item Rate | Work in Progress
HRDEM (MoHFW)
1 | Construction of National Emergency Life Support (NELS) at ZMC/H, Falkawn | % | 140 | 20.01.2026 | 20.01.2027 | 22% | 17.87 | 10% | 0 | 32% | 17.87 | Item Rate | Work in progress
Sr. Executive Engineer, PWD.,
Project Division-II, Aizawl

## PD- III
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI Part - I 2023 - 2024
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Gov't Serchhip College ( Sh: Administrative Block) | % | 650 | 27.2.2023 | 01.04.2026 | 99.8% | 245.67 | 0.05% | 0 | 99.85% | 245.67 | Work in Progress | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI 2023 -2024
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Const. of Football ground and volleyball court at Vapar, Selam, tualcheng, Hnahla. Hmunhmeltha | % | 203 | 13.10.2023 | 13.10.2024 | 100% | 99.3 | 0% | 0 | 100% | 99.3 | Work completed | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI 2023 -2024
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Const. of Khawbung futsal ground, gallery, Roofing, Lighting & Laying of Artificial Turf | % | 255.5 | 14.10.2023 | 7.2.2025 | 100% | 114.93 | 0% | 0 | 100% | 114.93 | Work completed | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI 2023 -2024
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Const. of Community Hall at Dulte & Chhawrtui | % | 271 | 13.10.2023 | 02.03.2025 | 100% | 139.98 | 0% | 0 | 100% | 139.98 | Work completed | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI 2023 -2024
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Development of Community Centre at Zotlang, Champhai (Sh: Cons of Market Building cum community Hall & Futsal Ground) | % | 215 | 14.10.2023 | 7.2.2025 | 100% | 89.98 | 0% | 0 | 100% | 89.98 | Work completed | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI 2023 -2024
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Additional works for const. of General Nursing Midwifery (GNM) hostel and Nursing Hostel at champhai | % | 438 | 13.10.2023 | 7.2.2025 | 100% | 264.07 | 0% | 0 | 100% | 264.07 | Work completed | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI 2023 -2024
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Const of Public Playground at Keitum, Lungchhuan | % | 250 | 13.10.2023 | 13.10.2024 | 100% | 97.5 | 0% | 0 | 100% | 97.5 | Work completed | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI 2023 -2024
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Const. of Gov't Building at Serchhip District (Sh: PWD staff qtrs, Extension of Gov't Serchhip College and Kitchen cum Dining at PTS, Thenzawl, Mizoram) | % | 362 | 13.10.2023 | 18.04.2025 | 100% | 308.84 | 0% | 0 | 100% | 308.84 | Work completed | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI 2023 -2024
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Const of Community Resource Center at Baktawng and Chhuanthar | % | 350 | 13.10.2023 | 13.10.2024 | 100% | 140 | 0% | 0 | 100% | 140 | Work completed | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI 2023 -2024
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Const of Community Hall at Khawzawl Vengthar, Arro Village, Khawzawl Dinthar and Khawhai South | % | 209 | 13.10.2023 | 13.10.2024 | 100% | 79.25 | 0% | 0 | 100% | 79.25 | Work completed | PWD Form - 8
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI Part V 2024-2025
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Gov't Quarters (General pool) under SASCI 2024 - 2025 at Serchhip (1299.68 lakhs) | % | 344.74 | 24.4.2025 | 24.4.2026 | 85% | 192.79 | 3% | 26.35 | 88% | 219.14 | Work in progress | -
a) Type - IV & III Quarters (Design - A) at P & E Veng (Treasury Department Site)
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI Part V 2024-2025
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Gov't Quarters (General pool) under SASCI 2024 - 2025 at Serchhip (1299.68 lakhs) | % | 296.54 | 24.4.2025 | 24.4.2026 | 85% | 157.84 | 3% | 0 | 88% | 157.84 | Work in progress | -
b) Type - IV & III Quarters (Design - B) at P & E Veng ( Treasury Department Site)
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI Part V 2024-2025
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Gov't Quarters (General pool) under SASCI 2024 - 2025 at Serchhip (1299.68 lakhs) | % | 351.94 | 24.4.2025 | 24.4.2026 | 74% | 193.85 | 5% | 0 | 79% | 193.85 | Work in progress | -
c) Type - IV & III Quarters (Design - A) at P & E Veng ( Soil & Water Conservation Department Site)
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI Part V 2024-2025
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Gov't Quarters (General pool) under SASCI 2024 - 2025 at Serchhip (1299.68 lakhs) | % | 306.46 | 24.4.2025 | 24.4.2026 | 84% | 171.47 | 4% | 0 | 88% | 171.47 | Work in progress | -
d) Type - IV Quarters ( 3 Units) at Hospital Complex, Serchhip, Mizoram
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI Part V 2024-2025
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Circuit House under DC Office (SH: Construction of Circuit House at Serchhip) | % | 652 | 16.4.2025 | 29.10.2026 | 69% | 270.81 | 2% | 0 | 71% | 270.81 | Work in progress | -
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI Part I 2024-2025
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Circuit House under DC Office (SH: Construction of Circuit House at Khawzawl) | % | 1000 | 16.7.2025 | 17.12.2026 | 33% | 122.09 | 4% | 77.91 | 37% | 200 | Work in progress | -
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI Part I 2024-2025
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Re-construction of District Jail, Serchhip | % | 372.4 | 8.5.2025 | 8.5.2026
| 1. Repair & Extension of Administrative Building |  |  |  |  | 3% | 106.41 | 4% | 0 | 7% | 106.41 | To be done only after Multipurpose Hall is completed and this office is shifted.
| 2. Multipurpose hall & Barrack |  |  |  |  | 39% |  | 0% |  | 39% |  | Work in progress
| 3. Segregation Cell & Vocation Hall |  |  |  |  | 73% |  | 6% |  | 79% |  | Structure completed.
| 4. Guard Duty Post (1 no) |  |  |  |  | 97% |  | 0% |  | 97% |  | Nearly completed.
| 5. Extension of MI Room |  |  |  |  | 83% |  | 4% |  | 87% |  | To be done only after Segregation Cell is completed and this office is shifted.
| 6. Staff Quarters Type-IV |  |  |  |  | 53% |  | 10% |  | 63% |  | Work just started. Delayed due to change of site.
| 7. Repair & Renovation of Male ward-2, 1st floor and Chapel |  |  |  |  | 23% |  | 10% |  | 33% |  | Work in progress
| Overall |  |  |  |  | 53% | 106.41 | 5% | 0 | 58% | 106.41
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI Part I 2024-2025
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Re-construction of District Jail, Champhai | % | 826.88 | 16.4.2025 | 17.10.2026 | [7 empty] | -
| 1. Male Ward |  |  |  |  | 0% | 265.15 | 0% | 0 | 0% | 265.15 | To be done only after Female ward is completed and Male prisoners shifted.
| 2. Female Ward |  |  |  |  | 84% |  | 0% |  | 84% |  | Structure completed.
| 3. Main Wall, Separation wall & Duty post |  |  |  |  | 72% |  | 5% |  | 77% |  | Work in progress
| 4. Type-II Quarters Block-I |  |  |  |  | 69% |  | 0% |  | 69% |  | Structure completed.
| 5. Type-II Quarters Block-II) |  |  |  |  | 0% |  | 2% |  | 2% |  | work in progress
| Overall |  |  |  |  | 54% | 256.15 | 2% | 0 | 56% | 256.15
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI Part I 2024-2025
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Re-construction of District Jail, Saitual (Sh: Separation Wall (31.30m)) | % | 45.43 | 29.4.2025 | 29.4.2026 | 100% | 22.26 | 0% | 0 | 100% | 22.26 | Work Completed | -
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI Part X 2024-2025
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Working Women Hostels(Champhai), Mizoram. | % | 1366 | 8.04.2025 | 9.10.2026 | 30% | 155.17 | 3% | 0.34 | 33% | 155.51 | Work in progress | -
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI Part V 2024-2025
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Circuit House under DC Office (SH: Construction of Circuit House at Saitual) | % | 640 | 16.4.2025 | 02.11.2026 | 55% | 247.33 | 1% | 1.76 | 56% | 249.09 | Work in progress | -
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI Part I 2024-2025
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of DC's Bungalow at Saitual DC Complex, Saitual N | % | 224 | 4.7.2025 | 4.7.2026 | 69% | 118.9 | 31% | 0 | 100% | 118.9 | Work in progress | Restricted Tender
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI Part I 2024-2025
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Revenue Staff Quarters at Serchhip | % | 333.81 | 16.7.2025 | 16.7.2026 | 48% | 92.33 | 4% | 0 | 52% | 92.33 | Work in progress | Restricted Tender
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI Part I 2024-2025
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Revenue Staff Quarters at Saitual | % | 198.12 | 23.7.2025 | 09.12.2026 | 30% | 46.98 | 5% | 0 | 35% | 46.98 | Work in progress | Restricted Tender
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI Part I 2024-2025
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Revenue Staff Quarters at Khawzawl | % | 211.19 | 23.7.2025 | 24.12.2026 | 19% | 0 | 6% | 43.04 | 25% | 43.04 | Work in progress | -
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI Part-VII(A) 2024-2025
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of DC Revenue (SO) Office at Champhai, Mizoram | % | 468 | 24.7.2025 | 25.10.2026 | 80% | 234.89 | 3% | 3.83 | 83% | 238.72 | Work in progress | Restricted Tender
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI Part I 2024-2025
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of SDO ( C ) Office and Quarter at N. Vanlaiphai | % | 189.29 | 4.7.2025 | 4.7.2026 | 95% | 134.53 | 1% | 0 | 96% | 134.53 | Work in progress | Restricted Tender
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI Part I 2024-2025
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of District Drugs Control and Awareness Centre at Serchhip excluding Bypass Road | % | 200 | 13.8.2025 | 13.8.2026 | 54% | 81.67 | 4% | 0 | 58% | 81.67 | Work in progress | Restricted Tender
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI Part-I 2025-2026
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Upgradation of District Research Office at Champhai | % | 50.32 | 19.8.2025 | 19.8.2026 | 80% | 30.33 | 2% | 0 | 82% | 30.33 | Work in progress | Restricted Tender
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI Part-I 2025-2026
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Upgradation of District Research Office at Khawzawl | % | 25.12 | 13.7.2025 | 13.7.2026 | 100% | 24.15 | 0% | 0 | 100% | 24.15 | Work Completed | Restricted Tender
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI Part-I 2025-2026
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Upgradation of District Research Office at Serchhip | % | 11.2 | 19.8.2025 | 19.8.2026 | 100% | 10.8 | 0% | 0 | 100% | 10.8 | Work completed | Restricted Tender
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI Part-I 2025-2026
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Upgradation of District Research Office at Saitual | % | 41 | 21.8.2025 | 21.8.2026 | 100% | 25 | 0% | 11.9 | 100% | 36.9 | Work completed | Restricted Tender
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI Part-I 2025-2026
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Const of Treasury Office, Treasury Officers Qtrs, and Treasury Staff Qtrs at Khawzawl | % | 300 | 11.3.2026 | 20.3.2027 | [6 empty] | Work could not be started yet | Restricted Tender
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026
.. |  | Project Division - III
Source of Funding : |  | SASCI Part-I 2025-2026
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Const of Treasury Office, Treasury Officers Qtrs, and Treasury Staff Qtrs at Saitual | % | 300 | 31.03.2026 | 31.03.2027 | [6 empty] | Work could not be started yet | Restricted Tender
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI Part -IV 2025 - 2026
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Upgradation of Infrastructures in GM Higher Secondary School at Champhai, Mizoram | % | 13.5 | 07.07.2026 | 07.07.2027 | 0% | 0 | 0% | 0 | 0% | 0 | Work not Started | Restricted Tender
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SASCI Part - I 2024 - 2025
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Const. of Sialhawk Multipurpose Hall Sialhawk, Khawzawl District, | % | 200 | 23.3.2026 | 24.3.2027 | 0% | 0 | 0% | 0 | 0% | 0 | Work not yet started | Restricted Tender
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | NLCPR
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Name of work : Construction of Community Hall at various places in Mizoram ( Sh: Const. Of Community Hall at Saitual, Thingsulthliah, Maite, Tualbung, Lungpher, Buhban, Lenchim, Chawrtui and Puilo). | % | 206.49 | 22.2.2012 | 30.11.2019 |  | 195.43 |  |  | 100% | 195.43 | Completed and balance fund of Rs.20.48 (Rs. 16.35 Lakhs NLCPR + Rs. 4.13 Lakhs SMS) awaited for clearing liabilities.
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SPP
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Circuit House at Serchhip | % | 358.18 | - | - | - | - | - | - | - | - | Work not executed due to various reasons. Fund received Rs. 358.18 lakhs is kept at D-III
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SCA/SASCE
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Improvement/Upgradation of Operational/Non-operational facilitiies of Lengpui Airport, (Sh: Renovation of terminal building). | % | 2124 | 10.3.2021 | 19.5.2026 | 99.6% | 1773.36 | 0% | 0 | 99.6% | 1773.36 | Power & Electricity Department seek fund amounting to Rs. 3.20 crore from Government of Mizoram for installation of new power supply. Until and unless the new power supply system is completed, work could not be continued. | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | ECRP - II
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of 50 Bedded critical care block at Champhai District Hospital, Mizoram | % | 1346.4 | 4.8.2023 | 5.9.2026 | 96% | 796.06 | 1% | 0 | 97% | 796.06 | Work in Progress | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | NABARD - WIF
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of 24 Warehouses with associated infrastructure in 23 locations in Mizoram under NABARD (Group VII : Teikhang ,Rabung & Dungtlang). | % | 336.53 | 17.7.2023 | 31.3.2026 | [6 empty] | Teikhang Warehouse is inaugurated on 30.04.2026. Civil Works at Rabung Warehouse is completed without I/E. Work in Progress at Dungtlang Warehouse. | PWD Form - 8
| i) Construction of 200 MT warehouse at Teikhang |  |  |  |  | 100% | 70.49 | 0% | 0 | 100% | 70.49
| ii) Construction of 200 MT warehouse at Rabung |  |  |  |  | 100% | 70.58 | 0% | 0 | 100% | 70.58
| iii) Construction of 200 MT warehouse at Dungtlang |  |  |  |  | 100% | 81.89 | 0% | 0 | 100% | 81.89
| iv) Construction of staff quarters at Dungtlang |  |  |  |  | 100% | 6.68 | 0% | 0 | 100% | 6.68
| Overall |  |  |  |  | 100% | 229.64 | 0% | 0 | 100% | 229.64
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | NABARD RIDF- XXX
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction Of Urban Primary Health Centre at Champhai | % | 176.9 | 07.10.2025 | 07.10.2026 | 20% | 30.91 | 10% | 0 | 30% | 30.91 | Work in Progress | -
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | NABARD RIDF- XXX
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction Of Ngopa CHC | % | 572.8 | 18.05.2026 | 18.05.2027 | 3% | 0 | 0% | 0 | 3% | 0 | Work in Progress | -
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | NABARD RIDF- XXX
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction Of Kawlkulh PHC | % | 401.03 | 16.12.2025 | 16.12.2026 | 4% | 0 | 0% | 0 | 4% | 0 | Work in Progress | -
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | SCA to TSS/CSS
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Const of 100 Bedded Dist hospital at Saitual ( Sh: Cons of OPD building at district hospital, Saitual) | % | 200 | 13.10.2023 | 13.10.2025 | 100% | 199.92 | 0% | 0 | 100% | 199.92 | Work completed | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | NEC
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Creation of Passion fruit Processing unit at Cold Storage , New Champhai Mizoram. | % | 185.39 | 23.9.2022 | 24.3.2024 | 100% | 185.39 | 0% | 0 | 100% | 185.39 | Building work completed. Procurement of plants and machineries being taken up by D.C. Champhai. | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | NEC
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Zomi cultural Centre and preservation of historical sites at Champhai | % | 478.69 458.43 (Revised) | 26.9.2022 | 7.2.2025 | 100% | 458.43 | 0% | 0 | 100% | 458.43 | Work completed NEC Revised approved sanctioned Rs. 478.69 lakh to Rs. 458.43 lakh and pull back Rs 20,25,356.00 | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | NEC
Sl no | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Biate Tea Tourism Circuit & Nature camp in Mizoram | % | 369.62 | 9.10.2023 | 31.03.2026 | 98.7% | 342.62 | 0.3% | 0 | 99% | 342.62 | Work in progress | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | NEC
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Establishing Mizo cultural heritage centre for protecting the historical and natural heritage of Mizo at Kawlri, Serchhip | % | 486.47 | 16.2.2024 | 16.12.2026 | 80% | 182.46 | 2% | 0 | 82% | 182.46 | Work in progress | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | NEC
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Auditorium at Bethel Veng Champhai | % | 1443.75 | 16.2.2024 | 17.12.2026 | 64% | 971.97 | 3% | 0 | 67% | 971.97 | Work in progress | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | NESIDS - OTRI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of 50 Bedded District Hospital Complex and Procurement of equipment at Khawzawl, Khawzawl District, Mizoram | % | 1775 | 11.6.2024 | 11.12.2026 | 80% | 991.13 | 1% | 0 | 81% | 991.13 | Work in progress | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | NESIDS-OTRI
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of 50 Bedded District Hospital Complex and Procurement of equipment at Saitual, Saitual District, Mizoram | % | 1696 | 10.6.2024 | 10.12.2026 | 47% | 757.05 | 1% | 0 | 48% | 757.05 | The local NGO's wanted to shift the layout of the hospital main building towards the backside and lowering of the courtyard which will involve additional fund. The matter is brought to Health Department and decision is awaited. Work for quarters only in progress. | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | NEC
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Upgradation of Sports Infrastructure of Ngopa Playground at Saitual District, Mizoram. | % | 394.15 | 15.3.2025 | 15.9.2027 | 100% | 347.76 | 0% | 0 | 100% | 347.76 | Work in progress | _
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | NEC
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Our Heritage, Our Treasure at Vangchhia Tourist Spot, Champhai, Mizoram | % | 115.76 | 19.7.2025 | 19.7.2026 | 54% | 30.19 | 10% | 0 | 64% | 30.19 | Work in progress | _
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | NESIDS
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Improvement/Upgradation of Operational/Non-operational facilities of Lengpui Airport, (Sh: Elevated road with connected components of Terminal Building). | % | 1959 | 30.9.2021 | 25.3.2025 | 100% | 1959 | 0% | 0 | 100% | 1959 | Work completed | Turnkey
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | CSS
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Tourist Lodge at Champhai | % | 328.73 | 9.12.2010 | 30.11.2020 |  |  |  |  | 100% | 300 | Taken over by the Department on Dt.3.8.2021 . LOC amounting to Rs. 30.00 lakh submitted for clearing liaibility. Hence, release of LOC awaited for financial closure.
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | CSS
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Polytechnic at Chhiahtlang | % | 800 | [8 empty] | Only approach road is executed. Out of fund received amount Rs. 300.00 lakhs balance amount of Rs. 196.34 lakhs is kept at D-III
| i) Approach road |  |  | 3.3.2016 | 2.8.2016 |  |  |  |  | 100% | 103.67
ii) Administrative & Academic Block
iii) Hostel Block
iv) Staff Quarter
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | CSS
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Hostel for S.T Girls at Champhai | % | 462.75 | 18.9.2023 | 31.12.2026 | 87.5% | 162.77 | 0% | 0 | 87.5% | 162.77 | Work temporarily halted due to fund problem since May 2025 | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | CSS
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | 10 - Bedded Integrated AYUSH Hospital at Keifang, Saitual District | % | 750 | 13.10.2023 | 7.10.2026 | 87% | 415.15 | 1% | 0 | 88% | 415.15 | Work in progress | PWD Form - 8 | Secured Advance Check leh angai
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | CSS
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Const of District Court Complex at Vengsang, Champhai. ( Sh: Main Building, phase- I) | % | 4915.35 | 17.10.2023 | 17.10.2026 | 80% | 1906.36 | 1% | 0 | 81% | 1906.36 | Work in progress (Due to an inadvertent clerical error, the financial progress in the previous month was mistakenly entered as 115.06 instead of 111.22. The corrected amount may be considered.) | PWD Form - 8
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | CSR
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of 100 Bedded District Hospital, Block A at Serchhip Mizoram under Powergrid CSR Initiative | % | 2100 |  |  | 31% | 0 | 0% | 0 | 31% | 0 | Revised DPR submitted to PGIL. Revised agreement to be signed with contractor after Revised DPR is approved by PGCIL. Only Supervision and Monitoring of work is under PWD. | -
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026
.. |  | Project Division - III
Source of Funding : |  | CSR
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Parking Area (Ground Floor and First Floor) of the ongoing Construction of 100 Bedded District Hospital, Block A at Serchhip. | % | 125.88 | 17.07.2026 | 17.07.2027 | 0% | 0 | 60% | 0 | 60% | 0 | Work in progress | Restricted Tender
`
Name of Division : |  | Project Division - III
Source of Funding : |  | CSS/ Fire & Emergency Services Department
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Fire Station Khawzawl | % | 194.38 | 03.07.2026 | 03.07.2027 | 0% | 0 | 0% | 0 | 0% | 0 | Work not started due to site problem. | Restricted Tender
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | CSS/ Fire & Emergency Services Department
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Fire Station Saitual | % | 193.46 | 01.04.2026 | 01.04.2028 | 4% | 0 | 14% | 34.86 | 18% | 34.86 | Work in progress | Restricted Tender
`
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026
Name of Division : |  | Project Division - III
Source of Funding : |  | Swadesh Darshan 2.0 (CSS)
Sl.No | Name of Work/Project | Unit | Approved Cost (Rs in lakh) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last month |  | Achievement of works during the month |  | Overall cummulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Conference Centre at Thingsulthliah, Mizoram | % | 9971 | 31.03.2026 | 31.03.2028 | 1% | 0 | 1% | 0 | 2% | 0 | Work in Progress | Restricted Tender
`
Sr.Executive Engineer, PWD., Project Division - III Aizawl, Mizoram

## Hnahthial
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026 UNDER HNAHTHIAL DIVISION ANNUAL PLAN(5054) DURING 2025 - 2026
Sl. No | Name of Scheme | Unit | Approved Cost (in lakh) | Date of Commencement | Target date of completion | Cummulative progress at the end of last Month |  | Achievement of Works during the Month |  | Overall Cummulative Achievement |  | Remarks | Mode of tender
| Name of Work/Project |  |  |  |  | Phy (%) | Fin (lakh) | Phy (%) | Fin (lakh) | Phy (%) | Fin (lakh)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Works under Annual Plan (5054) during 2025-2026 under PWD Hnahthial Division, Hnahthial
1 | Resurfacing of F.Zachhuma House to CL.Biaka House at S.Vanlaiphai | m | 15.07 | 2026-07-02 | 2026-07-05 | 100% | - | - |  | 100% | - | Completed | Open Tender
2 | Patch repair and seal coating of Hnahthial to Thingsai Road | m | 77.67 | 2026-07-02 | 2026-07-08 | 80% | - | 2% |  | 82% | - | In Progress | Open Tender
3 | Resurfacing of road from Leite to Rotlang 'E' | m | 109.62 | 03.04.2026 | 03.10.2026 | 25% | - | - | - | 25% | - | In Progress | Open Tender
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026 UNDER HNAHTHIAL DIVISION, ( NABARD )
Name of Work/Project |  |  | : | Construction of Galvanised Steel Truss Bridge over Mat River on Hnahthial to Haulawng Road via Zotui (Span 70.00m)
Name of Division |  |  | : | Hnahthial Division: Hnahthial
Date of Commencement |  |  | : | 1.11.2025
Target Date of Completion |  |  | : | 31.10.2027
Name of Contractor |  |  | : | Urban Infraprojects Private Limited AE-0310,1st Floor, Salt Lake, Sector-1 Kolkata - 700064
SI.No | Component of Works | As per Agreement |  |  | Achievement upto the previous month |  | Achievement during the month |  | Cumulative Achievement |  | Remarks | Mode of Tender
|  | Quantity (In lakh) | Unit | Item Amount (lakh) | Phy (%) | Fin (lakh) | Phy (%) | Fin (lakh) | Phy (%) | Fin (lakh)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
1 | Construction of Galvanised Steel Truss Bridge over Mat River on Hnahthial to Haulawng Road | 15,31.93 | Rm | 14,47.94 | 70% | 266.68 | 1% | 250 | 71% | 516.68 | In progress | Open Tender
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026 UNDER HNAHTHIAL DIVISION, ( SASCI )
Sl. No | Name of Work | Unit | Approved Cost Amount (in lakh) | Date of Commencement | Target date of completion | Cummulative progress at the end of the Month |  | Achievement of Works during the Month |  | Overall Cummulative Achievement |  | Remarks | Mode of Tender
[6 empty] | Phy (%) | Fin (lakh) | Phy (%) | Fin (lakh) | Phy (%) | Fin (lakh)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of PCC Flooring at Various locations viz. (I) Haulawng to Hmuntlang (ii) Melte to Khawiva (iii) Ramrikawn to Pangzawl (iv) Lena Stadium to New Maite. ( SH: Ramrikawn to Pangzawl ) | % | 58.56 | 2026-02-02 | 2027-02-02 | 80% | - | 1% | - | 81% | 32.79 | In Progress | Open Tender
2 | Construction of Drain along NH-54 and on different parts within Hnahthial Town, Hnahthial District | % | 240.39 | 2026-02-02 | 2027-02-02 | 85% | 90.47 | 4% | - | 89% | 90.47 | In Progress | Open Tender
ExecutiveEngineer, PWD
Hnahthial Division, Hnahthial.

## LLElectric
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026
FOR WORKS UNDER STATE PLAN FUND
Name of Division : PWD Electrical Division,Lunglei.
Source of funding : State funding | [11 empty] | Rs in Lakhs
Sl No | Name of works/Project | Unit | Approval Cost(Rs in lakh) | Date of Commencement | Target Date of comp- letion | Cumulative Progress at the end of last month |  | Achievement of works during the Month |  | Overall Cumulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy. | Fin. | Phy. | Fin. | Phy. | Fin.
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | 8443-108-PW Deposit-III
| a) I/E to DC Office at Siaha. |  | 47 |  |  | 90% | 0 | 5% | 44.6138 | 95% | 45 | I/E Works Completed S/c awaited | Departmental
2 | SASCI FUND ACCOUNT
| a) I/E to Gov't.Quarters(General pool)at Venglai, Lunglei.(Marcells's Quarters Site No 2,Type-III,2 Units) |  | 9.47 | Dt.29.5.26 | Dt.29.6.26 | 70% | 0 | 30% | 0 | 100% | 9.7 | Completed | Contractor
| b) I/E to Gov't.Quarters(General pool)at Venglai, Lunglei.(Marcells's Quarters Site No 1,Type-III,1 Unit) |  | 6.43 | Dt.29.5.26 | Dt.29.6.26 | 70% | 0 | 30% | 0 | 100% | 6.43 | Completed | Contractor
| c) I/E to Gov't.Quarters(General pool)at Venglai, Lunglei.(Ramnghaka's Quarters Site) Type-IV,Quarters 2- Units |  | 16.99 | Dt.29.5.26 | Dt.29.6.26 | 70% | 0 | 30% | 0 | 100% | 16.99 | Completed | Contractor
| d) I/E to Gov't.Quarters(General pool)at Venglai, Lunglei.(Zorini's Quarters Site) Type-III,Quarters 1-Block, 2-Units |  | 10.55 | Dt.29.5.26 | Dt.15.6.26 | 70% | 0 | 28% | 0 | 98% | 0 | I/Works Completed F&F Bill awaited | Contractor
| e) I/E to Gov't.Quarters(General pool)at Venglai, Lunglei.(Zautea's Quarters Site Type-IV,1-Unit) |  | 6.9 | Dt.29.5.26 | Dt.15.6.26 | 70% | 0 | 28% | 0 | 98% | 0 | I/Works Completed F&F Bill awaited | Contractor
| f) I/E to Gov't.Quarters(General pool)at Venglai, Lunglei.(Thapa's Quarters Site)Type-III Quarters,1 Block 2-Units |  | 10.55 | Dt.29.5.26 | Dt.15.6.26 | 70% | 0 | 28% | 0 | 98% | 0 | I/Works Completed F&F Bill awaited | Contractor
| g) I/E to Gov't.Quarters(General pool)at Venglai, Lunglei.(Quarters No-5 Site))Type-III Quarters 2-Units 1-Block. |  | 10.1 | Dt.29.5.26 | Dt.15.6.26 | 70% | 0 | 28% | 0 | 98% | 0 | I/Works Completed F&F Bill awaited | Contractor
| h) I/E to Gov't.Quarters(General pool)at Venglai, Lunglei.(Soil Quarters Site)Type-III Quarters,1-Units Type-IV Quarters 2-Units. |  | 17.57 | Dt.29.5.26 | Dt.15.6.26 | 70% | 0 | 28% | 0 | 98% | 0 | I/Works Completed F&F Bill awaited | Contractor
Sl No | Name of works/Project | Unit | Approval Cost(Rs in lakh) | Date of Commencement | Target Date of comp- letion | Cumulative Progress at the end of last month |  | Achievement of works during the Month |  | Overall Cumulative achievement |  | Remarks | Mode of Contract
[6 empty] | Phy. | Fin. | Phy. | Fin. | Phy. | Fin.
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
| i) I/E to Gov't.Quarters(General pool)at New Siaha.Near Additional DC Quarters,inside gate.(SH: Type-IV Quarters,1-Block,2- Units) |  | 17.742 lac |  |  | 0% | 0 | 0% | 0 | 0% | 0 | Estimate Submmitted T.S Accorded | Contractor
| j) I/E to Gov't.Quarters(General pool)at New Siaha.Near Additional DC Quarters,outside gate.(SH: Type-IV Quarters,1-Block,2- Units) |  | 17.70 lac |  |  | 0% | 0 | 0% | 0 | 0% | 0 | Estimate Submmitted T.S Accorded | Contractor
| c) I/E to Gov't.Quarters(General pool)at New Siaha.Near Additional DC quarters outside gate(SH: Type-III Quarters,1-Block,4- Units) |  | 20.426 lac |  |  | 0% | 0 | 0% | 0 | 0% | 0 | Estimate Submmitted T.S Accorded | Contractor
| k) I/E to Gov't.Quarters(General pool)at Meisavaih Site-I(SH: Type-III Quarters,1-Block,4- Units) |  | 20.528lac |  |  | 0% | 0 | 0% | 0 | 0% | 0 | Estimate Submmitted T.S Accorded | Contractor
| e) I/E to Gov't.Quarters(General pool)at Meisavaih Site-II (SH: Type-III Quarters,1-Block,4- Units) |  | 20.528lac |  |  | 0% | 0 | 0% | 0 | 0% | 0 | Estimate Submmitted T.S Accorded | Contractor
| l) I/E to SDO ( C) Quarter at Tipa.(SH: Type-IVQuarter,1-Block,1-Unit) |  | 6.81lac |  |  | 0% | 0 | 0% | 0 | 0% | 0 | Estimate Submmitted T.S Accorded | Contractor
| m) I/E to SDO ( C) Office at Tipa.Mizoram. |  | 5.51lac |  |  | 0% | 0 | 0% | 0 | 0% | 0 | Estimate Submmitted T.S Accorded | Contractor
| n) I/E to Improvemeat and Upgradation of District Prison.(SH: Administrative Building) |  | 12.144lac |  |  | 0% | 0 | 0% | 0 | 0% | 0 | Estimate Submmitted T.S Accorded | Contractor
| o) I/E to Improvemeat and Upgradation of District Prison.(SH: Type-III staff quarters)) |  | 3.011lac |  |  | 0% | 0 | 0% | 0 | 0% | 0 | Estimate Submmitted T.S Accorded | Contractor
FOR WORKS UNDER STATE PLAN FUND
Sl No | Name of works/Scheme | Estimated Amount | A/A or Not | Cumulative achievement as on March, 2016 |  | Target Date of comp- letion | Fund allocated during the year | Achievement during the Month |  | Cumulative achievement upto the end of the month during the year |  | Cumulative achievement since implementation of the project |  | Remarks
|  |  |  | Phy. | Fin. |  |  | Phy. | Fin. | Phy. | Fin. | Phy. | Fin.
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
2 | 4202 Co-On Education etc.
| b) Boys' Hostel for Govt. Lunglei College at Lunglei | 2.00 lacs | Yes | 20% |  |  | 2 | 20% |  | 40% |  | 40% |  | Completed
| c) Girls' Hostel for Govt. Lunglei College at Lunglei | 2.00 lacs | Yes | 20% |  |  | 2 | 20% |  | 40% |  | 40% |  | Completed
| d) I/E to Govt.Hnahthial College at Hnahthial | 10.56 lacs | Yes | 20% |  |  | 10.56 |  |  |  |  | 20% |  | On going works
| e) I/E to DIET Bldg at Saiha (Sangau Road) | 27.00 lacs | Yes | 20% |  |  | 27 |  |  | 40% |  | 40% |  | Completed
| f) I/E to DIET Bldg at Thingkah (Lawngtlai Dist.) | 27.00 lacs | Yes | 20% |  |  | 27 | 55% |  | 95% |  | 95% |  | Completed
| g) I/E to Indoor stadium at Chanmari, Lunglei | 15.00 lacs | Yes | Nil |  |  | 15 | 20% |  | 20% |  | 20% |  | On going works
| h) I/E to boys & girls Hostel for Govt.Saiha College bldg at Siaha | 2.00 lacs | Yes | 20% |  |  | 2 | 20% |  | 20% |  | 20% |  | On going works
| i) I/E to Infrastructure development of Lawngtlai College at Lawngtlai | 5.00 lacs | Yes | 20% |  |  | 5.00 lacs | 20% |  | 20% |  | 20% |  | On going works
3 | 4055 Co-On Police (P)
| d) I/E to Police Station at Vaseitlang | 8.00 lacs | Yes | Nil |  |  | 8 |  |  | 100% |  | 100% | 8.00 lacs | Completed
4 | 4408 Co-0n Food Storage and Warehousing
| a) I/E to Storage Godown at Kawlchaw | 3.00 lacs | Yes | Nil |  |  | 3 |  |  | 100% |  | 100% | 3.00 lacs | Completed
| b) I/E to Storage Godown at Vaseikai | 3.00 lacs | Yes | Nil |  |  | 3 |  |  | 100% |  | 100% | 3.00 lacs | Completed
| c) I/E Storage Godown at Hnahthial | 3.00 lacs | Yes | Nil |  |  | 3 | 5% |  | 100% |  | 100% | 3.00 lacs | Completed
| d) I/E Storage Godown at Sangau | 3.00 lacs | Yes | Nil |  |  | 3 | 5% |  | 100% |  | 100% | 3.00 lacs | Completed
| e) I/E Storage Godown at Lungsen | 3.00 lacs | Yes | Nil |  |  | 3 |  |  | 100% |  | 100% | 3.00 lacs | Completed
| f) I/E Storage Godown at Tlabung | 3.00 lacs | Yes | Nil |  |  | 3 |  |  | 100% |  | 100% | 3.00 lacs | Completed
5 | 4059 Co-On Public Works(P)
| a) I/E to Treasury Office at Saiha | 13.00 lacs | Yes | Nil |  |  | 13 |  |  | 100% |  | 100% | 13.00 lacs | Completed
6 | 8443-108-PW Deposit-III
| a) I/E to Govt Staff Qtrs (PWD), Type-II 4 units at Lunglei | 8.00 lacs | Yes | Nil |  |  | 8 | 10% |  | 100% |  | 100% | 8.00 lacs | Completed
| b) I/E to PHC at Haulawng | 10.00 lacs | Yes | Nil |  |  | 10 |  |  | 100% |  | 100% | 8.00 lacs | Completed
| c) I/E to PHC at Bunghmun | 10.00 lacs | Yes | Nil |  |  | 10 |  |  | 100% |  | 100% | 10.00 lacs | Completed
| d) I/E to PHC at Zobawk | 12.00 lacs | Yes | Nil |  |  | 12 | 40% |  | 90% |  | 90% |  | On going works
| e) I/E to PHC at Longpuighat | 11.00 lacs | Yes | Nil |  |  | 11 | 10% |  | 30% |  | 30% |  | On going works
7 | 4210 Co-On Medical
Construction of 100 Bedded Civil Hospital at Siaha
| (a) Power Distribution & Bed Lift | 114.83 lacs | Yes | 40% |  |  |  | 40% |  | 40% |  | 40% |  | On going works
(i) Power Distribution
(ii) SITC of 20 Passengers cum Stretcher Auto elevator
| (b) Solar Power | 146.00 lacs | Yes | 30% |  |  |  | 40% |  | 40% |  | 40% |  | On going works
(i) SITC of Solar Heating System (SHS)
(ii) SITC of 1X40 KWp SPV Power Plant
| (c) Fire fighting & VRF AC | 28.41 lacs | Yes | Nil |  |  |  | 10% |  | 10% |  | 10% |  | On going works
(i) SITC of fire detection/fighting system
(ii) SITC of 8 Tonnes (2+2+2+2) with 10 HP pure inverter out door unit with R410A Refrigerator AC VRF system
| (d) Internal Electrification main building | 61.40 lacs | Yes | Nil |  |  | 61.4 | 30% |  | 30% |  | 30% | 30 | On going works
| (e) I/E to Type-IV Quarter 3 units | 12.67 lacs | Yes | Nil |  |  |  | 10% |  | 10% |  | 10% |  | On going works
Executive Engineer, P.W.D.,
Electrical Division, Lunglei.

## PD - IV
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY, 2026
Name of Division |  | : Project Division - IV
Source of funding |  | : SASCI
Sl. No. | Name of work/project | Unit | Approved cost (Rs. in lakh) | Date of commencement | Target date of completion | Cummulative progress at the end of last month |  | Achievement of works during the month |  | Overall Cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin |  |  | COPY 5
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Working Women Hostel (50 Bedded) at Ramhlun Sports Complex, Aizawl. | % | 1400 | 2025-05-14 | 14-05-2026 31-12-2026 (1st EOT) | 42% | 357.3 | 3% | 92.22 | 45% | 449.52 | Work in progress. | Item rate.
2 | Construction of Revenue Staff Qtr. Complex at Aizawl. | % | 500
| a) Construction of Revenue Staff Quarters at Kawltheihuan, Aizawl | % | 298 | 2025-12-15 | 2026-12-15 | 30% | 0 | 5% | 50 | 35% | 50 | Work in progress. | Item rate.
| b) Construction of Revenue Staff Quarters at College Veng, Aizawl | % | 202 | 2026-01-21 | 2027-01-21 | 25% | 0 | 5% | 54.12 | 30% | 54.12 | Work in progress. | Item rate.
3 | Construction of Zamtea Multipurpose Hall at Sesawng | % | 492 | 2026-03-05 | 2027-03-05 | 6% | 0 | 4% | 0 | 10% | 0 | Foundation work started. | Item rate.
4 | Construction of Humam Development Centre at Lungleng | % | 853.63 | 2026-06-09 | 2027-06-09 | 5% | 0 | 4% | 0 | 9% | 0 | Foundation work started. | Item rate.
5 | Construction of Shelter at Hlimen Locality | % | 3.18 | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Estimate reframed observation queries from Financial Dept. To be submitted shortly | Item rate.
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY, 2026
Name of Division |  | : Project Division - IV
Source of funding |  | : SASCE
Sl. No. | Name of work/project | Unit | Approved cost (Rs. in lakh) | Date of commencement | Target date of completion | Cummulative progress at the end of last month |  | Achievement of works during the month |  | Overall Cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Multi Utility Centre at Zemabawk, Aizawl, Mizoram | % | 800 | 2022-12-19 | 2026-03-31 | 85% | 499.74 | 5% | 9.88 | 90% | 509.62 | Civil works completed. I/E works ongoing. | Item rate.
2 | Construction of Solid Waste Management Centre at Hualngohmun, Mizoram (Phase-I) | % | 1664 | 2023-04-07 | 15-04-2026 31-10-2026 (2nd EOT) | 68% | 979.69 | 2% | 0 | 70% | 979.69 | Work in progress. | Item rate.
3 | Restoration/renovation of DC Office at Aizawl. | % | 2000 | 2025-04-08 | 08-04-2026 08-02-2027 (1st EOT) | 32.5% | 339.96 | 2.5% | 200 | 35% | 539.96 | Work in progress. | Item rate.
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY, 2026
Name of Division |  | : Project Division - IV
Source of funding |  | : Article 275 (1)
Sl. No. | Name of work/project | Unit | Approved cost (Rs. in lakh) | Date of commencement | Target date of completion | Cummulative progress at the end of last month |  | Achievement of works during the month |  | Overall Cumulative achievement |  | Remarks | Mode of contract
[6 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Tribal Hostel at Suangpuilawn, Mizoram. | % | 320 | 2023-08-12 | 2025-07-22 | 76% | 139.9992 | 0% | 0 | 76% | 139.9992 | Work progress hindered due to irregularity in release of fund from Ministry. | Item rate.
2 | Construction of Multipurpose Community Hall at Darlawn, Mizoram. | % | 720 | 2023-08-12 | 2025-08-12 | 63% | 149.8635 | 0% | 0 | 63% | 149.8635 | Work progress hindered due to irregularity in release of fund from Ministry. | Item rate.
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY, 2026
Name of Division |  | : Project Division - IV
Source of funding |  | : NEDP
Sl. No. | Name of scheme | Unit | Approved cost (Rs. in lakh) | Date of commencement | Target date of completion | Cummulative progress at the end of last month |  | Achievement of works during the month |  | Overall Cumulative achievement |  | Remarks | Mode of contract
| Name of work/project |  |  |  |  | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Construction of Agriculture Growth Centre at Tuikual South, Aizawl. | % | 4555 | 2025-02-10 | 10-02-2026 10-01-2027 (1st EOT) | 34% | 1330.52 | 2% | 171.08 | 36% | 1501.6 | Work in progress. | Item rate.
Sr. Executive Engineer, PWD
Project Division - IV
Aizawl : Mizoram

## SERCHHIP DIV
PROGRESS REPORT OF NABARD WORKS FOR THE MONTH OF JULY 2026
Name of Work :CONSTRUCTION OF LINK ROAD AND LAND IMPROVEMENT AT ZAWLPUI IN THE STATE OF MIZORAM
NABARD
Date of Commencement: 3rd May, 2025 | [7 empty] | Division Serchhip Division
Agreement Amount: Rs. 9,63,30,359.97 | [7 empty] | Period for Completion 18 Months
Name of Contractor:-Evergreen Construction & culsuntancy Khatla, Aizawl
Sl. No. | Name of Work | Unit | As per Agreement/Deviation |  | Progress upto the end of last month |  |  |  | Cum.Prog.Upto the end of this month |  | Remarks
|  |  | Qty | Amount | Physical | Financial | Physical | Financial | Physical | Financial
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Land Improvement | M3 | 124539 | 21669786 | 124539 | 1313717.4 |  |  | 124539 | 1313717.4 | Work in Progress
| Restoration fo Rain cuts | Km | 10.837 | 3531843.57 | 10.837 | 2448695.47 |  |  | 10.837 | 2448695.47
2 | Compaction of Original Ground (Sub-grade) | Km | 10.837 | 1584396 | 10.837 | 1580595 |  |  | 10.837 | 1580595
3 | Granular Sub-Base | Km | 10.837 | 15311275.5 | 10.837 | 14834519.93 |  |  | 10.837 | 14834519.93
4 | Concrete Pavement | Km | 10.837 | 47880734 | 10.837 | 29657927.83 |  |  | 10.837 | 29657927.8282
5 | Earthen Shoulder | Km | 10.837 | 1765164.38 | 10.837 | 164536.96 |  |  | 10.837 | 164536.964
| 5 Years Maintenance |  |  | 4587160
| Total : |  |  | 96330359.45 |  | 49999992.59 |  |  |  | 49999992.5922
1 | Contincency |  |  | 2752296
| Quiality Control |  |  | 917432
| Over all Total |  |  | 100000087.45
Over all Physical Progress in Percentage=100%
PROGRESS REPORT OF NABARD WORKS FOR THE MONTH OF JULY, 2026
Name of Work :IMPROVEMENT OF SERCHHIP(CHAWMKAI) TO ZOTE SOUTH ROAD, SERCHHIP DISTRICT IN THE STATE OF MIZORAM
NABARD
Date of Commencement: 14th May, 2025 | [7 empty] | Division Serchhip Division
Agreement Amount: Rs. 21,80,92,941.13 | [7 empty] | Period for Completion 18 Months
Name of Contractor:-Huapzo Construction & consultancy Services, bawnkawn Shalom, Aizawl
Sl. No. | Name of Work | Unit | As per Agreement |  | Progress upto the end of last month |  | Progress during the month |  | Cum.Prog.Upto the end of this month |  | Remarks
|  |  | Qty | Amount | Physical | Financial | Physical | Financial | Physical | Financial
1 | 2 | 3 | 4 | 5 | 6 | 7 |  | 9 | 10 | 11 | 12
1 | Formation Cutting | Km | 14 | 22273648.36 | 14 | 22272972.35 |  |  | 14 | 22272972.35 | Work in Progress
2 | Compaction of Original Ground (Sub-grade) | Km | 14 | 4620000 | 14 | 4648958.85 |  |  | 14 | 4618958.85
3 | Granular Sub-Base | Km | 14 | 33446000 | 14 | 31055996.62 |  |  | 14 | 31055996.62
4 | WBM – II | Km | 6 | 8045730 |  |  |  |  | 0
5 | WBM – III | Km | 6 | 8197200 |  |  |  |  | 0
6 | Prime coat | Km | 6 | 2079000 |  |  |  |  | 0
7 | Tack coat | Km | 6 | 673200 |  |  |  |  | 0
8 | OGPC | Km | 6 | 6138000 |  |  |  |  | 0
9 | Seal Coat | Km | 6 | 2079000 |  |  |  |  | 0
10 | Concrete Pavement | Km | 8 | 48708000 | 7.5 | 22812871.5 |  |  | 7.5 | 22812871.5
12 | Surface Drain | Km | 14 | 13720000 | 6 |  | 8 | 13700000 | 14 | 13700000
13 | Protection Wall | Rm | 200 | 11297837 | 180 |  |  | 11024011.35 | 180 | 11024011.35
14 | Lined Side drain | Rm | 6762 | 17484569.315 | 450 |  |  |  | 450 |  |  |  | 6762 | 2585.7097 | 17484569.315
15 | Culverts, H/P, Minor Bridge | Nos | 28 | 27725827.65 | 18 |  |  | 5795689.65 | 18 | 5795689.65 |  |  | 10 | 990208.1304 | 9902081.3036
16 | Road Furnitures | Nos | 14 | 1219550 | 0 |  |  |  | 0 | [5 empty] | 27386650.6186
| 5 Years Maintenance |  |  | 10385378.14 | 0
| Total : |  |  | 218092940.46 |  | 80760799.32 |  |  |  | 80760799.32 |  | ,
| Contincency |  |  | 6231227 |  | 303700 |  | 1495799 |  | 1799499
| Quiality Control |  |  | 2077076 | [9 empty] | 101.4%
| Over all Total |  |  | 226401243.46 |  | 81064499.32 |  | 32015500 |  | 193840798.64
| Over all Physical Progress in Percentage = |  |  | 51.29% | [9 empty] | 221227449.2586
PROGRESS REPORT OF NABARD WORKS FOR THE MONTH OF JULY, 2026
Name of Work :WIDENING & IMPROVEMENT OF APPROACH ROAD TO PARAGLIDING GROUND AT SERCHHIP
NABARD
Date of Commencement: 8h May, 2025 | [7 empty] | Division Serchhip Division
Agreement Amount: Rs. 3,45,63,310.77 | [7 empty] | Period for Completion 18 Months
Name of Contractor:-Evergreen Construction & culsuntancy Khatla, Aizawl
Sl. No. | Name of Work | Unit | As per Agreement |  | Progress upto the end of last month |  | Progress during the month |  | Cum.Prog.Upto the end of this month |  | Remarks
|  |  | Qty | Amount | Physical | Financial | Physical | Financial | Physical | Financial
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Widening | Km | 4.7 | 1588390.58 | 4.7 | 1433216.78 |  |  | 4.7 | 1433216.78 | Work in Progress
2 | Compaction of Original Ground (Sub-grade) | Km | 4.7 | 123375 | 4.7 | 123375 |  |  | 4.7 | 123375
3 | Granular Sub-Base | Km | 3.78 | 6274422 | 3.78 | 7472934.45 |  |  | 3.78 | 7472934.45
10 | Concrete Pavement | Km | 4.7 | 24350700 | 4.7 | 8909378 |  |  | 4.7 | 8909378
16 | Road Furnitures | Nos | 900 | 580551.25 | 900 |  |  |  | 900
| 5 Years Maintenance |  |  | 1645871.94
| Total : |  |  | 34563310.77 |  | 17938904.23 |  |  |  | 17938904.23
Contingency
Quiality Control
Over all Total
Overall physical Progress in % = 100%
PROGRESS REPORT OF NABARD WORKS FOR THE MONTH OF JULY , 2026
Name of Work :IMPROVEMENT OF KIKAWN TO HMARVENG, SERCHHIP
NABARD
Date of Commencement: 14th May, 2025 | [7 empty] | Division Serchhip Division
Agreement Amount: Rs. 15,51,98,719.23 | [7 empty] | 8
Name of Contractor:-Studio Hamlet, Champhai Vengthlang, Champhai
Sl. No. | Name of Work | Unit | As per Agreement |  | Progress upto the end of last month |  | Progress during the month |  | Cum.Prog.Upto the end of this month |  | Remarks
|  |  | Qty | Amount | Physical | Financial | Physical | Financial | Physical | Financial
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Formation Cutting | Km | 6 | 52027848.88 | 6 | 499.17 |  |  | 6 | 499.17 | Work in Progress
| Compaction of Original Ground (Sub-grade) | Km | 6 | 805500 | 5.5 | 5.95 |  |  | 5.5 | 5.95
| Embankment | Km | 4 | 3420000 | 4 | 25.82 |  |  | 4 | 25.82
2 | Granular Sub-Base | Km | 6 | 14231250 | 3 | 72.15 |  |  | 3 | 72.15
4 | WBM – I | Km | 6 | 7290000 | 3 | 36.93 |  |  | 3 | 36.93
5 | WBM – II | Km | 6 | 7290000 | 3 | 36.93 |  |  | 3 | 36.93
6 | Prime coat | Km | 6 | 2160000
7 | Tack coat | Km | 6 | 1170000
8 | OGPC | Km | 6 | 6120000
| Seal Coat | Km | 6 | 1980000
9 | Earthen shoulder | Km | 6 | 1890000
| Surface Drain | Km | 6 | 900000 | 2 |  |  |  | 2
10 | Protection Wall | Rm | 1605 | 30932668.8 | 239 |  |  |  | 239
12 | Lined Side drain | Rm | 4666.85 | 11891072.7
13 | H/P Culvert NP3 | Nos | 12 | 5699963.25 | 2 |  |  |  | 2
|  | 5 Years Maintenance |  | 7390415.2
Total: |  |  |  | 155198718.83 |  | 676.95 |  |  |  | 676.95
| Contincency |  |  |  | 1.21 | 6.2 |  |  |  | 6.2
Quiality Control
Over all Total
Over all Physical Progress in Percentage =51%
MONTHLY PROGRESS REPORT OF SASCI FOR THE MONTH OF JULY, 2026
Name of Work :RESURFACING OF OLD NATIONAL HIGHWAY ROAD AT SERCHHIP UNDER SASCI PART-V,2025-2026
SASCI PART-V
Date of Commencement: 27th March, 2026 | [7 empty] | Division Serchhip Division
Agreement Amount: Rs. 9,61,55,482.00 | [7 empty] | Period for Completion 12 Months
Name of Contractor:-Urban Infraprojects Pvt.Ltd.
Sl. No. | Name of Work | Unit | As per Agreement |  | Progress upto the end of last month |  | Progress during the month |  | Cum.Prog.Upto the end of this month |  | Remarks
|  |  | Qty | Amount | Physical | Financial | Physical | Financial | Physical | Financial
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Landslide Clearance in soil | cum | 3310 | 873840 | 3310 |  |  | - | 3310 |  | Work in Progress
2 | Tack coat | Km | 10 | 1797210
3 | Bituminous Concrete | Km | 10 | 63030000
4 | Formation cutting | Rm | 100 | 209161.16 | 100 |  |  |  | 100
5 | Compaction of Original Ground (Sub-grade) | Rm | 450 | 20101.5 | 450 |  |  |  | 450
6 | Granular Sub-Base | Rm | 450 | 393750 | 450 |  |  |  | 450
7 | WBM – I | Rm | 450 | 371250 | 450 |  |  |  | 450
8 | DBM | Rm | 450 | 1147500
9 | Prime coat | Rm | 450 | 180000
10 | Tack coat | Rm | 450 | 90000
11 | Bituminous Concrete | Rm | 450 | 491400
10 | Lined Side drain | Rm | 5000 | 13990170.19 | 3000 |  | 200 |  | 3200
11 | Box Culvert | No. | 1 | 2271099.68
12 | Retaining Wall | Rm | 100 | 8300000.02
13 | Breast Wall | Rm | 65 | 2990000.05 | 20 |  |  |  | 20
| Total : |  |  | 96155482.6
Overall Physical Progress in % |  | = | 39.65%
MONTHLY PROGRESS REPORT OF SASCI FOR THE MONTH OF JULY, 2026
Name of Work :IMPROVEMENT OF THENTLANG TO LUNGPHO ROAD(BUANHMUNKAWN TO RAMRIKAWN)
SASCI PART-VII B
Date of Commencement: 7th July, 2026 | [7 empty] | Division Serchhip Division
Agreement Amount: Rs. 20,19,26,820.95 | [7 empty] | Period for Completion 12 Months
Name of Contractor:-Urban Infraprojects Pvt.Ltd.
Sl. No. | Name of Work | Unit | As per Agreement |  | Progress upto the end of last month |  | Progress during the month |  | Cum.Prog.Upto the end of this month |  | Remarks
|  |  | Qty | Amount | Physical | Financial | Physical | Financial | Physical | Financial
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Clearing & Grubbing | Hec | 4 | 575708 | [6 empty] | Material collection in progress
2 | Formation Cutting | Km | 10 | 48571896
3 | Earthen shoulder | Km | 10 | 3056361
4 | Granular Sub-Base | Km | 10 | 24580875
5 | WBM – I | Km | 10 | 30244500
6 | WBM – II | Km | 10 | 34209450
7 | Prime coat | Km | 10 | 5346000
8 | Tack coat | Km | 10 | 1386000
9 | OGPC | Km | 10 | 12705000
10 | Seal Coat | Km | 10 | 5412000
11 | Unlined Side Drain | Rm | 5000 | 632043
10 | H/P Culvert NP3 | No. | 10 | 7293055.95
11 | Retaining Wall | Rm | 100 | 5617042
12 | Lined Side drain | Rm | 7000 | 22296890
| Total : |  |  | 201926820.95
Overall Physical Progress in % |  | = | 0%
PROGRESS REPORT OF ANNUAL PLAN (UNTIED FUND) FOR THE MONTH OF JULY, 2026
Name of Work :BLACKTOPPING OF KHAWTETLANG TO BYPASS ROAD
ANNUAL PLAN (UNTIED FUND)
Date of Commencement: 26th March, 2026 | [7 empty] | Division Serchhip Division
Agreement Amount: Rs. 33,07,507.47 | [7 empty] | Period for Completion 3 Months
Name of Contractor:-Benjamin K.Zothanliana
Sl. No. | Name of Work | Unit | As per Agreement |  | Progress upto the end of last month |  | Progress during the month |  | Cum.Prog.Upto the end of this month |  | Remarks
|  |  | Qty | Amount | Physical | Financial | Physical | Financial | Physical | Financial
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Granular Sub-Base | Km | 0.46 | 1216138.85 | 0.46 |  |  | 1216138.85 | 0.46 | 1216138.85 | Completed
2 | WBM – I | Km | 0.46 | 637190.51 | 0.46 |  |  | 637190.51 | 0.46 | 637190.51
3 | WBM – II | Km | 0.46 | 642738.11 | 0.46 |  |  | 642738.11 | 0.46 | 642738.11
4 | Prime coat | Km | 0.46 | 129720 | 0.46 |  |  | 129720 | 0.46 | 129720
5 | Tack coat | Km | 0.46 | 77280 | 0.46 |  |  | 77280 | 0.46 | 77280
6 | OGPC | Km | 0.46 | 438840 | 0.46 |  |  | 438840 | 0.46 | 438840
7 | Seal Coat | Km | 0.46 | 165600 | 0.46 |  |  | 165600 | 0.46 | 165600
| Total : |  |  | 3307507.47 |  |  |  | 3307507.47 |  | 3307507.47
Overall Physical Progress in % |  | = | 0%
PROGRESS REPORT OF ANNUAL PLAN (UNTIED FUND) FOR THE MONTH OF JULY, 2026
Name of Work :APPROACH ROAD TO CIRCUIT HOUSE AND COURTYARD AT KHAWTETLANG SERCHHIP
ANNUAL PLAN (UNTIED FUND)
Date of Commencement: 26th March, 2026 | [7 empty] | Division Serchhip Division
Agreement Amount: Rs. 52,00,674.41 | [7 empty] | Period for Completion 18 Months
Name of Contractor:-Benjamin K.Zothanliana
Sl. No. | Name of Work | Unit | As per Agreement |  | Progress upto the end of last month |  | Progress during the month |  | Cum.Prog.Upto the end of this month |  | Remarks
|  |  | Qty | Amount | Physical | Financial | Physical | Financial | Physical | Financial
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Formation Cutting | Km | 0.66 | 1267204.7 | 0.66 |  |  | - | 0.66 | 0 | Completed
2 | Compaction of Original Ground (Sub-grade) | Km | 0.2 | 9088.75 | 0.2 |  |  |  | 0.2
3 | Earthen shoulder | Km | 0.2 | 66348.9 | 0.2 |  |  |  | 0.2
4 | Granular Sub-Base | Km | 0.2 | 491672.5 | 0.2 |  |  |  | 0.2
5 | WBM – I | Km | 0.2 | 654161.34 | 0.2 |  |  |  | 0.2
6 | WBM – II | Km | 0.2 | 642242.92 | 0.2 |  |  |  | 0.2
7 | Prime coat | Km | 0.2 | 160568.4 | 0.2 |  |  |  | 0.2
8 | Tack coat | Km | 0.2 | 52403.5 | 0.2 |  |  |  | 0.2
9 | OGPC | Km | 0.2 | 481816.75 | 0.2 |  |  |  | 0.2
10 | Seal Coat | Km | 0.2 | 165685.25 | 0.2 |  |  |  | 0.2
11 | Lined side Drain | Km | 0.2 | 479844 | 0.2 |  |  |  | 0.2
12 | Retaining Wall | Rm | 20 | 729637.4 | 20 |  |  |  | 20
| Total : |  |  | 5200674.41 | [5 empty] | 0
Overall Physical Progress in % |  | = | 0%
PROGRESS REPORT OF ANNUAL PLAN (UNTIED FUND) FOR THE MONTH OF JULY, 2026
Name of Work :CONSTRUCTION OF HOSITAL BYPASS ROAD
ANNUAL PLAN (UNTIED FUND)
Date of Commencement: 25th May, 2026 | [7 empty] | Division Serchhip Division
Agreement Amount: Rs. 88,73,037.57 | [7 empty] | Period for Completion 18 Months
Name of Contractor:-Lalbiakdika Sailo
Sl. No. | Name of Work | Unit | As per Agreement |  | Progress upto the end of last month |  | Progress during the month |  | Cum.Prog.Upto the end of this month |  | Remarks
|  |  | Qty | Amount | Physical | Financial | Physical | Financial | Physical | Financial
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Formation Cutting | Rm | 40 | 51005.1 | [6 empty] | Work could not be started due to monsoon rainfall Material collection in progress
2 | Compaction of Original Ground (Sub-grade) | Rm | 40 | 6688
3 | Embankment | Rm | 160 | 944240
4 | Earthen shoulder | Rm | 40 | 25389
5 | Granular Sub-Base | Rm | 160 | 453816
6 | WBM – I | Rm | 160 | 204840
7 | WBM – II | Rm | 160 | 201456
8 | Prime coat | Rm | 160 | 45600
9 | Tack coat | Rm | 160 | 29760
10 | OGPC | Rm | 160 | 136800
11 | Seal Coat | Rm | 160 | 47040
12 | Surface Drains | Rm | 160 | 22720
13 | Lined side Drain | Rm | 160 | 425930.4
14 | Retaining Wall | Rm | 40 | 2727245.58
15 | Breast Wall | Rm | 72 | 3550507.49
| Total : |  |  | 8873037.57
Overall Physical Progress in % |  | = | 0%
PROGRESS REPORT OF ANNUAL PLAN (UNTIED FUND) FOR THE MONTH OF JULY, 2026
Name of Work :RESTORATION OF FORMATION COLLAPSED AT VETY AR FARM TO ASSAM RIFLES GATE-III AT SERCHHIP
ANNUAL PLAN (UNTIED FUND)
Date of Commencement: 25th May, 2026 | [7 empty] | Division Serchhip Division
Agreement Amount: Rs. 88,73,037.57 | [7 empty] | Period for Completion 18 Months
Name of Contractor:-Benjamin K.Zothanliana
Sl. No. | Name of Work | Unit | As per Agreement |  | Progress upto the end of last month |  | Progress during the month |  | Cum.Prog.Upto the end of this month |  | Remarks
|  |  | Qty | Amount | Physical | Financial | Physical | Financial | Physical | Financial
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Gabion Wall | Rm | 40 | 4315082.54 | 40 |  |  | - | 40 |  | Work completed
2 | Embankment | Rm | 40 | 715440 | 40 |  |  | - | 40
3 | Granular Sub-Base | Rm | 40 | 117057.33 | 40 |  |  |  | 40
4 | WBM – I | Rm | 40 | 80779.34 | 40 |  |  |  | 40
5 | WBM – II | Rm | 40 | 79792.34 | 40 |  |  |  | 40
6 | Prime coat | Rm | 40 | 39909.8 | 40 |  |  |  | 40
7 | Tack coat | Rm | 40 | 35291.2 | 40 |  |  |  | 40
8 | OGPC | Rm | 40 | 66509.8 | 40 |  |  |  | 40
9 | Seal Coat | Rm | 40 | 40329.8 | 40 |  |  |  | 40
10 | Lined side Drain | Km | 40 | 1059910 | 40 |  |  |  | 40
11 | Breast Wall | Rm | 40 | 776685.22 | 40 |  |  |  | 40
12 | Retaining Wall | Rm | 12 | 1080882.84 | 12 |  |  |  | 12
| Total : |  |  | 8407670.19 | [5 empty] | 0
Overall Physical Progress in % |  | = | 0%
PROGRESS REPORT OF ANNUAL PLAN (5054) FOR THE MONTH OF JULY, 2026
Name of Work :RESURFACING OF CHHINGCHHIP TO THENTLANG ROAD
ANNUAL PLAN (5054)
Date of Commencement: 2th July, 2026 | [7 empty] | Division Serchhip Division
Agreement Amount: Rs. 1,85,80,816.07 | [7 empty] | Period for Completion 12 Months
Name of Contractor:-Ngurthanmawia Sailo
Sl. No. | Name of Work | Unit | As per Agreement |  | Progress upto the end of last month |  | Progress during the month |  | Cum.Prog.Upto the end of this month |  | Remarks
|  |  | Qty | Amount | Physical | Financial | Physical | Financial | Physical | Financial
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Clearing & Grubbing | Km | 10 | 55232.6 | [6 empty] | Work in progress
2 | Hill side drain clearance | Km | 8 | 648000 |  |  | 1 |  | 1
3 | Filling potholes with WBM | cum | 1020.15 | 509327.07
4 | Prime coat | Km | 9.8 | 2942940
5 | Tack coat | Km | 9.8 | 1131900
6 | OGPC | Km | 9.8 | 9555176.4
7 | Seal Coat | Km | 9.8 | 3738240
| Total : |  |  | 18580816.07
Overall Physical Progress in % |  | = | 0%
Sr Executive Engineer, PWD,
Serchhip Division:Serchhip

## SAITUAL DIV
NAME OF DIVISION : PWD Saitual Division
MONTHLY PROGRESS FOR THE MONTH OF : JULY 2026
[6 empty] | Physical in % |  |  |  | Financial is Rs in lakh
Sl. No | Name of Scheme | Unit | Approved Cost (in lakhs) | Date of Commencement | Target date of Completion | Cummulative Progress at the end of last Month |  | Achievement of works during the month |  | Overall Cumulative achievement |  | Remarks | Mode of Tender
| Name of Work/ Project |  |  |  |  | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
NESIDS
1 | Improvement & Upgradation of Daido to Vawngkawt- Buangpuilawn (Manipur) Road |  | 2404 | 14.03.2024 | 14.09.2025 | 100% | 1703.53 |  |  | 100% | 1703.53 | Security Deposit amounting to Rs. 0.93 Cr. Is lying in CNA Account | Open Tender
SASCI-II
1 | Improvement of Khawlek - Ratu Road (Length = 6Km) |  | 130 | 05.10.23 | 05.10.24 | 100% | 126.14 |  |  | 100% | 126.14 |  | Restricted Tender
2 | Widening and reconstruction of culverts on 3rd Road from Sedaikawn to PWD Kawn, Saitual (Length = 2.220Kms) |  | 137.52 | 05.10.23 | 05.10.24 | 100% | 137.52 |  |  | 100% | 137.52 |  | Restricted Tender
3 | Rigid pavement of Sakeibangla to ZMC via Thingsulthliah Road Thingsulthliah, PCC Pavement = 3.00km, Side drain = 2000m,R/Wall = 10m, Culvert = 2 Nos |  | 55.78 | 05.10.23 | 05.10.24 | 100% | 55.78 |  |  | 100% | 55.78 |  | Restricted Tender
4 | Pothole & Patch repair on Saitual to Phullen Road. ( 2.00 km ) |  | 15.5 | 05.10.23 | 05.10.24 | 100% | 15.5 |  |  | 100% | 15.5
SASCI & SASCI-II
1 | Restoration of damages due to cyclone remal under Khawzawl, Saitual & Serchhip Division (Saitual Division) |  | 165.25 | 16.06.2025 | 16.01.2026 | 100% | 59.76 |  |  | 100% | 59.76 |  | Restricted Tender | 21.53
2 | Restoration of damages due to cyclone remal under saitual division PART-II |  | 598.92 | 16.06.2025 | 16.01.2026 | 100% | 480.88 |  | 115.38 | 100% | 596.26 |  | Restricted Tender | 12.64
SASCI-V
1 | Extension of Saitual Town Via Khiangpuizawl under part V |  | 459 | 23.06.2025 | 23.06.2026 | 91.53% | 284.1388 | 6% |  | 97.53% | 284.1388 |  | Restricted Tender
SEDP
1 | Construction of Khanpui - Tualbung Road Phase-II |  | 1576.01 | 15.01.20 | 15.06.22 | 100% | 1575.73 |  |  | 100% | 1575.73
Executive Engineer, PWD.,
Saitual Division, Saitual.

## SIAHA DIV
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY 2026
Name of Division : PWD Siaha Division
Sl.No. | Name of Scheme | Unit | Approved Cost (in lakhs) | Date of Commencement | Target date of Completion | Commulative Progress at the end of last Month |  | Achievement of work during the month |  | Overall Cummulative achievement |  | Remarks | Mode of Tender
| Name of Work/Project |  |  |  |  | Phy | Fin | Phy | Fin | Phy | Fin |  |  | 0.1278
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
A | NABARD
Work under NABARD
1 | Up-gradation of Laki to Vahai Road From Ch. 0.00 km to Ch. 15.56 km | Km | 2163.43 | 28.06.2024 | 27.06.2026 | 100% | 1262.75 |  | 578.68 | 100% | 1841.43 | Work physically Completed | Item rate Contract | 0.13% | 0%
#REF!
B | NEC
Work under NEC
C | PMGSY
Work under PMGSY
D | SEDP
Work under SEDP
E | CSS
Work under CSS
F | MoRTH
Work under MoRTH
G (a) | 5054: (2024-2025)
1 | Annual Plan 2024 - 2025 Construction of Bailey Bridge (TDR) 170 ft span over R.Tuisumpui | No. | 250 | 01.10.2025 | 23.02.2026 | 100% | 250 |  |  | 100% | 250 | Work completed | Item rate Contract
G (b) | 5054: (2025-2026)
1 | Pothole Filling and resurfacing of Approach Road to Helipad Via DC Bungalow road | Km | 4.42 | 20.11.2025 | 21.01.2026 | 100% | 4.42 |  |  | 100% | 4.42 | Work completed | Item rate Contract
2 | Pothole filling and resurfacing of DC Bungalow Court Yard) | Km | 0.78 | 20.11.2025 | 21.01.2026 | 100% | 0.78 |  |  | 100% | 0.78 | Work completed | Item rate Contract
3 | Widening of pavement at selected locations on Circuit House to Bazar Traffic point road via Civil Hospital | Km | 19.24 | 20.11.2025 | 21.03.2026 | 100% | 19.24 |  |  | 100% | 19.24 | Work completed | Item rate Contract
4 | Construction of link drain at Tuisumpui Bridge site to prevent erosion of abutment foundation | No. | 5.98 | 20.11.2025 | 21.02.2026 | 100% | 5.98 |  |  | 100% | 5.98 | Work completed | Item rate Contract
5 | Pothole filling, Patch Repair & Resurfacing of BRTF Road to Suakkunga Road (Police Outpost - Suakkunga Road) at Bualpui NG (0.000 - 1.200 kmp) | Km | 27.13 | 20.11.2025 | 21.03.2026 | 100% | 27.13 |  |  | 100% | 27.13 | Work completed | Item rate Contract |  |  |  | 1.3.1980
6 | Pothole filling, Patch Repair & Resurfacing of Approach road to PHC Chhuarlung (0.000 - 0.370) km | Km | 7.31 | 20.11.2025 | 21.02.2026 | [6 empty] | Change of Work approval awaited | Item rate Contract
7 | Restoration of RCC Slab Culvert on Maisa-Lawngban Road at Ch.2.80 km | No. | 6.88 | 20.11.2025 | 21.02.2026 | 100% | 6.88 |  |  | 100% | 6.88 | Work completed | Item rate Contract
8 | Construction of Lined Side Drain on Tipa 'V' - Tipa 'L' Road (Tipa Lal Veng Peng Thuam - Waiting Shed on NH-02 at Tipa 'V') | Rm | 6.16 | 20.11.2025 | 21.02.2026 | 100% | 6.16 |  |  | 100% | 6.16 | Work completed | Item rate Contract
9 | Restoration of RCC Slab Culvert on Phura - Lungpuk Road at Ch. 15.80 km | No. | 5.72 | 20.11.2025 | 21.02.2026 | 100% | 5.72 |  |  | 100% | 5.72 | Work completed | Item rate Contract
| Total= |  | 83.62
G (c) | 5054: ROAD & BRIDGE UNTIED
1 | Pothole filling, Patch Repair & Resurfacing of Tlangpui - Niawhtlang Road (0.000 - 14.000 kmp) Phase - II | Km | 28.3 | 05.04.2026 | 25.06.2026 | 10% |  |  |  | 10% | 0 | Work in progress | Item rate Contract
2 | Construction of Gabion Wall and Hume pipe Culvert at Tuisumpui Bridge Site for Prevention of erosion). | No | 20 | 25.03.2026 | 25.06.2026 | 80% |  | 20% |  | 100% | 0 | Work in progress | Item rate Contract
3 | Resurfacing of AOC College Veng to Siaha Tlangkawn Road) | Km | 40 | 25.03.2026 | 25.06.2026 | 10% |  |  |  | 10% | 0 | Work in progress | Item rate Contract
H | CRF | [13 empty] | Withh = | 5.74
a) | Construction of Road from Chakhei to Siasi road (Length = 20 km) under CRF: Group-A (SH: FC & Pavement Works) | Km | 4982.15 | 08.07.19 | 20.12.2024 | 100% | 3237.07 |  |  | 100% | 3237.07 | Work completed | Item rate Contract |  | CC = | 29.2685 | 21.7265 | 2.6723 | 24.3989
b) | Construction of Road from Chakhei to Siasi road (Length = 20 km) under CRF: Group-B (SH: Permanent Works) | Km |  | 08.07.19 | 20.12.2024 | 100% | 1001.91 |  |  | 100% | 1001.91 | Work completed | Item rate Contract |  | QC = | 3.6 | 7.5419 | 0.92765 | 8.4695
I | 3054 | [14 empty] | 32.8685 |  |  | 32.8684
Work under Annual Maintenance Action Plan (3054) During 2025-26 under PWD Siaha Division
1 | Maintenance and Improvement of Approach road to PHC with PCC at Sangau | Km | 14.53 | 18.08.2025 | 31.03.2026 | 100% | 14.53 |  |  | 100% | 14.53 | Work completed | Departmental
2 | Construction of Retaining Wall on Tlangpui - Niawhtlang Road (0.000 - 14.000) kmp at Ch. 7.500 km | Rm | 6.66 | 07.07.2025 | 08.09.2025 | 100% | 6.66 |  |  | 100% | 6.66 | Work completed | Departmental
3 | Pothole filling of Meisatla forest check Gate to NH54B Tawngtaina Part-II | Km | 14.72 | 19.3.2026 | 31.3.2026 |  | 14.72 |  |  | 100% | 14.72 | Work completed | Departmental
4 | Resurfacing of Approach road to GHSS Complex at New Siaha | Km | 1.45 | 29.1.2026 | 30.1.2026 |  | 1.45 |  |  | 100% | 1.45 | Work completed | Departmental
5 | Pothole filling & Resurfacing of Er.VL khuma Residence to Council Veng via Council Veng Hall road | Km | 19.08 | 21.2.2026 | 17.3.2026 | 100% | 19.08 |  |  | 100% | 19.08 | Work completed | Departmental
6 | Pothole filling, Patch repair & Resurfacing of Bualpui Bazar - PWD Complex at Bualpui 'NG' Phase I | Km | 6.23 | 19.01.2026 | 05.02.2026 | 100% | 6.23 |  |  | 100% | 6.23 | Work completed | Departmental
7 | Pothole filling, Patch repair & Resurfacing of Chheihlu - Chakhang Road from Ch.1.000 km to Ch.2.000 km | Km | 10.63 | 16.2.2026 | 31.3.2026 | 100% | 10.63 |  |  | 100% | 10.63 | Work completed | Departmental
8 | Strengthening of Chheihlu - Chakhang road from Ch.3.00km to Ch.5.00km. | Km | 10.68 | 16.02.2026 | 31.03.2026 | 100% | 10.68 |  |  | 100% | 10.68 | Work completed | Departmental
9 | Reconstruction of Damaged slab Culvert Type -I on Siachangkawn - Vawmbuk road (0.000 - 12.250) km | No. | 3.49 | 19.1.2026 | 6.2.2026 | 100% | 3.49 |  |  | 100% | 3.49 | Work completed | Departmental
10 | Repair of RCC Slab Culvert on Phura - Lungpuk road at Ch.16.300 km | Km | 5.57 | 24.02.2026 | 14.3.2026 | 100% | 5.57 |  |  | 100% | 5.57 | Work completed | Departmental
11 | Construction of Approach road to Kaochao East IB With PCC Pavement | Km | 25 | 27.1.2026 | 31.03.2026 | 100% | 25 |  |  | 100% | 25 | Work completed | Departmental
| Total |  | 118.04
Executive Engineer, PWD
Siaha Division

## TLABUNG DIV
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY /2026
NAME OF ROAD : Improvement of Chawngte - Borapansury Road (0.000-30.00)KMP
Name of Division : Tlabung Division
Source of Funding : NABARD
No.R/TB-23/NABARD/EE(T)/ 68
Sanction Amount : Rs. 4381.00 Lakh
Sl. No | Name of Work/Project | Unit | Approved Cost (in Lakh) |  | Date of Commencement | Target Dt. Of Completion | Cummulative progress at the end of last mont |  | Achievement of works during the month |  | Overall Cummulative achievement |  | Remarks | Mode of Contract
|  |  | Qnty. | Cost |  |  | Phy | Fin | Phy. | Fin | Phy. | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Sub-grade preparation | Km | 30 | 76.73 | Dt.15.march.2023 | Dt.15.march.2025 | 30 | 1874.94 |  |  | 30 | 1874.94 | Extension granted upto Dt.13.07.2026 | Item Rate | 100
2 | GSB | Submission of Monthly Progress Report of Works under NABARD Scheme. | 20 | 711.27 |  |  | 20 |  |  |  | 20 |  |  |  | 100
3 | ANT (Soil stabilisation) | Km | 10 | 241.45 | [10 empty] | 0
4 | Panelled Concrete | km | 30 | 2298.83 |  |  | 11.5 |  | 0.5 |  | 12 |  |  |  | 40
5 | Eathen shoulder | Km | 30 | 213.39 |  |  | 10.5 |  |  |  | 10.5 |  |  |  | 35
6 | PROTECTION WORKS : | Rm | 146.5 | 99.26 |  |  | 146.5 |  |  |  | 146.5 |  |  |  | 100
7 | HP culvert | No | 15 | 94.09 |  |  | 14 |  |  |  | 14 |  |  |  | 93.3333
8 | Unline Side Drain | km | 23 | 91.13 |  |  | 20 |  |  |  | 20 |  |  |  | 86.9565
9 | Lined Side Drain | Rm | 2475 | 58.58 |  |  | 150 |  |  |  | 150 |  |  |  | 6.0606
10 | Tick Shape Side Drain | Rm | 4515 | 100.68 |  |  | 1600 |  |  |  | 1600 |  |  |  | 35.4374
11 | i) 5th Kilometre Stone | No | 6 | 0.5404 | [10 empty] | 0 |  | 1600
12 | ii) Ordinary Kilometre Stone | No | 25 | 1.0651 | [10 empty] | 0
|  |  | Total | 3987.0155 |  |  |  | 1874.94 |  |  |  | 1874.94 |  |  | 596.7879
[6 empty] | Overall Physical achievement in % |  |  |  |  | 49.7323 |  |  |  | 1200 | 100
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY /2026
NAME OF ROAD : Const of Galvanised Steel Concrete Composit Bridge over Borapansury River on Chawngte to Borapansury road
Name of Division : Tlabung Division
Source of Funding : NABARD
Name of Contractor :Urban Infra Projects Private Limited.
Agreement Amount : Rs. 635.69Lakh
Sl. No | Name of Work/Project | Unit | Approved Cost (in Lakh) |  | Date of Commencement | Target Dt. Of Completion | Cummulative progress at the end of last mont |  | Achievement of works during the month |  | Overall Cummulative achievement |  | Remarks | Mode of Contract
|  |  | Qnty. | Cost |  |  | Phy | Fin | Phy. | Fin | Phy. | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
| I FOUNDATION |  |  |  | Date.31.May.2024 | Dt.31.may.2026 | [7 empty] | Item Rate
1 | Earthwork in excavation of foundation in Ordinary rock | m3 | 532.5 | 4.264 | [10 empty] | 0
2 | Earthwork in excavation of foundation in Hard rock | m3 | 220 | 2.754 | [10 empty] | 0
3 | Plain /reinforced cement concrete in open foundation | m3 | 41.23 | 5.154
4 | Footing H.RCC Grade M15 | m3 | 215.67 | 32.354
5 | Supplying, fitting and placing un-coated HYSD bar reinforcement in foundation | MT | 19.01 | 25.664
II SUB-STRUCTURE
6 | Plain /reinforced cement concrete in sub-structure | m3 | 188.75 | 33.044
7 | Furnishing and placing reinforcement /prestressed cement concrete in super-structure | m3 | 88.93 | 17.794
8 | Supplying, fitting and placing un-coated HYSD bar reinforcement in sub-structure | MT | 66.67 | 90
9 | Providing weep hole in brick masonry/plain/ reinforced concrete abutment, wing wall/ return wall with 100mm dia | each | 250 | 4.54
10 | Back filling behind abutment, wing wall and return wall | m3 | 532.98 | 15.99
11 | Providing and laying of filter media with granular material/ stone crushed aggregates | m3 | 144 | 5.04
12 | Supplying, fitting and fixing in position true to line and level POT cum PTFE bearing conforming | No | 12 | 15.6
| III SUPER-STRUCTURE |  |  |  | Date.31.May.2024 | Dt.31.may.2026
13 | Supplying, fabricating and erecting the fabricated galvanised steel built-up | Ton | 81.13 | 202.83
14 | Furnishing and placing reinforcement /prestressed cement concrete in super-structure | m3 | 80.25 | 19.26
15 | PCC M15 Grade leveling course below approach slab | m3 | 11.18 | 1.397
16 | Reinforced Cement concrete approach slab including reinforcement and formwork | m3 | 22.36 | 4.025
17 | Mastic asphalt (Providing and laying 12mm thick mastic asphalt wearing course on top of deck slab excluding prome coat) | sqm | 180 | 2.16
18 | Strip seal expension joint | rm | 21.3 | 5.112
19 | Supplying, fitting and placing un-coated HYSD bar reinforcement in super-structure | ton | 20.22 | 27.297
20 | Reinforced Cement concrete crash barrier | m | 134 | 16.08
21 | Drain Spouts | no | 12 | 0.216
IV-APPROACH ROAD
22 | Excavation in soil by mechanical means | m3 | 1820 | 3.644
23 | Embakement construction with material obtained from borrow pits | m3 | 2296 | 8.274
24 | PCC 1:3:6 in foundation | m3 | 2.1 | 0.254
25 | Stone masonry work in cement mortar for substructure | m3 | 144.1 | 12.974
26 | Plain /reinforced cement concrete in sub-structure | m3 | 1.77 | 0.25
27 | GSB (Plant Mix Method) | m3 | 116.59 | 4.66
28 | Dry Lean cement concrete sub-base | m3 | 78.93 | 7.89
29 | Cement concrete pavement | m3 | 197.31 | 39.46
30 | Providing and laying of filter media with granular material/ stone crushed aggregates | m3 | 31.8 | 1.27
V. ROAD SIGNAGES, MAKINGS etc.
31 | Reto-reflectorised Traffic signs | each | 2 | 0.362
32 | 60 cm equilateral triangle | each | 2 | 0.2
33 | 60 cm circular | each | 2 | 0.2
34 | 60 cm x 4 cm rectangular | each | 2 | 0.2
35 | Road marking with hot applied thermoplastic compound with reflectorising glass beads on bituminous surface | m3 | 35.875 | 0.864 | Date.31.May.2024 | Dt.31.may.2026
36 | Type-A, "W" : Metal beam crash barrier | m | 143.5 | 12.054
VI RIVER BANK PROTECTION
37 | Boulder apron laid in wire crates | m3 | 160 | 10.4
38 | Gabian structure for erosion control, river training works and protection works | m3 | 24 | 2.16
|  | Total = |  | 635.691
Overall Physical achievement in % | [10 empty] | 1
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY / 2026
NAME OF ROAD : Restoration of Damage Due to Cyclone Remal under Tlabung Division
Name of Division : Tlabung Division
Source of Funding : SASCI-2025-26
Contractor : Laltlanmawia, Hmar Veng , Kolasib
Sanction Amount : Rs 830.00 Lakh
No.E/TB-1/MPR/SASCI/EE(T)/PWD/ 38 | Name of Work/Project | Unit | Approved Cost (in Lakh) |  | Date of Commencement | Target Dt. Of Completion | Cummulative progress at the end of last mont |  | Achievement of works during the month |  | Overall Cummulative achievement |  | Remarks | Mode of Contract
|  |  | Qnty. | Cost |  |  | Phy. | Fin | Phy. | Fin | Phy | Fin
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | PCC Pavement | Km | 2.024 | 597.29 | 16.06.2025 | 16.01.2026 | 2.024 | 671.75 |  | 128.25 | 2.024 | 800 | Completed Phy works and Fin works | Item Rates
2 | Retaining Wall | Rm | 211.93 | 114.97 |  |  | 211.93 |  |  |  | 211.93
3 | Submission of Monthly Progress Report of SASCI for the month of July/2026. | Rm | 51 | 57.03 |  |  | 51 |  |  |  | 51
4 | RCC Hume Pipe Culvert | Nos | 2 | 17.65 |  |  | 2 |  |  |  | 2
5 | RCC Slab Culvert | Nos | 2 | 13.06 |  |  | 2 |  |  |  | 2
| Total= |  |  | 800 |  |  |  | 671.75 |  | 128.25 |  | 800
[7 empty] | Overall Physical achievement in % |  |  |  | 100
Executive Engineer,PWD
Tlabung Division, Tlabung

## Thenzawl
MONTHLY PROGRESS REPORT
FOR THE MONTH OF JULY, 2026 under THENZAWL ROAD DIVISION
Sl. No. | Name of Schemes | Quantity | Unit | Approved Cost (Rs in Lakh) | Date of Commencement | Target Date of Comple-tion | Cumulative Progress at the end of last month (June '26) |  | Achievement of works during the month (July '26) |  | Overall Cumulative achievement |  | Remarks | Mode
| Name of Works / Project | [5 empty] | Phy | Fin | Phy | Fin | Phy | Fin
1 | 2 |  | 3 | 4 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
A | NESIDS
I | Construction of Thenzawl - Sialsuk via Sathlur and Lau River (Length - 16.74 km)
1 | SH:- Jungle clearance | 16.736 | Km | 4546 | 23.10.25 | 24.4.27 | 94.1% | 0 | 0% | 0 | 94.1% | 0 | On Going | EPC
2 | Earthwork | 16.736 | 3: Km; 8: 94.1%; 10: 0%; 12: 94.1%; 14: On Going
3 | Pavement
3.1 | a) SH:- CTSB (16595 x 3.75x0.110) | 9937.4 | 3: cum; 8: 0%; 10: 0%; 12: 0%; 14: Not yet started
3.2 | SH:- CTB (16595x3.75x0.110) | 6307.125 | 3: cum; 8: 0%; 10: 0%; 12: 0%; 14: Not yet started
3.3 | SH:- Hard Shoulder (16595x0.2x0.110) | 2074.375 | 3: cum; 8: 0%; 10: 0%; 12: 0%; 14: Not yet started
3.4 | SH:- Geotextile fabric (16595x3.75) | 63071.25 | 3: sqm; 8: 0%; 10: 0%; 12: 0%; 14: Not yet started
3.5 | SH:- Bitumen (BM) (16595x3.75x0.05) | 3153.56 | 3: cum; 8: 0%; 10: 0%; 12: 0%; 14: Not yet started
36 | SH:- Prime Coat (16595x3.75) | 63071.25 | 3: sqm; 8: 0%; 10: 0%; 12: 0%; 14: Not yet started
3.7 | SH:- Bitumen (BC) (16595x3.75x0.03) | 18952.1375 | 3: cum; 8: 0%; 10: 0%; 12: 0%; 14: Not yet started
3.8 | SH:- Tack Coat (16595x3.75) | 63071.25 | 3: sqm; 8: 0%; 10: 0%; 12: 0%; 14: Not yet started
4 | Side Drain
| Unlined Drain | 7986 | 3: m; 8: 15%; 10: 0%; 12: 15%; 14: On Going
4.1 | Concrete Lined Drain (Trapezoidal) | 8750 | 3: Rm; 8: 0%; 10: 0%; 12: 0%; 14: Not yet started
5 | Protection Work. (Retaining Wall & Breast Wall)
5.1 | Type-I (RW) Ht. 2m | 170 | 3: Rm; 8: 62.94%; 10: 0%; 12: 62.94%; 14: On Going
5.2 | Type-II(RW) Ht. 3m | 155 | 3: Rm; 8: 53.7%; 10: 0%; 12: 53.7%; 14: On Going
5.3 | Type-III (RW) Ht. 4m | 120 | 3: Rm; 8: 16.67%; 10: 0%; 12: 16.67%; 14: On Going
5.4 | Type-IV (RW) Ht. 5m | 115 | 3: Rm; 8: 0%; 10: 0%; 12: 0%; 14: On Going
6 | Cross Drainage works {Box Culvert & Slab Culvert} | [13 empty] | 2300
6.1 | Type-I (1.50m X 1.50m) | 43 | 3: Nos; 8: 46.52%; 10: 0%; 12: 46.52%; 14: On Going | 430
6.2 | Type-II (2m X 2m) | 15 | 3: Nos; 8: 47%; 10: 0%; 12: 47%; 14: On Going | 18.6957
6.3 | Type-II (3m X 3m) | 3 | 3: Nos; 8: 0%; 10: 0%; 12: 0%; 14: Not yet started
6.4 | Type-II (4m X 4m) | 2 | 3: Nos; 8: 0%; 10: 0%; 12: 0%; 14: Not yet started
PROJECT FACILITIES
| TRAFFIC SIGN & ROAD |  | 8: 0%; 10: 0%; 12: 0%; 14: Not yet started
7 | Road signs, Km stones, Informatory | 16.736 | 3: Km; 8: 0%; 10: 0%; 12: 0%; 14: Not yet started
8 | Build up Girder Bridge |  | 8: 0%; 10: 0%; 12: 0%; 14: Not yet started
8.1 | BUG Bridge (Span-30m) | 30 | 3: Rm; 8: 0%; 10: 0%; 12: 0%; 14: Not yet started
Overall = |  |  | 8: 35.05%; 10: 0%; 12: 35.05%
II | Construction of Khankawn to Rongura Hmun in Serchhip District (L=11.60 Kms)
1 | SH:- Jungle clearance | 11.6 | Km | 3259 | 23.10.25 | 24.4.27 | 100% | 0 | 0% | 0 | 100% | 0 | Completed | EPC
2 | Earthwork | 11.508 | 3: Km; 8: 100%; 10: 0%; 12: 100%; 14: Completed
3 | Pavement
3.1 | a) SH:- CTSB (110mm) - 5.40 m | 11.508 | 3: Km; 8: 0%; 10: 0%; 12: 0%; 14: Not yet started
3.2 | SH:- CTB (100mm) | 11.508 | 3: Km; 8: 0%; 10: 0%; 12: 0%; 14: Not yet started
3.4 | SH:- Bitumen (BC) (30mm) | 11.508 | 3: Km; 8: 0%; 10: 0%; 12: 0%; 14: Not yet started
3.5 | SH:- Bitumen (Tack Coat) | 11.508 | 3: Km; 8: 0%; 10: 0%; 12: 0%; 14: Not yet started
3.6 | Hard shoulders and Sub grade | 11.508 | 3: Km; 8: 0%; 10: 0%; 12: 0%; 14: Not yet started
4 | Side Drain
| Unlined Drain | 4100 | 3: m; 8: 100%; 10: 0%; 12: 100%; 14: Completed
4.1 | Concrete Lined Drain (Trapezoidal) | 7500 | 3: m; 8: 0%; 10: 0%; 12: 0%; 14: Not yet started
5 | Protection Work. (Retaining Wall & Breast Wall)
5.1 | Type-I (RW) Ht. 2m | 80 | 3: Rm; 8: 55%; 10: 0%; 12: 55%; 14: On Going
5.2 | Type-II (RW) Ht. 3m | 130 | 3: Rm; 8: 70.38%; 10: 0%; 12: 70.38%; 14: On Going
5.3 | Type-III (RW) Ht. 4m | 120 | 3: Rm; 8: 0%; 10: 0%; 12: 0%; 14: Not yet started
5.4 | Type-III (RW) Ht. 5m | 70 | 3: Rm; 8: 0%; 10: 0%; 12: 0%; 14: Not yet started
6 | Cross Drainage works {Box Culvert & Slab Culvert}
6.1 | Type-I (1.50m X 1.50m) | 32 | 3: Nos.; 8: 40.7%; 10: 0%; 12: 40.7%; 14: On Going
6.2 | Type-II (2m X 2m) | 17 | 3: Nos.; 8: 29.38%; 10: 0%; 12: 29.38%; 14: On Going
6.3 | Type-II (3m X 3m) | 2 | 3: Nos.; 8: 0%; 10: 0%; 12: 0%; 14: Not yet started |  | Approved cost
6.5 | Type-II (4m X 4m) | 1 | 3: no.; 8: 0%; 10: 0%; 12: 0%; 14: Not yet started |  | mode of contract
| PROJECT FACILITIES | [14 empty] | approved year
| TRAFFIC SIGN & ROAD |  | 8: 0%; 10: 0%; 12: 0%; 14: Not yet started
7 | Road signs, Km stones, Informatory |  | 8: 0%; 10: 0%; 12: 0%; 14: Not yet started
7.1 | PCC parapet Wall | 425 | 3: Nos.; 8: 0%; 10: 0%; 12: 0%; 14: Not yet started
Overall = |  |  | 8: 35.1%; 10: 0%; 12: 35.1%
B | PMGSY
I | Construction and Maintenance of Sumasumi to Tuikawi Road (0.00-19.22 Kmp)
1 | Formation Cutting | 19.22 | Km |  | 14.06.2019 | 31.03.2025 | 97.19% | 2132.42 | 0% | 0 | 97.19% | 2132.42 | On Going | Open tender
2 | Unline Side Drain | 19.22 | 3: Km; 8: 62.42%; 10: 0%; 12: 62.42%; 14: On Going
3 | Lind Side Drain | 4000 | 3: Rm; 8: 37.5%; 10: 0%; 12: 37.5%; 14: On Going
4 | Cross Drainage Work
| a) Slab Culvert | 15 | 3: Nos.; 8: 100%; 10: 0%; 12: 100%; 14: Completed
| b) Hume Pipe Culvert | 19 | 3: Nos.; 8: 63.27%; 10: 0%; 12: 63.27%; 14: On Going
5 | Protection Work
| a) Retaining Wall | 448 | 3: Rm; 8: 70.98%; 10: 0%; 12: 70.98%; 14: On Going
| b) Gabion Wall | 150 | 3: Rm; 8: 0%; 10: 0%; 12: 0%; 14: Not yet started
6 | Pavement Works
| a) Preparation of Sub-Grade | 19.22 | 3: Km; 8: 69.48%; 10: 0%; 12: 69.48%; 14: On Going
| b) GSB | 19.22 | 3: Km; 8: 69.48%; 10: 0%; 12: 69.48%; 14: On Going
| c) PCC Pavement Works | 19.22 | 3: Km; 8: 67.12%; 10: 0%; 12: 67.12%; 14: On Going
| d) Const. of Road Shoulder | 19.22 | 3: Km; 8: 67.12%; 10: 0%; 12: 67.12%; 14: On Going
| e) Repair of damages | 19.22 | 3: Km; 8: 69.48%; 10: 0%; 12: 69.48%; 14: On Going
7 | Traffic Sign and Road Safety Measures
| a) KM Stone | 97 | 3: Nos.; 8: 100%; 10: 0%; 12: 100%; 14: Completed
| b) 60cm Equilateral Triangle Traffic | 117 | 3: Nos.; 8: 100%; 10: 0%; 12: 100%; 14: Completed
| c) Traffic Signs | 4.35 | 3: m2; 8: 100%; 10: 0%; 12: 100%; 14: Completed
| d) PMGSY Logo and Informatory Board | 12 | 3: Nos.; 8: 100%; 10: 0%; 12: 100%; 14: Completed
Overall = |  |  | 8: 75.92%; 12: 75.92%
II | Construction and Maintenance of Bunghmun to Sachan Road (0.00-10.42 Kmp)
1 | Formation Cutting | 10.42 | Km |  | 13.12.2018 | 31.03.2025 | 100% | 1255.62 | 0% | 0% | 100% | 1255.62 | Completed | Open tender
2 | Pavement Works
| a) Sub-grade | 10.42 | 3: Km; 8: 100%; 10: 0%; 12: 100%; 14: Completed
| b) Repair of damages | 10.42 | 3: Km; 8: 100%; 10: 0%; 12: 100%; 14: Completed
| c) GSB | 10.42 | 3: Km; 8: 100%; 10: 0%; 12: 100%; 14: Completed
| d) Panel Concrete Pavement | 10.42 | 3: Km; 8: 100%; 10: 0%; 12: 100%; 14: Completed
3 | Shoulder | 10.42 | 3: Km; 8: 100%; 10: 0%; 12: 100%; 14: Completed
4 | Side drainage works
| a) Unline Side Drain | 10.42 | 3: Km; 8: 100%; 10: 0%; 12: 100%; 14: Completed
| b) Line side drain | 3800 | 3: Rm; 8: 29.38%; 10: 0%; 12: 29.38%; 14: On Going
5 | Protection works | bar: 10
| a) Retaining wall | 420 | 3: Rm; 8: 90.86%; 10: 0%; 12: 90.86%; 14: On Going
| b) Gabion wall | 180 | 3: Rm; 8: 0%; 10: 0%; 12: 0%; 14: Not yet started
6 | Cross drainage works
| a) Minor bridge | 2 | 3: Nos.; 8: 100%; 10: 0%; 12: 100%; 14: Completed
| b) Hume pipe culvert | 31 | 3: Nos.; 8: 100%; 10: 0%; 12: 100%; 14: Completed
7 | Parapets | 186 | 3: Nos.; 8: 53.23%; 10: 0%; 12: 53.23%; 14: On Going
8 | Road signs, logo, etc. with fixing, KM post, 200m stone | 129 | 3: Nos.; 8: 100%; 10: 0%; 12: 100%; 14: Completed
| Overall = |  | 8: 94.61%; 10: 0%; 12: 94.61%
III | Construction and Maintenance of Sachan to Sumasumi Road (0.00 - 24.09 Kmp)
1 | Formation Cutting | 24.09 | Km |  | 10.6.2019 | 31.3.2025 | 100% | 362901% | 0% | 0% | 100% | 3629.01 | Completed | Open tender
2 | Unline Side Drain | 24.09 | 3: Km; 8: 100%; 10: 0%; 12: 100%; 14: Completed
3 | line Side Drain | 4950 | 3: Rm; 8: 0%; 10: 0%; 12: 0%; 14: Not yet started
4 | Cross Drainage Work
| a) Minor Bridge | 1 | 3: Nos; 8: 100%; 10: 0%; 12: 100%; 14: Completed
| b) Slab Culvert | 76 | 3: Nos; 8: 100%; 10: 0%; 12: 100%; 14: Completed
5 | Protection Works
| a) Retaining Wall | 850 | 3: Rm; 8: 71.76%; 10: 0%; 12: 71.76%; 14: On Going
| b)Gabion Wall | 195 | 3: Rm; 8: 0%; 10: 0%; 12: 0%; 14: Not yet started
6 | Pavement Works
| a) Preparation of Sub-Grade | 24.09 | 3: Km; 8: 100%; 10: 0%; 12: 100%; 14: Completed
| b) Repair of Damages | 24.09 | 3: Km; 8: 100%; 10: 0%; 12: 100%; 14: Completed
| c) GSB | 24.09 | 3: Km; 8: 100%; 10: 0%; 12: 100%; 14: Completed
| d) WBM Grading 2 | 24.09 | 3: Km; 8: 100%; 10: 0%; 12: 100%; 14: Completed
| e) WBM Grading 3 | 24.09 | 3: Km; 8: 100%; 10: 0%; 12: 100%; 14: Completed
| f) Prime Coat | 24.09 | 3: Km; 8: 20.76%; 10: 0%; 12: 20.76%; 14: On Going
| g) Tack Coat | 24.09 | 3: Km; 8: 20.76%; 10: 0%; 12: 20.76%; 14: On Going
| h) 20mm thick OPC | 24.09 | 3: Km; 8: 20.76%; 10: 0%; 12: 20.76%; 14: On Going
| i) Seal Coat | 24.09 | 3: Km; 8: 20.76%; 10: 0%; 12: 20.76%; 14: On Going
| Embankment | 18673.269 | 3: m3; 8: 98.04%; 10: 0%; 12: 98.04%; 14: On Going
7 | Shoulder | 24.09 | 3: m3; 8: 100%; 10: 0%; 12: 100%; 14: Completed
8 | Parapets | 205 | 3: Nos; 8: 100%; 10: 0%; 12: 100%; 14: Completed
9 | Road signs with fixing | 315 | 3: Nos; 8: 100%; 10: 0%; 12: 100%; 14: Completed
| Overall = |  | 8: 86.66%; 10: 0%; 12: 86.66%
C | SASCI
I | Improvement and Upgradation of Buarpui to Bunghmun Road (0.000-17.800 kmp)
1 | Preparation of Sub grade | 14 | Km | 1000 | 27.01.2026 | 27.01.2027 | 100% | 0 | 0% | 0 | 100% | 0 | On Going | Restricted tender
2 | WBM Gr-I (Layer-I) | 14 | 3: Km; 8: 100%; 10: 0%; 12: 100%; 14: On Going
3 | WBM Gr-I (Layer-2) | 17.15 | 3: Km; 8: 0%; 10: 0%; 12: 0%; 14: Not yet started
4 | OPC/Seal Coat | 17.15 | 3: Km; 8: 0%; 10: 0%; 12: 0%; 14: Not yet started
5 | Earthen Shoulder | 17.15 | 3: Km; 8: 0%; 10: 0%; 12: 0%; 14: Not yet started
6 | Unlined Side Drain | 15000 | 3: Rm; 8: 67%; 10: 0%; 12: 67%; 14: On Going
Overall = |  |  | 8: 29.21%; 10: 0%; 12: 29.21%
D | 5054 (R & B) (Untied Fund)
Restoration of rain cuts and reconstruction of the WBM Layer at essential places on Buarpui to Bunghmun Road
1 | Subgrade | 3000 | m3 | 90 | 13.04.2026 | 13.08.2026 | 100% | 0 | 0% | 0 | 100% | 0 | Work completed | Open tender
2 | Restoration of rain cuts | 1500 | 3: m3; 8: 100%; 10: 0%; 12: 100%; 14: Work completed
3 | Side drain clearance | 5000 | 3: Rm; 8: 100%; 10: 0%; 12: 100%; 14: Work completed
4 | Filling pot holes with WBM Materials | 679.81 | 3: m3; 8: 100%; 10: 0%; 12: 100%; 14: Work completed
5 | WBM Grading-II | 407.98 | 3: m3; 8: 100%; 10: 0%; 12: 100%; 14: Work completed
[6 empty] | Overall = | 100% |  | 0% |  | 100%
ANNEXURE - F
MONTHLY PROGRESS REPORT FOR THE MONTH OF July 2026
(A. FINANCIAL REPORT)
Sl. No. | Name of the Project, Location & State | Name of Implementing Agency/ Dept | 3: Approved Cost by MDoNER/NESIDS; 6: Fund released by MDoNER/NESIDS; 8: Expenditure made; 11: Unspent balance out of fund released (Rs in lakhs); 13: Status of submission of U/Cs; 14: Remarks
|  |  | Original Cost (Rs in lakhs) | Revised Cost (Rs in lakhs) | During 2025-26 | Since inception (Cumulative) | During the month vis-a-vis target |  | Since inception (Cumulative) (Rs in lakhs)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |  | 9 | 10 |  | 11 | 12
1 | Construction of Khankawn to Rongura Hmun in Serchhip District (L=11.60 Kms) | Mizoram, PWD | 3259 | 3198 | 553.5 | 553.5 | 268.95 |  | 553.5 | nil |  | submitted
ANNEXURE - F
MONTHLY PROGRESS REPORT FOR THE MONTH OF July 2026
(B. PHYSICAL REPORT)
Sl. No. | Name of the Project, Location & State | Name of Implementing Agency/Dept | 3: Approved Cost by MDoNER/NESIDS; 6: Date of actual commencement of work/ scheme; 7: Target date of completion of work/ scheme; 8: Scope of work/ scheme in physical terms (eg. Kms, etc); 12: Physical achievement; 14: Remarks
|  |  | Cost (Rs in lakhs) | Date | [6 empty] | Percentage (during the month) | Percentage (Overall)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |  |  |  | 9 | 10 | 11
1 | Construction of Khankawn to Rongura Hmun in Serchhip District (L=11.60 Kms) | Mizoram, PWD | 3: 3259; 4: 24.03.2025; 6: 23.10.2025; 7: 24.04.2027; 8: Overall Progress
[7 empty] | 1 | SH:- Jungle clearance |  | 11.600 Km | 0% | 100% | Completed
[7 empty] | 2 | Earthwork |  | 11.508 Km | 0% | 100% | Completed
[7 empty] | 3 | Pavement
[7 empty] | 3.1 | CTSB (110mm) - 5.40 m |  | 11.508 Km | 0% | 0%
[7 empty] | 3.2 | CTB (100mm) |  | 11.508 Km | 0% | 0%
[7 empty] | 3.4 | Bitumen (BC) (30mm) |  | 11.508 Km | 0% | 0%
[7 empty] | 3.5 | Bitumen (Tack Coat) |  | 11.508 Km | 0% | 0%
[7 empty] | 3.6 | Hard shoulders and Sub grade |  | 11.508 Km | 0% | 0%
[7 empty] | 4 | Side Drain
[7 empty] | 4.1 | Unlined Drain |  | 4100.00 m | 0% | 100% | Completed
[7 empty] | 4.2 | Concrete Lined Drain (Trapezoidal) |  | 7500.00 m | 0% | 0%
[7 empty] | 5 | Protection Work. (Retaining Wall & Breast Wall)
[7 empty] | 5.1 | Type-I (RW) Ht. 2m |  | 80.00 Rm | 0% | 55%
[7 empty] | 5.2 | Type-II (RW) Ht. 3m |  | 130.00 Rm | 0% | 70.38%
[7 empty] | 5.3 | Type-III (RW) Ht. 4m |  | 120.00 Rm | 0% | 0%
[7 empty] | 5.4 | Type-IV (RW) Ht. 5m |  | 70.00 Rm | 0% | 0%
[7 empty] | 6 | Cross Drainage works {Box Culvert & Slab Culvert}
[7 empty] | 6.1 | Type-I (1.50m X 1.50m) |  | 32 Nos. | 0% | 40.7%
[7 empty] | 6.2 | Type-II (2m X 2m) |  | 17 Nos. | 5.88% | 29.38%
[7 empty] | 6.3 | Type-III (3m X 3m) |  | 2 Nos. | 0% | 0%
[7 empty] | 6.5 | Type-IV (4m X 4m) |  | 1 No. | 0% | 0%
PROJECT FACILITIES
[8 empty] | TRAFFIC SIGN & ROAD |  |  | 0% | 0%
[7 empty] | 7 | Road signs, Km stones, Informatory
[7 empty] | 7.1 | PCC parapet Wall |  | 425 Nos. | 0% | 0%
ANNEXURE - F
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY, 2026
(A. FINANCIAL REPORT)
Sl. No. | Name of the Project, Location & State | Name of Implementing Agency/ Dept | 3: Approved Cost by MDoNER/NESIDS; 6: Fund released by MDoNER/NESIDS; 8: Expenditure made; 11: Unspent balance out of fund released (Rs in lakhs); 13: Status of submission of U/Cs; 14: Remarks
|  |  | Original Cost (Rs in lakhs) | Revised Cost (Rs in lakhs) | During 2025-26 | Since inception (Cumulative) | During the month vis-a-vis target |  | Since inception (Cumulative) (Rs in lakhs)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |  | 9 | 10 |  | 11 | 12
1 | Construction of Thenzawl - Sialsuk via Sathlur and Lau River (Length - 16.74 km) | Mizoram, PWD | 4546 | 4503 | 818 | 818 | 625.59 |  | 818 | 0 |  | submitted
ANNEXURE - F
MONTHLY PROGRESS REPORT FOR THE MONTH OF JULY, 2026
(B. PHYSICAL REPORT)
Sl. No. | Name of the Project, Location & State | Name of Implementing Agency/Dept | 3: Approved Cost by MDoNER/NESIDS; 6: Date of actual commencement of work/ scheme; 7: Target date of completion of work/ scheme; 8: Scope of work/ scheme in physical terms (eg. Kms, etc); 12: Physical achievement; 14: Remarks
|  |  | Cost (Rs in lakhs) | Date | [6 empty] | Percentage (during the month) | Percentage (Overall)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |  |  |  | 9 | 10 | 11
1 | Construction of Thenzawl - Sialsuk via Sathlur and Lau River (Length - 16.74 km) | Mizoram, PWD | 3: 4546; 4: 17.02.2025; 6: 23.10.2025; 7: 24.04.2027; 8: Overall Progress
[7 empty] | 1 | SH:- Jungle clearance |  | 16.736 Km | 0% | 94.1%
[7 empty] | 2 | Earthwork |  | 16.736 Km | 0% | 94.1%
[7 empty] | 3 | Pavement
[7 empty] | 3.1 | CTSB (16595 x 3.75x0.110) |  | 9937.400 cum | 0% | 0%
[7 empty] | 3.2 | CTB (16595x3.75x0.110) |  | 6307.125 cum | 0% | 0%
[7 empty] | 3.3 | Hard Shoulder (16595x0.2x0.110) |  | 2074.375 cum | 0% | 0%
[7 empty] | 3.4 | Geotextile fabric (16595x3.75) |  | 63071.25 sqm | 0% | 0%
[7 empty] | 3.5 | Bitumen (BM) (16595x3.75x0.05) |  | 3153.56 cum | 0% | 0%
[7 empty] | 3.6 | Prime Coat (16595x3.75) |  | 63071.25 sqm | 0% | 0%
[7 empty] | 3.7 | Bitumen (BC) (16595x3.75x0.03) |  | 18952.1375 cum | 0% | 0%
[7 empty] | 3.8 | Tack Coat (16595x3.75) |  | 63071.25 sqm | 0% | 0%
[7 empty] | 4 | Side Drain
[7 empty] | 4.1 | Unlined Drain |  | 7986.00 m | 0% | 15%
[7 empty] | 4.2 | Concrete Lined Drain (Trapezoidal) |  | 8750.00 Rm | 0% | 0%
[7 empty] | 5 | Protection Work. (Retaining Wall & Breast Wall)
[7 empty] | 5.1 | Type-I (RW) Ht. 2m |  | 170.00 Rm | 0% | 62.94%
[7 empty] | 5.2 | Type-II(RW) Ht. 3m |  | 155.00 Rm | 0% | 53.7%
[7 empty] | 5.3 | Type-III (RW) Ht. 4m |  | 120.00 Rm | 0% | 16.67%
[7 empty] | 5.4 | Type-IV (RW) Ht. 5m |  | 115.00 Rm
[7 empty] | 6 | Cross Drainage works {Box Culvert & Slab Culvert}
[7 empty] | 6.1 | Type-I (1.50m X 1.50m) |  | 43 Nos. | 3.48% | 50%
[7 empty] | 6.2 | Type-II (2m X 2m) |  | 15 Nos. | 0% | 47%
[7 empty] | 6.3 | Type-III (3m X 3m) |  | 3 Nos. | 0% | 33.33%
[7 empty] | 6.5 | Type-IV (4m X 4m) |  | 2 Nos. | 0% | 0%
PROJECT FACILITIES
[8 empty] | TRAFFIC SIGN & ROAD |  | 16.736 Km | 0% | 0%
[7 empty] | 7 | Road signs, Km stones, Informatory
[7 empty] | 8 | Build up Girder Bridge
[7 empty] | 8.1 | BUG Bridge (Span-30m) |  | 30.00 Rm | 0% | 58.32%
[11 empty] | Overall Physical Progress = | 35.05%
Sr. Executive Engineer, PWD
Thenzawl Road Divsion
Thenzawl